## Slide 1
R&D Budget Review After August Close
R&D budget review after the August close, for the executive team on September 16, 2026. It covers January to August actuals and the September reforecast, explains three variance drivers and asks for two decisions.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 1

## Slide 2
What this review covers
R&D only; G&A is reviewed separately. Actuals are January to August 2026 and include accruals: $1.9 million of August expense was accrued rather than invoiced. The full-year view is the reforecast the executive team approved on September 11 against the $94.8 million budget.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 2
Notes: Remind the room that accruals for CRO and pass-through are estimates; half of August clinical expense was accrued.

## Slide 3
Year to date: $4.9 million under budget
Actual R&D expense was $59.5 million against a phased budget of $64.4 million. Most of the gap is timing in nonclinical and CMC work rather than savings; about $1.6 million is unused reserve phasing.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 3
Notes: Chart shows actual expense by month including accruals. The phased reserve is budgeted evenly by month and has no actuals.

## Slide 4
Year to date: $4.9 million under budget · USD
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 4
Chart: 
| 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08
actual_usd | 6567711.94 | 8112271.46 | 7407351.44 | 7373075.34 | 7358986.53 | 7925079.87 | 7544538.31 | 7219205.11

## Slide 5
Driver 1 – LRT-4051 work moves into 2027
LRT-4051 is forecast $1.28 million under budget for the year because GLP report milestones and part of the API campaign move into 2027: nonclinical $0.91 million under and CMC $0.41 million under. This is a timing shift; the same work is still needed for the IND.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 5

## Slide 6
Driver 2 – CANOPY-1 pass-through and change order 4
LRT-1107 is forecast at $55.05 million against $52.60 million: clinical pass-through +$1.60 million, CRO services +$0.90 million including the first months of change order 4, and consultants +$0.13 million, partly offset by CMC savings. About $1.3 million of change order 4 falls in FY2026; the rest lands in 2027 and early 2028.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 6
Notes: Pass-through is running ahead of plan as site payments catch up with enrollment.

## Slide 7
Driver 3 – discovery research services
Discovery is forecast $0.61 million over budget, mainly research services (+$0.62 million) from the two-FTE chemistry increase and external bioanalysis overflow. LRT-2240 is $0.49 million under its $4.10 million budget while Phase 2b readiness is paused.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 7

## Slide 8
Full year: $95.07 million, $0.27 million over
After the three drivers and smaller movements, the reforecast is $0.27 million over the approved budget. The net figure already includes the reserve release.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 8
Notes: Reserve: $2.4 million approved; $1.25 million released in the reforecast to cover the LRT-1107 and discovery overspends; $1.15 million remains unallocated for Q4.

## Slide 9
Decision 1 – endorse change order 4 for the board
Change order 4 adds one country with six sites and extends CRO services by about three months: $3.72 million in services plus an estimated $2.38 million in pass-through. Because the combined value including estimated pass-through is above $5 million, it needs board approval on October 8. We ask the executive team to endorse it for the board paper.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 9

## Slide 10
Decision 2 – interim bioanalysis funding to October 2
Research leadership will decide on bioanalytical capacity on October 2. Until then we propose continuing external overflow at about $30,000 a month from within the discovery forecast. A second triple-quadrupole system would cost about $640,000 in capital and is not in the FY2026 plan.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 10

## Slide 11
Appendix – definitions and reforecast totals
Variance is forecast minus budget; positive means over budget. Personnel cost is allocated from FTE estimates and is not a tracked actual by program. Totals by column for the 56 budget cells follow.
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 11

## Slide 12
Appendix – definitions and reforecast totals · extract summary
Measure: fy_budget_usd
Unit: USD
Total: 94800000.0
Mean: 1692857.1429
Records: 56
Period: 2026-01-01 to 2026-09-11
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 12

## Slide 13
Appendix – definitions and reforecast totals · extract summary
Measure: ytd_actual_usd
Unit: USD
Total: 59508220.0
Mean: 1062646.7857
Records: 56
Period: 2026-01-01 to 2026-09-11
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 13

## Slide 14
Appendix – definitions and reforecast totals · extract summary
Measure: h2_reforecast_usd
Unit: USD
Total: 35561780.0
Mean: 635031.7857
Records: 56
Period: 2026-01-01 to 2026-09-11
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 14

## Slide 15
Appendix – definitions and reforecast totals · extract summary
Measure: fy_forecast_usd
Unit: USD
Total: 95070000.0
Mean: 1697678.5714
Records: 56
Period: 2026-01-01 to 2026-09-11
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 15

## Slide 16
Appendix – definitions and reforecast totals · extract summary
Measure: variance_to_budget_usd
Unit: USD
Total: 270000.0
Mean: 4821.4286
Records: 56
Period: 2026-01-01 to 2026-09-11
Loblolly Ridge Therapeutics | Finance (FP&A) | 2026-09-16 | 16