## Read me
LRT-4051 IND-Enabling Workplan
Loblolly Ridge Therapeutics
Effective date | 2026-09-04
Purpose | Task-level IND-enabling schedule (nonclinical, DMPK, CMC, analytical, regulatory writing) with vendors, forecasts and float.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Task-level schedule for the LRT-4051 IND-enabling program: nonclinical safety, DMPK, CMC drug substance and drug product, analytical, regulatory writing and clinical planning. Status as of August 31, 2026, issued September 4.
What is in the schedule | 44 tasks with workstream, vendor, planned start and finish, forecast finish, actual finish, status, critical-path flag, float and predecessor. 13 are complete, 10 in progress and 21 not started; 18 are on the critical path to the IND.
Reading the dates | Planned dates are the FY2026 plan. Forecast finish is blank for completed tasks, and actual finish is blank for open ones. Predecessor gives one driving predecessor only; the scheduling tool holds the full logic.
Critical path and float | Critical path is yes for tasks with no float against the IND date. Float days are calendar days a task can slip before it moves the IND. The Summary total of float days has no meaning; use the flag and the float of individual tasks.
Current forecast | IND forecast June 4, 2027 against an April 30, 2027 baseline, driven by GLP toxicology final reports (forecast December 4, baseline October 30) and GMP API release (forecast December 11, baseline October 16). GLP repeat-dose in-life phases in two species finished in late July, about two weeks after plan. The pre-IND meeting request is forecast for November 20, with a meeting expected in February 2027.
Vendors | Vendor is shown by partner register ID. Partners on this program are Quarry Hill Preclinical, Ashcombe Genetic Toxicology, Alder Bioanalytical, Kestrel DMPK Services, Tessaro Fine Chemicals, Northgate Pharma Services, Brookmoor Analytical, Inkwell Medical Writing and Parkway Regulatory Publishing, plus regulatory consulting and the Phase 1 feasibility work. Internal tasks show internal.
Outside this schedule | Study protocols, study findings and the budget.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
LRT-4051 IND-enabling workplan | float_days | days | 1390 | 31.5909 | 44 | 2025-10-01 | 2026-08-31

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
LRT-4051 IND-enabling workplan | task_id | Task id |  | id
LRT-4051 IND-enabling workplan | float_days | Total float (0 on the critical path) | days | integer
LRT-4051 IND-enabling workplan | workstream | Workstream |  | category
LRT-4051 IND-enabling workplan | task | Task |  | category
LRT-4051 IND-enabling workplan | vendor_id | Vendor id |  | category
LRT-4051 IND-enabling workplan | planned_start | Planned start |  | category
LRT-4051 IND-enabling workplan | planned_finish | Planned finish |  | category
LRT-4051 IND-enabling workplan | forecast_finish | Forecast finish |  | category
LRT-4051 IND-enabling workplan | actual_finish | Actual finish |  | category
LRT-4051 IND-enabling workplan | status | Status |  | category
LRT-4051 IND-enabling workplan | critical_path | Critical path |  | category
LRT-4051 IND-enabling workplan | predecessor | Predecessor |  | category

## Data 1
task_id | float_days | workstream | task | vendor_id | planned_start | planned_finish | forecast_finish | actual_finish | status | critical_path | predecessor
T-001 | 0 | nonclinical safety | Dose-range-finding studies (rodent and non-rodent) | V-009 | 2025-11-10 | 2026-02-13 |  | 2026-02-20 | complete | yes
T-002 | 0 | nonclinical safety | GLP repeat-dose toxicology, rodent (in-life) | V-009 | 2026-03-02 | 2026-07-10 |  | 2026-07-24 | complete | yes | T-001
T-003 | 0 | nonclinical safety | GLP repeat-dose toxicology, non-rodent (in-life) | V-009 | 2026-03-02 | 2026-07-17 |  | 2026-07-31 | complete | yes | T-001
T-004 | 0 | nonclinical safety | GLP toxicology draft reports | V-009 | 2026-07-20 | 2026-09-25 | 2026-10-30 |  | in progress | yes | T-003
T-005 | 0 | nonclinical safety | GLP toxicology final reports | V-009 | 2026-09-28 | 2026-10-30 | 2026-12-04 |  | not started | yes | T-004
T-006 | 88 | nonclinical safety | Genetic toxicology battery | V-038 | 2026-01-12 | 2026-07-31 |  | 2026-07-24 | complete | no
T-007 | 63 | nonclinical safety | Safety pharmacology core battery | V-009 | 2026-04-06 | 2026-09-30 | 2026-10-09 |  | in progress | no
T-008 | 0 | nonclinical safety | Toxicology QA audit of draft reports | internal | 2026-09-28 | 2026-10-16 | 2026-11-13 |  | not started | yes | T-004
T-009 | 120 | DMPK | Non-GLP PK in two species | V-011 | 2025-10-20 | 2026-03-27 |  | 2026-03-20 | complete | no
T-010 | 102 | DMPK | In vitro metabolism and transporter panel | internal | 2025-11-03 | 2026-05-29 |  | 2026-06-12 | complete | no
T-011 | 0 | DMPK | GLP bioanalytical method validation | V-010 | 2025-11-17 | 2026-02-27 |  | 2026-03-06 | complete | yes
T-012 | 0 | DMPK | Toxicokinetic sample analysis | V-010 | 2026-03-16 | 2026-09-11 | 2026-10-02 |  | in progress | yes | T-011
T-013 | 49 | DMPK | Human dose projection memo | internal | 2026-09-14 | 2026-10-30 | 2026-11-20 |  | not started | no | T-012
T-014 | 0 | CMC drug substance | Route scouting and scale-up (non-GMP) | V-014 | 2025-11-03 | 2026-04-24 |  | 2026-05-08 | complete | yes
T-015 | 0 | CMC drug substance | GMP API campaign | V-014 | 2026-06-01 | 2026-09-25 | 2026-11-13 |  | in progress | yes | T-014
T-016 | 0 | CMC drug substance | API release testing and CoA | V-017 | 2026-09-28 | 2026-10-16 | 2026-12-11 |  | not started | yes | T-015
T-017 | 65 | CMC drug substance | Reference standard qualification | V-017 | 2026-07-06 | 2026-09-18 | 2026-10-02 |  | in progress | no | T-014
T-018 | 77 | CMC drug product | Formulation development | V-016 | 2026-03-02 | 2026-08-28 |  | 2026-08-27 | complete | no
T-019 | 0 | CMC drug product | Clinical drug product manufacture | V-016 | 2026-11-02 | 2027-02-19 | 2027-03-26 |  | not started | yes | T-016
T-020 | 5 | CMC drug product | Drug product release and labeling | V-008 | 2027-02-22 | 2027-03-19 | 2027-04-23 |  | not started | no | T-019
T-021 | 109 | analytical | Analytical method development (API) | V-017 | 2026-01-12 | 2026-05-29 |  | 2026-05-22 | complete | no
T-022 | 74 | analytical | Analytical method qualification | V-017 | 2026-06-01 | 2026-08-28 |  | 2026-09-04 | complete | no | T-021
T-023 | 39 | analytical | Stability program setup (API) | V-017 | 2026-10-19 | 2026-11-13 | 2026-12-18 |  | not started | no | T-016
T-024 | 5 | analytical | Three-month stability pull (DP) | V-017 | 2027-02-22 | 2027-05-21 | 2027-06-25 |  | not started | no | T-019
T-025 | 0 | regulatory writing | Pre-IND briefing package draft | internal | 2026-09-01 | 2026-10-09 | 2026-11-06 |  | not started | yes
T-026 | 0 | regulatory writing | Pre-IND meeting request | internal | 2026-10-12 | 2026-10-15 | 2026-11-20 |  | not started | yes | T-025
T-027 | 0 | regulatory writing | Pre-IND meeting | internal | 2027-01-11 | 2027-01-14 | 2027-02-18 |  | not started | yes | T-026
T-028 | 0 | regulatory writing | Nonclinical written and tabulated summaries | V-033 | 2026-11-02 | 2027-01-29 | 2027-03-05 |  | not started | yes | T-005
T-029 | 5 | regulatory writing | Quality (CMC) module drafting | V-031 | 2026-12-01 | 2027-03-12 | 2027-04-16 |  | not started | no | T-016
T-030 | 7 | regulatory writing | Investigator brochure v1 | V-033 | 2026-12-07 | 2027-02-26 | 2027-03-26 |  | not started | no | T-005
T-031 | 0 | regulatory writing | IND assembly and publishing | V-018 | 2027-03-15 | 2027-04-23 | 2027-05-28 |  | not started | yes | T-028
T-032 | 0 | regulatory writing | IND submission | internal | 2027-04-26 | 2027-04-30 | 2027-06-04 |  | not started | yes | T-031
T-033 | 60 | clinical planning | First-in-human synopsis | internal | 2026-07-06 | 2026-09-30 | 2026-10-16 |  | in progress | no
T-034 | 79 | clinical planning | Phase 1 outsourcing options review | internal | 2026-08-03 | 2026-08-20 |  | 2026-08-20 | complete | no
T-035 | 56 | clinical planning | Phase 1 unit feasibility assessment | V-041 | 2026-07-20 | 2026-10-30 | 2026-10-30 |  | in progress | no | T-034
T-036 | 28 | clinical planning | Phase 1 CRO request for proposal | internal | 2026-11-02 | 2026-12-18 | 2027-01-22 |  | not started | no | T-035
T-037 | 11 | clinical planning | First-in-human protocol draft | internal | 2026-11-02 | 2027-02-12 | 2027-03-12 |  | not started | no | T-033
T-038 | 30 | nonclinical safety | Nonclinical program gate review (internal) | internal | 2026-12-07 | 2026-12-11 | 2027-01-15 |  | not started | no | T-005
T-039 | 49 | DMPK | Metabolite profiling in toxicology species | V-010 | 2026-08-03 | 2026-10-30 | 2026-11-20 |  | in progress | no | T-012
T-040 | 51 | CMC drug substance | Impurity fate and purge assessment | internal | 2026-07-06 | 2026-10-30 | 2026-11-13 |  | in progress | no | T-014
T-041 | 98 | CMC drug product | Excipient compatibility report | V-016 | 2026-04-06 | 2026-06-26 |  | 2026-06-24 | complete | no
T-042 | 58 | analytical | Genotoxic impurity method | V-017 | 2026-06-15 | 2026-09-25 | 2026-10-23 |  | in progress | no | T-021
T-043 | 16 | regulatory writing | Pediatric plan assessment (initial) | internal | 2026-12-01 | 2027-02-26 | 2027-02-26 |  | not started | no
T-044 | 46 | regulatory writing | Fast-track eligibility assessment | V-031 | 2026-10-05 | 2026-11-27 | 2026-11-27 |  | not started | no