## Slide 1
External Partner Performance Review — Q3 2026 Interim
Interim Q3 2026 review of external partner performance for the outsourcing steering group (Clinical Operations, CMC, QA and Finance), September 22, 2026. Deliverables due January to August, status as of September 18. Purpose: agree follow-up actions before the Q4 oversight reviews.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 1

## Slide 2
Scope and data window
493 contracted deliverables due January to August 2026, from the deliverables tracker. Work orders and partner tiers from the register as of September 18: 97 active or pending work orders with $116.6 million of committed services.
Invoice accuracy is not reported this quarter; the Finance extract was not ready.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 2
Notes: The SOP asks for four oversight measures. We have three this time: timeliness, review outcomes and quality events.

## Slide 3
Scope and data window · extract summary
Measure: committed_usd
Unit: USD
Total: 128091000.0
Mean: 1164463.6364
Records: 110
Period: 2023-01-01 to 2026-09-18
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 3

## Slide 4
Scope and data window · extract summary
Measure: pass_through_estimate_usd
Unit: USD
Total: 38660000.0
Mean: 2416250.0
Records: 16
Period: 2023-01-01 to 2026-09-18
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 4

## Slide 5
Overall timeliness: 87% on time
487 of 493 received; 87% on or before the due date; 14 returned for revision; 6 not received. Monthly on-time share ranged from 76% in January to 91% in May and June. The chart counts on-time deliverables by due month.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 5
Notes: January is a small month (17 items) and includes two data transfers that were superseded.

## Slide 6
Overall timeliness: 87% on time · flag
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 6
Chart: 
| 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08
on_time_flag | 13 | 46 | 43 | 53 | 52 | 70 | 70 | 75

## Slide 7
Exception 1 – CDMO executed batch records
Executed batch records were on time for 9 of 16 (56%). Tessaro delivered 4 of 8 on time and Hanlin 0 of 2; Northgate delivered 5 of 6. Batch records gate QA release, so late records delay supply and the LRT-4051 GMP API.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 7
Notes: Tessaro's late records cluster around the LRT-4051 campaign; raise at the October business review.

## Slide 8
Exception 2 – final study reports
Final study reports were on time for 15 of 24 (62%). Alder Bioanalytical delivered 3 of 8 on time; its overall on-time share across 55 deliverables is 78%, the lowest among high-volume partners. Alder now also takes discovery overflow, so the load is rising.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 8

## Slide 9
Backup API supplier
Hanlin Pharmatech delivered 9 of 15 qualification-batch deliverables on time. Its audit response has not yet been accepted and the qualification batch is forecast for February 2027. QA leads the follow-up; this group tracks timeliness only.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 9

## Slide 10
Review workload
Median review time after receipt: QA 6 days, Finance 3 days, technical 4 days. QA reviews certificates of analysis, batch records, stability results and final study reports.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 10

## Slide 11
Actions and owners
Tessaro: agree batch-record turnaround target at the October business review – CMC & Clinical Supply.
Alder: capacity and report-writing plan for Q4 – DMPK & Bioanalytical with Outsourcing.
Hanlin: timeliness review at the next qualification checkpoint – CMC & Clinical Supply.
Invoice accuracy measure for Q4 reviews – Finance.
Confirm audit dates for 8 partners due by December 31 – QA.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 11

## Slide 12
Audits due by year end
8 partners have a routine audit or qualification follow-up due by December 31: Alder Bioanalytical, Aster Archive Services, Northgate Pharma Services, Brookmoor Analytical, Oakmont Statistical Programming, Harborview DSMB Services, Inkwell Medical Writing and Linden Biostatistics.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 12

## Slide 13
Data limitations
Timeliness counts a deliverable as on time or late regardless of how late; a batch record one day late counts the same as one a month late. Deliverables due after August are excluded. Quality events are reported by QA separately and are not joined to deliverables in this extract.
Loblolly Ridge Therapeutics | Outsourcing & Procurement | 2026-09-22 | 13