## Read me
Portfolio Project and Milestone Register
Loblolly Ridge Therapeutics
Effective date | 2026-09-18
Purpose | Single register of programs, studies and workstreams with the FY2026 milestone plan (baseline, forecast, actual).
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Extract of the PMO project register and FY2026 milestone plan, exported from the portfolio planning tool on September 18, 2026. The register is the system of record for program milestones; portfolio status documents quote it rather than keeping their own dates.
Sheets in this workbook | Data 1 – project register: 26 programs, studies, workstreams and internal projects with stage, ownership, lead function, status and FY2026 budget.
Sheets in this workbook | Data 2 – milestone plan: 150 milestones with gate code, baseline, forecast and actual dates, status, slip in days, owning function and predecessor.
Sheets in this workbook | Summary – record counts and column totals. The FY2026 budget total is meaningful; the slip-day total is not a portfolio measure and should be ignored.
Sheets in this workbook | Dictionary – field definitions for both data sheets.
Status definitions | Status is set by the owning function and checked by Portfolio & Program Management before each Portfolio Review Committee meeting, which is held on the third Thursday of the month.
Status definitions | complete – actual date recorded.
Status definitions | on track – forecast on or before baseline, with no named risk.
Status definitions | at risk – forecast after baseline, or a named risk to the forecast.
Status definitions | late – baseline date has passed and the milestone is not complete.
Status definitions | not started – no work begun; forecast is indicative.
Status definitions | cancelled – kept for history; none in this extract.
Baselines and slip | Open milestones were baselined in the FY2026 plan approved in December 2025. Completed milestones, and study milestones committed before that plan, keep their original plan date as baseline, which is why some baselines fall in 2024 and 2025. Slip days are forecast (or actual) minus baseline in calendar days.
Register at extract | 150 milestones: 100 complete, 20 on track, 21 at risk, 4 late and 5 not started. Excluding scheduled governance meetings, the 77 completed milestones finished a median of 3 days after baseline and 5 finished more than two weeks late.
Gate codes | Gate uses the stage-gate procedure codes: G0 target validation start, G1 lead series, G2 candidate nomination, G3 IND and first-in-human, G4 Phase 2 start (the LRT-2240 Phase 2b decision is recorded as G4) and G5 Phase 3 start. Operational milestones show none.
FY2026 budget column | Budgets are the December 2025 approved R&D budget of $94.8 million, including the $2.4 million unallocated reserve, assigned to study, workstream and internal project rows. Program rows and a few internal projects (change order 4, backup API qualification, the capacity assessment, the eQMS migration) are blank because their costs sit in other rows.
FY2026 budget column | Largest rows: CANOPY-1 $41.50 million, LRT-4051 IND-enabling $7.52 million, DP-07 $6.42 million and CANOPY-OLE $6.18 million. Personnel cost is allocated from quarterly FTE estimates, so a row budget is not a fully loaded project cost.
Not in this extract | Internal cost allocations by project; LRT-3318 milestones that the licensee manages internally (only milestones reported to the joint steering committee are listed); discovery milestones completed before January 2025.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Program and project register | fy2026_budget_usd | USD | 94800000 | 5925000 | 16 | 2012-01-01 | 2026-09-18
Milestone plan and actuals | slip_days | days | 2547 | 16.98 | 150 | 2024-02-01 | 2026-09-18

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Program and project register | project_code | Project code |  | id
Program and project register | project_name | Project name |  | category
Program and project register | project_type | Project type |  | category
Program and project register | program | Program |  | category
Program and project register | stage | Stage |  | category
Program and project register | ownership | Ownership |  | category
Program and project register | lead_function | Lead function |  | category
Program and project register | start_date | Start date |  | date
Program and project register | planned_end | Planned end |  | category
Program and project register | status | Status |  | category
Program and project register | fy2026_budget_usd | Approved FY2026 budget allocated to the project | USD | integer
Milestone plan and actuals | milestone_id | Milestone id |  | id
Milestone plan and actuals | project | Project |  | category
Milestone plan and actuals | milestone | Milestone |  | category
Milestone plan and actuals | milestone_class | Milestone class |  | category
Milestone plan and actuals | gate | Gate |  | category
Milestone plan and actuals | baseline_date | Baseline date |  | category
Milestone plan and actuals | forecast_date | Forecast date |  | category
Milestone plan and actuals | actual_date | Actual date |  | category
Milestone plan and actuals | status | Status |  | category
Milestone plan and actuals | slip_days | Actual or forecast date minus baseline date | days | integer
Milestone plan and actuals | owner_function | Owner function |  | category
Milestone plan and actuals | predecessor | Predecessor |  | category

## Data 1
project_code | project_name | project_type | program | stage | ownership | lead_function | start_date | planned_end | status | fy2026_budget_usd
PRJ-1107 | LRT-1107 development program | development program | LRT-1107 | Phase 3 | wholly owned | Clinical Development | 2019-05-01 | 2028-06 | active
PRJ-1107-C1 | CANOPY-1 pivotal study | clinical study | LRT-1107 | Phase 3 | wholly owned | Clinical Operations | 2024-06-01 | 2027-09 | active | 41500000
PRJ-1107-OLE | CANOPY-OLE extension study | clinical study | LRT-1107 | Phase 3 | wholly owned | Clinical Operations | 2026-04-20 | 2028-06 | active | 6180000
PRJ-1107-CMC | LRT-1107 clinical supply and CMC | CMC workstream | LRT-1107 | Phase 3 | wholly owned | CMC & Clinical Supply | 2024-01-15 | 2027-12 | active | 4920000
PRJ-1107-CO4 | CANOPY-1 change order 4 | internal project | LRT-1107 | Phase 3 | wholly owned | Clinical Operations | 2026-07-06 | 2026-10 | active
PRJ-2240 | LRT-2240 development program | development program | LRT-2240 | Phase 2 | in-licensed | Clinical Development | 2019-10-01 | 2027-12 | active
PRJ-2240-201 | Study 2240-201 Phase 2a | clinical study | LRT-2240 | completed | in-licensed | Clinical Operations | 2024-05-01 | 2026-07 | completed | 1620000
PRJ-2240-P2B | LRT-2240 Phase 2b readiness | clinical study | LRT-2240 | Phase 2 | in-licensed | Clinical Development | 2026-03-02 | 2027-06 | on hold | 1640000
PRJ-2240-BD | LRT-2240 partnering process | internal project | LRT-2240 | Phase 2 | in-licensed | Business Development | 2026-04-06 | 2027-03 | active | 840000
PRJ-3318 | LRT-3318 program (licensed to Castellane) | development program | LRT-3318 | licensed-out | out-licensed (licensee-run) | Business Development | 2020-06-01 | 2032-12 | active
PRJ-3318-TT | LRT-3318 technology transfer to licensee | alliance workstream | LRT-3318 | licensed-out | out-licensed (licensee-run) | CMC & Clinical Supply | 2025-12-15 | 2027-03 | active | 1850000
PRJ-3318-SUP | LRT-3318 drug substance supply to licensee | alliance workstream | LRT-3318 | licensed-out | out-licensed (licensee-run) | CMC & Clinical Supply | 2025-12-15 | 2027-06 | active | 1350000
PRJ-4051 | LRT-4051 development program | development program | LRT-4051 | IND-enabling | wholly owned | Nonclinical Safety | 2024-02-01 | 2027-12 | active
PRJ-4051-IND | LRT-4051 IND-enabling package | nonclinical workstream | LRT-4051 | IND-enabling | wholly owned | Nonclinical Safety | 2025-10-01 | 2027-06 | active | 7520000
PRJ-4051-CMC | LRT-4051 GMP API and drug product | CMC workstream | LRT-4051 | IND-enabling | wholly owned | CMC & Clinical Supply | 2025-11-03 | 2027-04 | active | 3880000
PRJ-DP07 | DP-07 cardiometabolic lead optimization | discovery project | DP-07 | lead optimization | wholly owned | Discovery Biology | 2023-01-09 | 2027-06 | active | 6420000
PRJ-DP09 | DP-09 neuropathic pain hit-to-lead | discovery project | DP-09 | hit-to-lead | wholly owned | Discovery Biology | 2024-09-02 | 2027-12 | active | 4310000
PRJ-DP12 | DP-12 renal target validation | discovery project | DP-12 | target validation | wholly owned | Discovery Biology | 2025-06-02 | 2027-03 | active | 2370000
PRJ-LAB | Research laboratory platform | internal project | Platform | n/a | wholly owned | Facilities, Lab Operations & EHS | 2014-01-06 | ongoing | active | 4960000
PRJ-LCMS | Bioanalytical LC-MS/MS capacity assessment | internal project | Platform | n/a | wholly owned | DMPK & Bioanalytical | 2026-07-13 | 2026-11 | active
PRJ-HUB2 | R&D Data Hub phase 2 (proposed) | internal project | Platform | n/a | wholly owned | Research Informatics | 2026-08-10 | 2027-06 | on hold
PRJ-BAPI | Backup API supplier qualification | CMC workstream | LRT-1107 | Phase 3 | wholly owned | CMC & Clinical Supply | 2025-10-06 | 2027-03 | active
PRJ-EQMS | eQMS migration | internal project | Corporate | n/a | wholly owned | Quality Assurance | 2025-03-03 | 2025-12 | completed
PRJ-SUPPORT | R&D support and quality | internal project | Corporate | n/a | wholly owned | Quality Assurance | 2016-01-04 | ongoing | active | 3040000
PRJ-RESERVE | R&D unallocated reserve | internal project | Corporate | n/a | wholly owned | Finance, Outsourcing & Procurement | 2026-01-01 | 2026-12 | active | 2400000
PRJ-0931 | LRT-0931 (closed) | development program | Corporate | closed | wholly owned | Clinical Development | 2018-03-01 | 2023-06 | closed

## Data 2
milestone_id | project | milestone | milestone_class | gate | baseline_date | forecast_date | actual_date | status | slip_days | owner_function | predecessor
MS-0001 | PRJ-1107 | Phase 3 program gate (G5) approved | governance | G5 | 2024-04-18 |  | 2024-04-18 | complete | 0 | Clinical Development
MS-0002 | PRJ-1107 | End-of-phase-2 meeting held | regulatory | none | 2024-02-27 |  | 2024-02-27 | complete | 0 | Clinical Development
MS-0003 | PRJ-1107 | Integrated development plan v3 approved | governance | none | 2026-09-15 |  | 2026-09-17 | complete | 2 | Clinical Development
MS-0004 | PRJ-1107 | Early commercial assessment complete | partnering | none | 2026-08-31 |  | 2026-09-04 | complete | 4 | Clinical Development
MS-0005 | PRJ-1107 | Topline results available | clinical | none | 2027-07-02 | 2027-09-14 |  | at risk | 74 | Clinical Development | MS-0021
MS-0006 | PRJ-1107 | Pre-NDA meeting request submitted | regulatory | none | 2027-09-30 | 2027-12-10 |  | not started | 71 | Clinical Development | MS-0005
MS-0007 | PRJ-1107-C1 | CRO work order executed | operational | none | 2024-06-01 |  | 2024-06-01 | complete | 0 | Clinical Operations
MS-0008 | PRJ-1107-C1 | First site activated | clinical | none | 2024-10-15 |  | 2024-10-21 | complete | 6 | Clinical Operations | MS-0007
MS-0009 | PRJ-1107-C1 | First participant randomized | clinical | none | 2024-11-15 |  | 2024-11-22 | complete | 7 | Clinical Operations | MS-0008
MS-0010 | PRJ-1107-C1 | 50% of sites activated | clinical | none | 2025-03-31 |  | 2025-04-03 | complete | 3 | Clinical Operations
MS-0011 | PRJ-1107-C1 | 100 participants randomized | clinical | none | 2025-06-05 |  | 2025-06-29 | complete | 24 | Clinical Operations | MS-0009
MS-0012 | PRJ-1107-C1 | All planned sites activated | clinical | none | 2025-09-30 | 2026-11-30 |  | late | 426 | Clinical Operations
MS-0013 | PRJ-1107-C1 | First DSMB review held | clinical | none | 2025-10-15 |  | 2025-10-22 | complete | 7 | Clinical Operations
MS-0014 | PRJ-1107-C1 | 50% of target randomized | clinical | none | 2026-01-29 |  | 2026-03-27 | complete | 57 | Clinical Operations | MS-0011
MS-0015 | PRJ-1107-C1 | Second DSMB review held | clinical | none | 2026-04-15 |  | 2026-04-28 | complete | 13 | Clinical Operations | MS-0013
MS-0016 | PRJ-1107-C1 | Enrollment reforecast agreed with CRO | operational | none | 2026-06-30 |  | 2026-06-30 | complete | 0 | Clinical Operations
MS-0017 | PRJ-1107-C1 | 75% of target randomized | clinical | none | 2026-07-14 | 2026-09-25 |  | late | 73 | Clinical Operations | MS-0014
MS-0018 | PRJ-1107-C1 | Third DSMB review held | clinical | none | 2026-10-14 | 2026-10-14 |  | on track | 0 | Clinical Operations | MS-0015
MS-0019 | PRJ-1107-C1 | Last participant randomized | clinical | none | 2026-12-31 | 2027-03-16 |  | at risk | 75 | Clinical Operations | MS-0017
MS-0020 | PRJ-1107-C1 | Last participant last visit | clinical | none | 2027-04-23 | 2027-07-06 |  | at risk | 74 | Clinical Operations | MS-0019
MS-0021 | PRJ-1107-C1 | Database lock | clinical | none | 2027-06-04 | 2027-08-17 |  | at risk | 74 | Clinical Operations | MS-0020
MS-0022 | PRJ-1107-C1 | Statistical analysis plan final | clinical | none | 2027-01-29 | 2027-02-12 |  | on track | 14 | Clinical Operations
MS-0023 | PRJ-1107-C1 | TMF completeness review (interim) | operational | none | 2026-06-15 |  | 2026-07-02 | complete | 17 | Clinical Operations
MS-0024 | PRJ-1107-CO4 | Change order 4 scope agreed with CRO | operational | none | 2026-08-14 |  | 2026-08-21 | complete | 7 | Clinical Operations
MS-0025 | PRJ-1107-CO4 | Change order 4 approved by board | financial | none | 2026-10-08 | 2026-10-08 |  | on track | 0 | Clinical Operations | MS-0024
MS-0026 | PRJ-1107-CO4 | Added country first site activated | clinical | none | 2026-12-01 | 2026-12-15 |  | not started | 14 | Clinical Operations | MS-0025
MS-0027 | PRJ-1107-OLE | OLE work order executed | operational | none | 2026-04-20 |  | 2026-04-20 | complete | 0 | Clinical Operations
MS-0028 | PRJ-1107-OLE | OLE first participant enrolled | clinical | none | 2026-06-15 |  | 2026-06-11 | complete | -4 | Clinical Operations | MS-0027
MS-0029 | PRJ-1107-OLE | OLE 100 participants enrolled | clinical | none | 2026-10-30 | 2026-11-13 |  | on track | 14 | Clinical Operations | MS-0028
MS-0030 | PRJ-1107-CMC | 2026 drug product campaign released | CMC | none | 2026-03-31 |  | 2026-03-24 | complete | -7 | CMC & Clinical Supply
MS-0031 | PRJ-1107-CMC | Clinical supply forecast v7 approved | CMC | none | 2026-07-15 |  | 2026-07-15 | complete | 0 | CMC & Clinical Supply
MS-0032 | PRJ-1107-CMC | Extension-period drug product campaign released | CMC | none | 2026-11-20 | 2026-11-20 |  | on track | 0 | CMC & Clinical Supply
MS-0033 | PRJ-1107-CMC | Shelf-life extension data filed | regulatory | none | 2026-08-28 |  | 2026-08-26 | complete | -2 | CMC & Clinical Supply
MS-0034 | PRJ-BAPI | Backup API supplier selected | CMC | none | 2025-12-12 |  | 2026-01-12 | complete | 31 | CMC & Clinical Supply
MS-0035 | PRJ-BAPI | Qualification audit performed | CMC | none | 2026-05-29 |  | 2026-06-09 | complete | 11 | CMC & Clinical Supply | MS-0034
MS-0036 | PRJ-BAPI | Audit response accepted | CMC | none | 2026-08-14 | 2026-10-16 |  | late | 63 | CMC & Clinical Supply | MS-0035
MS-0037 | PRJ-BAPI | Qualification batch released | CMC | none | 2026-12-18 | 2027-02-26 |  | at risk | 70 | CMC & Clinical Supply | MS-0036
MS-0038 | PRJ-BAPI | Backup supplier approved for clinical supply | CMC | none | 2027-01-29 | 2027-03-31 |  | at risk | 61 | CMC & Clinical Supply | MS-0037
MS-0039 | PRJ-2240 | Phase 2b design (draft) complete | clinical | none | 2026-05-29 |  | 2026-06-05 | complete | 7 | Clinical Development
MS-0040 | PRJ-2240 | Phase 2b gate (G4b) decision | governance | G4 | 2026-12-10 | 2027-02-11 |  | at risk | 63 | Clinical Development
MS-0041 | PRJ-2240-201 | Last participant last visit | clinical | none | 2025-11-14 |  | 2025-11-20 | complete | 6 | Clinical Operations
MS-0042 | PRJ-2240-201 | Database lock | clinical | none | 2026-01-16 |  | 2026-01-23 | complete | 7 | Clinical Operations | MS-0041
MS-0043 | PRJ-2240-201 | Topline analysis delivered | clinical | none | 2026-02-27 |  | 2026-02-26 | complete | -1 | Clinical Operations | MS-0042
MS-0044 | PRJ-2240-201 | Clinical study report final | clinical | none | 2026-06-12 |  | 2026-06-19 | complete | 7 | Clinical Operations | MS-0043
MS-0045 | PRJ-2240-201 | CRO close-out complete | operational | none | 2026-07-31 |  | 2026-07-28 | complete | -3 | Clinical Operations | MS-0044
MS-0046 | PRJ-2240-201 | TMF archived | operational | none | 2026-09-30 | 2026-10-16 |  | on track | 16 | Clinical Operations | MS-0045
MS-0047 | PRJ-2240-P2B | Phase 2b CRO shortlist | operational | none | 2026-07-31 | 2027-01-15 |  | at risk | 168 | Clinical Development
MS-0048 | PRJ-2240-P2B | Phase 2b protocol final | clinical | none | 2026-10-30 | 2027-02-26 |  | at risk | 119 | Clinical Development
MS-0049 | PRJ-2240-BD | Non-confidential presentation approved | partnering | none | 2026-05-08 |  | 2026-05-12 | complete | 4 | Business Development
MS-0050 | PRJ-2240-BD | Data room opened | partnering | none | 2026-05-29 |  | 2026-06-03 | complete | 5 | Business Development | MS-0049
MS-0051 | PRJ-2240-BD | First management meetings held | partnering | none | 2026-07-31 |  | 2026-08-06 | complete | 6 | Business Development | MS-0050
MS-0052 | PRJ-2240-BD | Indicative proposals received | partnering | none | 2026-10-30 | 2027-01-15 |  | at risk | 77 | Business Development | MS-0051
MS-0053 | PRJ-3318 | License agreement signed | partnering | none | 2025-11-14 |  | 2025-11-14 | complete | 0 | Business Development
MS-0054 | PRJ-3318 | Upfront payment received | financial | none | 2025-12-19 |  | 2025-12-17 | complete | -2 | Business Development | MS-0053
MS-0055 | PRJ-3318 | Development milestone 1 achieved | financial | none | 2026-06-30 |  | 2026-06-16 | complete | -14 | Business Development
MS-0056 | PRJ-3318 | Q3 joint steering committee held | governance | none | 2026-09-10 |  | 2026-09-10 | complete | 0 | Business Development
MS-0057 | PRJ-3318-TT | Tech transfer plan agreed | CMC | none | 2026-01-23 |  | 2026-01-23 | complete | 0 | CMC & Clinical Supply
MS-0058 | PRJ-3318-TT | Analytical methods package accepted | CMC | none | 2026-04-30 |  | 2026-04-22 | complete | -8 | CMC & Clinical Supply | MS-0057
MS-0059 | PRJ-3318-TT | Process description package accepted | CMC | none | 2026-06-30 |  | 2026-07-09 | complete | 9 | CMC & Clinical Supply | MS-0058
MS-0060 | PRJ-3318-TT | Stability and specifications package accepted | CMC | none | 2026-08-31 |  | 2026-09-11 | complete | 11 | CMC & Clinical Supply | MS-0059
MS-0061 | PRJ-3318-TT | Impurity control package accepted | CMC | none | 2026-10-30 | 2026-12-11 |  | at risk | 42 | CMC & Clinical Supply | MS-0060
MS-0062 | PRJ-3318-TT | Technology transfer complete | CMC | none | 2027-02-26 | 2027-03-26 |  | at risk | 28 | CMC & Clinical Supply | MS-0061
MS-0063 | PRJ-3318-SUP | Delivery 1 of drug substance | CMC | none | 2026-02-27 |  | 2026-02-24 | complete | -3 | CMC & Clinical Supply
MS-0064 | PRJ-3318-SUP | Delivery 2 of drug substance | CMC | none | 2026-06-26 |  | 2026-06-23 | complete | -3 | CMC & Clinical Supply | MS-0063
MS-0065 | PRJ-3318-SUP | Delivery 3 of drug substance | CMC | none | 2026-11-20 | 2026-11-20 |  | on track | 0 | CMC & Clinical Supply | MS-0064
MS-0066 | PRJ-4051 | Candidate nomination (G2) | governance | G2 | 2025-09-18 |  | 2025-09-18 | complete | 0 | Nonclinical Safety
MS-0067 | PRJ-4051 | Pre-IND meeting request submitted | regulatory | none | 2026-10-15 | 2026-11-20 |  | at risk | 36 | Nonclinical Safety
MS-0068 | PRJ-4051 | Pre-IND meeting held | regulatory | none | 2027-01-14 | 2027-02-18 |  | at risk | 35 | Nonclinical Safety | MS-0067
MS-0069 | PRJ-4051 | IND gate (G3) decision | governance | G3 | 2027-03-25 | 2027-04-29 |  | at risk | 35 | Nonclinical Safety | MS-0068
MS-0070 | PRJ-4051 | IND submitted | regulatory | none | 2027-04-30 | 2027-06-04 |  | at risk | 35 | Nonclinical Safety | MS-0069
MS-0071 | PRJ-4051-IND | GLP toxicology studies started | nonclinical | none | 2026-03-02 |  | 2026-03-09 | complete | 7 | Nonclinical Safety
MS-0072 | PRJ-4051-IND | Genetic toxicology battery final report | nonclinical | none | 2026-07-31 |  | 2026-07-24 | complete | -7 | Nonclinical Safety
MS-0073 | PRJ-4051-IND | GLP toxicology in-life complete | nonclinical | none | 2026-07-17 |  | 2026-07-31 | complete | 14 | Nonclinical Safety | MS-0071
MS-0074 | PRJ-4051-IND | GLP toxicology draft reports | nonclinical | none | 2026-09-25 | 2026-10-30 |  | at risk | 35 | Nonclinical Safety | MS-0073
MS-0075 | PRJ-4051-IND | GLP toxicology final reports | nonclinical | none | 2026-10-30 | 2026-12-04 |  | at risk | 35 | Nonclinical Safety | MS-0074
MS-0076 | PRJ-4051-IND | Validated bioanalytical method (GLP) | nonclinical | none | 2026-02-27 |  | 2026-03-06 | complete | 7 | Nonclinical Safety
MS-0077 | PRJ-4051-IND | Safety pharmacology final reports | nonclinical | none | 2026-09-30 | 2026-10-09 |  | on track | 9 | Nonclinical Safety
MS-0078 | PRJ-4051-IND | IND nonclinical summaries drafted | regulatory | none | 2027-01-29 | 2027-03-05 |  | not started | 35 | Nonclinical Safety | MS-0075
MS-0079 | PRJ-4051-CMC | GMP API campaign started | CMC | none | 2026-06-01 |  | 2026-06-15 | complete | 14 | CMC & Clinical Supply
MS-0080 | PRJ-4051-CMC | GMP API released | CMC | none | 2026-10-16 | 2026-12-11 |  | at risk | 56 | CMC & Clinical Supply | MS-0079
MS-0081 | PRJ-4051-CMC | Drug product formulation locked | CMC | none | 2026-08-28 |  | 2026-08-27 | complete | -1 | CMC & Clinical Supply
MS-0082 | PRJ-4051-CMC | Clinical drug product manufactured | CMC | none | 2027-02-19 | 2027-03-26 |  | at risk | 35 | CMC & Clinical Supply | MS-0080
MS-0083 | PRJ-4051-CMC | Stability data for IND (3 months) | CMC | none | 2027-03-12 | 2027-04-16 |  | not started | 35 | CMC & Clinical Supply | MS-0082
MS-0084 | PRJ-DP07 | Lead series selected | governance | G1 | 2025-03-20 |  | 2025-03-20 | complete | 0 | Discovery Biology
MS-0085 | PRJ-DP07 | Two development candidates profiled | nonclinical | none | 2026-06-30 |  | 2026-07-10 | complete | 10 | Discovery Biology
MS-0086 | PRJ-DP07 | Non-GLP rodent PK complete for backups | nonclinical | none | 2026-09-30 | 2026-10-09 |  | on track | 9 | Discovery Biology | MS-0085
MS-0087 | PRJ-DP07 | Candidate nomination (G2) | governance | G2 | 2027-05-20 | 2027-05-20 |  | on track | 0 | Discovery Biology | MS-0086
MS-0088 | PRJ-DP09 | Hit series confirmed | governance | G0 | 2025-11-13 |  | 2025-11-13 | complete | 0 | Discovery Biology
MS-0089 | PRJ-DP09 | Assay cascade validated | nonclinical | none | 2026-04-30 |  | 2026-05-22 | complete | 22 | Discovery Biology
MS-0090 | PRJ-DP09 | Lead series selection (G1) | governance | G1 | 2027-02-18 | 2027-03-18 |  | at risk | 28 | Discovery Biology | MS-0089
MS-0091 | PRJ-DP12 | Target validation plan approved | governance | G0 | 2025-07-17 |  | 2025-07-17 | complete | 0 | Discovery Biology
MS-0092 | PRJ-DP12 | Biomarker assay feasibility with academic partner | nonclinical | none | 2026-08-28 |  | 2026-09-02 | complete | 5 | Discovery Biology
MS-0093 | PRJ-DP12 | Target validation readout | governance | none | 2027-01-28 | 2027-01-28 |  | on track | 0 | Discovery Biology | MS-0092
MS-0094 | PRJ-LCMS | Capacity options analysis complete | operational | none | 2026-09-11 |  | 2026-09-15 | complete | 4 | DMPK & Bioanalytical
MS-0095 | PRJ-LCMS | Capacity decision by research leadership | operational | none | 2026-10-02 | 2026-10-02 |  | on track | 0 | DMPK & Bioanalytical | MS-0094
MS-0096 | PRJ-HUB2 | Phase 2 proposal reviewed | operational | none | 2026-09-17 |  | 2026-09-17 | complete | 0 | Research Informatics
MS-0097 | PRJ-HUB2 | Phase 2 planning approval | operational | none | 2026-10-30 | 2026-10-30 |  | not started | 0 | Research Informatics | MS-0096
MS-0098 | PRJ-EQMS | eQMS go-live | operational | none | 2025-11-10 |  | 2025-11-17 | complete | 7 | Quality Assurance
MS-0099 | PRJ-EQMS | Post-implementation review closed | operational | none | 2025-12-12 |  | 2025-12-12 | complete | 0 | Quality Assurance | MS-0098
MS-0100 | PRJ-SUPPORT | 2025 management review held | governance | none | 2026-02-20 |  | 2026-02-20 | complete | 0 | Quality Assurance
MS-0101 | PRJ-SUPPORT | Periodic-review backlog cleared | operational | none | 2026-06-30 | 2026-12-18 |  | late | 171 | Quality Assurance
MS-0102 | PRJ-SUPPORT | Tier 1 audit program 2026 complete | operational | none | 2026-12-18 | 2026-12-18 |  | on track | 0 | Quality Assurance
MS-0103 | PRJ-SUPPORT | Portfolio Review Committee January 2026 | governance | none | 2026-01-15 |  | 2026-01-15 | complete | 0 | Portfolio & Program Management
MS-0104 | PRJ-SUPPORT | Quarterly FTE allocation update January 2026 | governance | none | 2026-01-09 |  | 2026-01-09 | complete | 0 | Portfolio & Program Management
MS-0105 | PRJ-3318 | Joint steering committee January 2026 | governance | none | 2026-01-13 |  | 2026-01-13 | complete | 0 | Business Development
MS-0106 | PRJ-SUPPORT | Portfolio Review Committee February 2026 | governance | none | 2026-02-19 |  | 2026-02-19 | complete | 0 | Portfolio & Program Management
MS-0107 | PRJ-1107-C1 | CRO governance business review February 2026 | operational | none | 2026-02-20 |  | 2026-02-24 | complete | 4 | Clinical Operations
MS-0108 | PRJ-SUPPORT | Portfolio Review Committee March 2026 | governance | none | 2026-03-19 |  | 2026-03-19 | complete | 0 | Portfolio & Program Management
MS-0109 | PRJ-SUPPORT | Portfolio Review Committee April 2026 | governance | none | 2026-04-16 |  | 2026-04-16 | complete | 0 | Portfolio & Program Management
MS-0110 | PRJ-SUPPORT | Quarterly FTE allocation update April 2026 | governance | none | 2026-04-10 |  | 2026-04-10 | complete | 0 | Portfolio & Program Management
MS-0111 | PRJ-3318 | Joint steering committee April 2026 | governance | none | 2026-04-13 |  | 2026-04-13 | complete | 0 | Business Development
MS-0112 | PRJ-1107-C1 | CRO governance business review April 2026 | operational | none | 2026-04-21 |  | 2026-04-29 | complete | 8 | Clinical Operations
MS-0113 | PRJ-SUPPORT | Portfolio Review Committee May 2026 | governance | none | 2026-05-21 |  | 2026-05-21 | complete | 0 | Portfolio & Program Management
MS-0114 | PRJ-SUPPORT | Portfolio Review Committee June 2026 | governance | none | 2026-06-18 |  | 2026-06-18 | complete | 0 | Portfolio & Program Management
MS-0115 | PRJ-1107-C1 | CRO governance business review June 2026 | operational | none | 2026-06-22 |  | 2026-06-22 | complete | 0 | Clinical Operations
MS-0116 | PRJ-SUPPORT | Portfolio Review Committee July 2026 | governance | none | 2026-07-16 |  | 2026-07-16 | complete | 0 | Portfolio & Program Management
MS-0117 | PRJ-SUPPORT | Quarterly FTE allocation update July 2026 | governance | none | 2026-07-10 |  | 2026-07-10 | complete | 0 | Portfolio & Program Management
MS-0118 | PRJ-3318 | Joint steering committee July 2026 | governance | none | 2026-07-13 |  | 2026-07-13 | complete | 0 | Business Development
MS-0119 | PRJ-SUPPORT | Portfolio Review Committee August 2026 | governance | none | 2026-08-20 |  | 2026-08-20 | complete | 0 | Portfolio & Program Management
MS-0120 | PRJ-1107-C1 | CRO governance business review August 2026 | operational | none | 2026-08-21 |  | 2026-08-21 | complete | 0 | Clinical Operations
MS-0121 | PRJ-SUPPORT | Portfolio Review Committee September 2026 | governance | none | 2026-09-17 |  | 2026-09-17 | complete | 0 | Portfolio & Program Management
MS-0122 | PRJ-SUPPORT | Portfolio Review Committee October 2026 | governance | none | 2026-10-15 | 2026-10-15 |  | on track | 0 | Portfolio & Program Management
MS-0123 | PRJ-SUPPORT | Quarterly FTE allocation update October 2026 | governance | none | 2026-10-09 | 2026-10-09 |  | on track | 0 | Portfolio & Program Management
MS-0124 | PRJ-3318 | Joint steering committee October 2026 | governance | none | 2026-10-13 | 2026-10-13 |  | on track | 0 | Business Development
MS-0125 | PRJ-1107-C1 | CRO governance business review October 2026 | operational | none | 2026-10-21 | 2026-10-23 |  | on track | 2 | Clinical Operations
MS-0126 | PRJ-SUPPORT | Portfolio Review Committee November 2026 | governance | none | 2026-11-19 | 2026-11-19 |  | on track | 0 | Portfolio & Program Management
MS-0127 | PRJ-SUPPORT | Portfolio Review Committee December 2026 | governance | none | 2026-12-17 | 2026-12-17 |  | on track | 0 | Portfolio & Program Management
MS-0128 | PRJ-1107-C1 | CRO governance business review December 2026 | operational | none | 2026-12-21 | 2026-12-22 |  | on track | 1 | Clinical Operations
MS-0129 | PRJ-1107-CMC | Clinical supply forecast review January 2026 | CMC | none | 2026-01-15 |  | 2026-01-16 | complete | 1 | CMC & Clinical Supply
MS-0130 | PRJ-1107-CMC | Clinical supply forecast review February 2026 | CMC | none | 2026-02-16 |  | 2026-02-20 | complete | 4 | CMC & Clinical Supply
MS-0131 | PRJ-1107-CMC | Clinical supply forecast review March 2026 | CMC | none | 2026-03-16 |  | 2026-03-20 | complete | 4 | CMC & Clinical Supply
MS-0132 | PRJ-1107-CMC | Clinical supply forecast review April 2026 | CMC | none | 2026-04-15 |  | 2026-04-16 | complete | 1 | CMC & Clinical Supply
MS-0133 | PRJ-1107-CMC | Clinical supply forecast review May 2026 | CMC | none | 2026-05-15 |  | 2026-05-18 | complete | 3 | CMC & Clinical Supply
MS-0134 | PRJ-1107-CMC | Clinical supply forecast review June 2026 | CMC | none | 2026-06-15 |  | 2026-06-16 | complete | 1 | CMC & Clinical Supply
MS-0135 | PRJ-1107-CMC | Clinical supply forecast review July 2026 | CMC | none | 2026-07-15 |  | 2026-07-17 | complete | 2 | CMC & Clinical Supply
MS-0136 | PRJ-1107-CMC | Clinical supply forecast review August 2026 | CMC | none | 2026-08-14 |  | 2026-08-19 | complete | 5 | CMC & Clinical Supply
MS-0137 | PRJ-1107-C1 | Monthly enrollment report reviewed January 2026 | operational | none | 2026-02-10 |  | 2026-02-13 | complete | 3 | Clinical Operations
MS-0138 | PRJ-1107-C1 | Monthly enrollment report reviewed February 2026 | operational | none | 2026-03-10 |  | 2026-03-13 | complete | 3 | Clinical Operations
MS-0139 | PRJ-1107-C1 | Monthly enrollment report reviewed March 2026 | operational | none | 2026-04-10 |  | 2026-04-10 | complete | 0 | Clinical Operations
MS-0140 | PRJ-1107-C1 | Monthly enrollment report reviewed April 2026 | operational | none | 2026-05-11 |  | 2026-05-11 | complete | 0 | Clinical Operations
MS-0141 | PRJ-1107-C1 | Monthly enrollment report reviewed May 2026 | operational | none | 2026-06-10 |  | 2026-06-09 | complete | -1 | Clinical Operations
MS-0142 | PRJ-1107-C1 | Monthly enrollment report reviewed June 2026 | operational | none | 2026-07-10 |  | 2026-07-13 | complete | 3 | Clinical Operations
MS-0143 | PRJ-1107-C1 | Monthly enrollment report reviewed July 2026 | operational | none | 2026-08-10 |  | 2026-08-14 | complete | 4 | Clinical Operations
MS-0144 | PRJ-1107-C1 | Monthly enrollment report reviewed August 2026 | operational | none | 2026-09-10 |  | 2026-09-15 | complete | 5 | Clinical Operations
MS-0145 | PRJ-RESERVE | R&D accrual close January 2026 | financial | none | 2026-02-06 |  | 2026-02-06 | complete | 0 | Finance, Outsourcing & Procurement
MS-0146 | PRJ-RESERVE | R&D accrual close February 2026 | financial | none | 2026-03-06 |  | 2026-03-06 | complete | 0 | Finance, Outsourcing & Procurement
MS-0147 | PRJ-RESERVE | R&D accrual close March 2026 | financial | none | 2026-04-07 |  | 2026-04-09 | complete | 2 | Finance, Outsourcing & Procurement
MS-0148 | PRJ-RESERVE | R&D accrual close April 2026 | financial | none | 2026-05-07 |  | 2026-05-08 | complete | 1 | Finance, Outsourcing & Procurement
MS-0149 | PRJ-RESERVE | R&D accrual close May 2026 | financial | none | 2026-06-08 |  | 2026-06-08 | complete | 0 | Finance, Outsourcing & Procurement
MS-0150 | PRJ-RESERVE | R&D accrual close June 2026 | financial | none | 2026-07-07 |  | 2026-07-07 | complete | 0 | Finance, Outsourcing & Procurement