## Read me
Vendor Deliverables Tracker, January–August 2026
Loblolly Ridge Therapeutics
Effective date | 2026-09-18
Purpose | All contracted deliverables due January 1 to August 31, 2026 with receipt, review and outcome status as of September 18.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Extract from the deliverables tracker of every contracted deliverable due from January 1 to August 31, 2026, with receipt, review and outcome status as of September 18, 2026. Deliverables due after August 31 are excluded, so recent months are not yet complete.
What is in the data | 493 deliverables from partners' work orders: activity reports for accrual, monthly status reports, data transfers, certificates of analysis, executed batch records, stability results, draft and final study reports and TFL drafts. Each row carries the work order, partner, project, due date, received date, review type, review completion date, outcome, days late, review days and an on-time flag.
How deliverables are reviewed | Deliverables are logged on receipt. QA reviews certificates of analysis, executed batch records, stability results and final study reports; technical owners review other deliverables; Finance reviews activity reports used for accruals.
Definitions | On time: received on or before the due date (flag 1); late: flag 0; blank when not yet received. The mean of the flag in the Summary is the on-time share of received items.
Definitions | Days late: received date minus due date, zero when on time.
Definitions | Review days: review completion date minus received date. Blank for items not yet received or still under review, so the Summary mean covers reviewed items only.
Definitions | Outcome: accepted, accepted with comments, returned for revision, under review or not received.
Position at September 18 | Of the 493 deliverables due, 487 had been received, 87% of them on or before the due date. 14 were returned for revision and 6 had not been received. Two of the six are January data transfers that were superseded by the next transfer and not re-sent; they stay open until the owner closes them.
Position at September 18 | Median review time after receipt: QA 6 days, Finance 3 days, technical 4 days.
On-time share by type | Executed batch record 56% of 16; final study report 62% of 24; draft study report 79% of 24; certificate of analysis 85% of 39; activity report for accrual 88% of 121; data transfer 89% of 108; TFL draft 89% of 18; monthly status report 93% of 116; stability results 95% of 21. Hanlin Pharmatech delivered 9 of 15 qualification-batch deliverables on time.
Not included | Deliverable content, partner correspondence and deliverables due after August 31.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Contracted deliverables | on_time_flag | flag | 422 | 0.86653 | 487 | 2026-01-01 | 2026-09-18
Contracted deliverables | days_late | days | 559 | 1.1478 | 487 | 2026-01-01 | 2026-09-18
Contracted deliverables | review_days | days | 2399 | 4.9362 | 486 | 2026-01-01 | 2026-09-18

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Contracted deliverables | deliverable_id | Deliverable id |  | id
Contracted deliverables | on_time_flag | 1 if received on or before the due date, 0 if later; blank if not received | flag | integer
Contracted deliverables | wo_id | Wo id |  | category
Contracted deliverables | vendor_id | Vendor id |  | category
Contracted deliverables | project | Project |  | category
Contracted deliverables | deliverable_type | Deliverable type |  | category
Contracted deliverables | due_date | Due date |  | date
Contracted deliverables | received_date | Received date |  | date
Contracted deliverables | review_type | Review type |  | category
Contracted deliverables | review_complete_date | Review complete date |  | date
Contracted deliverables | outcome | Outcome |  | category
Contracted deliverables | days_late | Days after the due date (0 if on time) | days | integer
Contracted deliverables | review_days | Days from receipt to review completion | days | integer

## Data 1
deliverable_id | on_time_flag | wo_id | vendor_id | project | deliverable_type | due_date | received_date | review_type | review_complete_date | outcome | days_late | review_days
DL-00001 | 0 | WO-0039 | V-014 | PRJ-1107-CMC | executed batch record | 2026-01-02 | 2026-01-09 | QA | 2026-01-20 | accepted | 7 | 11
DL-00002 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-01-05 | 2026-01-04 | technical | 2026-01-08 | accepted with comments | 0 | 4
DL-00003 |  | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-01-07 |  | technical |  | not received
DL-00004 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | stability results | 2026-01-08 | 2026-01-03 | QA | 2026-01-14 | accepted | 0 | 11
DL-00005 | 0 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-01-12 | 2026-01-17 | technical | 2026-01-20 | accepted | 5 | 3
DL-00006 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-01-12 | 2026-01-11 | technical | 2026-01-13 | accepted | 0 | 2
DL-00007 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-01-13 | 2026-01-12 | technical | 2026-01-26 | accepted | 0 | 14
DL-00008 |  | WO-0029 | V-010 | PRJ-4051-IND | data transfer | 2026-01-13 |  | technical |  | not received
DL-00009 | 0 | WO-0029 | V-010 | PRJ-4051-IND | final study report | 2026-01-16 | 2026-02-13 | QA | 2026-02-19 | accepted | 28 | 6
DL-00010 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-01-19 | 2026-01-14 | technical | 2026-01-17 | accepted | 0 | 3
DL-00011 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | draft study report | 2026-01-19 | 2026-01-18 | technical | 2026-01-21 | accepted | 0 | 3
DL-00012 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-01-21 | 2026-01-19 | technical | 2026-01-24 | accepted | 0 | 5
DL-00013 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | executed batch record | 2026-01-21 | 2026-01-17 | QA | 2026-01-27 | accepted | 0 | 10
DL-00014 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | stability results | 2026-01-23 | 2026-01-23 | QA | 2026-02-04 | accepted | 0 | 12
DL-00015 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-01-26 | 2026-01-23 | technical | 2026-01-28 | accepted | 0 | 5
DL-00016 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | TFL draft | 2026-01-26 | 2026-01-26 | technical | 2026-02-01 | accepted | 0 | 6
DL-00017 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | draft study report | 2026-01-26 | 2026-01-25 | technical | 2026-01-30 | accepted | 0 | 5
DL-00018 | 0 | WO-0039 | V-014 | PRJ-1107-CMC | certificate of analysis | 2026-01-26 | 2026-01-28 | QA | 2026-02-06 | accepted with comments | 2 | 9
DL-00019 | 1 | WO-0029 | V-010 | PRJ-4051-IND | final study report | 2026-01-28 | 2026-01-26 | QA | 2026-01-28 | accepted with comments | 0 | 2
DL-00020 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-02-02 | 2026-01-30 | technical | 2026-02-04 | accepted with comments | 0 | 5
DL-00021 | 0 | WO-0029 | V-010 | PRJ-4051-IND | draft study report | 2026-02-02 | 2026-02-07 | technical | 2026-02-11 | accepted | 5 | 4
DL-00022 | 1 | WO-0032 | V-011 | PRJ-DP07 | final study report | 2026-02-02 | 2026-02-02 | QA | 2026-02-08 | accepted | 0 | 6
DL-00023 | 1 | WO-0033 | V-011 | PRJ-4051-IND | draft study report | 2026-02-02 | 2026-01-31 | technical | 2026-02-02 | accepted with comments | 0 | 2
DL-00024 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | certificate of analysis | 2026-02-02 | 2026-02-02 | QA | 2026-02-05 | accepted | 0 | 3
DL-00025 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | stability results | 2026-02-03 | 2026-02-01 | QA | 2026-02-22 | accepted | 0 | 21
DL-00026 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-02-04 | 2026-02-04 | technical | 2026-02-08 | accepted | 0 | 4
DL-00027 | 1 | WO-0062 | V-033 | PRJ-2240-201 | final study report | 2026-02-04 | 2026-02-02 | QA | 2026-02-10 | accepted | 0 | 8
DL-00028 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-02-05 | 2026-02-04 | finance | 2026-02-06 | accepted | 0 | 2
DL-00029 | 1 | WO-0008 | V-002 | PRJ-2240-201 | activity report for accrual | 2026-02-05 | 2026-01-31 | finance | 2026-02-03 | accepted | 0 | 3
DL-00030 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-02-05 | 2026-02-03 | finance | 2026-02-06 | accepted | 0 | 3
DL-00031 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-02-05 | 2026-01-31 | finance | 2026-02-01 | accepted with comments | 0 | 1
DL-00032 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | TFL draft | 2026-02-05 | 2026-02-05 | technical | 2026-02-10 | accepted | 0 | 5
DL-00033 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-02-05 | 2026-02-05 | finance | 2026-02-09 | accepted with comments | 0 | 4
DL-00034 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-02-05 | 2026-02-02 | finance | 2026-02-05 | accepted | 0 | 3
DL-00035 | 1 | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-02-05 | 2026-02-01 | finance | 2026-02-03 | accepted | 0 | 2
DL-00036 | 0 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-02-05 | 2026-02-11 | finance | 2026-02-15 | accepted | 6 | 4
DL-00037 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-02-05 | 2026-02-02 | finance | 2026-02-04 | accepted | 0 | 2
DL-00038 | 0 | WO-0029 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-02-05 | 2026-02-07 | finance | 2026-02-13 | accepted | 2 | 6
DL-00039 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | activity report for accrual | 2026-02-05 | 2026-02-01 | finance | 2026-02-04 | accepted | 0 | 3
DL-00040 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-02-05 | 2026-02-05 | finance | 2026-02-07 | accepted | 0 | 2
DL-00041 | 0 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-02-05 | 2026-02-08 | finance | 2026-02-10 | accepted with comments | 3 | 2
DL-00042 | 1 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-02-05 | 2026-02-05 | finance | 2026-02-07 | accepted | 0 | 2
DL-00043 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-02-05 | 2026-02-04 | finance | 2026-02-07 | accepted | 0 | 3
DL-00044 | 0 | WO-0071 | V-043 | PRJ-1107-C1 | TFL draft | 2026-02-05 | 2026-02-14 | technical | 2026-02-19 | accepted | 9 | 5
DL-00045 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | TFL draft | 2026-02-09 | 2026-02-04 | technical | 2026-02-08 | returned for revision | 0 | 4
DL-00046 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-02-09 | 2026-02-05 | technical | 2026-02-09 | accepted | 0 | 4
DL-00047 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-02-10 | 2026-02-05 | technical | 2026-02-07 | accepted with comments | 0 | 2
DL-00048 | 1 | WO-0008 | V-002 | PRJ-2240-201 | monthly status report | 2026-02-10 | 2026-02-07 | technical | 2026-02-11 | accepted with comments | 0 | 4
DL-00049 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-02-10 | 2026-02-08 | technical | 2026-02-11 | accepted | 0 | 3
DL-00050 | 1 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-02-10 | 2026-02-08 | technical | 2026-02-12 | accepted | 0 | 4
DL-00051 | 0 | WO-0019 | V-006 | PRJ-2240-201 | monthly status report | 2026-02-10 | 2026-02-16 | technical | 2026-02-20 | accepted | 6 | 4
DL-00052 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-02-10 | 2026-02-08 | technical | 2026-02-14 | accepted | 0 | 6
DL-00053 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-02-10 | 2026-02-08 | technical | 2026-02-13 | accepted | 0 | 5
DL-00054 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-02-10 | 2026-02-07 | technical | 2026-02-11 | accepted | 0 | 4
DL-00055 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-02-10 | 2026-02-08 | technical | 2026-02-11 | accepted | 0 | 3
DL-00056 | 1 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-02-10 | 2026-02-08 | technical | 2026-02-12 | accepted with comments | 0 | 4
DL-00057 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-02-10 | 2026-02-09 | technical | 2026-02-13 | accepted | 0 | 4
DL-00058 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-02-10 | 2026-02-09 | technical | 2026-02-14 | accepted | 0 | 5
DL-00059 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-02-10 | 2026-02-08 | technical | 2026-02-14 | accepted | 0 | 6
DL-00060 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-02-10 | 2026-02-06 | technical | 2026-02-09 | accepted | 0 | 3
DL-00061 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-02-10 | 2026-02-07 | technical | 2026-02-09 | accepted | 0 | 2
DL-00062 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | stability results | 2026-02-11 | 2026-02-08 | QA | 2026-02-10 | accepted | 0 | 2
DL-00063 | 0 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-02-12 | 2026-02-15 | technical | 2026-02-23 | accepted with comments | 3 | 8
DL-00064 | 1 | WO-0029 | V-010 | PRJ-4051-IND | data transfer | 2026-02-12 | 2026-02-09 | technical | 2026-02-12 | accepted with comments | 0 | 3
DL-00065 | 0 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-02-16 | 2026-02-18 | technical | 2026-02-28 | accepted | 2 | 10
DL-00066 | 1 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-02-16 | 2026-02-13 | technical | 2026-02-16 | accepted | 0 | 3
DL-00067 | 0 | WO-0030 | V-010 | PRJ-4051-IND | final study report | 2026-02-16 | 2026-03-08 | QA | 2026-03-15 | accepted | 20 | 7
DL-00068 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-02-18 | 2026-02-13 | technical | 2026-02-15 | accepted | 0 | 2
DL-00069 | 1 | WO-0039 | V-014 | PRJ-1107-CMC | certificate of analysis | 2026-02-19 | 2026-02-16 | QA | 2026-02-20 | accepted with comments | 0 | 4
DL-00070 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-02-23 | 2026-02-23 | technical | 2026-02-26 | accepted with comments | 0 | 3
DL-00071 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | final study report | 2026-02-23 | 2026-02-18 | QA | 2026-02-22 | accepted | 0 | 4
DL-00072 | 0 | WO-0043 | V-015 | PRJ-BAPI | executed batch record | 2026-02-23 | 2026-04-27 | QA | 2026-05-01 | accepted | 63 | 4
DL-00073 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | TFL draft | 2026-02-24 | 2026-02-19 | technical | 2026-02-27 | accepted | 0 | 8
DL-00074 | 1 | WO-0025 | V-009 | PRJ-4051-IND | draft study report | 2026-02-27 | 2026-02-22 | technical | 2026-02-25 | accepted with comments | 0 | 3
DL-00075 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | certificate of analysis | 2026-02-27 | 2026-02-24 | QA | 2026-03-01 | accepted | 0 | 5
DL-00076 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-03-02 | 2026-03-01 | technical | 2026-03-11 | accepted with comments | 0 | 10
DL-00077 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-03-04 | 2026-02-27 | technical | 2026-03-02 | accepted with comments | 0 | 3
DL-00078 | 0 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-03-05 | 2026-03-07 | finance | 2026-03-16 | accepted | 2 | 9
DL-00079 | 1 | WO-0008 | V-002 | PRJ-2240-201 | activity report for accrual | 2026-03-05 | 2026-03-04 | finance | 2026-03-07 | accepted | 0 | 3
DL-00080 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-03-05 | 2026-03-04 | finance | 2026-03-12 | accepted | 0 | 8
DL-00081 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-03-05 | 2026-03-03 | finance | 2026-03-16 | accepted | 0 | 13
DL-00082 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-03-05 | 2026-03-05 | finance | 2026-03-11 | accepted | 0 | 6
DL-00083 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-03-05 | 2026-03-02 | finance | 2026-03-10 | accepted | 0 | 8
DL-00084 | 1 | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-03-05 | 2026-02-28 | finance | 2026-03-01 | accepted | 0 | 1
DL-00085 | 1 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-03-05 | 2026-03-05 | finance | 2026-03-07 | accepted | 0 | 2
DL-00086 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-03-05 | 2026-02-28 | finance | 2026-03-02 | accepted | 0 | 2
DL-00087 | 1 | WO-0029 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-03-05 | 2026-03-03 | finance | 2026-03-07 | accepted | 0 | 4
DL-00088 | 1 | WO-0030 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-03-05 | 2026-02-28 | finance | 2026-03-09 | accepted | 0 | 9
DL-00089 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-03-05 | 2026-03-01 | finance | 2026-03-03 | accepted | 0 | 2
DL-00090 | 1 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-03-05 | 2026-03-04 | finance | 2026-03-07 | accepted | 0 | 3
DL-00091 | 1 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-03-05 | 2026-03-05 | finance | 2026-03-07 | accepted | 0 | 2
DL-00092 | 0 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-03-05 | 2026-03-08 | finance | 2026-03-09 | accepted | 3 | 1
DL-00093 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | certificate of analysis | 2026-03-05 | 2026-03-02 | QA | 2026-03-12 | accepted | 0 | 10
DL-00094 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-03-09 | 2026-03-06 | technical | 2026-03-12 | accepted | 0 | 6
DL-00095 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | TFL draft | 2026-03-09 | 2026-03-08 | technical | 2026-03-14 | accepted | 0 | 6
DL-00096 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-03-10 | 2026-03-05 | technical | 2026-03-08 | accepted with comments | 0 | 3
DL-00097 | 1 | WO-0008 | V-002 | PRJ-2240-201 | monthly status report | 2026-03-10 | 2026-03-07 | technical | 2026-03-09 | accepted with comments | 0 | 2
DL-00098 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-03-10 | 2026-03-07 | technical | 2026-03-12 | accepted | 0 | 5
DL-00099 | 1 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-03-10 | 2026-03-06 | technical | 2026-03-18 | accepted | 0 | 12
DL-00100 | 1 | WO-0019 | V-006 | PRJ-2240-201 | monthly status report | 2026-03-10 | 2026-03-10 | technical | 2026-03-18 | accepted | 0 | 8
DL-00101 | 0 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-03-10 | 2026-03-16 | technical | 2026-03-19 | accepted | 6 | 3
DL-00102 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-03-10 | 2026-03-10 | technical | 2026-03-13 | accepted with comments | 0 | 3
DL-00103 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-03-10 | 2026-03-08 | technical | 2026-03-12 | accepted | 0 | 4
DL-00104 | 1 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-03-10 | 2026-03-05 | technical | 2026-03-11 | accepted | 0 | 6
DL-00105 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-03-10 | 2026-03-05 | technical | 2026-03-07 | accepted | 0 | 2
DL-00106 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-03-10 | 2026-03-07 | technical | 2026-03-14 | accepted | 0 | 7
DL-00107 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-03-10 | 2026-03-06 | technical | 2026-03-10 | accepted | 0 | 4
DL-00108 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-03-10 | 2026-03-06 | technical | 2026-03-09 | accepted | 0 | 3
DL-00109 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-03-10 | 2026-03-06 | technical | 2026-03-09 | accepted with comments | 0 | 3
DL-00110 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-03-12 | 2026-03-09 | technical | 2026-03-16 | accepted | 0 | 7
DL-00111 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | certificate of analysis | 2026-03-12 | 2026-03-11 | QA | 2026-03-28 | accepted | 0 | 17
DL-00112 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-03-16 | 2026-03-11 | technical | 2026-03-12 | accepted | 0 | 1
DL-00113 | 0 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-03-16 | 2026-03-18 | technical | 2026-03-24 | accepted | 2 | 6
DL-00114 | 1 | WO-0029 | V-010 | PRJ-4051-IND | data transfer | 2026-03-16 | 2026-03-16 | technical | 2026-03-20 | returned for revision | 0 | 4
DL-00115 | 1 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-03-16 | 2026-03-12 | technical | 2026-03-15 | accepted with comments | 0 | 3
DL-00116 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | certificate of analysis | 2026-03-17 | 2026-03-13 | QA | 2026-03-17 | accepted | 0 | 4
DL-00117 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-03-18 | 2026-03-15 | technical | 2026-03-31 | accepted | 0 | 16
DL-00118 | 0 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-03-23 | 2026-03-25 | technical | 2026-03-27 | accepted | 2 | 2
DL-00119 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | certificate of analysis | 2026-03-24 | 2026-03-21 | QA | 2026-03-25 | accepted with comments | 0 | 4
DL-00120 | 1 | WO-0062 | V-033 | PRJ-2240-201 | final study report | 2026-03-24 | 2026-03-20 | QA | 2026-03-23 | accepted | 0 | 3
DL-00121 | 1 | WO-0032 | V-011 | PRJ-DP07 | final study report | 2026-03-26 | 2026-03-25 | QA | 2026-03-30 | accepted | 0 | 5
DL-00122 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-03-30 | 2026-03-28 | technical | 2026-04-02 | accepted | 0 | 5
DL-00123 | 0 | WO-0043 | V-015 | PRJ-BAPI | executed batch record | 2026-03-30 | 2026-04-12 | QA | 2026-04-15 | accepted with comments | 13 | 3
DL-00124 | 1 | WO-0047 | V-017 | PRJ-1107-CMC | stability results | 2026-03-30 | 2026-03-28 | QA | 2026-04-01 | accepted | 0 | 4
DL-00125 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-04-01 | 2026-04-01 | technical | 2026-04-03 | accepted | 0 | 2
DL-00126 | 1 | WO-0047 | V-017 | PRJ-1107-CMC | certificate of analysis | 2026-04-01 | 2026-04-01 | QA | 2026-04-07 | accepted | 0 | 6
DL-00127 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | executed batch record | 2026-04-03 | 2026-03-30 | QA | 2026-04-05 | accepted | 0 | 6
DL-00128 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-04-06 | 2026-04-01 | finance | 2026-04-06 | accepted | 0 | 5
DL-00129 | 0 | WO-0008 | V-002 | PRJ-2240-201 | activity report for accrual | 2026-04-06 | 2026-04-09 | finance | 2026-04-11 | accepted | 3 | 2
DL-00130 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-04-06 | 2026-04-04 | finance | 2026-04-08 | accepted with comments | 0 | 4
DL-00131 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-04-06 | 2026-04-06 | technical | 2026-04-09 | accepted | 0 | 3
DL-00132 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-04-06 | 2026-04-05 | finance | 2026-04-09 | accepted | 0 | 4
DL-00133 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-04-06 | 2026-04-04 | finance | 2026-04-06 | accepted | 0 | 2
DL-00134 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-04-06 | 2026-04-03 | finance | 2026-04-08 | accepted with comments | 0 | 5
DL-00135 | 1 | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-04-06 | 2026-04-01 | finance | 2026-04-04 | accepted | 0 | 3
DL-00136 | 1 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-04-06 | 2026-04-03 | finance | 2026-04-08 | accepted | 0 | 5
DL-00137 | 0 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-04-06 | 2026-04-11 | finance | 2026-04-21 | accepted | 5 | 10
DL-00138 | 1 | WO-0029 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-04-06 | 2026-04-01 | finance | 2026-04-03 | accepted with comments | 0 | 2
DL-00139 | 0 | WO-0030 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-04-06 | 2026-04-09 | finance | 2026-04-14 | accepted | 3 | 5
DL-00140 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-04-06 | 2026-04-06 | finance | 2026-04-08 | accepted with comments | 0 | 2
DL-00141 | 1 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-04-06 | 2026-04-03 | finance | 2026-04-06 | accepted | 0 | 3
DL-00142 | 1 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-04-06 | 2026-04-05 | finance | 2026-04-07 | accepted | 0 | 2
DL-00143 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-04-06 | 2026-04-01 | finance | 2026-04-09 | accepted | 0 | 8
DL-00144 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | executed batch record | 2026-04-06 | 2026-04-03 | QA | 2026-04-11 | accepted | 0 | 8
DL-00145 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | activity report for accrual | 2026-04-06 | 2026-04-05 | finance | 2026-04-08 | accepted with comments | 0 | 3
DL-00146 | 1 | WO-0047 | V-017 | PRJ-1107-CMC | stability results | 2026-04-07 | 2026-04-02 | QA | 2026-04-14 | accepted | 0 | 12
DL-00147 | 1 | WO-0027 | V-038 | PRJ-4051-IND | final study report | 2026-04-09 | 2026-04-08 | QA | 2026-04-13 | accepted | 0 | 5
DL-00148 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-04-10 | 2026-04-09 | technical | 2026-04-17 | accepted | 0 | 8
DL-00149 | 1 | WO-0008 | V-002 | PRJ-2240-201 | monthly status report | 2026-04-10 | 2026-04-06 | technical | 2026-04-08 | accepted | 0 | 2
DL-00150 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-04-10 | 2026-04-05 | technical | 2026-04-10 | accepted | 0 | 5
DL-00151 | 1 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-04-10 | 2026-04-10 | technical | 2026-04-12 | accepted with comments | 0 | 2
DL-00152 | 0 | WO-0019 | V-006 | PRJ-2240-201 | monthly status report | 2026-04-10 | 2026-04-13 | technical | 2026-04-19 | accepted | 3 | 6
DL-00153 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-04-10 | 2026-04-09 | technical | 2026-04-13 | accepted | 0 | 4
DL-00154 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-04-10 | 2026-04-07 | technical | 2026-04-09 | accepted | 0 | 2
DL-00155 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-04-10 | 2026-04-09 | technical | 2026-04-12 | accepted | 0 | 3
DL-00156 | 1 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-04-10 | 2026-04-10 | technical | 2026-04-14 | accepted | 0 | 4
DL-00157 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-04-10 | 2026-04-08 | technical | 2026-04-11 | accepted with comments | 0 | 3
DL-00158 | 1 | WO-0060 | V-031 | PRJ-4051-IND | monthly status report | 2026-04-10 | 2026-04-06 | technical | 2026-04-09 | accepted | 0 | 3
DL-00159 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-04-10 | 2026-04-07 | technical | 2026-04-11 | accepted | 0 | 4
DL-00160 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-04-10 | 2026-04-10 | technical | 2026-04-17 | accepted | 0 | 7
DL-00161 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-04-10 | 2026-04-08 | technical | 2026-04-11 | accepted | 0 | 3
DL-00162 | 0 | WO-0068 | V-040 | PRJ-1107-C1 | monthly status report | 2026-04-10 | 2026-04-12 | technical | 2026-04-18 | accepted | 2 | 6
DL-00163 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-04-10 | 2026-04-05 | technical | 2026-04-15 | accepted with comments | 0 | 10
DL-00164 | 1 | WO-0071 | V-043 | PRJ-1107-C1 | TFL draft | 2026-04-10 | 2026-04-10 | technical | 2026-04-12 | accepted | 0 | 2
DL-00165 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-04-13 | 2026-04-12 | technical | 2026-04-17 | accepted | 0 | 5
DL-00166 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-04-13 | 2026-04-11 | technical | 2026-04-16 | accepted | 0 | 5
DL-00167 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-04-13 | 2026-04-12 | technical | 2026-04-17 | accepted | 0 | 5
DL-00168 | 1 | WO-0029 | V-010 | PRJ-4051-IND | data transfer | 2026-04-13 | 2026-04-10 | technical | 2026-04-11 | accepted | 0 | 1
DL-00169 | 0 | WO-0033 | V-011 | PRJ-4051-IND | final study report | 2026-04-13 | 2026-04-22 | QA | 2026-04-27 | accepted | 9 | 5
DL-00170 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | certificate of analysis | 2026-04-13 | 2026-04-12 | QA | 2026-04-16 | accepted | 0 | 4
DL-00171 | 0 | WO-0043 | V-015 | PRJ-BAPI | certificate of analysis | 2026-04-13 | 2026-04-23 | QA | 2026-04-29 | accepted | 10 | 6
DL-00172 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | executed batch record | 2026-04-13 | 2026-04-10 | QA | 2026-04-24 | accepted | 0 | 14
DL-00173 | 0 | WO-0032 | V-011 | PRJ-DP07 | draft study report | 2026-04-14 | 2026-04-27 | technical | 2026-04-30 | accepted with comments | 13 | 3
DL-00174 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-04-15 | 2026-04-15 | technical | 2026-04-30 | accepted | 0 | 15
DL-00175 | 0 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-04-15 | 2026-04-18 | technical | 2026-04-22 | accepted | 3 | 4
DL-00176 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | certificate of analysis | 2026-04-15 | 2026-04-10 | QA | 2026-04-14 | accepted | 0 | 4
DL-00177 | 0 | WO-0001 | V-001 | PRJ-1107-C1 | TFL draft | 2026-04-17 | 2026-04-22 | technical | 2026-05-02 | accepted with comments | 5 | 10
DL-00178 | 0 | WO-0040 | V-014 | PRJ-3318-SUP | executed batch record | 2026-04-17 | 2026-05-07 | QA | 2026-05-12 | accepted | 20 | 5
DL-00179 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | TFL draft | 2026-04-20 | 2026-04-18 | technical | 2026-04-21 | returned for revision | 0 | 3
DL-00180 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-04-20 | 2026-04-19 | technical | 2026-04-23 | accepted | 0 | 4
DL-00181 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | certificate of analysis | 2026-04-20 | 2026-04-19 | QA | 2026-04-27 | accepted | 0 | 8
DL-00182 | 1 | WO-0041 | V-014 | PRJ-3318-TT | stability results | 2026-04-20 | 2026-04-20 | QA | 2026-04-26 | accepted with comments | 0 | 6
DL-00183 | 1 | WO-0030 | V-010 | PRJ-4051-IND | draft study report | 2026-04-21 | 2026-04-17 | technical | 2026-04-20 | accepted | 0 | 3
DL-00184 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-04-27 | 2026-04-25 | technical | 2026-04-30 | accepted | 0 | 5
DL-00185 | 1 | WO-0025 | V-009 | PRJ-4051-IND | final study report | 2026-04-27 | 2026-04-24 | QA | 2026-05-02 | accepted with comments | 0 | 8
DL-00186 | 1 | WO-0027 | V-038 | PRJ-4051-IND | draft study report | 2026-04-27 | 2026-04-25 | technical | 2026-05-08 | accepted with comments | 0 | 13
DL-00187 | 1 | WO-0033 | V-011 | PRJ-4051-IND | draft study report | 2026-04-27 | 2026-04-24 | technical | 2026-04-26 | accepted | 0 | 2
DL-00188 | 0 | WO-0047 | V-017 | PRJ-1107-CMC | certificate of analysis | 2026-04-28 | 2026-04-29 | QA | 2026-05-10 | accepted | 1 | 11
DL-00189 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-04-29 | 2026-04-25 | technical | 2026-04-29 | accepted | 0 | 4
DL-00190 | 0 | WO-0029 | V-010 | PRJ-4051-IND | draft study report | 2026-04-30 | 2026-05-12 | technical | 2026-05-14 | accepted | 12 | 2
DL-00191 | 0 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-05-01 | 2026-05-03 | technical | 2026-05-08 | accepted | 2 | 5
DL-00192 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-05-04 | 2026-05-01 | technical | 2026-05-08 | accepted | 0 | 7
DL-00193 | 1 | WO-0032 | V-011 | PRJ-DP07 | draft study report | 2026-05-04 | 2026-04-29 | technical | 2026-05-02 | accepted | 0 | 3
DL-00194 | 1 | WO-0041 | V-014 | PRJ-3318-TT | stability results | 2026-05-04 | 2026-05-04 | QA | 2026-05-11 | accepted | 0 | 7
DL-00195 | 1 | WO-0047 | V-017 | PRJ-1107-CMC | certificate of analysis | 2026-05-04 | 2026-04-29 | QA | 2026-05-02 | accepted | 0 | 3
DL-00196 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-05-05 | 2026-05-05 | finance | 2026-05-10 | accepted | 0 | 5
DL-00197 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | activity report for accrual | 2026-05-05 | 2026-05-03 | finance | 2026-05-05 | accepted | 0 | 2
DL-00198 | 1 | WO-0008 | V-002 | PRJ-2240-201 | activity report for accrual | 2026-05-05 | 2026-04-30 | finance | 2026-05-02 | accepted | 0 | 2
DL-00199 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-05-05 | 2026-05-01 | finance | 2026-05-18 | accepted | 0 | 17
DL-00200 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-05-05 | 2026-05-02 | finance | 2026-05-04 | accepted with comments | 0 | 2
DL-00201 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-05-05 | 2026-05-03 | finance | 2026-05-06 | accepted | 0 | 3
DL-00202 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-05-05 | 2026-05-05 | finance | 2026-05-07 | accepted | 0 | 2
DL-00203 |  | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-05-05 |  | finance |  | not received
DL-00204 | 1 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-05-05 | 2026-05-02 | finance | 2026-05-04 | accepted | 0 | 2
DL-00205 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-05-05 | 2026-04-30 | finance | 2026-05-01 | accepted | 0 | 1
DL-00206 | 1 | WO-0030 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-05-05 | 2026-04-30 | finance | 2026-05-03 | accepted | 0 | 3
DL-00207 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-05-05 | 2026-04-30 | finance | 2026-05-02 | accepted | 0 | 2
DL-00208 | 1 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-05-05 | 2026-05-03 | finance | 2026-05-05 | accepted | 0 | 2
DL-00209 | 0 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-05-05 | 2026-05-20 | finance | 2026-05-24 | accepted | 15 | 4
DL-00210 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-05-05 | 2026-05-01 | finance | 2026-05-06 | accepted | 0 | 5
DL-00211 | 0 | WO-0046 | V-016 | PRJ-4051-CMC | activity report for accrual | 2026-05-05 | 2026-05-07 | finance | 2026-05-09 | accepted | 2 | 2
DL-00212 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-05-08 | 2026-05-04 | technical | 2026-05-07 | accepted | 0 | 3
DL-00213 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-05-11 | 2026-05-06 | technical | 2026-05-07 | accepted | 0 | 1
DL-00214 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | monthly status report | 2026-05-11 | 2026-05-07 | technical | 2026-05-12 | accepted | 0 | 5
DL-00215 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-05-11 | 2026-05-10 | technical | 2026-05-14 | accepted | 0 | 4
DL-00216 | 1 | WO-0008 | V-002 | PRJ-2240-201 | monthly status report | 2026-05-11 | 2026-05-06 | technical | 2026-05-08 | accepted | 0 | 2
DL-00217 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-05-11 | 2026-05-06 | technical | 2026-05-07 | returned for revision | 0 | 1
DL-00218 | 1 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-05-11 | 2026-05-09 | technical | 2026-05-14 | accepted | 0 | 5
DL-00219 | 1 | WO-0019 | V-006 | PRJ-2240-201 | monthly status report | 2026-05-11 | 2026-05-08 | technical | 2026-05-11 | accepted with comments | 0 | 3
DL-00220 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-05-11 | 2026-05-08 | technical | 2026-05-13 | accepted | 0 | 5
DL-00221 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-05-11 | 2026-05-10 | technical | 2026-05-17 | accepted | 0 | 7
DL-00222 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-05-11 | 2026-05-07 | technical | 2026-05-17 | accepted | 0 | 10
DL-00223 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-05-11 | 2026-05-10 | technical | 2026-05-11 | accepted with comments | 0 | 1
DL-00224 | 0 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-05-11 | 2026-05-14 | technical | 2026-05-16 | accepted | 3 | 2
DL-00225 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-05-11 | 2026-05-08 | technical | 2026-05-12 | accepted | 0 | 4
DL-00226 | 0 | WO-0043 | V-015 | PRJ-BAPI | stability results | 2026-05-11 | 2026-05-19 | QA | 2026-06-06 | accepted | 8 | 18
DL-00227 | 1 | WO-0060 | V-031 | PRJ-4051-IND | monthly status report | 2026-05-11 | 2026-05-07 | technical | 2026-05-09 | accepted | 0 | 2
DL-00228 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-05-11 | 2026-05-11 | technical | 2026-05-17 | accepted | 0 | 6
DL-00229 | 1 | WO-0062 | V-033 | PRJ-2240-201 | draft study report | 2026-05-11 | 2026-05-07 | technical | 2026-05-10 | accepted | 0 | 3
DL-00230 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-05-11 | 2026-05-10 | technical | 2026-05-12 | accepted | 0 | 2
DL-00231 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | TFL draft | 2026-05-11 | 2026-05-09 | technical | 2026-05-11 | accepted | 0 | 2
DL-00232 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-05-11 | 2026-05-09 | technical | 2026-05-13 | accepted | 0 | 4
DL-00233 | 1 | WO-0068 | V-040 | PRJ-1107-C1 | monthly status report | 2026-05-11 | 2026-05-07 | technical | 2026-05-12 | accepted | 0 | 5
DL-00234 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-05-11 | 2026-05-07 | technical | 2026-05-11 | accepted | 0 | 4
DL-00235 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-05-13 | 2026-05-13 | technical | 2026-05-20 | accepted | 0 | 7
DL-00236 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-05-13 | 2026-05-12 | technical | 2026-05-15 | accepted | 0 | 3
DL-00237 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-05-15 | 2026-05-15 | technical | 2026-05-21 | accepted | 0 | 6
DL-00238 | 1 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-05-15 | 2026-05-12 | technical | 2026-05-19 | accepted | 0 | 7
DL-00239 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-05-18 | 2026-05-18 | technical | 2026-05-21 | accepted | 0 | 3
DL-00240 | 1 | WO-0043 | V-015 | PRJ-BAPI | stability results | 2026-05-19 | 2026-05-17 | QA | 2026-05-21 | accepted | 0 | 4
DL-00241 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-05-22 | 2026-05-18 | technical | 2026-05-22 | accepted | 0 | 4
DL-00242 | 1 | WO-0059 | V-030 | PRJ-1107 | final study report | 2026-05-22 | 2026-05-19 | QA | 2026-05-24 | accepted | 0 | 5
DL-00243 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-05-25 | 2026-05-24 | technical | 2026-05-27 | accepted with comments | 0 | 3
DL-00244 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | certificate of analysis | 2026-05-25 | 2026-05-20 | QA | 2026-05-31 | accepted | 0 | 11
DL-00245 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | certificate of analysis | 2026-05-25 | 2026-05-23 | QA | 2026-06-04 | accepted | 0 | 12
DL-00246 | 1 | WO-0062 | V-033 | PRJ-2240-201 | draft study report | 2026-05-26 | 2026-05-23 | technical | 2026-06-04 | accepted | 0 | 12
DL-00247 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-05-27 | 2026-05-22 | technical | 2026-05-26 | accepted with comments | 0 | 4
DL-00248 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-05-29 | 2026-05-26 | technical | 2026-05-28 | accepted with comments | 0 | 2
DL-00249 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-06-01 | 2026-05-28 | technical | 2026-05-30 | accepted | 0 | 2
DL-00250 | 0 | WO-0042 | V-014 | PRJ-4051-CMC | certificate of analysis | 2026-06-03 | 2026-06-07 | QA | 2026-06-15 | accepted with comments | 4 | 8
DL-00251 | 0 | WO-0042 | V-014 | PRJ-4051-CMC | executed batch record | 2026-06-03 | 2026-06-18 | QA | 2026-07-04 | accepted | 15 | 16
DL-00252 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-06 | accepted | 0 | 2
DL-00253 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | activity report for accrual | 2026-06-05 | 2026-06-01 | finance | 2026-06-04 | accepted | 0 | 3
DL-00254 | 1 | WO-0008 | V-002 | PRJ-2240-201 | activity report for accrual | 2026-06-05 | 2026-06-03 | finance | 2026-06-06 | accepted with comments | 0 | 3
DL-00255 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-06 | accepted | 0 | 2
DL-00256 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-08 | accepted | 0 | 4
DL-00257 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-06-05 | 2026-06-02 | technical | 2026-06-05 | accepted | 0 | 3
DL-00258 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-06-05 | 2026-06-01 | finance | 2026-06-05 | accepted | 0 | 4
DL-00259 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-06-05 | 2026-06-03 | finance | 2026-06-11 | accepted with comments | 0 | 8
DL-00260 | 1 | WO-0023 | V-008 | PRJ-1107-OLE | activity report for accrual | 2026-06-05 | 2026-06-03 | finance | 2026-06-06 | accepted | 0 | 3
DL-00261 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-06-05 | 2026-05-31 | finance | 2026-06-01 | returned for revision | 0 | 1
DL-00262 | 1 | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-09 | accepted | 0 | 5
DL-00263 | 1 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-06 | accepted | 0 | 2
DL-00264 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-06-05 | 2026-06-03 | finance | 2026-06-05 | accepted | 0 | 2
DL-00265 | 1 | WO-0030 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-06-05 | 2026-06-01 | finance | 2026-06-02 | accepted | 0 | 1
DL-00266 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-07 | accepted | 0 | 3
DL-00267 | 1 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-06-05 | 2026-06-03 | finance | 2026-06-16 | accepted with comments | 0 | 13
DL-00268 | 1 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-06-05 | 2026-06-02 | finance | 2026-06-04 | accepted | 0 | 2
DL-00269 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-06-05 | 2026-06-04 | finance | 2026-06-06 | accepted | 0 | 2
DL-00270 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | activity report for accrual | 2026-06-05 | 2026-06-03 | finance | 2026-06-12 | accepted with comments | 0 | 9
DL-00271 | 0 | WO-0046 | V-016 | PRJ-4051-CMC | activity report for accrual | 2026-06-05 | 2026-06-10 | finance | 2026-06-13 | accepted | 5 | 3
DL-00272 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | TFL draft | 2026-06-08 | 2026-06-03 | technical | 2026-06-05 | accepted | 0 | 2
DL-00273 | 1 | WO-0008 | V-002 | PRJ-2240-201 | TFL draft | 2026-06-08 | 2026-06-05 | technical | 2026-06-11 | accepted | 0 | 6
DL-00274 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-06-08 | 2026-06-08 | technical | 2026-06-16 | accepted | 0 | 8
DL-00275 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-06-08 | 2026-06-06 | technical | 2026-06-13 | accepted | 0 | 7
DL-00276 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | certificate of analysis | 2026-06-09 | 2026-06-07 | QA | 2026-06-13 | accepted with comments | 0 | 6
DL-00277 | 0 | WO-0059 | V-030 | PRJ-1107 | draft study report | 2026-06-09 | 2026-06-22 | technical | 2026-06-24 | accepted | 13 | 2
DL-00278 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-06-10 | 2026-06-10 | technical | 2026-06-17 | accepted | 0 | 7
DL-00279 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-06-10 | 2026-06-08 | technical | 2026-06-11 | accepted | 0 | 3
DL-00280 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | monthly status report | 2026-06-10 | 2026-06-06 | technical | 2026-06-10 | accepted | 0 | 4
DL-00281 | 1 | WO-0008 | V-002 | PRJ-2240-201 | monthly status report | 2026-06-10 | 2026-06-08 | technical | 2026-06-11 | accepted | 0 | 3
DL-00282 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-06-10 | 2026-06-06 | technical | 2026-06-08 | accepted | 0 | 2
DL-00283 | 1 | WO-0014 | V-004 | PRJ-1107-OLE | monthly status report | 2026-06-10 | 2026-06-08 | technical | 2026-06-11 | accepted | 0 | 3
DL-00284 | 1 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-06-10 | 2026-06-05 | technical | 2026-06-08 | accepted | 0 | 3
DL-00285 | 1 | WO-0018 | V-006 | PRJ-1107-OLE | monthly status report | 2026-06-10 | 2026-06-06 | technical | 2026-06-08 | accepted | 0 | 2
DL-00286 | 1 | WO-0019 | V-006 | PRJ-2240-201 | monthly status report | 2026-06-10 | 2026-06-10 | technical | 2026-06-15 | accepted | 0 | 5
DL-00287 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-06-10 | 2026-06-06 | technical | 2026-06-07 | accepted | 0 | 1
DL-00288 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-06-10 | 2026-06-09 | technical | 2026-06-11 | accepted | 0 | 2
DL-00289 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-06-10 | 2026-06-08 | technical | 2026-06-17 | accepted | 0 | 9
DL-00290 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-06-10 | 2026-06-05 | technical | 2026-06-08 | accepted | 0 | 3
DL-00291 | 1 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-06-10 | 2026-06-05 | technical | 2026-06-13 | accepted | 0 | 8
DL-00292 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-06-10 | 2026-06-07 | technical | 2026-06-08 | accepted | 0 | 1
DL-00293 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | certificate of analysis | 2026-06-10 | 2026-06-08 | QA | 2026-06-15 | accepted | 0 | 7
DL-00294 | 1 | WO-0060 | V-031 | PRJ-4051-IND | monthly status report | 2026-06-10 | 2026-06-06 | technical | 2026-06-09 | accepted | 0 | 3
DL-00295 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-06-10 | 2026-06-10 | technical | 2026-06-14 | accepted with comments | 0 | 4
DL-00296 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-06-10 | 2026-06-08 | technical | 2026-06-23 | accepted | 0 | 15
DL-00297 | 0 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-06-10 | 2026-06-14 | technical | 2026-06-17 | accepted | 4 | 3
DL-00298 | 1 | WO-0068 | V-040 | PRJ-1107-C1 | monthly status report | 2026-06-10 | 2026-06-09 | technical | 2026-06-13 | accepted | 0 | 4
DL-00299 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-06-10 | 2026-06-06 | technical | 2026-06-12 | accepted | 0 | 6
DL-00300 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-06-12 | 2026-06-07 | technical | 2026-06-12 | accepted | 0 | 5
DL-00301 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-06-12 | 2026-06-08 | technical | 2026-06-14 | returned for revision | 0 | 6
DL-00302 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-06-12 | 2026-06-08 | technical | 2026-06-12 | accepted | 0 | 4
DL-00303 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-06-15 | 2026-06-12 | technical | 2026-06-22 | accepted | 0 | 10
DL-00304 | 1 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-06-15 | 2026-06-11 | technical | 2026-06-17 | accepted | 0 | 6
DL-00305 | 1 | WO-0043 | V-015 | PRJ-BAPI | certificate of analysis | 2026-06-15 | 2026-06-10 | QA | 2026-06-14 | accepted with comments | 0 | 4
DL-00306 | 1 | WO-0041 | V-014 | PRJ-3318-TT | stability results | 2026-06-16 | 2026-06-13 | QA | 2026-06-16 | accepted with comments | 0 | 3
DL-00307 | 1 | WO-0033 | V-011 | PRJ-4051-IND | final study report | 2026-06-18 | 2026-06-14 | QA | 2026-06-17 | accepted | 0 | 3
DL-00308 | 1 | WO-0041 | V-014 | PRJ-3318-TT | certificate of analysis | 2026-06-18 | 2026-06-13 | QA | 2026-06-19 | accepted with comments | 0 | 6
DL-00309 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-06-19 | 2026-06-16 | technical | 2026-06-19 | accepted with comments | 0 | 3
DL-00310 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-06-22 | 2026-06-21 | technical | 2026-06-25 | accepted with comments | 0 | 4
DL-00311 | 0 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-06-22 | 2026-06-24 | technical | 2026-06-30 | accepted | 2 | 6
DL-00312 | 0 | WO-0030 | V-010 | PRJ-4051-IND | final study report | 2026-06-22 | 2026-07-14 | QA | 2026-07-17 | accepted | 22 | 3
DL-00313 | 1 | WO-0031 | V-010 | PRJ-DP07 | data transfer | 2026-06-22 | 2026-06-20 | technical | 2026-06-25 | accepted with comments | 0 | 5
DL-00314 | 1 | WO-0041 | V-014 | PRJ-3318-TT | executed batch record | 2026-06-22 | 2026-06-18 | QA | 2026-06-20 | accepted | 0 | 2
DL-00315 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | certificate of analysis | 2026-06-22 | 2026-06-21 | QA | 2026-06-27 | accepted | 0 | 6
DL-00316 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-06-24 | 2026-06-24 | technical | 2026-06-27 | accepted | 0 | 3
DL-00317 | 1 | WO-0030 | V-010 | PRJ-4051-IND | draft study report | 2026-06-25 | 2026-06-21 | technical | 2026-06-27 | accepted | 0 | 6
DL-00318 | 1 | WO-0041 | V-014 | PRJ-3318-TT | certificate of analysis | 2026-06-25 | 2026-06-24 | QA | 2026-07-01 | accepted with comments | 0 | 7
DL-00319 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-06-26 | 2026-06-22 | technical | 2026-06-27 | accepted with comments | 0 | 5
DL-00320 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-06-26 | 2026-06-22 | technical | 2026-06-24 | accepted with comments | 0 | 2
DL-00321 | 1 | WO-0031 | V-010 | PRJ-DP07 | draft study report | 2026-06-26 | 2026-06-21 | technical | 2026-07-03 | accepted | 0 | 12
DL-00322 | 1 | WO-0008 | V-002 | PRJ-2240-201 | TFL draft | 2026-06-29 | 2026-06-25 | technical | 2026-06-30 | accepted | 0 | 5
DL-00323 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-06-29 | 2026-06-25 | technical | 2026-07-01 | returned for revision | 0 | 6
DL-00324 | 1 | WO-0041 | V-014 | PRJ-3318-TT | executed batch record | 2026-06-29 | 2026-06-24 | QA | 2026-06-28 | returned for revision | 0 | 4
DL-00325 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | stability results | 2026-06-29 | 2026-06-25 | QA | 2026-06-30 | accepted | 0 | 5
DL-00326 | 0 | WO-0045 | V-016 | PRJ-1107-OLE | executed batch record | 2026-07-02 | 2026-07-20 | QA | 2026-07-25 | accepted | 18 | 5
DL-00327 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | certificate of analysis | 2026-07-02 | 2026-06-30 | QA | 2026-07-07 | accepted | 0 | 7
DL-00328 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-07-03 | 2026-07-03 | technical | 2026-07-08 | accepted | 0 | 5
DL-00329 | 1 | WO-0031 | V-010 | PRJ-DP07 | final study report | 2026-07-03 | 2026-07-01 | QA | 2026-07-21 | accepted with comments | 0 | 20
DL-00330 | 1 | WO-0043 | V-015 | PRJ-BAPI | stability results | 2026-07-03 | 2026-06-30 | QA | 2026-07-03 | accepted | 0 | 3
DL-00331 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-07-06 | 2026-07-02 | finance | 2026-07-03 | returned for revision | 0 | 1
DL-00332 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-09 | accepted | 0 | 3
DL-00333 | 1 | WO-0008 | V-002 | PRJ-2240-201 | activity report for accrual | 2026-07-06 | 2026-07-05 | finance | 2026-07-13 | accepted | 0 | 8
DL-00334 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-07-06 | 2026-07-02 | technical | 2026-07-12 | accepted | 0 | 10
DL-00335 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-07-06 | 2026-07-04 | finance | 2026-07-08 | accepted | 0 | 4
DL-00336 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-07-06 | 2026-07-06 | technical | 2026-07-15 | accepted | 0 | 9
DL-00337 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | activity report for accrual | 2026-07-06 | 2026-07-04 | finance | 2026-07-06 | accepted | 0 | 2
DL-00338 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-08 | accepted | 0 | 2
DL-00339 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-07-06 | 2026-07-01 | finance | 2026-07-04 | accepted | 0 | 3
DL-00340 | 1 | WO-0023 | V-008 | PRJ-1107-OLE | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-09 | accepted | 0 | 3
DL-00341 | 1 | WO-0023 | V-008 | PRJ-1107-OLE | certificate of analysis | 2026-07-06 | 2026-07-03 | QA | 2026-07-17 | accepted | 0 | 14
DL-00342 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-09 | accepted | 0 | 3
DL-00343 | 1 | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-07-06 | 2026-07-05 | finance | 2026-07-06 | returned for revision | 0 | 1
DL-00344 | 0 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-07-06 | 2026-07-10 | finance | 2026-07-29 | accepted | 4 | 19
DL-00345 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-08 | accepted | 0 | 2
DL-00346 | 1 | WO-0030 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-09 | accepted | 0 | 3
DL-00347 | 1 | WO-0031 | V-010 | PRJ-DP07 | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-10 | accepted | 0 | 4
DL-00348 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-07-06 | 2026-07-03 | finance | 2026-07-07 | accepted | 0 | 4
DL-00349 | 1 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-07-06 | 2026-07-05 | finance | 2026-07-11 | accepted | 0 | 6
DL-00350 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-13 | accepted | 0 | 7
DL-00351 | 0 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-07-06 | 2026-07-26 | finance | 2026-07-30 | accepted | 20 | 4
DL-00352 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-07-06 | 2026-07-06 | finance | 2026-07-07 | accepted | 0 | 1
DL-00353 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | activity report for accrual | 2026-07-06 | 2026-07-01 | finance | 2026-07-05 | accepted | 0 | 4
DL-00354 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | executed batch record | 2026-07-06 | 2026-07-01 | QA | 2026-07-11 | accepted | 0 | 10
DL-00355 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | activity report for accrual | 2026-07-06 | 2026-07-05 | finance | 2026-07-08 | accepted | 0 | 3
DL-00356 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-07-08 | 2026-07-04 | technical | 2026-07-06 | accepted | 0 | 2
DL-00357 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | certificate of analysis | 2026-07-09 | 2026-07-09 | QA | 2026-07-13 | accepted with comments | 0 | 4
DL-00358 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-07-10 | 2026-07-07 | technical | 2026-07-14 | accepted | 0 | 7
DL-00359 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-07-10 | 2026-07-08 | technical | 2026-07-15 | accepted | 0 | 7
DL-00360 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | monthly status report | 2026-07-10 | 2026-07-10 | technical | 2026-07-12 | accepted | 0 | 2
DL-00361 | 1 | WO-0008 | V-002 | PRJ-2240-201 | monthly status report | 2026-07-10 | 2026-07-06 | technical | 2026-07-10 | accepted with comments | 0 | 4
DL-00362 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-07-10 | 2026-07-07 | technical | 2026-07-18 | accepted | 0 | 11
DL-00363 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-07-10 | 2026-07-06 | technical | 2026-07-11 | accepted | 0 | 5
DL-00364 | 1 | WO-0014 | V-004 | PRJ-1107-OLE | monthly status report | 2026-07-10 | 2026-07-09 | technical | 2026-07-13 | accepted | 0 | 4
DL-00365 | 1 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-07-10 | 2026-07-07 | technical | 2026-07-11 | accepted | 0 | 4
DL-00366 | 1 | WO-0018 | V-006 | PRJ-1107-OLE | monthly status report | 2026-07-10 | 2026-07-06 | technical | 2026-07-14 | accepted | 0 | 8
DL-00367 | 1 | WO-0019 | V-006 | PRJ-2240-201 | monthly status report | 2026-07-10 | 2026-07-10 | technical | 2026-07-13 | accepted | 0 | 3
DL-00368 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-07-10 | 2026-07-09 | technical | 2026-07-18 | accepted | 0 | 9
DL-00369 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-07-10 | 2026-07-06 | technical | 2026-07-11 | accepted | 0 | 5
DL-00370 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-07-10 | 2026-07-10 | technical | 2026-07-15 | accepted | 0 | 5
DL-00371 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-07-10 | 2026-07-05 | technical | 2026-07-07 | accepted | 0 | 2
DL-00372 | 1 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-07-10 | 2026-07-06 | technical | 2026-07-12 | accepted | 0 | 6
DL-00373 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-07-10 | 2026-07-07 | technical | 2026-07-16 | accepted with comments | 0 | 9
DL-00374 | 1 | WO-0060 | V-031 | PRJ-4051-IND | monthly status report | 2026-07-10 | 2026-07-06 | technical | 2026-07-10 | accepted | 0 | 4
DL-00375 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-07-10 | 2026-07-08 | technical | 2026-07-11 | accepted with comments | 0 | 3
DL-00376 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-07-10 | 2026-07-06 | technical | 2026-07-10 | accepted | 0 | 4
DL-00377 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-07-10 | 2026-07-08 | technical | 2026-07-15 | accepted | 0 | 7
DL-00378 | 1 | WO-0068 | V-040 | PRJ-1107-C1 | monthly status report | 2026-07-10 | 2026-07-09 | technical | 2026-07-11 | accepted with comments | 0 | 2
DL-00379 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-07-10 | 2026-07-08 | technical | 2026-07-12 | accepted | 0 | 4
DL-00380 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-07-13 | 2026-07-13 | technical | 2026-07-23 | accepted with comments | 0 | 10
DL-00381 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-07-13 | 2026-07-10 | technical | 2026-07-21 | accepted | 0 | 11
DL-00382 | 0 | WO-0042 | V-014 | PRJ-4051-CMC | executed batch record | 2026-07-13 | 2026-07-26 | QA | 2026-07-31 | accepted | 13 | 5
DL-00383 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | stability results | 2026-07-13 | 2026-07-11 | QA | 2026-07-25 | accepted with comments | 0 | 14
DL-00384 | 1 | WO-0048 | V-017 | PRJ-4051-CMC | certificate of analysis | 2026-07-13 | 2026-07-12 | QA | 2026-07-20 | accepted | 0 | 8
DL-00385 | 1 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-07-14 | 2026-07-14 | technical | 2026-07-16 | accepted with comments | 0 | 2
DL-00386 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | TFL draft | 2026-07-15 | 2026-07-12 | technical | 2026-07-16 | accepted | 0 | 4
DL-00387 | 1 | WO-0008 | V-002 | PRJ-2240-201 | TFL draft | 2026-07-15 | 2026-07-11 | technical | 2026-07-13 | accepted | 0 | 2
DL-00388 | 0 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-07-17 | 2026-07-22 | technical | 2026-07-27 | accepted | 5 | 5
DL-00389 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | TFL draft | 2026-07-17 | 2026-07-16 | technical | 2026-07-19 | accepted | 0 | 3
DL-00390 | 1 | WO-0008 | V-002 | PRJ-2240-201 | data transfer | 2026-07-20 | 2026-07-18 | technical | 2026-07-20 | accepted with comments | 0 | 2
DL-00391 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-07-20 | 2026-07-16 | technical | 2026-07-20 | accepted | 0 | 4
DL-00392 | 0 | WO-0021 | V-008 | PRJ-1107-CMC | certificate of analysis | 2026-07-20 | 2026-07-28 | QA | 2026-08-05 | accepted with comments | 8 | 8
DL-00393 | 0 | WO-0031 | V-010 | PRJ-DP07 | data transfer | 2026-07-21 | 2026-07-23 | technical | 2026-07-26 | accepted | 2 | 3
DL-00394 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | executed batch record | 2026-07-21 | 2026-07-18 | QA | 2026-07-27 | accepted with comments | 0 | 9
DL-00395 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-07-22 | 2026-07-22 | technical | 2026-07-28 | accepted | 0 | 6
DL-00396 | 1 | WO-0069 | V-041 | PRJ-4051 | draft study report | 2026-07-23 | 2026-07-21 | technical | 2026-07-26 | accepted with comments | 0 | 5
DL-00397 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-07-24 | 2026-07-20 | technical | 2026-07-22 | accepted | 0 | 2
DL-00398 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-07-24 | 2026-07-20 | technical | 2026-08-05 | accepted | 0 | 16
DL-00399 | 1 | WO-0048 | V-017 | PRJ-4051-CMC | stability results | 2026-07-24 | 2026-07-22 | QA | 2026-07-28 | accepted | 0 | 6
DL-00400 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-07-27 | 2026-07-22 | technical | 2026-07-28 | accepted with comments | 0 | 6
DL-00401 | 1 | WO-0047 | V-017 | PRJ-1107-CMC | stability results | 2026-07-28 | 2026-07-24 | QA | 2026-07-26 | accepted | 0 | 2
DL-00402 | 0 | WO-0031 | V-010 | PRJ-DP07 | final study report | 2026-07-30 | 2026-08-04 | QA | 2026-08-08 | accepted | 5 | 4
DL-00403 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-07-31 | 2026-07-28 | technical | 2026-08-04 | accepted | 0 | 7
DL-00404 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-08-03 | 2026-08-02 | technical | 2026-08-06 | accepted | 0 | 4
DL-00405 | 1 | WO-0021 | V-008 | PRJ-1107-CMC | certificate of analysis | 2026-08-03 | 2026-07-31 | QA | 2026-08-05 | accepted | 0 | 5
DL-00406 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | stability results | 2026-08-03 | 2026-08-03 | QA | 2026-08-11 | accepted | 0 | 8
DL-00407 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | activity report for accrual | 2026-08-05 | 2026-08-04 | finance | 2026-08-07 | accepted | 0 | 3
DL-00408 | 0 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-08-05 | 2026-08-11 | technical | 2026-08-12 | accepted | 6 | 1
DL-00409 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | activity report for accrual | 2026-08-05 | 2026-08-04 | finance | 2026-08-07 | accepted | 0 | 3
DL-00410 | 0 | WO-0010 | V-003 | PRJ-1107-C1 | activity report for accrual | 2026-08-05 | 2026-08-10 | finance | 2026-08-16 | accepted | 5 | 6
DL-00411 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | activity report for accrual | 2026-08-05 | 2026-08-04 | finance | 2026-08-06 | accepted | 0 | 2
DL-00412 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | activity report for accrual | 2026-08-05 | 2026-07-31 | finance | 2026-08-01 | accepted | 0 | 1
DL-00413 | 0 | WO-0021 | V-008 | PRJ-1107-CMC | activity report for accrual | 2026-08-05 | 2026-08-09 | finance | 2026-08-11 | returned for revision | 4 | 2
DL-00414 | 1 | WO-0023 | V-008 | PRJ-1107-OLE | activity report for accrual | 2026-08-05 | 2026-08-01 | finance | 2026-08-04 | accepted with comments | 0 | 3
DL-00415 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | activity report for accrual | 2026-08-05 | 2026-07-31 | finance | 2026-08-03 | accepted | 0 | 3
DL-00416 | 1 | WO-0025 | V-009 | PRJ-4051-IND | activity report for accrual | 2026-08-05 | 2026-08-01 | finance | 2026-08-04 | accepted | 0 | 3
DL-00417 | 1 | WO-0027 | V-038 | PRJ-4051-IND | activity report for accrual | 2026-08-05 | 2026-08-03 | finance | 2026-08-06 | accepted | 0 | 3
DL-00418 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | activity report for accrual | 2026-08-05 | 2026-07-31 | finance | 2026-08-01 | accepted | 0 | 1
DL-00419 | 1 | WO-0030 | V-010 | PRJ-4051-IND | activity report for accrual | 2026-08-05 | 2026-08-04 | finance | 2026-08-06 | accepted | 0 | 2
DL-00420 | 1 | WO-0031 | V-010 | PRJ-DP07 | activity report for accrual | 2026-08-05 | 2026-08-05 | finance | 2026-08-18 | accepted with comments | 0 | 13
DL-00421 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | activity report for accrual | 2026-08-05 | 2026-08-04 | finance | 2026-08-06 | accepted | 0 | 2
DL-00422 | 1 | WO-0041 | V-014 | PRJ-3318-TT | activity report for accrual | 2026-08-05 | 2026-08-03 | finance | 2026-08-06 | accepted | 0 | 3
DL-00423 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | activity report for accrual | 2026-08-05 | 2026-07-31 | finance | 2026-08-04 | accepted | 0 | 4
DL-00424 | 1 | WO-0043 | V-015 | PRJ-BAPI | activity report for accrual | 2026-08-05 | 2026-08-03 | finance | 2026-08-06 | accepted | 0 | 3
DL-00425 | 1 | WO-0044 | V-016 | PRJ-1107-CMC | activity report for accrual | 2026-08-05 | 2026-08-02 | finance | 2026-08-03 | accepted | 0 | 1
DL-00426 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | activity report for accrual | 2026-08-05 | 2026-08-03 | finance | 2026-08-05 | accepted | 0 | 2
DL-00427 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | activity report for accrual | 2026-08-05 | 2026-08-02 | finance | 2026-08-04 | accepted with comments | 0 | 2
DL-00428 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-08-07 | 2026-08-02 | technical | 2026-08-09 | accepted | 0 | 7
DL-00429 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-08-07 | 2026-08-04 | technical | 2026-08-07 | accepted | 0 | 3
DL-00430 | 1 | WO-0071 | V-043 | PRJ-1107-C1 | TFL draft | 2026-08-07 | 2026-08-06 | technical | 2026-08-09 | accepted with comments | 0 | 3
DL-00431 | 1 | WO-0001 | V-001 | PRJ-1107-C1 | monthly status report | 2026-08-10 | 2026-08-07 | technical | 2026-08-10 | accepted with comments | 0 | 3
DL-00432 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | TFL draft | 2026-08-10 | 2026-08-05 | technical | 2026-08-08 | accepted | 0 | 3
DL-00433 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | monthly status report | 2026-08-10 | 2026-08-09 | technical | 2026-08-21 | accepted | 0 | 12
DL-00434 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-08-10 | 2026-08-09 | technical | 2026-08-20 | accepted with comments | 0 | 11
DL-00435 | 1 | WO-0013 | V-004 | PRJ-1107-C1 | monthly status report | 2026-08-10 | 2026-08-06 | technical | 2026-08-12 | accepted | 0 | 6
DL-00436 | 1 | WO-0014 | V-004 | PRJ-1107-OLE | monthly status report | 2026-08-10 | 2026-08-08 | technical | 2026-08-15 | accepted | 0 | 7
DL-00437 | 0 | WO-0017 | V-006 | PRJ-1107 | monthly status report | 2026-08-10 | 2026-08-16 | technical | 2026-08-18 | accepted | 6 | 2
DL-00438 | 0 | WO-0018 | V-006 | PRJ-1107-OLE | monthly status report | 2026-08-10 | 2026-08-20 | technical | 2026-08-23 | accepted | 10 | 3
DL-00439 | 1 | WO-0020 | V-007 | PRJ-1107-C1 | monthly status report | 2026-08-10 | 2026-08-09 | technical | 2026-08-12 | accepted | 0 | 3
DL-00440 | 0 | WO-0025 | V-009 | PRJ-4051-IND | final study report | 2026-08-10 | 2026-08-30 | QA | 2026-09-12 | accepted | 20 | 13
DL-00441 | 1 | WO-0028 | V-010 | PRJ-1107-C1 | data transfer | 2026-08-10 | 2026-08-06 | technical | 2026-08-10 | accepted | 0 | 4
DL-00442 | 1 | WO-0034 | V-012 | PRJ-DP07 | monthly status report | 2026-08-10 | 2026-08-09 | technical | 2026-08-13 | accepted | 0 | 4
DL-00443 | 1 | WO-0036 | V-012 | PRJ-DP09 | monthly status report | 2026-08-10 | 2026-08-09 | technical | 2026-08-10 | accepted with comments | 0 | 1
DL-00444 | 1 | WO-0037 | V-013 | PRJ-DP12 | monthly status report | 2026-08-10 | 2026-08-08 | technical | 2026-08-12 | accepted | 0 | 4
DL-00445 | 1 | WO-0038 | V-013 | PRJ-DP09 | monthly status report | 2026-08-10 | 2026-08-06 | technical | 2026-08-08 | accepted | 0 | 2
DL-00446 | 1 | WO-0060 | V-031 | PRJ-4051-IND | monthly status report | 2026-08-10 | 2026-08-10 | technical | 2026-08-12 | accepted | 0 | 2
DL-00447 | 1 | WO-0061 | V-031 | PRJ-1107 | monthly status report | 2026-08-10 | 2026-08-08 | technical | 2026-08-10 | accepted | 0 | 2
DL-00448 | 1 | WO-0065 | V-035 | PRJ-1107-C1 | monthly status report | 2026-08-10 | 2026-08-05 | technical | 2026-08-16 | accepted | 0 | 11
DL-00449 | 1 | WO-0067 | V-039 | PRJ-1107-C1 | monthly status report | 2026-08-10 | 2026-08-09 | technical | 2026-08-10 | accepted with comments | 0 | 1
DL-00450 | 1 | WO-0068 | V-040 | PRJ-1107-C1 | monthly status report | 2026-08-10 | 2026-08-07 | technical | 2026-08-14 | accepted | 0 | 7
DL-00451 | 1 | WO-0070 | V-042 | PRJ-SUPPORT | monthly status report | 2026-08-10 | 2026-08-07 | technical | 2026-08-10 | accepted | 0 | 3
DL-00452 | 1 | WO-0015 | V-005 | PRJ-1107-C1 | data transfer | 2026-08-11 | 2026-08-09 | technical | 2026-08-18 | accepted with comments | 0 | 9
DL-00453 | 1 | WO-0059 | V-030 | PRJ-1107 | final study report | 2026-08-11 | 2026-08-11 | QA | 2026-08-17 | accepted | 0 | 6
DL-00454 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | stability results | 2026-08-12 | 2026-08-10 | QA | 2026-08-14 | accepted | 0 | 4
DL-00455 | 1 | WO-0048 | V-017 | PRJ-4051-CMC | stability results | 2026-08-12 | 2026-08-12 | QA | 2026-08-14 | accepted with comments | 0 | 2
DL-00456 | 1 | WO-0030 | V-010 | PRJ-4051-IND | data transfer | 2026-08-13 | 2026-08-13 | technical | 2026-08-16 | accepted with comments | 0 | 3
DL-00457 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-08-14 | 2026-08-12 | technical | 2026-08-17 | accepted | 0 | 5
DL-00458 | 1 | WO-0041 | V-014 | PRJ-3318-TT | certificate of analysis | 2026-08-14 | 2026-08-11 | QA | 2026-08-19 | accepted with comments | 0 | 8
DL-00459 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-08-17 | 2026-08-15 | technical | 2026-08-22 | accepted | 0 | 7
DL-00460 | 1 | WO-0024 | V-008 | PRJ-3318-SUP | certificate of analysis | 2026-08-17 | 2026-08-14 | QA | 2026-08-18 | accepted | 0 | 4
DL-00461 | 1 | WO-0031 | V-010 | PRJ-DP07 | draft study report | 2026-08-17 | 2026-08-14 | technical | 2026-08-18 | returned for revision | 0 | 4
DL-00462 | 1 | WO-0042 | V-014 | PRJ-4051-CMC | certificate of analysis | 2026-08-17 | 2026-08-15 | QA | 2026-08-20 | accepted with comments | 0 | 5
DL-00463 | 1 | WO-0043 | V-015 | PRJ-BAPI | certificate of analysis | 2026-08-17 | 2026-08-12 | QA | 2026-08-17 | accepted | 0 | 5
DL-00464 | 0 | WO-0048 | V-017 | PRJ-4051-CMC | certificate of analysis | 2026-08-17 | 2026-08-26 | QA | 2026-09-02 | accepted with comments | 9 | 7
DL-00465 | 1 | WO-0048 | V-017 | PRJ-4051-CMC | certificate of analysis | 2026-08-17 | 2026-08-13 | QA | 2026-08-15 | accepted | 0 | 2
DL-00466 | 1 | WO-0023 | V-008 | PRJ-1107-OLE | certificate of analysis | 2026-08-18 | 2026-08-15 | QA | 2026-08-30 | accepted | 0 | 15
DL-00467 | 1 | WO-0025 | V-009 | PRJ-4051-IND | draft study report | 2026-08-18 | 2026-08-18 | technical | 2026-08-21 | accepted | 0 | 3
DL-00468 | 0 | WO-0001 | V-001 | PRJ-1107-C1 | data transfer | 2026-08-19 | 2026-08-21 | technical | 2026-08-25 | accepted | 2 | 4
DL-00469 | 1 | WO-0031 | V-010 | PRJ-DP07 | data transfer | 2026-08-20 | 2026-08-19 | technical | 2026-08-21 | accepted | 0 | 2
DL-00470 | 1 | WO-0007 | V-001 | PRJ-1107-OLE | data transfer | 2026-08-21 | 2026-08-20 | technical | 2026-08-25 | accepted | 0 | 5
DL-00471 | 1 | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-08-21 | 2026-08-19 | technical | 2026-08-23 | accepted | 0 | 4
DL-00472 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-08-24 | 2026-08-20 | technical | 2026-08-23 | accepted | 0 | 3
DL-00473 | 0 | WO-0027 | V-038 | PRJ-4051-IND | final study report | 2026-08-24 | 2026-09-16 | QA |  | under review | 23
DL-00474 | 1 | WO-0046 | V-016 | PRJ-4051-CMC | executed batch record | 2026-08-24 | 2026-08-24 | QA | 2026-08-28 | returned for revision | 0 | 4
DL-00475 | 1 | WO-0048 | V-017 | PRJ-4051-CMC | stability results | 2026-08-24 | 2026-08-23 | QA | 2026-09-08 | accepted | 0 | 16
DL-00476 | 1 | WO-0069 | V-041 | PRJ-4051 | draft study report | 2026-08-24 | 2026-08-23 | technical | 2026-08-27 | accepted with comments | 0 | 4
DL-00477 |  | WO-0059 | V-030 | PRJ-1107 | draft study report | 2026-08-25 |  | technical |  | not received
DL-00478 | 1 | WO-0066 | V-036 | PRJ-LCMS | final study report | 2026-08-25 | 2026-08-24 | QA | 2026-08-29 | accepted | 0 | 5
DL-00479 | 1 | WO-0063 | V-033 | PRJ-4051-IND | draft study report | 2026-08-26 | 2026-08-26 | technical | 2026-08-29 | returned for revision | 0 | 3
DL-00480 | 1 | WO-0063 | V-033 | PRJ-4051-IND | draft study report | 2026-08-26 | 2026-08-21 | technical | 2026-08-24 | accepted | 0 | 3
DL-00481 | 0 | WO-0028 | V-010 | PRJ-1107-C1 | final study report | 2026-08-27 | 2026-08-31 | QA | 2026-09-05 | accepted with comments | 4 | 5
DL-00482 | 1 | WO-0040 | V-014 | PRJ-3318-SUP | stability results | 2026-08-27 | 2026-08-22 | QA | 2026-08-25 | accepted with comments | 0 | 3
DL-00483 | 1 | WO-0045 | V-016 | PRJ-1107-OLE | certificate of analysis | 2026-08-27 | 2026-08-27 | QA | 2026-08-29 | accepted | 0 | 2
DL-00484 | 0 | WO-0063 | V-033 | PRJ-4051-IND | final study report | 2026-08-27 | 2026-09-08 | QA | 2026-09-12 | accepted | 12 | 4
DL-00485 | 0 | WO-0066 | V-036 | PRJ-LCMS | draft study report | 2026-08-27 | 2026-09-06 | technical | 2026-09-09 | accepted | 10 | 3
DL-00486 |  | WO-0012 | V-003 | PRJ-1107-OLE | data transfer | 2026-08-28 |  | technical |  | not received
DL-00487 | 1 | WO-0023 | V-008 | PRJ-1107-OLE | certificate of analysis | 2026-08-28 | 2026-08-27 | QA | 2026-09-04 | accepted | 0 | 8
DL-00488 |  | WO-0027 | V-038 | PRJ-4051-IND | draft study report | 2026-08-28 |  | technical |  | not received
DL-00489 | 1 | WO-0063 | V-033 | PRJ-4051-IND | final study report | 2026-08-28 | 2026-08-27 | QA | 2026-09-04 | accepted | 0 | 8
DL-00490 | 1 | WO-0010 | V-003 | PRJ-1107-C1 | data transfer | 2026-08-31 | 2026-08-27 | technical | 2026-08-30 | accepted | 0 | 3
DL-00491 | 1 | WO-0066 | V-036 | PRJ-LCMS | data transfer | 2026-08-31 | 2026-08-31 | technical | 2026-09-05 | accepted | 0 | 5
DL-00492 | 1 | WO-0066 | V-036 | PRJ-LCMS | draft study report | 2026-08-31 | 2026-08-29 | technical | 2026-09-13 | accepted | 0 | 15
DL-00493 | 1 | WO-0066 | V-036 | PRJ-LCMS | final study report | 2026-08-31 | 2026-08-28 | QA | 2026-09-02 | accepted | 0 | 5