## Slide 1
Patient Flow Pilot — September Checkpoint
West Capacity & Patient Flow Program. Operating committee, September 17, 2026. Pilot units: 4 West, 5 West and Telemetry at Medical Center West, live since March 2, 2026.
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 1

## Slide 2
Where we said we would be
January charter aim: 30% of pilot-unit discharges before 11 a.m. by August 31, with lower ED boarding for pilot units as a secondary aim.
Pilot live March 2 as planned
EHR next-day discharge list live April 20 (paper list until then)
90-day review held June 4
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 2
Notes: The EHR list was three weeks late because of the IS build queue.

## Slide 3
What changed on the units
Expected discharge date set by day 2 on most admissions
Next-day discharge list agreed at 3 p.m. on each unit
9:30 huddle now reports planned early discharges and barriers
EVS notified when the patient leaves rather than at EHR release
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 3

## Slide 4
Discharge timing results
Share of discharges before 11 a.m., three pilot units combined: 14.3% before the pilot (February 1 to March 1, 419 discharges) and 27.1% from March 2 to August 31 (2,793 discharges).
Monthly: 25.0% March, 29.7% April, 23.4% May, 28.2% June, 27.4% July, 28.3% August
Target of 30% not reached in any month
Comparison units (Progressive Care, 6 West) did not change
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 4
Notes: The February baseline is one month and noisy; Telemetry started lowest.

## Slide 5
Boarding and season
ED boarding hours for pilot units fell from about 13.4 per unit-day in February to 9.6 in June to August. Other West units fell by a similar share, from 4.4 to 3.0.
West boarding totaled 1,741 hours in February, 1,150 in June and 1,489 in August
West census rose again in August
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 5
Notes: Do not claim a boarding effect. The drop matches the seasonal drop on non-pilot units.

## Slide 6
Census context, February to August
Monthly census-days for all 12 units at both hospitals, including observation patients.
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 6
Notes: Chart covers both hospitals; West alone rose to 81.8% occupancy in August.

## Slide 7
Census context, February to August · patients
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 7
Chart: 
| 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08
midnight_census | 6369 | 6683 | 6272 | 6620 | 6468 | 6751 | 7150

## Slide 8
What we cannot conclude yet
Whether earlier discharges reduced boarding once season is accounted for
Whether the gain will hold during winter census
Effect on readmissions: no concerns logged, but the data are thin
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 8

## Slide 9
Recommendation for October
Continue the pilot unchanged through December 2026
Spread to Progressive Care and 6 West in January 2027 if approved
Keep the 30% target
Add a 10 a.m. discharge-readiness call between case management and hospitalists
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 9
Notes: Decision requested at the October 15 operating committee.

## Slide 10
Next steps
Decision Support to add a same-month-last-year boarding comparison by unit
Unit leads to prepare the spread training plan
Report winter results in February 2027
Tallowbrook Health | Performance Improvement Office | 2026-09-17 | 10