## Read me
Improvement Portfolio Milestone Tracker
Tallowbrook Health
Effective date | 2026-09-18
Purpose | Track baseline and forecast or actual dates and status for portfolio milestones.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Milestones for the improvement portfolio, as of September 18, 2026. Maintained by Hannah Mercer, Director, Performance Improvement, and updated by project leads before each monthly portfolio check-in.
Contents | One row per milestone (34 rows) with project, milestone, owner, baseline date, actual or forecast date, status and comment.
Coverage | The four active projects (West Capacity & Patient Flow Program, Central Staffing Office Phase 2, Clinical Engineering CMMS Consolidation and the Fort Bend Fourth-Floor Options Study) and the Outpatient Imaging Scheduling Consolidation, which closed in April 2025 and is kept for reference.
Definitions and cautions | Baseline date: the date in the approved project charter or the last approved re-baseline.
Definitions and cautions | Actual or forecast date: the completion date for completed milestones; otherwise the owner's current forecast. Dates after September 18, 2026 are forecasts.
Definitions and cautions | Status: Complete; On track; At risk (baseline date not yet reached, but the forecast has moved because of a dependency); Late (baseline date has passed without completion); Not started; Pending decision (depends on a leadership decision not yet made).
Definitions and cautions | One Central Staffing Phase 1 milestone is kept for reference and is not part of Phase 2 scope.
Definitions and cautions | Milestone dates are not a measure of project benefit; see the project reports for results.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Improvement Portfolio Milestones | Row count | records |  |  | 34 | 2024-10-01 | 2026-09-18

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Improvement Portfolio Milestones | milestone_id | Row identifier |  | id
Improvement Portfolio Milestones | milestone_key | Milestone code |  | category
Improvement Portfolio Milestones | project | Project |  | category
Improvement Portfolio Milestones | milestone | Milestone |  | category
Improvement Portfolio Milestones | owner | Owner |  | category
Improvement Portfolio Milestones | baseline_date | Baseline date |  | category
Improvement Portfolio Milestones | forecast_or_actual_date | Actual date, or forecast if not complete |  | category
Improvement Portfolio Milestones | status | Status |  | category
Improvement Portfolio Milestones | comment | Comment |  | category

## Data 1
milestone_id | milestone_key | project | milestone | owner | baseline_date | forecast_or_actual_date | status | comment
project_milestones-000001 | MS-01 | Outpatient Imaging Scheduling Consolidation | Charter approved | Luis Carrillo | 2024-10-07 | 2024-10-07 | Complete
project_milestones-000002 | MS-02 | Outpatient Imaging Scheduling Consolidation | Pavilion MRI and CT scheduling moved to central scheduling | Luis Carrillo | 2024-12-02 | 2024-12-09 | Complete | One-week slip for scheduler training
project_milestones-000003 | MS-03 | Outpatient Imaging Scheduling Consolidation | Stafford imaging scheduling moved | Luis Carrillo | 2025-02-03 | 2025-02-17 | Complete | Phone tree change waited on telecom vendor
project_milestones-000004 | MS-04 | Outpatient Imaging Scheduling Consolidation | Ultrasound and mammography scheduling moved | Luis Carrillo | 2025-03-03 | 2025-03-10 | Complete
project_milestones-000005 | MS-05 | Outpatient Imaging Scheduling Consolidation | Project closeout | Hannah Mercer | 2025-04-15 | 2025-04-18 | Complete | Therapy scheduling deferred to FY2026
project_milestones-000006 | MS-06 | West Capacity & Patient Flow Program | Charter approved | Hannah Mercer | 2026-01-28 | 2026-01-28 | Complete
project_milestones-000007 | MS-07 | West Capacity & Patient Flow Program | Baseline data pull (Oct 2025-Jan 2026) | Priya Raman | 2026-02-20 | 2026-02-24 | Complete
project_milestones-000008 | MS-08 | West Capacity & Patient Flow Program | Pilot go-live on 4 West, 5 West and Telemetry | Aaron Foster | 2026-03-02 | 2026-03-02 | Complete
project_milestones-000009 | MS-09 | West Capacity & Patient Flow Program | Next-day discharge list built in EHR | Arjun Mehta | 2026-03-30 | 2026-04-20 | Complete | EHR build queue delay; paper list used until then
project_milestones-000010 | MS-10 | West Capacity & Patient Flow Program | 90-day pilot review | Hannah Mercer | 2026-06-01 | 2026-06-04 | Complete
project_milestones-000011 | MS-11 | West Capacity & Patient Flow Program | Summer evaluation and checkpoint | Hannah Mercer | 2026-09-15 | 2026-09-17 | Complete | Season confounds boarding comparison
project_milestones-000012 | MS-12 | West Capacity & Patient Flow Program | Spread decision at operating committee | Victor Salinas | 2026-10-15 | 2026-10-15 | On track
project_milestones-000013 | MS-13 | West Capacity & Patient Flow Program | Spread wave 1 (if approved) | Aaron Foster | 2026-12-01 | 2027-01-11 | Pending decision | Holiday census period avoided
project_milestones-000014 | MS-14 | Central Staffing Office Phase 2 | Phase 1 go-live at Medical Center West | Tamika Greer | 2025-10-20 | 2025-10-20 | Complete | Phase 1 milestone kept for reference
project_milestones-000015 | MS-15 | Central Staffing Office Phase 2 | Phase 2 kickoff | Tamika Greer | 2026-01-05 | 2026-01-05 | Complete
project_milestones-000016 | MS-16 | Central Staffing Office Phase 2 | Hospital Fort Bend joins CSO | Tamika Greer | 2026-02-16 | 2026-02-16 | Complete
project_milestones-000017 | MS-17 | Central Staffing Office Phase 2 | Float pool reaches 45 RN FTEs | Tamika Greer | 2026-06-30 | 2026-07-12 | Complete
project_milestones-000018 | MS-18 | Central Staffing Office Phase 2 | Self-scheduling configuration complete | Arjun Mehta | 2026-08-14 | 2026-09-25 | Late | WFS module configuration about six weeks behind
project_milestones-000019 | MS-19 | Central Staffing Office Phase 2 | Outpatient sites onboarded to CSO | Farah Siddiqui | 2026-08-31 | 2026-10-05 | Late | Sequenced after self-scheduling
project_milestones-000020 | MS-20 | Central Staffing Office Phase 2 | Self-scheduling pilot on two units | Tamika Greer | 2026-10-01 | 2026-11-16 | At risk | Depends on configuration
project_milestones-000021 | MS-21 | Central Staffing Office Phase 2 | Float pool reaches 52 RN FTEs | Tamika Greer | 2027-03-31 | 2027-03-31 | On track | 47 filled at end of August
project_milestones-000022 | MS-22 | Central Staffing Office Phase 2 | Phase 2 close | Hannah Mercer | 2027-03-31 | 2027-03-31 | On track
project_milestones-000023 | MS-23 | Clinical Engineering CMMS Consolidation | Business case approved | Samuel Ibekwe | 2026-06-24 | 2026-06-24 | Complete
project_milestones-000024 | MS-24 | Clinical Engineering CMMS Consolidation | Data cleanup started | Samuel Ibekwe | 2026-07-06 | 2026-07-06 | Complete
project_milestones-000025 | MS-25 | Clinical Engineering CMMS Consolidation | Requirements review | Samuel Ibekwe | 2026-09-16 | 2026-09-16 | Complete | Two open decisions carried forward
project_milestones-000026 | MS-26 | Clinical Engineering CMMS Consolidation | Asset record reconciliation complete | Samuel Ibekwe | 2026-10-30 | 2026-10-30 | On track
project_milestones-000027 | MS-27 | Clinical Engineering CMMS Consolidation | Configuration and testing complete | Arjun Mehta | 2026-12-18 | 2026-12-18 | Not started
project_milestones-000028 | MS-28 | Clinical Engineering CMMS Consolidation | Legacy record migration starts | Samuel Ibekwe | 2027-01-11 | 2027-01-11 | Not started
project_milestones-000029 | MS-29 | Clinical Engineering CMMS Consolidation | Legacy CE CMMS retired | Arjun Mehta | 2027-04-30 | 2027-04-30 | Not started
project_milestones-000030 | MS-30 | Fort Bend Fourth-Floor Options Study | Options study kickoff | Meredith Cole | 2026-04-15 | 2026-04-20 | Complete
project_milestones-000031 | MS-31 | Fort Bend Fourth-Floor Options Study | Demand projection refresh | Meredith Cole | 2026-07-31 | 2026-08-05 | Complete
project_milestones-000032 | MS-32 | Fort Bend Fourth-Floor Options Study | Preliminary cost estimates | Kenneth Duhon | 2026-08-01 | 2026-08-01 | Complete | Order-of-magnitude estimates
project_milestones-000033 | MS-33 | Fort Bend Fourth-Floor Options Study | Executive options review | Janelle Brooks | 2026-10-06 | 2026-10-06 | On track
project_milestones-000034 | MS-34 | Fort Bend Fourth-Floor Options Study | Board decision in FY2028 capital plan | Dana Whitfield | 2027-02-18 | 2027-02-18 | On track