## Slide 1
Architecture Review Board — FY2027 Integration Roadmap
Architecture review board, August 12, 2026. Presented by Arjun Mehta, Vice President and Chief Information Officer. Planned FY2027 integration changes, their order and dependencies.
Tallowbrook Health | Information Services | 2026-08-12 | 1

## Slide 2
Four changes for FY2027
CMMS consolidation: move legacy clinical engineering records into the enterprise CMMS
Automated surgery center case feed to replace the monthly file
WFS self-scheduling for Central Staffing Phase 2
Supply cabinet interface upgrade
Tallowbrook Health | Information Services | 2026-08-12 | 2
Notes: The board reviews integration changes and new applications monthly; today's ask is agreement on sequence.

## Slide 3
Where we start from
EDW loads run nightly from 1:00 to 5:30 a.m. Two feeds are still manual or monthly: the surgery center sends a case summary file each month and the legacy CE CMMS is exported by hand each month.
Both gaps delay reporting by up to a month
Both are addressed by this roadmap
Tallowbrook Health | Information Services | 2026-08-12 | 3

## Slide 4
CMMS consolidation
Approved by the executive team in June 2026. Data cleanup July to October 2026; legacy record migration January to April 2027.
Integration work: retire the manual export; add clinical engineering work order types to the weekly EDW extract
Legacy server can be retired after parallel running
Tallowbrook Health | Information Services | 2026-08-12 | 4

## Slide 5
Surgery center case feed
Replace the monthly case summary file with a nightly flat-file extract from the surgery center practice-management system through the integration engine.
Needs agreement from the surgery center board on data sharing under the services agreement
Target: build in Q4 FY2027 (April to June 2027), after the CMMS migration
Tallowbrook Health | Information Services | 2026-08-12 | 5

## Slide 6
WFS self-scheduling
Central Staffing Phase 2 started in January 2026, and Hospital Fort Bend units have requested float staff through the office since February 16. Self-scheduling is the next WFS change and affects the nightly scheduled-hours feed.
Configuration and testing in Q2 FY2027
No change to the payroll interface
Tallowbrook Health | Information Services | 2026-08-12 | 6

## Slide 7
Supply cabinet interface
Upgrade the interface between point-of-use cabinets and the ERP to the vendor's current version before support for the old version ends. Lowest dependency on the others; can run in Q1 FY2027.
Tallowbrook Health | Information Services | 2026-08-12 | 7

## Slide 8
Proposed sequence
Q1 (Jul-Sep): supply cabinet interface; CMMS data cleanup
Q2 (Oct-Dec): WFS self-scheduling; CMMS cleanup completes in October
Q3 (Jan-Mar): CMMS legacy migration
Q4 (Apr-Jun): CMMS migration completes in April; surgery center feed built and live; legacy CMMS server retired
Tallowbrook Health | Information Services | 2026-08-12 | 8
Notes: The integration team cannot carry the CMMS migration and a second large build in the same quarter.

## Slide 9
Decisions requested
Agree the sequence above
Confirm the surgery center feed can wait until Q4
Bring each change back to the board for design approval before build
Tallowbrook Health | Information Services | 2026-08-12 | 9