## Slide 1
Outpatient Imaging Scheduling Consolidation — Closeout Review
Project closeout. Ambulatory leadership and sponsors, April 18, 2025. Outpatient imaging scheduling for the Outpatient Pavilion West and Imaging & Therapy Stafford moved from site front desks to central scheduling.
Tallowbrook Health | Patient Access & Central Scheduling | 2025-04-18 | 1

## Slide 2
Objectives
One phone number and one team for outpatient imaging
Consistent prep calls and reminders
Weekly access measures for every imaging schedule
Front desks focused on check-in and registration
Tallowbrook Health | Patient Access & Central Scheduling | 2025-04-18 | 2

## Slide 3
What moved and when
Oct 2024: charter approved
Dec 9, 2024: Pavilion MRI and CT (one week late for scheduler training)
Feb 17, 2025: Stafford imaging (two weeks late; phone tree change waited on telecom vendor)
Mar 10, 2025: ultrasound and mammography at both sites
Schedulers now sit at the System Service Center in Stafford
Tallowbrook Health | Patient Access & Central Scheduling | 2025-04-18 | 3
Notes: All modalities live one to two weeks behind baseline dates.

## Slide 4
Results
All imaging orders for both sites now enter one work queue
Reminders at 72 and 24 hours are automated for every modality
Schedulers call every patient whose exam needs preparation
Slots offered, booked and completed plus 3NA reported weekly from April
Tallowbrook Health | Patient Access & Central Scheduling | 2025-04-18 | 4
Notes: 3NA = third-next-available appointment. Baseline 3NA before consolidation was not measured consistently, so we are not claiming an improvement number.

## Slide 5
What we learned
Train schedulers on modality prep rules before go-live, not during
Telecom changes need a four-week lead time
Site staff need a clear escalation path for walk-in patients
Referring offices want one fax number and one portal queue
Tallowbrook Health | Patient Access & Central Scheduling | 2025-04-18 | 5

## Slide 6
Open items and handoffs
Outpatient therapy scheduling to follow in FY2026 (Ambulatory Services)
Standard work document to be revised to v2.1 by June (Patient Access)
Pavilion and Stafford front desk staffing review (site managers)
Weekly access dashboard handed to Decision Support
Tallowbrook Health | Patient Access & Central Scheduling | 2025-04-18 | 6
Notes: Project closed; remaining items owned by operations.