## Read me
Capital Project Register and Monthly Spend, 2026
Sedgewater Energy Holdings
Effective date | 2026-09-14
Purpose | List every 2026 capital project with budget, forecast, actual and in-service dates, plus monthly actuals.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Capital project register for 2026 with monthly actual spend by project from January to August, prepared by Capital Portfolio after the August close. Budget, forecast and in-service dates reflect the September 2026 forecast.
Sheets | Data 1 - project register: 2026 budget, forecast and actual to date, total budget, program, business, district, stage, sponsor and planned and forecast in-service dates.
Sheets | Data 2 - monthly actuals by project, January to August 2026.
Sheets | Summary - formula totals of each numeric column.
Headline figures | The 2026 capital budget is $1,120 million across 152 projects. January to August actual spend was $683.0 million (61% of budget) and the September forecast is $1,108 million.
Headline figures | By business (budget / actual / forecast): Electric $930 million / $570.4 million / $920 million; Gas $150 million / $92.8 million / $150 million; Shared $40 million / $19.8 million / $38 million. Monthly spend rose from $68.6 million in January to $109.6 million in August.
Largest programs | Growth - new service $248 million; Transmission $142 million; Growth - substation and feeder $131 million; Reliability - distribution $118 million; Gas - pipe replacement $78 million; Resiliency - pole replacement $62 million.
Resiliency programs | Resiliency programs have a 2026 budget of $196 million; $109.0 million was spent to August and the forecast is $180 million, mainly because strategic undergrounding is forecast at $26 million against a $42 million budget.
Schedule | 37 of 152 projects forecast in-service dates later than planned; 5 of them are undergrounding projects. Two undergrounding projects show forecast in-service dates earlier than baseline after their scope was reduced in July 2026.
Selected projects | CP-26-050 Harbor North 138 kV substation and feeders (Design): $6.5 million in 2026 for design and long-lead equipment of an estimated $85 million; planned in service December 15, 2028.
Selected projects | CP-26-085 Next-generation meter pilot (Construct): $14.8 million in 2026 of a $16.5 million total; forecast in service moved from December 18, 2026 to January 29, 2027.
Selected projects | CP-26-096 Work management system upgrade, phase 0 (Initiate): $1.2 million in 2026.
Stages and approvals | Projects move through Initiate, Design, Construct, In service and Closeout. Projects above $50 million need board approval.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Capital project register, 2026 (snapshot 2026-08-31) | budget_2026_usd | USD | 1120000000 | 7368421.0526 | 152 | 2026-01-01 | 2026-08-31
Capital project register, 2026 (snapshot 2026-08-31) | forecast_2026_usd | USD | 1108000000 | 7289473.6842 | 152 | 2026-01-01 | 2026-08-31
Capital project register, 2026 (snapshot 2026-08-31) | actual_ytd_usd | USD | 683000000 | 4493421.0526 | 152 | 2026-01-01 | 2026-08-31
Capital project register, 2026 (snapshot 2026-08-31) | total_budget_usd | USD | 2157100000 | 14191447.3684 | 152 | 2026-01-01 | 2026-08-31
Capital actuals by project and month, Jan-Aug 2026 | actual_usd | USD | 683000000 | 561677.6316 | 1216 | 2026-01-01 | 2026-08-31

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Capital project register, 2026 (snapshot 2026-08-31) | project_code | CP-26-001 |  | id
Capital project register, 2026 (snapshot 2026-08-31) | budget_2026_usd | Approved 2026 budget | USD | number
Capital project register, 2026 (snapshot 2026-08-31) | forecast_2026_usd | Current 2026 forecast | USD | number
Capital project register, 2026 (snapshot 2026-08-31) | actual_ytd_usd | Actual Jan-Aug 2026 | USD | number
Capital project register, 2026 (snapshot 2026-08-31) | total_budget_usd | Total project budget | USD | number
Capital project register, 2026 (snapshot 2026-08-31) | project_name | Name |  | category
Capital project register, 2026 (snapshot 2026-08-31) | program | Program |  | category
Capital project register, 2026 (snapshot 2026-08-31) | business | Business |  | category
Capital project register, 2026 (snapshot 2026-08-31) | district | District |  | category
Capital project register, 2026 (snapshot 2026-08-31) | stage | Stage |  | category
Capital project register, 2026 (snapshot 2026-08-31) | sponsor | Sponsor (role holder) |  | category
Capital project register, 2026 (snapshot 2026-08-31) | planned_in_service | Baseline in-service (ISO date string; future dates allowed) |  | category
Capital project register, 2026 (snapshot 2026-08-31) | forecast_in_service | Forecast in-service (ISO date string) |  | category
Capital actuals by project and month, Jan-Aug 2026 | record_id | CM-000001 |  | id
Capital actuals by project and month, Jan-Aug 2026 | actual_usd | Actual spend | USD | number
Capital actuals by project and month, Jan-Aug 2026 | project_code | Project (FK) |  | category
Capital actuals by project and month, Jan-Aug 2026 | program | Program (copied) |  | category
Capital actuals by project and month, Jan-Aug 2026 | month_start | Month |  | date

## Data 1
project_code | budget_2026_usd | forecast_2026_usd | actual_ytd_usd | total_budget_usd | project_name | program | business | district | stage | sponsor | planned_in_service | forecast_in_service
CP-26-001 | 11758241 | 12298766 | 8115682 | 19700000 | Pole replacement - Systemwide program 1 | Resiliency - pole replacement | Electric | Systemwide | In service | Colin Marsh | 2026-06-21 | 2026-06-21
CP-26-002 | 2235473 | 2396580 | 1300483 | 5300000 | Pole replacement - Crossroads package 2 | Resiliency - pole replacement | Electric | Crossroads | Construct | Colin Marsh | 2026-09-30 | 2026-09-30
CP-26-003 | 17768954 | 17425486 | 9880650 | 37100000 | Pole replacement - Crossroads phase 1 3 | Resiliency - pole replacement | Electric | Crossroads | Construct | Colin Marsh | 2027-04-01 | 2027-04-01
CP-26-004 | 2111859 | 2044966 | 1835831 | 4800000 | Pole replacement - Bayou phase 2 4 | Resiliency - pole replacement | Electric | Bayou | In service | Colin Marsh | 2026-03-17 | 2026-03-17
CP-26-005 | 3213095 | 3274862 | 2114623 | 3900000 | Pole replacement - Prairie blanket 5 | Resiliency - pole replacement | Electric | Prairie | In service | Colin Marsh | 2026-01-23 | 2026-01-23
CP-26-006 | 1274626 | 1319112 | 614821 | 2900000 | Pole replacement - Systemwide project 6 | Resiliency - pole replacement | Electric | Systemwide | Design | Colin Marsh | 2027-06-27 | 2027-06-27
CP-26-007 | 6048743 | 5558545 | 3971975 | 11000000 | Pole replacement - Bayou program 7 | Resiliency - pole replacement | Electric | Bayou | Design | Colin Marsh | 2027-12-29 | 2028-06-26
CP-26-008 | 17589009 | 17681683 | 16165935 | 22500000 | Pole replacement - Prairie package 8 | Resiliency - pole replacement | Electric | Prairie | Design | Colin Marsh | 2028-05-08 | 2028-05-08
CP-26-009 | 6092566 | 5472647 | 5221284 | 11900000 | Automation - Bayou program 1 | Resiliency - automation | Electric | Bayou | Construct | Colin Marsh | 2026-05-21 | 2026-09-18
CP-26-010 | 3883191 | 3727786 | 1807579 | 6500000 | Automation - Harbor package 2 | Resiliency - automation | Electric | Harbor | Design | Colin Marsh | 2026-09-24 | 2026-09-24
CP-26-011 | 1117272 | 1144406 | 497598 | 2700000 | Automation - Bayou phase 1 3 | Resiliency - automation | Electric | Bayou | Construct | Colin Marsh | 2026-11-29 | 2026-11-29
CP-26-012 | 12361972 | 13136973 | 7272667 | 29900000 | Automation - Prairie phase 2 4 | Resiliency - automation | Electric | Prairie | Design | Colin Marsh | 2028-04-26 | 2028-04-26
CP-26-013 | 2927462 | 3157867 | 2354169 | 5200000 | Automation - Prairie blanket 5 | Resiliency - automation | Electric | Prairie | Construct | Colin Marsh | 2028-05-13 | 2028-05-13
CP-26-014 | 7617537 | 7360321 | 4646703 | 17300000 | Automation - Harbor project 6 | Resiliency - automation | Electric | Harbor | Closeout | Colin Marsh | 2026-06-26 | 2026-06-26
CP-26-015 | 11709441 | 7012066 | 3387792 | 25900000 | Undergrounding - Harbor program 1 | Resiliency - undergrounding | Electric | Harbor | Construct | Colin Marsh | 2027-12-08 | 2028-04-06
CP-26-016 | 1943200 | 1276990 | 744094 | 4300000 | Undergrounding - Crossroads package 2 | Resiliency - undergrounding | Electric | Crossroads | Design | Colin Marsh | 2028-04-11 | 2028-01-27
CP-26-017 | 7271732 | 4835443 | 1772940 | 14100000 | Undergrounding - Prairie phase 1 3 | Resiliency - undergrounding | Electric | Prairie | Design | Colin Marsh | 2026-06-05 | 2026-10-03
CP-26-018 | 2081676 | 1336332 | 723594 | 5000000 | Undergrounding - Bayou phase 2 4 | Resiliency - undergrounding | Electric | Bayou | Design | Colin Marsh | 2028-07-10 | 2028-05-26
CP-26-019 | 9644407 | 5787785 | 3473568 | 23700000 | Undergrounding - Bayou blanket 5 | Resiliency - undergrounding | Electric | Bayou | Construct | Colin Marsh | 2027-05-27 | 2027-11-23
CP-26-020 | 6977290 | 4184463 | 2466642 | 12700000 | Undergrounding - Crossroads project 6 | Resiliency - undergrounding | Electric | Crossroads | Construct | Colin Marsh | 2028-05-01 | 2028-09-28
CP-26-021 | 2372254 | 1566921 | 831370 | 6000000 | Undergrounding - Prairie program 7 | Resiliency - undergrounding | Electric | Prairie | Construct | Colin Marsh | 2026-11-03 | 2027-03-03
CP-26-022 | 8961840 | 9036060 | 2722499 | 16300000 | Substation flood mitigation - Prairie program 1 | Resiliency - substation flood mitigation | Electric | Prairie | Construct | Colin Marsh | 2027-10-03 | 2027-10-03
CP-26-023 | 2953678 | 2685622 | 1508369 | 7300000 | Substation flood mitigation - Systemwide package 2 | Resiliency - substation flood mitigation | Electric | Systemwide | In service | Colin Marsh | 2026-03-22 | 2026-03-22
CP-26-024 | 6084482 | 6278318 | 3869132 | 6600000 | Substation flood mitigation - Systemwide phase 1 3 | Resiliency - substation flood mitigation | Electric | Systemwide | Construct | Colin Marsh | 2026-11-16 | 2026-11-16
CP-26-025 | 5289887 | 5158248 | 3725304 | 13300000 | Urd cable - Harbor program 1 | Resiliency - URD cable | Electric | Harbor | Construct | Colin Marsh | 2026-07-24 | 2026-11-21
CP-26-026 | 3732948 | 3832337 | 2456562 | 8700000 | Urd cable - Prairie package 2 | Resiliency - URD cable | Electric | Prairie | Design | Colin Marsh | 2028-07-14 | 2028-08-13
CP-26-027 | 2484665 | 2221058 | 1516203 | 2500000 | Urd cable - Prairie phase 1 3 | Resiliency - URD cable | Electric | Prairie | Design | Colin Marsh | 2026-03-10 | 2026-05-09
CP-26-028 | 1688291 | 1631078 | 604506 | 3200000 | Urd cable - Harbor phase 2 4 | Resiliency - URD cable | Electric | Harbor | In service | Colin Marsh | 2026-07-26 | 2026-07-26
CP-26-029 | 4206096 | 4459224 | 2209554 | 7500000 | Urd cable - Bayou blanket 5 | Resiliency - URD cable | Electric | Bayou | Construct | Colin Marsh | 2027-09-25 | 2027-09-25
CP-26-030 | 3598113 | 3698055 | 2087871 | 4600000 | Urd cable - Prairie project 6 | Resiliency - URD cable | Electric | Prairie | Construct | Colin Marsh | 2028-04-14 | 2028-04-14
CP-26-031 | 4363160 | 4382236 | 2089777 | 5900000 | Transmission hardening - Harbor program 1 | Resiliency - transmission hardening | Electric | Harbor | Initiate | Colin Marsh | 2027-05-06 | 2027-05-06
CP-26-032 | 2604956 | 2404236 | 1334195 | 3700000 | Transmission hardening - Prairie package 2 | Resiliency - transmission hardening | Electric | Prairie | Construct | Colin Marsh | 2026-10-26 | 2027-02-23
CP-26-033 | 2843628 | 2874940 | 1401883 | 6700000 | Transmission hardening - Prairie phase 1 3 | Resiliency - transmission hardening | Electric | Prairie | In service | Colin Marsh | 2026-06-13 | 2026-06-13
CP-26-034 | 3188256 | 3338588 | 1474145 | 6800000 | Transmission hardening - Systemwide phase 2 4 | Resiliency - transmission hardening | Electric | Systemwide | In service | Colin Marsh | 2026-01-04 | 2026-01-04
CP-26-035 | 2000000 | 2000000 | 1300000 | 3600000 | Weather and monitoring - Bayou program 1 | Resiliency - weather and monitoring | Electric | Bayou | In service | Colin Marsh | 2026-04-16 | 2026-04-16
CP-26-036 | 1950250 | 1932094 | 603481 | 2500000 | Substation security - Systemwide program 1 | Resiliency - substation security | Electric | Systemwide | Construct | Colin Marsh | 2027-02-05 | 2027-02-05
CP-26-037 | 2049750 | 2067906 | 896519 | 3900000 | Substation security - Prairie package 2 | Resiliency - substation security | Electric | Prairie | Construct | Colin Marsh | 2028-07-31 | 2029-01-27
CP-26-038 | 33391325 | 34686137 | 22330946 | 86100000 | New service - Harbor program 1 | Growth - new service | Electric | Harbor | Construct | Jeremy Kowalczyk | 2027-09-13 | 2027-09-13
CP-26-039 | 28865638 | 30074294 | 19840413 | 50400000 | New service - Prairie package 2 | Growth - new service | Electric | Prairie | Construct | Jeremy Kowalczyk | 2026-09-27 | 2026-09-27
CP-26-040 | 21277935 | 20960304 | 17098224 | 39100000 | New service - Prairie phase 1 3 | Growth - new service | Electric | Prairie | Construct | Jeremy Kowalczyk | 2028-04-30 | 2028-04-30
CP-26-041 | 14861460 | 15690402 | 9344111 | 34500000 | New service - Harbor phase 2 4 | Growth - new service | Electric | Harbor | Closeout | Jeremy Kowalczyk | 2025-12-06 | 2025-12-06
CP-26-042 | 3894307 | 3702547 | 1952538 | 5300000 | New service - Systemwide blanket 5 | Growth - new service | Electric | Systemwide | Construct | Jeremy Kowalczyk | 2026-09-20 | 2026-09-20
CP-26-043 | 6709173 | 6652250 | 3028347 | 16000000 | New service - Crossroads project 6 | Growth - new service | Electric | Crossroads | In service | Jeremy Kowalczyk | 2026-04-04 | 2026-04-04
CP-26-044 | 11934069 | 11269821 | 5514753 | 22300000 | New service - Bayou program 7 | Growth - new service | Electric | Bayou | Construct | Jeremy Kowalczyk | 2027-07-10 | 2027-07-10
CP-26-045 | 7929359 | 7088881 | 5063709 | 18000000 | New service - Harbor package 8 | Growth - new service | Electric | Harbor | Design | Jeremy Kowalczyk | 2027-12-08 | 2027-12-08
CP-26-046 | 64037020 | 65814823 | 43308564 | 82300000 | New service - Prairie phase 1 9 | Growth - new service | Electric | Prairie | Design | Jeremy Kowalczyk | 2027-11-10 | 2027-11-10
CP-26-047 | 13776013 | 12981217 | 12805626 | 25100000 | New service - Crossroads phase 2 10 | Growth - new service | Electric | Crossroads | Construct | Jeremy Kowalczyk | 2026-08-20 | 2026-08-20
CP-26-048 | 16721253 | 16723809 | 11664971 | 31100000 | New service - Prairie blanket 11 | Growth - new service | Electric | Prairie | Construct | Jeremy Kowalczyk | 2027-12-05 | 2028-01-04
CP-26-049 | 24602448 | 26355515 | 20047798 | 62600000 | New service - Crossroads project 12 | Growth - new service | Electric | Crossroads | Initiate | Jeremy Kowalczyk | 2027-04-29 | 2027-04-29
CP-26-050 | 6500000 | 6453118 | 4129825 | 85000000 | Harbor North 138 kV substation and feeders | Growth - substation and feeder | Electric | Harbor | Design | Jeremy Kowalczyk | 2028-12-15 | 2028-12-15
CP-26-051 | 3684438 | 3435195 | 2252942 | 7300000 | Substation and feeder - Harbor package 2 | Growth - substation and feeder | Electric | Harbor | Design | Jeremy Kowalczyk | 2027-09-24 | 2027-09-24
CP-26-052 | 11469021 | 10428097 | 8407841 | 14500000 | Substation and feeder - Systemwide phase 1 3 | Growth - substation and feeder | Electric | Systemwide | Construct | Jeremy Kowalczyk | 2028-01-20 | 2028-01-20
CP-26-053 | 19574581 | 19540658 | 12579358 | 30600000 | Substation and feeder - Prairie phase 2 4 | Growth - substation and feeder | Electric | Prairie | Design | Jeremy Kowalczyk | 2027-09-07 | 2027-09-07
CP-26-054 | 19705801 | 18564790 | 8821220 | 26000000 | Substation and feeder - Prairie blanket 5 | Growth - substation and feeder | Electric | Prairie | Construct | Jeremy Kowalczyk | 2028-06-01 | 2028-06-01
CP-26-055 | 13981720 | 14598419 | 8244231 | 31200000 | Substation and feeder - Prairie project 6 | Growth - substation and feeder | Electric | Prairie | Construct | Jeremy Kowalczyk | 2027-12-24 | 2027-12-24
CP-26-056 | 16481474 | 16645312 | 9285339 | 31600000 | Substation and feeder - Prairie program 7 | Growth - substation and feeder | Electric | Prairie | Construct | Jeremy Kowalczyk | 2028-06-16 | 2028-08-15
CP-26-057 | 9238645 | 8853657 | 3837922 | 19300000 | Substation and feeder - Systemwide package 8 | Growth - substation and feeder | Electric | Systemwide | Closeout | Jeremy Kowalczyk | 2026-04-26 | 2026-04-26
CP-26-058 | 22008825 | 21786176 | 12947780 | 47000000 | Substation and feeder - Systemwide phase 1 9 | Growth - substation and feeder | Electric | Systemwide | Design | Jeremy Kowalczyk | 2028-03-22 | 2028-04-21
CP-26-059 | 8355495 | 7694578 | 3993542 | 11500000 | Substation and feeder - Crossroads phase 2 10 | Growth - substation and feeder | Electric | Crossroads | Design | Jeremy Kowalczyk | 2026-03-23 | 2026-03-23
CP-26-060 | 23631003 | 24510263 | 15208985 | 61000000 | Transmission - Prairie program 1 | Transmission | Electric | Prairie | Construct | Kwame Asante | 2027-04-20 | 2027-04-20
CP-26-061 | 11907345 | 13787573 | 6132904 | 20200000 | Transmission - Harbor package 2 | Transmission | Electric | Harbor | In service | Kwame Asante | 2026-05-16 | 2026-05-16
CP-26-062 | 5574142 | 5507204 | 2579450 | 10800000 | Transmission - Prairie phase 1 3 | Transmission | Electric | Prairie | In service | Kwame Asante | 2025-11-18 | 2025-11-18
CP-26-063 | 12170191 | 11920069 | 8032882 | 24300000 | Transmission - Systemwide phase 2 4 | Transmission | Electric | Systemwide | Design | Kwame Asante | 2026-06-24 | 2026-06-24
CP-26-064 | 17802087 | 19891443 | 10367731 | 24600000 | Transmission - Systemwide blanket 5 | Transmission | Electric | Systemwide | In service | Kwame Asante | 2026-02-09 | 2026-02-09
CP-26-065 | 26197340 | 27105752 | 16921771 | 35500000 | Transmission - Prairie project 6 | Transmission | Electric | Prairie | Design | Kwame Asante | 2027-10-12 | 2028-02-09
CP-26-066 | 18772961 | 19810942 | 13941725 | 34900000 | Transmission - Harbor program 7 | Transmission | Electric | Harbor | In service | Kwame Asante | 2026-03-07 | 2026-03-07
CP-26-067 | 15141850 | 17033411 | 10999086 | 35300000 | Transmission - Crossroads package 8 | Transmission | Electric | Crossroads | Construct | Kwame Asante | 2027-06-02 | 2027-06-02
CP-26-068 | 10803081 | 10433343 | 5815466 | 12500000 | Transmission - Harbor phase 1 9 | Transmission | Electric | Harbor | Construct | Kwame Asante | 2028-01-25 | 2028-01-25
CP-26-069 | 6816155 | 7420746 | 5612286 | 10800000 | Distribution - Harbor program 1 | Reliability - distribution | Electric | Harbor | Construct | Nadia Farouk | 2026-09-15 | 2026-09-15
CP-26-070 | 3964146 | 4057806 | 2097209 | 8300000 | Distribution - Prairie package 2 | Reliability - distribution | Electric | Prairie | Construct | Nadia Farouk | 2026-10-09 | 2026-12-08
CP-26-071 | 10939059 | 10269927 | 5818529 | 22600000 | Distribution - Bayou phase 1 3 | Reliability - distribution | Electric | Bayou | Design | Nadia Farouk | 2027-08-14 | 2027-08-14
CP-26-072 | 4968863 | 4812281 | 2944937 | 10800000 | Distribution - Bayou phase 2 4 | Reliability - distribution | Electric | Bayou | Initiate | Nadia Farouk | 2027-07-20 | 2027-08-19
CP-26-073 | 1652320 | 1598657 | 922992 | 2800000 | Distribution - Harbor blanket 5 | Reliability - distribution | Electric | Harbor | In service | Nadia Farouk | 2025-11-01 | 2025-11-01
CP-26-074 | 6356034 | 6373801 | 4956053 | 7900000 | Distribution - Prairie project 6 | Reliability - distribution | Electric | Prairie | Initiate | Nadia Farouk | 2026-11-15 | 2026-11-15
CP-26-075 | 9029951 | 9543715 | 6825261 | 13800000 | Distribution - Prairie program 7 | Reliability - distribution | Electric | Prairie | Construct | Nadia Farouk | 2027-06-05 | 2027-06-05
CP-26-076 | 8627312 | 8034444 | 5214532 | 12700000 | Distribution - Crossroads package 8 | Reliability - distribution | Electric | Crossroads | Construct | Nadia Farouk | 2028-07-10 | 2028-07-10
CP-26-077 | 7005887 | 7409825 | 2998834 | 16100000 | Distribution - Crossroads phase 1 9 | Reliability - distribution | Electric | Crossroads | In service | Nadia Farouk | 2026-05-08 | 2026-05-08
CP-26-078 | 17559672 | 19005531 | 13340687 | 36000000 | Distribution - Systemwide phase 2 10 | Reliability - distribution | Electric | Systemwide | Design | Nadia Farouk | 2028-08-05 | 2028-08-05
CP-26-079 | 4609693 | 4783875 | 3970299 | 6100000 | Distribution - Harbor blanket 11 | Reliability - distribution | Electric | Harbor | Design | Nadia Farouk | 2027-04-11 | 2027-04-11
CP-26-080 | 5844487 | 6446491 | 4693886 | 10800000 | Distribution - Harbor project 12 | Reliability - distribution | Electric | Harbor | Construct | Nadia Farouk | 2027-06-02 | 2027-07-02
CP-26-081 | 8348786 | 8068897 | 4530252 | 12200000 | Distribution - Crossroads program 13 | Reliability - distribution | Electric | Crossroads | Construct | Nadia Farouk | 2026-03-17 | 2026-03-17
CP-26-082 | 2126351 | 2084759 | 1113516 | 4600000 | Distribution - Systemwide package 14 | Reliability - distribution | Electric | Systemwide | In service | Nadia Farouk | 2026-08-05 | 2026-08-05
CP-26-083 | 16635093 | 16837373 | 10430070 | 35300000 | Distribution - Systemwide phase 1 15 | Reliability - distribution | Electric | Systemwide | Initiate | Nadia Farouk | 2026-06-15 | 2026-06-15
CP-26-084 | 3516191 | 3251872 | 3030657 | 7600000 | Distribution - Crossroads phase 2 16 | Reliability - distribution | Electric | Crossroads | Design | Nadia Farouk | 2027-01-17 | 2027-01-17
CP-26-085 | 14800000 | 11844827 | 2104587 | 16500000 | Next-generation meter pilot (Crossroads) | Metering | Electric | Crossroads | Construct | Luis Montoya | 2026-12-18 | 2027-01-29
CP-26-086 | 2962355 | 2643705 | 1685009 | 6800000 | Metering - Bayou package 2 | Metering | Electric | Bayou | Construct | Luis Montoya | 2026-06-27 | 2026-06-27
CP-26-087 | 4237645 | 3511468 | 2410404 | 6600000 | Metering - Crossroads phase 1 3 | Metering | Electric | Crossroads | Construct | Luis Montoya | 2026-07-09 | 2026-07-09
CP-26-088 | 2973794 | 2768237 | 2009109 | 5400000 | Facilities and fleet - Harbor program 1 | Facilities and fleet | Electric | Harbor | Design | Frank Lindqvist | 2026-03-09 | 2026-05-08
CP-26-089 | 3137516 | 2925038 | 1947406 | 4400000 | Facilities and fleet - Systemwide package 2 | Facilities and fleet | Electric | Systemwide | In service | Frank Lindqvist | 2026-02-17 | 2026-02-17
CP-26-090 | 6651610 | 6997868 | 3332388 | 8600000 | Facilities and fleet - Crossroads phase 1 3 | Facilities and fleet | Electric | Crossroads | Design | Frank Lindqvist | 2027-02-28 | 2027-02-28
CP-26-091 | 2705725 | 2870389 | 1882652 | 6000000 | Facilities and fleet - Harbor phase 2 4 | Facilities and fleet | Electric | Harbor | In service | Frank Lindqvist | 2026-01-06 | 2026-01-06
CP-26-092 | 2229846 | 2265008 | 942485 | 2900000 | Facilities and fleet - Harbor blanket 5 | Facilities and fleet | Electric | Harbor | Design | Frank Lindqvist | 2027-11-10 | 2027-11-10
CP-26-093 | 8675098 | 8704619 | 4075255 | 20300000 | Facilities and fleet - Crossroads project 6 | Facilities and fleet | Electric | Crossroads | Construct | Frank Lindqvist | 2027-04-06 | 2027-04-06
CP-26-094 | 10807118 | 10925378 | 7167921 | 23900000 | Facilities and fleet - Prairie program 7 | Facilities and fleet | Electric | Prairie | Construct | Frank Lindqvist | 2026-12-11 | 2027-01-10
CP-26-095 | 3819293 | 3543463 | 1442784 | 4900000 | Facilities and fleet - Prairie package 8 | Facilities and fleet | Electric | Prairie | Closeout | Frank Lindqvist | 2026-01-14 | 2026-01-14
CP-26-096 | 1200000 | 1092451 | 853232 | 14000000 | Work management system upgrade (phase 0) | IT and OT | Electric | Systemwide | Initiate | Patrick Nguyen | 2028-06-30 | 2028-06-30
CP-26-097 | 1832237 | 1771679 | 1205027 | 2700000 | It and ot - Crossroads package 2 | IT and OT | Electric | Crossroads | Closeout | Patrick Nguyen | 2025-12-25 | 2025-12-25
CP-26-098 | 7089674 | 6941062 | 3788977 | 11300000 | It and ot - Prairie phase 1 3 | IT and OT | Electric | Prairie | Closeout | Patrick Nguyen | 2026-08-05 | 2026-08-05
CP-26-099 | 2917305 | 2807694 | 1118777 | 3500000 | It and ot - Harbor phase 2 4 | IT and OT | Electric | Harbor | Construct | Patrick Nguyen | 2028-07-28 | 2028-07-28
CP-26-100 | 510920 | 546498 | 269424 | 800000 | It and ot - Systemwide blanket 5 | IT and OT | Electric | Systemwide | Design | Patrick Nguyen | 2027-09-24 | 2027-09-24
CP-26-101 | 6145465 | 6235045 | 4195104 | 13200000 | It and ot - Crossroads project 6 | IT and OT | Electric | Crossroads | Construct | Patrick Nguyen | 2027-06-07 | 2027-06-07
CP-26-102 | 4346254 | 4100744 | 1673901 | 5400000 | It and ot - Bayou program 7 | IT and OT | Electric | Bayou | Initiate | Patrick Nguyen | 2026-11-25 | 2026-12-25
CP-26-103 | 5021635 | 4636860 | 2962957 | 11300000 | It and ot - Harbor package 8 | IT and OT | Electric | Harbor | Construct | Patrick Nguyen | 2026-10-11 | 2026-12-10
CP-26-104 | 2281881 | 2243676 | 964540 | 5100000 | It and ot - Systemwide phase 1 9 | IT and OT | Electric | Systemwide | Construct | Patrick Nguyen | 2027-03-23 | 2027-09-19
CP-26-105 | 654629 | 624291 | 368061 | 700000 | It and ot - Harbor phase 2 10 | IT and OT | Electric | Harbor | In service | Patrick Nguyen | 2026-07-28 | 2026-07-28
CP-26-106 | 2189284 | 2156867 | 1365974 | 3400000 | Pipe replacement - Bayou program 1 | Gas - pipe replacement | Gas | Bayou | Closeout | Renee Dufresne | 2026-03-02 | 2026-03-02
CP-26-107 | 2713021 | 2538688 | 2227336 | 6600000 | Pipe replacement - Bayou package 2 | Gas - pipe replacement | Gas | Bayou | Construct | Renee Dufresne | 2027-01-02 | 2027-01-02
CP-26-108 | 5037849 | 5011619 | 3384875 | 8200000 | Pipe replacement - Bayou phase 1 3 | Gas - pipe replacement | Gas | Bayou | Construct | Renee Dufresne | 2026-11-24 | 2026-11-24
CP-26-109 | 7806075 | 7870913 | 3716405 | 8000000 | Pipe replacement - Prairie phase 2 4 | Gas - pipe replacement | Gas | Prairie | Design | Renee Dufresne | 2026-06-15 | 2026-06-15
CP-26-110 | 14736038 | 16273107 | 6650237 | 32000000 | Pipe replacement - Crossroads blanket 5 | Gas - pipe replacement | Gas | Crossroads | In service | Renee Dufresne | 2026-06-16 | 2026-06-16
CP-26-111 | 2121134 | 2053864 | 1749014 | 2500000 | Pipe replacement - Prairie project 6 | Gas - pipe replacement | Gas | Prairie | In service | Renee Dufresne | 2025-12-16 | 2025-12-16
CP-26-112 | 5421298 | 5223312 | 4745600 | 11900000 | Pipe replacement - Crossroads program 7 | Gas - pipe replacement | Gas | Crossroads | Construct | Renee Dufresne | 2028-04-26 | 2028-04-26
CP-26-113 | 1294340 | 1258398 | 666212 | 1400000 | Pipe replacement - Crossroads package 8 | Gas - pipe replacement | Gas | Crossroads | In service | Renee Dufresne | 2025-11-13 | 2025-11-13
CP-26-114 | 4930798 | 4650315 | 2964397 | 9600000 | Pipe replacement - Prairie phase 1 9 | Gas - pipe replacement | Gas | Prairie | Construct | Renee Dufresne | 2026-11-27 | 2026-11-27
CP-26-115 | 9402414 | 9799290 | 4052070 | 13300000 | Pipe replacement - Bayou phase 2 10 | Gas - pipe replacement | Gas | Bayou | Design | Renee Dufresne | 2026-11-24 | 2026-11-24
CP-26-116 | 11846233 | 11300709 | 10230468 | 29700000 | Pipe replacement - Systemwide blanket 11 | Gas - pipe replacement | Gas | Systemwide | Construct | Renee Dufresne | 2028-02-06 | 2028-02-06
CP-26-117 | 4553377 | 4277296 | 3063649 | 6800000 | Pipe replacement - Systemwide project 12 | Gas - pipe replacement | Gas | Systemwide | Design | Renee Dufresne | 2026-04-23 | 2026-06-22
CP-26-118 | 2856571 | 2737306 | 1894033 | 6600000 | Pipe replacement - Prairie program 13 | Gas - pipe replacement | Gas | Prairie | Design | Renee Dufresne | 2026-04-23 | 2026-04-23
CP-26-119 | 3091568 | 2848316 | 2589730 | 4700000 | Pipe replacement - Prairie package 14 | Gas - pipe replacement | Gas | Prairie | Construct | Renee Dufresne | 2028-05-14 | 2028-09-11
CP-26-120 | 3775414 | 3539993 | 2538603 | 4800000 | System reinforcement - Bayou program 1 | Gas - system reinforcement | Gas | Bayou | Design | Renee Dufresne | 2028-02-08 | 2028-02-08
CP-26-121 | 3841372 | 3857597 | 2649572 | 7400000 | System reinforcement - Prairie package 2 | Gas - system reinforcement | Gas | Prairie | Construct | Renee Dufresne | 2028-02-15 | 2028-03-16
CP-26-122 | 2181607 | 2227615 | 1187355 | 2900000 | System reinforcement - Systemwide phase 1 3 | Gas - system reinforcement | Gas | Systemwide | Design | Renee Dufresne | 2026-12-09 | 2027-04-08
CP-26-123 | 3999832 | 3656721 | 2076839 | 5500000 | System reinforcement - Crossroads phase 2 4 | Gas - system reinforcement | Gas | Crossroads | Initiate | Renee Dufresne | 2028-03-20 | 2028-03-20
CP-26-124 | 5348824 | 5567668 | 2896658 | 9100000 | System reinforcement - Crossroads blanket 5 | Gas - system reinforcement | Gas | Crossroads | Design | Renee Dufresne | 2027-04-11 | 2027-04-11
CP-26-125 | 4052706 | 4138734 | 2339456 | 5300000 | System reinforcement - Crossroads project 6 | Gas - system reinforcement | Gas | Crossroads | Closeout | Renee Dufresne | 2026-01-12 | 2026-01-12
CP-26-126 | 3373732 | 3499066 | 2570011 | 7100000 | System reinforcement - Bayou program 7 | Gas - system reinforcement | Gas | Bayou | In service | Renee Dufresne | 2026-02-22 | 2026-02-22
CP-26-127 | 4805458 | 4442188 | 2541846 | 12300000 | System reinforcement - Systemwide package 8 | Gas - system reinforcement | Gas | Systemwide | Construct | Renee Dufresne | 2027-08-08 | 2027-08-08
CP-26-128 | 11617465 | 11649242 | 5828972 | 21900000 | System reinforcement - Bayou phase 1 9 | Gas - system reinforcement | Gas | Bayou | Construct | Renee Dufresne | 2026-12-19 | 2026-12-19
CP-26-129 | 9003590 | 8421176 | 5970688 | 10500000 | System reinforcement - Crossroads phase 2 10 | Gas - system reinforcement | Gas | Crossroads | Construct | Renee Dufresne | 2026-08-18 | 2026-09-17
CP-26-130 | 7619025 | 7935539 | 5160096 | 18400000 | New business and meters - Systemwide program 1 | Gas - new business and meters | Gas | Systemwide | Construct | Renee Dufresne | 2027-08-05 | 2027-08-05
CP-26-131 | 3907178 | 4256747 | 2286822 | 5100000 | New business and meters - Prairie package 2 | Gas - new business and meters | Gas | Prairie | Construct | Renee Dufresne | 2028-08-02 | 2029-01-29
CP-26-132 | 1578950 | 1595962 | 1092805 | 2100000 | New business and meters - Bayou phase 1 3 | Gas - new business and meters | Gas | Bayou | Construct | Renee Dufresne | 2027-11-11 | 2027-11-11
CP-26-133 | 3544362 | 3555249 | 2644904 | 7900000 | New business and meters - Bayou phase 2 4 | Gas - new business and meters | Gas | Bayou | Design | Renee Dufresne | 2026-07-27 | 2026-07-27
CP-26-134 | 3350485 | 3656503 | 1715373 | 7300000 | New business and meters - Prairie blanket 5 | Gas - new business and meters | Gas | Prairie | Construct | Renee Dufresne | 2026-11-08 | 2027-05-07
CP-26-135 | 1563802 | 1460748 | 579861 | 2300000 | It and ot - Systemwide program 1 | IT and OT | Shared | Systemwide | Design | Patrick Nguyen | 2026-12-09 | 2026-12-09
CP-26-136 | 8393391 | 8034283 | 3044358 | 19200000 | It and ot - Systemwide package 2 | IT and OT | Shared | Systemwide | Closeout | Patrick Nguyen | 2026-06-10 | 2026-06-10
CP-26-137 | 5175420 | 4469433 | 2222230 | 12200000 | It and ot - Prairie phase 1 3 | IT and OT | Shared | Prairie | Construct | Patrick Nguyen | 2028-01-31 | 2028-01-31
CP-26-138 | 1435160 | 1290509 | 685785 | 2900000 | It and ot - Bayou phase 2 4 | IT and OT | Shared | Bayou | In service | Patrick Nguyen | 2026-06-21 | 2026-06-21
CP-26-139 | 2622795 | 2331904 | 1068728 | 6100000 | It and ot - Prairie blanket 5 | IT and OT | Shared | Prairie | Design | Patrick Nguyen | 2027-09-06 | 2027-09-06
CP-26-140 | 3111892 | 3079186 | 2403189 | 4900000 | It and ot - Harbor project 6 | IT and OT | Shared | Harbor | In service | Patrick Nguyen | 2025-11-04 | 2025-11-04
CP-26-141 | 2133438 | 2131913 | 1227832 | 3400000 | It and ot - Systemwide program 7 | IT and OT | Shared | Systemwide | In service | Patrick Nguyen | 2026-05-23 | 2026-05-23
CP-26-142 | 2232226 | 2192916 | 809803 | 2700000 | It and ot - Prairie package 8 | IT and OT | Shared | Prairie | Design | Patrick Nguyen | 2028-06-02 | 2028-06-02
CP-26-143 | 2190523 | 1937466 | 1337175 | 4500000 | It and ot - Harbor phase 1 9 | IT and OT | Shared | Harbor | Design | Patrick Nguyen | 2027-01-27 | 2027-01-27
CP-26-144 | 2141353 | 2071642 | 1221039 | 4300000 | It and ot - Systemwide phase 2 10 | IT and OT | Shared | Systemwide | Construct | Patrick Nguyen | 2028-05-02 | 2028-06-01
CP-26-145 | 1044966 | 970624 | 537357 | 1800000 | Facilities and fleet - Crossroads program 1 | Facilities and fleet | Shared | Crossroads | Construct | Frank Lindqvist | 2027-10-06 | 2027-12-05
CP-26-146 | 524084 | 564451 | 190279 | 1200000 | Facilities and fleet - Harbor package 2 | Facilities and fleet | Shared | Harbor | Construct | Frank Lindqvist | 2028-01-04 | 2028-07-02
CP-26-147 | 1787446 | 1896468 | 1208066 | 4400000 | Facilities and fleet - Harbor phase 1 3 | Facilities and fleet | Shared | Harbor | In service | Frank Lindqvist | 2026-03-26 | 2026-03-26
CP-26-148 | 580388 | 519818 | 349680 | 1300000 | Facilities and fleet - Bayou phase 2 4 | Facilities and fleet | Shared | Bayou | Construct | Frank Lindqvist | 2027-02-12 | 2027-02-12
CP-26-149 | 1956708 | 2035545 | 1019770 | 4200000 | Facilities and fleet - Prairie blanket 5 | Facilities and fleet | Shared | Prairie | Construct | Frank Lindqvist | 2028-02-25 | 2028-02-25
CP-26-150 | 1013649 | 1035589 | 613160 | 1900000 | Facilities and fleet - Prairie project 6 | Facilities and fleet | Shared | Prairie | Construct | Frank Lindqvist | 2027-05-25 | 2027-05-25
CP-26-151 | 304876 | 282395 | 111075 | 400000 | Facilities and fleet - Bayou program 7 | Facilities and fleet | Shared | Bayou | Construct | Frank Lindqvist | 2028-02-09 | 2028-03-10
CP-26-152 | 1787883 | 1695110 | 1170613 | 3000000 | Facilities and fleet - Bayou package 8 | Facilities and fleet | Shared | Bayou | Construct | Frank Lindqvist | 2027-11-22 | 2028-03-21

## Data 2
record_id | actual_usd | project_code | program | month_start
CM-000001 | 993288.38 | CP-26-001 | Resiliency - pole replacement | 2026-01-01
CM-000002 | 838950.4 | CP-26-001 | Resiliency - pole replacement | 2026-02-01
CM-000003 | 1121449.2 | CP-26-001 | Resiliency - pole replacement | 2026-03-01
CM-000004 | 743362.8 | CP-26-001 | Resiliency - pole replacement | 2026-04-01
CM-000005 | 842897.85 | CP-26-001 | Resiliency - pole replacement | 2026-05-01
CM-000006 | 992724.22 | CP-26-001 | Resiliency - pole replacement | 2026-06-01
CM-000007 | 1389137.54 | CP-26-001 | Resiliency - pole replacement | 2026-07-01
CM-000008 | 1193871.61 | CP-26-001 | Resiliency - pole replacement | 2026-08-01
CM-000009 | 188792.3 | CP-26-002 | Resiliency - pole replacement | 2026-01-01
CM-000010 | 110949.46 | CP-26-002 | Resiliency - pole replacement | 2026-02-01
CM-000011 | 202601.76 | CP-26-002 | Resiliency - pole replacement | 2026-03-01
CM-000012 | 144364.45 | CP-26-002 | Resiliency - pole replacement | 2026-04-01
CM-000013 | 200215.37 | CP-26-002 | Resiliency - pole replacement | 2026-05-01
CM-000014 | 131659.47 | CP-26-002 | Resiliency - pole replacement | 2026-06-01
CM-000015 | 142768.28 | CP-26-002 | Resiliency - pole replacement | 2026-07-01
CM-000016 | 179131.91 | CP-26-002 | Resiliency - pole replacement | 2026-08-01
CM-000017 | 962062.12 | CP-26-003 | Resiliency - pole replacement | 2026-01-01
CM-000018 | 1465983.03 | CP-26-003 | Resiliency - pole replacement | 2026-02-01
CM-000019 | 1098400.08 | CP-26-003 | Resiliency - pole replacement | 2026-03-01
CM-000020 | 1100789.64 | CP-26-003 | Resiliency - pole replacement | 2026-04-01
CM-000021 | 946054.09 | CP-26-003 | Resiliency - pole replacement | 2026-05-01
CM-000022 | 1117549.62 | CP-26-003 | Resiliency - pole replacement | 2026-06-01
CM-000023 | 1724658.44 | CP-26-003 | Resiliency - pole replacement | 2026-07-01
CM-000024 | 1465152.98 | CP-26-003 | Resiliency - pole replacement | 2026-08-01
CM-000025 | 256285.58 | CP-26-004 | Resiliency - pole replacement | 2026-01-01
CM-000026 | 237904.03 | CP-26-004 | Resiliency - pole replacement | 2026-02-01
CM-000027 | 249379.81 | CP-26-004 | Resiliency - pole replacement | 2026-03-01
CM-000028 | 197517.55 | CP-26-004 | Resiliency - pole replacement | 2026-04-01
CM-000029 | 214749.84 | CP-26-004 | Resiliency - pole replacement | 2026-05-01
CM-000030 | 206559.8 | CP-26-004 | Resiliency - pole replacement | 2026-06-01
CM-000031 | 209554.81 | CP-26-004 | Resiliency - pole replacement | 2026-07-01
CM-000032 | 263879.58 | CP-26-004 | Resiliency - pole replacement | 2026-08-01
CM-000033 | 175239.79 | CP-26-005 | Resiliency - pole replacement | 2026-01-01
CM-000034 | 224775.22 | CP-26-005 | Resiliency - pole replacement | 2026-02-01
CM-000035 | 292389.24 | CP-26-005 | Resiliency - pole replacement | 2026-03-01
CM-000036 | 222879.05 | CP-26-005 | Resiliency - pole replacement | 2026-04-01
CM-000037 | 233413.76 | CP-26-005 | Resiliency - pole replacement | 2026-05-01
CM-000038 | 369437.48 | CP-26-005 | Resiliency - pole replacement | 2026-06-01
CM-000039 | 309867.29 | CP-26-005 | Resiliency - pole replacement | 2026-07-01
CM-000040 | 286621.17 | CP-26-005 | Resiliency - pole replacement | 2026-08-01
CM-000041 | 73538.12 | CP-26-006 | Resiliency - pole replacement | 2026-01-01
CM-000042 | 66646.13 | CP-26-006 | Resiliency - pole replacement | 2026-02-01
CM-000043 | 85937.48 | CP-26-006 | Resiliency - pole replacement | 2026-03-01
CM-000044 | 63596.22 | CP-26-006 | Resiliency - pole replacement | 2026-04-01
CM-000045 | 66689.51 | CP-26-006 | Resiliency - pole replacement | 2026-05-01
CM-000046 | 59256.43 | CP-26-006 | Resiliency - pole replacement | 2026-06-01
CM-000047 | 85521.65 | CP-26-006 | Resiliency - pole replacement | 2026-07-01
CM-000048 | 113635.46 | CP-26-006 | Resiliency - pole replacement | 2026-08-01
CM-000049 | 504937.13 | CP-26-007 | Resiliency - pole replacement | 2026-01-01
CM-000050 | 444531.77 | CP-26-007 | Resiliency - pole replacement | 2026-02-01
CM-000051 | 490550.15 | CP-26-007 | Resiliency - pole replacement | 2026-03-01
CM-000052 | 522591.14 | CP-26-007 | Resiliency - pole replacement | 2026-04-01
CM-000053 | 419491.78 | CP-26-007 | Resiliency - pole replacement | 2026-05-01
CM-000054 | 507277.06 | CP-26-007 | Resiliency - pole replacement | 2026-06-01
CM-000055 | 487304.71 | CP-26-007 | Resiliency - pole replacement | 2026-07-01
CM-000056 | 595291.26 | CP-26-007 | Resiliency - pole replacement | 2026-08-01
CM-000057 | 1867388.7 | CP-26-008 | Resiliency - pole replacement | 2026-01-01
CM-000058 | 1896711.82 | CP-26-008 | Resiliency - pole replacement | 2026-02-01
CM-000059 | 1754641.97 | CP-26-008 | Resiliency - pole replacement | 2026-03-01
CM-000060 | 1943361.26 | CP-26-008 | Resiliency - pole replacement | 2026-04-01
CM-000061 | 2246752.67 | CP-26-008 | Resiliency - pole replacement | 2026-05-01
CM-000062 | 2597443.5 | CP-26-008 | Resiliency - pole replacement | 2026-06-01
CM-000063 | 1791815.5 | CP-26-008 | Resiliency - pole replacement | 2026-07-01
CM-000064 | 2067819.58 | CP-26-008 | Resiliency - pole replacement | 2026-08-01
CM-000065 | 395259.59 | CP-26-009 | Resiliency - automation | 2026-01-01
CM-000066 | 708075.68 | CP-26-009 | Resiliency - automation | 2026-02-01
CM-000067 | 440621.23 | CP-26-009 | Resiliency - automation | 2026-03-01
CM-000068 | 718244.76 | CP-26-009 | Resiliency - automation | 2026-04-01
CM-000069 | 778544.3 | CP-26-009 | Resiliency - automation | 2026-05-01
CM-000070 | 529834.89 | CP-26-009 | Resiliency - automation | 2026-06-01
CM-000071 | 873660.41 | CP-26-009 | Resiliency - automation | 2026-07-01
CM-000072 | 777043.14 | CP-26-009 | Resiliency - automation | 2026-08-01
CM-000073 | 156893.39 | CP-26-010 | Resiliency - automation | 2026-01-01
CM-000074 | 246297.36 | CP-26-010 | Resiliency - automation | 2026-02-01
CM-000075 | 239961.77 | CP-26-010 | Resiliency - automation | 2026-03-01
CM-000076 | 218079.86 | CP-26-010 | Resiliency - automation | 2026-04-01
CM-000077 | 183824.52 | CP-26-010 | Resiliency - automation | 2026-05-01
CM-000078 | 231637.75 | CP-26-010 | Resiliency - automation | 2026-06-01
CM-000079 | 216830.67 | CP-26-010 | Resiliency - automation | 2026-07-01
CM-000080 | 314053.68 | CP-26-010 | Resiliency - automation | 2026-08-01
CM-000081 | 58200.36 | CP-26-011 | Resiliency - automation | 2026-01-01
CM-000082 | 68778.07 | CP-26-011 | Resiliency - automation | 2026-02-01
CM-000083 | 69299.54 | CP-26-011 | Resiliency - automation | 2026-03-01
CM-000084 | 49006.14 | CP-26-011 | Resiliency - automation | 2026-04-01
CM-000085 | 74883.65 | CP-26-011 | Resiliency - automation | 2026-05-01
CM-000086 | 54107.8 | CP-26-011 | Resiliency - automation | 2026-06-01
CM-000087 | 70641.83 | CP-26-011 | Resiliency - automation | 2026-07-01
CM-000088 | 52680.61 | CP-26-011 | Resiliency - automation | 2026-08-01
CM-000089 | 617970.11 | CP-26-012 | Resiliency - automation | 2026-01-01
CM-000090 | 732032.58 | CP-26-012 | Resiliency - automation | 2026-02-01
CM-000091 | 749940.77 | CP-26-012 | Resiliency - automation | 2026-03-01
CM-000092 | 1042165.53 | CP-26-012 | Resiliency - automation | 2026-04-01
CM-000093 | 985496.88 | CP-26-012 | Resiliency - automation | 2026-05-01
CM-000094 | 769432.18 | CP-26-012 | Resiliency - automation | 2026-06-01
CM-000095 | 1139857.37 | CP-26-012 | Resiliency - automation | 2026-07-01
CM-000096 | 1235771.58 | CP-26-012 | Resiliency - automation | 2026-08-01
CM-000097 | 239942.23 | CP-26-013 | Resiliency - automation | 2026-01-01
CM-000098 | 216442.7 | CP-26-013 | Resiliency - automation | 2026-02-01
CM-000099 | 257729.25 | CP-26-013 | Resiliency - automation | 2026-03-01
CM-000100 | 313750.21 | CP-26-013 | Resiliency - automation | 2026-04-01
CM-000101 | 214367.22 | CP-26-013 | Resiliency - automation | 2026-05-01
CM-000102 | 362473.15 | CP-26-013 | Resiliency - automation | 2026-06-01
CM-000103 | 380256.1 | CP-26-013 | Resiliency - automation | 2026-07-01
CM-000104 | 369208.14 | CP-26-013 | Resiliency - automation | 2026-08-01
CM-000105 | 575554.59 | CP-26-014 | Resiliency - automation | 2026-01-01
CM-000106 | 467284.06 | CP-26-014 | Resiliency - automation | 2026-02-01
CM-000107 | 531802.32 | CP-26-014 | Resiliency - automation | 2026-03-01
CM-000108 | 528258.76 | CP-26-014 | Resiliency - automation | 2026-04-01
CM-000109 | 498869.49 | CP-26-014 | Resiliency - automation | 2026-05-01
CM-000110 | 685397.55 | CP-26-014 | Resiliency - automation | 2026-06-01
CM-000111 | 547085.26 | CP-26-014 | Resiliency - automation | 2026-07-01
CM-000112 | 812450.97 | CP-26-014 | Resiliency - automation | 2026-08-01
CM-000113 | 351133.6 | CP-26-015 | Resiliency - undergrounding | 2026-01-01
CM-000114 | 435197.44 | CP-26-015 | Resiliency - undergrounding | 2026-02-01
CM-000115 | 300770.39 | CP-26-015 | Resiliency - undergrounding | 2026-03-01
CM-000116 | 342034.62 | CP-26-015 | Resiliency - undergrounding | 2026-04-01
CM-000117 | 379213.57 | CP-26-015 | Resiliency - undergrounding | 2026-05-01
CM-000118 | 459961.1 | CP-26-015 | Resiliency - undergrounding | 2026-06-01
CM-000119 | 580606.76 | CP-26-015 | Resiliency - undergrounding | 2026-07-01
CM-000120 | 538874.52 | CP-26-015 | Resiliency - undergrounding | 2026-08-01
CM-000121 | 71044.29 | CP-26-016 | Resiliency - undergrounding | 2026-01-01
CM-000122 | 94254.83 | CP-26-016 | Resiliency - undergrounding | 2026-02-01
CM-000123 | 91665.71 | CP-26-016 | Resiliency - undergrounding | 2026-03-01
CM-000124 | 97437.05 | CP-26-016 | Resiliency - undergrounding | 2026-04-01
CM-000125 | 98562.94 | CP-26-016 | Resiliency - undergrounding | 2026-05-01
CM-000126 | 105624.38 | CP-26-016 | Resiliency - undergrounding | 2026-06-01
CM-000127 | 86488.5 | CP-26-016 | Resiliency - undergrounding | 2026-07-01
CM-000128 | 99016.3 | CP-26-016 | Resiliency - undergrounding | 2026-08-01
CM-000129 | 226120.8 | CP-26-017 | Resiliency - undergrounding | 2026-01-01
CM-000130 | 195993.4 | CP-26-017 | Resiliency - undergrounding | 2026-02-01
CM-000131 | 198517.97 | CP-26-017 | Resiliency - undergrounding | 2026-03-01
CM-000132 | 231183.15 | CP-26-017 | Resiliency - undergrounding | 2026-04-01
CM-000133 | 161059.67 | CP-26-017 | Resiliency - undergrounding | 2026-05-01
CM-000134 | 225431.27 | CP-26-017 | Resiliency - undergrounding | 2026-06-01
CM-000135 | 275381.14 | CP-26-017 | Resiliency - undergrounding | 2026-07-01
CM-000136 | 259252.6 | CP-26-017 | Resiliency - undergrounding | 2026-08-01
CM-000137 | 77621.17 | CP-26-018 | Resiliency - undergrounding | 2026-01-01
CM-000138 | 90186.86 | CP-26-018 | Resiliency - undergrounding | 2026-02-01
CM-000139 | 86171.97 | CP-26-018 | Resiliency - undergrounding | 2026-03-01
CM-000140 | 99761.12 | CP-26-018 | Resiliency - undergrounding | 2026-04-01
CM-000141 | 60542.82 | CP-26-018 | Resiliency - undergrounding | 2026-05-01
CM-000142 | 92680.21 | CP-26-018 | Resiliency - undergrounding | 2026-06-01
CM-000143 | 117999 | CP-26-018 | Resiliency - undergrounding | 2026-07-01
CM-000144 | 98630.85 | CP-26-018 | Resiliency - undergrounding | 2026-08-01
CM-000145 | 366047.44 | CP-26-019 | Resiliency - undergrounding | 2026-01-01
CM-000146 | 414161.11 | CP-26-019 | Resiliency - undergrounding | 2026-02-01
CM-000147 | 295550.4 | CP-26-019 | Resiliency - undergrounding | 2026-03-01
CM-000148 | 439541.76 | CP-26-019 | Resiliency - undergrounding | 2026-04-01
CM-000149 | 374188.89 | CP-26-019 | Resiliency - undergrounding | 2026-05-01
CM-000150 | 410107.45 | CP-26-019 | Resiliency - undergrounding | 2026-06-01
CM-000151 | 605635.59 | CP-26-019 | Resiliency - undergrounding | 2026-07-01
CM-000152 | 568335.36 | CP-26-019 | Resiliency - undergrounding | 2026-08-01
CM-000153 | 307526.43 | CP-26-020 | Resiliency - undergrounding | 2026-01-01
CM-000154 | 320345.07 | CP-26-020 | Resiliency - undergrounding | 2026-02-01
CM-000155 | 302521.46 | CP-26-020 | Resiliency - undergrounding | 2026-03-01
CM-000156 | 351497.63 | CP-26-020 | Resiliency - undergrounding | 2026-04-01
CM-000157 | 274724 | CP-26-020 | Resiliency - undergrounding | 2026-05-01
CM-000158 | 375197.74 | CP-26-020 | Resiliency - undergrounding | 2026-06-01
CM-000159 | 233019.21 | CP-26-020 | Resiliency - undergrounding | 2026-07-01
CM-000160 | 301810.46 | CP-26-020 | Resiliency - undergrounding | 2026-08-01
CM-000161 | 65736.03 | CP-26-021 | Resiliency - undergrounding | 2026-01-01
CM-000162 | 102887.14 | CP-26-021 | Resiliency - undergrounding | 2026-02-01
CM-000163 | 126666.6 | CP-26-021 | Resiliency - undergrounding | 2026-03-01
CM-000164 | 104842.46 | CP-26-021 | Resiliency - undergrounding | 2026-04-01
CM-000165 | 92510.78 | CP-26-021 | Resiliency - undergrounding | 2026-05-01
CM-000166 | 127238.75 | CP-26-021 | Resiliency - undergrounding | 2026-06-01
CM-000167 | 81481.12 | CP-26-021 | Resiliency - undergrounding | 2026-07-01
CM-000168 | 130007.12 | CP-26-021 | Resiliency - undergrounding | 2026-08-01
CM-000169 | 211520.07 | CP-26-022 | Resiliency - substation flood mitigation | 2026-01-01
CM-000170 | 380183.75 | CP-26-022 | Resiliency - substation flood mitigation | 2026-02-01
CM-000171 | 243824.86 | CP-26-022 | Resiliency - substation flood mitigation | 2026-03-01
CM-000172 | 403440.96 | CP-26-022 | Resiliency - substation flood mitigation | 2026-04-01
CM-000173 | 296461.46 | CP-26-022 | Resiliency - substation flood mitigation | 2026-05-01
CM-000174 | 354429.44 | CP-26-022 | Resiliency - substation flood mitigation | 2026-06-01
CM-000175 | 370135.46 | CP-26-022 | Resiliency - substation flood mitigation | 2026-07-01
CM-000176 | 462503 | CP-26-022 | Resiliency - substation flood mitigation | 2026-08-01
CM-000177 | 217918.97 | CP-26-023 | Resiliency - substation flood mitigation | 2026-01-01
CM-000178 | 227374.03 | CP-26-023 | Resiliency - substation flood mitigation | 2026-02-01
CM-000179 | 176422.8 | CP-26-023 | Resiliency - substation flood mitigation | 2026-03-01
CM-000180 | 153646.98 | CP-26-023 | Resiliency - substation flood mitigation | 2026-04-01
CM-000181 | 159832.3 | CP-26-023 | Resiliency - substation flood mitigation | 2026-05-01
CM-000182 | 184424.19 | CP-26-023 | Resiliency - substation flood mitigation | 2026-06-01
CM-000183 | 211566.74 | CP-26-023 | Resiliency - substation flood mitigation | 2026-07-01
CM-000184 | 177182.99 | CP-26-023 | Resiliency - substation flood mitigation | 2026-08-01
CM-000185 | 411222.8 | CP-26-024 | Resiliency - substation flood mitigation | 2026-01-01
CM-000186 | 340049.44 | CP-26-024 | Resiliency - substation flood mitigation | 2026-02-01
CM-000187 | 597522.1 | CP-26-024 | Resiliency - substation flood mitigation | 2026-03-01
CM-000188 | 599156.26 | CP-26-024 | Resiliency - substation flood mitigation | 2026-04-01
CM-000189 | 532101.81 | CP-26-024 | Resiliency - substation flood mitigation | 2026-05-01
CM-000190 | 419585.5 | CP-26-024 | Resiliency - substation flood mitigation | 2026-06-01
CM-000191 | 401241.17 | CP-26-024 | Resiliency - substation flood mitigation | 2026-07-01
CM-000192 | 568252.92 | CP-26-024 | Resiliency - substation flood mitigation | 2026-08-01
CM-000193 | 357375.1 | CP-26-025 | Resiliency - URD cable | 2026-01-01
CM-000194 | 449208.52 | CP-26-025 | Resiliency - URD cable | 2026-02-01
CM-000195 | 429630.07 | CP-26-025 | Resiliency - URD cable | 2026-03-01
CM-000196 | 479858.91 | CP-26-025 | Resiliency - URD cable | 2026-04-01
CM-000197 | 357891.71 | CP-26-025 | Resiliency - URD cable | 2026-05-01
CM-000198 | 562449.27 | CP-26-025 | Resiliency - URD cable | 2026-06-01
CM-000199 | 641095.93 | CP-26-025 | Resiliency - URD cable | 2026-07-01
CM-000200 | 447794.49 | CP-26-025 | Resiliency - URD cable | 2026-08-01
CM-000201 | 235087.62 | CP-26-026 | Resiliency - URD cable | 2026-01-01
CM-000202 | 219172.49 | CP-26-026 | Resiliency - URD cable | 2026-02-01
CM-000203 | 301100.43 | CP-26-026 | Resiliency - URD cable | 2026-03-01
CM-000204 | 231454.95 | CP-26-026 | Resiliency - URD cable | 2026-04-01
CM-000205 | 329246.3 | CP-26-026 | Resiliency - URD cable | 2026-05-01
CM-000206 | 392809.62 | CP-26-026 | Resiliency - URD cable | 2026-06-01
CM-000207 | 313984.05 | CP-26-026 | Resiliency - URD cable | 2026-07-01
CM-000208 | 433706.54 | CP-26-026 | Resiliency - URD cable | 2026-08-01
CM-000209 | 131290.93 | CP-26-027 | Resiliency - URD cable | 2026-01-01
CM-000210 | 122685.48 | CP-26-027 | Resiliency - URD cable | 2026-02-01
CM-000211 | 221600.36 | CP-26-027 | Resiliency - URD cable | 2026-03-01
CM-000212 | 209610.33 | CP-26-027 | Resiliency - URD cable | 2026-04-01
CM-000213 | 202128.77 | CP-26-027 | Resiliency - URD cable | 2026-05-01
CM-000214 | 219055.79 | CP-26-027 | Resiliency - URD cable | 2026-06-01
CM-000215 | 206460.84 | CP-26-027 | Resiliency - URD cable | 2026-07-01
CM-000216 | 203370.5 | CP-26-027 | Resiliency - URD cable | 2026-08-01
CM-000217 | 55701.75 | CP-26-028 | Resiliency - URD cable | 2026-01-01
CM-000218 | 79133.04 | CP-26-028 | Resiliency - URD cable | 2026-02-01
CM-000219 | 59065.96 | CP-26-028 | Resiliency - URD cable | 2026-03-01
CM-000220 | 79705.13 | CP-26-028 | Resiliency - URD cable | 2026-04-01
CM-000221 | 94109.37 | CP-26-028 | Resiliency - URD cable | 2026-05-01
CM-000222 | 62535.51 | CP-26-028 | Resiliency - URD cable | 2026-06-01
CM-000223 | 64381.1 | CP-26-028 | Resiliency - URD cable | 2026-07-01
CM-000224 | 109874.14 | CP-26-028 | Resiliency - URD cable | 2026-08-01
CM-000225 | 262243.86 | CP-26-029 | Resiliency - URD cable | 2026-01-01
CM-000226 | 204897.45 | CP-26-029 | Resiliency - URD cable | 2026-02-01
CM-000227 | 276564.18 | CP-26-029 | Resiliency - URD cable | 2026-03-01
CM-000228 | 312946.5 | CP-26-029 | Resiliency - URD cable | 2026-04-01
CM-000229 | 249819.94 | CP-26-029 | Resiliency - URD cable | 2026-05-01
CM-000230 | 332943.8 | CP-26-029 | Resiliency - URD cable | 2026-06-01
CM-000231 | 242668.27 | CP-26-029 | Resiliency - URD cable | 2026-07-01
CM-000232 | 327470 | CP-26-029 | Resiliency - URD cable | 2026-08-01
CM-000233 | 255651.48 | CP-26-030 | Resiliency - URD cable | 2026-01-01
CM-000234 | 178582.21 | CP-26-030 | Resiliency - URD cable | 2026-02-01
CM-000235 | 309999.87 | CP-26-030 | Resiliency - URD cable | 2026-03-01
CM-000236 | 261010.29 | CP-26-030 | Resiliency - URD cable | 2026-04-01
CM-000237 | 314283.98 | CP-26-030 | Resiliency - URD cable | 2026-05-01
CM-000238 | 198049.49 | CP-26-030 | Resiliency - URD cable | 2026-06-01
CM-000239 | 287094.59 | CP-26-030 | Resiliency - URD cable | 2026-07-01
CM-000240 | 283199.09 | CP-26-030 | Resiliency - URD cable | 2026-08-01
CM-000241 | 0 | CP-26-031 | Resiliency - transmission hardening | 2026-01-01
CM-000242 | 0 | CP-26-031 | Resiliency - transmission hardening | 2026-02-01
CM-000243 | 0 | CP-26-031 | Resiliency - transmission hardening | 2026-03-01
CM-000244 | 0 | CP-26-031 | Resiliency - transmission hardening | 2026-04-01
CM-000245 | 0 | CP-26-031 | Resiliency - transmission hardening | 2026-05-01
CM-000246 | 417955.4 | CP-26-031 | Resiliency - transmission hardening | 2026-06-01
CM-000247 | 835910.8 | CP-26-031 | Resiliency - transmission hardening | 2026-07-01
CM-000248 | 835910.8 | CP-26-031 | Resiliency - transmission hardening | 2026-08-01
CM-000249 | 171920.44 | CP-26-032 | Resiliency - transmission hardening | 2026-01-01
CM-000250 | 168867.74 | CP-26-032 | Resiliency - transmission hardening | 2026-02-01
CM-000251 | 151647.32 | CP-26-032 | Resiliency - transmission hardening | 2026-03-01
CM-000252 | 128178.39 | CP-26-032 | Resiliency - transmission hardening | 2026-04-01
CM-000253 | 122662.45 | CP-26-032 | Resiliency - transmission hardening | 2026-05-01
CM-000254 | 160486.26 | CP-26-032 | Resiliency - transmission hardening | 2026-06-01
CM-000255 | 193003.11 | CP-26-032 | Resiliency - transmission hardening | 2026-07-01
CM-000256 | 237429.29 | CP-26-032 | Resiliency - transmission hardening | 2026-08-01
CM-000257 | 164470.9 | CP-26-033 | Resiliency - transmission hardening | 2026-01-01
CM-000258 | 137986.1 | CP-26-033 | Resiliency - transmission hardening | 2026-02-01
CM-000259 | 174966.5 | CP-26-033 | Resiliency - transmission hardening | 2026-03-01
CM-000260 | 225447.19 | CP-26-033 | Resiliency - transmission hardening | 2026-04-01
CM-000261 | 146441.06 | CP-26-033 | Resiliency - transmission hardening | 2026-05-01
CM-000262 | 151664.74 | CP-26-033 | Resiliency - transmission hardening | 2026-06-01
CM-000263 | 209861.78 | CP-26-033 | Resiliency - transmission hardening | 2026-07-01
CM-000264 | 191044.73 | CP-26-033 | Resiliency - transmission hardening | 2026-08-01
CM-000265 | 141322.27 | CP-26-034 | Resiliency - transmission hardening | 2026-01-01
CM-000266 | 136048.24 | CP-26-034 | Resiliency - transmission hardening | 2026-02-01
CM-000267 | 249304.03 | CP-26-034 | Resiliency - transmission hardening | 2026-03-01
CM-000268 | 179560.75 | CP-26-034 | Resiliency - transmission hardening | 2026-04-01
CM-000269 | 161707.41 | CP-26-034 | Resiliency - transmission hardening | 2026-05-01
CM-000270 | 161456.17 | CP-26-034 | Resiliency - transmission hardening | 2026-06-01
CM-000271 | 191356.5 | CP-26-034 | Resiliency - transmission hardening | 2026-07-01
CM-000272 | 253389.63 | CP-26-034 | Resiliency - transmission hardening | 2026-08-01
CM-000273 | 153740.49 | CP-26-035 | Resiliency - weather and monitoring | 2026-01-01
CM-000274 | 170460.25 | CP-26-035 | Resiliency - weather and monitoring | 2026-02-01
CM-000275 | 176832.11 | CP-26-035 | Resiliency - weather and monitoring | 2026-03-01
CM-000276 | 135080.37 | CP-26-035 | Resiliency - weather and monitoring | 2026-04-01
CM-000277 | 147884.6 | CP-26-035 | Resiliency - weather and monitoring | 2026-05-01
CM-000278 | 131326.23 | CP-26-035 | Resiliency - weather and monitoring | 2026-06-01
CM-000279 | 184817.74 | CP-26-035 | Resiliency - weather and monitoring | 2026-07-01
CM-000280 | 199858.21 | CP-26-035 | Resiliency - weather and monitoring | 2026-08-01
CM-000281 | 48385.31 | CP-26-036 | Resiliency - substation security | 2026-01-01
CM-000282 | 64332.22 | CP-26-036 | Resiliency - substation security | 2026-02-01
CM-000283 | 83093.54 | CP-26-036 | Resiliency - substation security | 2026-03-01
CM-000284 | 103030.98 | CP-26-036 | Resiliency - substation security | 2026-04-01
CM-000285 | 78857.12 | CP-26-036 | Resiliency - substation security | 2026-05-01
CM-000286 | 58042.3 | CP-26-036 | Resiliency - substation security | 2026-06-01
CM-000287 | 78960.57 | CP-26-036 | Resiliency - substation security | 2026-07-01
CM-000288 | 88778.96 | CP-26-036 | Resiliency - substation security | 2026-08-01
CM-000289 | 114863.18 | CP-26-037 | Resiliency - substation security | 2026-01-01
CM-000290 | 123601.82 | CP-26-037 | Resiliency - substation security | 2026-02-01
CM-000291 | 96658.5 | CP-26-037 | Resiliency - substation security | 2026-03-01
CM-000292 | 88605.23 | CP-26-037 | Resiliency - substation security | 2026-04-01
CM-000293 | 96479.45 | CP-26-037 | Resiliency - substation security | 2026-05-01
CM-000294 | 137006.84 | CP-26-037 | Resiliency - substation security | 2026-06-01
CM-000295 | 115001.08 | CP-26-037 | Resiliency - substation security | 2026-07-01
CM-000296 | 124302.9 | CP-26-037 | Resiliency - substation security | 2026-08-01
CM-000297 | 2669463.51 | CP-26-038 | Growth - new service | 2026-01-01
CM-000298 | 1862307.1 | CP-26-038 | Growth - new service | 2026-02-01
CM-000299 | 2282182.4 | CP-26-038 | Growth - new service | 2026-03-01
CM-000300 | 3405695.53 | CP-26-038 | Growth - new service | 2026-04-01
CM-000301 | 2021933.51 | CP-26-038 | Growth - new service | 2026-05-01
CM-000302 | 3222779.63 | CP-26-038 | Growth - new service | 2026-06-01
CM-000303 | 3125673.89 | CP-26-038 | Growth - new service | 2026-07-01
CM-000304 | 3740910.43 | CP-26-038 | Growth - new service | 2026-08-01
CM-000305 | 2434836.77 | CP-26-039 | Growth - new service | 2026-01-01
CM-000306 | 2647914.03 | CP-26-039 | Growth - new service | 2026-02-01
CM-000307 | 2436629.52 | CP-26-039 | Growth - new service | 2026-03-01
CM-000308 | 2582991.01 | CP-26-039 | Growth - new service | 2026-04-01
CM-000309 | 2068004.9 | CP-26-039 | Growth - new service | 2026-05-01
CM-000310 | 2771249.23 | CP-26-039 | Growth - new service | 2026-06-01
CM-000311 | 2401395.49 | CP-26-039 | Growth - new service | 2026-07-01
CM-000312 | 2497392.05 | CP-26-039 | Growth - new service | 2026-08-01
CM-000313 | 1538662.53 | CP-26-040 | Growth - new service | 2026-01-01
CM-000314 | 1693560.9 | CP-26-040 | Growth - new service | 2026-02-01
CM-000315 | 2382963.28 | CP-26-040 | Growth - new service | 2026-03-01
CM-000316 | 1928283.31 | CP-26-040 | Growth - new service | 2026-04-01
CM-000317 | 2403526.33 | CP-26-040 | Growth - new service | 2026-05-01
CM-000318 | 2280921.91 | CP-26-040 | Growth - new service | 2026-06-01
CM-000319 | 2795094.79 | CP-26-040 | Growth - new service | 2026-07-01
CM-000320 | 2075210.95 | CP-26-040 | Growth - new service | 2026-08-01
CM-000321 | 1215003.58 | CP-26-041 | Growth - new service | 2026-01-01
CM-000322 | 992470.88 | CP-26-041 | Growth - new service | 2026-02-01
CM-000323 | 914180.88 | CP-26-041 | Growth - new service | 2026-03-01
CM-000324 | 956243.46 | CP-26-041 | Growth - new service | 2026-04-01
CM-000325 | 1184173.55 | CP-26-041 | Growth - new service | 2026-05-01
CM-000326 | 1526256.42 | CP-26-041 | Growth - new service | 2026-06-01
CM-000327 | 1076560.08 | CP-26-041 | Growth - new service | 2026-07-01
CM-000328 | 1479222.15 | CP-26-041 | Growth - new service | 2026-08-01
CM-000329 | 186649.3 | CP-26-042 | Growth - new service | 2026-01-01
CM-000330 | 167450.67 | CP-26-042 | Growth - new service | 2026-02-01
CM-000331 | 219058.22 | CP-26-042 | Growth - new service | 2026-03-01
CM-000332 | 255576.56 | CP-26-042 | Growth - new service | 2026-04-01
CM-000333 | 235630.91 | CP-26-042 | Growth - new service | 2026-05-01
CM-000334 | 293965.75 | CP-26-042 | Growth - new service | 2026-06-01
CM-000335 | 266202.24 | CP-26-042 | Growth - new service | 2026-07-01
CM-000336 | 328004.35 | CP-26-042 | Growth - new service | 2026-08-01
CM-000337 | 326877.24 | CP-26-043 | Growth - new service | 2026-01-01
CM-000338 | 380566.14 | CP-26-043 | Growth - new service | 2026-02-01
CM-000339 | 401988.09 | CP-26-043 | Growth - new service | 2026-03-01
CM-000340 | 461741.92 | CP-26-043 | Growth - new service | 2026-04-01
CM-000341 | 267863.43 | CP-26-043 | Growth - new service | 2026-05-01
CM-000342 | 293563.72 | CP-26-043 | Growth - new service | 2026-06-01
CM-000343 | 510590.53 | CP-26-043 | Growth - new service | 2026-07-01
CM-000344 | 385155.93 | CP-26-043 | Growth - new service | 2026-08-01
CM-000345 | 719754.97 | CP-26-044 | Growth - new service | 2026-01-01
CM-000346 | 721870.4 | CP-26-044 | Growth - new service | 2026-02-01
CM-000347 | 704218.66 | CP-26-044 | Growth - new service | 2026-03-01
CM-000348 | 886374.26 | CP-26-044 | Growth - new service | 2026-04-01
CM-000349 | 501299.61 | CP-26-044 | Growth - new service | 2026-05-01
CM-000350 | 679178.95 | CP-26-044 | Growth - new service | 2026-06-01
CM-000351 | 592998.54 | CP-26-044 | Growth - new service | 2026-07-01
CM-000352 | 709057.61 | CP-26-044 | Growth - new service | 2026-08-01
CM-000353 | 458681.91 | CP-26-045 | Growth - new service | 2026-01-01
CM-000354 | 617122.01 | CP-26-045 | Growth - new service | 2026-02-01
CM-000355 | 707732.01 | CP-26-045 | Growth - new service | 2026-03-01
CM-000356 | 495487.29 | CP-26-045 | Growth - new service | 2026-04-01
CM-000357 | 558969.69 | CP-26-045 | Growth - new service | 2026-05-01
CM-000358 | 724769.66 | CP-26-045 | Growth - new service | 2026-06-01
CM-000359 | 795259.83 | CP-26-045 | Growth - new service | 2026-07-01
CM-000360 | 705686.6 | CP-26-045 | Growth - new service | 2026-08-01
CM-000361 | 4536941.03 | CP-26-046 | Growth - new service | 2026-01-01
CM-000362 | 4707400.98 | CP-26-046 | Growth - new service | 2026-02-01
CM-000363 | 5907518.63 | CP-26-046 | Growth - new service | 2026-03-01
CM-000364 | 4776059.37 | CP-26-046 | Growth - new service | 2026-04-01
CM-000365 | 5176017.49 | CP-26-046 | Growth - new service | 2026-05-01
CM-000366 | 6592959.14 | CP-26-046 | Growth - new service | 2026-06-01
CM-000367 | 6230314.78 | CP-26-046 | Growth - new service | 2026-07-01
CM-000368 | 5381352.58 | CP-26-046 | Growth - new service | 2026-08-01
CM-000369 | 1108770.61 | CP-26-047 | Growth - new service | 2026-01-01
CM-000370 | 1325999.32 | CP-26-047 | Growth - new service | 2026-02-01
CM-000371 | 1755033.49 | CP-26-047 | Growth - new service | 2026-03-01
CM-000372 | 1464645.07 | CP-26-047 | Growth - new service | 2026-04-01
CM-000373 | 1841925.28 | CP-26-047 | Growth - new service | 2026-05-01
CM-000374 | 1726272.19 | CP-26-047 | Growth - new service | 2026-06-01
CM-000375 | 1623576.69 | CP-26-047 | Growth - new service | 2026-07-01
CM-000376 | 1959403.35 | CP-26-047 | Growth - new service | 2026-08-01
CM-000377 | 1424625.55 | CP-26-048 | Growth - new service | 2026-01-01
CM-000378 | 1170013.79 | CP-26-048 | Growth - new service | 2026-02-01
CM-000379 | 1609750.77 | CP-26-048 | Growth - new service | 2026-03-01
CM-000380 | 1815708.01 | CP-26-048 | Growth - new service | 2026-04-01
CM-000381 | 1283989.81 | CP-26-048 | Growth - new service | 2026-05-01
CM-000382 | 1673263.73 | CP-26-048 | Growth - new service | 2026-06-01
CM-000383 | 1185444.95 | CP-26-048 | Growth - new service | 2026-07-01
CM-000384 | 1502174.39 | CP-26-048 | Growth - new service | 2026-08-01
CM-000385 | 0 | CP-26-049 | Growth - new service | 2026-01-01
CM-000386 | 0 | CP-26-049 | Growth - new service | 2026-02-01
CM-000387 | 0 | CP-26-049 | Growth - new service | 2026-03-01
CM-000388 | 0 | CP-26-049 | Growth - new service | 2026-04-01
CM-000389 | 0 | CP-26-049 | Growth - new service | 2026-05-01
CM-000390 | 4009559.6 | CP-26-049 | Growth - new service | 2026-06-01
CM-000391 | 8019119.2 | CP-26-049 | Growth - new service | 2026-07-01
CM-000392 | 8019119.2 | CP-26-049 | Growth - new service | 2026-08-01
CM-000393 | 356185.43 | CP-26-050 | Growth - substation and feeder | 2026-01-01
CM-000394 | 374786.17 | CP-26-050 | Growth - substation and feeder | 2026-02-01
CM-000395 | 457241.12 | CP-26-050 | Growth - substation and feeder | 2026-03-01
CM-000396 | 631151.51 | CP-26-050 | Growth - substation and feeder | 2026-04-01
CM-000397 | 599239.2 | CP-26-050 | Growth - substation and feeder | 2026-05-01
CM-000398 | 545200.31 | CP-26-050 | Growth - substation and feeder | 2026-06-01
CM-000399 | 573330.95 | CP-26-050 | Growth - substation and feeder | 2026-07-01
CM-000400 | 592690.31 | CP-26-050 | Growth - substation and feeder | 2026-08-01
CM-000401 | 239076.82 | CP-26-051 | Growth - substation and feeder | 2026-01-01
CM-000402 | 253677.29 | CP-26-051 | Growth - substation and feeder | 2026-02-01
CM-000403 | 276695.7 | CP-26-051 | Growth - substation and feeder | 2026-03-01
CM-000404 | 338257.61 | CP-26-051 | Growth - substation and feeder | 2026-04-01
CM-000405 | 190969.25 | CP-26-051 | Growth - substation and feeder | 2026-05-01
CM-000406 | 223146.88 | CP-26-051 | Growth - substation and feeder | 2026-06-01
CM-000407 | 388984.42 | CP-26-051 | Growth - substation and feeder | 2026-07-01
CM-000408 | 342134.03 | CP-26-051 | Growth - substation and feeder | 2026-08-01
CM-000409 | 917146.15 | CP-26-052 | Growth - substation and feeder | 2026-01-01
CM-000410 | 1002425.09 | CP-26-052 | Growth - substation and feeder | 2026-02-01
CM-000411 | 661163.41 | CP-26-052 | Growth - substation and feeder | 2026-03-01
CM-000412 | 1046413.64 | CP-26-052 | Growth - substation and feeder | 2026-04-01
CM-000413 | 1122104.2 | CP-26-052 | Growth - substation and feeder | 2026-05-01
CM-000414 | 1023430.24 | CP-26-052 | Growth - substation and feeder | 2026-06-01
CM-000415 | 1213201.32 | CP-26-052 | Growth - substation and feeder | 2026-07-01
CM-000416 | 1421956.95 | CP-26-052 | Growth - substation and feeder | 2026-08-01
CM-000417 | 1403675.39 | CP-26-053 | Growth - substation and feeder | 2026-01-01
CM-000418 | 1563337.99 | CP-26-053 | Growth - substation and feeder | 2026-02-01
CM-000419 | 1451368.73 | CP-26-053 | Growth - substation and feeder | 2026-03-01
CM-000420 | 1427375.09 | CP-26-053 | Growth - substation and feeder | 2026-04-01
CM-000421 | 1647391.9 | CP-26-053 | Growth - substation and feeder | 2026-05-01
CM-000422 | 1235435.69 | CP-26-053 | Growth - substation and feeder | 2026-06-01
CM-000423 | 1984857.38 | CP-26-053 | Growth - substation and feeder | 2026-07-01
CM-000424 | 1865915.83 | CP-26-053 | Growth - substation and feeder | 2026-08-01
CM-000425 | 647851.92 | CP-26-054 | Growth - substation and feeder | 2026-01-01
CM-000426 | 994727.39 | CP-26-054 | Growth - substation and feeder | 2026-02-01
CM-000427 | 1007871.06 | CP-26-054 | Growth - substation and feeder | 2026-03-01
CM-000428 | 1296227.55 | CP-26-054 | Growth - substation and feeder | 2026-04-01
CM-000429 | 1112070.55 | CP-26-054 | Growth - substation and feeder | 2026-05-01
CM-000430 | 1354149.42 | CP-26-054 | Growth - substation and feeder | 2026-06-01
CM-000431 | 1034364.66 | CP-26-054 | Growth - substation and feeder | 2026-07-01
CM-000432 | 1373957.45 | CP-26-054 | Growth - substation and feeder | 2026-08-01
CM-000433 | 1039600.11 | CP-26-055 | Growth - substation and feeder | 2026-01-01
CM-000434 | 1026639.62 | CP-26-055 | Growth - substation and feeder | 2026-02-01
CM-000435 | 882112.7 | CP-26-055 | Growth - substation and feeder | 2026-03-01
CM-000436 | 1022414.94 | CP-26-055 | Growth - substation and feeder | 2026-04-01
CM-000437 | 1134002.75 | CP-26-055 | Growth - substation and feeder | 2026-05-01
CM-000438 | 894464.68 | CP-26-055 | Growth - substation and feeder | 2026-06-01
CM-000439 | 857502.4 | CP-26-055 | Growth - substation and feeder | 2026-07-01
CM-000440 | 1387493.8 | CP-26-055 | Growth - substation and feeder | 2026-08-01
CM-000441 | 1101661.45 | CP-26-056 | Growth - substation and feeder | 2026-01-01
CM-000442 | 1123619.41 | CP-26-056 | Growth - substation and feeder | 2026-02-01
CM-000443 | 1126510.06 | CP-26-056 | Growth - substation and feeder | 2026-03-01
CM-000444 | 1270471.87 | CP-26-056 | Growth - substation and feeder | 2026-04-01
CM-000445 | 1234871.53 | CP-26-056 | Growth - substation and feeder | 2026-05-01
CM-000446 | 919159.59 | CP-26-056 | Growth - substation and feeder | 2026-06-01
CM-000447 | 1395906.14 | CP-26-056 | Growth - substation and feeder | 2026-07-01
CM-000448 | 1113138.95 | CP-26-056 | Growth - substation and feeder | 2026-08-01
CM-000449 | 542787.37 | CP-26-057 | Growth - substation and feeder | 2026-01-01
CM-000450 | 471092.17 | CP-26-057 | Growth - substation and feeder | 2026-02-01
CM-000451 | 458775.95 | CP-26-057 | Growth - substation and feeder | 2026-03-01
CM-000452 | 441258.01 | CP-26-057 | Growth - substation and feeder | 2026-04-01
CM-000453 | 372597.95 | CP-26-057 | Growth - substation and feeder | 2026-05-01
CM-000454 | 446579.37 | CP-26-057 | Growth - substation and feeder | 2026-06-01
CM-000455 | 595393.76 | CP-26-057 | Growth - substation and feeder | 2026-07-01
CM-000456 | 509437.42 | CP-26-057 | Growth - substation and feeder | 2026-08-01
CM-000457 | 1660038.24 | CP-26-058 | Growth - substation and feeder | 2026-01-01
CM-000458 | 1828722.7 | CP-26-058 | Growth - substation and feeder | 2026-02-01
CM-000459 | 1870775.42 | CP-26-058 | Growth - substation and feeder | 2026-03-01
CM-000460 | 1381324.4 | CP-26-058 | Growth - substation and feeder | 2026-04-01
CM-000461 | 1244509.72 | CP-26-058 | Growth - substation and feeder | 2026-05-01
CM-000462 | 1293291.46 | CP-26-058 | Growth - substation and feeder | 2026-06-01
CM-000463 | 2016602.89 | CP-26-058 | Growth - substation and feeder | 2026-07-01
CM-000464 | 1652515.17 | CP-26-058 | Growth - substation and feeder | 2026-08-01
CM-000465 | 333459.97 | CP-26-059 | Growth - substation and feeder | 2026-01-01
CM-000466 | 447383.97 | CP-26-059 | Growth - substation and feeder | 2026-02-01
CM-000467 | 455208.12 | CP-26-059 | Growth - substation and feeder | 2026-03-01
CM-000468 | 526918.91 | CP-26-059 | Growth - substation and feeder | 2026-04-01
CM-000469 | 625104.72 | CP-26-059 | Growth - substation and feeder | 2026-05-01
CM-000470 | 467910.79 | CP-26-059 | Growth - substation and feeder | 2026-06-01
CM-000471 | 465980.72 | CP-26-059 | Growth - substation and feeder | 2026-07-01
CM-000472 | 671574.8 | CP-26-059 | Growth - substation and feeder | 2026-08-01
CM-000473 | 1607527.76 | CP-26-060 | Transmission | 2026-01-01
CM-000474 | 1421560.35 | CP-26-060 | Transmission | 2026-02-01
CM-000475 | 2134092.98 | CP-26-060 | Transmission | 2026-03-01
CM-000476 | 1758291.18 | CP-26-060 | Transmission | 2026-04-01
CM-000477 | 1988595.36 | CP-26-060 | Transmission | 2026-05-01
CM-000478 | 1976853.21 | CP-26-060 | Transmission | 2026-06-01
CM-000479 | 1935077.49 | CP-26-060 | Transmission | 2026-07-01
CM-000480 | 2386986.67 | CP-26-060 | Transmission | 2026-08-01
CM-000481 | 538075.42 | CP-26-061 | Transmission | 2026-01-01
CM-000482 | 665292.88 | CP-26-061 | Transmission | 2026-02-01
CM-000483 | 578366.83 | CP-26-061 | Transmission | 2026-03-01
CM-000484 | 1004294.86 | CP-26-061 | Transmission | 2026-04-01
CM-000485 | 889111.78 | CP-26-061 | Transmission | 2026-05-01
CM-000486 | 897565.85 | CP-26-061 | Transmission | 2026-06-01
CM-000487 | 845309.28 | CP-26-061 | Transmission | 2026-07-01
CM-000488 | 714887.1 | CP-26-061 | Transmission | 2026-08-01
CM-000489 | 221405.74 | CP-26-062 | Transmission | 2026-01-01
CM-000490 | 234311.01 | CP-26-062 | Transmission | 2026-02-01
CM-000491 | 385523.1 | CP-26-062 | Transmission | 2026-03-01
CM-000492 | 283181.12 | CP-26-062 | Transmission | 2026-04-01
CM-000493 | 349668.48 | CP-26-062 | Transmission | 2026-05-01
CM-000494 | 347190.81 | CP-26-062 | Transmission | 2026-06-01
CM-000495 | 327552.52 | CP-26-062 | Transmission | 2026-07-01
CM-000496 | 430617.22 | CP-26-062 | Transmission | 2026-08-01
CM-000497 | 954957.23 | CP-26-063 | Transmission | 2026-01-01
CM-000498 | 862403.81 | CP-26-063 | Transmission | 2026-02-01
CM-000499 | 1024840.82 | CP-26-063 | Transmission | 2026-03-01
CM-000500 | 1239436.1 | CP-26-063 | Transmission | 2026-04-01
CM-000501 | 706610.11 | CP-26-063 | Transmission | 2026-05-01
CM-000502 | 810391.14 | CP-26-063 | Transmission | 2026-06-01
CM-000503 | 954760.2 | CP-26-063 | Transmission | 2026-07-01
CM-000504 | 1479482.59 | CP-26-063 | Transmission | 2026-08-01
CM-000505 | 1361367.86 | CP-26-064 | Transmission | 2026-01-01
CM-000506 | 1178318.51 | CP-26-064 | Transmission | 2026-02-01
CM-000507 | 1000164.73 | CP-26-064 | Transmission | 2026-03-01
CM-000508 | 1216354.71 | CP-26-064 | Transmission | 2026-04-01
CM-000509 | 1010066.82 | CP-26-064 | Transmission | 2026-05-01
CM-000510 | 1724837.2 | CP-26-064 | Transmission | 2026-06-01
CM-000511 | 1776475.23 | CP-26-064 | Transmission | 2026-07-01
CM-000512 | 1100145.94 | CP-26-064 | Transmission | 2026-08-01
CM-000513 | 1986531.12 | CP-26-065 | Transmission | 2026-01-01
CM-000514 | 2208991.22 | CP-26-065 | Transmission | 2026-02-01
CM-000515 | 2128445.88 | CP-26-065 | Transmission | 2026-03-01
CM-000516 | 1808860.72 | CP-26-065 | Transmission | 2026-04-01
CM-000517 | 2151398.71 | CP-26-065 | Transmission | 2026-05-01
CM-000518 | 2250817.45 | CP-26-065 | Transmission | 2026-06-01
CM-000519 | 2703011.23 | CP-26-065 | Transmission | 2026-07-01
CM-000520 | 1683714.67 | CP-26-065 | Transmission | 2026-08-01
CM-000521 | 1536689.21 | CP-26-066 | Transmission | 2026-01-01
CM-000522 | 1121863.52 | CP-26-066 | Transmission | 2026-02-01
CM-000523 | 1577736.83 | CP-26-066 | Transmission | 2026-03-01
CM-000524 | 1927524.02 | CP-26-066 | Transmission | 2026-04-01
CM-000525 | 1779717.11 | CP-26-066 | Transmission | 2026-05-01
CM-000526 | 1820723.92 | CP-26-066 | Transmission | 2026-06-01
CM-000527 | 2166884.46 | CP-26-066 | Transmission | 2026-07-01
CM-000528 | 2010585.93 | CP-26-066 | Transmission | 2026-08-01
CM-000529 | 900789.76 | CP-26-067 | Transmission | 2026-01-01
CM-000530 | 1545104.46 | CP-26-067 | Transmission | 2026-02-01
CM-000531 | 1027608.02 | CP-26-067 | Transmission | 2026-03-01
CM-000532 | 1319887.07 | CP-26-067 | Transmission | 2026-04-01
CM-000533 | 1452518 | CP-26-067 | Transmission | 2026-05-01
CM-000534 | 1308060.33 | CP-26-067 | Transmission | 2026-06-01
CM-000535 | 1614984.16 | CP-26-067 | Transmission | 2026-07-01
CM-000536 | 1830134.2 | CP-26-067 | Transmission | 2026-08-01
CM-000537 | 840282.03 | CP-26-068 | Transmission | 2026-01-01
CM-000538 | 604142.55 | CP-26-068 | Transmission | 2026-02-01
CM-000539 | 632418.3 | CP-26-068 | Transmission | 2026-03-01
CM-000540 | 928284.41 | CP-26-068 | Transmission | 2026-04-01
CM-000541 | 743910.7 | CP-26-068 | Transmission | 2026-05-01
CM-000542 | 606437.3 | CP-26-068 | Transmission | 2026-06-01
CM-000543 | 699251.77 | CP-26-068 | Transmission | 2026-07-01
CM-000544 | 760738.94 | CP-26-068 | Transmission | 2026-08-01
CM-000545 | 661197.81 | CP-26-069 | Reliability - distribution | 2026-01-01
CM-000546 | 592058.18 | CP-26-069 | Reliability - distribution | 2026-02-01
CM-000547 | 622735.18 | CP-26-069 | Reliability - distribution | 2026-03-01
CM-000548 | 622443.79 | CP-26-069 | Reliability - distribution | 2026-04-01
CM-000549 | 813657.71 | CP-26-069 | Reliability - distribution | 2026-05-01
CM-000550 | 717416.91 | CP-26-069 | Reliability - distribution | 2026-06-01
CM-000551 | 665727.49 | CP-26-069 | Reliability - distribution | 2026-07-01
CM-000552 | 917048.93 | CP-26-069 | Reliability - distribution | 2026-08-01
CM-000553 | 192498.56 | CP-26-070 | Reliability - distribution | 2026-01-01
CM-000554 | 225921.08 | CP-26-070 | Reliability - distribution | 2026-02-01
CM-000555 | 245908.84 | CP-26-070 | Reliability - distribution | 2026-03-01
CM-000556 | 247141.26 | CP-26-070 | Reliability - distribution | 2026-04-01
CM-000557 | 300905.09 | CP-26-070 | Reliability - distribution | 2026-05-01
CM-000558 | 311899.58 | CP-26-070 | Reliability - distribution | 2026-06-01
CM-000559 | 246859.4 | CP-26-070 | Reliability - distribution | 2026-07-01
CM-000560 | 326075.19 | CP-26-070 | Reliability - distribution | 2026-08-01
CM-000561 | 752588.57 | CP-26-071 | Reliability - distribution | 2026-01-01
CM-000562 | 567922.53 | CP-26-071 | Reliability - distribution | 2026-02-01
CM-000563 | 787397.46 | CP-26-071 | Reliability - distribution | 2026-03-01
CM-000564 | 688357.13 | CP-26-071 | Reliability - distribution | 2026-04-01
CM-000565 | 539822.28 | CP-26-071 | Reliability - distribution | 2026-05-01
CM-000566 | 676145.21 | CP-26-071 | Reliability - distribution | 2026-06-01
CM-000567 | 1049310.54 | CP-26-071 | Reliability - distribution | 2026-07-01
CM-000568 | 756985.28 | CP-26-071 | Reliability - distribution | 2026-08-01
CM-000569 | 0 | CP-26-072 | Reliability - distribution | 2026-01-01
CM-000570 | 0 | CP-26-072 | Reliability - distribution | 2026-02-01
CM-000571 | 0 | CP-26-072 | Reliability - distribution | 2026-03-01
CM-000572 | 0 | CP-26-072 | Reliability - distribution | 2026-04-01
CM-000573 | 0 | CP-26-072 | Reliability - distribution | 2026-05-01
CM-000574 | 588987.4 | CP-26-072 | Reliability - distribution | 2026-06-01
CM-000575 | 1177974.8 | CP-26-072 | Reliability - distribution | 2026-07-01
CM-000576 | 1177974.8 | CP-26-072 | Reliability - distribution | 2026-08-01
CM-000577 | 70768 | CP-26-073 | Reliability - distribution | 2026-01-01
CM-000578 | 127013.49 | CP-26-073 | Reliability - distribution | 2026-02-01
CM-000579 | 94322.07 | CP-26-073 | Reliability - distribution | 2026-03-01
CM-000580 | 143872.51 | CP-26-073 | Reliability - distribution | 2026-04-01
CM-000581 | 102107.6 | CP-26-073 | Reliability - distribution | 2026-05-01
CM-000582 | 103542.14 | CP-26-073 | Reliability - distribution | 2026-06-01
CM-000583 | 141059.24 | CP-26-073 | Reliability - distribution | 2026-07-01
CM-000584 | 140306.95 | CP-26-073 | Reliability - distribution | 2026-08-01
CM-000585 | 0 | CP-26-074 | Reliability - distribution | 2026-01-01
CM-000586 | 0 | CP-26-074 | Reliability - distribution | 2026-02-01
CM-000587 | 0 | CP-26-074 | Reliability - distribution | 2026-03-01
CM-000588 | 0 | CP-26-074 | Reliability - distribution | 2026-04-01
CM-000589 | 0 | CP-26-074 | Reliability - distribution | 2026-05-01
CM-000590 | 991210.6 | CP-26-074 | Reliability - distribution | 2026-06-01
CM-000591 | 1982421.2 | CP-26-074 | Reliability - distribution | 2026-07-01
CM-000592 | 1982421.2 | CP-26-074 | Reliability - distribution | 2026-08-01
CM-000593 | 685844.19 | CP-26-075 | Reliability - distribution | 2026-01-01
CM-000594 | 646667.6 | CP-26-075 | Reliability - distribution | 2026-02-01
CM-000595 | 833357.12 | CP-26-075 | Reliability - distribution | 2026-03-01
CM-000596 | 1011258.71 | CP-26-075 | Reliability - distribution | 2026-04-01
CM-000597 | 870651.5 | CP-26-075 | Reliability - distribution | 2026-05-01
CM-000598 | 907038.19 | CP-26-075 | Reliability - distribution | 2026-06-01
CM-000599 | 783664.33 | CP-26-075 | Reliability - distribution | 2026-07-01
CM-000600 | 1086779.36 | CP-26-075 | Reliability - distribution | 2026-08-01
CM-000601 | 675716.7 | CP-26-076 | Reliability - distribution | 2026-01-01
CM-000602 | 513110.51 | CP-26-076 | Reliability - distribution | 2026-02-01
CM-000603 | 852820.24 | CP-26-076 | Reliability - distribution | 2026-03-01
CM-000604 | 608227.88 | CP-26-076 | Reliability - distribution | 2026-04-01
CM-000605 | 553267.98 | CP-26-076 | Reliability - distribution | 2026-05-01
CM-000606 | 567098.74 | CP-26-076 | Reliability - distribution | 2026-06-01
CM-000607 | 668117.93 | CP-26-076 | Reliability - distribution | 2026-07-01
CM-000608 | 776172.02 | CP-26-076 | Reliability - distribution | 2026-08-01
CM-000609 | 284798.31 | CP-26-077 | Reliability - distribution | 2026-01-01
CM-000610 | 459829.16 | CP-26-077 | Reliability - distribution | 2026-02-01
CM-000611 | 490321.27 | CP-26-077 | Reliability - distribution | 2026-03-01
CM-000612 | 367986.14 | CP-26-077 | Reliability - distribution | 2026-04-01
CM-000613 | 324429.82 | CP-26-077 | Reliability - distribution | 2026-05-01
CM-000614 | 317711.98 | CP-26-077 | Reliability - distribution | 2026-06-01
CM-000615 | 315827.99 | CP-26-077 | Reliability - distribution | 2026-07-01
CM-000616 | 437929.33 | CP-26-077 | Reliability - distribution | 2026-08-01
CM-000617 | 1286576.11 | CP-26-078 | Reliability - distribution | 2026-01-01
CM-000618 | 1227406.37 | CP-26-078 | Reliability - distribution | 2026-02-01
CM-000619 | 1812472.75 | CP-26-078 | Reliability - distribution | 2026-03-01
CM-000620 | 1881448.61 | CP-26-078 | Reliability - distribution | 2026-04-01
CM-000621 | 1637131.77 | CP-26-078 | Reliability - distribution | 2026-05-01
CM-000622 | 1826797.18 | CP-26-078 | Reliability - distribution | 2026-06-01
CM-000623 | 2053820.98 | CP-26-078 | Reliability - distribution | 2026-07-01
CM-000624 | 1615033.23 | CP-26-078 | Reliability - distribution | 2026-08-01
CM-000625 | 366819.34 | CP-26-079 | Reliability - distribution | 2026-01-01
CM-000626 | 414820.9 | CP-26-079 | Reliability - distribution | 2026-02-01
CM-000627 | 529680.3 | CP-26-079 | Reliability - distribution | 2026-03-01
CM-000628 | 550446.31 | CP-26-079 | Reliability - distribution | 2026-04-01
CM-000629 | 353426.51 | CP-26-079 | Reliability - distribution | 2026-05-01
CM-000630 | 574216.99 | CP-26-079 | Reliability - distribution | 2026-06-01
CM-000631 | 548760.06 | CP-26-079 | Reliability - distribution | 2026-07-01
CM-000632 | 632128.59 | CP-26-079 | Reliability - distribution | 2026-08-01
CM-000633 | 627951.94 | CP-26-080 | Reliability - distribution | 2026-01-01
CM-000634 | 660137.71 | CP-26-080 | Reliability - distribution | 2026-02-01
CM-000635 | 573756.09 | CP-26-080 | Reliability - distribution | 2026-03-01
CM-000636 | 531954.9 | CP-26-080 | Reliability - distribution | 2026-04-01
CM-000637 | 502134.21 | CP-26-080 | Reliability - distribution | 2026-05-01
CM-000638 | 498855.3 | CP-26-080 | Reliability - distribution | 2026-06-01
CM-000639 | 715143.44 | CP-26-080 | Reliability - distribution | 2026-07-01
CM-000640 | 583952.41 | CP-26-080 | Reliability - distribution | 2026-08-01
CM-000641 | 405862.12 | CP-26-081 | Reliability - distribution | 2026-01-01
CM-000642 | 600396.02 | CP-26-081 | Reliability - distribution | 2026-02-01
CM-000643 | 568498.31 | CP-26-081 | Reliability - distribution | 2026-03-01
CM-000644 | 614805.45 | CP-26-081 | Reliability - distribution | 2026-04-01
CM-000645 | 547672.17 | CP-26-081 | Reliability - distribution | 2026-05-01
CM-000646 | 639323.94 | CP-26-081 | Reliability - distribution | 2026-06-01
CM-000647 | 521733.54 | CP-26-081 | Reliability - distribution | 2026-07-01
CM-000648 | 631960.45 | CP-26-081 | Reliability - distribution | 2026-08-01
CM-000649 | 118102.55 | CP-26-082 | Reliability - distribution | 2026-01-01
CM-000650 | 96712.69 | CP-26-082 | Reliability - distribution | 2026-02-01
CM-000651 | 139670.34 | CP-26-082 | Reliability - distribution | 2026-03-01
CM-000652 | 148603.65 | CP-26-082 | Reliability - distribution | 2026-04-01
CM-000653 | 162704.21 | CP-26-082 | Reliability - distribution | 2026-05-01
CM-000654 | 144265.5 | CP-26-082 | Reliability - distribution | 2026-06-01
CM-000655 | 179629.01 | CP-26-082 | Reliability - distribution | 2026-07-01
CM-000656 | 123828.05 | CP-26-082 | Reliability - distribution | 2026-08-01
CM-000657 | 0 | CP-26-083 | Reliability - distribution | 2026-01-01
CM-000658 | 0 | CP-26-083 | Reliability - distribution | 2026-02-01
CM-000659 | 0 | CP-26-083 | Reliability - distribution | 2026-03-01
CM-000660 | 0 | CP-26-083 | Reliability - distribution | 2026-04-01
CM-000661 | 0 | CP-26-083 | Reliability - distribution | 2026-05-01
CM-000662 | 2086014 | CP-26-083 | Reliability - distribution | 2026-06-01
CM-000663 | 4172028 | CP-26-083 | Reliability - distribution | 2026-07-01
CM-000664 | 4172028 | CP-26-083 | Reliability - distribution | 2026-08-01
CM-000665 | 378446.47 | CP-26-084 | Reliability - distribution | 2026-01-01
CM-000666 | 259506.84 | CP-26-084 | Reliability - distribution | 2026-02-01
CM-000667 | 382787.37 | CP-26-084 | Reliability - distribution | 2026-03-01
CM-000668 | 456220.29 | CP-26-084 | Reliability - distribution | 2026-04-01
CM-000669 | 430214.7 | CP-26-084 | Reliability - distribution | 2026-05-01
CM-000670 | 319693.67 | CP-26-084 | Reliability - distribution | 2026-06-01
CM-000671 | 457053.83 | CP-26-084 | Reliability - distribution | 2026-07-01
CM-000672 | 346733.83 | CP-26-084 | Reliability - distribution | 2026-08-01
CM-000673 | 42091.74 | CP-26-085 | Metering | 2026-01-01
CM-000674 | 42091.74 | CP-26-085 | Metering | 2026-02-01
CM-000675 | 63137.61 | CP-26-085 | Metering | 2026-03-01
CM-000676 | 63137.61 | CP-26-085 | Metering | 2026-04-01
CM-000677 | 105229.35 | CP-26-085 | Metering | 2026-05-01
CM-000678 | 210458.7 | CP-26-085 | Metering | 2026-06-01
CM-000679 | 526146.75 | CP-26-085 | Metering | 2026-07-01
CM-000680 | 1052293.5 | CP-26-085 | Metering | 2026-08-01
CM-000681 | 165634.41 | CP-26-086 | Metering | 2026-01-01
CM-000682 | 184398.21 | CP-26-086 | Metering | 2026-02-01
CM-000683 | 247413.91 | CP-26-086 | Metering | 2026-03-01
CM-000684 | 172355.7 | CP-26-086 | Metering | 2026-04-01
CM-000685 | 251203.6 | CP-26-086 | Metering | 2026-05-01
CM-000686 | 215411.38 | CP-26-086 | Metering | 2026-06-01
CM-000687 | 172332.17 | CP-26-086 | Metering | 2026-07-01
CM-000688 | 276259.62 | CP-26-086 | Metering | 2026-08-01
CM-000689 | 254099.83 | CP-26-087 | Metering | 2026-01-01
CM-000690 | 222756.37 | CP-26-087 | Metering | 2026-02-01
CM-000691 | 377955.35 | CP-26-087 | Metering | 2026-03-01
CM-000692 | 313565.43 | CP-26-087 | Metering | 2026-04-01
CM-000693 | 261925.34 | CP-26-087 | Metering | 2026-05-01
CM-000694 | 396536.05 | CP-26-087 | Metering | 2026-06-01
CM-000695 | 310100.75 | CP-26-087 | Metering | 2026-07-01
CM-000696 | 273464.88 | CP-26-087 | Metering | 2026-08-01
CM-000697 | 261139.34 | CP-26-088 | Facilities and fleet | 2026-01-01
CM-000698 | 185078.21 | CP-26-088 | Facilities and fleet | 2026-02-01
CM-000699 | 170069.53 | CP-26-088 | Facilities and fleet | 2026-03-01
CM-000700 | 309758.88 | CP-26-088 | Facilities and fleet | 2026-04-01
CM-000701 | 267862.63 | CP-26-088 | Facilities and fleet | 2026-05-01
CM-000702 | 285793.57 | CP-26-088 | Facilities and fleet | 2026-06-01
CM-000703 | 283062.1 | CP-26-088 | Facilities and fleet | 2026-07-01
CM-000704 | 246344.74 | CP-26-088 | Facilities and fleet | 2026-08-01
CM-000705 | 147452.63 | CP-26-089 | Facilities and fleet | 2026-01-01
CM-000706 | 224037.84 | CP-26-089 | Facilities and fleet | 2026-02-01
CM-000707 | 303337.64 | CP-26-089 | Facilities and fleet | 2026-03-01
CM-000708 | 232285.95 | CP-26-089 | Facilities and fleet | 2026-04-01
CM-000709 | 168611.97 | CP-26-089 | Facilities and fleet | 2026-05-01
CM-000710 | 211069.21 | CP-26-089 | Facilities and fleet | 2026-06-01
CM-000711 | 326692.47 | CP-26-089 | Facilities and fleet | 2026-07-01
CM-000712 | 333918.29 | CP-26-089 | Facilities and fleet | 2026-08-01
CM-000713 | 383161.42 | CP-26-090 | Facilities and fleet | 2026-01-01
CM-000714 | 359857.2 | CP-26-090 | Facilities and fleet | 2026-02-01
CM-000715 | 474419.2 | CP-26-090 | Facilities and fleet | 2026-03-01
CM-000716 | 383201.66 | CP-26-090 | Facilities and fleet | 2026-04-01
CM-000717 | 475363.78 | CP-26-090 | Facilities and fleet | 2026-05-01
CM-000718 | 388774.85 | CP-26-090 | Facilities and fleet | 2026-06-01
CM-000719 | 482190.42 | CP-26-090 | Facilities and fleet | 2026-07-01
CM-000720 | 385419.47 | CP-26-090 | Facilities and fleet | 2026-08-01
CM-000721 | 171504.42 | CP-26-091 | Facilities and fleet | 2026-01-01
CM-000722 | 162314.48 | CP-26-091 | Facilities and fleet | 2026-02-01
CM-000723 | 278876.68 | CP-26-091 | Facilities and fleet | 2026-03-01
CM-000724 | 302744.16 | CP-26-091 | Facilities and fleet | 2026-04-01
CM-000725 | 252956.44 | CP-26-091 | Facilities and fleet | 2026-05-01
CM-000726 | 181990.25 | CP-26-091 | Facilities and fleet | 2026-06-01
CM-000727 | 220288.37 | CP-26-091 | Facilities and fleet | 2026-07-01
CM-000728 | 311977.2 | CP-26-091 | Facilities and fleet | 2026-08-01
CM-000729 | 108593.56 | CP-26-092 | Facilities and fleet | 2026-01-01
CM-000730 | 90198.99 | CP-26-092 | Facilities and fleet | 2026-02-01
CM-000731 | 118601.12 | CP-26-092 | Facilities and fleet | 2026-03-01
CM-000732 | 144268.39 | CP-26-092 | Facilities and fleet | 2026-04-01
CM-000733 | 93719.31 | CP-26-092 | Facilities and fleet | 2026-05-01
CM-000734 | 98764.54 | CP-26-092 | Facilities and fleet | 2026-06-01
CM-000735 | 169888.36 | CP-26-092 | Facilities and fleet | 2026-07-01
CM-000736 | 118450.73 | CP-26-092 | Facilities and fleet | 2026-08-01
CM-000737 | 303107.18 | CP-26-093 | Facilities and fleet | 2026-01-01
CM-000738 | 397146.07 | CP-26-093 | Facilities and fleet | 2026-02-01
CM-000739 | 574952.86 | CP-26-093 | Facilities and fleet | 2026-03-01
CM-000740 | 440308.83 | CP-26-093 | Facilities and fleet | 2026-04-01
CM-000741 | 487380.66 | CP-26-093 | Facilities and fleet | 2026-05-01
CM-000742 | 516588.99 | CP-26-093 | Facilities and fleet | 2026-06-01
CM-000743 | 663545.85 | CP-26-093 | Facilities and fleet | 2026-07-01
CM-000744 | 692224.56 | CP-26-093 | Facilities and fleet | 2026-08-01
CM-000745 | 725284.7 | CP-26-094 | Facilities and fleet | 2026-01-01
CM-000746 | 721906.46 | CP-26-094 | Facilities and fleet | 2026-02-01
CM-000747 | 850432.02 | CP-26-094 | Facilities and fleet | 2026-03-01
CM-000748 | 852955.29 | CP-26-094 | Facilities and fleet | 2026-04-01
CM-000749 | 712150.41 | CP-26-094 | Facilities and fleet | 2026-05-01
CM-000750 | 1004276.8 | CP-26-094 | Facilities and fleet | 2026-06-01
CM-000751 | 1094279.68 | CP-26-094 | Facilities and fleet | 2026-07-01
CM-000752 | 1206635.64 | CP-26-094 | Facilities and fleet | 2026-08-01
CM-000753 | 167587.13 | CP-26-095 | Facilities and fleet | 2026-01-01
CM-000754 | 159505.71 | CP-26-095 | Facilities and fleet | 2026-02-01
CM-000755 | 163163.11 | CP-26-095 | Facilities and fleet | 2026-03-01
CM-000756 | 200986.62 | CP-26-095 | Facilities and fleet | 2026-04-01
CM-000757 | 161502.68 | CP-26-095 | Facilities and fleet | 2026-05-01
CM-000758 | 156101.68 | CP-26-095 | Facilities and fleet | 2026-06-01
CM-000759 | 162013.77 | CP-26-095 | Facilities and fleet | 2026-07-01
CM-000760 | 271923.3 | CP-26-095 | Facilities and fleet | 2026-08-01
CM-000761 | 0 | CP-26-096 | IT and OT | 2026-01-01
CM-000762 | 0 | CP-26-096 | IT and OT | 2026-02-01
CM-000763 | 0 | CP-26-096 | IT and OT | 2026-03-01
CM-000764 | 0 | CP-26-096 | IT and OT | 2026-04-01
CM-000765 | 0 | CP-26-096 | IT and OT | 2026-05-01
CM-000766 | 170646.4 | CP-26-096 | IT and OT | 2026-06-01
CM-000767 | 341292.8 | CP-26-096 | IT and OT | 2026-07-01
CM-000768 | 341292.8 | CP-26-096 | IT and OT | 2026-08-01
CM-000769 | 108051.05 | CP-26-097 | IT and OT | 2026-01-01
CM-000770 | 97706.09 | CP-26-097 | IT and OT | 2026-02-01
CM-000771 | 157031.44 | CP-26-097 | IT and OT | 2026-03-01
CM-000772 | 127092.91 | CP-26-097 | IT and OT | 2026-04-01
CM-000773 | 173288.57 | CP-26-097 | IT and OT | 2026-05-01
CM-000774 | 133548.74 | CP-26-097 | IT and OT | 2026-06-01
CM-000775 | 208948.27 | CP-26-097 | IT and OT | 2026-07-01
CM-000776 | 199359.93 | CP-26-097 | IT and OT | 2026-08-01
CM-000777 | 456552.08 | CP-26-098 | IT and OT | 2026-01-01
CM-000778 | 338790.79 | CP-26-098 | IT and OT | 2026-02-01
CM-000779 | 354520.33 | CP-26-098 | IT and OT | 2026-03-01
CM-000780 | 436422.84 | CP-26-098 | IT and OT | 2026-04-01
CM-000781 | 544927.29 | CP-26-098 | IT and OT | 2026-05-01
CM-000782 | 345998.56 | CP-26-098 | IT and OT | 2026-06-01
CM-000783 | 609263.5 | CP-26-098 | IT and OT | 2026-07-01
CM-000784 | 702501.61 | CP-26-098 | IT and OT | 2026-08-01
CM-000785 | 107548 | CP-26-099 | IT and OT | 2026-01-01
CM-000786 | 109191.67 | CP-26-099 | IT and OT | 2026-02-01
CM-000787 | 149421.49 | CP-26-099 | IT and OT | 2026-03-01
CM-000788 | 155090.09 | CP-26-099 | IT and OT | 2026-04-01
CM-000789 | 160888.56 | CP-26-099 | IT and OT | 2026-05-01
CM-000790 | 113552.33 | CP-26-099 | IT and OT | 2026-06-01
CM-000791 | 120151.41 | CP-26-099 | IT and OT | 2026-07-01
CM-000792 | 202933.45 | CP-26-099 | IT and OT | 2026-08-01
CM-000793 | 20721.68 | CP-26-100 | IT and OT | 2026-01-01
CM-000794 | 28382.97 | CP-26-100 | IT and OT | 2026-02-01
CM-000795 | 27264.27 | CP-26-100 | IT and OT | 2026-03-01
CM-000796 | 39241.15 | CP-26-100 | IT and OT | 2026-04-01
CM-000797 | 35215.81 | CP-26-100 | IT and OT | 2026-05-01
CM-000798 | 42165.77 | CP-26-100 | IT and OT | 2026-06-01
CM-000799 | 46856.71 | CP-26-100 | IT and OT | 2026-07-01
CM-000800 | 29575.64 | CP-26-100 | IT and OT | 2026-08-01
CM-000801 | 567895.37 | CP-26-101 | IT and OT | 2026-01-01
CM-000802 | 651028.26 | CP-26-101 | IT and OT | 2026-02-01
CM-000803 | 580493.62 | CP-26-101 | IT and OT | 2026-03-01
CM-000804 | 576315.93 | CP-26-101 | IT and OT | 2026-04-01
CM-000805 | 427380.11 | CP-26-101 | IT and OT | 2026-05-01
CM-000806 | 438887.88 | CP-26-101 | IT and OT | 2026-06-01
CM-000807 | 470915.01 | CP-26-101 | IT and OT | 2026-07-01
CM-000808 | 482187.82 | CP-26-101 | IT and OT | 2026-08-01
CM-000809 | 0 | CP-26-102 | IT and OT | 2026-01-01
CM-000810 | 0 | CP-26-102 | IT and OT | 2026-02-01
CM-000811 | 0 | CP-26-102 | IT and OT | 2026-03-01
CM-000812 | 0 | CP-26-102 | IT and OT | 2026-04-01
CM-000813 | 0 | CP-26-102 | IT and OT | 2026-05-01
CM-000814 | 334780.2 | CP-26-102 | IT and OT | 2026-06-01
CM-000815 | 669560.4 | CP-26-102 | IT and OT | 2026-07-01
CM-000816 | 669560.4 | CP-26-102 | IT and OT | 2026-08-01
CM-000817 | 223840.36 | CP-26-103 | IT and OT | 2026-01-01
CM-000818 | 366613.25 | CP-26-103 | IT and OT | 2026-02-01
CM-000819 | 329267.51 | CP-26-103 | IT and OT | 2026-03-01
CM-000820 | 446585.71 | CP-26-103 | IT and OT | 2026-04-01
CM-000821 | 421388.28 | CP-26-103 | IT and OT | 2026-05-01
CM-000822 | 314011.27 | CP-26-103 | IT and OT | 2026-06-01
CM-000823 | 395098.89 | CP-26-103 | IT and OT | 2026-07-01
CM-000824 | 466151.73 | CP-26-103 | IT and OT | 2026-08-01
CM-000825 | 122515.68 | CP-26-104 | IT and OT | 2026-01-01
CM-000826 | 78326.1 | CP-26-104 | IT and OT | 2026-02-01
CM-000827 | 137599.07 | CP-26-104 | IT and OT | 2026-03-01
CM-000828 | 154935.26 | CP-26-104 | IT and OT | 2026-04-01
CM-000829 | 119072.22 | CP-26-104 | IT and OT | 2026-05-01
CM-000830 | 144620.39 | CP-26-104 | IT and OT | 2026-06-01
CM-000831 | 99394.61 | CP-26-104 | IT and OT | 2026-07-01
CM-000832 | 108076.67 | CP-26-104 | IT and OT | 2026-08-01
CM-000833 | 37107.03 | CP-26-105 | IT and OT | 2026-01-01
CM-000834 | 38302.7 | CP-26-105 | IT and OT | 2026-02-01
CM-000835 | 33795.46 | CP-26-105 | IT and OT | 2026-03-01
CM-000836 | 60106.6 | CP-26-105 | IT and OT | 2026-04-01
CM-000837 | 42987.44 | CP-26-105 | IT and OT | 2026-05-01
CM-000838 | 61530.18 | CP-26-105 | IT and OT | 2026-06-01
CM-000839 | 40834.05 | CP-26-105 | IT and OT | 2026-07-01
CM-000840 | 53397.54 | CP-26-105 | IT and OT | 2026-08-01
CM-000841 | 174560.11 | CP-26-106 | Gas - pipe replacement | 2026-01-01
CM-000842 | 162903.77 | CP-26-106 | Gas - pipe replacement | 2026-02-01
CM-000843 | 162420.75 | CP-26-106 | Gas - pipe replacement | 2026-03-01
CM-000844 | 180040.67 | CP-26-106 | Gas - pipe replacement | 2026-04-01
CM-000845 | 142523.52 | CP-26-106 | Gas - pipe replacement | 2026-05-01
CM-000846 | 201681.36 | CP-26-106 | Gas - pipe replacement | 2026-06-01
CM-000847 | 178954.41 | CP-26-106 | Gas - pipe replacement | 2026-07-01
CM-000848 | 162889.41 | CP-26-106 | Gas - pipe replacement | 2026-08-01
CM-000849 | 166636.86 | CP-26-107 | Gas - pipe replacement | 2026-01-01
CM-000850 | 215917.03 | CP-26-107 | Gas - pipe replacement | 2026-02-01
CM-000851 | 225766.61 | CP-26-107 | Gas - pipe replacement | 2026-03-01
CM-000852 | 275764.55 | CP-26-107 | Gas - pipe replacement | 2026-04-01
CM-000853 | 319097.09 | CP-26-107 | Gas - pipe replacement | 2026-05-01
CM-000854 | 324692.84 | CP-26-107 | Gas - pipe replacement | 2026-06-01
CM-000855 | 303331.09 | CP-26-107 | Gas - pipe replacement | 2026-07-01
CM-000856 | 396129.93 | CP-26-107 | Gas - pipe replacement | 2026-08-01
CM-000857 | 397592.84 | CP-26-108 | Gas - pipe replacement | 2026-01-01
CM-000858 | 262780.75 | CP-26-108 | Gas - pipe replacement | 2026-02-01
CM-000859 | 437425.34 | CP-26-108 | Gas - pipe replacement | 2026-03-01
CM-000860 | 493714.9 | CP-26-108 | Gas - pipe replacement | 2026-04-01
CM-000861 | 418159.84 | CP-26-108 | Gas - pipe replacement | 2026-05-01
CM-000862 | 336287.18 | CP-26-108 | Gas - pipe replacement | 2026-06-01
CM-000863 | 554227.64 | CP-26-108 | Gas - pipe replacement | 2026-07-01
CM-000864 | 484686.51 | CP-26-108 | Gas - pipe replacement | 2026-08-01
CM-000865 | 455120.27 | CP-26-109 | Gas - pipe replacement | 2026-01-01
CM-000866 | 490143.87 | CP-26-109 | Gas - pipe replacement | 2026-02-01
CM-000867 | 500231.12 | CP-26-109 | Gas - pipe replacement | 2026-03-01
CM-000868 | 331752.71 | CP-26-109 | Gas - pipe replacement | 2026-04-01
CM-000869 | 359852.98 | CP-26-109 | Gas - pipe replacement | 2026-05-01
CM-000870 | 538814.08 | CP-26-109 | Gas - pipe replacement | 2026-06-01
CM-000871 | 531958.69 | CP-26-109 | Gas - pipe replacement | 2026-07-01
CM-000872 | 508531.28 | CP-26-109 | Gas - pipe replacement | 2026-08-01
CM-000873 | 625012.36 | CP-26-110 | Gas - pipe replacement | 2026-01-01
CM-000874 | 724175.65 | CP-26-110 | Gas - pipe replacement | 2026-02-01
CM-000875 | 816339.49 | CP-26-110 | Gas - pipe replacement | 2026-03-01
CM-000876 | 977185.53 | CP-26-110 | Gas - pipe replacement | 2026-04-01
CM-000877 | 530141.48 | CP-26-110 | Gas - pipe replacement | 2026-05-01
CM-000878 | 825036.74 | CP-26-110 | Gas - pipe replacement | 2026-06-01
CM-000879 | 1104355.56 | CP-26-110 | Gas - pipe replacement | 2026-07-01
CM-000880 | 1047990.19 | CP-26-110 | Gas - pipe replacement | 2026-08-01
CM-000881 | 170773.46 | CP-26-111 | Gas - pipe replacement | 2026-01-01
CM-000882 | 187179.42 | CP-26-111 | Gas - pipe replacement | 2026-02-01
CM-000883 | 163097.46 | CP-26-111 | Gas - pipe replacement | 2026-03-01
CM-000884 | 191588.6 | CP-26-111 | Gas - pipe replacement | 2026-04-01
CM-000885 | 258050.07 | CP-26-111 | Gas - pipe replacement | 2026-05-01
CM-000886 | 276387.67 | CP-26-111 | Gas - pipe replacement | 2026-06-01
CM-000887 | 286693.38 | CP-26-111 | Gas - pipe replacement | 2026-07-01
CM-000888 | 215243.94 | CP-26-111 | Gas - pipe replacement | 2026-08-01
CM-000889 | 466196.93 | CP-26-112 | Gas - pipe replacement | 2026-01-01
CM-000890 | 605066.48 | CP-26-112 | Gas - pipe replacement | 2026-02-01
CM-000891 | 504137.39 | CP-26-112 | Gas - pipe replacement | 2026-03-01
CM-000892 | 489402.67 | CP-26-112 | Gas - pipe replacement | 2026-04-01
CM-000893 | 511527.42 | CP-26-112 | Gas - pipe replacement | 2026-05-01
CM-000894 | 581645.03 | CP-26-112 | Gas - pipe replacement | 2026-06-01
CM-000895 | 766352.29 | CP-26-112 | Gas - pipe replacement | 2026-07-01
CM-000896 | 821271.79 | CP-26-112 | Gas - pipe replacement | 2026-08-01
CM-000897 | 94451.18 | CP-26-113 | Gas - pipe replacement | 2026-01-01
CM-000898 | 62141.83 | CP-26-113 | Gas - pipe replacement | 2026-02-01
CM-000899 | 82170.97 | CP-26-113 | Gas - pipe replacement | 2026-03-01
CM-000900 | 68513.68 | CP-26-113 | Gas - pipe replacement | 2026-04-01
CM-000901 | 92358.15 | CP-26-113 | Gas - pipe replacement | 2026-05-01
CM-000902 | 65872.47 | CP-26-113 | Gas - pipe replacement | 2026-06-01
CM-000903 | 95291.05 | CP-26-113 | Gas - pipe replacement | 2026-07-01
CM-000904 | 105412.67 | CP-26-113 | Gas - pipe replacement | 2026-08-01
CM-000905 | 237624.69 | CP-26-114 | Gas - pipe replacement | 2026-01-01
CM-000906 | 414488.87 | CP-26-114 | Gas - pipe replacement | 2026-02-01
CM-000907 | 374145.12 | CP-26-114 | Gas - pipe replacement | 2026-03-01
CM-000908 | 284868.32 | CP-26-114 | Gas - pipe replacement | 2026-04-01
CM-000909 | 358794.81 | CP-26-114 | Gas - pipe replacement | 2026-05-01
CM-000910 | 497847.36 | CP-26-114 | Gas - pipe replacement | 2026-06-01
CM-000911 | 385691.32 | CP-26-114 | Gas - pipe replacement | 2026-07-01
CM-000912 | 410936.51 | CP-26-114 | Gas - pipe replacement | 2026-08-01
CM-000913 | 427009.8 | CP-26-115 | Gas - pipe replacement | 2026-01-01
CM-000914 | 549161.48 | CP-26-115 | Gas - pipe replacement | 2026-02-01
CM-000915 | 388349.16 | CP-26-115 | Gas - pipe replacement | 2026-03-01
CM-000916 | 466037.83 | CP-26-115 | Gas - pipe replacement | 2026-04-01
CM-000917 | 589813.5 | CP-26-115 | Gas - pipe replacement | 2026-05-01
CM-000918 | 381115.39 | CP-26-115 | Gas - pipe replacement | 2026-06-01
CM-000919 | 503384.3 | CP-26-115 | Gas - pipe replacement | 2026-07-01
CM-000920 | 747198.54 | CP-26-115 | Gas - pipe replacement | 2026-08-01
CM-000921 | 998287.95 | CP-26-116 | Gas - pipe replacement | 2026-01-01
CM-000922 | 1271832.69 | CP-26-116 | Gas - pipe replacement | 2026-02-01
CM-000923 | 1460730.31 | CP-26-116 | Gas - pipe replacement | 2026-03-01
CM-000924 | 1102575.64 | CP-26-116 | Gas - pipe replacement | 2026-04-01
CM-000925 | 1423802.37 | CP-26-116 | Gas - pipe replacement | 2026-05-01
CM-000926 | 977234.91 | CP-26-116 | Gas - pipe replacement | 2026-06-01
CM-000927 | 1734394.02 | CP-26-116 | Gas - pipe replacement | 2026-07-01
CM-000928 | 1261610.11 | CP-26-116 | Gas - pipe replacement | 2026-08-01
CM-000929 | 285238.73 | CP-26-117 | Gas - pipe replacement | 2026-01-01
CM-000930 | 312552.61 | CP-26-117 | Gas - pipe replacement | 2026-02-01
CM-000931 | 443104.86 | CP-26-117 | Gas - pipe replacement | 2026-03-01
CM-000932 | 327694.92 | CP-26-117 | Gas - pipe replacement | 2026-04-01
CM-000933 | 452136.93 | CP-26-117 | Gas - pipe replacement | 2026-05-01
CM-000934 | 379975.45 | CP-26-117 | Gas - pipe replacement | 2026-06-01
CM-000935 | 418466.76 | CP-26-117 | Gas - pipe replacement | 2026-07-01
CM-000936 | 444478.74 | CP-26-117 | Gas - pipe replacement | 2026-08-01
CM-000937 | 149254.79 | CP-26-118 | Gas - pipe replacement | 2026-01-01
CM-000938 | 263208.53 | CP-26-118 | Gas - pipe replacement | 2026-02-01
CM-000939 | 189072.19 | CP-26-118 | Gas - pipe replacement | 2026-03-01
CM-000940 | 241456.29 | CP-26-118 | Gas - pipe replacement | 2026-04-01
CM-000941 | 211622.81 | CP-26-118 | Gas - pipe replacement | 2026-05-01
CM-000942 | 307338.07 | CP-26-118 | Gas - pipe replacement | 2026-06-01
CM-000943 | 230808.06 | CP-26-118 | Gas - pipe replacement | 2026-07-01
CM-000944 | 301272.26 | CP-26-118 | Gas - pipe replacement | 2026-08-01
CM-000945 | 344898.23 | CP-26-119 | Gas - pipe replacement | 2026-01-01
CM-000946 | 334681.07 | CP-26-119 | Gas - pipe replacement | 2026-02-01
CM-000947 | 264639.68 | CP-26-119 | Gas - pipe replacement | 2026-03-01
CM-000948 | 284129.63 | CP-26-119 | Gas - pipe replacement | 2026-04-01
CM-000949 | 257352.23 | CP-26-119 | Gas - pipe replacement | 2026-05-01
CM-000950 | 231834.9 | CP-26-119 | Gas - pipe replacement | 2026-06-01
CM-000951 | 447127.85 | CP-26-119 | Gas - pipe replacement | 2026-07-01
CM-000952 | 425066.41 | CP-26-119 | Gas - pipe replacement | 2026-08-01
CM-000953 | 329140.65 | CP-26-120 | Gas - system reinforcement | 2026-01-01
CM-000954 | 229274.6 | CP-26-120 | Gas - system reinforcement | 2026-02-01
CM-000955 | 373480.26 | CP-26-120 | Gas - system reinforcement | 2026-03-01
CM-000956 | 308652.76 | CP-26-120 | Gas - system reinforcement | 2026-04-01
CM-000957 | 232328.35 | CP-26-120 | Gas - system reinforcement | 2026-05-01
CM-000958 | 307604.77 | CP-26-120 | Gas - system reinforcement | 2026-06-01
CM-000959 | 366123.34 | CP-26-120 | Gas - system reinforcement | 2026-07-01
CM-000960 | 391998.27 | CP-26-120 | Gas - system reinforcement | 2026-08-01
CM-000961 | 305884.36 | CP-26-121 | Gas - system reinforcement | 2026-01-01
CM-000962 | 274255.97 | CP-26-121 | Gas - system reinforcement | 2026-02-01
CM-000963 | 381776.9 | CP-26-121 | Gas - system reinforcement | 2026-03-01
CM-000964 | 313002.57 | CP-26-121 | Gas - system reinforcement | 2026-04-01
CM-000965 | 313625.82 | CP-26-121 | Gas - system reinforcement | 2026-05-01
CM-000966 | 331055.47 | CP-26-121 | Gas - system reinforcement | 2026-06-01
CM-000967 | 419093.08 | CP-26-121 | Gas - system reinforcement | 2026-07-01
CM-000968 | 310877.83 | CP-26-121 | Gas - system reinforcement | 2026-08-01
CM-000969 | 92528.16 | CP-26-122 | Gas - system reinforcement | 2026-01-01
CM-000970 | 181338.62 | CP-26-122 | Gas - system reinforcement | 2026-02-01
CM-000971 | 108253.87 | CP-26-122 | Gas - system reinforcement | 2026-03-01
CM-000972 | 152479.34 | CP-26-122 | Gas - system reinforcement | 2026-04-01
CM-000973 | 138315.45 | CP-26-122 | Gas - system reinforcement | 2026-05-01
CM-000974 | 138642.66 | CP-26-122 | Gas - system reinforcement | 2026-06-01
CM-000975 | 186165.26 | CP-26-122 | Gas - system reinforcement | 2026-07-01
CM-000976 | 189631.64 | CP-26-122 | Gas - system reinforcement | 2026-08-01
CM-000977 | 0 | CP-26-123 | Gas - system reinforcement | 2026-01-01
CM-000978 | 0 | CP-26-123 | Gas - system reinforcement | 2026-02-01
CM-000979 | 0 | CP-26-123 | Gas - system reinforcement | 2026-03-01
CM-000980 | 0 | CP-26-123 | Gas - system reinforcement | 2026-04-01
CM-000981 | 0 | CP-26-123 | Gas - system reinforcement | 2026-05-01
CM-000982 | 415367.8 | CP-26-123 | Gas - system reinforcement | 2026-06-01
CM-000983 | 830735.6 | CP-26-123 | Gas - system reinforcement | 2026-07-01
CM-000984 | 830735.6 | CP-26-123 | Gas - system reinforcement | 2026-08-01
CM-000985 | 244330.78 | CP-26-124 | Gas - system reinforcement | 2026-01-01
CM-000986 | 329266.56 | CP-26-124 | Gas - system reinforcement | 2026-02-01
CM-000987 | 268365.9 | CP-26-124 | Gas - system reinforcement | 2026-03-01
CM-000988 | 432929.83 | CP-26-124 | Gas - system reinforcement | 2026-04-01
CM-000989 | 319751.76 | CP-26-124 | Gas - system reinforcement | 2026-05-01
CM-000990 | 450273.71 | CP-26-124 | Gas - system reinforcement | 2026-06-01
CM-000991 | 517367.19 | CP-26-124 | Gas - system reinforcement | 2026-07-01
CM-000992 | 334372.27 | CP-26-124 | Gas - system reinforcement | 2026-08-01
CM-000993 | 326756.29 | CP-26-125 | Gas - system reinforcement | 2026-01-01
CM-000994 | 267836.24 | CP-26-125 | Gas - system reinforcement | 2026-02-01
CM-000995 | 320516.15 | CP-26-125 | Gas - system reinforcement | 2026-03-01
CM-000996 | 226277.13 | CP-26-125 | Gas - system reinforcement | 2026-04-01
CM-000997 | 233676.06 | CP-26-125 | Gas - system reinforcement | 2026-05-01
CM-000998 | 306196.74 | CP-26-125 | Gas - system reinforcement | 2026-06-01
CM-000999 | 303696.17 | CP-26-125 | Gas - system reinforcement | 2026-07-01
CM-001000 | 354501.22 | CP-26-125 | Gas - system reinforcement | 2026-08-01
CM-001001 | 309173.03 | CP-26-126 | Gas - system reinforcement | 2026-01-01
CM-001002 | 274344.4 | CP-26-126 | Gas - system reinforcement | 2026-02-01
CM-001003 | 404906.63 | CP-26-126 | Gas - system reinforcement | 2026-03-01
CM-001004 | 264458.96 | CP-26-126 | Gas - system reinforcement | 2026-04-01
CM-001005 | 252986.96 | CP-26-126 | Gas - system reinforcement | 2026-05-01
CM-001006 | 363107.19 | CP-26-126 | Gas - system reinforcement | 2026-06-01
CM-001007 | 392223.14 | CP-26-126 | Gas - system reinforcement | 2026-07-01
CM-001008 | 308810.69 | CP-26-126 | Gas - system reinforcement | 2026-08-01
CM-001009 | 316889.88 | CP-26-127 | Gas - system reinforcement | 2026-01-01
CM-001010 | 362986.43 | CP-26-127 | Gas - system reinforcement | 2026-02-01
CM-001011 | 370832.72 | CP-26-127 | Gas - system reinforcement | 2026-03-01
CM-001012 | 404938.73 | CP-26-127 | Gas - system reinforcement | 2026-04-01
CM-001013 | 241312.13 | CP-26-127 | Gas - system reinforcement | 2026-05-01
CM-001014 | 250146.41 | CP-26-127 | Gas - system reinforcement | 2026-06-01
CM-001015 | 292009.42 | CP-26-127 | Gas - system reinforcement | 2026-07-01
CM-001016 | 302730.28 | CP-26-127 | Gas - system reinforcement | 2026-08-01
CM-001017 | 579477.13 | CP-26-128 | Gas - system reinforcement | 2026-01-01
CM-001018 | 524740.89 | CP-26-128 | Gas - system reinforcement | 2026-02-01
CM-001019 | 757780.39 | CP-26-128 | Gas - system reinforcement | 2026-03-01
CM-001020 | 916718.33 | CP-26-128 | Gas - system reinforcement | 2026-04-01
CM-001021 | 624540.23 | CP-26-128 | Gas - system reinforcement | 2026-05-01
CM-001022 | 842024.81 | CP-26-128 | Gas - system reinforcement | 2026-06-01
CM-001023 | 748469.81 | CP-26-128 | Gas - system reinforcement | 2026-07-01
CM-001024 | 835220.41 | CP-26-128 | Gas - system reinforcement | 2026-08-01
CM-001025 | 720420.74 | CP-26-129 | Gas - system reinforcement | 2026-01-01
CM-001026 | 680338.8 | CP-26-129 | Gas - system reinforcement | 2026-02-01
CM-001027 | 818974.98 | CP-26-129 | Gas - system reinforcement | 2026-03-01
CM-001028 | 542652.27 | CP-26-129 | Gas - system reinforcement | 2026-04-01
CM-001029 | 682764.34 | CP-26-129 | Gas - system reinforcement | 2026-05-01
CM-001030 | 955293.02 | CP-26-129 | Gas - system reinforcement | 2026-06-01
CM-001031 | 947790.66 | CP-26-129 | Gas - system reinforcement | 2026-07-01
CM-001032 | 622453.19 | CP-26-129 | Gas - system reinforcement | 2026-08-01
CM-001033 | 459473.47 | CP-26-130 | Gas - new business and meters | 2026-01-01
CM-001034 | 471586.27 | CP-26-130 | Gas - new business and meters | 2026-02-01
CM-001035 | 745947.13 | CP-26-130 | Gas - new business and meters | 2026-03-01
CM-001036 | 633537.72 | CP-26-130 | Gas - new business and meters | 2026-04-01
CM-001037 | 522522.42 | CP-26-130 | Gas - new business and meters | 2026-05-01
CM-001038 | 743577.25 | CP-26-130 | Gas - new business and meters | 2026-06-01
CM-001039 | 798391.27 | CP-26-130 | Gas - new business and meters | 2026-07-01
CM-001040 | 785060.47 | CP-26-130 | Gas - new business and meters | 2026-08-01
CM-001041 | 268046.39 | CP-26-131 | Gas - new business and meters | 2026-01-01
CM-001042 | 323752.41 | CP-26-131 | Gas - new business and meters | 2026-02-01
CM-001043 | 198761.78 | CP-26-131 | Gas - new business and meters | 2026-03-01
CM-001044 | 222314.12 | CP-26-131 | Gas - new business and meters | 2026-04-01
CM-001045 | 261613.07 | CP-26-131 | Gas - new business and meters | 2026-05-01
CM-001046 | 222614 | CP-26-131 | Gas - new business and meters | 2026-06-01
CM-001047 | 383224.93 | CP-26-131 | Gas - new business and meters | 2026-07-01
CM-001048 | 406495.3 | CP-26-131 | Gas - new business and meters | 2026-08-01
CM-001049 | 125513.17 | CP-26-132 | Gas - new business and meters | 2026-01-01
CM-001050 | 101556.25 | CP-26-132 | Gas - new business and meters | 2026-02-01
CM-001051 | 159392.49 | CP-26-132 | Gas - new business and meters | 2026-03-01
CM-001052 | 119606.3 | CP-26-132 | Gas - new business and meters | 2026-04-01
CM-001053 | 157906.79 | CP-26-132 | Gas - new business and meters | 2026-05-01
CM-001054 | 132622.23 | CP-26-132 | Gas - new business and meters | 2026-06-01
CM-001055 | 172213.95 | CP-26-132 | Gas - new business and meters | 2026-07-01
CM-001056 | 123993.82 | CP-26-132 | Gas - new business and meters | 2026-08-01
CM-001057 | 238507.74 | CP-26-133 | Gas - new business and meters | 2026-01-01
CM-001058 | 213733.76 | CP-26-133 | Gas - new business and meters | 2026-02-01
CM-001059 | 354147.94 | CP-26-133 | Gas - new business and meters | 2026-03-01
CM-001060 | 440654.9 | CP-26-133 | Gas - new business and meters | 2026-04-01
CM-001061 | 249882.16 | CP-26-133 | Gas - new business and meters | 2026-05-01
CM-001062 | 413817.79 | CP-26-133 | Gas - new business and meters | 2026-06-01
CM-001063 | 400001.36 | CP-26-133 | Gas - new business and meters | 2026-07-01
CM-001064 | 334158.35 | CP-26-133 | Gas - new business and meters | 2026-08-01
CM-001065 | 151759.41 | CP-26-134 | Gas - new business and meters | 2026-01-01
CM-001066 | 236372.05 | CP-26-134 | Gas - new business and meters | 2026-02-01
CM-001067 | 197530.11 | CP-26-134 | Gas - new business and meters | 2026-03-01
CM-001068 | 238378.25 | CP-26-134 | Gas - new business and meters | 2026-04-01
CM-001069 | 201462.55 | CP-26-134 | Gas - new business and meters | 2026-05-01
CM-001070 | 298494.3 | CP-26-134 | Gas - new business and meters | 2026-06-01
CM-001071 | 180556.22 | CP-26-134 | Gas - new business and meters | 2026-07-01
CM-001072 | 210820.11 | CP-26-134 | Gas - new business and meters | 2026-08-01
CM-001073 | 55125.83 | CP-26-135 | IT and OT | 2026-01-01
CM-001074 | 52930.85 | CP-26-135 | IT and OT | 2026-02-01
CM-001075 | 62676.17 | CP-26-135 | IT and OT | 2026-03-01
CM-001076 | 83123.04 | CP-26-135 | IT and OT | 2026-04-01
CM-001077 | 55130.97 | CP-26-135 | IT and OT | 2026-05-01
CM-001078 | 108253.06 | CP-26-135 | IT and OT | 2026-06-01
CM-001079 | 64897.6 | CP-26-135 | IT and OT | 2026-07-01
CM-001080 | 97723.48 | CP-26-135 | IT and OT | 2026-08-01
CM-001081 | 242532.44 | CP-26-136 | IT and OT | 2026-01-01
CM-001082 | 377750.4 | CP-26-136 | IT and OT | 2026-02-01
CM-001083 | 300170.95 | CP-26-136 | IT and OT | 2026-03-01
CM-001084 | 385397.67 | CP-26-136 | IT and OT | 2026-04-01
CM-001085 | 406952.27 | CP-26-136 | IT and OT | 2026-05-01
CM-001086 | 459094.54 | CP-26-136 | IT and OT | 2026-06-01
CM-001087 | 296516.32 | CP-26-136 | IT and OT | 2026-07-01
CM-001088 | 575943.41 | CP-26-136 | IT and OT | 2026-08-01
CM-001089 | 251236.43 | CP-26-137 | IT and OT | 2026-01-01
CM-001090 | 227050.24 | CP-26-137 | IT and OT | 2026-02-01
CM-001091 | 325919.53 | CP-26-137 | IT and OT | 2026-03-01
CM-001092 | 296731.17 | CP-26-137 | IT and OT | 2026-04-01
CM-001093 | 247729.31 | CP-26-137 | IT and OT | 2026-05-01
CM-001094 | 271185.64 | CP-26-137 | IT and OT | 2026-06-01
CM-001095 | 330304.38 | CP-26-137 | IT and OT | 2026-07-01
CM-001096 | 272073.3 | CP-26-137 | IT and OT | 2026-08-01
CM-001097 | 51855.64 | CP-26-138 | IT and OT | 2026-01-01
CM-001098 | 77819.13 | CP-26-138 | IT and OT | 2026-02-01
CM-001099 | 62103.11 | CP-26-138 | IT and OT | 2026-03-01
CM-001100 | 66836.76 | CP-26-138 | IT and OT | 2026-04-01
CM-001101 | 100907.17 | CP-26-138 | IT and OT | 2026-05-01
CM-001102 | 103680.34 | CP-26-138 | IT and OT | 2026-06-01
CM-001103 | 117699.27 | CP-26-138 | IT and OT | 2026-07-01
CM-001104 | 104883.58 | CP-26-138 | IT and OT | 2026-08-01
CM-001105 | 111852.57 | CP-26-139 | IT and OT | 2026-01-01
CM-001106 | 100702.33 | CP-26-139 | IT and OT | 2026-02-01
CM-001107 | 171197.26 | CP-26-139 | IT and OT | 2026-03-01
CM-001108 | 155278.45 | CP-26-139 | IT and OT | 2026-04-01
CM-001109 | 126281.56 | CP-26-139 | IT and OT | 2026-05-01
CM-001110 | 105556.48 | CP-26-139 | IT and OT | 2026-06-01
CM-001111 | 123016.45 | CP-26-139 | IT and OT | 2026-07-01
CM-001112 | 174842.9 | CP-26-139 | IT and OT | 2026-08-01
CM-001113 | 296411.63 | CP-26-140 | IT and OT | 2026-01-01
CM-001114 | 295567.63 | CP-26-140 | IT and OT | 2026-02-01
CM-001115 | 344140.76 | CP-26-140 | IT and OT | 2026-03-01
CM-001116 | 325132.45 | CP-26-140 | IT and OT | 2026-04-01
CM-001117 | 220548.72 | CP-26-140 | IT and OT | 2026-05-01
CM-001118 | 282753.15 | CP-26-140 | IT and OT | 2026-06-01
CM-001119 | 319868.17 | CP-26-140 | IT and OT | 2026-07-01
CM-001120 | 318766.49 | CP-26-140 | IT and OT | 2026-08-01
CM-001121 | 123026 | CP-26-141 | IT and OT | 2026-01-01
CM-001122 | 152629.99 | CP-26-141 | IT and OT | 2026-02-01
CM-001123 | 128560.99 | CP-26-141 | IT and OT | 2026-03-01
CM-001124 | 138421.34 | CP-26-141 | IT and OT | 2026-04-01
CM-001125 | 179249.56 | CP-26-141 | IT and OT | 2026-05-01
CM-001126 | 189299.99 | CP-26-141 | IT and OT | 2026-06-01
CM-001127 | 172766.28 | CP-26-141 | IT and OT | 2026-07-01
CM-001128 | 143877.85 | CP-26-141 | IT and OT | 2026-08-01
CM-001129 | 123576.12 | CP-26-142 | IT and OT | 2026-01-01
CM-001130 | 90653.07 | CP-26-142 | IT and OT | 2026-02-01
CM-001131 | 106192.02 | CP-26-142 | IT and OT | 2026-03-01
CM-001132 | 90032.5 | CP-26-142 | IT and OT | 2026-04-01
CM-001133 | 112592.56 | CP-26-142 | IT and OT | 2026-05-01
CM-001134 | 91373.79 | CP-26-142 | IT and OT | 2026-06-01
CM-001135 | 96126.84 | CP-26-142 | IT and OT | 2026-07-01
CM-001136 | 99256.1 | CP-26-142 | IT and OT | 2026-08-01
CM-001137 | 102792.11 | CP-26-143 | IT and OT | 2026-01-01
CM-001138 | 163123.85 | CP-26-143 | IT and OT | 2026-02-01
CM-001139 | 167206.94 | CP-26-143 | IT and OT | 2026-03-01
CM-001140 | 177563.5 | CP-26-143 | IT and OT | 2026-04-01
CM-001141 | 133182.79 | CP-26-143 | IT and OT | 2026-05-01
CM-001142 | 206784.9 | CP-26-143 | IT and OT | 2026-06-01
CM-001143 | 181026.49 | CP-26-143 | IT and OT | 2026-07-01
CM-001144 | 205494.42 | CP-26-143 | IT and OT | 2026-08-01
CM-001145 | 121580.59 | CP-26-144 | IT and OT | 2026-01-01
CM-001146 | 174877.99 | CP-26-144 | IT and OT | 2026-02-01
CM-001147 | 132040.95 | CP-26-144 | IT and OT | 2026-03-01
CM-001148 | 159582.98 | CP-26-144 | IT and OT | 2026-04-01
CM-001149 | 110453.62 | CP-26-144 | IT and OT | 2026-05-01
CM-001150 | 191138.11 | CP-26-144 | IT and OT | 2026-06-01
CM-001151 | 147421.2 | CP-26-144 | IT and OT | 2026-07-01
CM-001152 | 183943.56 | CP-26-144 | IT and OT | 2026-08-01
CM-001153 | 40606.92 | CP-26-145 | Facilities and fleet | 2026-01-01
CM-001154 | 73000.45 | CP-26-145 | Facilities and fleet | 2026-02-01
CM-001155 | 80870.26 | CP-26-145 | Facilities and fleet | 2026-03-01
CM-001156 | 61775.02 | CP-26-145 | Facilities and fleet | 2026-04-01
CM-001157 | 60675.83 | CP-26-145 | Facilities and fleet | 2026-05-01
CM-001158 | 75364.05 | CP-26-145 | Facilities and fleet | 2026-06-01
CM-001159 | 72404.34 | CP-26-145 | Facilities and fleet | 2026-07-01
CM-001160 | 72660.13 | CP-26-145 | Facilities and fleet | 2026-08-01
CM-001161 | 15863.64 | CP-26-146 | Facilities and fleet | 2026-01-01
CM-001162 | 19858.01 | CP-26-146 | Facilities and fleet | 2026-02-01
CM-001163 | 25632.87 | CP-26-146 | Facilities and fleet | 2026-03-01
CM-001164 | 19634.65 | CP-26-146 | Facilities and fleet | 2026-04-01
CM-001165 | 19076.24 | CP-26-146 | Facilities and fleet | 2026-05-01
CM-001166 | 31758.64 | CP-26-146 | Facilities and fleet | 2026-06-01
CM-001167 | 25462.63 | CP-26-146 | Facilities and fleet | 2026-07-01
CM-001168 | 32992.32 | CP-26-146 | Facilities and fleet | 2026-08-01
CM-001169 | 107031.19 | CP-26-147 | Facilities and fleet | 2026-01-01
CM-001170 | 149347.38 | CP-26-147 | Facilities and fleet | 2026-02-01
CM-001171 | 141406.23 | CP-26-147 | Facilities and fleet | 2026-03-01
CM-001172 | 177552.15 | CP-26-147 | Facilities and fleet | 2026-04-01
CM-001173 | 114513.81 | CP-26-147 | Facilities and fleet | 2026-05-01
CM-001174 | 191747.74 | CP-26-147 | Facilities and fleet | 2026-06-01
CM-001175 | 136753.4 | CP-26-147 | Facilities and fleet | 2026-07-01
CM-001176 | 189714.1 | CP-26-147 | Facilities and fleet | 2026-08-01
CM-001177 | 41573.16 | CP-26-148 | Facilities and fleet | 2026-01-01
CM-001178 | 33543.52 | CP-26-148 | Facilities and fleet | 2026-02-01
CM-001179 | 38579.9 | CP-26-148 | Facilities and fleet | 2026-03-01
CM-001180 | 34159.03 | CP-26-148 | Facilities and fleet | 2026-04-01
CM-001181 | 52719.04 | CP-26-148 | Facilities and fleet | 2026-05-01
CM-001182 | 56715.38 | CP-26-148 | Facilities and fleet | 2026-06-01
CM-001183 | 44927.69 | CP-26-148 | Facilities and fleet | 2026-07-01
CM-001184 | 47462.28 | CP-26-148 | Facilities and fleet | 2026-08-01
CM-001185 | 104172.87 | CP-26-149 | Facilities and fleet | 2026-01-01
CM-001186 | 132276.27 | CP-26-149 | Facilities and fleet | 2026-02-01
CM-001187 | 94546.87 | CP-26-149 | Facilities and fleet | 2026-03-01
CM-001188 | 100582.87 | CP-26-149 | Facilities and fleet | 2026-04-01
CM-001189 | 157200.23 | CP-26-149 | Facilities and fleet | 2026-05-01
CM-001190 | 101372.62 | CP-26-149 | Facilities and fleet | 2026-06-01
CM-001191 | 124857.44 | CP-26-149 | Facilities and fleet | 2026-07-01
CM-001192 | 204760.83 | CP-26-149 | Facilities and fleet | 2026-08-01
CM-001193 | 52381.2 | CP-26-150 | Facilities and fleet | 2026-01-01
CM-001194 | 82914.04 | CP-26-150 | Facilities and fleet | 2026-02-01
CM-001195 | 71881.75 | CP-26-150 | Facilities and fleet | 2026-03-01
CM-001196 | 59501.21 | CP-26-150 | Facilities and fleet | 2026-04-01
CM-001197 | 57203.82 | CP-26-150 | Facilities and fleet | 2026-05-01
CM-001198 | 72299.6 | CP-26-150 | Facilities and fleet | 2026-06-01
CM-001199 | 112426.17 | CP-26-150 | Facilities and fleet | 2026-07-01
CM-001200 | 104552.21 | CP-26-150 | Facilities and fleet | 2026-08-01
CM-001201 | 12512.87 | CP-26-151 | Facilities and fleet | 2026-01-01
CM-001202 | 13824.92 | CP-26-151 | Facilities and fleet | 2026-02-01
CM-001203 | 8315.39 | CP-26-151 | Facilities and fleet | 2026-03-01
CM-001204 | 14847.38 | CP-26-151 | Facilities and fleet | 2026-04-01
CM-001205 | 14827.09 | CP-26-151 | Facilities and fleet | 2026-05-01
CM-001206 | 15819.27 | CP-26-151 | Facilities and fleet | 2026-06-01
CM-001207 | 16825.22 | CP-26-151 | Facilities and fleet | 2026-07-01
CM-001208 | 14102.86 | CP-26-151 | Facilities and fleet | 2026-08-01
CM-001209 | 153904.04 | CP-26-152 | Facilities and fleet | 2026-01-01
CM-001210 | 120527.88 | CP-26-152 | Facilities and fleet | 2026-02-01
CM-001211 | 166457.92 | CP-26-152 | Facilities and fleet | 2026-03-01
CM-001212 | 168267 | CP-26-152 | Facilities and fleet | 2026-04-01
CM-001213 | 116854.35 | CP-26-152 | Facilities and fleet | 2026-05-01
CM-001214 | 127434.67 | CP-26-152 | Facilities and fleet | 2026-06-01
CM-001215 | 125700.34 | CP-26-152 | Facilities and fleet | 2026-07-01
CM-001216 | 191466.8 | CP-26-152 | Facilities and fleet | 2026-08-01