## Read me
Field Work Orders and Crew Hours: Bayou and Crossroads Districts, January-August 2026
Sedgewater Energy Holdings
Effective date | 2026-09-09
Purpose | Provide work orders and weekly crew-hours for two districts to show workload, priorities and capacity.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Workbook of field work orders created from January to August 2026 in the Bayou and Crossroads districts, with weekly crew hours for all four districts. Extracted from the work management system on September 9, 2026 for the operations review.
Sheets | Data 1 - work orders: one row per order with district, feeder, type, priority, created, scheduled and completed dates, crew type, contractor, labor hours, material cost, status and storm flag.
Sheets | Data 2 - crew capacity: available, regular, overtime and storm hours by district, crew type and week.
Sheets | Summary - formula totals of each numeric column.
Scope | Work orders cover Bayou and Crossroads only, the two districts that moved to the current WMS configuration first; crew capacity covers all four districts. Remotely completed service orders and storm restoration tickets are not work orders and are not included.
Status at August 31, 2026 | 9,600 orders were created from January to August: 8,911 completed, 352 scheduled, 216 cancelled, 87 awaiting material and 34 awaiting a planned outage. The 87 awaiting material are 71 transformer replacements, 9 pole replacements and 7 small new services.
Time to complete | Median calendar days from creation to completion: P1 emergency 0 days (1,711 completed); P2 same day 0 days (2,518); P3 within 10 days 7 days (3,026); P4 planned 34 days (1,656). Recorded labor was 41,185 hours and material $8.3 million; 102 orders were storm-related.
Crew hours | In the 35 weeks to August 31, crews logged 1,008,195 regular and 112,359 overtime hours (overtime 10.0% of worked hours) against 1,074,645 available hours. 61,717 hours were charged to storms, 42,588 of them in the two weeks from May 18. Overtime share by district: Harbor 9.8%, Crossroads 10.2%, Bayou 9.9%, Prairie 10.2%.
Definitions | Priorities: P1 emergency (respond immediately), P2 same day, P3 within 10 calendar days, P4 planned. Statuses: Scheduled, Completed, Cancelled, 'Open - awaiting material' and 'Open - awaiting outage'; an order is set to an awaiting status only after the planner confirms the constraint. Crew types: internal line, troubleman, underground, contract line and contract vegetation.
Data notes | 562 orders (5.9%) have no feeder code; all are streetlight work, which is logged without a feeder because the lighting network is recorded separately in GIS. Since March 2026 internal troubleman crews have handled streetlight repairs that previously went to the lighting contractor.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | labor_hours | hours | 41184.9 | 4.6218 | 8911 | 2026-01-01 | 2026-08-31
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | material_usd | USD | 8256533.26 | 926.5552 | 8911 | 2026-01-01 | 2026-08-31
Weekly crew hours by district and crew type, 2026 | available_hours | crew-hours | 1074645.2 | 1535.2074 | 700 | 2026-01-05 | 2026-08-31
Weekly crew hours by district and crew type, 2026 | regular_hours | crew-hours | 1008194.9 | 1440.2784 | 700 | 2026-01-05 | 2026-08-31
Weekly crew hours by district and crew type, 2026 | overtime_hours | crew-hours | 112358.9 | 160.5127 | 700 | 2026-01-05 | 2026-08-31
Weekly crew hours by district and crew type, 2026 | storm_hours | crew-hours | 61716.8 | 88.1669 | 700 | 2026-01-05 | 2026-08-31

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | wo_number | WO-26-000001 |  | id
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | labor_hours | Recorded labor hours | hours | number
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | district | District |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | feeder_code | Feeder (FK; null for some types) |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | wo_type | Work type |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | priority | Priority |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | created_date | Created |  | date
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | scheduled_date | Scheduled (ISO date) |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | completed_date | Completed |  | date
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | crew_type | Assigned crew |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | contractor_code | Contractor if contract crew (FK) |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | material_usd | Material issued | USD | number
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | status | Status |  | category
Field work orders, Bayou and Crossroads districts, Jan-Aug 2026 | storm_related | Linked to May 2026 event |  | category
Weekly crew hours by district and crew type, 2026 | record_id | CC-000001 |  | id
Weekly crew hours by district and crew type, 2026 | available_hours | Scheduled straight-time capacity | crew-hours | number
Weekly crew hours by district and crew type, 2026 | district | District |  | category
Weekly crew hours by district and crew type, 2026 | crew_type | Crew type |  | category
Weekly crew hours by district and crew type, 2026 | week_start | Monday of week |  | date
Weekly crew hours by district and crew type, 2026 | regular_hours | Straight-time hours worked | crew-hours | number
Weekly crew hours by district and crew type, 2026 | overtime_hours | Overtime hours | crew-hours | number
Weekly crew hours by district and crew type, 2026 | storm_hours | Hours charged to storm | crew-hours | number

## Data 1
wo_number | labor_hours | district | feeder_code | wo_type | priority | created_date | scheduled_date | completed_date | crew_type | contractor_code | material_usd | status | storm_related
WO-26-000001 | 9.7 | Bayou | BY-S06-02 | Corrective maintenance | P4 planned | 2026-01-01 | 2026-02-02 | 2026-02-02 | Contract line | CT-04 | 1064.69 | Completed | No
WO-26-000002 | 7.2 | Bayou | BY-S17-04 | Corrective maintenance | P3 within 10 days | 2026-01-01 | 2026-01-07 | 2026-01-08 | Internal line |  | 2129.57 | Completed | No
WO-26-000003 | 3.8 | Bayou | BY-S09-04 | Corrective maintenance | P4 planned | 2026-01-01 | 2026-02-08 | 2026-02-08 | Contract line | CT-03 | 393.92 | Completed | No
WO-26-000004 | 5.3 | Bayou | BY-S16-04 | Corrective maintenance | P3 within 10 days | 2026-01-01 | 2026-01-09 | 2026-01-11 | Contract line | CT-03 | 1048.31 | Completed | No
WO-26-000005 |  | Bayou | BY-S09-04 | Corrective maintenance | P4 planned | 2026-01-01 | 2026-02-22 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-000006 | 5.1 | Bayou | BY-S22-01 | Corrective maintenance | P3 within 10 days | 2026-01-01 | 2026-01-08 | 2026-01-09 | Internal line |  | 969.55 | Completed | No
WO-26-000007 | 1.1 | Bayou | BY-S06-03 | Meter exchange | P4 planned | 2026-01-01 | 2026-03-01 | 2026-03-05 | Meter technician |  | 124.02 | Completed | No
WO-26-000008 | 0.9 | Bayou | BY-S23-05 | Meter exchange | P4 planned | 2026-01-01 | 2026-02-10 | 2026-02-18 | Meter technician |  | 104.52 | Completed | No
WO-26-000009 | 1.4 | Bayou | BY-S25-04 | Meter exchange | P3 within 10 days | 2026-01-01 | 2026-01-07 | 2026-01-07 | Meter technician |  | 69.55 | Completed | No
WO-26-000010 | 1.1 | Bayou | BY-S04-03 | Meter exchange | P4 planned | 2026-01-01 | 2026-02-09 | 2026-02-10 | Meter technician |  | 107.78 | Completed | No
WO-26-000011 | 0.7 | Bayou | BY-S18-04 | Meter exchange | P3 within 10 days | 2026-01-01 | 2026-01-02 | 2026-01-03 | Meter technician |  | 61.49 | Completed | No
WO-26-000012 | 0.8 | Bayou | BY-S21-03 | Meter exchange | P4 planned | 2026-01-01 | 2026-01-09 | 2026-01-13 | Meter technician |  | 175.09 | Completed | No
WO-26-000013 | 1.3 | Bayou | BY-S23-05 | Meter exchange | P3 within 10 days | 2026-01-01 | 2026-01-09 | 2026-01-10 | Meter technician |  | 69.11 | Completed | No
WO-26-000014 | 1.3 | Bayou | BY-S17-04 | Meter exchange | P4 planned | 2026-01-01 | 2026-01-26 | 2026-01-26 | Meter technician |  | 72.53 | Completed | No
WO-26-000015 | 6.8 | Bayou | BY-S17-01 | Preventive maintenance | P4 planned | 2026-01-01 | 2026-03-01 | 2026-03-01 | Internal line |  | 433.92 | Completed | No
WO-26-000016 | 5.3 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-01-01 | 2026-01-18 | 2026-01-20 | Underground crew |  | 152.18 | Completed | No
WO-26-000017 | 4.6 | Bayou | BY-S30-02 | Preventive maintenance | P4 planned | 2026-01-01 | 2026-02-15 | 2026-02-17 | Underground crew |  | 4.62 | Completed | No
WO-26-000018 | 1 | Bayou | BY-S13-01 | Service order - field | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Meter technician |  | 5.53 | Completed | No
WO-26-000019 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-01 | 2026-01-03 | 2026-01-04 | Contract line | CT-04 | 306.38 | Completed | No
WO-26-000020 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-01 | 2026-01-02 | 2026-01-03 | Internal line |  | 126.98 | Completed | No
WO-26-000021 | 8.3 | Bayou | BY-S30-01 | Transformer replacement | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Contract line | CT-03 | 3002.76 | Completed | No
WO-26-000022 | 7.5 | Bayou | BY-S26-02 | Transformer replacement | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Contract line | CT-04 | 6387.79 | Completed | No
WO-26-000023 | 5.6 | Bayou | BY-S27-01 | Trouble - no power | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Troubleman |  | 20.88 | Completed | No
WO-26-000024 | 5.1 | Bayou | BY-S11-03 | Trouble - no power | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Internal line |  | 209.13 | Completed | No
WO-26-000025 | 3.6 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Internal line |  | 281.46 | Completed | No
WO-26-000026 | 1.6 | Bayou | BY-S16-06 | Trouble - partial or voltage | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Troubleman |  | 212.28 | Completed | No
WO-26-000027 | 2.2 | Bayou | BY-S21-02 | Trouble - partial or voltage | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Troubleman |  | 142.15 | Completed | No
WO-26-000028 | 6.1 | Crossroads | CR-S21-03 | Corrective maintenance | P4 planned | 2026-01-01 | 2026-02-15 | 2026-02-15 | Internal line |  | 336.45 | Completed | No
WO-26-000029 | 5.8 | Crossroads | CR-S26-03 | Corrective maintenance | P3 within 10 days | 2026-01-01 | 2026-01-06 | 2026-01-06 | Contract line | CT-01 | 1723.7 | Completed | No
WO-26-000030 | 0.8 | Crossroads | CR-S17-02 | Meter exchange | P4 planned | 2026-01-01 | 2026-02-25 | 2026-02-25 | Meter technician |  | 141.19 | Completed | No
WO-26-000031 | 0.9 | Crossroads | CR-S17-01 | Meter exchange | P4 planned | 2026-01-01 | 2026-01-20 | 2026-01-20 | Meter technician |  | 68.31 | Completed | No
WO-26-000032 | 1 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-01-01 | 2026-01-11 | 2026-01-11 | Meter technician |  | 133.96 | Completed | No
WO-26-000033 | 1.1 | Crossroads | CR-S24-04 | Meter exchange | P4 planned | 2026-01-01 | 2026-02-19 | 2026-02-20 | Meter technician |  | 161.72 | Completed | No
WO-26-000034 | 15.8 | Crossroads | CR-S11-01 | New service - small | P4 planned | 2026-01-01 | 2026-01-11 | 2026-01-11 | Underground crew |  | 1720.49 | Completed | No
WO-26-000035 | 8.4 | Crossroads | CR-S17-01 | New service - small | P4 planned | 2026-01-01 | 2026-02-19 | 2026-02-19 | Contract line | CT-01 | 1972.56 | Completed | No
WO-26-000036 | 7.6 | Crossroads | CR-S30-06 | Preventive maintenance | P4 planned | 2026-01-01 | 2026-02-17 | 2026-02-17 | Underground crew |  | 416.2 | Completed | No
WO-26-000037 | 1.2 | Crossroads | CR-S21-01 | Service order - field | P3 within 10 days | 2026-01-01 | 2026-01-02 | 2026-01-03 | Meter technician |  | 16.66 | Completed | No
WO-26-000038 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-01 | 2026-01-09 | 2026-01-11 | Internal line |  | 295.7 | Completed | No
WO-26-000039 |  | Crossroads | CR-S07-05 | Transformer replacement | P2 same day | 2026-01-01 | 2026-01-02 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-000040 | 9.2 | Crossroads | CR-S32-05 | Transformer replacement | P3 within 10 days | 2026-01-01 | 2026-01-05 | 2026-01-05 | Internal line |  | 8240.23 | Completed | No
WO-26-000041 | 2.7 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Troubleman |  | 200.78 | Completed | No
WO-26-000042 | 2.9 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Troubleman |  | 93.56 | Completed | No
WO-26-000043 | 4.6 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Troubleman |  | 190.5 | Completed | No
WO-26-000044 | 3.9 | Crossroads | CR-S10-03 | Trouble - no power | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Troubleman |  | 212.54 | Completed | No
WO-26-000045 | 2.8 | Crossroads | CR-S05-06 | Trouble - no power | P1 emergency | 2026-01-01 | 2026-01-01 | 2026-01-01 | Troubleman |  | 39.93 | Completed | No
WO-26-000046 | 2.3 | Crossroads | CR-S05-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-01 | 2026-01-07 | 2026-01-07 | Troubleman |  | 11.28 | Completed | No
WO-26-000047 | 2.8 | Crossroads | CR-S01-04 | Trouble - partial or voltage | P2 same day | 2026-01-01 | 2026-01-02 | 2026-01-02 | Troubleman |  | 122.41 | Completed | No
WO-26-000048 | 6.4 | Bayou | BY-S23-02 | Corrective maintenance | P4 planned | 2026-01-02 | 2026-02-04 | 2026-02-06 | Underground crew |  | 1879.25 | Completed | No
WO-26-000049 | 8 | Bayou | BY-S27-01 | Corrective maintenance | P3 within 10 days | 2026-01-02 | 2026-01-08 | 2026-01-12 | Internal line |  | 2266.32 | Completed | No
WO-26-000050 | 5.5 | Bayou | BY-S23-02 | Corrective maintenance | P4 planned | 2026-01-02 | 2026-03-03 | 2026-03-03 | Contract line | CT-03 | 1199.93 | Completed | No
WO-26-000051 | 0.9 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-01-02 | 2026-01-08 | 2026-01-08 | Meter technician |  | 150.58 | Completed | No
WO-26-000052 | 0.8 | Bayou | BY-S26-01 | Meter exchange | P4 planned | 2026-01-02 | 2026-02-28 | 2026-02-28 | Meter technician |  | 96.74 | Completed | No
WO-26-000053 | 1.2 | Bayou | BY-S10-04 | Meter exchange | P4 planned | 2026-01-02 | 2026-02-10 | 2026-02-10 | Meter technician |  | 161.1 | Completed | No
WO-26-000054 | 0.9 | Bayou | BY-S19-01 | Meter exchange | P3 within 10 days | 2026-01-02 | 2026-01-10 | 2026-01-18 | Meter technician |  | 88.23 | Completed | No
WO-26-000055 | 0.7 | Bayou | BY-S17-04 | Meter exchange | P3 within 10 days | 2026-01-02 | 2026-01-06 | 2026-01-08 | Meter technician |  | 152.64 | Completed | No
WO-26-000056 | 14.9 | Bayou | BY-S30-01 | Pole replacement | P3 within 10 days | 2026-01-02 | 2026-01-12 | 2026-01-12 | Contract line | CT-04 | 3099.33 | Completed | No
WO-26-000057 | 1.1 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Meter technician |  | 13.14 | Completed | No
WO-26-000058 | 9.6 | Bayou | BY-S29-04 | Transformer replacement | P3 within 10 days | 2026-01-02 | 2026-01-03 | 2026-01-03 | Internal line |  | 12261.04 | Completed | No
WO-26-000059 | 13.4 | Bayou | BY-S06-01 | Transformer replacement | P3 within 10 days | 2026-01-02 | 2026-01-12 | 2026-01-16 | Internal line |  | 5893.61 | Completed | No
WO-26-000060 | 6.5 | Bayou | BY-S19-04 | Transformer replacement | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Internal line |  | 10165.89 | Completed | No
WO-26-000061 | 10.2 | Bayou | BY-S30-01 | Transformer replacement | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Internal line |  | 4726.19 | Completed | No
WO-26-000062 | 4.5 | Bayou | BY-S18-06 | Trouble - no power | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Troubleman |  | 292.41 | Completed | No
WO-26-000063 | 2.8 | Bayou | BY-S20-03 | Trouble - no power | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Troubleman |  | 71.8 | Completed | No
WO-26-000064 | 2.8 | Bayou | BY-S02-01 | Trouble - no power | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Troubleman |  | 175.82 | Completed | No
WO-26-000065 | 4 | Bayou | BY-S21-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-02 | 2026-01-07 | 2026-01-07 | Internal line |  | 75 | Completed | No
WO-26-000066 | 4.9 | Bayou | BY-S16-03 | Trouble - partial or voltage | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Troubleman |  | 202.92 | Completed | No
WO-26-000067 | 1.4 | Crossroads | CR-S07-01 | Meter exchange | P3 within 10 days | 2026-01-02 | 2026-01-10 | 2026-01-11 | Meter technician |  | 150.41 | Completed | No
WO-26-000068 | 0.6 | Crossroads | CR-S12-02 | Meter exchange | P4 planned | 2026-01-02 | 2026-02-20 | 2026-02-20 | Meter technician |  | 162.02 | Completed | No
WO-26-000069 | 0.7 | Crossroads | CR-S30-05 | Meter exchange | P4 planned | 2026-01-02 | 2026-02-13 | 2026-02-13 | Meter technician |  | 164.41 | Completed | No
WO-26-000070 | 0.9 | Crossroads | CR-S16-06 | Meter exchange | P4 planned | 2026-01-02 | 2026-02-17 | 2026-02-17 | Meter technician |  | 98.74 | Completed | No
WO-26-000071 | 1.5 | Crossroads | CR-S31-01 | Meter exchange | P4 planned | 2026-01-02 | 2026-02-17 | 2026-02-21 | Meter technician |  | 139.67 | Completed | No
WO-26-000072 | 22.1 | Crossroads | CR-S19-04 | Pole replacement | P3 within 10 days | 2026-01-02 | 2026-01-11 | 2026-01-13 | Internal line |  | 2297.7 | Completed | No
WO-26-000073 | 20.8 | Crossroads | CR-S05-01 | Pole replacement | P3 within 10 days | 2026-01-02 | 2026-01-10 | 2026-01-12 | Contract line | CT-01 | 2243.26 | Completed | No
WO-26-000074 | 14 | Crossroads | CR-S05-01 | Pole replacement | P3 within 10 days | 2026-01-02 | 2026-01-03 | 2026-01-03 | Contract line | CT-01 | 2657.28 | Completed | No
WO-26-000075 | 6.2 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-01-02 | 2026-01-18 | 2026-01-22 | Internal line |  | 247.56 | Completed | No
WO-26-000076 | 5.3 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-01-02 | 2026-01-11 | 2026-01-11 | Internal line |  | 165.71 | Completed | No
WO-26-000077 |  | Crossroads | CR-S29-03 | Preventive maintenance | P4 planned | 2026-01-02 | 2026-02-08 |  | Underground crew |  |  | Cancelled | No
WO-26-000078 | 4.9 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-01-02 | 2026-03-01 | 2026-03-05 | Underground crew |  | 544.59 | Completed | No
WO-26-000079 | 0.7 | Crossroads | CR-S07-07 | Service order - field | P3 within 10 days | 2026-01-02 | 2026-01-06 | 2026-01-06 | Meter technician |  | 25.91 | Completed | No
WO-26-000080 | 1.3 | Crossroads | CR-S25-05 | Service order - field | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Meter technician |  | 25.27 | Completed | No
WO-26-000081 | 1.1 | Crossroads | CR-S25-04 | Service order - field | P3 within 10 days | 2026-01-02 | 2026-01-03 | 2026-01-03 | Meter technician |  | 18.82 | Completed | No
WO-26-000082 | 1.1 | Crossroads | CR-S22-04 | Service order - field | P3 within 10 days | 2026-01-02 | 2026-01-11 | 2026-01-15 | Meter technician |  | 4.58 | Completed | No
WO-26-000083 | 1.9 | Crossroads | CR-S20-03 | Service order - field | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Meter technician |  | 30.34 | Completed | No
WO-26-000084 | 1.1 | Crossroads | CR-S26-03 | Service order - field | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Meter technician |  | 20.48 | Completed | No
WO-26-000085 | 2 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-01-02 | 2026-01-08 | 2026-01-08 | Meter technician |  | 5.31 | Completed | No
WO-26-000086 | 0.9 | Crossroads | CR-S07-05 | Service order - field | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Meter technician |  | 20.51 | Completed | No
WO-26-000087 | 1.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-02 | 2026-01-12 | 2026-01-12 | Contract line | CT-01 | 101.27 | Completed | No
WO-26-000088 | 9.2 | Crossroads | CR-S21-03 | Transformer replacement | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Internal line |  | 8381.07 | Completed | No
WO-26-000089 | 13.7 | Crossroads | CR-S16-05 | Transformer replacement | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Contract line | CT-02 | 10861.75 | Completed | No
WO-26-000090 | 7.3 | Crossroads | CR-S19-03 | Transformer replacement | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Internal line |  | 3427.22 | Completed | No
WO-26-000091 | 6.7 | Crossroads | CR-S28-04 | Transformer replacement | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Internal line |  | 10702.91 | Completed | No
WO-26-000092 | 6.7 | Crossroads | CR-S17-01 | Transformer replacement | P3 within 10 days | 2026-01-02 | 2026-01-12 | 2026-01-14 | Contract line | CT-02 | 6572.16 | Completed | No
WO-26-000093 | 8.3 | Crossroads | CR-S24-04 | Transformer replacement | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Internal line |  | 2948.2 | Completed | No
WO-26-000094 | 5.1 | Crossroads | CR-S16-02 | Trouble - no power | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Troubleman |  | 347.23 | Completed | No
WO-26-000095 | 5.4 | Crossroads | CR-S25-03 | Trouble - no power | P1 emergency | 2026-01-02 | 2026-01-02 | 2026-01-02 | Internal line |  | 155.43 | Completed | No
WO-26-000096 | 4.1 | Crossroads | CR-S23-03 | Trouble - no power | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Troubleman |  | 347.67 | Completed | No
WO-26-000097 | 3.2 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-01-02 | 2026-01-02 | 2026-01-02 | Troubleman |  | 162.2 | Completed | No
WO-26-000098 | 5.4 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Troubleman |  | 84.3 | Completed | No
WO-26-000099 | 2.7 | Crossroads | CR-S18-01 | Trouble - partial or voltage | P2 same day | 2026-01-02 | 2026-01-03 | 2026-01-03 | Troubleman |  | 156.24 | Completed | No
WO-26-000100 | 1.3 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Meter technician |  | 6.59 | Completed | No
WO-26-000101 | 1.8 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Meter technician |  | 29.21 | Completed | No
WO-26-000102 | 2 | Bayou | BY-S25-04 | Service order - field | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Meter technician |  | 8.29 | Completed | No
WO-26-000103 | 10 | Bayou | BY-S08-01 | Transformer replacement | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Internal line |  | 7474.34 | Completed | No
WO-26-000104 | 2.4 | Bayou | BY-S09-01 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Internal line |  | 261.13 | Completed | No
WO-26-000105 | 5.2 | Bayou | BY-S21-02 | Trouble - no power | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 289.1 | Completed | No
WO-26-000106 | 6 | Bayou | BY-S27-04 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 6.69 | Completed | No
WO-26-000107 | 5.4 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 334.73 | Completed | No
WO-26-000108 | 5.4 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 189.92 | Completed | No
WO-26-000109 | 3.9 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 260.64 | Completed | No
WO-26-000110 | 2.8 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 244.62 | Completed | No
WO-26-000111 | 3.9 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Troubleman |  | 72.79 | Completed | No
WO-26-000112 | 2.3 | Bayou | BY-S01-01 | Trouble - partial or voltage | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 53.74 | Completed | No
WO-26-000113 | 2.2 | Bayou | BY-S06-03 | Trouble - partial or voltage | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 194.49 | Completed | No
WO-26-000114 | 2.1 | Bayou | BY-S30-03 | Trouble - partial or voltage | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Troubleman |  | 168.76 | Completed | No
WO-26-000115 | 5.1 | Crossroads | CR-S03-01 | Corrective maintenance | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Underground crew |  | 1132.29 | Completed | No
WO-26-000116 | 0.5 | Crossroads | CR-S25-03 | Service order - field | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Meter technician |  | 7.63 | Completed | No
WO-26-000117 | 12 | Crossroads | CR-S15-01 | Transformer replacement | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Contract line | CT-02 | 4207.94 | Completed | No
WO-26-000118 | 10.8 | Crossroads | CR-S13-06 | Transformer replacement | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Contract line | CT-01 | 5430.65 | Completed | No
WO-26-000119 | 2.4 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 318.71 | Completed | No
WO-26-000120 | 4.5 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Internal line |  | 47.14 | Completed | No
WO-26-000121 | 3.3 | Crossroads | CR-S20-05 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 177.02 | Completed | No
WO-26-000122 | 2.2 | Crossroads | CR-S25-01 | Trouble - no power | P2 same day | 2026-01-03 | 2026-01-03 | 2026-01-03 | Internal line |  | 86.98 | Completed | No
WO-26-000123 | 2.1 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-01-03 | 2026-01-03 | 2026-01-03 | Troubleman |  | 266.41 | Completed | No
WO-26-000124 | 2.9 | Crossroads | CR-S09-04 | Trouble - partial or voltage | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Troubleman |  | 234.18 | Completed | No
WO-26-000125 | 3.4 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-01-03 | 2026-01-04 | 2026-01-04 | Troubleman |  | 106.99 | Completed | No
WO-26-000126 | 1.5 | Bayou | BY-S27-05 | Service order - field | P2 same day | 2026-01-04 | 2026-01-05 | 2026-01-05 | Meter technician |  | 28.46 | Completed | No
WO-26-000127 | 4.4 | Bayou | BY-S15-04 | Trouble - no power | P2 same day | 2026-01-04 | 2026-01-04 | 2026-01-04 | Troubleman |  | 241.36 | Completed | No
WO-26-000128 | 5.9 | Bayou | BY-S11-01 | Trouble - no power | P1 emergency | 2026-01-04 | 2026-01-04 | 2026-01-04 | Troubleman |  | 287.94 | Completed | No
WO-26-000129 | 2.2 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-01-04 | 2026-01-05 | 2026-01-05 | Troubleman |  | 56.1 | Completed | No
WO-26-000130 | 4 | Crossroads | CR-S13-03 | Corrective maintenance | P2 same day | 2026-01-04 | 2026-01-04 | 2026-01-04 | Internal line |  | 2079.38 | Completed | No
WO-26-000131 | 1.5 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-01-04 | 2026-01-05 | 2026-01-05 | Meter technician |  | 39.31 | Completed | No
WO-26-000132 | 1.1 | Crossroads | CR-S08-06 | Service order - field | P2 same day | 2026-01-04 | 2026-01-05 | 2026-01-05 | Meter technician |  | 32.3 | Completed | No
WO-26-000133 | 6 | Crossroads | CR-S13-03 | Transformer replacement | P2 same day | 2026-01-04 | 2026-01-04 | 2026-01-04 | Internal line |  | 5613.23 | Completed | No
WO-26-000134 | 5.7 | Crossroads | CR-S01-02 | Trouble - no power | P1 emergency | 2026-01-04 | 2026-01-04 | 2026-01-04 | Troubleman |  | 127.31 | Completed | No
WO-26-000135 | 3.1 | Bayou | BY-S15-03 | Corrective maintenance | P3 within 10 days | 2026-01-05 | 2026-01-15 | 2026-01-15 | Internal line |  | 515.74 | Completed | No
WO-26-000136 | 3.5 | Bayou | BY-S21-04 | Corrective maintenance | P3 within 10 days | 2026-01-05 | 2026-01-13 | 2026-01-14 | Internal line |  | 995.06 | Completed | No
WO-26-000137 | 3.5 | Bayou | BY-S14-03 | Corrective maintenance | P3 within 10 days | 2026-01-05 | 2026-01-06 | 2026-01-14 | Internal line |  | 1387.22 | Completed | No
WO-26-000138 | 0.6 | Bayou | BY-S23-02 | Meter exchange | P4 planned | 2026-01-05 | 2026-01-24 | 2026-01-24 | Meter technician |  | 118.41 | Completed | No
WO-26-000139 | 0.9 | Bayou | BY-S06-03 | Meter exchange | P3 within 10 days | 2026-01-05 | 2026-01-12 | 2026-01-13 | Meter technician |  | 82.04 | Completed | No
WO-26-000140 | 1.5 | Bayou | BY-S06-01 | Meter exchange | P3 within 10 days | 2026-01-05 | 2026-01-08 | 2026-01-08 | Meter technician |  | 67.47 | Completed | No
WO-26-000141 | 0.9 | Bayou | BY-S21-03 | Meter exchange | P4 planned | 2026-01-05 | 2026-01-27 | 2026-01-31 | Meter technician |  | 134.39 | Completed | No
WO-26-000142 | 0.9 | Bayou | BY-S06-03 | Service order - field | P3 within 10 days | 2026-01-05 | 2026-01-10 | 2026-01-10 | Meter technician |  | 13.63 | Completed | No
WO-26-000143 | 1.4 | Bayou | BY-S09-02 | Service order - field | P3 within 10 days | 2026-01-05 | 2026-01-07 | 2026-01-07 | Meter technician |  | 31.56 | Completed | No
WO-26-000144 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-05 | 2026-01-12 | 2026-01-14 | Internal line |  | 71.39 | Completed | No
WO-26-000145 | 8.1 | Bayou | BY-S11-01 | Transformer replacement | P2 same day | 2026-01-05 | 2026-01-05 | 2026-01-05 | Contract line | CT-04 | 9657.59 | Completed | No
WO-26-000146 | 5.2 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-01-05 | 2026-01-05 | 2026-01-05 | Troubleman |  | 245.89 | Completed | No
WO-26-000147 | 4.2 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-01-05 | 2026-01-05 | 2026-01-05 | Troubleman |  | 255.12 | Completed | No
WO-26-000148 | 2.2 | Bayou | BY-S19-04 | Trouble - no power | P1 emergency | 2026-01-05 | 2026-01-05 | 2026-01-05 | Troubleman |  | 3.06 | Completed | No
WO-26-000149 | 5.9 | Bayou | BY-S04-02 | Trouble - no power | P2 same day | 2026-01-05 | 2026-01-06 | 2026-01-06 | Troubleman |  | 196.82 | Completed | No
WO-26-000150 | 3.1 | Bayou | BY-S03-01 | Trouble - partial or voltage | P2 same day | 2026-01-05 | 2026-01-06 | 2026-01-06 | Troubleman |  | 212.47 | Completed | No
WO-26-000151 | 9.2 | Crossroads | CR-S15-01 | Corrective maintenance | P4 planned | 2026-01-05 | 2026-03-03 | 2026-03-03 | Underground crew |  | 444.59 | Completed | No
WO-26-000152 | 4.6 | Crossroads | CR-S28-04 | Corrective maintenance | P3 within 10 days | 2026-01-05 | 2026-01-10 | 2026-01-11 | Internal line |  | 1573.12 | Completed | No
WO-26-000153 | 7.5 | Crossroads | CR-S18-02 | Corrective maintenance | P3 within 10 days | 2026-01-05 | 2026-01-07 | 2026-01-11 | Internal line |  | 975.72 | Completed | No
WO-26-000154 | 7.2 | Crossroads | CR-S15-03 | Corrective maintenance | P3 within 10 days | 2026-01-05 | 2026-01-06 | 2026-01-06 | Internal line |  | 1867.98 | Completed | No
WO-26-000155 | 1.1 | Crossroads | CR-S32-02 | Meter exchange | P3 within 10 days | 2026-01-05 | 2026-01-12 | 2026-01-12 | Meter technician |  | 163.34 | Completed | No
WO-26-000156 | 1 | Crossroads | CR-S07-02 | Meter exchange | P3 within 10 days | 2026-01-05 | 2026-01-13 | 2026-01-13 | Meter technician |  | 79.79 | Completed | No
WO-26-000157 | 0.6 | Crossroads | CR-S08-02 | Meter exchange | P3 within 10 days | 2026-01-05 | 2026-01-06 | 2026-01-06 | Meter technician |  | 162.14 | Completed | No
WO-26-000158 | 1.3 | Crossroads | CR-S07-05 | Meter exchange | P4 planned | 2026-01-05 | 2026-01-18 | 2026-01-19 | Meter technician |  | 65.73 | Completed | No
WO-26-000159 | 6.6 | Crossroads | CR-S20-04 | New service - small | P4 planned | 2026-01-05 | 2026-02-26 | 2026-03-02 | Internal line |  | 4164.86 | Completed | No
WO-26-000160 | 3.2 | Crossroads | CR-S23-02 | Preventive maintenance | P4 planned | 2026-01-05 | 2026-02-27 | 2026-03-01 | Contract line | CT-02 | 428.76 | Completed | No
WO-26-000161 | 5.1 | Crossroads | CR-S27-04 | Preventive maintenance | P4 planned | 2026-01-05 | 2026-02-18 | 2026-02-22 | Underground crew |  | 157.7 | Completed | No
WO-26-000162 | 6.6 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-01-05 | 2026-01-14 | 2026-01-16 | Internal line |  | 63.61 | Completed | No
WO-26-000163 | 1.7 | Crossroads | CR-S15-02 | Service order - field | P3 within 10 days | 2026-01-05 | 2026-01-11 | 2026-01-19 | Meter technician |  | 12.69 | Completed | No
WO-26-000164 | 6.4 | Crossroads | CR-S13-03 | Transformer replacement | P3 within 10 days | 2026-01-05 | 2026-01-08 | 2026-01-10 | Internal line |  | 11324.82 | Completed | No
WO-26-000165 | 11.4 | Crossroads | CR-S05-02 | Transformer replacement | P1 emergency | 2026-01-05 | 2026-01-05 | 2026-01-05 | Internal line |  | 4566.53 | Completed | No
WO-26-000166 | 2.7 | Crossroads | CR-S32-01 | Trouble - no power | P2 same day | 2026-01-05 | 2026-01-05 | 2026-01-05 | Internal line |  | 347.36 | Completed | No
WO-26-000167 | 8.7 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-01-06 | 2026-01-11 | 2026-01-11 | Internal line |  | 2259.09 | Completed | No
WO-26-000168 | 3.9 | Bayou | BY-S11-01 | Corrective maintenance | P3 within 10 days | 2026-01-06 | 2026-01-13 | 2026-01-14 | Internal line |  | 1851.24 | Completed | No
WO-26-000169 | 10.7 | Bayou | BY-S21-05 | Corrective maintenance | P3 within 10 days | 2026-01-06 | 2026-01-08 | 2026-01-12 | Internal line |  | 289.87 | Completed | No
WO-26-000170 | 0.6 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-01-06 | 2026-01-11 | 2026-01-11 | Meter technician |  | 161.45 | Completed | No
WO-26-000171 | 1.3 | Bayou | BY-S30-02 | Meter exchange | P4 planned | 2026-01-06 | 2026-02-25 | 2026-02-25 | Meter technician |  | 138.83 | Completed | No
WO-26-000172 | 15.9 | Bayou | BY-S17-02 | New service - small | P3 within 10 days | 2026-01-06 | 2026-01-11 | 2026-01-19 | Internal line |  | 3306.36 | Completed | No
WO-26-000173 | 14.4 | Bayou | BY-S17-01 | Pole replacement | P3 within 10 days | 2026-01-06 | 2026-01-08 | 2026-01-10 | Contract line | CT-03 | 1469.85 | Completed | No
WO-26-000174 | 11.7 | Bayou | BY-S30-01 | Pole replacement | P2 same day | 2026-01-06 | 2026-01-06 | 2026-01-06 | Contract line | CT-04 | 1985.79 | Completed | No
WO-26-000175 | 10.4 | Bayou | BY-S04-03 | Pole replacement | P4 planned | 2026-01-06 | 2026-01-27 | 2026-01-27 | Internal line |  | 3197 | Completed | No
WO-26-000176 | 4.4 | Bayou | BY-S15-06 | Preventive maintenance | P4 planned | 2026-01-06 | 2026-02-18 | 2026-02-18 | Underground crew |  | 597.26 | Completed | No
WO-26-000177 | 0.7 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-01-06 | 2026-01-13 | 2026-01-13 | Meter technician |  | 20.16 | Completed | No
WO-26-000178 | 1.6 | Bayou | BY-S15-03 | Service order - field | P3 within 10 days | 2026-01-06 | 2026-01-14 | 2026-01-14 | Meter technician |  | 39.7 | Completed | No
WO-26-000179 | 0.7 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-01-06 | 2026-01-06 | 2026-01-06 | Meter technician |  | 6.47 | Completed | No
WO-26-000180 | 0.9 | Bayou | BY-S29-05 | Service order - field | P3 within 10 days | 2026-01-06 | 2026-01-09 | 2026-01-09 | Meter technician |  | 25.48 | Completed | No
WO-26-000181 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-06 | 2026-01-13 | 2026-01-14 | Internal line |  | 111.03 | Completed | No
WO-26-000182 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-06 | 2026-01-10 | 2026-01-11 | Internal line |  | 188.07 | Completed | No
WO-26-000183 | 10.5 | Bayou | BY-S22-04 | Transformer replacement | P2 same day | 2026-01-06 | 2026-01-06 | 2026-01-06 | Contract line | CT-03 | 9365.69 | Completed | No
WO-26-000184 | 3.6 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-01-06 | 2026-01-06 | 2026-01-06 | Troubleman |  | 37.52 | Completed | No
WO-26-000185 | 2.3 | Bayou | BY-S28-01 | Trouble - partial or voltage | P2 same day | 2026-01-06 | 2026-01-06 | 2026-01-06 | Troubleman |  | 36.75 | Completed | No
WO-26-000186 | 11.7 | Crossroads | CR-S16-03 | Corrective maintenance | P3 within 10 days | 2026-01-06 | 2026-01-09 | 2026-01-09 | Contract line | CT-01 | 991.07 | Completed | No
WO-26-000187 | 4 | Crossroads | CR-S13-03 | Corrective maintenance | P3 within 10 days | 2026-01-06 | 2026-01-13 | 2026-01-13 | Internal line |  | 1040.49 | Completed | No
WO-26-000188 | 6.3 | Crossroads | CR-S16-04 | Corrective maintenance | P4 planned | 2026-01-06 | 2026-01-29 | 2026-02-06 | Underground crew |  | 1874.28 | Completed | No
WO-26-000189 | 0.6 | Crossroads | CR-S31-01 | Meter exchange | P3 within 10 days | 2026-01-06 | 2026-01-08 | 2026-01-08 | Meter technician |  | 149.49 | Completed | No
WO-26-000190 | 0.9 | Crossroads | CR-S32-01 | Meter exchange | P3 within 10 days | 2026-01-06 | 2026-01-09 | 2026-01-10 | Meter technician |  | 171.45 | Completed | No
WO-26-000191 | 15.8 | Crossroads | CR-S07-07 | New service - small | P4 planned | 2026-01-06 | 2026-01-20 | 2026-01-20 | Contract line | CT-01 | 3308.11 | Completed | No
WO-26-000192 | 15.3 | Crossroads | CR-S24-02 | Pole replacement | P2 same day | 2026-01-06 | 2026-01-07 | 2026-01-07 | Contract line | CT-01 | 2565.72 | Completed | No
WO-26-000193 | 15.1 | Crossroads | CR-S32-01 | Pole replacement | P4 planned | 2026-01-06 | 2026-02-28 | 2026-03-01 | Contract line | CT-02 | 3143.81 | Completed | No
WO-26-000194 | 4.7 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-01-06 | 2026-01-22 | 2026-01-22 | Internal line |  | 85.68 | Completed | No
WO-26-000195 | 3.1 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-01-06 | 2026-02-11 | 2026-02-19 | Underground crew |  | 349.29 | Completed | No
WO-26-000196 | 4.2 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-01-06 | 2026-02-03 | 2026-02-05 | Internal line |  | 403.74 | Completed | No
WO-26-000197 | 5.2 | Crossroads | CR-S28-01 | Preventive maintenance | P4 planned | 2026-01-06 | 2026-02-07 | 2026-02-09 | Underground crew |  | 80.8 | Completed | No
WO-26-000198 | 1.6 | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-01-06 | 2026-01-07 | 2026-01-07 | Meter technician |  | 11.28 | Completed | No
WO-26-000199 | 0.7 | Crossroads | CR-S27-03 | Service order - field | P3 within 10 days | 2026-01-06 | 2026-01-07 | 2026-01-07 | Meter technician |  | 17 | Completed | No
WO-26-000200 | 1.1 | Crossroads | CR-S26-06 | Service order - field | P3 within 10 days | 2026-01-06 | 2026-01-15 | 2026-01-16 | Meter technician |  | 21.58 | Completed | No
WO-26-000201 | 1.1 | Crossroads | CR-S07-06 | Service order - field | P3 within 10 days | 2026-01-06 | 2026-01-07 | 2026-01-07 | Meter technician |  | 39.96 | Completed | No
WO-26-000202 | 1.4 | Crossroads | CR-S13-02 | Service order - field | P2 same day | 2026-01-06 | 2026-01-06 | 2026-01-06 | Meter technician |  | 1.65 | Completed | No
WO-26-000203 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-06 | 2026-01-14 | 2026-01-14 | Internal line |  | 429.61 | Completed | No
WO-26-000204 | 2.9 | Crossroads |  | Streetlight | P4 planned | 2026-01-06 | 2026-02-23 | 2026-02-23 | Contract line | CT-01 | 421.09 | Completed | No
WO-26-000205 | 9.7 | Crossroads | CR-S07-07 | Transformer replacement | P1 emergency | 2026-01-06 | 2026-01-06 | 2026-01-06 | Internal line |  | 12449.58 | Completed | No
WO-26-000206 | 6.7 | Crossroads | CR-S10-02 | Transformer replacement | P3 within 10 days | 2026-01-06 | 2026-01-16 | 2026-01-16 | Internal line |  | 3592.97 | Completed | No
WO-26-000207 | 4.7 | Crossroads | CR-S25-02 | Trouble - no power | P1 emergency | 2026-01-06 | 2026-01-06 | 2026-01-06 | Troubleman |  | 144.58 | Completed | No
WO-26-000208 | 3.9 | Crossroads | CR-S26-01 | Trouble - no power | P1 emergency | 2026-01-06 | 2026-01-06 | 2026-01-06 | Troubleman |  | 16.37 | Completed | No
WO-26-000209 | 2.3 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-01-06 | 2026-01-06 | 2026-01-06 | Troubleman |  | 218.99 | Completed | No
WO-26-000210 | 4.3 | Crossroads | CR-S26-03 | Trouble - no power | P1 emergency | 2026-01-06 | 2026-01-06 | 2026-01-06 | Troubleman |  | 313.66 | Completed | No
WO-26-000211 | 3.8 | Crossroads | CR-S04-04 | Trouble - partial or voltage | P2 same day | 2026-01-06 | 2026-01-07 | 2026-01-07 | Troubleman |  | 64.5 | Completed | No
WO-26-000212 | 3.3 | Crossroads | CR-S27-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-06 | 2026-01-12 | 2026-01-12 | Troubleman |  | 101.23 | Completed | No
WO-26-000213 | 2.2 | Crossroads | CR-S05-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-06 | 2026-01-07 | 2026-01-07 | Troubleman |  | 75.87 | Completed | No
WO-26-000214 | 11 | Bayou | BY-S26-04 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-09 | 2026-01-09 | Contract line | CT-04 | 2223.61 | Completed | No
WO-26-000215 | 4.3 | Bayou | BY-S11-03 | Corrective maintenance | P4 planned | 2026-01-07 | 2026-01-28 | 2026-01-28 | Contract line | CT-03 | 2013.51 | Completed | No
WO-26-000216 | 7.2 | Bayou | BY-S07-06 | Corrective maintenance | P2 same day | 2026-01-07 | 2026-01-08 | 2026-01-08 | Underground crew |  | 1031.37 | Completed | No
WO-26-000217 | 11.5 | Bayou | BY-S22-04 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-17 | 2026-01-18 | Contract line | CT-04 | 750.32 | Completed | No
WO-26-000218 | 1.2 | Bayou | BY-S10-05 | Meter exchange | P4 planned | 2026-01-07 | 2026-03-01 | 2026-03-02 | Meter technician |  | 116.52 | Completed | No
WO-26-000219 | 0.7 | Bayou | BY-S11-01 | Meter exchange | P3 within 10 days | 2026-01-07 | 2026-01-12 | 2026-01-16 | Meter technician |  | 124.79 | Completed | No
WO-26-000220 | 0.7 | Bayou | BY-S26-04 | Meter exchange | P3 within 10 days | 2026-01-07 | 2026-01-09 | 2026-01-13 | Meter technician |  | 91.34 | Completed | No
WO-26-000221 | 0.9 | Bayou | BY-S19-01 | Meter exchange | P4 planned | 2026-01-07 | 2026-01-20 | 2026-01-24 | Meter technician |  | 130.36 | Completed | No
WO-26-000222 |  | Bayou | BY-S13-05 | Meter exchange | P3 within 10 days | 2026-01-07 | 2026-01-13 |  | Meter technician |  |  | Cancelled | No
WO-26-000223 | 1.2 | Bayou | BY-S11-01 | Meter exchange | P3 within 10 days | 2026-01-07 | 2026-01-16 | 2026-01-16 | Meter technician |  | 104.01 | Completed | No
WO-26-000224 | 8.8 | Bayou | BY-S25-01 | New service - small | P4 planned | 2026-01-07 | 2026-01-30 | 2026-01-31 | Contract line | CT-03 | 637.61 | Completed | No
WO-26-000225 | 4.1 | Bayou | BY-S21-01 | New service - small | P4 planned | 2026-01-07 | 2026-03-07 | 2026-03-11 | Contract line | CT-03 | 3289.87 | Completed | No
WO-26-000226 | 5.3 | Bayou | BY-S27-06 | Preventive maintenance | P4 planned | 2026-01-07 | 2026-01-29 | 2026-01-30 | Contract line | CT-04 | 512.46 | Completed | No
WO-26-000227 | 2.5 | Bayou | BY-S02-01 | Preventive maintenance | P4 planned | 2026-01-07 | 2026-03-07 | 2026-03-09 | Contract line | CT-03 | 121.05 | Completed | No
WO-26-000228 | 1.6 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-01-07 | 2026-01-14 | 2026-01-15 | Meter technician |  | 35.78 | Completed | No
WO-26-000229 | 0.7 | Bayou | BY-S26-01 | Service order - field | P3 within 10 days | 2026-01-07 | 2026-01-14 | 2026-01-14 | Meter technician |  | 9.85 | Completed | No
WO-26-000230 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-07 | 2026-01-09 | 2026-01-09 | Contract line | CT-04 | 310.32 | Completed | No
WO-26-000231 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-07 | 2026-01-17 | 2026-01-25 | Contract line | CT-03 | 326.03 | Completed | No
WO-26-000232 | 11.1 | Bayou | BY-S05-02 | Transformer replacement | P1 emergency | 2026-01-07 | 2026-01-07 | 2026-01-07 | Internal line |  | 9096.68 | Completed | No
WO-26-000233 | 4.3 | Bayou | BY-S21-05 | Trouble - no power | P1 emergency | 2026-01-07 | 2026-01-07 | 2026-01-07 | Troubleman |  | 94.15 | Completed | No
WO-26-000234 | 3.1 | Bayou | BY-S16-01 | Trouble - no power | P1 emergency | 2026-01-07 | 2026-01-07 | 2026-01-07 | Troubleman |  | 202.07 | Completed | No
WO-26-000235 | 3.3 | Bayou | BY-S22-02 | Trouble - partial or voltage | P2 same day | 2026-01-07 | 2026-01-07 | 2026-01-07 | Internal line |  | 33.17 | Completed | No
WO-26-000236 | 4 | Bayou | BY-S13-06 | Trouble - partial or voltage | P3 within 10 days | 2026-01-07 | 2026-01-10 | 2026-01-12 | Troubleman |  | 214 | Completed | No
WO-26-000237 | 4.7 | Bayou | BY-S12-04 | Trouble - partial or voltage | P3 within 10 days | 2026-01-07 | 2026-01-11 | 2026-01-15 | Troubleman |  | 93.2 | Completed | No
WO-26-000238 | 2.6 | Bayou | BY-S29-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-07 | 2026-01-13 | 2026-01-13 | Troubleman |  | 21.34 | Completed | No
WO-26-000239 | 7.8 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-16 | 2026-01-16 | Contract line | CT-01 | 1874.17 | Completed | No
WO-26-000240 | 6 | Crossroads | CR-S14-01 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-08 | 2026-01-08 | Contract line | CT-01 | 1375.65 | Completed | No
WO-26-000241 | 5.5 | Crossroads | CR-S15-02 | Corrective maintenance | P4 planned | 2026-01-07 | 2026-01-21 | 2026-01-21 | Internal line |  | 873.51 | Completed | No
WO-26-000242 |  | Crossroads | CR-S26-02 | Corrective maintenance | P2 same day | 2026-01-07 | 2026-01-07 |  | Underground crew |  |  | Cancelled | No
WO-26-000243 | 10.6 | Crossroads | CR-S07-07 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-16 | 2026-01-16 | Underground crew |  | 1653.29 | Completed | No
WO-26-000244 | 7.6 | Crossroads | CR-S18-03 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-12 | 2026-01-13 | Internal line |  | 1564.64 | Completed | No
WO-26-000245 | 9.5 | Crossroads | CR-S07-02 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-09 | 2026-01-09 | Internal line |  | 1952.61 | Completed | No
WO-26-000246 | 5.8 | Crossroads | CR-S02-05 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-12 | 2026-01-12 | Internal line |  | 763.05 | Completed | No
WO-26-000247 | 5.5 | Crossroads | CR-S32-05 | Corrective maintenance | P3 within 10 days | 2026-01-07 | 2026-01-15 | 2026-01-19 | Underground crew |  | 836.9 | Completed | No
WO-26-000248 | 10.8 | Crossroads | CR-S28-03 | New service - small | P4 planned | 2026-01-07 | 2026-02-23 | 2026-02-27 | Contract line | CT-01 | 3680.44 | Completed | No
WO-26-000249 | 15.2 | Crossroads | CR-S30-03 | Pole replacement | P3 within 10 days | 2026-01-07 | 2026-01-09 | 2026-01-10 | Contract line | CT-02 | 1319.52 | Completed | No
WO-26-000250 |  | Crossroads | CR-S14-04 | Service order - field | P3 within 10 days | 2026-01-07 | 2026-01-12 |  | Meter technician |  |  | Cancelled | No
WO-26-000251 | 1.9 | Crossroads | CR-S32-01 | Service order - field | P2 same day | 2026-01-07 | 2026-01-08 | 2026-01-08 | Meter technician |  | 33.1 | Completed | No
WO-26-000252 | 2 | Crossroads | CR-S05-01 | Service order - field | P2 same day | 2026-01-07 | 2026-01-07 | 2026-01-07 | Meter technician |  | 16.72 | Completed | No
WO-26-000253 | 0.8 | Crossroads | CR-S16-05 | Service order - field | P3 within 10 days | 2026-01-07 | 2026-01-10 | 2026-01-18 | Meter technician |  | 22.09 | Completed | No
WO-26-000254 | 1.6 | Crossroads | CR-S22-02 | Service order - field | P2 same day | 2026-01-07 | 2026-01-08 | 2026-01-08 | Meter technician |  | 20.22 | Completed | No
WO-26-000255 | 1.3 | Crossroads |  | Streetlight | P4 planned | 2026-01-07 | 2026-02-19 | 2026-02-23 | Contract line | CT-02 | 449.54 | Completed | No
WO-26-000256 | 1.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-07 | 2026-01-14 | 2026-01-18 | Internal line |  | 334.21 | Completed | No
WO-26-000257 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-07 | 2026-01-15 | 2026-01-16 | Contract line | CT-02 | 223.39 | Completed | No
WO-26-000258 | 1.2 | Crossroads |  | Streetlight | P4 planned | 2026-01-07 | 2026-02-03 | 2026-02-11 | Internal line |  | 88.5 | Completed | No
WO-26-000259 | 2.9 | Crossroads | CR-S10-03 | Trouble - no power | P1 emergency | 2026-01-07 | 2026-01-07 | 2026-01-07 | Troubleman |  | 153.9 | Completed | No
WO-26-000260 | 3.7 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-01-07 | 2026-01-07 | 2026-01-07 | Troubleman |  | 16.1 | Completed | No
WO-26-000261 | 3.4 | Crossroads | CR-S24-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-07 | 2026-01-09 | 2026-01-09 | Troubleman |  | 183.25 | Completed | No
WO-26-000262 | 6.9 | Bayou | BY-S07-05 | Corrective maintenance | P3 within 10 days | 2026-01-08 | 2026-01-13 | 2026-01-17 | Underground crew |  | 1340.23 | Completed | No
WO-26-000263 | 1.4 | Bayou | BY-S23-03 | Meter exchange | P3 within 10 days | 2026-01-08 | 2026-01-17 | 2026-01-19 | Meter technician |  | 129.43 | Completed | No
WO-26-000264 | 1.3 | Bayou | BY-S07-06 | Meter exchange | P3 within 10 days | 2026-01-08 | 2026-01-10 | 2026-01-11 | Meter technician |  | 81.43 | Completed | No
WO-26-000265 | 13.3 | Bayou | BY-S12-04 | New service - small | P3 within 10 days | 2026-01-08 | 2026-01-09 | 2026-01-10 | Underground crew |  | 809.39 | Completed | No
WO-26-000266 | 4.2 | Bayou | BY-S19-03 | Preventive maintenance | P4 planned | 2026-01-08 | 2026-02-06 | 2026-02-08 | Internal line |  | 315.36 | Completed | No
WO-26-000267 | 5.3 | Bayou | BY-S09-05 | Preventive maintenance | P4 planned | 2026-01-08 | 2026-02-12 | 2026-02-16 | Contract line | CT-03 | 95.05 | Completed | No
WO-26-000268 | 4.3 | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-01-08 | 2026-03-05 | 2026-03-07 | Contract line | CT-03 | 361.57 | Completed | No
WO-26-000269 | 4.5 | Bayou | BY-S16-05 | Preventive maintenance | P4 planned | 2026-01-08 | 2026-01-18 | 2026-01-18 | Internal line |  | 29.19 | Completed | No
WO-26-000270 | 4.7 | Bayou | BY-S16-02 | Preventive maintenance | P4 planned | 2026-01-08 | 2026-01-23 | 2026-01-25 | Internal line |  | 157.32 | Completed | No
WO-26-000271 | 1.1 | Bayou | BY-S15-03 | Service order - field | P2 same day | 2026-01-08 | 2026-01-08 | 2026-01-08 | Meter technician |  | 10.08 | Completed | No
WO-26-000272 | 9 | Bayou | BY-S29-01 | Transformer replacement | P3 within 10 days | 2026-01-08 | 2026-01-16 | 2026-01-16 | Internal line |  | 12232.05 | Completed | No
WO-26-000273 | 2.1 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Troubleman |  | 295.16 | Completed | No
WO-26-000274 | 2.7 | Bayou | BY-S11-01 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Troubleman |  | 211.19 | Completed | No
WO-26-000275 | 12 | Crossroads | CR-S32-03 | Corrective maintenance | P2 same day | 2026-01-08 | 2026-01-08 | 2026-01-08 | Contract line | CT-02 | 1239.29 | Completed | No
WO-26-000276 | 9.6 | Crossroads | CR-S06-03 | Corrective maintenance | P3 within 10 days | 2026-01-08 | 2026-01-11 | 2026-01-11 | Contract line | CT-02 | 1947.33 | Completed | No
WO-26-000277 | 7.7 | Crossroads | CR-S27-02 | Corrective maintenance | P3 within 10 days | 2026-01-08 | 2026-01-12 | 2026-01-14 | Underground crew |  | 1113.18 | Completed | No
WO-26-000278 | 1.2 | Crossroads | CR-S23-04 | Meter exchange | P3 within 10 days | 2026-01-08 | 2026-01-12 | 2026-01-12 | Meter technician |  | 117.16 | Completed | No
WO-26-000279 | 0.9 | Crossroads | CR-S22-03 | Meter exchange | P4 planned | 2026-01-08 | 2026-02-19 | 2026-02-23 | Meter technician |  | 165.26 | Completed | No
WO-26-000280 | 1 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-01-08 | 2026-01-18 | 2026-01-18 | Meter technician |  | 107.53 | Completed | No
WO-26-000281 | 7.8 | Crossroads | CR-S09-01 | New service - small | P4 planned | 2026-01-08 | 2026-02-19 | 2026-02-19 | Contract line | CT-02 | 3587.59 | Completed | No
WO-26-000282 | 10.1 | Crossroads | CR-S26-04 | New service - small | P4 planned | 2026-01-08 | 2026-02-08 | 2026-02-08 | Underground crew |  | 1546.96 | Completed | No
WO-26-000283 | 22.2 | Crossroads | CR-S16-02 | Pole replacement | P2 same day | 2026-01-08 | 2026-01-08 | 2026-01-08 | Internal line |  | 2236.71 | Completed | No
WO-26-000284 | 7.3 | Crossroads | CR-S27-04 | Preventive maintenance | P4 planned | 2026-01-08 | 2026-01-27 | 2026-01-27 | Internal line |  | 419.72 | Completed | No
WO-26-000285 | 0.7 | Crossroads | CR-S05-02 | Service order - field | P2 same day | 2026-01-08 | 2026-01-08 | 2026-01-08 | Meter technician |  | 10.19 | Completed | No
WO-26-000286 | 1 | Crossroads | CR-S07-01 | Service order - field | P2 same day | 2026-01-08 | 2026-01-08 | 2026-01-08 | Meter technician |  | 2.54 | Completed | No
WO-26-000287 | 1.3 | Crossroads | CR-S07-05 | Service order - field | P3 within 10 days | 2026-01-08 | 2026-01-09 | 2026-01-09 | Meter technician |  | 3.71 | Completed | No
WO-26-000288 | 1.3 | Crossroads | CR-S15-02 | Service order - field | P2 same day | 2026-01-08 | 2026-01-08 | 2026-01-08 | Meter technician |  | 12.09 | Completed | No
WO-26-000289 | 1.8 | Crossroads | CR-S32-05 | Service order - field | P3 within 10 days | 2026-01-08 | 2026-01-18 | 2026-01-22 | Meter technician |  | 28.83 | Completed | No
WO-26-000290 | 2.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-08 | 2026-01-15 | 2026-01-15 | Contract line | CT-01 | 152.3 | Completed | No
WO-26-000291 | 9.2 | Crossroads | CR-S27-02 | Transformer replacement | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Internal line |  | 9093.12 | Completed | No
WO-26-000292 | 12.6 | Crossroads | CR-S31-01 | Transformer replacement | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Internal line |  | 11080.53 | Completed | No
WO-26-000293 | 3 | Crossroads | CR-S25-03 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Troubleman |  | 33.66 | Completed | No
WO-26-000294 | 2.6 | Crossroads | CR-S18-03 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Troubleman |  | 210.1 | Completed | No
WO-26-000295 | 5.6 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Troubleman |  | 189.11 | Completed | No
WO-26-000296 | 5.4 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Internal line |  | 120.87 | Completed | No
WO-26-000297 | 5.1 | Crossroads | CR-S25-01 | Trouble - no power | P1 emergency | 2026-01-08 | 2026-01-08 | 2026-01-08 | Troubleman |  | 337.7 | Completed | No
WO-26-000298 | 3 | Crossroads | CR-S03-02 | Trouble - no power | P2 same day | 2026-01-08 | 2026-01-09 | 2026-01-09 | Internal line |  | 334.37 | Completed | No
WO-26-000299 | 1 | Bayou | BY-S14-01 | Meter exchange | P4 planned | 2026-01-09 | 2026-02-17 | 2026-02-19 | Meter technician |  | 118.36 | Completed | No
WO-26-000300 |  | Bayou | BY-S01-02 | Meter exchange | P3 within 10 days | 2026-01-09 | 2026-01-10 |  | Meter technician |  |  | Cancelled | No
WO-26-000301 | 10.5 | Bayou | BY-S18-01 | New service - small | P3 within 10 days | 2026-01-09 | 2026-01-17 | 2026-01-18 | Underground crew |  | 2593.12 | Completed | No
WO-26-000302 | 22.5 | Bayou | BY-S06-03 | Pole replacement | P3 within 10 days | 2026-01-09 | 2026-01-19 | 2026-01-23 | Internal line |  | 2163.82 | Completed | No
WO-26-000303 | 4.4 | Bayou | BY-S23-01 | Preventive maintenance | P4 planned | 2026-01-09 | 2026-02-15 | 2026-02-17 | Internal line |  | 568.75 | Completed | No
WO-26-000304 | 3.6 | Bayou | BY-S25-01 | Preventive maintenance | P4 planned | 2026-01-09 | 2026-01-18 | 2026-01-22 | Contract line | CT-03 | 497.08 | Completed | No
WO-26-000305 | 7.4 | Bayou | BY-S03-01 | Preventive maintenance | P4 planned | 2026-01-09 | 2026-02-11 | 2026-02-13 | Contract line | CT-04 | 497.74 | Completed | No
WO-26-000306 | 1.5 | Bayou | BY-S10-04 | Service order - field | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Meter technician |  | 19.34 | Completed | No
WO-26-000307 | 1.5 | Bayou | BY-S15-03 | Service order - field | P3 within 10 days | 2026-01-09 | 2026-01-19 | 2026-01-23 | Meter technician |  | 12.87 | Completed | No
WO-26-000308 | 1.1 | Bayou | BY-S26-04 | Service order - field | P3 within 10 days | 2026-01-09 | 2026-01-15 | 2026-01-23 | Meter technician |  | 32.29 | Completed | No
WO-26-000309 | 1.2 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-01-09 | 2026-01-18 | 2026-01-18 | Meter technician |  | 2 | Completed | No
WO-26-000310 | 1.1 | Bayou | BY-S26-01 | Service order - field | P3 within 10 days | 2026-01-09 | 2026-01-19 | 2026-01-27 | Meter technician |  | 33.41 | Completed | No
WO-26-000311 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-09 | 2026-01-13 | 2026-01-13 | Contract line | CT-04 | 107.32 | Completed | No
WO-26-000312 | 2.7 | Bayou |  | Streetlight | P4 planned | 2026-01-09 | 2026-03-02 | 2026-03-02 | Internal line |  | 368.3 | Completed | No
WO-26-000313 | 1.2 | Bayou |  | Streetlight | P4 planned | 2026-01-09 | 2026-03-04 | 2026-03-06 | Internal line |  | 98.18 | Completed | No
WO-26-000314 | 2.8 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Troubleman |  | 162.35 | Completed | No
WO-26-000315 | 4.6 | Bayou | BY-S23-01 | Trouble - no power | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Internal line |  | 214 | Completed | No
WO-26-000316 | 2.6 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Troubleman |  | 212.57 | Completed | No
WO-26-000317 | 1.7 | Bayou | BY-S27-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-09 | 2026-01-18 | 2026-01-18 | Internal line |  | 142.94 | Completed | No
WO-26-000318 | 3.5 | Crossroads | CR-S20-02 | Corrective maintenance | P3 within 10 days | 2026-01-09 | 2026-01-15 | 2026-01-15 | Internal line |  | 451.24 | Completed | No
WO-26-000319 | 4.4 | Crossroads | CR-S21-02 | Corrective maintenance | P2 same day | 2026-01-09 | 2026-01-10 | 2026-01-10 | Underground crew |  | 1752.77 | Completed | No
WO-26-000320 | 3.4 | Crossroads | CR-S27-01 | Corrective maintenance | P3 within 10 days | 2026-01-09 | 2026-01-18 | 2026-01-18 | Internal line |  | 683.12 | Completed | No
WO-26-000321 | 0.6 | Crossroads | CR-S03-01 | Meter exchange | P4 planned | 2026-01-09 | 2026-02-06 | 2026-02-07 | Meter technician |  | 93.09 | Completed | No
WO-26-000322 | 1 | Crossroads | CR-S16-03 | Meter exchange | P3 within 10 days | 2026-01-09 | 2026-01-17 | 2026-01-17 | Meter technician |  | 119.71 | Completed | No
WO-26-000323 | 15.8 | Crossroads | CR-S26-06 | New service - small | P3 within 10 days | 2026-01-09 | 2026-01-14 | 2026-01-16 | Contract line | CT-02 | 4184.33 | Completed | No
WO-26-000324 | 20.6 | Crossroads | CR-S13-02 | Pole replacement | P4 planned | 2026-01-09 | 2026-01-18 | 2026-01-18 | Contract line | CT-02 | 2728.81 | Completed | No
WO-26-000325 | 21.6 | Crossroads | CR-S09-03 | Pole replacement | P4 planned | 2026-01-09 | 2026-01-20 | 2026-01-28 | Internal line |  | 2670.72 | Completed | No
WO-26-000326 | 0.9 | Crossroads | CR-S06-02 | Service order - field | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Meter technician |  | 18.74 | Completed | No
WO-26-000327 | 1.4 | Crossroads | CR-S13-05 | Service order - field | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Meter technician |  | 11.27 | Completed | No
WO-26-000328 | 1.6 | Crossroads | CR-S14-02 | Service order - field | P3 within 10 days | 2026-01-09 | 2026-01-14 | 2026-01-14 | Meter technician |  | 7.12 | Completed | No
WO-26-000329 | 1 | Crossroads | CR-S25-06 | Service order - field | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Meter technician |  | 30.8 | Completed | No
WO-26-000330 | 1 | Crossroads | CR-S20-05 | Service order - field | P3 within 10 days | 2026-01-09 | 2026-01-10 | 2026-01-11 | Meter technician |  | 14.24 | Completed | No
WO-26-000331 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-09 | 2026-01-13 | 2026-01-13 | Internal line |  | 363.49 | Completed | No
WO-26-000332 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-09 | 2026-01-10 | 2026-01-11 | Contract line | CT-02 | 294.25 | Completed | No
WO-26-000333 | 8.2 | Crossroads | CR-S25-03 | Transformer replacement | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Internal line |  | 5177.06 | Completed | No
WO-26-000334 | 10.7 | Crossroads | CR-S08-03 | Transformer replacement | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Internal line |  | 9531.43 | Completed | No
WO-26-000335 | 3.8 | Crossroads | CR-S02-02 | Trouble - no power | P2 same day | 2026-01-09 | 2026-01-10 | 2026-01-10 | Troubleman |  | 176.87 | Completed | No
WO-26-000336 | 4.7 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Troubleman |  | 319.39 | Completed | No
WO-26-000337 | 5.2 | Crossroads | CR-S26-04 | Trouble - no power | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Troubleman |  | 272.94 | Completed | No
WO-26-000338 | 2.1 | Crossroads | CR-S15-01 | Trouble - no power | P2 same day | 2026-01-09 | 2026-01-10 | 2026-01-10 | Internal line |  | 119.49 | Completed | No
WO-26-000339 | 3.9 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-01-09 | 2026-01-09 | 2026-01-09 | Troubleman |  | 225.48 | Completed | No
WO-26-000340 | 4.1 | Crossroads | CR-S07-07 | Trouble - no power | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Troubleman |  | 205.61 | Completed | No
WO-26-000341 | 2.2 | Crossroads | CR-S12-02 | Trouble - no power | P2 same day | 2026-01-09 | 2026-01-09 | 2026-01-09 | Internal line |  | 98.89 | Completed | No
WO-26-000342 | 2.4 | Crossroads | CR-S15-03 | Trouble - partial or voltage | P2 same day | 2026-01-09 | 2026-01-10 | 2026-01-10 | Internal line |  | 171.93 | Completed | No
WO-26-000343 | 2.4 | Bayou | BY-S15-06 | Trouble - no power | P1 emergency | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 229.06 | Completed | No
WO-26-000344 | 3 | Bayou | BY-S09-01 | Trouble - no power | P1 emergency | 2026-01-10 | 2026-01-10 | 2026-01-10 | Internal line |  | 39.95 | Completed | No
WO-26-000345 | 2.7 | Bayou | BY-S28-03 | Trouble - no power | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 339.59 | Completed | No
WO-26-000346 | 5.2 | Bayou | BY-S15-02 | Trouble - no power | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 18.21 | Completed | No
WO-26-000347 | 4.8 | Bayou | BY-S09-01 | Trouble - no power | P1 emergency | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 190.62 | Completed | No
WO-26-000348 | 1.6 | Bayou | BY-S19-01 | Trouble - partial or voltage | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 88.21 | Completed | No
WO-26-000349 | 2.2 | Bayou | BY-S26-02 | Trouble - partial or voltage | P2 same day | 2026-01-10 | 2026-01-11 | 2026-01-11 | Troubleman |  | 30.84 | Completed | No
WO-26-000350 | 17.7 | Crossroads | CR-S22-01 | Pole replacement | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Contract line | CT-02 | 3212.39 | Completed | No
WO-26-000351 | 1.1 | Crossroads | CR-S03-02 | Service order - field | P2 same day | 2026-01-10 | 2026-01-11 | 2026-01-11 | Meter technician |  | 35.69 | Completed | No
WO-26-000352 | 1.6 | Crossroads | CR-S25-04 | Service order - field | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Meter technician |  | 10.11 | Completed | No
WO-26-000353 | 1.4 | Crossroads | CR-S11-01 | Service order - field | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Meter technician |  | 5.81 | Completed | No
WO-26-000354 | 5.5 | Crossroads | CR-S02-04 | Trouble - no power | P2 same day | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 212.27 | Completed | No
WO-26-000355 | 4.8 | Crossroads | CR-S07-06 | Trouble - no power | P1 emergency | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 148.81 | Completed | No
WO-26-000356 | 2.7 | Crossroads | CR-S24-01 | Trouble - no power | P1 emergency | 2026-01-10 | 2026-01-10 | 2026-01-10 | Troubleman |  | 324.15 | Completed | No
WO-26-000357 | 1.7 | Bayou | BY-S23-04 | Service order - field | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Meter technician |  | 24.85 | Completed | No
WO-26-000358 | 1.4 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Meter technician |  | 33.6 | Completed | No
WO-26-000359 | 1.1 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Meter technician |  | 4.28 | Completed | No
WO-26-000360 | 1 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Meter technician |  | 4.43 | Completed | No
WO-26-000361 | 10.1 | Bayou | BY-S13-06 | Transformer replacement | P2 same day | 2026-01-11 | 2026-01-12 | 2026-01-12 | Contract line | CT-04 | 3250.33 | Completed | No
WO-26-000362 |  | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 |  | Internal line |  |  | Cancelled | No
WO-26-000363 | 2.1 | Bayou | BY-S18-07 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Troubleman |  | 140.22 | Completed | No
WO-26-000364 | 4.2 | Bayou | BY-S23-01 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Troubleman |  | 346.66 | Completed | No
WO-26-000365 | 4.7 | Bayou | BY-S13-04 | Trouble - partial or voltage | P2 same day | 2026-01-11 | 2026-01-12 | 2026-01-12 | Internal line |  | 25.99 | Completed | No
WO-26-000366 | 4.9 | Bayou | BY-S24-01 | Trouble - partial or voltage | P2 same day | 2026-01-11 | 2026-01-12 | 2026-01-12 | Troubleman |  | 35.22 | Completed | No
WO-26-000367 | 8.8 | Crossroads | CR-S32-01 | Corrective maintenance | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Underground crew |  | 1409.23 | Completed | No
WO-26-000368 | 1.5 | Crossroads | CR-S28-01 | Service order - field | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Meter technician |  | 25.96 | Completed | No
WO-26-000369 | 0.9 | Crossroads | CR-S15-02 | Service order - field | P2 same day | 2026-01-11 | 2026-01-11 | 2026-01-11 | Meter technician |  | 19.29 | Completed | No
WO-26-000370 | 3 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-01-11 | 2026-01-12 | 2026-01-12 | Troubleman |  | 257 | Completed | No
WO-26-000371 | 5.3 | Crossroads | CR-S03-02 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Troubleman |  | 175.48 | Completed | No
WO-26-000372 | 4.2 | Crossroads | CR-S24-04 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Troubleman |  | 83.68 | Completed | No
WO-26-000373 | 5.4 | Crossroads | CR-S25-02 | Trouble - no power | P2 same day | 2026-01-11 | 2026-01-12 | 2026-01-12 | Troubleman |  | 56.5 | Completed | No
WO-26-000374 | 4.8 | Crossroads | CR-S03-02 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Troubleman |  | 163.22 | Completed | No
WO-26-000375 | 4.1 | Crossroads | CR-S24-03 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Troubleman |  | 48.1 | Completed | No
WO-26-000376 | 5.4 | Crossroads | CR-S16-03 | Trouble - no power | P1 emergency | 2026-01-11 | 2026-01-11 | 2026-01-11 | Internal line |  | 173.88 | Completed | No
WO-26-000377 | 4.1 | Crossroads | CR-S08-02 | Trouble - partial or voltage | P2 same day | 2026-01-11 | 2026-01-12 | 2026-01-12 | Troubleman |  | 34.22 | Completed | No
WO-26-000378 | 6.7 | Bayou | BY-S15-02 | Corrective maintenance | P4 planned | 2026-01-12 | 2026-01-29 | 2026-01-30 | Internal line |  | 674.53 | Completed | No
WO-26-000379 | 7 | Bayou | BY-S07-01 | Corrective maintenance | P4 planned | 2026-01-12 | 2026-02-16 | 2026-02-16 | Internal line |  | 522.44 | Completed | No
WO-26-000380 | 4.1 | Bayou | BY-S29-03 | Corrective maintenance | P3 within 10 days | 2026-01-12 | 2026-01-18 | 2026-01-19 | Internal line |  | 2198.36 | Completed | No
WO-26-000381 | 3.6 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-01-12 | 2026-01-16 | 2026-01-17 | Internal line |  | 289.7 | Completed | No
WO-26-000382 | 1.1 | Bayou | BY-S15-02 | Meter exchange | P3 within 10 days | 2026-01-12 | 2026-01-19 | 2026-01-20 | Meter technician |  | 143.89 | Completed | No
WO-26-000383 | 0.9 | Bayou | BY-S04-02 | Meter exchange | P3 within 10 days | 2026-01-12 | 2026-01-14 | 2026-01-14 | Meter technician |  | 70.15 | Completed | No
WO-26-000384 | 1.1 | Bayou | BY-S21-01 | Meter exchange | P4 planned | 2026-01-12 | 2026-02-04 | 2026-02-04 | Meter technician |  | 125.69 | Completed | No
WO-26-000385 | 4.4 | Bayou | BY-S07-01 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-02-27 | 2026-02-28 | Internal line |  | 289.71 | Completed | No
WO-26-000386 | 6.1 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-02-09 | 2026-02-13 | Internal line |  | 445.08 | Completed | No
WO-26-000387 | 3.4 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-02-24 | 2026-02-25 | Internal line |  | 498.56 | Completed | No
WO-26-000388 | 1.7 | Bayou | BY-S27-01 | Service order - field | P3 within 10 days | 2026-01-12 | 2026-01-19 | 2026-01-19 | Meter technician |  | 20.64 | Completed | No
WO-26-000389 | 1.4 | Bayou | BY-S18-06 | Service order - field | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Meter technician |  | 29.68 | Completed | No
WO-26-000390 | 1 | Bayou | BY-S27-01 | Service order - field | P2 same day | 2026-01-12 | 2026-01-13 | 2026-01-13 | Meter technician |  | 29.01 | Completed | No
WO-26-000391 | 1.7 | Bayou | BY-S18-02 | Service order - field | P3 within 10 days | 2026-01-12 | 2026-01-17 | 2026-01-17 | Meter technician |  | 17.99 | Completed | No
WO-26-000392 | 1.7 | Bayou | BY-S30-01 | Service order - field | P3 within 10 days | 2026-01-12 | 2026-01-13 | 2026-01-13 | Meter technician |  | 5.98 | Completed | No
WO-26-000393 | 1.5 | Bayou | BY-S02-01 | Service order - field | P3 within 10 days | 2026-01-12 | 2026-01-21 | 2026-01-22 | Meter technician |  | 6.05 | Completed | No
WO-26-000394 | 0.7 | Bayou | BY-S13-06 | Service order - field | P2 same day | 2026-01-12 | 2026-01-13 | 2026-01-13 | Meter technician |  | 8.96 | Completed | No
WO-26-000395 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-12 | 2026-01-22 | 2026-01-22 | Internal line |  | 408 | Completed | No
WO-26-000396 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-12 | 2026-01-19 | 2026-01-20 | Contract line | CT-04 | 167.06 | Completed | No
WO-26-000397 | 4.3 | Bayou | BY-S05-02 | Trouble - no power | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 98.44 | Completed | No
WO-26-000398 | 2 | Bayou | BY-S05-02 | Trouble - no power | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 149.83 | Completed | No
WO-26-000399 | 3.7 | Bayou | BY-S16-06 | Trouble - no power | P2 same day | 2026-01-12 | 2026-01-13 | 2026-01-13 | Troubleman |  | 228.09 | Completed | No
WO-26-000400 | 4.1 | Bayou | BY-S23-01 | Trouble - no power | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 339.64 | Completed | No
WO-26-000401 | 3.7 | Bayou | BY-S15-01 | Trouble - partial or voltage | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 162.64 | Completed | No
WO-26-000402 | 2.3 | Bayou | BY-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-12 | 2026-01-22 | 2026-01-22 | Troubleman |  | 179.65 | Completed | No
WO-26-000403 | 4.7 | Bayou | BY-S08-02 | Trouble - partial or voltage | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Internal line |  | 244.54 | Completed | No
WO-26-000404 | 10.3 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-01-12 | 2026-01-12 | 2026-01-12 | Internal line |  | 2095.4 | Completed | No
WO-26-000405 | 4.9 | Crossroads | CR-S14-01 | Corrective maintenance | P4 planned | 2026-01-12 | 2026-03-13 | 2026-03-13 | Underground crew |  | 2020.76 | Completed | No
WO-26-000406 | 7 | Crossroads | CR-S17-03 | Corrective maintenance | P2 same day | 2026-01-12 | 2026-01-13 | 2026-01-13 | Contract line | CT-02 | 1187.6 | Completed | No
WO-26-000407 | 4.6 | Crossroads | CR-S20-02 | Corrective maintenance | P3 within 10 days | 2026-01-12 | 2026-01-20 | 2026-01-22 | Underground crew |  | 1453.56 | Completed | No
WO-26-000408 | 9.3 | Crossroads | CR-S13-03 | Corrective maintenance | P3 within 10 days | 2026-01-12 | 2026-01-16 | 2026-01-17 | Underground crew |  | 589.63 | Completed | No
WO-26-000409 | 1.2 | Crossroads | CR-S14-03 | Meter exchange | P4 planned | 2026-01-12 | 2026-01-31 | 2026-01-31 | Meter technician |  | 172.62 | Completed | No
WO-26-000410 | 1.2 | Crossroads | CR-S19-02 | Meter exchange | P3 within 10 days | 2026-01-12 | 2026-01-22 | 2026-01-23 | Meter technician |  | 179.21 | Completed | No
WO-26-000411 | 0.8 | Crossroads | CR-S19-03 | Meter exchange | P4 planned | 2026-01-12 | 2026-01-20 | 2026-01-20 | Meter technician |  | 128.98 | Completed | No
WO-26-000412 | 11.4 | Crossroads | CR-S32-04 | New service - small | P4 planned | 2026-01-12 | 2026-03-06 | 2026-03-06 | Contract line | CT-01 | 2938.01 | Completed | No
WO-26-000413 | 17.4 | Crossroads | CR-S04-01 | Pole replacement | P4 planned | 2026-01-12 | 2026-02-28 | 2026-03-04 | Contract line | CT-01 | 2456.76 | Completed | No
WO-26-000414 | 11.2 | Crossroads | CR-S24-02 | Pole replacement | P3 within 10 days | 2026-01-12 | 2026-01-21 | 2026-01-21 | Contract line | CT-01 | 1805.91 | Completed | No
WO-26-000415 | 3 | Crossroads | CR-S14-01 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-02-07 | 2026-02-08 | Contract line | CT-02 | 306.63 | Completed | No
WO-26-000416 | 2 | Crossroads | CR-S20-04 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-01-27 | 2026-01-31 | Internal line |  | 260.15 | Completed | No
WO-26-000417 | 5.2 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-01-23 | 2026-01-23 | Internal line |  | 445.97 | Completed | No
WO-26-000418 | 5.8 | Crossroads | CR-S13-05 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-03-02 | 2026-03-02 | Internal line |  | 497.99 | Completed | No
WO-26-000419 | 2.2 | Crossroads | CR-S24-04 | Preventive maintenance | P4 planned | 2026-01-12 | 2026-01-21 | 2026-01-21 | Contract line | CT-02 | 43.49 | Completed | No
WO-26-000420 | 2.2 | Crossroads |  | Streetlight | P4 planned | 2026-01-12 | 2026-02-24 | 2026-02-28 | Contract line | CT-01 | 359.61 | Completed | No
WO-26-000421 | 1.7 | Crossroads |  | Streetlight | P4 planned | 2026-01-12 | 2026-01-21 | 2026-01-21 | Contract line | CT-02 | 223.78 | Completed | No
WO-26-000422 | 1.9 | Crossroads |  | Streetlight | P4 planned | 2026-01-12 | 2026-02-25 | 2026-02-26 | Internal line |  | 389.37 | Completed | No
WO-26-000423 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-12 | 2026-01-20 | 2026-01-21 | Contract line | CT-02 | 363.18 | Completed | No
WO-26-000424 | 10.9 | Crossroads | CR-S08-02 | Transformer replacement | P1 emergency | 2026-01-12 | 2026-01-12 | 2026-01-12 | Contract line | CT-01 | 9582.65 | Completed | No
WO-26-000425 | 3.6 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-01-12 | 2026-01-13 | 2026-01-13 | Troubleman |  | 75.16 | Completed | No
WO-26-000426 | 3.8 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 84.34 | Completed | No
WO-26-000427 | 2 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 244.56 | Completed | No
WO-26-000428 | 5.7 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-01-12 | 2026-01-12 | 2026-01-12 | Troubleman |  | 137.31 | Completed | No
WO-26-000429 | 4.1 | Crossroads | CR-S09-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-12 | 2026-01-17 | 2026-01-17 | Internal line |  | 11.97 | Completed | No
WO-26-000430 | 3.4 | Crossroads | CR-S04-05 | Trouble - partial or voltage | P2 same day | 2026-01-12 | 2026-01-13 | 2026-01-13 | Troubleman |  | 27.12 | Completed | No
WO-26-000431 | 7.6 | Bayou | BY-S14-01 | Corrective maintenance | P3 within 10 days | 2026-01-13 | 2026-01-21 | 2026-01-21 | Contract line | CT-04 | 830.52 | Completed | No
WO-26-000432 | 9.5 | Bayou | BY-S16-06 | Corrective maintenance | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Contract line | CT-04 | 1319.28 | Completed | No
WO-26-000433 | 11.5 | Bayou | BY-S07-03 | Corrective maintenance | P3 within 10 days | 2026-01-13 | 2026-01-23 | 2026-01-24 | Underground crew |  | 1630.05 | Completed | No
WO-26-000434 | 11.8 | Bayou | BY-S01-02 | Corrective maintenance | P3 within 10 days | 2026-01-13 | 2026-01-23 | 2026-01-27 | Internal line |  | 1491.53 | Completed | No
WO-26-000435 | 1.1 | Bayou | BY-S18-06 | Meter exchange | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-25 | Meter technician |  | 139.87 | Completed | No
WO-26-000436 | 14.2 | Bayou | BY-S25-04 | Pole replacement | P4 planned | 2026-01-13 | 2026-02-19 | 2026-02-19 | Internal line |  | 1415.47 | Completed | No
WO-26-000437 | 5.9 | Bayou | BY-S15-06 | Preventive maintenance | P4 planned | 2026-01-13 | 2026-02-16 | 2026-02-16 | Internal line |  | 239.22 | Completed | No
WO-26-000438 | 1.2 | Bayou | BY-S15-03 | Service order - field | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Meter technician |  | 11.06 | Completed | No
WO-26-000439 | 1.7 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-22 | 2026-01-26 | Meter technician |  | 7.16 | Completed | No
WO-26-000440 | 1.2 | Bayou | BY-S01-01 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-17 | Meter technician |  | 14.38 | Completed | No
WO-26-000441 | 0.6 | Bayou | BY-S13-04 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-22 | 2026-01-24 | Meter technician |  | 3.5 | Completed | No
WO-26-000442 | 1.2 | Bayou | BY-S10-02 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-21 | 2026-01-21 | Meter technician |  | 29.89 | Completed | No
WO-26-000443 | 7.8 | Bayou | BY-S03-02 | Transformer replacement | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Internal line |  | 4652.66 | Completed | No
WO-26-000444 | 9.4 | Bayou | BY-S30-03 | Transformer replacement | P2 same day | 2026-01-13 | 2026-01-13 | 2026-01-13 | Internal line |  | 5099.35 | Completed | No
WO-26-000445 | 5.7 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-01-13 | 2026-01-13 | 2026-01-13 | Troubleman |  | 101.61 | Completed | No
WO-26-000446 | 1.6 | Bayou | BY-S29-05 | Trouble - partial or voltage | P2 same day | 2026-01-13 | 2026-01-13 | 2026-01-13 | Troubleman |  | 131.04 | Completed | No
WO-26-000447 | 3.3 | Bayou | BY-S06-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-19 | Troubleman |  | 237.03 | Completed | No
WO-26-000448 | 5.1 | Crossroads | CR-S24-03 | Corrective maintenance | P3 within 10 days | 2026-01-13 | 2026-01-23 | 2026-01-25 | Internal line |  | 1847.71 | Completed | No
WO-26-000449 | 9.2 | Crossroads | CR-S07-06 | Corrective maintenance | P2 same day | 2026-01-13 | 2026-01-13 | 2026-01-13 | Internal line |  | 1059.71 | Completed | No
WO-26-000450 | 6.5 | Crossroads | CR-S18-01 | Corrective maintenance | P3 within 10 days | 2026-01-13 | 2026-01-21 | 2026-01-22 | Contract line | CT-02 | 475.63 | Completed | No
WO-26-000451 | 1 | Crossroads | CR-S28-02 | Meter exchange | P3 within 10 days | 2026-01-13 | 2026-01-14 | 2026-01-14 | Meter technician |  | 132.94 | Completed | No
WO-26-000452 | 0.7 | Crossroads | CR-S06-01 | Meter exchange | P4 planned | 2026-01-13 | 2026-03-07 | 2026-03-07 | Meter technician |  | 75.47 | Completed | No
WO-26-000453 |  | Crossroads | CR-S02-01 | Meter exchange | P4 planned | 2026-01-13 | 2026-02-10 |  | Meter technician |  |  | Cancelled | No
WO-26-000454 | 1.4 | Crossroads | CR-S29-01 | Meter exchange | P3 within 10 days | 2026-01-13 | 2026-01-21 | 2026-01-21 | Meter technician |  | 105.21 | Completed | No
WO-26-000455 | 22.5 | Crossroads | CR-S25-02 | Pole replacement | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-18 | Internal line |  | 2333.29 | Completed | No
WO-26-000456 | 20.7 | Crossroads | CR-S18-05 | Pole replacement | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Contract line | CT-01 | 2710.79 | Completed | No
WO-26-000457 | 7.1 | Crossroads | CR-S04-01 | Preventive maintenance | P4 planned | 2026-01-13 | 2026-02-17 | 2026-02-18 | Underground crew |  | 96.43 | Completed | No
WO-26-000458 | 4.8 | Crossroads | CR-S15-02 | Preventive maintenance | P4 planned | 2026-01-13 | 2026-02-28 | 2026-03-08 | Internal line |  | 535.64 | Completed | No
WO-26-000459 | 7.7 | Crossroads | CR-S28-03 | Preventive maintenance | P4 planned | 2026-01-13 | 2026-03-12 | 2026-03-12 | Internal line |  | 447.2 | Completed | No
WO-26-000460 | 3.3 | Crossroads | CR-S16-06 | Preventive maintenance | P4 planned | 2026-01-13 | 2026-02-22 | 2026-02-23 | Underground crew |  | 222.18 | Completed | No
WO-26-000461 | 0.8 | Crossroads | CR-S05-03 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-17 | Meter technician |  | 6.97 | Completed | No
WO-26-000462 | 1.4 | Crossroads | CR-S32-03 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-16 | 2026-01-16 | Meter technician |  | 7.76 | Completed | No
WO-26-000463 | 0.8 | Crossroads | CR-S13-06 | Service order - field | P3 within 10 days | 2026-01-13 | 2026-01-16 | 2026-01-16 | Meter technician |  | 38.34 | Completed | No
WO-26-000464 | 1.2 | Crossroads | CR-S24-01 | Service order - field | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Meter technician |  | 6.92 | Completed | No
WO-26-000465 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-25 | Contract line | CT-02 | 223.83 | Completed | No
WO-26-000466 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-13 | 2026-01-22 | 2026-01-22 | Internal line |  | 69.79 | Completed | No
WO-26-000467 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-13 | 2026-01-17 | 2026-01-18 | Internal line |  | 425.16 | Completed | No
WO-26-000468 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-13 | 2026-01-20 | 2026-01-21 | Contract line | CT-01 | 278.81 | Completed | No
WO-26-000469 | 1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-13 | 2026-01-18 | 2026-01-18 | Contract line | CT-02 | 385.15 | Completed | No
WO-26-000470 | 2.8 | Crossroads |  | Streetlight | P4 planned | 2026-01-13 | 2026-02-02 | 2026-02-02 | Contract line | CT-01 | 138.84 | Completed | No
WO-26-000471 | 12.5 | Crossroads | CR-S16-02 | Transformer replacement | P2 same day | 2026-01-13 | 2026-01-13 | 2026-01-13 | Contract line | CT-01 | 11965.28 | Completed | No
WO-26-000472 | 3.2 | Crossroads | CR-S20-05 | Trouble - no power | P1 emergency | 2026-01-13 | 2026-01-13 | 2026-01-13 | Troubleman |  | 286 | Completed | No
WO-26-000473 | 3.4 | Crossroads | CR-S04-01 | Trouble - no power | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Troubleman |  | 130.06 | Completed | No
WO-26-000474 | 2.1 | Crossroads | CR-S13-03 | Trouble - no power | P2 same day | 2026-01-13 | 2026-01-13 | 2026-01-13 | Troubleman |  | 189.68 | Completed | No
WO-26-000475 | 4.4 | Crossroads | CR-S19-04 | Trouble - no power | P2 same day | 2026-01-13 | 2026-01-14 | 2026-01-14 | Internal line |  | 89.85 | Completed | No
WO-26-000476 | 10 | Bayou | BY-S07-01 | Corrective maintenance | P3 within 10 days | 2026-01-14 | 2026-01-20 | 2026-01-20 | Internal line |  | 1638.99 | Completed | No
WO-26-000477 | 10.4 | Bayou | BY-S25-02 | Corrective maintenance | P3 within 10 days | 2026-01-14 | 2026-01-17 | 2026-01-18 | Underground crew |  | 1538.36 | Completed | No
WO-26-000478 | 3.3 | Bayou | BY-S18-01 | Corrective maintenance | P3 within 10 days | 2026-01-14 | 2026-01-21 | 2026-01-21 | Internal line |  | 1782.41 | Completed | No
WO-26-000479 | 5.3 | Bayou | BY-S28-01 | Corrective maintenance | P4 planned | 2026-01-14 | 2026-01-23 | 2026-01-23 | Underground crew |  | 1233.01 | Completed | No
WO-26-000480 | 11 | Bayou | BY-S27-06 | Corrective maintenance | P3 within 10 days | 2026-01-14 | 2026-01-23 | 2026-01-24 | Underground crew |  | 2154.23 | Completed | No
WO-26-000481 | 2.6 | Bayou | BY-S11-03 | Preventive maintenance | P4 planned | 2026-01-14 | 2026-02-23 | 2026-02-27 | Contract line | CT-04 | 396.32 | Completed | No
WO-26-000482 | 0.9 | Bayou | BY-S06-02 | Service order - field | P3 within 10 days | 2026-01-14 | 2026-01-22 | 2026-01-22 | Meter technician |  | 30.94 | Completed | No
WO-26-000483 | 2 | Bayou |  | Streetlight | P4 planned | 2026-01-14 | 2026-02-08 | 2026-02-10 | Contract line | CT-04 | 182.83 | Completed | No
WO-26-000484 | 8.6 | Bayou | BY-S13-06 | Transformer replacement | P1 emergency | 2026-01-14 | 2026-01-14 | 2026-01-14 | Internal line |  | 8143.25 | Completed | No
WO-26-000485 | 2.2 | Bayou | BY-S11-02 | Trouble - no power | P1 emergency | 2026-01-14 | 2026-01-14 | 2026-01-14 | Troubleman |  | 16.75 | Completed | No
WO-26-000486 | 3.3 | Crossroads | CR-S20-05 | Corrective maintenance | P2 same day | 2026-01-14 | 2026-01-14 | 2026-01-14 | Underground crew |  | 807.8 | Completed | No
WO-26-000487 | 6.1 | Crossroads | CR-S14-05 | Corrective maintenance | P2 same day | 2026-01-14 | 2026-01-15 | 2026-01-15 | Internal line |  | 941.03 | Completed | No
WO-26-000488 | 7.8 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-01-14 | 2026-01-15 | 2026-01-19 | Underground crew |  | 1688.97 | Completed | No
WO-26-000489 | 4 | Crossroads | CR-S23-02 | New service - small | P3 within 10 days | 2026-01-14 | 2026-01-23 | 2026-01-23 | Contract line | CT-01 | 1788.82 | Completed | No
WO-26-000490 | 4.5 | Crossroads | CR-S16-02 | New service - small | P4 planned | 2026-01-14 | 2026-03-06 | 2026-03-06 | Internal line |  | 2291.35 | Completed | No
WO-26-000491 | 10.2 | Crossroads | CR-S26-02 | Pole replacement | P2 same day | 2026-01-14 | 2026-01-15 | 2026-01-15 | Contract line | CT-01 | 1494.47 | Completed | No
WO-26-000492 | 6.5 | Crossroads | CR-S23-05 | Preventive maintenance | P4 planned | 2026-01-14 | 2026-03-08 | 2026-03-08 | Underground crew |  | 237.95 | Completed | No
WO-26-000493 | 0.7 | Crossroads | CR-S05-04 | Service order - field | P3 within 10 days | 2026-01-14 | 2026-01-23 | 2026-01-23 | Meter technician |  | 31.31 | Completed | No
WO-26-000494 | 1.1 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-01-14 | 2026-01-15 | 2026-01-15 | Meter technician |  | 3.33 | Completed | No
WO-26-000495 | 1 | Crossroads | CR-S31-01 | Service order - field | P2 same day | 2026-01-14 | 2026-01-14 | 2026-01-14 | Meter technician |  | 20.54 | Completed | No
WO-26-000496 | 0.8 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-01-14 | 2026-01-14 | 2026-01-14 | Meter technician |  | 38.31 | Completed | No
WO-26-000497 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-14 | 2026-01-20 | 2026-01-20 | Contract line | CT-02 | 220.84 | Completed | No
WO-26-000498 | 8.6 | Crossroads | CR-S17-01 | Transformer replacement | P3 within 10 days | 2026-01-14 | 2026-01-21 | 2026-01-21 | Contract line | CT-02 | 3235.42 | Completed | No
WO-26-000499 |  | Crossroads | CR-S21-03 | Transformer replacement | P3 within 10 days | 2026-01-14 | 2026-01-19 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-000500 | 5.9 | Crossroads | CR-S02-01 | Trouble - no power | P2 same day | 2026-01-14 | 2026-01-14 | 2026-01-14 | Internal line |  | 190.19 | Completed | No
WO-26-000501 | 5.7 | Crossroads | CR-S23-05 | Trouble - no power | P1 emergency | 2026-01-14 | 2026-01-14 | 2026-01-14 | Troubleman |  | 248.38 | Completed | No
WO-26-000502 | 3.4 | Crossroads | CR-S23-03 | Trouble - no power | P1 emergency | 2026-01-14 | 2026-01-14 | 2026-01-14 | Internal line |  | 284.85 | Completed | No
WO-26-000503 | 3.4 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-01-14 | 2026-01-14 | 2026-01-14 | Internal line |  | 275.17 | Completed | No
WO-26-000504 | 4.4 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-01-14 | 2026-01-14 | 2026-01-14 | Troubleman |  | 270.21 | Completed | No
WO-26-000505 | 3.1 | Crossroads | CR-S04-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-14 | 2026-01-23 | 2026-01-25 | Troubleman |  | 140.48 | Completed | No
WO-26-000506 | 10.4 | Bayou | BY-S28-01 | Corrective maintenance | P3 within 10 days | 2026-01-15 | 2026-01-24 | 2026-01-28 | Underground crew |  | 1588.09 | Completed | No
WO-26-000507 | 0.9 | Bayou | BY-S23-04 | Meter exchange | P4 planned | 2026-01-15 | 2026-02-15 | 2026-02-15 | Meter technician |  | 84.99 | Completed | No
WO-26-000508 | 1.3 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-01-15 | 2026-01-20 | 2026-01-20 | Meter technician |  | 88.01 | Completed | No
WO-26-000509 | 0.8 | Bayou | BY-S23-03 | Meter exchange | P3 within 10 days | 2026-01-15 | 2026-01-17 | 2026-01-17 | Meter technician |  | 70.37 | Completed | No
WO-26-000510 | 7.8 | Bayou | BY-S20-03 | Preventive maintenance | P4 planned | 2026-01-15 | 2026-02-13 | 2026-02-13 | Internal line |  | 388.15 | Completed | No
WO-26-000511 | 0.6 | Bayou | BY-S21-03 | Service order - field | P3 within 10 days | 2026-01-15 | 2026-01-25 | 2026-01-25 | Meter technician |  | 3.8 | Completed | No
WO-26-000512 | 0.7 | Bayou | BY-S18-01 | Service order - field | P3 within 10 days | 2026-01-15 | 2026-01-19 | 2026-01-20 | Meter technician |  | 37.46 | Completed | No
WO-26-000513 | 1.7 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Meter technician |  | 9.77 | Completed | No
WO-26-000514 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-15 | 2026-01-22 | 2026-01-30 | Internal line |  | 191.88 | Completed | No
WO-26-000515 | 1.8 | Bayou |  | Streetlight | P4 planned | 2026-01-15 | 2026-02-07 | 2026-02-07 | Internal line |  | 343.89 | Completed | No
WO-26-000516 | 9 | Bayou | BY-S07-04 | Transformer replacement | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Internal line |  | 10374.56 | Completed | No
WO-26-000517 | 3.9 | Bayou | BY-S26-05 | Trouble - no power | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 86.45 | Completed | No
WO-26-000518 | 4.2 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-01-15 | 2026-01-15 | 2026-01-15 | Internal line |  | 196.62 | Completed | No
WO-26-000519 | 4.5 | Bayou | BY-S21-04 | Trouble - partial or voltage | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 42.54 | Completed | No
WO-26-000520 | 2 | Bayou | BY-S07-06 | Trouble - partial or voltage | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Internal line |  | 157.45 | Completed | No
WO-26-000521 | 4.7 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-01-15 | 2026-01-25 | 2026-01-27 | Contract line | CT-01 | 843.47 | Completed | No
WO-26-000522 | 6.6 | Crossroads | CR-S23-03 | Corrective maintenance | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Underground crew |  | 1577.16 | Completed | No
WO-26-000523 | 8.3 | Crossroads | CR-S28-03 | Corrective maintenance | P3 within 10 days | 2026-01-15 | 2026-01-17 | 2026-01-17 | Contract line | CT-02 | 1202.28 | Completed | No
WO-26-000524 | 10.3 | Crossroads | CR-S31-02 | Corrective maintenance | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Internal line |  | 1136.95 | Completed | No
WO-26-000525 | 0.9 | Crossroads | CR-S25-05 | Meter exchange | P3 within 10 days | 2026-01-15 | 2026-01-18 | 2026-01-18 | Meter technician |  | 79.86 | Completed | No
WO-26-000526 | 1.2 | Crossroads | CR-S22-04 | Meter exchange | P3 within 10 days | 2026-01-15 | 2026-01-20 | 2026-01-24 | Meter technician |  | 62.94 | Completed | No
WO-26-000527 | 0.5 | Crossroads | CR-S16-06 | Meter exchange | P4 planned | 2026-01-15 | 2026-03-09 | 2026-03-09 | Meter technician |  | 69.66 | Completed | No
WO-26-000528 | 1 | Crossroads | CR-S04-06 | Meter exchange | P4 planned | 2026-01-15 | 2026-01-24 | 2026-01-25 | Meter technician |  | 78.34 | Completed | No
WO-26-000529 | 1.4 | Crossroads | CR-S05-02 | Meter exchange | P4 planned | 2026-01-15 | 2026-02-22 | 2026-02-22 | Meter technician |  | 167.78 | Completed | No
WO-26-000530 | 1.5 | Crossroads | CR-S24-01 | Meter exchange | P4 planned | 2026-01-15 | 2026-02-19 | 2026-02-19 | Meter technician |  | 115.73 | Completed | No
WO-26-000531 | 3 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-01-15 | 2026-02-28 | 2026-02-28 | Internal line |  | 68.6 | Completed | No
WO-26-000532 | 3.2 | Crossroads | CR-S07-05 | Preventive maintenance | P4 planned | 2026-01-15 | 2026-03-16 | 2026-03-20 | Underground crew |  | 469.71 | Completed | No
WO-26-000533 | 0.6 | Crossroads | CR-S28-04 | Service order - field | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Meter technician |  | 20.42 | Completed | No
WO-26-000534 | 1.2 | Crossroads | CR-S14-05 | Service order - field | P3 within 10 days | 2026-01-15 | 2026-01-19 | 2026-01-21 | Meter technician |  | 27.86 | Completed | No
WO-26-000535 | 1 | Crossroads | CR-S15-01 | Service order - field | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Meter technician |  | 8.97 | Completed | No
WO-26-000536 | 0.9 | Crossroads | CR-S07-07 | Service order - field | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Meter technician |  | 28.8 | Completed | No
WO-26-000537 | 1.9 | Crossroads | CR-S03-01 | Service order - field | P3 within 10 days | 2026-01-15 | 2026-01-24 | 2026-01-26 | Meter technician |  | 21 | Completed | No
WO-26-000538 | 1.3 | Crossroads | CR-S22-04 | Service order - field | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Meter technician |  | 9.06 | Completed | No
WO-26-000539 | 13 | Crossroads | CR-S24-03 | Transformer replacement | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Contract line | CT-02 | 3637.74 | Completed | No
WO-26-000540 | 9.2 | Crossroads | CR-S15-03 | Transformer replacement | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Internal line |  | 5593.19 | Completed | No
WO-26-000541 | 3.7 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 226.45 | Completed | No
WO-26-000542 | 3.5 | Crossroads | CR-S24-02 | Trouble - no power | P1 emergency | 2026-01-15 | 2026-01-15 | 2026-01-15 | Internal line |  | 40.29 | Completed | No
WO-26-000543 | 2.3 | Crossroads | CR-S18-02 | Trouble - no power | P1 emergency | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 72.7 | Completed | No
WO-26-000544 | 2.9 | Crossroads | CR-S18-05 | Trouble - no power | P2 same day | 2026-01-15 | 2026-01-16 | 2026-01-16 | Troubleman |  | 115.34 | Completed | No
WO-26-000545 | 3 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 204.42 | Completed | No
WO-26-000546 | 3.5 | Crossroads | CR-S17-03 | Trouble - no power | P1 emergency | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 238.75 | Completed | No
WO-26-000547 | 2.2 | Crossroads | CR-S16-01 | Trouble - partial or voltage | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 197.45 | Completed | No
WO-26-000548 | 1.8 | Crossroads | CR-S18-04 | Trouble - partial or voltage | P2 same day | 2026-01-15 | 2026-01-15 | 2026-01-15 | Troubleman |  | 57.38 | Completed | No
WO-26-000549 | 3.4 | Crossroads | CR-S20-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-15 | 2026-01-23 | 2026-01-23 | Troubleman |  | 118.62 | Completed | No
WO-26-000550 | 11.9 | Bayou | BY-S28-02 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-22 | 2026-01-23 | Contract line | CT-03 | 196.26 | Completed | No
WO-26-000551 | 4.8 | Bayou | BY-S25-03 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-18 | 2026-01-18 | Internal line |  | 1998.22 | Completed | No
WO-26-000552 | 11.9 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-20 | 2026-01-20 | Internal line |  | 2221.05 | Completed | No
WO-26-000553 | 8.5 | Bayou | BY-S09-04 | Corrective maintenance | P4 planned | 2026-01-16 | 2026-02-26 | 2026-03-06 | Underground crew |  | 298.36 | Completed | No
WO-26-000554 | 10.7 | Bayou | BY-S17-04 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-24 | 2026-01-24 | Contract line | CT-03 | 1130.63 | Completed | No
WO-26-000555 | 4.8 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-19 | 2026-01-20 | Internal line |  | 1448.28 | Completed | No
WO-26-000556 | 3.1 | Bayou | BY-S22-04 | Corrective maintenance | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Underground crew |  | 2119.86 | Completed | No
WO-26-000557 | 1.2 | Bayou | BY-S15-05 | Meter exchange | P3 within 10 days | 2026-01-16 | 2026-01-21 | 2026-01-21 | Meter technician |  | 126.74 | Completed | No
WO-26-000558 | 0.8 | Bayou | BY-S18-03 | Meter exchange | P3 within 10 days | 2026-01-16 | 2026-01-21 | 2026-01-21 | Meter technician |  | 73.54 | Completed | No
WO-26-000559 | 19.3 | Bayou | BY-S08-03 | Pole replacement | P3 within 10 days | 2026-01-16 | 2026-01-20 | 2026-01-20 | Contract line | CT-04 | 2061.27 | Completed | No
WO-26-000560 | 4.3 | Bayou | BY-S10-01 | Preventive maintenance | P4 planned | 2026-01-16 | 2026-03-07 | 2026-03-07 | Internal line |  | 303.7 | Completed | No
WO-26-000561 | 6.7 | Bayou | BY-S03-02 | Preventive maintenance | P4 planned | 2026-01-16 | 2026-03-13 | 2026-03-13 | Contract line | CT-04 | 89.08 | Completed | No
WO-26-000562 | 8 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-01-16 | 2026-02-01 | 2026-02-01 | Internal line |  | 180.31 | Completed | No
WO-26-000563 | 0.8 | Bayou | BY-S09-04 | Service order - field | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Meter technician |  | 22.7 | Completed | No
WO-26-000564 | 0.9 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-22 | 2026-01-23 | Meter technician |  | 3.32 | Completed | No
WO-26-000565 | 0.6 | Bayou | BY-S09-02 | Service order - field | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Meter technician |  | 37.77 | Completed | No
WO-26-000566 | 1.4 | Bayou | BY-S22-03 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-19 | 2026-01-20 | Meter technician |  | 34.17 | Completed | No
WO-26-000567 | 10.7 | Bayou | BY-S13-05 | Transformer replacement | P3 within 10 days | 2026-01-16 | 2026-01-18 | 2026-01-19 | Internal line |  | 7482.04 | Completed | No
WO-26-000568 | 3.9 | Bayou | BY-S16-01 | Trouble - no power | P1 emergency | 2026-01-16 | 2026-01-16 | 2026-01-16 | Troubleman |  | 191.13 | Completed | No
WO-26-000569 | 4.5 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-01-16 | 2026-01-16 | 2026-01-16 | Troubleman |  | 243.89 | Completed | No
WO-26-000570 | 2.9 | Bayou | BY-S05-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-16 | 2026-01-24 | 2026-01-24 | Troubleman |  | 130.6 | Completed | No
WO-26-000571 | 7.2 | Crossroads | CR-S14-05 | Corrective maintenance | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Underground crew |  | 947.31 | Completed | No
WO-26-000572 | 11.2 | Crossroads | CR-S21-02 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-17 | 2026-01-17 | Underground crew |  | 967.63 | Completed | No
WO-26-000573 | 10.7 | Crossroads | CR-S28-03 | Corrective maintenance | P3 within 10 days | 2026-01-16 | 2026-01-19 | 2026-01-19 | Contract line | CT-02 | 1991.63 | Completed | No
WO-26-000574 | 1 | Crossroads | CR-S32-05 | Meter exchange | P3 within 10 days | 2026-01-16 | 2026-01-17 | 2026-01-17 | Meter technician |  | 98.31 | Completed | No
WO-26-000575 | 0.5 | Crossroads | CR-S14-06 | Meter exchange | P4 planned | 2026-01-16 | 2026-02-12 | 2026-02-13 | Meter technician |  | 70.83 | Completed | No
WO-26-000576 | 0.5 | Crossroads | CR-S02-03 | Meter exchange | P4 planned | 2026-01-16 | 2026-02-06 | 2026-02-10 | Meter technician |  | 166.67 | Completed | No
WO-26-000577 | 1.3 | Crossroads | CR-S16-04 | Meter exchange | P3 within 10 days | 2026-01-16 | 2026-01-18 | 2026-01-18 | Meter technician |  | 72.7 | Completed | No
WO-26-000578 | 9.4 | Crossroads | CR-S27-04 | New service - small | P4 planned | 2026-01-16 | 2026-02-16 | 2026-02-16 | Contract line | CT-01 | 359.64 | Completed | No
WO-26-000579 | 9.9 | Crossroads | CR-S13-06 | New service - small | P4 planned | 2026-01-16 | 2026-02-04 | 2026-02-04 | Contract line | CT-02 | 1808.65 | Completed | No
WO-26-000580 | 4.4 | Crossroads | CR-S24-03 | Preventive maintenance | P4 planned | 2026-01-16 | 2026-03-10 | 2026-03-10 | Internal line |  | 578.87 | Completed | No
WO-26-000581 | 3.8 | Crossroads | CR-S07-06 | Preventive maintenance | P4 planned | 2026-01-16 | 2026-01-28 | 2026-01-28 | Internal line |  | 95.57 | Completed | No
WO-26-000582 | 3.8 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-01-16 | 2026-03-10 | 2026-03-10 | Underground crew |  | 430.15 | Completed | No
WO-26-000583 | 1.9 | Crossroads | CR-S07-04 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-22 | 2026-01-22 | Meter technician |  | 8.43 | Completed | No
WO-26-000584 | 1.4 | Crossroads | CR-S25-03 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-20 | 2026-01-20 | Meter technician |  | 16.38 | Completed | No
WO-26-000585 | 1.5 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-19 | 2026-01-19 | Meter technician |  | 23.5 | Completed | No
WO-26-000586 |  | Crossroads | CR-S18-03 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-23 |  | Meter technician |  |  | Cancelled | No
WO-26-000587 | 1.5 | Crossroads | CR-S18-05 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-26 | 2026-01-26 | Meter technician |  | 17.28 | Completed | No
WO-26-000588 | 1.8 | Crossroads | CR-S05-02 | Service order - field | P3 within 10 days | 2026-01-16 | 2026-01-26 | 2026-01-27 | Meter technician |  | 29.1 | Completed | No
WO-26-000589 | 2.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-16 | 2026-01-20 | 2026-01-20 | Contract line | CT-01 | 205.51 | Completed | No
WO-26-000590 | 10.3 | Crossroads | CR-S19-03 | Transformer replacement | P3 within 10 days | 2026-01-16 | 2026-01-22 | 2026-01-26 | Internal line |  | 4747.3 | Completed | No
WO-26-000591 | 7.6 | Crossroads | CR-S20-02 | Transformer replacement | P3 within 10 days | 2026-01-16 | 2026-01-24 | 2026-01-24 | Internal line |  | 8586.29 | Completed | No
WO-26-000592 | 4.7 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Troubleman |  | 268.95 | Completed | No
WO-26-000593 | 2.1 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-01-16 | 2026-01-16 | 2026-01-16 | Troubleman |  | 107.53 | Completed | No
WO-26-000594 | 2.4 | Crossroads | CR-S10-03 | Trouble - no power | P2 same day | 2026-01-16 | 2026-01-16 | 2026-01-16 | Troubleman |  | 205.3 | Completed | No
WO-26-000595 | 2.7 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-01-16 | 2026-01-16 | 2026-01-16 | Troubleman |  | 250.58 | Completed | No
WO-26-000596 | 2.1 | Crossroads | CR-S16-06 | Trouble - partial or voltage | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Troubleman |  | 183.49 | Completed | No
WO-26-000597 | 4.5 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P2 same day | 2026-01-16 | 2026-01-17 | 2026-01-17 | Internal line |  | 249.7 | Completed | No
WO-26-000598 | 3.7 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P2 same day | 2026-01-16 | 2026-01-16 | 2026-01-16 | Troubleman |  | 125.2 | Completed | No
WO-26-000599 | 1.4 | Bayou | BY-S09-05 | Service order - field | P2 same day | 2026-01-17 | 2026-01-18 | 2026-01-18 | Meter technician |  | 17.01 | Completed | No
WO-26-000600 | 9 | Bayou | BY-S29-05 | Transformer replacement | P1 emergency | 2026-01-17 | 2026-01-17 | 2026-01-17 | Contract line | CT-03 | 3762.45 | Completed | No
WO-26-000601 | 7.8 | Bayou | BY-S13-05 | Transformer replacement | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Internal line |  | 10021.63 | Completed | No
WO-26-000602 | 6.3 | Bayou | BY-S16-03 | Transformer replacement | P2 same day | 2026-01-17 | 2026-01-18 | 2026-01-18 | Internal line |  | 5885.33 | Completed | No
WO-26-000603 | 3.2 | Bayou | BY-S25-02 | Trouble - no power | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Troubleman |  | 339.09 | Completed | No
WO-26-000604 | 3.9 | Bayou | BY-S25-03 | Trouble - no power | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Troubleman |  | 17.66 | Completed | No
WO-26-000605 | 2.9 | Bayou | BY-S26-01 | Trouble - no power | P1 emergency | 2026-01-17 | 2026-01-17 | 2026-01-17 | Troubleman |  | 339.41 | Completed | No
WO-26-000606 | 4.7 | Bayou | BY-S02-01 | Trouble - partial or voltage | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Internal line |  | 104.46 | Completed | No
WO-26-000607 | 4.6 | Bayou | BY-S26-03 | Trouble - partial or voltage | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Internal line |  | 102.38 | Completed | No
WO-26-000608 | 0.6 | Crossroads | CR-S04-02 | Service order - field | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Meter technician |  | 11.13 | Completed | No
WO-26-000609 | 1.6 | Crossroads | CR-S27-03 | Service order - field | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Meter technician |  | 1.79 | Completed | No
WO-26-000610 | 1.1 | Crossroads | CR-S02-02 | Service order - field | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Meter technician |  | 24.08 | Completed | No
WO-26-000611 | 8.1 | Crossroads | CR-S16-04 | Transformer replacement | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Internal line |  | 8687.51 | Completed | No
WO-26-000612 | 4.6 | Crossroads | CR-S07-02 | Trouble - no power | P1 emergency | 2026-01-17 | 2026-01-17 | 2026-01-17 | Troubleman |  | 118.7 | Completed | No
WO-26-000613 | 3.8 | Crossroads | CR-S30-01 | Trouble - no power | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Troubleman |  | 35.48 | Completed | No
WO-26-000614 | 5.4 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-01-17 | 2026-01-17 | 2026-01-17 | Internal line |  | 187.46 | Completed | No
WO-26-000615 | 1.5 | Crossroads | CR-S20-03 | Trouble - partial or voltage | P2 same day | 2026-01-17 | 2026-01-17 | 2026-01-17 | Troubleman |  | 8.87 | Completed | No
WO-26-000616 | 1.9 | Crossroads | CR-S16-04 | Trouble - partial or voltage | P2 same day | 2026-01-17 | 2026-01-18 | 2026-01-18 | Troubleman |  | 210.41 | Completed | No
WO-26-000617 | 1.7 | Bayou | BY-S16-03 | Service order - field | P2 same day | 2026-01-18 | 2026-01-19 | 2026-01-19 | Meter technician |  | 17.12 | Completed | No
WO-26-000618 | 1.4 | Bayou | BY-S17-03 | Service order - field | P2 same day | 2026-01-18 | 2026-01-18 | 2026-01-18 | Meter technician |  | 1.25 | Completed | No
WO-26-000619 | 5.7 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-01-18 | 2026-01-18 | 2026-01-18 | Troubleman |  | 5.91 | Completed | No
WO-26-000620 | 5.6 | Bayou | BY-S16-04 | Trouble - no power | P1 emergency | 2026-01-18 | 2026-01-18 | 2026-01-18 | Troubleman |  | 68.8 | Completed | No
WO-26-000621 | 4.8 | Bayou | BY-S01-01 | Trouble - partial or voltage | P2 same day | 2026-01-18 | 2026-01-18 | 2026-01-18 | Troubleman |  | 233.95 | Completed | No
WO-26-000622 | 2.9 | Bayou | BY-S26-02 | Trouble - partial or voltage | P2 same day | 2026-01-18 | 2026-01-18 | 2026-01-18 | Troubleman |  | 32.21 | Completed | No
WO-26-000623 | 1.9 | Crossroads | CR-S02-01 | Service order - field | P2 same day | 2026-01-18 | 2026-01-19 | 2026-01-19 | Meter technician |  | 12.28 | Completed | No
WO-26-000624 | 1.1 | Crossroads | CR-S02-04 | Service order - field | P2 same day | 2026-01-18 | 2026-01-19 | 2026-01-19 | Meter technician |  | 9.75 | Completed | No
WO-26-000625 | 12.7 | Crossroads | CR-S21-01 | Transformer replacement | P2 same day | 2026-01-18 | 2026-01-19 | 2026-01-19 | Internal line |  | 4083.77 | Completed | No
WO-26-000626 | 6.5 | Crossroads | CR-S03-02 | Transformer replacement | P1 emergency | 2026-01-18 | 2026-01-18 | 2026-01-18 | Contract line | CT-01 | 7302.11 | Completed | No
WO-26-000627 | 4.9 | Crossroads | CR-S20-03 | Trouble - no power | P1 emergency | 2026-01-18 | 2026-01-18 | 2026-01-18 | Troubleman |  | 32.81 | Completed | No
WO-26-000628 | 4.5 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-01-18 | 2026-01-18 | 2026-01-18 | Troubleman |  | 141.78 | Completed | No
WO-26-000629 | 4.9 | Crossroads | CR-S21-03 | Trouble - partial or voltage | P2 same day | 2026-01-18 | 2026-01-19 | 2026-01-19 | Troubleman |  | 75.8 | Completed | No
WO-26-000630 | 6.6 | Bayou | BY-S25-01 | Corrective maintenance | P3 within 10 days | 2026-01-19 | 2026-01-22 | 2026-01-22 | Internal line |  | 897.32 | Completed | No
WO-26-000631 | 0.7 | Bayou | BY-S17-01 | Meter exchange | P4 planned | 2026-01-19 | 2026-02-22 | 2026-02-22 | Meter technician |  | 105.83 | Completed | No
WO-26-000632 | 1.3 | Bayou | BY-S08-01 | Meter exchange | P3 within 10 days | 2026-01-19 | 2026-01-23 | 2026-01-31 | Meter technician |  | 114.57 | Completed | No
WO-26-000633 | 13.7 | Bayou | BY-S23-04 | Pole replacement | P2 same day | 2026-01-19 | 2026-01-20 | 2026-01-20 | Contract line | CT-04 | 2042.24 | Completed | No
WO-26-000634 | 16.2 | Bayou | BY-S07-01 | Pole replacement | P4 planned | 2026-01-19 | 2026-01-28 | 2026-02-01 | Contract line | CT-03 | 1269.08 | Completed | No
WO-26-000635 | 4.6 | Bayou | BY-S30-02 | Preventive maintenance | P4 planned | 2026-01-19 | 2026-03-10 | 2026-03-12 | Underground crew |  | 4.59 | Completed | No
WO-26-000636 | 3.7 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-01-19 | 2026-02-08 | 2026-02-10 | Contract line | CT-04 | 336.03 | Completed | No
WO-26-000637 | 2.9 | Bayou | BY-S28-03 | Preventive maintenance | P4 planned | 2026-01-19 | 2026-03-07 | 2026-03-08 | Internal line |  | 377.64 | Completed | No
WO-26-000638 | 2.6 | Bayou | BY-S07-06 | Preventive maintenance | P4 planned | 2026-01-19 | 2026-03-16 | 2026-03-20 | Internal line |  | 331.64 | Completed | No
WO-26-000639 | 1.8 | Bayou | BY-S11-02 | Service order - field | P3 within 10 days | 2026-01-19 | 2026-01-27 | 2026-01-28 | Meter technician |  | 26.85 | Completed | No
WO-26-000640 | 1.1 | Bayou | BY-S06-01 | Service order - field | P3 within 10 days | 2026-01-19 | 2026-01-25 | 2026-01-29 | Meter technician |  | 11.24 | Completed | No
WO-26-000641 | 2 | Bayou | BY-S24-04 | Service order - field | P2 same day | 2026-01-19 | 2026-01-19 | 2026-01-19 | Meter technician |  | 10.58 | Completed | No
WO-26-000642 | 0.8 | Bayou | BY-S26-01 | Service order - field | P2 same day | 2026-01-19 | 2026-01-20 | 2026-01-20 | Meter technician |  | 11.18 | Completed | No
WO-26-000643 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-19 | 2026-01-21 | 2026-01-22 | Contract line | CT-03 | 309.71 | Completed | No
WO-26-000644 | 1.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-19 | 2026-01-25 | 2026-01-25 | Internal line |  | 193.28 | Completed | No
WO-26-000645 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-19 | 2026-01-26 | 2026-01-28 | Internal line |  | 358.67 | Completed | No
WO-26-000646 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-19 | 2026-01-25 | 2026-01-26 | Contract line | CT-03 | 329.98 | Completed | No
WO-26-000647 | 6.4 | Bayou | BY-S29-01 | Transformer replacement | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Internal line |  | 2941.09 | Completed | No
WO-26-000648 | 5.2 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-01-19 | 2026-01-19 | 2026-01-19 | Internal line |  | 343.94 | Completed | No
WO-26-000649 | 3.5 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 298.34 | Completed | No
WO-26-000650 | 4.3 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 212.85 | Completed | No
WO-26-000651 | 3.6 | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 56.38 | Completed | No
WO-26-000652 | 2.3 | Bayou | BY-S15-06 | Trouble - partial or voltage | P2 same day | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 166.62 | Completed | No
WO-26-000653 | 10.2 | Crossroads | CR-S32-03 | Corrective maintenance | P3 within 10 days | 2026-01-19 | 2026-01-29 | 2026-02-06 | Internal line |  | 752.86 | Completed | No
WO-26-000654 | 9 | Crossroads | CR-S02-04 | Corrective maintenance | P3 within 10 days | 2026-01-19 | 2026-01-25 | 2026-01-26 | Internal line |  | 894.21 | Completed | No
WO-26-000655 | 6.9 | Crossroads | CR-S10-01 | Corrective maintenance | P4 planned | 2026-01-19 | 2026-02-21 | 2026-02-22 | Underground crew |  | 165 | Completed | No
WO-26-000656 | 8.9 | Crossroads | CR-S15-03 | Corrective maintenance | P2 same day | 2026-01-19 | 2026-01-19 | 2026-01-19 | Underground crew |  | 1453.36 | Completed | No
WO-26-000657 | 8.9 | Crossroads | CR-S17-01 | Corrective maintenance | P3 within 10 days | 2026-01-19 | 2026-01-22 | 2026-01-26 | Underground crew |  | 2185.18 | Completed | No
WO-26-000658 | 1.2 | Crossroads | CR-S20-02 | Meter exchange | P4 planned | 2026-01-19 | 2026-02-13 | 2026-02-15 | Meter technician |  | 76.11 | Completed | No
WO-26-000659 | 1.3 | Crossroads | CR-S14-03 | Meter exchange | P4 planned | 2026-01-19 | 2026-02-22 | 2026-02-22 | Meter technician |  | 120.64 | Completed | No
WO-26-000660 | 1.1 | Crossroads | CR-S12-02 | Meter exchange | P3 within 10 days | 2026-01-19 | 2026-01-23 | 2026-01-23 | Meter technician |  | 86.14 | Completed | No
WO-26-000661 | 0.7 | Crossroads | CR-S27-04 | Meter exchange | P4 planned | 2026-01-19 | 2026-02-19 | 2026-02-19 | Meter technician |  | 113.78 | Completed | No
WO-26-000662 | 7.3 | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-01-19 | 2026-03-17 | 2026-03-19 | Contract line | CT-02 | 43.46 | Completed | No
WO-26-000663 | 5.4 | Crossroads | CR-S30-01 | Preventive maintenance | P4 planned | 2026-01-19 | 2026-02-24 | 2026-02-24 | Underground crew |  | 460.88 | Completed | No
WO-26-000664 | 1.2 | Crossroads | CR-S25-05 | Service order - field | P3 within 10 days | 2026-01-19 | 2026-01-20 | 2026-01-20 | Meter technician |  | 39.06 | Completed | No
WO-26-000665 | 1.7 | Crossroads | CR-S04-01 | Service order - field | P2 same day | 2026-01-19 | 2026-01-20 | 2026-01-20 | Meter technician |  | 28.47 | Completed | No
WO-26-000666 | 8.7 | Crossroads | CR-S30-06 | Transformer replacement | P3 within 10 days | 2026-01-19 | 2026-01-26 | 2026-01-26 | Contract line | CT-02 | 9578.74 | Completed | No
WO-26-000667 | 10.8 | Crossroads | CR-S22-03 | Transformer replacement | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Contract line | CT-02 | 6876.01 | Completed | No
WO-26-000668 | 5.3 | Crossroads | CR-S03-02 | Trouble - no power | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 129.6 | Completed | No
WO-26-000669 | 4 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 140.66 | Completed | No
WO-26-000670 | 5.9 | Crossroads | CR-S20-01 | Trouble - no power | P1 emergency | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 173.6 | Completed | No
WO-26-000671 | 3.1 | Crossroads | CR-S16-03 | Trouble - no power | P2 same day | 2026-01-19 | 2026-01-19 | 2026-01-19 | Troubleman |  | 110.63 | Completed | No
WO-26-000672 | 10.9 | Bayou | BY-S12-03 | Corrective maintenance | P3 within 10 days | 2026-01-20 | 2026-01-25 | 2026-01-26 | Underground crew |  | 1596.71 | Completed | No
WO-26-000673 | 9.8 | Bayou | BY-S17-02 | Corrective maintenance | P2 same day | 2026-01-20 | 2026-01-21 | 2026-01-21 | Underground crew |  | 1011.76 | Completed | No
WO-26-000674 | 10.3 | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-01-20 | 2026-01-21 | 2026-01-21 | Contract line | CT-04 | 2135.43 | Completed | No
WO-26-000675 | 9.3 | Bayou | BY-S05-02 | New service - small | P4 planned | 2026-01-20 | 2026-02-01 | 2026-02-03 | Internal line |  | 2125.96 | Completed | No
WO-26-000676 | 4.7 | Bayou | BY-S19-04 | New service - small | P4 planned | 2026-01-20 | 2026-03-16 | 2026-03-16 | Underground crew |  | 1547.11 | Completed | No
WO-26-000677 | 18.1 | Bayou | BY-S20-01 | Pole replacement | P3 within 10 days | 2026-01-20 | 2026-01-28 | 2026-01-30 | Contract line | CT-03 | 1260.29 | Completed | No
WO-26-000678 | 10.1 | Bayou | BY-S26-02 | Pole replacement | P4 planned | 2026-01-20 | 2026-02-26 | 2026-02-26 | Internal line |  | 2040.92 | Completed | No
WO-26-000679 | 1.8 | Bayou | BY-S29-02 | Service order - field | P3 within 10 days | 2026-01-20 | 2026-01-29 | 2026-02-02 | Meter technician |  | 24.31 | Completed | No
WO-26-000680 | 1 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-01-20 | 2026-01-20 | 2026-01-20 | Meter technician |  | 19.03 | Completed | No
WO-26-000681 | 1.3 | Bayou | BY-S05-03 | Service order - field | P3 within 10 days | 2026-01-20 | 2026-01-30 | 2026-01-31 | Meter technician |  | 7.92 | Completed | No
WO-26-000682 | 1.9 | Bayou | BY-S24-05 | Service order - field | P2 same day | 2026-01-20 | 2026-01-21 | 2026-01-21 | Meter technician |  | 39.53 | Completed | No
WO-26-000683 | 12.9 | Bayou | BY-S28-02 | Transformer replacement | P2 same day | 2026-01-20 | 2026-01-20 | 2026-01-20 | Internal line |  | 10471.55 | Completed | No
WO-26-000684 | 3.8 | Bayou | BY-S26-06 | Trouble - no power | P1 emergency | 2026-01-20 | 2026-01-20 | 2026-01-20 | Troubleman |  | 288.37 | Completed | No
WO-26-000685 | 2.8 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-01-20 | 2026-01-20 | 2026-01-20 | Internal line |  | 100.4 | Completed | No
WO-26-000686 | 5.6 | Bayou | BY-S23-03 | Trouble - no power | P2 same day | 2026-01-20 | 2026-01-20 | 2026-01-20 | Troubleman |  | 208.76 | Completed | No
WO-26-000687 | 4 | Bayou | BY-S28-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-20 | 2026-01-22 | 2026-01-22 | Troubleman |  | 178.31 | Completed | No
WO-26-000688 | 4.1 | Bayou | BY-S19-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-20 | 2026-01-27 | 2026-01-27 | Troubleman |  | 38.55 | Completed | No
WO-26-000689 | 2.6 | Bayou | BY-S21-04 | Trouble - partial or voltage | P3 within 10 days | 2026-01-20 | 2026-01-27 | 2026-01-27 | Troubleman |  | 136.53 | Completed | No
WO-26-000690 | 4.1 | Bayou | BY-S15-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-20 | 2026-01-29 | 2026-01-29 | Troubleman |  | 108.19 | Completed | No
WO-26-000691 | 2.6 | Bayou | BY-S25-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-20 | 2026-01-29 | 2026-01-29 | Troubleman |  | 199.23 | Completed | No
WO-26-000692 | 1.9 | Bayou | BY-S25-03 | Trouble - partial or voltage | P2 same day | 2026-01-20 | 2026-01-20 | 2026-01-20 | Troubleman |  | 90.24 | Completed | No
WO-26-000693 | 10.3 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-01-20 | 2026-01-30 | 2026-01-31 | Internal line |  | 1984.97 | Completed | No
WO-26-000694 | 0.6 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-01-20 | 2026-01-30 | 2026-02-03 | Meter technician |  | 108.74 | Completed | No
WO-26-000695 | 1 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-01-20 | 2026-01-28 | 2026-01-28 | Meter technician |  | 143.7 | Completed | No
WO-26-000696 | 11.8 | Crossroads | CR-S28-03 | New service - small | P4 planned | 2026-01-20 | 2026-02-03 | 2026-02-04 | Contract line | CT-01 | 2519.03 | Completed | No
WO-26-000697 | 20.3 | Crossroads | CR-S14-03 | Pole replacement | P3 within 10 days | 2026-01-20 | 2026-01-29 | 2026-01-29 | Contract line | CT-01 | 2161.26 | Completed | No
WO-26-000698 | 11.5 | Crossroads | CR-S28-01 | Pole replacement | P3 within 10 days | 2026-01-20 | 2026-01-23 | 2026-01-27 | Contract line | CT-01 | 3310.49 | Completed | No
WO-26-000699 | 4.4 | Crossroads | CR-S07-01 | Preventive maintenance | P4 planned | 2026-01-20 | 2026-02-10 | 2026-02-12 | Underground crew |  | 122.23 | Completed | No
WO-26-000700 | 7.5 | Crossroads | CR-S02-05 | Preventive maintenance | P4 planned | 2026-01-20 | 2026-03-17 | 2026-03-17 | Underground crew |  | 489.4 | Completed | No
WO-26-000701 | 1.5 | Crossroads | CR-S32-01 | Service order - field | P2 same day | 2026-01-20 | 2026-01-20 | 2026-01-20 | Meter technician |  | 27.47 | Completed | No
WO-26-000702 | 1.9 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-01-20 | 2026-01-21 | 2026-01-23 | Meter technician |  | 18.06 | Completed | No
WO-26-000703 | 1.5 | Crossroads | CR-S31-02 | Service order - field | P3 within 10 days | 2026-01-20 | 2026-01-24 | 2026-01-24 | Meter technician |  | 2.64 | Completed | No
WO-26-000704 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-20 | 2026-01-21 | 2026-01-22 | Contract line | CT-01 | 426.01 | Completed | No
WO-26-000705 | 4.5 | Crossroads | CR-S30-01 | Trouble - no power | P2 same day | 2026-01-20 | 2026-01-20 | 2026-01-20 | Troubleman |  | 37.32 | Completed | No
WO-26-000706 | 4.5 | Crossroads | CR-S19-02 | Trouble - partial or voltage | P2 same day | 2026-01-20 | 2026-01-21 | 2026-01-21 | Troubleman |  | 154.43 | Completed | No
WO-26-000707 | 3.4 | Crossroads | CR-S24-04 | Trouble - partial or voltage | P3 within 10 days | 2026-01-20 | 2026-01-30 | 2026-01-30 | Troubleman |  | 167.05 | Completed | No
WO-26-000708 | 10.2 | Bayou | BY-S21-04 | Corrective maintenance | P3 within 10 days | 2026-01-21 | 2026-01-23 | 2026-01-24 | Contract line | CT-03 | 1384.72 | Completed | No
WO-26-000709 | 7.9 | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-01-21 | 2026-01-28 | 2026-02-01 | Contract line | CT-04 | 1492.36 | Completed | No
WO-26-000710 | 0.6 | Bayou | BY-S12-03 | Meter exchange | P3 within 10 days | 2026-01-21 | 2026-01-22 | 2026-01-23 | Meter technician |  | 166.92 | Completed | No
WO-26-000711 | 1 | Bayou | BY-S13-06 | Meter exchange | P3 within 10 days | 2026-01-21 | 2026-01-31 | 2026-01-31 | Meter technician |  | 155.52 | Completed | No
WO-26-000712 | 10.3 | Bayou | BY-S30-01 | New service - small | P4 planned | 2026-01-21 | 2026-02-09 | 2026-02-13 | Underground crew |  | 2403.35 | Completed | No
WO-26-000713 | 11.1 | Bayou | BY-S15-06 | New service - small | P3 within 10 days | 2026-01-21 | 2026-01-27 | 2026-01-29 | Contract line | CT-04 | 978.92 | Completed | No
WO-26-000714 | 14.2 | Bayou | BY-S07-03 | Pole replacement | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Contract line | CT-03 | 2226.62 | Completed | No
WO-26-000715 | 10.9 | Bayou | BY-S10-05 | Pole replacement | P3 within 10 days | 2026-01-21 | 2026-01-23 | 2026-01-25 | Contract line | CT-04 | 3224.36 | Completed | No
WO-26-000716 | 2.6 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-01-21 | 2026-03-22 | 2026-03-26 | Internal line |  | 280.49 | Completed | No
WO-26-000717 | 4.9 | Bayou | BY-S10-01 | Preventive maintenance | P4 planned | 2026-01-21 | 2026-03-14 | 2026-03-16 | Contract line | CT-03 | 301.63 | Completed | No
WO-26-000718 | 1.4 | Bayou | BY-S18-01 | Service order - field | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Meter technician |  | 39.63 | Completed | No
WO-26-000719 | 0.6 | Bayou | BY-S12-03 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-25 | 2026-02-02 | Meter technician |  | 0.64 | Completed | No
WO-26-000720 | 1.4 | Bayou | BY-S24-01 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-27 | 2026-01-27 | Meter technician |  | 34.63 | Completed | No
WO-26-000721 | 1.1 | Bayou | BY-S06-02 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-28 | 2026-01-30 | Meter technician |  | 3.78 | Completed | No
WO-26-000722 | 1.6 | Bayou | BY-S19-03 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-29 | 2026-01-29 | Meter technician |  | 35.35 | Completed | No
WO-26-000723 | 5.4 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-01-21 | 2026-01-21 | 2026-01-21 | Troubleman |  | 273.21 | Completed | No
WO-26-000724 | 4.9 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-01-21 | 2026-01-21 | 2026-01-21 | Internal line |  | 101.83 | Completed | No
WO-26-000725 | 4.9 | Bayou | BY-S14-01 | Trouble - partial or voltage | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Troubleman |  | 126.12 | Completed | No
WO-26-000726 | 3.1 | Bayou | BY-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-21 | 2026-01-30 | 2026-02-03 | Troubleman |  | 236.24 | Completed | No
WO-26-000727 | 3.4 | Bayou | BY-S16-04 | Trouble - partial or voltage | P2 same day | 2026-01-21 | 2026-01-21 | 2026-01-21 | Troubleman |  | 139.4 | Completed | No
WO-26-000728 | 4.1 | Bayou | BY-S15-02 | Trouble - partial or voltage | P2 same day | 2026-01-21 | 2026-01-21 | 2026-01-21 | Troubleman |  | 149.83 | Completed | No
WO-26-000729 | 6.7 | Crossroads | CR-S01-01 | Corrective maintenance | P3 within 10 days | 2026-01-21 | 2026-01-30 | 2026-01-30 | Underground crew |  | 1900.15 | Completed | No
WO-26-000730 | 4.4 | Crossroads | CR-S22-04 | Corrective maintenance | P3 within 10 days | 2026-01-21 | 2026-01-27 | 2026-01-28 | Underground crew |  | 258.07 | Completed | No
WO-26-000731 | 4.6 | Crossroads | CR-S11-01 | Corrective maintenance | P2 same day | 2026-01-21 | 2026-01-21 | 2026-01-21 | Internal line |  | 2179.35 | Completed | No
WO-26-000732 | 11 | Crossroads | CR-S15-03 | Corrective maintenance | P3 within 10 days | 2026-01-21 | 2026-01-29 | 2026-02-06 | Underground crew |  | 824.67 | Completed | No
WO-26-000733 | 0.5 | Crossroads | CR-S21-01 | Meter exchange | P4 planned | 2026-01-21 | 2026-03-11 | 2026-03-11 | Meter technician |  | 81.63 | Completed | No
WO-26-000734 | 5.3 | Crossroads | CR-S23-03 | New service - small | P3 within 10 days | 2026-01-21 | 2026-01-25 | 2026-01-29 | Contract line | CT-02 | 3805.21 | Completed | No
WO-26-000735 | 21.3 | Crossroads | CR-S28-02 | Pole replacement | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Contract line | CT-02 | 2088.04 | Completed | No
WO-26-000736 | 6.4 | Crossroads | CR-S15-02 | Preventive maintenance | P4 planned | 2026-01-21 | 2026-03-07 | 2026-03-07 | Underground crew |  | 479.76 | Completed | No
WO-26-000737 | 3.5 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-01-21 | 2026-02-04 | 2026-02-04 | Underground crew |  | 112.71 | Completed | No
WO-26-000738 | 5.6 | Crossroads | CR-S24-02 | Preventive maintenance | P4 planned | 2026-01-21 | 2026-01-29 | 2026-01-29 | Internal line |  | 306.73 | Completed | No
WO-26-000739 | 2.8 | Crossroads | CR-S23-05 | Preventive maintenance | P4 planned | 2026-01-21 | 2026-02-21 | 2026-02-21 | Internal line |  | 280.98 | Completed | No
WO-26-000740 | 1.2 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-28 | 2026-02-01 | Meter technician |  | 21.68 | Completed | No
WO-26-000741 | 0.7 | Crossroads | CR-S30-06 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-22 | 2026-01-23 | Meter technician |  | 13.21 | Completed | No
WO-26-000742 | 1.8 | Crossroads | CR-S13-03 | Service order - field | P2 same day | 2026-01-21 | 2026-01-21 | 2026-01-21 | Meter technician |  | 13.04 | Completed | No
WO-26-000743 | 0.9 | Crossroads | CR-S18-01 | Service order - field | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Meter technician |  | 39.95 | Completed | No
WO-26-000744 | 0.7 | Crossroads | CR-S21-01 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-30 | 2026-02-01 | Meter technician |  | 2.96 | Completed | No
WO-26-000745 | 1.9 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-30 | 2026-01-30 | Meter technician |  | 36.16 | Completed | No
WO-26-000746 | 0.8 | Crossroads | CR-S04-04 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-31 | 2026-02-08 | Meter technician |  | 13.6 | Completed | No
WO-26-000747 | 1 | Crossroads | CR-S08-02 | Service order - field | P3 within 10 days | 2026-01-21 | 2026-01-29 | 2026-01-29 | Meter technician |  | 19.89 | Completed | No
WO-26-000748 | 0.9 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-01-21 | 2026-01-21 | 2026-01-21 | Meter technician |  | 23.16 | Completed | No
WO-26-000749 | 2 | Crossroads | CR-S20-03 | Service order - field | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Meter technician |  | 20.32 | Completed | No
WO-26-000750 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-21 | 2026-01-23 | 2026-01-24 | Contract line | CT-01 | 359.11 | Completed | No
WO-26-000751 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-21 | 2026-01-31 | 2026-01-31 | Internal line |  | 163.65 | Completed | No
WO-26-000752 | 7.5 | Crossroads | CR-S14-01 | Transformer replacement | P3 within 10 days | 2026-01-21 | 2026-01-27 | 2026-01-27 | Contract line | CT-01 | 9295.51 | Completed | No
WO-26-000753 | 13.3 | Crossroads | CR-S26-02 | Transformer replacement | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Internal line |  | 9567.37 | Completed | No
WO-26-000754 | 2.1 | Crossroads | CR-S20-02 | Trouble - no power | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Troubleman |  | 184.1 | Completed | No
WO-26-000755 | 3.8 | Crossroads | CR-S15-01 | Trouble - no power | P2 same day | 2026-01-21 | 2026-01-22 | 2026-01-22 | Troubleman |  | 191.89 | Completed | No
WO-26-000756 | 4.2 | Crossroads | CR-S31-01 | Trouble - no power | P2 same day | 2026-01-21 | 2026-01-21 | 2026-01-21 | Internal line |  | 52.61 | Completed | No
WO-26-000757 | 4.2 | Crossroads | CR-S09-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-21 | 2026-01-31 | 2026-02-04 | Troubleman |  | 233.33 | Completed | No
WO-26-000758 | 4.2 | Bayou | BY-S17-04 | Corrective maintenance | P3 within 10 days | 2026-01-22 | 2026-02-01 | 2026-02-01 | Internal line |  | 208.74 | Completed | No
WO-26-000759 | 10.4 | Bayou | BY-S05-02 | Corrective maintenance | P2 same day | 2026-01-22 | 2026-01-23 | 2026-01-23 | Underground crew |  | 333.18 | Completed | No
WO-26-000760 | 11.8 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-01-22 | 2026-01-23 | 2026-01-23 | Internal line |  | 619.18 | Completed | No
WO-26-000761 | 6.5 | Bayou | BY-S29-01 | Corrective maintenance | P2 same day | 2026-01-22 | 2026-01-22 | 2026-01-22 | Internal line |  | 2057.6 | Completed | No
WO-26-000762 | 9.3 | Bayou | BY-S14-02 | Corrective maintenance | P3 within 10 days | 2026-01-22 | 2026-01-23 | 2026-01-24 | Contract line | CT-04 | 791.57 | Completed | No
WO-26-000763 | 0.9 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-01-22 | 2026-02-01 | 2026-02-01 | Meter technician |  | 75.96 | Completed | No
WO-26-000764 | 23 | Bayou | BY-S18-05 | Pole replacement | P4 planned | 2026-01-22 | 2026-02-04 | 2026-02-06 | Contract line | CT-04 | 3377.73 | Completed | No
WO-26-000765 | 4.4 | Bayou | BY-S13-05 | Preventive maintenance | P4 planned | 2026-01-22 | 2026-02-09 | 2026-02-09 | Internal line |  | 266.23 | Completed | No
WO-26-000766 | 4.7 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-01-22 | 2026-03-09 | 2026-03-09 | Underground crew |  | 434.71 | Completed | No
WO-26-000767 | 5.7 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-01-22 | 2026-02-22 | 2026-02-22 | Internal line |  | 175.53 | Completed | No
WO-26-000768 | 7.2 | Bayou | BY-S04-01 | Preventive maintenance | P4 planned | 2026-01-22 | 2026-03-15 | 2026-03-19 | Internal line |  | 581.83 | Completed | No
WO-26-000769 | 3.6 | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-01-22 | 2026-01-30 | 2026-01-31 | Internal line |  | 93.68 | Completed | No
WO-26-000770 | 0.8 | Bayou | BY-S08-01 | Service order - field | P3 within 10 days | 2026-01-22 | 2026-01-24 | 2026-01-25 | Meter technician |  | 36.37 | Completed | No
WO-26-000771 | 5.1 | Bayou | BY-S18-02 | Trouble - no power | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 212.85 | Completed | No
WO-26-000772 | 2.3 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 235.68 | Completed | No
WO-26-000773 | 3.9 | Bayou | BY-S16-05 | Trouble - no power | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Internal line |  | 274.04 | Completed | No
WO-26-000774 | 5.4 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 188.11 | Completed | No
WO-26-000775 | 3.1 | Bayou | BY-S30-01 | Trouble - partial or voltage | P2 same day | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 225.49 | Completed | No
WO-26-000776 | 8.1 | Crossroads | CR-S19-02 | Corrective maintenance | P3 within 10 days | 2026-01-22 | 2026-01-31 | 2026-02-04 | Internal line |  | 2051.78 | Completed | No
WO-26-000777 | 6.8 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-01-22 | 2026-01-25 | 2026-01-25 | Underground crew |  | 291.66 | Completed | No
WO-26-000778 | 3.2 | Crossroads | CR-S20-05 | Corrective maintenance | P4 planned | 2026-01-22 | 2026-02-01 | 2026-02-02 | Internal line |  | 100.3 | Completed | No
WO-26-000779 | 6.1 | Crossroads | CR-S14-01 | Corrective maintenance | P3 within 10 days | 2026-01-22 | 2026-01-25 | 2026-01-25 | Underground crew |  | 1361.84 | Completed | No
WO-26-000780 | 18.1 | Crossroads | CR-S24-03 | Pole replacement | P3 within 10 days | 2026-01-22 | 2026-01-29 | 2026-01-29 | Contract line | CT-02 | 3358.36 | Completed | No
WO-26-000781 | 17.9 | Crossroads | CR-S31-02 | Pole replacement | P2 same day | 2026-01-22 | 2026-01-22 | 2026-01-22 | Internal line |  | 1546.62 | Completed | No
WO-26-000782 | 22.7 | Crossroads | CR-S14-02 | Pole replacement | P2 same day | 2026-01-22 | 2026-01-23 | 2026-01-23 | Contract line | CT-02 | 1539.09 | Completed | No
WO-26-000783 | 6.8 | Crossroads | CR-S18-01 | Preventive maintenance | P4 planned | 2026-01-22 | 2026-03-12 | 2026-03-12 | Underground crew |  | 114.14 | Completed | No
WO-26-000784 | 1.1 | Crossroads | CR-S06-02 | Service order - field | P3 within 10 days | 2026-01-22 | 2026-01-29 | 2026-01-30 | Meter technician |  | 19.19 | Completed | No
WO-26-000785 | 1.6 | Crossroads | CR-S14-04 | Service order - field | P3 within 10 days | 2026-01-22 | 2026-01-31 | 2026-02-02 | Meter technician |  | 37.95 | Completed | No
WO-26-000786 | 1.1 | Crossroads | CR-S16-02 | Service order - field | P3 within 10 days | 2026-01-22 | 2026-01-28 | 2026-01-28 | Meter technician |  | 0.36 | Completed | No
WO-26-000787 | 10 | Crossroads | CR-S04-06 | Transformer replacement | P2 same day | 2026-01-22 | 2026-01-23 | 2026-01-23 | Internal line |  | 5170.68 | Completed | No
WO-26-000788 | 7.3 | Crossroads | CR-S17-03 | Transformer replacement | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Contract line | CT-01 | 10579.52 | Completed | No
WO-26-000789 | 2.9 | Crossroads | CR-S05-03 | Trouble - no power | P2 same day | 2026-01-22 | 2026-01-23 | 2026-01-23 | Troubleman |  | 247.75 | Completed | No
WO-26-000790 | 2.8 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 144.78 | Completed | No
WO-26-000791 | 5.6 | Crossroads | CR-S08-05 | Trouble - no power | P1 emergency | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 269.07 | Completed | No
WO-26-000792 | 4.1 | Crossroads | CR-S27-02 | Trouble - partial or voltage | P3 within 10 days | 2026-01-22 | 2026-01-26 | 2026-01-26 | Troubleman |  | 74.65 | Completed | No
WO-26-000793 | 3.5 | Crossroads | CR-S09-02 | Trouble - partial or voltage | P2 same day | 2026-01-22 | 2026-01-22 | 2026-01-22 | Troubleman |  | 199.36 | Completed | No
WO-26-000794 | 3.2 | Bayou | BY-S12-04 | Corrective maintenance | P3 within 10 days | 2026-01-23 | 2026-02-02 | 2026-02-03 | Internal line |  | 1757.31 | Completed | No
WO-26-000795 | 11.9 | Bayou | BY-S08-03 | Corrective maintenance | P3 within 10 days | 2026-01-23 | 2026-01-30 | 2026-02-03 | Internal line |  | 1371.7 | Completed | No
WO-26-000796 | 7.7 | Bayou | BY-S16-01 | Corrective maintenance | P3 within 10 days | 2026-01-23 | 2026-02-01 | 2026-02-02 | Internal line |  | 829.33 | Completed | No
WO-26-000797 | 4.2 | Bayou | BY-S03-02 | Corrective maintenance | P3 within 10 days | 2026-01-23 | 2026-01-31 | 2026-01-31 | Underground crew |  | 884.01 | Completed | No
WO-26-000798 | 9.4 | Bayou | BY-S19-04 | Corrective maintenance | P3 within 10 days | 2026-01-23 | 2026-02-02 | 2026-02-06 | Contract line | CT-03 | 190.78 | Completed | No
WO-26-000799 | 1.2 | Bayou | BY-S28-03 | Meter exchange | P4 planned | 2026-01-23 | 2026-02-17 | 2026-02-17 | Meter technician |  | 85.05 | Completed | No
WO-26-000800 | 0.5 | Bayou | BY-S17-02 | Meter exchange | P3 within 10 days | 2026-01-23 | 2026-01-28 | 2026-01-28 | Meter technician |  | 130.73 | Completed | No
WO-26-000801 | 1.4 | Bayou | BY-S17-01 | Meter exchange | P4 planned | 2026-01-23 | 2026-03-01 | 2026-03-03 | Meter technician |  | 61.84 | Completed | No
WO-26-000802 | 12.5 | Bayou | BY-S15-04 | New service - small | P4 planned | 2026-01-23 | 2026-03-21 | 2026-03-23 | Internal line |  | 912.97 | Completed | No
WO-26-000803 | 21.6 | Bayou | BY-S07-05 | Pole replacement | P3 within 10 days | 2026-01-23 | 2026-01-29 | 2026-02-02 | Contract line | CT-03 | 3424.67 | Completed | No
WO-26-000804 | 5.6 | Bayou | BY-S16-01 | Preventive maintenance | P4 planned | 2026-01-23 | 2026-02-21 | 2026-02-23 | Contract line | CT-04 | 89.25 | Completed | No
WO-26-000805 | 1.2 | Bayou | BY-S14-01 | Service order - field | P3 within 10 days | 2026-01-23 | 2026-01-30 | 2026-01-31 | Meter technician |  | 0.49 | Completed | No
WO-26-000806 | 2.9 | Bayou |  | Streetlight | P4 planned | 2026-01-23 | 2026-02-16 | 2026-02-16 | Contract line | CT-03 | 363.67 | Completed | No
WO-26-000807 | 3.2 | Bayou | BY-S21-02 | Trouble - no power | P1 emergency | 2026-01-23 | 2026-01-23 | 2026-01-23 | Troubleman |  | 55.68 | Completed | No
WO-26-000808 | 4.5 | Bayou | BY-S02-01 | Trouble - no power | P2 same day | 2026-01-23 | 2026-01-24 | 2026-01-24 | Troubleman |  | 233.45 | Completed | No
WO-26-000809 | 3.2 | Bayou | BY-S06-01 | Trouble - partial or voltage | P2 same day | 2026-01-23 | 2026-01-23 | 2026-01-23 | Troubleman |  | 110.85 | Completed | No
WO-26-000810 | 9.3 | Crossroads | CR-S26-06 | Corrective maintenance | P3 within 10 days | 2026-01-23 | 2026-02-02 | 2026-02-02 | Internal line |  | 772.01 | Completed | No
WO-26-000811 | 7.6 | Crossroads | CR-S27-04 | Corrective maintenance | P2 same day | 2026-01-23 | 2026-01-24 | 2026-01-24 | Internal line |  | 1213.62 | Completed | No
WO-26-000812 | 1.3 | Crossroads | CR-S28-03 | Meter exchange | P4 planned | 2026-01-23 | 2026-03-24 | 2026-04-01 | Meter technician |  | 77.26 | Completed | No
WO-26-000813 | 1.5 | Crossroads | CR-S16-06 | Meter exchange | P4 planned | 2026-01-23 | 2026-03-10 | 2026-03-11 | Meter technician |  | 174.13 | Completed | No
WO-26-000814 | 0.7 | Crossroads | CR-S04-02 | Meter exchange | P3 within 10 days | 2026-01-23 | 2026-01-26 | 2026-01-26 | Meter technician |  | 159.9 | Completed | No
WO-26-000815 | 10.7 | Crossroads | CR-S07-01 | Pole replacement | P4 planned | 2026-01-23 | 2026-02-06 | 2026-02-06 | Contract line | CT-02 | 2789.11 | Completed | No
WO-26-000816 | 7.4 | Crossroads | CR-S27-02 | Preventive maintenance | P4 planned | 2026-01-23 | 2026-02-18 | 2026-02-26 | Underground crew |  | 22.68 | Completed | No
WO-26-000817 | 5.8 | Crossroads | CR-S24-01 | Preventive maintenance | P4 planned | 2026-01-23 | 2026-03-19 | 2026-03-19 | Internal line |  | 476.76 | Completed | No
WO-26-000818 | 1.9 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-01-23 | 2026-01-23 | 2026-01-23 | Meter technician |  | 36.85 | Completed | No
WO-26-000819 | 0.8 | Crossroads | CR-S18-02 | Service order - field | P3 within 10 days | 2026-01-23 | 2026-02-02 | 2026-02-06 | Meter technician |  | 4.96 | Completed | No
WO-26-000820 |  | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-01-23 | 2026-01-24 |  | Meter technician |  |  | Cancelled | No
WO-26-000821 | 1.1 | Crossroads | CR-S21-02 | Service order - field | P2 same day | 2026-01-23 | 2026-01-23 | 2026-01-23 | Meter technician |  | 29.56 | Completed | No
WO-26-000822 | 1.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-23 | 2026-01-26 | 2026-01-30 | Contract line | CT-01 | 295.25 | Completed | No
WO-26-000823 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-23 | 2026-01-31 |  | Internal line |  |  | Cancelled | No
WO-26-000824 | 9.6 | Crossroads | CR-S27-01 | Transformer replacement | P2 same day | 2026-01-23 | 2026-01-24 | 2026-01-24 | Contract line | CT-02 | 6830.97 | Completed | No
WO-26-000825 | 3.6 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-01-23 | 2026-01-23 | 2026-01-23 | Internal line |  | 226.36 | Completed | No
WO-26-000826 | 4 | Crossroads | CR-S26-06 | Trouble - no power | P2 same day | 2026-01-23 | 2026-01-24 | 2026-01-24 | Troubleman |  | 256.13 | Completed | No
WO-26-000827 | 2.9 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-01-23 | 2026-01-23 | 2026-01-23 | Troubleman |  | 70.24 | Completed | No
WO-26-000828 | 4 | Crossroads | CR-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-23 | 2026-01-24 | 2026-02-01 | Troubleman |  | 184.36 | Completed | No
WO-26-000829 | 3.5 | Crossroads | CR-S04-06 | Trouble - partial or voltage | P2 same day | 2026-01-23 | 2026-01-23 | 2026-01-23 | Troubleman |  | 136.58 | Completed | No
WO-26-000830 | 0.7 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-01-24 | 2026-01-24 | 2026-01-24 | Meter technician |  | 14.94 | Completed | No
WO-26-000831 | 13.6 | Bayou | BY-S18-04 | Transformer replacement | P2 same day | 2026-01-24 | 2026-01-25 | 2026-01-25 | Internal line |  | 3420.11 | Completed | No
WO-26-000832 | 11 | Bayou | BY-S23-03 | Transformer replacement | P2 same day | 2026-01-24 | 2026-01-25 | 2026-01-25 | Internal line |  | 3402.08 | Completed | No
WO-26-000833 | 3.6 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 138.85 | Completed | No
WO-26-000834 | 3.7 | Bayou | BY-S18-07 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 346.79 | Completed | No
WO-26-000835 | 3.9 | Bayou | BY-S16-02 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 165.49 | Completed | No
WO-26-000836 | 5 | Bayou | BY-S16-04 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 326.3 | Completed | No
WO-26-000837 | 3.5 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 112.81 | Completed | No
WO-26-000838 | 3.7 | Bayou | BY-S15-01 | Trouble - partial or voltage | P2 same day | 2026-01-24 | 2026-01-25 | 2026-01-25 | Troubleman |  | 146.93 | Completed | No
WO-26-000839 | 10.2 | Crossroads | CR-S31-02 | Corrective maintenance | P2 same day | 2026-01-24 | 2026-01-24 | 2026-01-24 | Contract line | CT-01 | 1803.76 | Completed | No
WO-26-000840 | 1.4 | Crossroads | CR-S29-01 | Service order - field | P2 same day | 2026-01-24 | 2026-01-24 | 2026-01-24 | Meter technician |  | 20.4 | Completed | No
WO-26-000841 | 1.9 | Crossroads | CR-S32-03 | Service order - field | P2 same day | 2026-01-24 | 2026-01-24 | 2026-01-24 | Meter technician |  | 16.58 | Completed | No
WO-26-000842 | 10.2 | Crossroads | CR-S24-01 | Transformer replacement | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Contract line | CT-01 | 7916.3 | Completed | No
WO-26-000843 | 2.3 | Crossroads | CR-S05-03 | Trouble - no power | P2 same day | 2026-01-24 | 2026-01-25 | 2026-01-25 | Troubleman |  | 274.66 | Completed | No
WO-26-000844 | 3.9 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 348.81 | Completed | No
WO-26-000845 | 2.7 | Crossroads | CR-S14-04 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 324.31 | Completed | No
WO-26-000846 | 3.5 | Crossroads | CR-S01-03 | Trouble - no power | P1 emergency | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 288.63 | Completed | No
WO-26-000847 | 1.8 | Crossroads | CR-S22-04 | Trouble - partial or voltage | P2 same day | 2026-01-24 | 2026-01-25 | 2026-01-25 | Troubleman |  | 226.15 | Completed | No
WO-26-000848 | 4.7 | Crossroads | CR-S02-05 | Trouble - partial or voltage | P2 same day | 2026-01-24 | 2026-01-24 | 2026-01-24 | Troubleman |  | 58.38 | Completed | No
WO-26-000849 | 7.7 | Bayou | BY-S26-04 | Corrective maintenance | P2 same day | 2026-01-25 | 2026-01-26 | 2026-01-26 | Contract line | CT-04 | 235.78 | Completed | No
WO-26-000850 | 10.3 | Bayou | BY-S08-03 | Corrective maintenance | P2 same day | 2026-01-25 | 2026-01-26 | 2026-01-26 | Internal line |  | 1367.24 | Completed | No
WO-26-000851 | 1.2 | Bayou | BY-S29-02 | Service order - field | P2 same day | 2026-01-25 | 2026-01-25 | 2026-01-25 | Meter technician |  | 21.64 | Completed | No
WO-26-000852 | 1.8 | Bayou | BY-S25-01 | Service order - field | P2 same day | 2026-01-25 | 2026-01-25 | 2026-01-25 | Meter technician |  | 33.97 | Completed | No
WO-26-000853 | 9 | Bayou | BY-S19-01 | Transformer replacement | P2 same day | 2026-01-25 | 2026-01-25 | 2026-01-25 | Contract line | CT-03 | 3556.32 | Completed | No
WO-26-000854 | 6.3 | Bayou | BY-S27-06 | Transformer replacement | P2 same day | 2026-01-25 | 2026-01-26 | 2026-01-26 | Contract line | CT-04 | 7121.48 | Completed | No
WO-26-000855 | 4 | Bayou | BY-S27-05 | Trouble - no power | P2 same day | 2026-01-25 | 2026-01-25 | 2026-01-25 | Internal line |  | 297.79 | Completed | No
WO-26-000856 | 4.7 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-01-25 | 2026-01-25 | 2026-01-25 | Troubleman |  | 334.05 | Completed | No
WO-26-000857 | 5.7 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-01-25 | 2026-01-26 | 2026-01-26 | Contract line | CT-02 | 1184.2 | Completed | No
WO-26-000858 | 0.5 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-01-25 | 2026-01-25 | 2026-01-25 | Meter technician |  | 27.91 | Completed | No
WO-26-000859 | 4.4 | Crossroads | CR-S26-03 | Trouble - no power | P1 emergency | 2026-01-25 | 2026-01-25 | 2026-01-25 | Internal line |  | 291.37 | Completed | No
WO-26-000860 | 2 | Crossroads | CR-S26-01 | Trouble - no power | P1 emergency | 2026-01-25 | 2026-01-25 | 2026-01-25 | Troubleman |  | 63.93 | Completed | No
WO-26-000861 | 3.5 | Crossroads | CR-S01-04 | Trouble - no power | P1 emergency | 2026-01-25 | 2026-01-25 | 2026-01-25 | Troubleman |  | 330.88 | Completed | No
WO-26-000862 | 2.6 | Crossroads | CR-S09-02 | Trouble - no power | P1 emergency | 2026-01-25 | 2026-01-25 | 2026-01-25 | Troubleman |  | 225.91 | Completed | No
WO-26-000863 | 4.3 | Crossroads | CR-S24-03 | Trouble - no power | P1 emergency | 2026-01-25 | 2026-01-25 | 2026-01-25 | Troubleman |  | 285.8 | Completed | No
WO-26-000864 | 4.3 | Crossroads | CR-S18-03 | Trouble - partial or voltage | P2 same day | 2026-01-25 | 2026-01-25 | 2026-01-25 | Troubleman |  | 53.51 | Completed | No
WO-26-000865 | 2.3 | Crossroads | CR-S10-01 | Trouble - partial or voltage | P2 same day | 2026-01-25 | 2026-01-26 | 2026-01-26 | Troubleman |  | 19.31 | Completed | No
WO-26-000866 | 11.3 | Bayou | BY-S16-05 | Corrective maintenance | P3 within 10 days | 2026-01-26 | 2026-01-30 | 2026-01-30 | Internal line |  | 1979.3 | Completed | No
WO-26-000867 | 0.9 | Bayou | BY-S25-05 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-01-30 | 2026-01-31 | Meter technician |  | 157.05 | Completed | No
WO-26-000868 | 0.8 | Bayou | BY-S06-01 | Meter exchange | P4 planned | 2026-01-26 | 2026-03-25 | 2026-03-26 | Meter technician |  | 95.31 | Completed | No
WO-26-000869 | 0.9 | Bayou | BY-S21-04 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-02-01 | 2026-02-01 | Meter technician |  | 94.83 | Completed | No
WO-26-000870 | 0.7 | Bayou | BY-S26-01 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-02-03 | 2026-02-05 | Meter technician |  | 158.73 | Completed | No
WO-26-000871 | 16.6 | Bayou | BY-S01-01 | Pole replacement | P2 same day | 2026-01-26 | 2026-01-27 | 2026-01-27 | Contract line | CT-04 | 2768.18 | Completed | No
WO-26-000872 | 12 | Bayou | BY-S30-01 | Pole replacement | P4 planned | 2026-01-26 | 2026-02-07 | 2026-02-07 | Contract line | CT-04 | 3029.17 | Completed | No
WO-26-000873 | 5.7 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-01-26 | 2026-03-27 | 2026-03-27 | Internal line |  | 125.96 | Completed | No
WO-26-000874 | 1.3 | Bayou | BY-S16-04 | Service order - field | P2 same day | 2026-01-26 | 2026-01-27 | 2026-01-27 | Meter technician |  | 5.65 | Completed | No
WO-26-000875 | 1.4 | Bayou | BY-S28-03 | Service order - field | P3 within 10 days | 2026-01-26 | 2026-02-05 | 2026-02-09 | Meter technician |  | 22.49 | Completed | No
WO-26-000876 | 2.9 | Bayou | BY-S12-03 | Trouble - no power | P1 emergency | 2026-01-26 | 2026-01-26 | 2026-01-26 | Internal line |  | 154.88 | Completed | No
WO-26-000877 | 4.8 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-01-26 | 2026-01-27 | 2026-01-27 | Troubleman |  | 217.95 | Completed | No
WO-26-000878 | 10.1 | Crossroads | CR-S04-04 | Corrective maintenance | P3 within 10 days | 2026-01-26 | 2026-02-03 | 2026-02-03 | Contract line | CT-02 | 2266.37 | Completed | No
WO-26-000879 | 12 | Crossroads | CR-S23-03 | Corrective maintenance | P3 within 10 days | 2026-01-26 | 2026-02-01 | 2026-02-02 | Contract line | CT-01 | 1634.7 | Completed | No
WO-26-000880 | 6.5 | Crossroads | CR-S08-02 | Corrective maintenance | P3 within 10 days | 2026-01-26 | 2026-02-05 | 2026-02-13 | Underground crew |  | 536.99 | Completed | No
WO-26-000881 | 7.8 | Crossroads | CR-S20-02 | Corrective maintenance | P4 planned | 2026-01-26 | 2026-02-19 | 2026-02-27 | Internal line |  | 1191.9 | Completed | No
WO-26-000882 | 3.9 | Crossroads | CR-S21-01 | Corrective maintenance | P3 within 10 days | 2026-01-26 | 2026-01-31 | 2026-01-31 | Contract line | CT-02 | 1639.53 | Completed | No
WO-26-000883 | 9.5 | Crossroads | CR-S22-01 | Corrective maintenance | P4 planned | 2026-01-26 | 2026-03-18 | 2026-03-18 | Internal line |  | 1268.78 | Completed | No
WO-26-000884 | 9.7 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-01-26 | 2026-01-29 | 2026-01-30 | Internal line |  | 1461.88 | Completed | No
WO-26-000885 | 1.4 | Crossroads | CR-S18-04 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-01-30 | 2026-02-03 | Meter technician |  | 112.37 | Completed | No
WO-26-000886 | 1.5 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-01-27 | 2026-02-04 | Meter technician |  | 135.97 | Completed | No
WO-26-000887 | 0.7 | Crossroads | CR-S14-02 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-02-05 | 2026-02-07 | Meter technician |  | 154.32 | Completed | No
WO-26-000888 | 0.6 | Crossroads | CR-S30-05 | Meter exchange | P3 within 10 days | 2026-01-26 | 2026-02-05 | 2026-02-06 | Meter technician |  | 167.75 | Completed | No
WO-26-000889 | 0.9 | Crossroads | CR-S14-06 | Meter exchange | P4 planned | 2026-01-26 | 2026-03-10 | 2026-03-14 | Meter technician |  | 91.13 | Completed | No
WO-26-000890 | 11.7 | Crossroads | CR-S04-03 | New service - small | P4 planned | 2026-01-26 | 2026-02-14 | 2026-02-14 | Internal line |  | 1925.84 | Completed | No
WO-26-000891 | 8.7 | Crossroads | CR-S25-04 | New service - small | P4 planned | 2026-01-26 | 2026-02-23 | 2026-02-23 | Contract line | CT-02 | 2290.41 | Completed | No
WO-26-000892 | 22.4 | Crossroads | CR-S10-02 | Pole replacement | P4 planned | 2026-01-26 | 2026-03-09 | 2026-03-09 | Contract line | CT-01 | 2418.62 | Completed | No
WO-26-000893 | 4.3 | Crossroads | CR-S19-04 | Preventive maintenance | P4 planned | 2026-01-26 | 2026-03-07 | 2026-03-07 | Underground crew |  | 48.51 | Completed | No
WO-26-000894 | 7.4 | Crossroads | CR-S28-01 | Preventive maintenance | P4 planned | 2026-01-26 | 2026-02-03 | 2026-02-03 | Internal line |  | 490.78 | Completed | No
WO-26-000895 | 2 | Crossroads | CR-S12-01 | Preventive maintenance | P4 planned | 2026-01-26 | 2026-03-24 | 2026-03-28 | Internal line |  | 142.42 | Completed | No
WO-26-000896 | 0.7 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-01-26 | 2026-01-27 | 2026-01-27 | Meter technician |  | 12.76 | Completed | No
WO-26-000897 | 0.9 | Crossroads | CR-S04-03 | Service order - field | P3 within 10 days | 2026-01-26 | 2026-02-05 | 2026-02-05 | Meter technician |  | 6.51 | Completed | No
WO-26-000898 | 1.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-26 | 2026-02-01 | 2026-02-01 | Contract line | CT-02 | 48.24 | Completed | No
WO-26-000899 | 10.5 | Crossroads | CR-S17-01 | Transformer replacement | P1 emergency | 2026-01-26 | 2026-01-26 | 2026-01-26 | Contract line | CT-01 | 4621.33 | Completed | No
WO-26-000900 | 2.8 | Crossroads | CR-S01-03 | Trouble - no power | P1 emergency | 2026-01-26 | 2026-01-26 | 2026-01-26 | Troubleman |  | 5.07 | Completed | No
WO-26-000901 |  | Crossroads | CR-S19-01 | Trouble - no power | P2 same day | 2026-01-26 | 2026-01-26 |  | Troubleman |  |  | Cancelled | No
WO-26-000902 | 5.5 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-01-26 | 2026-01-26 | 2026-01-26 | Troubleman |  | 209.95 | Completed | No
WO-26-000903 | 4.7 | Crossroads | CR-S08-03 | Trouble - no power | P1 emergency | 2026-01-26 | 2026-01-26 | 2026-01-26 | Troubleman |  | 101.24 | Completed | No
WO-26-000904 | 4.8 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-01-26 | 2026-02-05 | 2026-02-05 | Troubleman |  | 163.06 | Completed | No
WO-26-000905 | 4.4 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-01-27 | 2026-02-06 | 2026-02-06 | Contract line | CT-04 | 2183.28 | Completed | No
WO-26-000906 | 6.9 | Bayou | BY-S06-01 | Corrective maintenance | P4 planned | 2026-01-27 | 2026-03-05 | 2026-03-06 | Internal line |  | 554.98 | Completed | No
WO-26-000907 | 10.9 | Bayou | BY-S14-01 | Corrective maintenance | P2 same day | 2026-01-27 | 2026-01-27 | 2026-01-27 | Internal line |  | 1119.31 | Completed | No
WO-26-000908 | 10.5 | Bayou | BY-S07-02 | Corrective maintenance | P3 within 10 days | 2026-01-27 | 2026-01-30 | 2026-01-30 | Internal line |  | 1886.09 | Completed | No
WO-26-000909 | 10.4 | Bayou | BY-S26-06 | Corrective maintenance | P4 planned | 2026-01-27 | 2026-02-25 | 2026-03-05 | Internal line |  | 140.13 | Completed | No
WO-26-000910 | 0.9 | Bayou | BY-S28-03 | Meter exchange | P4 planned | 2026-01-27 | 2026-02-06 | 2026-02-06 | Meter technician |  | 81.79 | Completed | No
WO-26-000911 | 1.2 | Bayou | BY-S20-01 | Meter exchange | P4 planned | 2026-01-27 | 2026-02-10 | 2026-02-10 | Meter technician |  | 125.24 | Completed | No
WO-26-000912 | 1 | Bayou | BY-S25-02 | Meter exchange | P3 within 10 days | 2026-01-27 | 2026-01-29 | 2026-01-29 | Meter technician |  | 117.78 | Completed | No
WO-26-000913 | 5.8 | Bayou | BY-S13-04 | New service - small | P3 within 10 days | 2026-01-27 | 2026-01-29 | 2026-01-31 | Contract line | CT-04 | 3726.73 | Completed | No
WO-26-000914 | 11.3 | Bayou | BY-S16-01 | Pole replacement | P3 within 10 days | 2026-01-27 | 2026-01-31 | 2026-01-31 | Internal line |  | 1351.73 | Completed | No
WO-26-000915 | 19.8 | Bayou | BY-S26-04 | Pole replacement | P3 within 10 days | 2026-01-27 | 2026-02-04 | 2026-02-08 | Contract line | CT-04 | 1376.72 | Completed | No
WO-26-000916 | 15.2 | Bayou | BY-S26-02 | Pole replacement | P4 planned | 2026-01-27 | 2026-03-21 | 2026-03-22 | Internal line |  | 2222.97 | Completed | No
WO-26-000917 | 3.6 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-03-03 | 2026-03-07 | Internal line |  | 39.55 | Completed | No
WO-26-000918 | 2.7 | Bayou | BY-S22-02 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-02-17 | 2026-02-18 | Internal line |  | 464.52 | Completed | No
WO-26-000919 | 3.6 | Bayou | BY-S10-05 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-02-22 | 2026-02-23 | Internal line |  | 342.9 | Completed | No
WO-26-000920 | 1.2 | Bayou | BY-S28-02 | Service order - field | P3 within 10 days | 2026-01-27 | 2026-02-05 | 2026-02-09 | Meter technician |  | 0.35 | Completed | No
WO-26-000921 | 1.8 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Meter technician |  | 15.1 | Completed | No
WO-26-000922 | 1.8 | Bayou | BY-S09-05 | Service order - field | P3 within 10 days | 2026-01-27 | 2026-02-04 | 2026-02-04 | Meter technician |  | 12.11 | Completed | No
WO-26-000923 | 4.7 | Bayou | BY-S06-01 | Trouble - no power | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Internal line |  | 92.64 | Completed | No
WO-26-000924 | 3.6 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 216.71 | Completed | No
WO-26-000925 | 5.9 | Bayou | BY-S16-05 | Trouble - no power | P1 emergency | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 328.8 | Completed | No
WO-26-000926 | 2.4 | Bayou | BY-S27-02 | Trouble - no power | P2 same day | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 104.92 | Completed | No
WO-26-000927 | 2.8 | Bayou | BY-S12-03 | Trouble - no power | P2 same day | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 59.66 | Completed | No
WO-26-000928 | 2.3 | Bayou | BY-S12-01 | Trouble - no power | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Troubleman |  | 187.95 | Completed | No
WO-26-000929 | 7.1 | Crossroads | CR-S01-03 | Corrective maintenance | P3 within 10 days | 2026-01-27 | 2026-02-01 | 2026-02-09 | Underground crew |  | 1017 | Completed | No
WO-26-000930 | 8.2 | Crossroads | CR-S07-02 | Corrective maintenance | P3 within 10 days | 2026-01-27 | 2026-02-06 | 2026-02-06 | Contract line | CT-01 | 875.89 | Completed | No
WO-26-000931 | 11.4 | Crossroads | CR-S32-01 | Corrective maintenance | P3 within 10 days | 2026-01-27 | 2026-02-02 | 2026-02-02 | Underground crew |  | 764.98 | Completed | No
WO-26-000932 | 0.7 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-01-27 | 2026-01-31 | 2026-01-31 | Meter technician |  | 156.58 | Completed | No
WO-26-000933 | 0.6 | Crossroads | CR-S08-04 | Meter exchange | P4 planned | 2026-01-27 | 2026-03-23 | 2026-03-23 | Meter technician |  | 100.12 | Completed | No
WO-26-000934 | 11.4 | Crossroads | CR-S01-03 | New service - small | P4 planned | 2026-01-27 | 2026-03-28 | 2026-03-29 | Contract line | CT-02 | 1207.45 | Completed | No
WO-26-000935 | 16.5 | Crossroads | CR-S28-01 | Pole replacement | P3 within 10 days | 2026-01-27 | 2026-02-03 | 2026-02-03 | Contract line | CT-02 | 3316.09 | Completed | No
WO-26-000936 | 6.7 | Crossroads | CR-S14-03 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-02-28 | 2026-02-28 | Underground crew |  | 282.4 | Completed | No
WO-26-000937 | 6.4 | Crossroads | CR-S15-02 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-02-13 | 2026-02-13 | Underground crew |  | 20.93 | Completed | No
WO-26-000938 | 2.9 | Crossroads | CR-S05-06 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-02-25 | 2026-02-25 | Contract line | CT-02 | 59 | Completed | No
WO-26-000939 | 7 | Crossroads | CR-S27-03 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-03-02 | 2026-03-02 | Underground crew |  | 456.09 | Completed | No
WO-26-000940 | 7 | Crossroads | CR-S08-02 | Preventive maintenance | P4 planned | 2026-01-27 | 2026-03-08 | 2026-03-09 | Internal line |  | 48.37 | Completed | No
WO-26-000941 | 1.6 | Crossroads | CR-S07-02 | Service order - field | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Meter technician |  | 13.41 | Completed | No
WO-26-000942 | 1.1 | Crossroads | CR-S15-03 | Service order - field | P3 within 10 days | 2026-01-27 | 2026-02-04 | 2026-02-08 | Meter technician |  | 31.11 | Completed | No
WO-26-000943 | 0.8 | Crossroads | CR-S26-05 | Service order - field | P3 within 10 days | 2026-01-27 | 2026-02-01 | 2026-02-02 | Meter technician |  | 22.1 | Completed | No
WO-26-000944 | 0.7 | Crossroads | CR-S03-02 | Service order - field | P2 same day | 2026-01-27 | 2026-01-27 | 2026-01-27 | Meter technician |  | 6.06 | Completed | No
WO-26-000945 | 1.8 | Crossroads | CR-S02-04 | Service order - field | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Meter technician |  | 19.08 | Completed | No
WO-26-000946 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-27 | 2026-02-03 | 2026-02-03 | Internal line |  | 168.01 | Completed | No
WO-26-000947 | 8 | Crossroads | CR-S26-02 | Transformer replacement | P3 within 10 days | 2026-01-27 | 2026-01-28 | 2026-01-28 | Internal line |  | 5010.88 | Completed | No
WO-26-000948 | 11.8 | Crossroads | CR-S22-01 | Transformer replacement | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Contract line | CT-02 | 3445.52 | Completed | No
WO-26-000949 | 3.7 | Crossroads | CR-S26-02 | Trouble - no power | P1 emergency | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 84.82 | Completed | No
WO-26-000950 | 3.2 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 133.18 | Completed | No
WO-26-000951 | 4.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-01-27 | 2026-01-27 | 2026-01-27 | Troubleman |  | 146.26 | Completed | No
WO-26-000952 | 5.4 | Crossroads | CR-S32-02 | Trouble - no power | P2 same day | 2026-01-27 | 2026-01-28 | 2026-01-28 | Troubleman |  | 290.71 | Completed | No
WO-26-000953 |  | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-01-27 | 2026-01-27 |  | Troubleman |  |  | Cancelled | No
WO-26-000954 | 5.1 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-01-28 | 2026-02-03 | 2026-02-03 | Internal line |  | 2213.31 | Completed | No
WO-26-000955 | 6.3 | Bayou | BY-S07-05 | Corrective maintenance | P4 planned | 2026-01-28 | 2026-03-19 | 2026-03-23 | Internal line |  | 1181.22 | Completed | No
WO-26-000956 | 0.8 | Bayou | BY-S16-01 | Meter exchange | P4 planned | 2026-01-28 | 2026-03-05 | 2026-03-13 | Meter technician |  | 67.04 | Completed | No
WO-26-000957 | 0.5 | Bayou | BY-S27-04 | Meter exchange | P3 within 10 days | 2026-01-28 | 2026-02-04 | 2026-02-04 | Meter technician |  | 115.94 | Completed | No
WO-26-000958 | 1.4 | Bayou | BY-S06-01 | Meter exchange | P4 planned | 2026-01-28 | 2026-02-20 | 2026-02-20 | Meter technician |  | 86.9 | Completed | No
WO-26-000959 | 0.9 | Bayou | BY-S16-02 | Meter exchange | P4 planned | 2026-01-28 | 2026-02-25 | 2026-02-25 | Meter technician |  | 125.27 | Completed | No
WO-26-000960 | 11.5 | Bayou | BY-S12-03 | Pole replacement | P3 within 10 days | 2026-01-28 | 2026-01-30 | 2026-01-30 | Contract line | CT-03 | 2563.27 | Completed | No
WO-26-000961 | 1.4 | Bayou | BY-S21-05 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-02-02 | 2026-02-02 | Meter technician |  | 29.32 | Completed | No
WO-26-000962 | 1.2 | Bayou | BY-S15-03 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-01-29 | 2026-01-29 | Meter technician |  | 4.13 | Completed | No
WO-26-000963 | 1.4 | Bayou | BY-S26-05 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-02-01 | 2026-02-01 | Meter technician |  | 38.78 | Completed | No
WO-26-000964 | 1.3 | Bayou | BY-S17-02 | Service order - field | P2 same day | 2026-01-28 | 2026-01-29 | 2026-01-29 | Meter technician |  | 30.54 | Completed | No
WO-26-000965 | 1.1 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-01-31 | 2026-02-02 | Meter technician |  | 39.13 | Completed | No
WO-26-000966 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-28 | 2026-02-07 | 2026-02-08 | Contract line | CT-04 | 271.16 | Completed | No
WO-26-000967 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-28 | 2026-02-01 | 2026-02-01 | Internal line |  | 379.87 | Completed | No
WO-26-000968 | 10.3 | Bayou | BY-S27-05 | Transformer replacement | P2 same day | 2026-01-28 | 2026-01-28 | 2026-01-28 | Internal line |  | 12270.88 | Completed | No
WO-26-000969 | 2.3 | Bayou | BY-S17-03 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 208.47 | Completed | No
WO-26-000970 | 2.3 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 52.49 | Completed | No
WO-26-000971 | 4.2 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 314.07 | Completed | No
WO-26-000972 | 3.4 | Bayou | BY-S07-04 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 341.11 | Completed | No
WO-26-000973 | 2.5 | Bayou | BY-S22-04 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 337.33 | Completed | No
WO-26-000974 | 4.9 | Bayou | BY-S18-06 | Trouble - partial or voltage | P3 within 10 days | 2026-01-28 | 2026-02-07 | 2026-02-08 | Troubleman |  | 111.16 | Completed | No
WO-26-000975 | 4.8 | Bayou | BY-S23-05 | Trouble - partial or voltage | P2 same day | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 199.92 | Completed | No
WO-26-000976 | 7.1 | Crossroads | CR-S02-05 | Corrective maintenance | P4 planned | 2026-01-28 | 2026-02-12 | 2026-02-16 | Internal line |  | 1220.39 | Completed | No
WO-26-000977 | 11.3 | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-01-28 | 2026-02-03 | 2026-02-05 | Internal line |  | 1130.49 | Completed | No
WO-26-000978 | 4.7 | Crossroads | CR-S24-02 | Corrective maintenance | P3 within 10 days | 2026-01-28 | 2026-01-30 | 2026-02-03 | Underground crew |  | 1625.7 | Completed | No
WO-26-000979 | 5.6 | Crossroads | CR-S30-03 | Corrective maintenance | P3 within 10 days | 2026-01-28 | 2026-02-06 | 2026-02-10 | Internal line |  | 1754.84 | Completed | No
WO-26-000980 | 1.4 | Crossroads | CR-S13-06 | Meter exchange | P3 within 10 days | 2026-01-28 | 2026-02-07 | 2026-02-15 | Meter technician |  | 143.44 | Completed | No
WO-26-000981 | 1.2 | Crossroads | CR-S22-03 | Meter exchange | P4 planned | 2026-01-28 | 2026-03-22 | 2026-03-24 | Meter technician |  | 126.9 | Completed | No
WO-26-000982 | 0.6 | Crossroads | CR-S09-05 | Meter exchange | P4 planned | 2026-01-28 | 2026-02-08 | 2026-02-08 | Meter technician |  | 65.33 | Completed | No
WO-26-000983 | 9 | Crossroads | CR-S14-02 | New service - small | P4 planned | 2026-01-28 | 2026-03-20 | 2026-03-24 | Underground crew |  | 2509.41 | Completed | No
WO-26-000984 | 5.3 | Crossroads | CR-S30-06 | Preventive maintenance | P4 planned | 2026-01-28 | 2026-02-23 | 2026-02-25 | Internal line |  | 181.82 | Completed | No
WO-26-000985 | 4.6 | Crossroads | CR-S09-01 | Preventive maintenance | P4 planned | 2026-01-28 | 2026-03-10 | 2026-03-10 | Contract line | CT-01 | 526.08 | Completed | No
WO-26-000986 | 0.9 | Crossroads | CR-S07-02 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-01-30 | 2026-01-30 | Meter technician |  | 30.42 | Completed | No
WO-26-000987 | 1.1 | Crossroads | CR-S25-04 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-02-07 | 2026-02-15 | Meter technician |  | 32.55 | Completed | No
WO-26-000988 | 1.3 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-01-28 | 2026-02-02 | 2026-02-04 | Meter technician |  | 16.53 | Completed | No
WO-26-000989 | 1.9 | Crossroads | CR-S11-02 | Service order - field | P2 same day | 2026-01-28 | 2026-01-29 | 2026-01-29 | Meter technician |  | 5.81 | Completed | No
WO-26-000990 | 2.9 | Crossroads |  | Streetlight | P4 planned | 2026-01-28 | 2026-03-05 | 2026-03-06 | Contract line | CT-01 | 215.91 | Completed | No
WO-26-000991 | 8.2 | Crossroads | CR-S13-04 | Transformer replacement | P3 within 10 days | 2026-01-28 | 2026-02-04 | 2026-02-04 | Internal line |  | 7158.31 | Completed | No
WO-26-000992 | 3.6 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 279.2 | Completed | No
WO-26-000993 | 4.1 | Crossroads | CR-S04-04 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 236.79 | Completed | No
WO-26-000994 | 3.4 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-01-28 | 2026-01-28 | 2026-01-28 | Troubleman |  | 327.5 | Completed | No
WO-26-000995 | 2.3 | Crossroads | CR-S18-02 | Trouble - partial or voltage | P2 same day | 2026-01-28 | 2026-01-29 | 2026-01-29 | Troubleman |  | 168.87 | Completed | No
WO-26-000996 | 0.6 | Bayou | BY-S08-03 | Meter exchange | P3 within 10 days | 2026-01-29 | 2026-01-31 | 2026-02-01 | Meter technician |  | 177.46 | Completed | No
WO-26-000997 | 15.9 | Bayou | BY-S16-04 | New service - small | P3 within 10 days | 2026-01-29 | 2026-02-07 | 2026-02-07 | Contract line | CT-03 | 833.47 | Completed | No
WO-26-000998 | 9 | Bayou | BY-S23-03 | New service - small | P4 planned | 2026-01-29 | 2026-03-11 | 2026-03-11 | Internal line |  | 4186.9 | Completed | No
WO-26-000999 | 12.8 | Bayou | BY-S12-04 | New service - small | P4 planned | 2026-01-29 | 2026-03-03 | 2026-03-05 | Underground crew |  | 1834.36 | Completed | No
WO-26-001000 | 15.9 | Bayou | BY-S16-05 | Pole replacement | P3 within 10 days | 2026-01-29 | 2026-02-06 | 2026-02-08 | Internal line |  | 1677.63 | Completed | No
WO-26-001001 | 12.4 | Bayou | BY-S03-02 | Pole replacement | P4 planned | 2026-01-29 | 2026-03-22 | 2026-03-30 | Contract line | CT-04 | 2077.09 | Completed | No
WO-26-001002 | 12.4 | Bayou | BY-S07-06 | Pole replacement | P3 within 10 days | 2026-01-29 | 2026-02-08 | 2026-02-09 | Internal line |  | 2116.28 | Completed | No
WO-26-001003 | 5.2 | Bayou | BY-S26-04 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-03-24 | 2026-03-25 | Contract line | CT-04 | 364.96 | Completed | No
WO-26-001004 | 6.8 | Bayou | BY-S09-05 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-02-28 | 2026-03-02 | Internal line |  | 174.78 | Completed | No
WO-26-001005 | 7.2 | Bayou | BY-S23-04 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-02-14 | 2026-02-18 | Underground crew |  | 7.03 | Completed | No
WO-26-001006 | 3.6 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-02-10 | 2026-02-11 | Internal line |  | 193.4 | Completed | No
WO-26-001007 | 0.9 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-01-29 | 2026-01-30 | 2026-01-30 | Meter technician |  | 9.59 | Completed | No
WO-26-001008 | 1.9 | Bayou | BY-S05-02 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 11.86 | Completed | No
WO-26-001009 | 1.8 | Bayou | BY-S19-02 | Service order - field | P3 within 10 days | 2026-01-29 | 2026-01-31 | 2026-01-31 | Meter technician |  | 21.78 | Completed | No
WO-26-001010 | 0.9 | Bayou | BY-S13-04 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 22.83 | Completed | No
WO-26-001011 | 1.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-01-29 | 2026-02-03 | 2026-02-07 | Internal line |  | 218.76 | Completed | No
WO-26-001012 | 1.9 | Bayou |  | Streetlight | P4 planned | 2026-01-29 | 2026-03-30 | 2026-03-30 | Contract line | CT-03 | 428.94 | Completed | No
WO-26-001013 | 2.7 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-01-29 | 2026-01-29 | 2026-01-29 | Internal line |  | 179.86 | Completed | No
WO-26-001014 | 4 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Underground crew |  | 1589.99 | Completed | No
WO-26-001015 | 9.6 | Crossroads | CR-S14-05 | Corrective maintenance | P3 within 10 days | 2026-01-29 | 2026-02-01 | 2026-02-03 | Contract line | CT-02 | 1235.48 | Completed | No
WO-26-001016 | 3.8 | Crossroads | CR-S28-04 | Corrective maintenance | P3 within 10 days | 2026-01-29 | 2026-02-05 | 2026-02-05 | Contract line | CT-01 | 207.4 | Completed | No
WO-26-001017 | 7.7 | Crossroads | CR-S04-01 | Corrective maintenance | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Contract line | CT-01 | 890.42 | Completed | No
WO-26-001018 | 10.7 | Crossroads | CR-S07-01 | Corrective maintenance | P3 within 10 days | 2026-01-29 | 2026-02-03 | 2026-02-04 | Underground crew |  | 2336.44 | Completed | No
WO-26-001019 | 1.3 | Crossroads | CR-S21-03 | Meter exchange | P4 planned | 2026-01-29 | 2026-02-22 | 2026-02-22 | Meter technician |  | 75.13 | Completed | No
WO-26-001020 | 14.3 | Crossroads | CR-S22-01 | New service - small | P4 planned | 2026-01-29 | 2026-02-27 | 2026-03-03 | Contract line | CT-02 | 1895.9 | Completed | No
WO-26-001021 | 10.5 | Crossroads | CR-S17-01 | New service - small | P3 within 10 days | 2026-01-29 | 2026-02-06 | 2026-02-06 | Contract line | CT-01 | 438.13 | Completed | No
WO-26-001022 | 4.1 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-03-20 | 2026-03-21 | Underground crew |  | 65.4 | Completed | No
WO-26-001023 | 2 | Crossroads | CR-S19-01 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-03-01 | 2026-03-01 | Internal line |  | 214.25 | Completed | No
WO-26-001024 | 2.1 | Crossroads | CR-S19-03 | Preventive maintenance | P4 planned | 2026-01-29 | 2026-02-09 | 2026-02-11 | Underground crew |  | 364.48 | Completed | No
WO-26-001025 | 1.5 | Crossroads | CR-S19-02 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 36.34 | Completed | No
WO-26-001026 | 1.7 | Crossroads | CR-S18-04 | Service order - field | P3 within 10 days | 2026-01-29 | 2026-02-01 | 2026-02-03 | Meter technician |  | 12.11 | Completed | No
WO-26-001027 | 1.6 | Crossroads | CR-S13-03 | Service order - field | P3 within 10 days | 2026-01-29 | 2026-02-01 | 2026-02-09 | Meter technician |  | 29.24 | Completed | No
WO-26-001028 | 1.2 | Crossroads | CR-S21-01 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 16.4 | Completed | No
WO-26-001029 | 0.9 | Crossroads | CR-S24-02 | Service order - field | P3 within 10 days | 2026-01-29 | 2026-02-07 | 2026-02-08 | Meter technician |  | 3.52 | Completed | No
WO-26-001030 |  | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-01-29 | 2026-01-30 |  | Meter technician |  |  | Cancelled | No
WO-26-001031 | 0.5 | Crossroads | CR-S13-05 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 20.95 | Completed | No
WO-26-001032 | 1.3 | Crossroads | CR-S05-06 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 15.41 | Completed | No
WO-26-001033 | 1.8 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 32.7 | Completed | No
WO-26-001034 | 1.9 | Crossroads | CR-S02-05 | Service order - field | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Meter technician |  | 35.9 | Completed | No
WO-26-001035 | 1 | Crossroads | CR-S31-03 | Service order - field | P3 within 10 days | 2026-01-29 | 2026-01-31 | 2026-01-31 | Meter technician |  | 35.07 | Completed | No
WO-26-001036 | 2 | Crossroads |  | Streetlight | P4 planned | 2026-01-29 | 2026-03-20 | 2026-03-28 | Contract line | CT-01 | 311.28 | Completed | No
WO-26-001037 | 12.8 | Crossroads | CR-S11-01 | Transformer replacement | P1 emergency | 2026-01-29 | 2026-01-29 | 2026-01-29 | Internal line |  | 4621.87 | Completed | No
WO-26-001038 | 2.6 | Crossroads | CR-S14-03 | Trouble - no power | P1 emergency | 2026-01-29 | 2026-01-29 | 2026-01-29 | Troubleman |  | 4.63 | Completed | No
WO-26-001039 | 5.2 | Crossroads | CR-S12-01 | Trouble - no power | P2 same day | 2026-01-29 | 2026-01-29 | 2026-01-29 | Internal line |  | 223.16 | Completed | No
WO-26-001040 | 5.1 | Crossroads | CR-S09-03 | Trouble - no power | P1 emergency | 2026-01-29 | 2026-01-29 | 2026-01-29 | Internal line |  | 125.35 | Completed | No
WO-26-001041 | 2.4 | Crossroads | CR-S23-02 | Trouble - partial or voltage | P2 same day | 2026-01-29 | 2026-01-30 | 2026-01-30 | Troubleman |  | 210.65 | Completed | No
WO-26-001042 | 4.5 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-29 | 2026-02-03 | 2026-02-05 | Troubleman |  | 135.53 | Completed | No
WO-26-001043 | 3.4 | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-01-30 | 2026-02-08 | 2026-02-12 | Internal line |  | 173.02 | Completed | No
WO-26-001044 | 0.6 | Bayou | BY-S19-02 | Meter exchange | P4 planned | 2026-01-30 | 2026-03-02 | 2026-03-02 | Meter technician |  | 96.6 | Completed | No
WO-26-001045 | 4.6 | Bayou | BY-S15-06 | New service - small | P4 planned | 2026-01-30 | 2026-03-10 | 2026-03-18 | Contract line | CT-03 | 2893.16 | Completed | No
WO-26-001046 | 11.9 | Bayou | BY-S12-01 | Pole replacement | P4 planned | 2026-01-30 | 2026-03-20 | 2026-03-20 | Internal line |  | 3286.18 | Completed | No
WO-26-001047 | 0.6 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Meter technician |  | 27.73 | Completed | No
WO-26-001048 | 1.3 | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Meter technician |  | 28.43 | Completed | No
WO-26-001049 | 1.7 | Bayou | BY-S26-04 | Service order - field | P3 within 10 days | 2026-01-30 | 2026-02-08 | 2026-02-08 | Meter technician |  | 39.02 | Completed | No
WO-26-001050 | 1.4 | Bayou | BY-S04-01 | Service order - field | P3 within 10 days | 2026-01-30 | 2026-02-03 | 2026-02-03 | Meter technician |  | 15.35 | Completed | No
WO-26-001051 | 1 | Bayou | BY-S26-05 | Service order - field | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Meter technician |  | 14.41 | Completed | No
WO-26-001052 | 6.3 | Bayou | BY-S15-02 | Transformer replacement | P1 emergency | 2026-01-30 | 2026-01-30 | 2026-01-30 | Internal line |  | 4543.27 | Completed | No
WO-26-001053 | 6.5 | Bayou | BY-S10-05 | Transformer replacement | P3 within 10 days | 2026-01-30 | 2026-02-03 | 2026-02-05 | Contract line | CT-04 | 3965.68 | Completed | No
WO-26-001054 | 4.7 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 337.08 | Completed | No
WO-26-001055 | 5.1 | Bayou | BY-S25-05 | Trouble - no power | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Internal line |  | 61.88 | Completed | No
WO-26-001056 | 6 | Bayou | BY-S07-02 | Trouble - no power | P1 emergency | 2026-01-30 | 2026-01-30 | 2026-01-30 | Internal line |  | 53.12 | Completed | No
WO-26-001057 | 3.4 | Bayou | BY-S04-03 | Trouble - no power | P1 emergency | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 216.42 | Completed | No
WO-26-001058 | 3.5 | Bayou | BY-S26-06 | Trouble - no power | P1 emergency | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 140.5 | Completed | No
WO-26-001059 | 2.6 | Bayou | BY-S26-04 | Trouble - partial or voltage | P2 same day | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 84.5 | Completed | No
WO-26-001060 | 1.8 | Bayou | BY-S24-04 | Trouble - partial or voltage | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Troubleman |  | 156.69 | Completed | No
WO-26-001061 | 2.5 | Bayou | BY-S29-01 | Trouble - partial or voltage | P3 within 10 days | 2026-01-30 | 2026-02-06 | 2026-02-06 | Troubleman |  | 124.18 | Completed | No
WO-26-001062 | 4.2 | Bayou | BY-S07-01 | Trouble - partial or voltage | P2 same day | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 10.02 | Completed | No
WO-26-001063 | 11.4 | Crossroads | CR-S04-01 | Corrective maintenance | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Internal line |  | 1670.27 | Completed | No
WO-26-001064 | 3.4 | Crossroads | CR-S09-04 | Corrective maintenance | P3 within 10 days | 2026-01-30 | 2026-02-07 | 2026-02-08 | Contract line | CT-02 | 2227.35 | Completed | No
WO-26-001065 | 7.5 | Crossroads | CR-S11-02 | Corrective maintenance | P4 planned | 2026-01-30 | 2026-03-05 | 2026-03-05 | Internal line |  | 1255.05 | Completed | No
WO-26-001066 | 7.3 | Crossroads | CR-S24-02 | Corrective maintenance | P3 within 10 days | 2026-01-30 | 2026-02-05 | 2026-02-05 | Underground crew |  | 2040.96 | Completed | No
WO-26-001067 | 9.2 | Crossroads | CR-S09-05 | Corrective maintenance | P3 within 10 days | 2026-01-30 | 2026-02-05 | 2026-02-05 | Underground crew |  | 1638.73 | Completed | No
WO-26-001068 | 1.4 | Crossroads | CR-S05-06 | Meter exchange | P4 planned | 2026-01-30 | 2026-03-28 | 2026-03-28 | Meter technician |  | 108.63 | Completed | No
WO-26-001069 | 1.4 | Crossroads | CR-S05-06 | Meter exchange | P3 within 10 days | 2026-01-30 | 2026-02-08 | 2026-02-08 | Meter technician |  | 108.63 | Completed | No
WO-26-001070 | 13.8 | Crossroads | CR-S02-05 | Pole replacement | P3 within 10 days | 2026-01-30 | 2026-02-07 | 2026-02-09 | Contract line | CT-02 | 3096.06 | Completed | No
WO-26-001071 | 6.9 | Crossroads | CR-S27-04 | Preventive maintenance | P4 planned | 2026-01-30 | 2026-03-04 | 2026-03-06 | Underground crew |  | 401.52 | Completed | No
WO-26-001072 | 6.6 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-01-30 | 2026-02-13 | 2026-02-13 | Internal line |  | 427.97 | Completed | No
WO-26-001073 | 6 | Crossroads | CR-S25-01 | Preventive maintenance | P4 planned | 2026-01-30 | 2026-03-09 | 2026-03-09 | Underground crew |  | 418.73 | Completed | No
WO-26-001074 | 2.4 | Crossroads | CR-S23-02 | Preventive maintenance | P4 planned | 2026-01-30 | 2026-02-14 | 2026-02-14 | Internal line |  | 449.25 | Completed | No
WO-26-001075 | 1.9 | Crossroads | CR-S24-04 | Service order - field | P3 within 10 days | 2026-01-30 | 2026-02-03 | 2026-02-07 | Meter technician |  | 10.75 | Completed | No
WO-26-001076 | 1.9 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-01-30 | 2026-02-07 | 2026-02-09 | Meter technician |  | 0.01 | Completed | No
WO-26-001077 | 1 | Crossroads | CR-S07-07 | Service order - field | P2 same day | 2026-01-30 | 2026-01-30 | 2026-01-30 | Meter technician |  | 15.15 | Completed | No
WO-26-001078 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-01-30 | 2026-02-07 | 2026-02-15 | Contract line | CT-02 | 265.03 | Completed | No
WO-26-001079 | 1.2 | Crossroads |  | Streetlight | P4 planned | 2026-01-30 | 2026-03-12 | 2026-03-12 | Contract line | CT-01 | 86.23 | Completed | No
WO-26-001080 | 2.6 | Crossroads | CR-S28-04 | Trouble - no power | P2 same day | 2026-01-30 | 2026-01-31 | 2026-01-31 | Troubleman |  | 12.09 | Completed | No
WO-26-001081 | 2.5 | Crossroads | CR-S30-03 | Trouble - no power | P2 same day | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 97.61 | Completed | No
WO-26-001082 | 2.4 | Crossroads | CR-S24-03 | Trouble - no power | P1 emergency | 2026-01-30 | 2026-01-30 | 2026-01-30 | Troubleman |  | 232.98 | Completed | No
WO-26-001083 | 21.7 | Bayou | BY-S29-02 | Pole replacement | P2 same day | 2026-01-31 | 2026-01-31 | 2026-01-31 | Contract line | CT-04 | 2290.65 | Completed | No
WO-26-001084 | 0.7 | Bayou | BY-S10-04 | Service order - field | P2 same day | 2026-01-31 | 2026-01-31 | 2026-01-31 | Meter technician |  | 29.76 | Completed | No
WO-26-001085 | 1.3 | Bayou | BY-S27-01 | Service order - field | P2 same day | 2026-01-31 | 2026-02-01 | 2026-02-01 | Meter technician |  | 13.62 | Completed | No
WO-26-001086 |  | Bayou | BY-S16-04 | Transformer replacement | P1 emergency | 2026-01-31 | 2026-01-31 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-001087 | 8.5 | Bayou | BY-S26-02 | Transformer replacement | P2 same day | 2026-01-31 | 2026-02-01 | 2026-02-01 | Contract line | CT-03 | 8091.64 | Completed | No
WO-26-001088 | 4.3 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-01-31 | 2026-01-31 | 2026-01-31 | Troubleman |  | 91.32 | Completed | No
WO-26-001089 | 3.9 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-01-31 | 2026-01-31 | 2026-01-31 | Internal line |  | 317.91 | Completed | No
WO-26-001090 | 5.5 | Bayou | BY-S25-01 | Trouble - no power | P2 same day | 2026-01-31 | 2026-01-31 | 2026-01-31 | Troubleman |  | 198.91 | Completed | No
WO-26-001091 | 11.3 | Crossroads | CR-S16-02 | Pole replacement | P2 same day | 2026-01-31 | 2026-01-31 | 2026-01-31 | Contract line | CT-01 | 2764.99 | Completed | No
WO-26-001092 | 2 | Crossroads | CR-S08-03 | Service order - field | P2 same day | 2026-01-31 | 2026-02-01 | 2026-02-01 | Meter technician |  | 6.79 | Completed | No
WO-26-001093 | 2 | Crossroads | CR-S19-04 | Service order - field | P2 same day | 2026-01-31 | 2026-01-31 | 2026-01-31 | Meter technician |  | 4.36 | Completed | No
WO-26-001094 | 3.3 | Crossroads | CR-S29-01 | Trouble - no power | P2 same day | 2026-01-31 | 2026-02-01 | 2026-02-01 | Internal line |  | 172.16 | Completed | No
WO-26-001095 | 5.5 | Crossroads | CR-S32-05 | Trouble - no power | P2 same day | 2026-01-31 | 2026-02-01 | 2026-02-01 | Internal line |  | 95.43 | Completed | No
WO-26-001096 | 5.8 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-01-31 | 2026-01-31 | 2026-01-31 | Troubleman |  | 285.2 | Completed | No
WO-26-001097 | 2 | Crossroads | CR-S26-02 | Trouble - partial or voltage | P2 same day | 2026-01-31 | 2026-02-01 | 2026-02-01 | Troubleman |  | 104.16 | Completed | No
WO-26-001098 | 10.6 | Bayou | BY-S21-03 | Corrective maintenance | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Contract line | CT-03 | 1834.28 | Completed | No
WO-26-001099 | 10.4 | Bayou | BY-S24-05 | Pole replacement | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Contract line | CT-03 | 2408.11 | Completed | No
WO-26-001100 | 1.2 | Bayou | BY-S25-05 | Service order - field | P2 same day | 2026-02-01 | 2026-02-02 | 2026-02-02 | Meter technician |  | 24.46 | Completed | No
WO-26-001101 | 12.2 | Bayou | BY-S25-05 | Transformer replacement | P2 same day | 2026-02-01 | 2026-02-02 | 2026-02-02 | Internal line |  | 5848.67 | Completed | No
WO-26-001102 | 3.6 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 10 | Completed | No
WO-26-001103 | 5.4 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 340.28 | Completed | No
WO-26-001104 |  | Bayou | BY-S10-04 | Trouble - no power | P1 emergency | 2026-02-01 | 2026-02-01 |  | Troubleman |  |  | Cancelled | No
WO-26-001105 | 2 | Bayou | BY-S21-05 | Trouble - partial or voltage | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 41.16 | Completed | No
WO-26-001106 | 3 | Bayou | BY-S24-01 | Trouble - partial or voltage | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 38 | Completed | No
WO-26-001107 | 1.5 | Crossroads | CR-S29-01 | Service order - field | P2 same day | 2026-02-01 | 2026-02-02 | 2026-02-02 | Meter technician |  | 19.58 | Completed | No
WO-26-001108 | 1 | Crossroads | CR-S24-01 | Service order - field | P2 same day | 2026-02-01 | 2026-02-02 | 2026-02-02 | Meter technician |  | 1.39 | Completed | No
WO-26-001109 | 1.4 | Crossroads | CR-S22-01 | Service order - field | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Meter technician |  | 34.73 | Completed | No
WO-26-001110 | 0.8 | Crossroads | CR-S29-03 | Service order - field | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Meter technician |  | 6.98 | Completed | No
WO-26-001111 | 1.4 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-02-01 | 2026-02-02 | 2026-02-02 | Meter technician |  | 14.43 | Completed | No
WO-26-001112 | 6.2 | Crossroads | CR-S02-01 | Transformer replacement | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Internal line |  | 5452.68 | Completed | No
WO-26-001113 | 5.7 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 282.41 | Completed | No
WO-26-001114 | 3 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 172.07 | Completed | No
WO-26-001115 | 2.1 | Crossroads | CR-S18-02 | Trouble - no power | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Troubleman |  | 171.21 | Completed | No
WO-26-001116 |  | Crossroads | CR-S11-02 | Trouble - no power | P2 same day | 2026-02-01 | 2026-02-02 |  | Internal line |  |  | Cancelled | No
WO-26-001117 | 2.2 | Crossroads | CR-S30-02 | Trouble - no power | P2 same day | 2026-02-01 | 2026-02-01 | 2026-02-01 | Internal line |  | 176.47 | Completed | No
WO-26-001118 | 4.2 | Crossroads | CR-S01-03 | Trouble - partial or voltage | P2 same day | 2026-02-01 | 2026-02-02 | 2026-02-02 | Troubleman |  | 114.4 | Completed | No
WO-26-001119 | 10.6 | Bayou | BY-S09-01 | Corrective maintenance | P2 same day | 2026-02-02 | 2026-02-03 | 2026-02-03 | Underground crew |  | 308.3 | Completed | No
WO-26-001120 | 9.8 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-02-02 | 2026-02-05 | 2026-02-06 | Internal line |  | 497.55 | Completed | No
WO-26-001121 | 12.2 | Bayou | BY-S16-03 | New service - small | P4 planned | 2026-02-02 | 2026-03-06 | 2026-03-07 | Underground crew |  | 4070.65 | Completed | No
WO-26-001122 | 19.2 | Bayou | BY-S15-04 | Pole replacement | P4 planned | 2026-02-02 | 2026-03-16 | 2026-03-16 | Contract line | CT-03 | 1667.65 | Completed | No
WO-26-001123 | 11.4 | Bayou | BY-S16-01 | Pole replacement | P4 planned | 2026-02-02 | 2026-03-03 | 2026-03-03 | Contract line | CT-04 | 2854.24 | Completed | No
WO-26-001124 | 4.2 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-02-02 | 2026-02-19 | 2026-02-27 | Contract line | CT-04 | 174.05 | Completed | No
WO-26-001125 | 4.4 | Bayou | BY-S29-04 | Preventive maintenance | P4 planned | 2026-02-02 | 2026-03-26 | 2026-03-27 | Internal line |  | 258.88 | Completed | No
WO-26-001126 | 0.6 | Bayou | BY-S19-02 | Service order - field | P3 within 10 days | 2026-02-02 | 2026-02-11 | 2026-02-12 | Meter technician |  | 18.6 | Completed | No
WO-26-001127 | 1.4 | Bayou | BY-S13-05 | Service order - field | P3 within 10 days | 2026-02-02 | 2026-02-09 | 2026-02-09 | Meter technician |  | 30.33 | Completed | No
WO-26-001128 | 1.1 | Bayou | BY-S18-03 | Service order - field | P2 same day | 2026-02-02 | 2026-02-03 | 2026-02-03 | Meter technician |  | 18.38 | Completed | No
WO-26-001129 | 1.9 | Bayou | BY-S07-02 | Service order - field | P2 same day | 2026-02-02 | 2026-02-03 | 2026-02-03 | Meter technician |  | 14 | Completed | No
WO-26-001130 | 1.9 | Bayou | BY-S21-01 | Service order - field | P2 same day | 2026-02-02 | 2026-02-02 | 2026-02-02 | Meter technician |  | 0.07 | Completed | No
WO-26-001131 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-02 | 2026-02-11 | 2026-02-11 | Contract line | CT-03 | 331.98 | Completed | No
WO-26-001132 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-02 | 2026-02-12 | 2026-02-16 | Internal line |  | 335.32 | Completed | No
WO-26-001133 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-02 | 2026-02-10 | 2026-02-11 | Internal line |  | 185.28 | Completed | No
WO-26-001134 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-02 | 2026-02-10 | 2026-02-10 | Contract line | CT-04 | 78.14 | Completed | No
WO-26-001135 | 2.8 | Bayou |  | Streetlight | P4 planned | 2026-02-02 | 2026-03-01 | 2026-03-03 | Contract line | CT-04 | 259.78 | Completed | No
WO-26-001136 | 13.1 | Bayou | BY-S12-02 | Transformer replacement | P3 within 10 days | 2026-02-02 | 2026-02-12 | 2026-02-20 | Internal line |  | 9002.16 | Completed | No
WO-26-001137 | 5.9 | Bayou | BY-S11-01 | Trouble - no power | P2 same day | 2026-02-02 | 2026-02-02 | 2026-02-02 | Internal line |  | 298.9 | Completed | No
WO-26-001138 | 4.5 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-02-02 | 2026-02-02 | 2026-02-02 | Troubleman |  | 30.03 | Completed | No
WO-26-001139 | 2.3 | Bayou | BY-S27-01 | Trouble - no power | P1 emergency | 2026-02-02 | 2026-02-02 | 2026-02-02 | Troubleman |  | 280.57 | Completed | No
WO-26-001140 | 1.8 | Bayou | BY-S01-01 | Trouble - partial or voltage | P2 same day | 2026-02-02 | 2026-02-02 | 2026-02-02 | Troubleman |  | 235.98 | Completed | No
WO-26-001141 | 2.5 | Bayou | BY-S08-02 | Trouble - partial or voltage | P3 within 10 days | 2026-02-02 | 2026-02-06 | 2026-02-10 | Troubleman |  | 108.01 | Completed | No
WO-26-001142 | 11.4 | Crossroads | CR-S15-03 | Corrective maintenance | P3 within 10 days | 2026-02-02 | 2026-02-06 | 2026-02-06 | Underground crew |  | 1341.16 | Completed | No
WO-26-001143 | 8.3 | Crossroads | CR-S02-01 | Corrective maintenance | P4 planned | 2026-02-02 | 2026-03-27 | 2026-03-27 | Contract line | CT-02 | 564.57 | Completed | No
WO-26-001144 | 3.4 | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-02-02 | 2026-02-06 | 2026-02-10 | Contract line | CT-02 | 1301.36 | Completed | No
WO-26-001145 | 5.2 | Crossroads | CR-S28-03 | Corrective maintenance | P2 same day | 2026-02-02 | 2026-02-02 | 2026-02-02 | Internal line |  | 1380.81 | Completed | No
WO-26-001146 | 0.9 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-02-02 | 2026-02-04 | 2026-02-04 | Meter technician |  | 161.88 | Completed | No
WO-26-001147 | 0.8 | Crossroads | CR-S15-02 | Meter exchange | P3 within 10 days | 2026-02-02 | 2026-02-04 | 2026-02-06 | Meter technician |  | 93.6 | Completed | No
WO-26-001148 | 13.7 | Crossroads | CR-S18-03 | New service - small | P4 planned | 2026-02-02 | 2026-03-31 | 2026-04-02 | Internal line |  | 1648.2 | Completed | No
WO-26-001149 | 6.7 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-02-02 | 2026-02-20 | 2026-02-20 | Underground crew |  | 305.38 | Completed | No
WO-26-001150 | 7.2 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-02-02 | 2026-03-16 | 2026-03-17 | Contract line | CT-02 | 258.88 | Completed | No
WO-26-001151 |  | Crossroads | CR-S27-03 | Service order - field | P3 within 10 days | 2026-02-02 | 2026-02-05 |  | Meter technician |  |  | Cancelled | No
WO-26-001152 | 1.2 | Crossroads | CR-S13-05 | Service order - field | P2 same day | 2026-02-02 | 2026-02-02 | 2026-02-02 | Meter technician |  | 20.7 | Completed | No
WO-26-001153 | 2.6 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-02-02 | 2026-02-02 | 2026-02-02 | Troubleman |  | 244.17 | Completed | No
WO-26-001154 | 4.9 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-02-02 | 2026-02-02 | 2026-02-02 | Troubleman |  | 95.31 | Completed | No
WO-26-001155 | 4.9 | Crossroads | CR-S16-04 | Trouble - partial or voltage | P3 within 10 days | 2026-02-02 | 2026-02-10 | 2026-02-10 | Internal line |  | 90.89 | Completed | No
WO-26-001156 | 3.3 | Crossroads | CR-S12-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-02 | 2026-02-11 | 2026-02-11 | Troubleman |  | 117.94 | Completed | No
WO-26-001157 | 1.6 | Crossroads | CR-S12-02 | Trouble - partial or voltage | P2 same day | 2026-02-02 | 2026-02-02 | 2026-02-02 | Troubleman |  | 117.94 | Completed | No
WO-26-001158 | 1.8 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P2 same day | 2026-02-02 | 2026-02-03 | 2026-02-03 | Troubleman |  | 139.01 | Completed | No
WO-26-001159 | 4.9 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-02 | 2026-02-08 | 2026-02-09 | Troubleman |  | 73.53 | Completed | No
WO-26-001160 | 5.3 | Bayou | BY-S24-05 | Corrective maintenance | P2 same day | 2026-02-03 | 2026-02-04 | 2026-02-04 | Internal line |  | 1653.46 | Completed | No
WO-26-001161 | 8.8 | Bayou | BY-S13-02 | Corrective maintenance | P3 within 10 days | 2026-02-03 | 2026-02-12 | 2026-02-12 | Contract line | CT-04 | 1003.39 | Completed | No
WO-26-001162 | 0.8 | Bayou | BY-S04-03 | Meter exchange | P4 planned | 2026-02-03 | 2026-02-13 | 2026-02-13 | Meter technician |  | 76.09 | Completed | No
WO-26-001163 | 0.9 | Bayou | BY-S26-03 | Meter exchange | P3 within 10 days | 2026-02-03 | 2026-02-04 | 2026-02-04 | Meter technician |  | 99.84 | Completed | No
WO-26-001164 | 0.9 | Bayou | BY-S07-04 | Meter exchange | P3 within 10 days | 2026-02-03 | 2026-02-10 | 2026-02-11 | Meter technician |  | 109.08 | Completed | No
WO-26-001165 | 1.1 | Bayou | BY-S15-06 | Meter exchange | P4 planned | 2026-02-03 | 2026-03-11 | 2026-03-11 | Meter technician |  | 124.82 | Completed | No
WO-26-001166 | 7 | Bayou | BY-S01-01 | New service - small | P3 within 10 days | 2026-02-03 | 2026-02-11 | 2026-02-12 | Contract line | CT-04 | 2691 | Completed | No
WO-26-001167 | 22.3 | Bayou | BY-S14-01 | Pole replacement | P3 within 10 days | 2026-02-03 | 2026-02-04 | 2026-02-04 | Contract line | CT-04 | 1269.38 | Completed | No
WO-26-001168 | 0.6 | Bayou | BY-S01-01 | Service order - field | P3 within 10 days | 2026-02-03 | 2026-02-07 | 2026-02-08 | Meter technician |  | 9.19 | Completed | No
WO-26-001169 | 1 | Bayou | BY-S28-02 | Service order - field | P3 within 10 days | 2026-02-03 | 2026-02-12 | 2026-02-12 | Meter technician |  | 23.02 | Completed | No
WO-26-001170 | 0.9 | Bayou | BY-S14-02 | Service order - field | P2 same day | 2026-02-03 | 2026-02-03 | 2026-02-03 | Meter technician |  | 29.68 | Completed | No
WO-26-001171 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-03 | 2026-02-07 | 2026-02-07 | Contract line | CT-04 | 251.63 | Completed | No
WO-26-001172 | 6.7 | Bayou | BY-S22-01 | Transformer replacement | P2 same day | 2026-02-03 | 2026-02-04 | 2026-02-04 | Contract line | CT-04 | 6457.3 | Completed | No
WO-26-001173 | 2.3 | Bayou | BY-S16-04 | Trouble - no power | P2 same day | 2026-02-03 | 2026-02-03 | 2026-02-03 | Troubleman |  | 142.63 | Completed | No
WO-26-001174 | 3.8 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-02-03 | 2026-02-03 | 2026-02-03 | Troubleman |  | 288.1 | Completed | No
WO-26-001175 | 2.9 | Bayou | BY-S04-03 | Trouble - no power | P1 emergency | 2026-02-03 | 2026-02-03 | 2026-02-03 | Troubleman |  | 265.14 | Completed | No
WO-26-001176 | 2.6 | Bayou | BY-S24-05 | Trouble - no power | P1 emergency | 2026-02-03 | 2026-02-03 | 2026-02-03 | Internal line |  | 103.13 | Completed | No
WO-26-001177 | 2.3 | Bayou | BY-S07-05 | Trouble - partial or voltage | P2 same day | 2026-02-03 | 2026-02-04 | 2026-02-04 | Troubleman |  | 142.21 | Completed | No
WO-26-001178 | 3.4 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-02-03 | 2026-02-04 | 2026-02-04 | Troubleman |  | 217.94 | Completed | No
WO-26-001179 | 8.9 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-02-03 | 2026-02-05 | 2026-02-05 | Underground crew |  | 657.26 | Completed | No
WO-26-001180 | 8.5 | Crossroads | CR-S27-02 | Corrective maintenance | P3 within 10 days | 2026-02-03 | 2026-02-08 | 2026-02-12 | Underground crew |  | 2039.24 | Completed | No
WO-26-001181 | 0.9 | Crossroads | CR-S16-03 | Meter exchange | P3 within 10 days | 2026-02-03 | 2026-02-05 | 2026-02-06 | Meter technician |  | 154.71 | Completed | No
WO-26-001182 | 1.2 | Crossroads | CR-S26-05 | Meter exchange | P3 within 10 days | 2026-02-03 | 2026-02-05 | 2026-02-05 | Meter technician |  | 152.25 | Completed | No
WO-26-001183 | 0.7 | Crossroads | CR-S27-04 | Meter exchange | P4 planned | 2026-02-03 | 2026-02-25 | 2026-02-26 | Meter technician |  | 166.18 | Completed | No
WO-26-001184 | 1 | Crossroads | CR-S17-03 | Service order - field | P3 within 10 days | 2026-02-03 | 2026-02-11 | 2026-02-19 | Meter technician |  | 36.18 | Completed | No
WO-26-001185 | 1.7 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-02-03 | 2026-02-06 | 2026-02-10 | Meter technician |  | 16.01 | Completed | No
WO-26-001186 | 5.3 | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-02-03 | 2026-02-03 | 2026-02-03 | Troubleman |  | 167.87 | Completed | No
WO-26-001187 | 4.4 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-02-03 | 2026-02-03 | 2026-02-03 | Troubleman |  | 168.24 | Completed | No
WO-26-001188 | 2.5 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-02-03 | 2026-02-03 | 2026-02-03 | Internal line |  | 6.78 | Completed | No
WO-26-001189 | 1.9 | Crossroads | CR-S03-03 | Trouble - partial or voltage | P2 same day | 2026-02-03 | 2026-02-03 | 2026-02-03 | Internal line |  | 124.67 | Completed | No
WO-26-001190 | 1.9 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-03 | 2026-02-11 | 2026-02-12 | Troubleman |  | 117.74 | Completed | No
WO-26-001191 | 3.8 | Bayou | BY-S21-04 | Corrective maintenance | P3 within 10 days | 2026-02-04 | 2026-02-09 | 2026-02-09 | Internal line |  | 2375.06 | Completed | No
WO-26-001192 | 0.8 | Bayou | BY-S29-01 | Meter exchange | P3 within 10 days | 2026-02-04 | 2026-02-06 | 2026-02-06 | Meter technician |  | 79.03 | Completed | No
WO-26-001193 | 0.7 | Bayou | BY-S15-06 | Meter exchange | P3 within 10 days | 2026-02-04 | 2026-02-13 | 2026-02-13 | Meter technician |  | 95.48 | Completed | No
WO-26-001194 | 1.5 | Bayou | BY-S16-06 | Meter exchange | P3 within 10 days | 2026-02-04 | 2026-02-06 | 2026-02-06 | Meter technician |  | 143.27 | Completed | No
WO-26-001195 | 0.5 | Bayou | BY-S13-05 | Meter exchange | P4 planned | 2026-02-04 | 2026-03-02 | 2026-03-02 | Meter technician |  | 143.76 | Completed | No
WO-26-001196 | 12 | Bayou | BY-S21-05 | New service - small | P4 planned | 2026-02-04 | 2026-03-14 | 2026-03-14 | Contract line | CT-03 | 2045.81 | Completed | No
WO-26-001197 | 2.9 | Bayou | BY-S20-02 | Preventive maintenance | P4 planned | 2026-02-04 | 2026-04-04 | 2026-04-05 | Underground crew |  | 577.33 | Completed | No
WO-26-001198 | 1.1 | Bayou | BY-S03-02 | Service order - field | P3 within 10 days | 2026-02-04 | 2026-02-12 | 2026-02-12 | Meter technician |  | 31.58 | Completed | No
WO-26-001199 | 1.9 | Bayou | BY-S23-03 | Service order - field | P2 same day | 2026-02-04 | 2026-02-05 | 2026-02-05 | Meter technician |  | 24.85 | Completed | No
WO-26-001200 | 0.5 | Bayou | BY-S12-03 | Service order - field | P3 within 10 days | 2026-02-04 | 2026-02-06 | 2026-02-06 | Meter technician |  | 21.83 | Completed | No
WO-26-001201 | 1.5 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-02-04 | 2026-02-05 | 2026-02-05 | Meter technician |  | 5.06 | Completed | No
WO-26-001202 | 1.1 | Bayou | BY-S18-04 | Service order - field | P2 same day | 2026-02-04 | 2026-02-04 | 2026-02-04 | Meter technician |  | 16.43 | Completed | No
WO-26-001203 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-04 | 2026-02-10 | 2026-02-14 | Contract line | CT-03 | 315.85 | Completed | No
WO-26-001204 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-04 | 2026-02-10 | 2026-02-10 | Contract line | CT-04 | 127.37 | Completed | No
WO-26-001205 | 2.5 | Bayou |  | Streetlight | P4 planned | 2026-02-04 | 2026-02-25 | 2026-02-25 | Contract line | CT-04 | 310.68 | Completed | No
WO-26-001206 | 10.5 | Bayou | BY-S20-01 | Transformer replacement | P3 within 10 days | 2026-02-04 | 2026-02-12 | 2026-02-12 | Contract line | CT-03 | 8135.52 | Completed | No
WO-26-001207 | 3.4 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 126.72 | Completed | No
WO-26-001208 | 2.3 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 8.36 | Completed | No
WO-26-001209 | 2.4 | Bayou | BY-S24-04 | Trouble - no power | P2 same day | 2026-02-04 | 2026-02-05 | 2026-02-05 | Internal line |  | 288.84 | Completed | No
WO-26-001210 | 5 | Bayou | BY-S21-02 | Trouble - no power | P1 emergency | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 242.61 | Completed | No
WO-26-001211 | 7.3 | Crossroads | CR-S08-01 | Corrective maintenance | P2 same day | 2026-02-04 | 2026-02-05 | 2026-02-05 | Internal line |  | 824.58 | Completed | No
WO-26-001212 | 5.8 | Crossroads | CR-S22-02 | Corrective maintenance | P3 within 10 days | 2026-02-04 | 2026-02-09 | 2026-02-09 | Underground crew |  | 417.53 | Completed | No
WO-26-001213 | 4.5 | Crossroads | CR-S24-02 | Corrective maintenance | P3 within 10 days | 2026-02-04 | 2026-02-11 | 2026-02-19 | Internal line |  | 1514.8 | Completed | No
WO-26-001214 | 9.3 | Crossroads | CR-S14-05 | Corrective maintenance | P3 within 10 days | 2026-02-04 | 2026-02-14 | 2026-02-14 | Underground crew |  | 115.48 | Completed | No
WO-26-001215 | 1.3 | Crossroads | CR-S06-02 | Meter exchange | P4 planned | 2026-02-04 | 2026-03-07 | 2026-03-07 | Meter technician |  | 81.61 | Completed | No
WO-26-001216 | 0.5 | Crossroads | CR-S10-02 | Meter exchange | P3 within 10 days | 2026-02-04 | 2026-02-05 | 2026-02-09 | Meter technician |  | 69.58 | Completed | No
WO-26-001217 | 1.2 | Crossroads | CR-S25-01 | Meter exchange | P3 within 10 days | 2026-02-04 | 2026-02-07 | 2026-02-07 | Meter technician |  | 172.28 | Completed | No
WO-26-001218 | 15.5 | Crossroads | CR-S26-03 | Pole replacement | P3 within 10 days | 2026-02-04 | 2026-02-13 | 2026-02-14 | Contract line | CT-01 | 1681.41 | Completed | No
WO-26-001219 | 18.4 | Crossroads | CR-S14-03 | Pole replacement | P3 within 10 days | 2026-02-04 | 2026-02-13 | 2026-02-13 | Internal line |  | 1687.39 | Completed | No
WO-26-001220 | 4.5 | Crossroads | CR-S20-02 | Preventive maintenance | P4 planned | 2026-02-04 | 2026-03-31 | 2026-04-02 | Underground crew |  | 415.11 | Completed | No
WO-26-001221 | 7.1 | Crossroads | CR-S28-04 | Preventive maintenance | P4 planned | 2026-02-04 | 2026-03-01 | 2026-03-01 | Underground crew |  | 240.41 | Completed | No
WO-26-001222 | 2.3 | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-02-04 | 2026-03-24 | 2026-03-24 | Internal line |  | 493.52 | Completed | No
WO-26-001223 | 3.1 | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-02-04 | 2026-04-05 | 2026-04-06 | Underground crew |  | 572.04 | Completed | No
WO-26-001224 | 3.5 | Crossroads | CR-S05-05 | Preventive maintenance | P4 planned | 2026-02-04 | 2026-03-09 | 2026-03-10 | Internal line |  | 44.07 | Completed | No
WO-26-001225 | 1.6 | Crossroads | CR-S32-04 | Service order - field | P3 within 10 days | 2026-02-04 | 2026-02-14 | 2026-02-16 | Meter technician |  | 28.37 | Completed | No
WO-26-001226 | 10.5 | Crossroads | CR-S18-04 | Transformer replacement | P1 emergency | 2026-02-04 | 2026-02-04 | 2026-02-04 | Internal line |  | 8701.97 | Completed | No
WO-26-001227 | 5.4 | Crossroads | CR-S16-01 | Trouble - no power | P1 emergency | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 12.49 | Completed | No
WO-26-001228 | 4.4 | Crossroads | CR-S11-02 | Trouble - no power | P1 emergency | 2026-02-04 | 2026-02-04 | 2026-02-04 | Internal line |  | 67.68 | Completed | No
WO-26-001229 | 5.9 | Crossroads | CR-S19-04 | Trouble - no power | P2 same day | 2026-02-04 | 2026-02-05 | 2026-02-05 | Troubleman |  | 68.35 | Completed | No
WO-26-001230 | 4.7 | Crossroads | CR-S12-03 | Trouble - no power | P2 same day | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 126.17 | Completed | No
WO-26-001231 | 1.6 | Crossroads | CR-S24-04 | Trouble - partial or voltage | P3 within 10 days | 2026-02-04 | 2026-02-09 | 2026-02-09 | Troubleman |  | 162.75 | Completed | No
WO-26-001232 | 4 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 194.28 | Completed | No
WO-26-001233 | 4.6 | Crossroads | CR-S19-04 | Trouble - partial or voltage | P2 same day | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 140.14 | Completed | No
WO-26-001234 | 1.9 | Crossroads | CR-S08-06 | Trouble - partial or voltage | P2 same day | 2026-02-04 | 2026-02-04 | 2026-02-04 | Troubleman |  | 200.24 | Completed | No
WO-26-001235 | 8.5 | Bayou | BY-S11-01 | New service - small | P4 planned | 2026-02-05 | 2026-02-13 | 2026-02-13 | Contract line | CT-03 | 3210.3 | Completed | No
WO-26-001236 | 0.7 | Bayou | BY-S26-06 | Service order - field | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Meter technician |  | 26.92 | Completed | No
WO-26-001237 | 0.6 | Bayou | BY-S29-02 | Service order - field | P3 within 10 days | 2026-02-05 | 2026-02-07 | 2026-02-07 | Meter technician |  | 18.68 | Completed | No
WO-26-001238 | 0.9 | Bayou | BY-S07-05 | Service order - field | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Meter technician |  | 32.31 | Completed | No
WO-26-001239 |  | Bayou | BY-S23-04 | Service order - field | P3 within 10 days | 2026-02-05 | 2026-02-08 |  | Meter technician |  |  | Cancelled | No
WO-26-001240 | 1.7 | Bayou | BY-S25-01 | Service order - field | P3 within 10 days | 2026-02-05 | 2026-02-06 | 2026-02-07 | Meter technician |  | 28.75 | Completed | No
WO-26-001241 | 1.4 | Bayou | BY-S19-03 | Service order - field | P2 same day | 2026-02-05 | 2026-02-06 | 2026-02-06 | Meter technician |  | 6.77 | Completed | No
WO-26-001242 | 7.5 | Bayou | BY-S15-02 | Transformer replacement | P2 same day | 2026-02-05 | 2026-02-06 | 2026-02-06 | Internal line |  | 5961.64 | Completed | No
WO-26-001243 | 6.8 | Bayou | BY-S13-03 | Transformer replacement | P3 within 10 days | 2026-02-05 | 2026-02-06 | 2026-02-14 | Internal line |  | 10016.96 | Completed | No
WO-26-001244 | 4.2 | Bayou | BY-S16-03 | Trouble - no power | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Internal line |  | 157.7 | Completed | No
WO-26-001245 | 3.1 | Bayou | BY-S14-03 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 108.21 | Completed | No
WO-26-001246 | 2.5 | Bayou | BY-S07-06 | Trouble - no power | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 82.63 | Completed | No
WO-26-001247 | 3.4 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 182.68 | Completed | No
WO-26-001248 | 3.6 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 162.93 | Completed | No
WO-26-001249 | 11.8 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-02-05 | 2026-02-06 | 2026-02-06 | Underground crew |  | 1435.11 | Completed | No
WO-26-001250 | 3.3 | Crossroads | CR-S17-01 | Corrective maintenance | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Underground crew |  | 542.58 | Completed | No
WO-26-001251 | 10.6 | Crossroads | CR-S18-05 | Corrective maintenance | P3 within 10 days | 2026-02-05 | 2026-02-15 | 2026-02-15 | Internal line |  | 1005.17 | Completed | No
WO-26-001252 | 3.5 | Crossroads | CR-S15-01 | Corrective maintenance | P4 planned | 2026-02-05 | 2026-04-02 | 2026-04-02 | Underground crew |  | 2057.71 | Completed | No
WO-26-001253 |  | Crossroads | CR-S01-03 | Meter exchange | P3 within 10 days | 2026-02-05 | 2026-02-08 |  | Meter technician |  |  | Cancelled | No
WO-26-001254 | 1.3 | Crossroads | CR-S02-04 | Meter exchange | P3 within 10 days | 2026-02-05 | 2026-02-12 | 2026-02-12 | Meter technician |  | 60.8 | Completed | No
WO-26-001255 | 1.1 | Crossroads | CR-S09-01 | Meter exchange | P3 within 10 days | 2026-02-05 | 2026-02-15 | 2026-02-15 | Meter technician |  | 115.03 | Completed | No
WO-26-001256 | 1.4 | Crossroads | CR-S32-01 | Meter exchange | P3 within 10 days | 2026-02-05 | 2026-02-13 | 2026-02-15 | Meter technician |  | 104.16 | Completed | No
WO-26-001257 | 0.8 | Crossroads | CR-S04-04 | Meter exchange | P3 within 10 days | 2026-02-05 | 2026-02-15 | 2026-02-15 | Meter technician |  | 132.18 | Completed | No
WO-26-001258 | 0.7 | Crossroads | CR-S20-04 | Meter exchange | P4 planned | 2026-02-05 | 2026-03-11 | 2026-03-11 | Meter technician |  | 173.11 | Completed | No
WO-26-001259 | 2.5 | Crossroads | CR-S24-01 | Preventive maintenance | P4 planned | 2026-02-05 | 2026-03-28 | 2026-03-28 | Contract line | CT-02 | 224.04 | Completed | No
WO-26-001260 | 1 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-02-05 | 2026-02-11 | 2026-02-15 | Meter technician |  | 18.12 | Completed | No
WO-26-001261 | 1.9 | Crossroads | CR-S29-01 | Service order - field | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Meter technician |  | 16.36 | Completed | No
WO-26-001262 | 0.5 | Crossroads | CR-S18-03 | Service order - field | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Meter technician |  | 10.37 | Completed | No
WO-26-001263 | 1.6 | Crossroads | CR-S05-03 | Service order - field | P3 within 10 days | 2026-02-05 | 2026-02-11 | 2026-02-11 | Meter technician |  | 17.11 | Completed | No
WO-26-001264 | 3.6 | Crossroads | CR-S07-07 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 109.7 | Completed | No
WO-26-001265 | 4.9 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 331.41 | Completed | No
WO-26-001266 | 5.2 | Crossroads | CR-S03-03 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 157.57 | Completed | No
WO-26-001267 | 2.1 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 338.88 | Completed | No
WO-26-001268 | 3.7 | Crossroads | CR-S16-04 | Trouble - no power | P2 same day | 2026-02-05 | 2026-02-05 | 2026-02-05 | Troubleman |  | 288.3 | Completed | No
WO-26-001269 | 2.7 | Crossroads | CR-S25-02 | Trouble - no power | P2 same day | 2026-02-05 | 2026-02-06 | 2026-02-06 | Internal line |  | 294.08 | Completed | No
WO-26-001270 | 5.9 | Crossroads | CR-S07-02 | Trouble - no power | P2 same day | 2026-02-05 | 2026-02-06 | 2026-02-06 | Troubleman |  | 226.93 | Completed | No
WO-26-001271 | 8.8 | Bayou | BY-S06-02 | Corrective maintenance | P2 same day | 2026-02-06 | 2026-02-07 | 2026-02-07 | Contract line | CT-04 | 1137.08 | Completed | No
WO-26-001272 | 3.4 | Bayou | BY-S17-04 | Corrective maintenance | P4 planned | 2026-02-06 | 2026-03-13 | 2026-03-14 | Internal line |  | 2140.97 | Completed | No
WO-26-001273 | 8.4 | Bayou | BY-S24-05 | Corrective maintenance | P2 same day | 2026-02-06 | 2026-02-07 | 2026-02-07 | Internal line |  | 2050.35 | Completed | No
WO-26-001274 | 0.6 | Bayou | BY-S27-05 | Meter exchange | P4 planned | 2026-02-06 | 2026-03-22 | 2026-03-24 | Meter technician |  | 129.26 | Completed | No
WO-26-001275 |  | Bayou | BY-S15-06 | Meter exchange | P3 within 10 days | 2026-02-06 | 2026-02-10 |  | Meter technician |  |  | Cancelled | No
WO-26-001276 | 1.1 | Bayou | BY-S28-02 | Meter exchange | P3 within 10 days | 2026-02-06 | 2026-02-12 | 2026-02-16 | Meter technician |  | 123.32 | Completed | No
WO-26-001277 | 10.5 | Bayou | BY-S16-01 | New service - small | P4 planned | 2026-02-06 | 2026-03-31 | 2026-04-01 | Contract line | CT-03 | 309.7 | Completed | No
WO-26-001278 | 7.8 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-02-06 | 2026-03-25 | 2026-04-02 | Underground crew |  | 598.12 | Completed | No
WO-26-001279 | 2.3 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-02-06 | 2026-03-11 | 2026-03-11 | Underground crew |  | 1.27 | Completed | No
WO-26-001280 | 1.1 | Bayou | BY-S21-03 | Service order - field | P2 same day | 2026-02-06 | 2026-02-06 | 2026-02-06 | Meter technician |  | 8.15 | Completed | No
WO-26-001281 | 0.5 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-02-06 | 2026-02-07 | 2026-02-08 | Meter technician |  | 26.6 | Completed | No
WO-26-001282 | 0.9 | Bayou | BY-S14-01 | Service order - field | P2 same day | 2026-02-06 | 2026-02-06 | 2026-02-06 | Meter technician |  | 16.83 | Completed | No
WO-26-001283 |  | Bayou | BY-S12-04 | Service order - field | P3 within 10 days | 2026-02-06 | 2026-02-13 |  | Meter technician |  |  | Cancelled | No
WO-26-001284 | 2.9 | Bayou |  | Streetlight | P4 planned | 2026-02-06 | 2026-04-05 | 2026-04-05 | Contract line | CT-03 | 344.23 | Completed | No
WO-26-001285 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-06 | 2026-02-13 | 2026-02-15 | Contract line | CT-03 | 394.28 | Completed | No
WO-26-001286 | 4.7 | Bayou | BY-S18-03 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 253.77 | Completed | No
WO-26-001287 | 5 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 209.36 | Completed | No
WO-26-001288 | 4.7 | Bayou | BY-S08-02 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 | 2026-02-06 | Internal line |  | 330.08 | Completed | No
WO-26-001289 |  | Bayou | BY-S09-02 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 |  | Troubleman |  |  | Cancelled | No
WO-26-001290 | 4.2 | Bayou | BY-S25-05 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 187.94 | Completed | No
WO-26-001291 | 5.8 | Bayou | BY-S01-01 | Trouble - no power | P2 same day | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 298.72 | Completed | No
WO-26-001292 | 3.5 | Bayou | BY-S22-04 | Trouble - partial or voltage | P2 same day | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 33.88 | Completed | No
WO-26-001293 | 9.9 | Crossroads | CR-S24-04 | Corrective maintenance | P4 planned | 2026-02-06 | 2026-03-11 | 2026-03-11 | Underground crew |  | 1544.81 | Completed | No
WO-26-001294 | 8.9 | Crossroads | CR-S14-01 | Corrective maintenance | P3 within 10 days | 2026-02-06 | 2026-02-11 | 2026-02-11 | Contract line | CT-01 | 1796.79 | Completed | No
WO-26-001295 | 12 | Crossroads | CR-S30-01 | Corrective maintenance | P3 within 10 days | 2026-02-06 | 2026-02-12 | 2026-02-16 | Internal line |  | 1058.57 | Completed | No
WO-26-001296 | 8.3 | Crossroads | CR-S05-04 | Corrective maintenance | P3 within 10 days | 2026-02-06 | 2026-02-11 | 2026-02-11 | Internal line |  | 1424.81 | Completed | No
WO-26-001297 | 10.5 | Crossroads | CR-S23-05 | Corrective maintenance | P2 same day | 2026-02-06 | 2026-02-06 | 2026-02-06 | Underground crew |  | 1103.54 | Completed | No
WO-26-001298 | 3.7 | Crossroads | CR-S14-02 | Corrective maintenance | P3 within 10 days | 2026-02-06 | 2026-02-14 | 2026-02-15 | Contract line | CT-02 | 225.32 | Completed | No
WO-26-001299 | 10 | Crossroads | CR-S04-02 | Corrective maintenance | P3 within 10 days | 2026-02-06 | 2026-02-07 | 2026-02-09 | Underground crew |  | 852.18 | Completed | No
WO-26-001300 | 7.6 | Crossroads | CR-S18-04 | Corrective maintenance | P4 planned | 2026-02-06 | 2026-02-24 | 2026-02-24 | Underground crew |  | 286.16 | Completed | No
WO-26-001301 | 8.6 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-02-06 | 2026-02-15 | 2026-02-23 | Contract line | CT-02 | 679.64 | Completed | No
WO-26-001302 | 1.1 | Crossroads | CR-S32-05 | Meter exchange | P3 within 10 days | 2026-02-06 | 2026-02-11 | 2026-02-12 | Meter technician |  | 92.62 | Completed | No
WO-26-001303 | 1.5 | Crossroads | CR-S15-03 | Meter exchange | P3 within 10 days | 2026-02-06 | 2026-02-08 | 2026-02-12 | Meter technician |  | 145.29 | Completed | No
WO-26-001304 | 15.6 | Crossroads | CR-S25-06 | New service - small | P4 planned | 2026-02-06 | 2026-03-21 | 2026-03-22 | Contract line | CT-01 | 2186.92 | Completed | No
WO-26-001305 | 10.6 | Crossroads | CR-S09-03 | New service - small | P4 planned | 2026-02-06 | 2026-03-01 | 2026-03-01 | Contract line | CT-01 | 4105.84 | Completed | No
WO-26-001306 | 16.7 | Crossroads | CR-S28-03 | Pole replacement | P3 within 10 days | 2026-02-06 | 2026-02-08 | 2026-02-08 | Internal line |  | 1375.71 | Completed | No
WO-26-001307 | 23.9 | Crossroads | CR-S22-01 | Pole replacement | P3 within 10 days | 2026-02-06 | 2026-02-07 | 2026-02-09 | Internal line |  | 2975.34 | Completed | No
WO-26-001308 | 5.7 | Crossroads | CR-S15-01 | Preventive maintenance | P4 planned | 2026-02-06 | 2026-03-26 | 2026-03-30 | Underground crew |  | 321.64 | Completed | No
WO-26-001309 | 5.1 | Crossroads | CR-S07-03 | Preventive maintenance | P4 planned | 2026-02-06 | 2026-02-22 | 2026-02-24 | Internal line |  | 442.21 | Completed | No
WO-26-001310 | 6.4 | Crossroads | CR-S30-01 | Preventive maintenance | P4 planned | 2026-02-06 | 2026-02-18 | 2026-02-19 | Internal line |  | 21.49 | Completed | No
WO-26-001311 | 1.5 | Crossroads | CR-S09-01 | Service order - field | P3 within 10 days | 2026-02-06 | 2026-02-14 | 2026-02-14 | Meter technician |  | 13.91 | Completed | No
WO-26-001312 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-06 | 2026-02-10 | 2026-02-10 | Internal line |  | 250.21 | Completed | No
WO-26-001313 |  | Crossroads | CR-S23-04 | Transformer replacement | P1 emergency | 2026-02-06 | 2026-02-06 |  | Internal line |  |  | Cancelled | No
WO-26-001314 | 2.8 | Crossroads | CR-S09-01 | Trouble - no power | P2 same day | 2026-02-06 | 2026-02-07 | 2026-02-07 | Troubleman |  | 168.91 | Completed | No
WO-26-001315 | 4 | Crossroads | CR-S13-02 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 117.63 | Completed | No
WO-26-001316 | 5.3 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-02-06 | 2026-02-06 | 2026-02-06 | Troubleman |  | 221.22 | Completed | No
WO-26-001317 | 2 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-02-07 | 2026-02-07 | 2026-02-07 | Meter technician |  | 16.48 | Completed | No
WO-26-001318 | 1.6 | Bayou | BY-S17-01 | Service order - field | P2 same day | 2026-02-07 | 2026-02-08 | 2026-02-08 | Meter technician |  | 20.67 | Completed | No
WO-26-001319 | 1.8 | Bayou | BY-S28-02 | Service order - field | P2 same day | 2026-02-07 | 2026-02-07 | 2026-02-07 | Meter technician |  | 37.35 | Completed | No
WO-26-001320 | 6.5 | Bayou | BY-S25-02 | Transformer replacement | P1 emergency | 2026-02-07 | 2026-02-07 | 2026-02-07 | Internal line |  | 9195.39 | Completed | No
WO-26-001321 | 5.6 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-02-07 | 2026-02-07 | 2026-02-07 | Troubleman |  | 174.08 | Completed | No
WO-26-001322 | 6 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-02-07 | 2026-02-07 | 2026-02-07 | Troubleman |  | 194.51 | Completed | No
WO-26-001323 | 5.9 | Bayou | BY-S23-03 | Trouble - no power | P2 same day | 2026-02-07 | 2026-02-07 | 2026-02-07 | Troubleman |  | 174.89 | Completed | No
WO-26-001324 | 4.5 | Bayou | BY-S27-05 | Trouble - partial or voltage | P2 same day | 2026-02-07 | 2026-02-08 | 2026-02-08 | Troubleman |  | 10.98 | Completed | No
WO-26-001325 | 3.5 | Crossroads | CR-S16-02 | Trouble - no power | P2 same day | 2026-02-07 | 2026-02-08 | 2026-02-08 | Internal line |  | 92.72 | Completed | No
WO-26-001326 | 2.6 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-02-07 | 2026-02-08 | 2026-02-08 | Troubleman |  | 272.17 | Completed | No
WO-26-001327 | 4.8 | Bayou | BY-S15-03 | Corrective maintenance | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Internal line |  | 1883.29 | Completed | No
WO-26-001328 | 9.6 | Bayou | BY-S16-05 | Corrective maintenance | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Contract line | CT-04 | 717.06 | Completed | No
WO-26-001329 | 14 | Bayou | BY-S04-01 | Pole replacement | P2 same day | 2026-02-08 | 2026-02-08 | 2026-02-08 | Contract line | CT-03 | 2347.46 | Completed | No
WO-26-001330 | 3.4 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-02-08 | 2026-02-08 | 2026-02-08 | Troubleman |  | 220.87 | Completed | No
WO-26-001331 | 3.8 | Bayou | BY-S15-03 | Trouble - no power | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Troubleman |  | 114.2 | Completed | No
WO-26-001332 | 5.7 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-02-08 | 2026-02-08 | 2026-02-08 | Troubleman |  | 180.51 | Completed | No
WO-26-001333 | 3 | Bayou | BY-S15-02 | Trouble - partial or voltage | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Troubleman |  | 244.61 | Completed | No
WO-26-001334 | 4.2 | Bayou | BY-S10-03 | Trouble - partial or voltage | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Troubleman |  | 45.5 | Completed | No
WO-26-001335 | 0.6 | Crossroads | CR-S11-02 | Service order - field | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Meter technician |  | 22.93 | Completed | No
WO-26-001336 | 11.4 | Crossroads | CR-S29-02 | Transformer replacement | P2 same day | 2026-02-08 | 2026-02-09 | 2026-02-09 | Internal line |  | 5040.96 | Completed | No
WO-26-001337 | 5.4 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-02-08 | 2026-02-08 | 2026-02-08 | Internal line |  | 6.63 | Completed | No
WO-26-001338 | 4.1 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-02-08 | 2026-02-08 | 2026-02-08 | Troubleman |  | 0.8 | Completed | No
WO-26-001339 | 2.4 | Crossroads | CR-S25-01 | Trouble - partial or voltage | P2 same day | 2026-02-08 | 2026-02-08 | 2026-02-08 | Troubleman |  | 209.88 | Completed | No
WO-26-001340 | 11.3 | Bayou | BY-S13-05 | Corrective maintenance | P3 within 10 days | 2026-02-09 | 2026-02-18 | 2026-02-18 | Internal line |  | 2131.89 | Completed | No
WO-26-001341 | 10.4 | Bayou | BY-S20-01 | Corrective maintenance | P3 within 10 days | 2026-02-09 | 2026-02-15 | 2026-02-15 | Internal line |  | 1212.91 | Completed | No
WO-26-001342 | 4.2 | Bayou | BY-S21-03 | Corrective maintenance | P4 planned | 2026-02-09 | 2026-03-07 | 2026-03-15 | Internal line |  | 1190.96 | Completed | No
WO-26-001343 | 7.6 | Bayou | BY-S30-01 | Corrective maintenance | P4 planned | 2026-02-09 | 2026-03-20 | 2026-03-20 | Contract line | CT-04 | 1483.66 | Completed | No
WO-26-001344 | 1 | Bayou | BY-S24-03 | Meter exchange | P4 planned | 2026-02-09 | 2026-03-04 | 2026-03-04 | Meter technician |  | 165.12 | Completed | No
WO-26-001345 | 0.5 | Bayou | BY-S30-01 | Meter exchange | P4 planned | 2026-02-09 | 2026-02-27 | 2026-02-27 | Meter technician |  | 141.24 | Completed | No
WO-26-001346 | 1 | Bayou | BY-S08-01 | Meter exchange | P4 planned | 2026-02-09 | 2026-03-13 | 2026-03-13 | Meter technician |  | 170.54 | Completed | No
WO-26-001347 | 10.8 | Bayou | BY-S29-01 | New service - small | P4 planned | 2026-02-09 | 2026-03-10 | 2026-03-10 | Contract line | CT-03 | 2053.2 | Completed | No
WO-26-001348 |  | Bayou | BY-S09-01 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-03-10 |  | Internal line |  |  | Cancelled | No
WO-26-001349 | 2.4 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-03-23 | 2026-03-24 | Underground crew |  | 508.39 | Completed | No
WO-26-001350 | 2.9 | Bayou | BY-S21-03 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-02-17 | 2026-02-18 | Underground crew |  | 585.86 | Completed | No
WO-26-001351 | 2.4 | Bayou | BY-S26-05 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-03-01 | 2026-03-05 | Internal line |  | 397.89 | Completed | No
WO-26-001352 | 0.5 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Meter technician |  | 17.74 | Completed | No
WO-26-001353 | 1.1 | Bayou | BY-S25-03 | Service order - field | P3 within 10 days | 2026-02-09 | 2026-02-11 | 2026-02-12 | Meter technician |  | 20.22 | Completed | No
WO-26-001354 | 9.5 | Bayou | BY-S08-03 | Transformer replacement | P1 emergency | 2026-02-09 | 2026-02-09 | 2026-02-09 | Internal line |  | 10521.79 | Completed | No
WO-26-001355 | 13.4 | Bayou | BY-S15-02 | Transformer replacement | P2 same day | 2026-02-09 | 2026-02-09 | 2026-02-09 | Internal line |  | 11016.14 | Completed | No
WO-26-001356 | 2.4 | Bayou | BY-S24-03 | Trouble - no power | P1 emergency | 2026-02-09 | 2026-02-09 | 2026-02-09 | Troubleman |  | 146.16 | Completed | No
WO-26-001357 | 5.9 | Bayou | BY-S07-02 | Trouble - no power | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Troubleman |  | 346.34 | Completed | No
WO-26-001358 | 3.1 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-02-09 | 2026-02-09 | 2026-02-09 | Troubleman |  | 317.38 | Completed | No
WO-26-001359 | 2.9 | Bayou | BY-S27-06 | Trouble - no power | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Troubleman |  | 290.86 | Completed | No
WO-26-001360 | 3.1 | Bayou | BY-S13-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-09 | 2026-02-18 | 2026-02-26 | Troubleman |  | 110.51 | Completed | No
WO-26-001361 | 6.1 | Crossroads | CR-S31-03 | Corrective maintenance | P3 within 10 days | 2026-02-09 | 2026-02-12 | 2026-02-12 | Internal line |  | 1307.26 | Completed | No
WO-26-001362 | 8 | Crossroads | CR-S28-03 | Corrective maintenance | P3 within 10 days | 2026-02-09 | 2026-02-13 | 2026-02-13 | Internal line |  | 1812.84 | Completed | No
WO-26-001363 | 1.2 | Crossroads | CR-S30-03 | Meter exchange | P4 planned | 2026-02-09 | 2026-03-08 | 2026-03-10 | Meter technician |  | 170.6 | Completed | No
WO-26-001364 | 1.4 | Crossroads | CR-S28-03 | Meter exchange | P3 within 10 days | 2026-02-09 | 2026-02-14 | 2026-02-22 | Meter technician |  | 91.78 | Completed | No
WO-26-001365 | 1.4 | Crossroads | CR-S20-01 | Meter exchange | P4 planned | 2026-02-09 | 2026-03-31 | 2026-04-02 | Meter technician |  | 147.61 | Completed | No
WO-26-001366 | 0.7 | Crossroads | CR-S30-03 | Meter exchange | P3 within 10 days | 2026-02-09 | 2026-02-12 | 2026-02-12 | Meter technician |  | 90.15 | Completed | No
WO-26-001367 | 21.6 | Crossroads | CR-S20-03 | Pole replacement | P3 within 10 days | 2026-02-09 | 2026-02-14 | 2026-02-15 | Internal line |  | 1480.7 | Completed | No
WO-26-001368 | 3.6 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-03-29 | 2026-03-29 | Contract line | CT-01 | 476.25 | Completed | No
WO-26-001369 | 7.4 | Crossroads | CR-S13-02 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-02-20 | 2026-02-20 | Underground crew |  | 59.57 | Completed | No
WO-26-001370 | 4.4 | Crossroads | CR-S27-02 | Preventive maintenance | P4 planned | 2026-02-09 | 2026-04-06 | 2026-04-10 | Internal line |  | 572.3 | Completed | No
WO-26-001371 | 1.6 | Crossroads | CR-S22-01 | Service order - field | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Meter technician |  | 13.55 | Completed | No
WO-26-001372 | 1.7 | Crossroads | CR-S13-01 | Service order - field | P3 within 10 days | 2026-02-09 | 2026-02-19 | 2026-02-23 | Meter technician |  | 33.68 | Completed | No
WO-26-001373 | 0.8 | Crossroads | CR-S28-02 | Service order - field | P3 within 10 days | 2026-02-09 | 2026-02-18 | 2026-02-20 | Meter technician |  | 31.5 | Completed | No
WO-26-001374 | 0.5 | Crossroads | CR-S24-04 | Service order - field | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Meter technician |  | 36.08 | Completed | No
WO-26-001375 | 0.7 | Crossroads | CR-S14-02 | Service order - field | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Meter technician |  | 21.6 | Completed | No
WO-26-001376 | 7.9 | Crossroads | CR-S04-03 | Transformer replacement | P3 within 10 days | 2026-02-09 | 2026-02-19 | 2026-02-20 | Internal line |  | 4656.23 | Completed | No
WO-26-001377 | 3.5 | Crossroads | CR-S30-07 | Trouble - no power | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Troubleman |  | 303.51 | Completed | No
WO-26-001378 | 4.8 | Crossroads | CR-S05-03 | Trouble - no power | P1 emergency | 2026-02-09 | 2026-02-09 | 2026-02-09 | Troubleman |  | 10.85 | Completed | No
WO-26-001379 | 3.9 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-02-09 | 2026-02-09 | 2026-02-09 | Troubleman |  | 57.8 | Completed | No
WO-26-001380 | 3 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-02-09 | 2026-02-09 | 2026-02-09 | Troubleman |  | 251.73 | Completed | No
WO-26-001381 | 6 | Crossroads | CR-S19-02 | Trouble - no power | P2 same day | 2026-02-09 | 2026-02-10 | 2026-02-10 | Troubleman |  | 63.25 | Completed | No
WO-26-001382 | 11.2 | Bayou | BY-S13-05 | Corrective maintenance | P3 within 10 days | 2026-02-10 | 2026-02-12 | 2026-02-12 | Underground crew |  | 356.29 | Completed | No
WO-26-001383 | 7.3 | Bayou | BY-S08-02 | Corrective maintenance | P3 within 10 days | 2026-02-10 | 2026-02-20 | 2026-02-20 | Internal line |  | 1712.88 | Completed | No
WO-26-001384 | 1.3 | Bayou | BY-S16-06 | Meter exchange | P3 within 10 days | 2026-02-10 | 2026-02-11 | 2026-02-11 | Meter technician |  | 71.99 | Completed | No
WO-26-001385 | 0.9 | Bayou | BY-S21-01 | Meter exchange | P3 within 10 days | 2026-02-10 | 2026-02-13 | 2026-02-13 | Meter technician |  | 113.78 | Completed | No
WO-26-001386 | 0.8 | Bayou | BY-S17-02 | Meter exchange | P3 within 10 days | 2026-02-10 | 2026-02-12 | 2026-02-16 | Meter technician |  | 169.81 | Completed | No
WO-26-001387 | 1.3 | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-02-10 | 2026-02-12 | 2026-02-12 | Meter technician |  | 81.73 | Completed | No
WO-26-001388 | 6.5 | Bayou | BY-S24-04 | Preventive maintenance | P4 planned | 2026-02-10 | 2026-03-21 | 2026-03-25 | Contract line | CT-03 | 511.98 | Completed | No
WO-26-001389 | 6 | Bayou | BY-S07-01 | Preventive maintenance | P4 planned | 2026-02-10 | 2026-03-16 | 2026-03-16 | Contract line | CT-03 | 465.38 | Completed | No
WO-26-001390 | 7.6 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-02-10 | 2026-02-26 | 2026-02-28 | Contract line | CT-04 | 260.83 | Completed | No
WO-26-001391 | 1.1 | Bayou | BY-S21-01 | Service order - field | P3 within 10 days | 2026-02-10 | 2026-02-13 | 2026-02-13 | Meter technician |  | 10.52 | Completed | No
WO-26-001392 | 1.9 | Bayou | BY-S16-03 | Service order - field | P3 within 10 days | 2026-02-10 | 2026-02-15 | 2026-02-15 | Meter technician |  | 6.15 | Completed | No
WO-26-001393 | 1.2 | Bayou | BY-S16-01 | Service order - field | P3 within 10 days | 2026-02-10 | 2026-02-12 | 2026-02-14 | Meter technician |  | 15.74 | Completed | No
WO-26-001394 | 1 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-02-10 | 2026-02-13 | 2026-02-14 | Meter technician |  | 36.25 | Completed | No
WO-26-001395 | 0.8 | Bayou | BY-S18-07 | Service order - field | P3 within 10 days | 2026-02-10 | 2026-02-17 | 2026-02-17 | Meter technician |  | 5.55 | Completed | No
WO-26-001396 |  | Bayou | BY-S08-02 | Service order - field | P3 within 10 days | 2026-02-10 | 2026-02-12 |  | Meter technician |  |  | Cancelled | No
WO-26-001397 | 6.1 | Bayou | BY-S27-06 | Transformer replacement | P2 same day | 2026-02-10 | 2026-02-10 | 2026-02-10 | Internal line |  | 4523.03 | Completed | No
WO-26-001398 | 2.4 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-02-10 | 2026-02-10 | 2026-02-10 | Troubleman |  | 277.02 | Completed | No
WO-26-001399 | 4.4 | Bayou | BY-S18-07 | Trouble - no power | P1 emergency | 2026-02-10 | 2026-02-10 | 2026-02-10 | Troubleman |  | 297.68 | Completed | No
WO-26-001400 | 2.9 | Bayou | BY-S07-01 | Trouble - no power | P2 same day | 2026-02-10 | 2026-02-11 | 2026-02-11 | Troubleman |  | 253.67 | Completed | No
WO-26-001401 | 10.3 | Crossroads | CR-S31-02 | Corrective maintenance | P3 within 10 days | 2026-02-10 | 2026-02-13 | 2026-02-17 | Underground crew |  | 87.57 | Completed | No
WO-26-001402 | 6.3 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-02-10 | 2026-02-19 | 2026-02-19 | Underground crew |  | 416.34 | Completed | No
WO-26-001403 | 5.1 | Crossroads | CR-S28-01 | Corrective maintenance | P3 within 10 days | 2026-02-10 | 2026-02-16 | 2026-02-17 | Underground crew |  | 336.07 | Completed | No
WO-26-001404 | 4.5 | Crossroads | CR-S30-03 | Corrective maintenance | P3 within 10 days | 2026-02-10 | 2026-02-19 | 2026-02-19 | Underground crew |  | 1515.17 | Completed | No
WO-26-001405 | 11.7 | Crossroads | CR-S24-03 | Corrective maintenance | P4 planned | 2026-02-10 | 2026-04-10 | 2026-04-18 | Internal line |  | 390.92 | Completed | No
WO-26-001406 | 1.3 | Crossroads | CR-S04-06 | Meter exchange | P4 planned | 2026-02-10 | 2026-03-23 | 2026-03-24 | Meter technician |  | 165.91 | Completed | No
WO-26-001407 | 0.8 | Crossroads | CR-S23-01 | Meter exchange | P4 planned | 2026-02-10 | 2026-03-11 | 2026-03-11 | Meter technician |  | 62.17 | Completed | No
WO-26-001408 | 1.5 | Crossroads | CR-S20-04 | Meter exchange | P3 within 10 days | 2026-02-10 | 2026-02-17 | 2026-02-17 | Meter technician |  | 156.09 | Completed | No
WO-26-001409 | 3.3 | Crossroads | CR-S15-02 | Preventive maintenance | P4 planned | 2026-02-10 | 2026-03-19 | 2026-03-20 | Underground crew |  | 449.71 | Completed | No
WO-26-001410 | 1.4 | Crossroads | CR-S13-04 | Service order - field | P2 same day | 2026-02-10 | 2026-02-10 | 2026-02-10 | Meter technician |  | 1.39 | Completed | No
WO-26-001411 | 1.8 | Crossroads | CR-S10-03 | Service order - field | P2 same day | 2026-02-10 | 2026-02-11 | 2026-02-11 | Meter technician |  | 10.67 | Completed | No
WO-26-001412 | 1.9 | Crossroads | CR-S16-05 | Service order - field | P2 same day | 2026-02-10 | 2026-02-11 | 2026-02-11 | Meter technician |  | 3.46 | Completed | No
WO-26-001413 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-10 | 2026-02-17 | 2026-02-17 | Contract line | CT-02 | 179.31 | Completed | No
WO-26-001414 | 1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-10 | 2026-02-19 | 2026-02-21 | Contract line | CT-01 | 305.8 | Completed | No
WO-26-001415 | 8 | Crossroads | CR-S32-01 | Transformer replacement | P1 emergency | 2026-02-10 | 2026-02-10 | 2026-02-10 | Internal line |  | 7051.41 | Completed | No
WO-26-001416 | 5.2 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-02-10 | 2026-02-10 | 2026-02-10 | Troubleman |  | 18.38 | Completed | No
WO-26-001417 | 3.5 | Crossroads | CR-S17-02 | Trouble - partial or voltage | P2 same day | 2026-02-10 | 2026-02-11 | 2026-02-11 | Troubleman |  | 80.46 | Completed | No
WO-26-001418 | 3.2 | Crossroads | CR-S18-02 | Trouble - partial or voltage | P2 same day | 2026-02-10 | 2026-02-10 | 2026-02-10 | Troubleman |  | 222.41 | Completed | No
WO-26-001419 | 3.8 | Crossroads | CR-S02-02 | Trouble - partial or voltage | P2 same day | 2026-02-10 | 2026-02-11 | 2026-02-11 | Troubleman |  | 125.73 | Completed | No
WO-26-001420 | 2.9 | Crossroads | CR-S23-03 | Trouble - partial or voltage | P2 same day | 2026-02-10 | 2026-02-10 | 2026-02-10 | Troubleman |  | 160.59 | Completed | No
WO-26-001421 | 3.9 | Bayou | BY-S05-02 | Corrective maintenance | P3 within 10 days | 2026-02-11 | 2026-02-16 | 2026-02-18 | Internal line |  | 2176.24 | Completed | No
WO-26-001422 | 1 | Bayou | BY-S25-02 | Meter exchange | P4 planned | 2026-02-11 | 2026-04-03 | 2026-04-03 | Meter technician |  | 135.28 | Completed | No
WO-26-001423 | 1.4 | Bayou | BY-S26-05 | Meter exchange | P3 within 10 days | 2026-02-11 | 2026-02-21 | 2026-02-21 | Meter technician |  | 151.39 | Completed | No
WO-26-001424 | 22.1 | Bayou | BY-S24-03 | Pole replacement | P3 within 10 days | 2026-02-11 | 2026-02-16 | 2026-02-16 | Internal line |  | 2879.4 | Completed | No
WO-26-001425 | 13.8 | Bayou | BY-S24-03 | Pole replacement | P3 within 10 days | 2026-02-11 | 2026-02-12 | 2026-02-20 | Contract line | CT-04 | 1333.69 | Completed | No
WO-26-001426 | 5.5 | Bayou | BY-S27-02 | Preventive maintenance | P4 planned | 2026-02-11 | 2026-02-28 | 2026-03-04 | Internal line |  | 593.42 | Completed | No
WO-26-001427 | 7.9 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-02-11 | 2026-04-03 | 2026-04-03 | Internal line |  | 566.12 | Completed | No
WO-26-001428 | 3.3 | Bayou | BY-S23-04 | Preventive maintenance | P4 planned | 2026-02-11 | 2026-04-08 | 2026-04-08 | Internal line |  | 514.95 | Completed | No
WO-26-001429 | 2.7 | Bayou | BY-S23-05 | Preventive maintenance | P4 planned | 2026-02-11 | 2026-04-05 | 2026-04-06 | Contract line | CT-03 | 444.4 | Completed | No
WO-26-001430 | 1.8 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Meter technician |  | 3.33 | Completed | No
WO-26-001431 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-11 | 2026-02-14 | 2026-02-14 | Contract line | CT-04 | 448.79 | Completed | No
WO-26-001432 | 2 | Bayou |  | Streetlight | P4 planned | 2026-02-11 | 2026-04-10 | 2026-04-12 | Contract line | CT-04 | 91.25 | Completed | No
WO-26-001433 | 10.9 | Bayou | BY-S28-03 | Transformer replacement | P2 same day | 2026-02-11 | 2026-02-12 | 2026-02-12 | Internal line |  | 9581.05 | Completed | No
WO-26-001434 | 10.5 | Bayou | BY-S20-01 | Transformer replacement | P1 emergency | 2026-02-11 | 2026-02-11 | 2026-02-11 | Internal line |  | 8009.39 | Completed | No
WO-26-001435 | 3.5 | Bayou | BY-S15-04 | Trouble - no power | P1 emergency | 2026-02-11 | 2026-02-11 | 2026-02-11 | Troubleman |  | 18.28 | Completed | No
WO-26-001436 | 2.8 | Bayou | BY-S30-01 | Trouble - no power | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Troubleman |  | 23.4 | Completed | No
WO-26-001437 | 3.8 | Bayou | BY-S07-04 | Trouble - no power | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Internal line |  | 301.88 | Completed | No
WO-26-001438 | 5.4 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-02-11 | 2026-02-11 | 2026-02-11 | Troubleman |  | 131.29 | Completed | No
WO-26-001439 | 4.3 | Bayou | BY-S06-03 | Trouble - partial or voltage | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Troubleman |  | 101.63 | Completed | No
WO-26-001440 | 1.6 | Bayou | BY-S27-01 | Trouble - partial or voltage | P2 same day | 2026-02-11 | 2026-02-12 | 2026-02-12 | Troubleman |  | 180.43 | Completed | No
WO-26-001441 | 5 | Bayou | BY-S16-01 | Trouble - partial or voltage | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Internal line |  | 64.86 | Completed | No
WO-26-001442 | 5 | Crossroads | CR-S28-02 | Corrective maintenance | P3 within 10 days | 2026-02-11 | 2026-02-13 | 2026-02-13 | Contract line | CT-02 | 1492.01 | Completed | No
WO-26-001443 | 11.2 | Crossroads | CR-S25-03 | Corrective maintenance | P4 planned | 2026-02-11 | 2026-03-24 | 2026-03-24 | Internal line |  | 2315.52 | Completed | No
WO-26-001444 | 6.9 | Crossroads | CR-S07-07 | Corrective maintenance | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Contract line | CT-02 | 125.11 | Completed | No
WO-26-001445 | 1.1 | Crossroads | CR-S23-01 | Meter exchange | P3 within 10 days | 2026-02-11 | 2026-02-17 | 2026-02-17 | Meter technician |  | 118.02 | Completed | No
WO-26-001446 | 1 | Crossroads | CR-S17-03 | Meter exchange | P3 within 10 days | 2026-02-11 | 2026-02-15 | 2026-02-16 | Meter technician |  | 123.24 | Completed | No
WO-26-001447 | 11.1 | Crossroads | CR-S20-02 | New service - small | P3 within 10 days | 2026-02-11 | 2026-02-15 | 2026-02-19 | Underground crew |  | 997.87 | Completed | No
WO-26-001448 | 18.4 | Crossroads | CR-S26-02 | Pole replacement | P3 within 10 days | 2026-02-11 | 2026-02-12 | 2026-02-12 | Internal line |  | 2825.8 | Completed | No
WO-26-001449 | 2.6 | Crossroads | CR-S21-01 | Preventive maintenance | P4 planned | 2026-02-11 | 2026-02-26 | 2026-02-28 | Internal line |  | 376.64 | Completed | No
WO-26-001450 | 2.2 | Crossroads | CR-S24-04 | Preventive maintenance | P4 planned | 2026-02-11 | 2026-02-26 | 2026-03-02 | Underground crew |  | 147.94 | Completed | No
WO-26-001451 | 0.6 | Crossroads | CR-S24-03 | Service order - field | P2 same day | 2026-02-11 | 2026-02-12 | 2026-02-12 | Meter technician |  | 2.56 | Completed | No
WO-26-001452 | 0.8 | Crossroads | CR-S22-01 | Service order - field | P3 within 10 days | 2026-02-11 | 2026-02-14 | 2026-02-18 | Meter technician |  | 36.87 | Completed | No
WO-26-001453 | 1.3 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-02-11 | 2026-02-11 | 2026-02-11 | Meter technician |  | 34.37 | Completed | No
WO-26-001454 | 1.6 | Crossroads | CR-S28-04 | Service order - field | P3 within 10 days | 2026-02-11 | 2026-02-20 | 2026-02-20 | Meter technician |  | 5.47 | Completed | No
WO-26-001455 | 1.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-11 | 2026-02-21 | 2026-02-21 | Internal line |  | 91.37 | Completed | No
WO-26-001456 | 10.3 | Crossroads | CR-S12-03 | Transformer replacement | P3 within 10 days | 2026-02-11 | 2026-02-15 | 2026-02-15 | Internal line |  | 11929.17 | Completed | No
WO-26-001457 | 2.7 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-02-11 | 2026-02-11 | 2026-02-11 | Troubleman |  | 247.61 | Completed | No
WO-26-001458 | 5.8 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-02-11 | 2026-02-11 | 2026-02-11 | Troubleman |  | 37.76 | Completed | No
WO-26-001459 | 2.3 | Crossroads | CR-S05-06 | Trouble - partial or voltage | P3 within 10 days | 2026-02-11 | 2026-02-13 | 2026-02-13 | Troubleman |  | 219.62 | Completed | No
WO-26-001460 | 3.8 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-02-12 | 2026-02-14 | 2026-02-14 | Internal line |  | 1888.68 | Completed | No
WO-26-001461 | 0.7 | Bayou | BY-S02-01 | Meter exchange | P3 within 10 days | 2026-02-12 | 2026-02-21 | 2026-02-21 | Meter technician |  | 175.81 | Completed | No
WO-26-001462 | 13.1 | Bayou | BY-S29-02 | New service - small | P3 within 10 days | 2026-02-12 | 2026-02-13 | 2026-02-15 | Underground crew |  | 1675.89 | Completed | No
WO-26-001463 | 16.9 | Bayou | BY-S18-02 | Pole replacement | P3 within 10 days | 2026-02-12 | 2026-02-19 | 2026-02-19 | Internal line |  | 3040.89 | Completed | No
WO-26-001464 | 16.8 | Bayou | BY-S29-01 | Pole replacement | P3 within 10 days | 2026-02-12 | 2026-02-18 | 2026-02-18 | Contract line | CT-04 | 2454.43 | Completed | No
WO-26-001465 | 2 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-02-12 | 2026-02-21 | 2026-02-22 | Meter technician |  | 5.62 | Completed | No
WO-26-001466 | 1 | Bayou | BY-S07-06 | Service order - field | P3 within 10 days | 2026-02-12 | 2026-02-19 | 2026-02-19 | Meter technician |  | 1.06 | Completed | No
WO-26-001467 | 1.1 | Bayou | BY-S28-03 | Service order - field | P2 same day | 2026-02-12 | 2026-02-12 | 2026-02-12 | Meter technician |  | 19.79 | Completed | No
WO-26-001468 | 0.9 | Bayou | BY-S27-01 | Service order - field | P2 same day | 2026-02-12 | 2026-02-12 | 2026-02-12 | Meter technician |  | 13.9 | Completed | No
WO-26-001469 | 13.3 | Bayou | BY-S27-03 | Transformer replacement | P2 same day | 2026-02-12 | 2026-02-12 | 2026-02-12 | Contract line | CT-03 | 4029.36 | Completed | No
WO-26-001470 | 5 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-02-12 | 2026-02-12 | 2026-02-12 | Troubleman |  | 208.41 | Completed | No
WO-26-001471 | 2.4 | Bayou | BY-S18-04 | Trouble - no power | P2 same day | 2026-02-12 | 2026-02-13 | 2026-02-13 | Troubleman |  | 28.61 | Completed | No
WO-26-001472 | 2.6 | Bayou | BY-S27-05 | Trouble - no power | P1 emergency | 2026-02-12 | 2026-02-12 | 2026-02-12 | Troubleman |  | 100.05 | Completed | No
WO-26-001473 | 3.1 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-02-12 | 2026-02-12 | 2026-02-12 | Troubleman |  | 204.5 | Completed | No
WO-26-001474 | 4.4 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-02-12 | 2026-02-12 | 2026-02-12 | Troubleman |  | 45.85 | Completed | No
WO-26-001475 | 2.8 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-02-12 | 2026-02-12 | 2026-02-12 | Troubleman |  | 197.46 | Completed | No
WO-26-001476 | 3.1 | Bayou | BY-S29-05 | Trouble - partial or voltage | P3 within 10 days | 2026-02-12 | 2026-02-13 | 2026-02-13 | Troubleman |  | 139.29 | Completed | No
WO-26-001477 | 3.4 | Bayou | BY-S07-02 | Trouble - partial or voltage | P2 same day | 2026-02-12 | 2026-02-13 | 2026-02-13 | Troubleman |  | 29.34 | Completed | No
WO-26-001478 | 10 | Crossroads | CR-S17-03 | Corrective maintenance | P3 within 10 days | 2026-02-12 | 2026-02-15 | 2026-02-15 | Internal line |  | 433.05 | Completed | No
WO-26-001479 |  | Crossroads | CR-S24-02 | Corrective maintenance | P2 same day | 2026-02-12 | 2026-02-13 |  | Internal line |  |  | Cancelled | No
WO-26-001480 | 3.5 | Crossroads | CR-S19-03 | Corrective maintenance | P3 within 10 days | 2026-02-12 | 2026-02-22 | 2026-02-22 | Underground crew |  | 113.68 | Completed | No
WO-26-001481 | 5.4 | Crossroads | CR-S28-03 | Corrective maintenance | P3 within 10 days | 2026-02-12 | 2026-02-22 | 2026-02-26 | Underground crew |  | 1841.14 | Completed | No
WO-26-001482 | 7.6 | Crossroads | CR-S23-03 | Corrective maintenance | P2 same day | 2026-02-12 | 2026-02-13 | 2026-02-13 | Underground crew |  | 593.69 | Completed | No
WO-26-001483 | 1.5 | Crossroads | CR-S07-07 | Meter exchange | P3 within 10 days | 2026-02-12 | 2026-02-17 | 2026-02-17 | Meter technician |  | 93.47 | Completed | No
WO-26-001484 | 1 | Crossroads | CR-S10-03 | Meter exchange | P4 planned | 2026-02-12 | 2026-03-16 | 2026-03-16 | Meter technician |  | 171.09 | Completed | No
WO-26-001485 | 1.1 | Crossroads | CR-S20-01 | Meter exchange | P4 planned | 2026-02-12 | 2026-03-16 | 2026-03-17 | Meter technician |  | 120.21 | Completed | No
WO-26-001486 | 1.4 | Crossroads | CR-S16-02 | Meter exchange | P4 planned | 2026-02-12 | 2026-03-01 | 2026-03-01 | Meter technician |  | 101.31 | Completed | No
WO-26-001487 | 6.8 | Crossroads | CR-S05-02 | New service - small | P3 within 10 days | 2026-02-12 | 2026-02-18 | 2026-02-18 | Underground crew |  | 3112.68 | Completed | No
WO-26-001488 | 9.5 | Crossroads | CR-S01-02 | New service - small | P4 planned | 2026-02-12 | 2026-03-14 | 2026-03-16 | Internal line |  | 3289.25 | Completed | No
WO-26-001489 | 9.8 | Crossroads | CR-S15-01 | New service - small | P4 planned | 2026-02-12 | 2026-02-27 | 2026-03-07 | Underground crew |  | 2335.19 | Completed | No
WO-26-001490 | 14.4 | Crossroads | CR-S19-02 | Pole replacement | P4 planned | 2026-02-12 | 2026-03-29 | 2026-03-31 | Contract line | CT-01 | 1723.11 | Completed | No
WO-26-001491 | 3.3 | Crossroads | CR-S04-02 | Preventive maintenance | P4 planned | 2026-02-12 | 2026-02-26 | 2026-02-26 | Internal line |  | 42.55 | Completed | No
WO-26-001492 | 5 | Crossroads | CR-S22-01 | Preventive maintenance | P4 planned | 2026-02-12 | 2026-03-31 | 2026-03-31 | Internal line |  | 158.09 | Completed | No
WO-26-001493 | 3.9 | Crossroads | CR-S22-01 | Preventive maintenance | P4 planned | 2026-02-12 | 2026-03-23 | 2026-03-25 | Internal line |  | 574.1 | Completed | No
WO-26-001494 | 2 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-02-12 | 2026-02-12 | 2026-02-12 | Meter technician |  | 9.62 | Completed | No
WO-26-001495 | 0.7 | Crossroads | CR-S12-02 | Service order - field | P3 within 10 days | 2026-02-12 | 2026-02-19 | 2026-02-19 | Meter technician |  | 24.94 | Completed | No
WO-26-001496 | 1.7 | Crossroads | CR-S07-02 | Service order - field | P2 same day | 2026-02-12 | 2026-02-13 | 2026-02-13 | Meter technician |  | 38.92 | Completed | No
WO-26-001497 | 2.5 | Crossroads |  | Streetlight | P4 planned | 2026-02-12 | 2026-03-19 | 2026-03-21 | Internal line |  | 198.64 | Completed | No
WO-26-001498 | 3.6 | Crossroads | CR-S20-04 | Trouble - no power | P1 emergency | 2026-02-12 | 2026-02-12 | 2026-02-12 | Internal line |  | 257.07 | Completed | No
WO-26-001499 | 5.8 | Crossroads | CR-S29-02 | Trouble - no power | P2 same day | 2026-02-12 | 2026-02-13 | 2026-02-13 | Troubleman |  | 83.63 | Completed | No
WO-26-001500 | 5.1 | Crossroads | CR-S19-01 | Trouble - no power | P2 same day | 2026-02-12 | 2026-02-12 | 2026-02-12 | Troubleman |  | 21.63 | Completed | No
WO-26-001501 | 4 | Crossroads | CR-S14-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-12 | 2026-02-18 | 2026-02-18 | Troubleman |  | 95.18 | Completed | No
WO-26-001502 | 1.8 | Crossroads | CR-S07-07 | Trouble - partial or voltage | P3 within 10 days | 2026-02-12 | 2026-02-17 | 2026-02-17 | Troubleman |  | 55.99 | Completed | No
WO-26-001503 | 10.5 | Bayou | BY-S13-06 | Corrective maintenance | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Contract line | CT-03 | 1560.36 | Completed | No
WO-26-001504 | 3.8 | Bayou | BY-S05-02 | Corrective maintenance | P3 within 10 days | 2026-02-13 | 2026-02-17 | 2026-02-17 | Internal line |  | 982.56 | Completed | No
WO-26-001505 |  | Bayou | BY-S05-01 | Meter exchange | P3 within 10 days | 2026-02-13 | 2026-02-23 |  | Meter technician |  |  | Cancelled | No
WO-26-001506 | 1 | Bayou | BY-S26-06 | Meter exchange | P4 planned | 2026-02-13 | 2026-04-08 | 2026-04-08 | Meter technician |  | 129.66 | Completed | No
WO-26-001507 | 22.5 | Bayou | BY-S07-05 | Pole replacement | P2 same day | 2026-02-13 | 2026-02-14 | 2026-02-14 | Contract line | CT-03 | 3337.86 | Completed | No
WO-26-001508 | 4.8 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-02-13 | 2026-03-24 | 2026-04-01 | Underground crew |  | 492.44 | Completed | No
WO-26-001509 | 1.3 | Bayou | BY-S13-06 | Service order - field | P2 same day | 2026-02-13 | 2026-02-14 | 2026-02-14 | Meter technician |  | 29.89 | Completed | No
WO-26-001510 | 9.7 | Bayou | BY-S19-02 | Transformer replacement | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Internal line |  | 3555.19 | Completed | No
WO-26-001511 | 11.6 | Bayou | BY-S08-03 | Transformer replacement | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Internal line |  | 7360.99 | Completed | No
WO-26-001512 | 2.2 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 121.92 | Completed | No
WO-26-001513 | 5.4 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Internal line |  | 123.84 | Completed | No
WO-26-001514 | 3.7 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 148.11 | Completed | No
WO-26-001515 | 1.8 | Bayou | BY-S07-03 | Trouble - partial or voltage | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 1.94 | Completed | No
WO-26-001516 | 3.9 | Bayou | BY-S07-01 | Trouble - partial or voltage | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 242.34 | Completed | No
WO-26-001517 | 8.4 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-02-13 | 2026-02-14 | 2026-02-14 | Underground crew |  | 1687.68 | Completed | No
WO-26-001518 | 9.3 | Crossroads | CR-S15-01 | Corrective maintenance | P4 planned | 2026-02-13 | 2026-02-23 | 2026-02-23 | Contract line | CT-02 | 326.37 | Completed | No
WO-26-001519 | 6.5 | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-02-13 | 2026-02-21 | 2026-03-01 | Underground crew |  | 1505.91 | Completed | No
WO-26-001520 | 11.9 | Crossroads | CR-S07-03 | Corrective maintenance | P3 within 10 days | 2026-02-13 | 2026-02-16 | 2026-02-16 | Internal line |  | 1625.93 | Completed | No
WO-26-001521 | 7.4 | Crossroads | CR-S04-03 | Corrective maintenance | P3 within 10 days | 2026-02-13 | 2026-02-19 | 2026-02-21 | Internal line |  | 1054.32 | Completed | No
WO-26-001522 | 4.8 | Crossroads | CR-S04-02 | Corrective maintenance | P4 planned | 2026-02-13 | 2026-04-02 | 2026-04-02 | Contract line | CT-02 | 240.88 | Completed | No
WO-26-001523 | 0.7 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-02-13 | 2026-02-16 | 2026-02-17 | Meter technician |  | 149.55 | Completed | No
WO-26-001524 | 0.7 | Crossroads | CR-S16-02 | Meter exchange | P4 planned | 2026-02-13 | 2026-03-05 | 2026-03-05 | Meter technician |  | 82.76 | Completed | No
WO-26-001525 | 1.4 | Crossroads | CR-S06-03 | Meter exchange | P3 within 10 days | 2026-02-13 | 2026-02-19 | 2026-02-19 | Meter technician |  | 129.89 | Completed | No
WO-26-001526 | 12.5 | Crossroads | CR-S14-01 | Pole replacement | P4 planned | 2026-02-13 | 2026-02-23 | 2026-02-24 | Contract line | CT-01 | 1263.74 | Completed | No
WO-26-001527 | 16.4 | Crossroads | CR-S16-01 | Pole replacement | P3 within 10 days | 2026-02-13 | 2026-02-14 | 2026-02-18 | Contract line | CT-01 | 2822.97 | Completed | No
WO-26-001528 | 6.9 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-02-13 | 2026-04-02 | 2026-04-02 | Internal line |  | 39.7 | Completed | No
WO-26-001529 | 1.6 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-02-13 | 2026-02-18 | 2026-02-20 | Meter technician |  | 28.72 | Completed | No
WO-26-001530 | 1.3 | Crossroads | CR-S23-05 | Service order - field | P2 same day | 2026-02-13 | 2026-02-14 | 2026-02-14 | Meter technician |  | 9.08 | Completed | No
WO-26-001531 | 0.7 | Crossroads | CR-S06-01 | Service order - field | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Meter technician |  | 11.94 | Completed | No
WO-26-001532 | 1.6 | Crossroads | CR-S27-02 | Service order - field | P2 same day | 2026-02-13 | 2026-02-14 | 2026-02-14 | Meter technician |  | 30.86 | Completed | No
WO-26-001533 | 1.7 | Crossroads | CR-S31-03 | Service order - field | P2 same day | 2026-02-13 | 2026-02-14 | 2026-02-14 | Meter technician |  | 23.48 | Completed | No
WO-26-001534 | 8.8 | Crossroads | CR-S02-01 | Transformer replacement | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Contract line | CT-01 | 8885.34 | Completed | No
WO-26-001535 |  | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 |  | Troubleman |  |  | Cancelled | No
WO-26-001536 | 3.9 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 268.22 | Completed | No
WO-26-001537 | 5.1 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 219.5 | Completed | No
WO-26-001538 | 4 | Crossroads | CR-S30-07 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 185.7 | Completed | No
WO-26-001539 |  | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 |  | Troubleman |  |  | Cancelled | No
WO-26-001540 | 2.1 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Internal line |  | 162.56 | Completed | No
WO-26-001541 | 5.5 | Crossroads | CR-S09-03 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Internal line |  | 164.94 | Completed | No
WO-26-001542 | 4.1 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-02-13 | 2026-02-13 | 2026-02-13 | Internal line |  | 84.03 | Completed | No
WO-26-001543 | 2.4 | Crossroads | CR-S26-03 | Trouble - partial or voltage | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 100.55 | Completed | No
WO-26-001544 | 3.3 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-13 | 2026-02-19 | 2026-02-19 | Troubleman |  | 136.32 | Completed | No
WO-26-001545 | 2.4 | Crossroads | CR-S14-02 | Trouble - partial or voltage | P2 same day | 2026-02-13 | 2026-02-13 | 2026-02-13 | Troubleman |  | 139.56 | Completed | No
WO-26-001546 | 3.1 | Crossroads | CR-S23-02 | Trouble - partial or voltage | P2 same day | 2026-02-13 | 2026-02-14 | 2026-02-14 | Troubleman |  | 200.78 | Completed | No
WO-26-001547 | 1.2 | Bayou | BY-S04-03 | Service order - field | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Meter technician |  | 13.72 | Completed | No
WO-26-001548 | 0.9 | Bayou | BY-S11-01 | Service order - field | P2 same day | 2026-02-14 | 2026-02-14 | 2026-02-14 | Meter technician |  | 23.73 | Completed | No
WO-26-001549 | 0.9 | Bayou | BY-S23-01 | Service order - field | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Meter technician |  | 7.56 | Completed | No
WO-26-001550 | 1.9 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Meter technician |  | 28.24 | Completed | No
WO-26-001551 | 9.5 | Bayou | BY-S29-04 | Transformer replacement | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Internal line |  | 3932.34 | Completed | No
WO-26-001552 | 5.8 | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-02-14 | 2026-02-14 | 2026-02-14 | Troubleman |  | 93.69 | Completed | No
WO-26-001553 |  | Bayou | BY-S23-01 | Trouble - no power | P2 same day | 2026-02-14 | 2026-02-15 |  | Troubleman |  |  | Cancelled | No
WO-26-001554 | 1.6 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Troubleman |  | 85.15 | Completed | No
WO-26-001555 | 5.1 | Crossroads | CR-S13-04 | Corrective maintenance | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Internal line |  | 909.41 | Completed | No
WO-26-001556 | 1.2 | Crossroads | CR-S04-01 | Service order - field | P2 same day | 2026-02-14 | 2026-02-14 | 2026-02-14 | Meter technician |  | 6.79 | Completed | No
WO-26-001557 | 1.7 | Crossroads | CR-S14-04 | Service order - field | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Meter technician |  | 3.44 | Completed | No
WO-26-001558 | 0.6 | Crossroads | CR-S12-01 | Service order - field | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Meter technician |  | 21.74 | Completed | No
WO-26-001559 | 2.8 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-02-14 | 2026-02-14 | 2026-02-14 | Troubleman |  | 177.69 | Completed | No
WO-26-001560 | 2.2 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-02-14 | 2026-02-14 | 2026-02-14 | Internal line |  | 325.23 | Completed | No
WO-26-001561 | 2 | Crossroads | CR-S26-01 | Trouble - no power | P1 emergency | 2026-02-14 | 2026-02-14 | 2026-02-14 | Troubleman |  | 196.18 | Completed | No
WO-26-001562 | 5 | Crossroads | CR-S22-01 | Trouble - no power | P1 emergency | 2026-02-14 | 2026-02-14 | 2026-02-14 | Troubleman |  | 83.06 | Completed | No
WO-26-001563 | 4.7 | Crossroads | CR-S26-02 | Trouble - partial or voltage | P2 same day | 2026-02-14 | 2026-02-15 | 2026-02-15 | Troubleman |  | 241.25 | Completed | No
WO-26-001564 | 1.4 | Bayou | BY-S15-03 | Service order - field | P2 same day | 2026-02-15 | 2026-02-15 | 2026-02-15 | Meter technician |  | 3.64 | Completed | No
WO-26-001565 | 1.6 | Bayou | BY-S04-01 | Service order - field | P2 same day | 2026-02-15 | 2026-02-16 | 2026-02-16 | Meter technician |  | 32.58 | Completed | No
WO-26-001566 | 0.8 | Bayou | BY-S25-03 | Service order - field | P2 same day | 2026-02-15 | 2026-02-15 | 2026-02-15 | Meter technician |  | 8.65 | Completed | No
WO-26-001567 | 3.8 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 19.49 | Completed | No
WO-26-001568 | 4.1 | Bayou | BY-S28-02 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 224.6 | Completed | No
WO-26-001569 | 11.6 | Crossroads | CR-S17-01 | Transformer replacement | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Contract line | CT-02 | 8868.92 | Completed | No
WO-26-001570 | 13.5 | Crossroads | CR-S18-04 | Transformer replacement | P2 same day | 2026-02-15 | 2026-02-15 | 2026-02-15 | Internal line |  | 10338.87 | Completed | No
WO-26-001571 | 12.3 | Crossroads | CR-S29-01 | Transformer replacement | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Internal line |  | 10538.62 | Completed | No
WO-26-001572 | 4.7 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-02-15 | 2026-02-16 | 2026-02-16 | Troubleman |  | 255.72 | Completed | No
WO-26-001573 | 2.9 | Crossroads | CR-S32-04 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 223.82 | Completed | No
WO-26-001574 | 2.5 | Crossroads | CR-S24-04 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 132.69 | Completed | No
WO-26-001575 | 3.2 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 239.71 | Completed | No
WO-26-001576 | 4 | Crossroads | CR-S14-05 | Trouble - no power | P2 same day | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 229.54 | Completed | No
WO-26-001577 | 4.4 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 11.33 | Completed | No
WO-26-001578 | 2.4 | Crossroads | CR-S09-03 | Trouble - no power | P1 emergency | 2026-02-15 | 2026-02-15 | 2026-02-15 | Internal line |  | 196.9 | Completed | No
WO-26-001579 | 3.8 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P2 same day | 2026-02-15 | 2026-02-15 | 2026-02-15 | Troubleman |  | 162.31 | Completed | No
WO-26-001580 | 4.7 | Bayou | BY-S05-03 | Corrective maintenance | P3 within 10 days | 2026-02-16 | 2026-02-25 | 2026-02-27 | Contract line | CT-04 | 1137.81 | Completed | No
WO-26-001581 | 5.6 | Bayou | BY-S16-05 | Corrective maintenance | P4 planned | 2026-02-16 | 2026-03-23 | 2026-03-25 | Underground crew |  | 1824.85 | Completed | No
WO-26-001582 | 6.5 | Bayou | BY-S07-06 | Corrective maintenance | P3 within 10 days | 2026-02-16 | 2026-02-17 | 2026-02-18 | Internal line |  | 92.93 | Completed | No
WO-26-001583 | 9.8 | Bayou | BY-S21-05 | Corrective maintenance | P3 within 10 days | 2026-02-16 | 2026-02-22 | 2026-02-22 | Internal line |  | 874.74 | Completed | No
WO-26-001584 | 0.8 | Bayou | BY-S15-02 | Meter exchange | P3 within 10 days | 2026-02-16 | 2026-02-17 | 2026-02-17 | Meter technician |  | 105.39 | Completed | No
WO-26-001585 | 1.3 | Bayou | BY-S07-02 | Meter exchange | P3 within 10 days | 2026-02-16 | 2026-02-19 | 2026-02-19 | Meter technician |  | 130.43 | Completed | No
WO-26-001586 | 7.4 | Bayou | BY-S08-02 | New service - small | P4 planned | 2026-02-16 | 2026-03-28 | 2026-03-29 | Contract line | CT-03 | 4035.8 | Completed | No
WO-26-001587 | 4.4 | Bayou | BY-S18-06 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-03-28 | 2026-03-28 | Underground crew |  | 145.88 | Completed | No
WO-26-001588 | 6.5 | Bayou | BY-S22-03 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-03-29 | 2026-04-06 | Underground crew |  | 579.62 | Completed | No
WO-26-001589 | 0.7 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-02-16 | 2026-02-19 | 2026-02-20 | Meter technician |  | 20.27 | Completed | No
WO-26-001590 | 0.7 | Bayou | BY-S23-03 | Service order - field | P2 same day | 2026-02-16 | 2026-02-16 | 2026-02-16 | Meter technician |  | 15.22 | Completed | No
WO-26-001591 | 2.7 | Bayou |  | Streetlight | P4 planned | 2026-02-16 | 2026-04-17 | 2026-04-17 | Internal line |  | 76.17 | Completed | No
WO-26-001592 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-16 | 2026-02-18 | 2026-02-19 | Contract line | CT-03 | 214.25 | Completed | No
WO-26-001593 | 3.7 | Bayou | BY-S12-03 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 207.67 | Completed | No
WO-26-001594 | 5.9 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-02-16 | 2026-02-17 | 2026-02-17 | Troubleman |  | 166.79 | Completed | No
WO-26-001595 | 4 | Bayou | BY-S04-03 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 22.79 | Completed | No
WO-26-001596 | 2.3 | Bayou | BY-S23-03 | Trouble - no power | P2 same day | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 67.61 | Completed | No
WO-26-001597 | 1.9 | Bayou | BY-S19-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-16 | 2026-02-25 | 2026-02-27 | Internal line |  | 107.88 | Completed | No
WO-26-001598 | 12 | Crossroads | CR-S26-04 | Corrective maintenance | P3 within 10 days | 2026-02-16 | 2026-02-20 | 2026-02-20 | Underground crew |  | 417.46 | Completed | No
WO-26-001599 | 1.4 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-02-16 | 2026-02-26 | 2026-02-26 | Meter technician |  | 139.4 | Completed | No
WO-26-001600 | 0.9 | Crossroads | CR-S04-06 | Meter exchange | P4 planned | 2026-02-16 | 2026-03-28 | 2026-04-05 | Meter technician |  | 169.58 | Completed | No
WO-26-001601 | 1.3 | Crossroads | CR-S07-05 | Meter exchange | P4 planned | 2026-02-16 | 2026-04-12 | 2026-04-16 | Meter technician |  | 134.79 | Completed | No
WO-26-001602 | 0.9 | Crossroads | CR-S26-02 | Meter exchange | P3 within 10 days | 2026-02-16 | 2026-02-17 | 2026-02-17 | Meter technician |  | 126.36 | Completed | No
WO-26-001603 | 7.8 | Crossroads | CR-S19-01 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-03-21 | 2026-03-25 | Internal line |  | 577.53 | Completed | No
WO-26-001604 | 3.1 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-03-10 | 2026-03-10 | Internal line |  | 23.46 | Completed | No
WO-26-001605 | 5.7 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-04-17 | 2026-04-17 | Internal line |  | 50.61 | Completed | No
WO-26-001606 | 2.2 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-03-03 | 2026-03-03 | Contract line | CT-02 | 10.28 | Completed | No
WO-26-001607 | 7.4 | Crossroads | CR-S22-02 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-03-15 | 2026-03-15 | Underground crew |  | 545.58 | Completed | No
WO-26-001608 | 6.2 | Crossroads | CR-S28-03 | Preventive maintenance | P4 planned | 2026-02-16 | 2026-04-16 | 2026-04-18 | Contract line | CT-02 | 412.95 | Completed | No
WO-26-001609 | 0.5 | Crossroads | CR-S07-07 | Service order - field | P3 within 10 days | 2026-02-16 | 2026-02-18 | 2026-02-18 | Meter technician |  | 9.39 | Completed | No
WO-26-001610 | 1.7 | Crossroads | CR-S18-03 | Service order - field | P2 same day | 2026-02-16 | 2026-02-16 | 2026-02-16 | Meter technician |  | 10.47 | Completed | No
WO-26-001611 | 0.6 | Crossroads | CR-S15-02 | Service order - field | P2 same day | 2026-02-16 | 2026-02-16 | 2026-02-16 | Meter technician |  | 33.61 | Completed | No
WO-26-001612 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-16 | 2026-02-20 | 2026-02-24 | Internal line |  | 153.01 | Completed | No
WO-26-001613 | 5.2 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 246.31 | Completed | No
WO-26-001614 | 4.7 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 56.1 | Completed | No
WO-26-001615 | 5.4 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 229.18 | Completed | No
WO-26-001616 | 3.9 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 157.52 | Completed | No
WO-26-001617 | 3.6 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Troubleman |  | 134.52 | Completed | No
WO-26-001618 | 4 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-02-16 | 2026-02-16 | 2026-02-16 | Internal line |  | 232.99 | Completed | No
WO-26-001619 | 2.9 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P3 within 10 days | 2026-02-16 | 2026-02-26 | 2026-02-27 | Troubleman |  | 217.85 | Completed | No
WO-26-001620 | 2.6 | Crossroads | CR-S31-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-16 | 2026-02-17 | 2026-02-17 | Internal line |  | 62.25 | Completed | No
WO-26-001621 | 9.3 | Bayou | BY-S25-05 | Corrective maintenance | P4 planned | 2026-02-17 | 2026-03-13 | 2026-03-13 | Underground crew |  | 779.48 | Completed | No
WO-26-001622 | 5.2 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-02-17 | 2026-02-19 | 2026-02-19 | Contract line | CT-04 | 1067.55 | Completed | No
WO-26-001623 | 7.5 | Bayou | BY-S05-01 | Corrective maintenance | P4 planned | 2026-02-17 | 2026-03-01 | 2026-03-01 | Internal line |  | 2148.19 | Completed | No
WO-26-001624 | 1.1 | Bayou | BY-S09-01 | Meter exchange | P3 within 10 days | 2026-02-17 | 2026-02-22 | 2026-02-22 | Meter technician |  | 176.93 | Completed | No
WO-26-001625 | 1.1 | Bayou | BY-S11-01 | Meter exchange | P4 planned | 2026-02-17 | 2026-04-08 | 2026-04-09 | Meter technician |  | 127.98 | Completed | No
WO-26-001626 | 1 | Bayou | BY-S16-01 | Meter exchange | P4 planned | 2026-02-17 | 2026-03-23 | 2026-03-23 | Meter technician |  | 168.52 | Completed | No
WO-26-001627 | 0.9 | Bayou | BY-S10-05 | Meter exchange | P3 within 10 days | 2026-02-17 | 2026-02-24 | 2026-02-28 | Meter technician |  | 108.22 | Completed | No
WO-26-001628 | 5.5 | Bayou | BY-S13-05 | New service - small | P3 within 10 days | 2026-02-17 | 2026-02-22 | 2026-02-22 | Contract line | CT-04 | 1457.16 | Completed | No
WO-26-001629 | 2.3 | Bayou | BY-S14-02 | Preventive maintenance | P4 planned | 2026-02-17 | 2026-03-14 | 2026-03-18 | Contract line | CT-03 | 395.1 | Completed | No
WO-26-001630 | 0.5 | Bayou | BY-S13-03 | Service order - field | P3 within 10 days | 2026-02-17 | 2026-02-22 | 2026-02-22 | Meter technician |  | 9.39 | Completed | No
WO-26-001631 | 0.9 | Bayou | BY-S17-04 | Service order - field | P3 within 10 days | 2026-02-17 | 2026-02-27 | 2026-03-03 | Meter technician |  | 6.75 | Completed | No
WO-26-001632 | 1.9 | Bayou | BY-S04-02 | Service order - field | P2 same day | 2026-02-17 | 2026-02-18 | 2026-02-18 | Meter technician |  | 25.07 | Completed | No
WO-26-001633 | 0.5 | Bayou | BY-S16-02 | Service order - field | P2 same day | 2026-02-17 | 2026-02-18 | 2026-02-18 | Meter technician |  | 25.66 | Completed | No
WO-26-001634 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-17 | 2026-02-24 | 2026-02-24 | Contract line | CT-03 | 246.62 | Completed | No
WO-26-001635 | 7.4 | Bayou | BY-S06-03 | Transformer replacement | P2 same day | 2026-02-17 | 2026-02-18 | 2026-02-18 | Internal line |  | 3490.26 | Completed | No
WO-26-001636 |  | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-02-17 | 2026-02-17 |  | Troubleman |  |  | Cancelled | No
WO-26-001637 | 2.6 | Bayou | BY-S19-04 | Trouble - no power | P2 same day | 2026-02-17 | 2026-02-18 | 2026-02-18 | Troubleman |  | 43.8 | Completed | No
WO-26-001638 | 3.2 | Bayou | BY-S07-01 | Trouble - no power | P1 emergency | 2026-02-17 | 2026-02-17 | 2026-02-17 | Internal line |  | 69.5 | Completed | No
WO-26-001639 | 2.8 | Bayou | BY-S07-04 | Trouble - no power | P1 emergency | 2026-02-17 | 2026-02-17 | 2026-02-17 | Troubleman |  | 93.3 | Completed | No
WO-26-001640 | 2.1 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-02-17 | 2026-02-17 | 2026-02-17 | Troubleman |  | 207.5 | Completed | No
WO-26-001641 | 2.6 | Bayou | BY-S24-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-17 | 2026-02-25 | 2026-02-25 | Troubleman |  | 65.8 | Completed | No
WO-26-001642 | 4 | Bayou | BY-S27-05 | Trouble - partial or voltage | P3 within 10 days | 2026-02-17 | 2026-02-24 | 2026-02-28 | Troubleman |  | 139.28 | Completed | No
WO-26-001643 | 6 | Crossroads | CR-S09-02 | Corrective maintenance | P2 same day | 2026-02-17 | 2026-02-18 | 2026-02-18 | Internal line |  | 1513.27 | Completed | No
WO-26-001644 | 6.1 | Crossroads | CR-S13-05 | Corrective maintenance | P4 planned | 2026-02-17 | 2026-02-28 | 2026-02-28 | Internal line |  | 336.53 | Completed | No
WO-26-001645 | 7.1 | Crossroads | CR-S02-01 | Corrective maintenance | P4 planned | 2026-02-17 | 2026-04-05 | 2026-04-05 | Contract line | CT-02 | 2262.14 | Completed | No
WO-26-001646 | 1.5 | Crossroads | CR-S30-04 | Meter exchange | P3 within 10 days | 2026-02-17 | 2026-02-25 | 2026-02-25 | Meter technician |  | 160.09 | Completed | No
WO-26-001647 |  | Crossroads | CR-S08-02 | Meter exchange | P3 within 10 days | 2026-02-17 | 2026-02-26 |  | Meter technician |  |  | Cancelled | No
WO-26-001648 | 0.8 | Crossroads | CR-S26-01 | Meter exchange | P4 planned | 2026-02-17 | 2026-03-23 | 2026-03-23 | Meter technician |  | 113.01 | Completed | No
WO-26-001649 | 1.1 | Crossroads | CR-S16-04 | Meter exchange | P4 planned | 2026-02-17 | 2026-03-31 | 2026-04-04 | Meter technician |  | 154.62 | Completed | No
WO-26-001650 | 0.6 | Crossroads | CR-S18-01 | Meter exchange | P4 planned | 2026-02-17 | 2026-04-05 | 2026-04-05 | Meter technician |  | 155.23 | Completed | No
WO-26-001651 | 0.8 | Crossroads | CR-S20-05 | Meter exchange | P3 within 10 days | 2026-02-17 | 2026-02-21 | 2026-02-21 | Meter technician |  | 90.09 | Completed | No
WO-26-001652 | 14.3 | Crossroads | CR-S17-01 | New service - small | P4 planned | 2026-02-17 | 2026-04-07 | 2026-04-07 | Internal line |  | 3910.7 | Completed | No
WO-26-001653 | 19 | Crossroads | CR-S26-06 | Pole replacement | P3 within 10 days | 2026-02-17 | 2026-02-24 | 2026-02-26 | Contract line | CT-01 | 2384.81 | Completed | No
WO-26-001654 | 2.4 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-02-17 | 2026-03-20 | 2026-03-21 | Underground crew |  | 594.39 | Completed | No
WO-26-001655 | 6.5 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-02-17 | 2026-03-16 | 2026-03-16 | Underground crew |  | 235.38 | Completed | No
WO-26-001656 | 2.4 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-02-17 | 2026-03-14 | 2026-03-18 | Internal line |  | 207.29 | Completed | No
WO-26-001657 | 5.6 | Crossroads | CR-S24-04 | Preventive maintenance | P4 planned | 2026-02-17 | 2026-03-28 | 2026-04-01 | Underground crew |  | 320.71 | Completed | No
WO-26-001658 | 0.6 | Crossroads | CR-S15-01 | Service order - field | P3 within 10 days | 2026-02-17 | 2026-02-26 | 2026-02-28 | Meter technician |  | 21.13 | Completed | No
WO-26-001659 | 0.9 | Crossroads | CR-S04-01 | Service order - field | P2 same day | 2026-02-17 | 2026-02-17 | 2026-02-17 | Meter technician |  | 38.26 | Completed | No
WO-26-001660 | 1.4 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-02-17 | 2026-02-26 | 2026-02-28 | Meter technician |  | 16.7 | Completed | No
WO-26-001661 | 0.8 | Crossroads | CR-S32-01 | Service order - field | P2 same day | 2026-02-17 | 2026-02-17 | 2026-02-17 | Meter technician |  | 10.58 | Completed | No
WO-26-001662 | 0.7 | Crossroads | CR-S14-02 | Service order - field | P3 within 10 days | 2026-02-17 | 2026-02-19 | 2026-02-21 | Meter technician |  | 2.29 | Completed | No
WO-26-001663 | 1.6 | Crossroads | CR-S14-02 | Service order - field | P3 within 10 days | 2026-02-17 | 2026-02-22 | 2026-02-24 | Meter technician |  | 33.81 | Completed | No
WO-26-001664 | 1.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-17 | 2026-02-24 | 2026-03-04 | Internal line |  | 76.31 | Completed | No
WO-26-001665 | 9.3 | Crossroads | CR-S05-03 | Transformer replacement | P2 same day | 2026-02-17 | 2026-02-17 | 2026-02-17 | Internal line |  | 11941.49 | Completed | No
WO-26-001666 | 7.8 | Crossroads | CR-S11-01 | Transformer replacement | P2 same day | 2026-02-17 | 2026-02-17 | 2026-02-17 | Internal line |  | 9769.96 | Completed | No
WO-26-001667 | 2.3 | Crossroads | CR-S24-01 | Trouble - no power | P2 same day | 2026-02-17 | 2026-02-17 | 2026-02-17 | Internal line |  | 89.97 | Completed | No
WO-26-001668 | 3.5 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-02-17 | 2026-02-17 | 2026-02-17 | Troubleman |  | 188.04 | Completed | No
WO-26-001669 | 2.5 | Crossroads | CR-S25-06 | Trouble - partial or voltage | P3 within 10 days | 2026-02-17 | 2026-02-22 | 2026-02-22 | Internal line |  | 130.17 | Completed | No
WO-26-001670 | 10.6 | Bayou | BY-S09-03 | Corrective maintenance | P3 within 10 days | 2026-02-18 | 2026-02-22 | 2026-02-22 | Underground crew |  | 411.01 | Completed | No
WO-26-001671 | 9.5 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-02-18 | 2026-02-28 | 2026-02-28 | Contract line | CT-04 | 2039.41 | Completed | No
WO-26-001672 | 7.9 | Bayou | BY-S13-05 | Corrective maintenance | P4 planned | 2026-02-18 | 2026-04-08 | 2026-04-08 | Internal line |  | 2193.04 | Completed | No
WO-26-001673 | 1.1 | Bayou | BY-S28-03 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-20 | 2026-02-28 | Meter technician |  | 173.93 | Completed | No
WO-26-001674 |  | Bayou | BY-S10-01 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-27 |  | Meter technician |  |  | Cancelled | No
WO-26-001675 | 1.4 | Bayou | BY-S23-02 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-25 | 2026-02-25 | Meter technician |  | 172.32 | Completed | No
WO-26-001676 | 5.4 | Bayou | BY-S26-02 | New service - small | P3 within 10 days | 2026-02-18 | 2026-02-19 | 2026-02-19 | Contract line | CT-03 | 1482.03 | Completed | No
WO-26-001677 | 10.5 | Bayou | BY-S12-04 | Pole replacement | P3 within 10 days | 2026-02-18 | 2026-02-22 | 2026-02-22 | Contract line | CT-04 | 1441.15 | Completed | No
WO-26-001678 | 5.1 | Bayou | BY-S07-06 | Preventive maintenance | P4 planned | 2026-02-18 | 2026-04-14 | 2026-04-14 | Internal line |  | 253.65 | Completed | No
WO-26-001679 | 2.5 | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-02-18 | 2026-02-26 | 2026-02-26 | Underground crew |  | 255.5 | Completed | No
WO-26-001680 | 5.3 | Bayou | BY-S18-02 | Preventive maintenance | P4 planned | 2026-02-18 | 2026-03-13 | 2026-03-17 | Underground crew |  | 36.52 | Completed | No
WO-26-001681 | 0.8 | Bayou | BY-S11-01 | Service order - field | P2 same day | 2026-02-18 | 2026-02-19 | 2026-02-19 | Meter technician |  | 3.62 | Completed | No
WO-26-001682 | 1.9 | Bayou | BY-S26-02 | Service order - field | P3 within 10 days | 2026-02-18 | 2026-02-24 | 2026-03-04 | Meter technician |  | 26.5 | Completed | No
WO-26-001683 | 1.4 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-02-18 | 2026-02-24 | 2026-02-24 | Meter technician |  | 7.39 | Completed | No
WO-26-001684 | 3.1 | Bayou | BY-S20-01 | Trouble - no power | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Troubleman |  | 309.94 | Completed | No
WO-26-001685 | 3.6 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Troubleman |  | 51.37 | Completed | No
WO-26-001686 | 4.7 | Bayou | BY-S13-06 | Trouble - no power | P2 same day | 2026-02-18 | 2026-02-19 | 2026-02-19 | Internal line |  | 146.97 | Completed | No
WO-26-001687 | 4.5 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Troubleman |  | 78.32 | Completed | No
WO-26-001688 | 3.4 | Bayou | BY-S16-02 | Trouble - no power | P2 same day | 2026-02-18 | 2026-02-19 | 2026-02-19 | Troubleman |  | 197.52 | Completed | No
WO-26-001689 | 3.2 | Bayou | BY-S20-02 | Trouble - partial or voltage | P3 within 10 days | 2026-02-18 | 2026-02-22 | 2026-03-02 | Troubleman |  | 110.71 | Completed | No
WO-26-001690 | 7.6 | Crossroads | CR-S30-03 | Corrective maintenance | P3 within 10 days | 2026-02-18 | 2026-02-20 | 2026-02-28 | Internal line |  | 179.85 | Completed | No
WO-26-001691 | 9.6 | Crossroads | CR-S08-04 | Corrective maintenance | P3 within 10 days | 2026-02-18 | 2026-02-23 | 2026-02-23 | Internal line |  | 676.35 | Completed | No
WO-26-001692 | 3.2 | Crossroads | CR-S16-01 | Corrective maintenance | P3 within 10 days | 2026-02-18 | 2026-02-26 | 2026-02-28 | Internal line |  | 2314.17 | Completed | No
WO-26-001693 | 3.2 | Crossroads | CR-S32-01 | Corrective maintenance | P2 same day | 2026-02-18 | 2026-02-19 | 2026-02-19 | Internal line |  | 2331.47 | Completed | No
WO-26-001694 | 0.9 | Crossroads | CR-S08-06 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-26 | 2026-02-28 | Meter technician |  | 93.84 | Completed | No
WO-26-001695 |  | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-21 |  | Meter technician |  |  | Cancelled | No
WO-26-001696 | 0.5 | Crossroads | CR-S06-02 | Meter exchange | P4 planned | 2026-02-18 | 2026-04-14 | 2026-04-16 | Meter technician |  | 147.5 | Completed | No
WO-26-001697 | 1.2 | Crossroads | CR-S27-01 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-21 | 2026-02-21 | Meter technician |  | 87 | Completed | No
WO-26-001698 | 1.2 | Crossroads | CR-S30-07 | Meter exchange | P3 within 10 days | 2026-02-18 | 2026-02-24 | 2026-02-28 | Meter technician |  | 68.34 | Completed | No
WO-26-001699 | 8.8 | Crossroads | CR-S07-01 | New service - small | P4 planned | 2026-02-18 | 2026-04-11 | 2026-04-11 | Internal line |  | 3718.57 | Completed | No
WO-26-001700 | 12.9 | Crossroads | CR-S28-03 | Pole replacement | P4 planned | 2026-02-18 | 2026-03-24 | 2026-03-28 | Contract line | CT-01 | 1972.84 | Completed | No
WO-26-001701 |  | Crossroads | CR-S02-05 | Preventive maintenance | P4 planned | 2026-02-18 | 2026-03-09 |  | Internal line |  |  | Cancelled | No
WO-26-001702 | 7.4 | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-02-18 | 2026-04-02 | 2026-04-03 | Internal line |  | 335.27 | Completed | No
WO-26-001703 | 5.3 | Crossroads | CR-S21-01 | Preventive maintenance | P4 planned | 2026-02-18 | 2026-03-04 | 2026-03-05 | Underground crew |  | 185.81 | Completed | No
WO-26-001704 | 0.6 | Crossroads | CR-S15-01 | Service order - field | P3 within 10 days | 2026-02-18 | 2026-02-25 | 2026-02-27 | Meter technician |  | 29.51 | Completed | No
WO-26-001705 | 1.8 | Crossroads | CR-S17-03 | Service order - field | P3 within 10 days | 2026-02-18 | 2026-02-26 | 2026-02-26 | Meter technician |  | 32.69 | Completed | No
WO-26-001706 | 0.7 | Crossroads | CR-S25-01 | Service order - field | P3 within 10 days | 2026-02-18 | 2026-02-26 | 2026-02-28 | Meter technician |  | 36.86 | Completed | No
WO-26-001707 | 2.6 | Crossroads |  | Streetlight | P4 planned | 2026-02-18 | 2026-03-30 | 2026-03-30 | Internal line |  | 413.54 | Completed | No
WO-26-001708 | 12.6 | Crossroads | CR-S04-04 | Transformer replacement | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Internal line |  | 6361.04 | Completed | No
WO-26-001709 | 5.2 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Troubleman |  | 99.53 | Completed | No
WO-26-001710 | 4.8 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Internal line |  | 177.43 | Completed | No
WO-26-001711 | 4.3 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-02-18 | 2026-02-18 | 2026-02-18 | Troubleman |  | 173.24 | Completed | No
WO-26-001712 | 8.3 | Bayou | BY-S05-02 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-22 | 2026-02-24 | Internal line |  | 1004.73 | Completed | No
WO-26-001713 | 3.2 | Bayou | BY-S09-03 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-23 | 2026-02-23 | Internal line |  | 1567.46 | Completed | No
WO-26-001714 | 3.9 | Bayou | BY-S02-02 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-20 | 2026-02-24 | Contract line | CT-04 | 1430.36 | Completed | No
WO-26-001715 | 10.2 | Bayou | BY-S09-05 | Corrective maintenance | P2 same day | 2026-02-19 | 2026-02-20 | 2026-02-20 | Internal line |  | 2212.2 | Completed | No
WO-26-001716 | 1.3 | Bayou | BY-S05-02 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-03-01 | 2026-03-01 | Meter technician |  | 164.21 | Completed | No
WO-26-001717 | 0.8 | Bayou | BY-S23-03 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-02-20 | 2026-02-20 | Meter technician |  | 148.05 | Completed | No
WO-26-001718 | 1.2 | Bayou | BY-S19-02 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-02-20 | 2026-02-20 | Meter technician |  | 175.05 | Completed | No
WO-26-001719 | 1.3 | Bayou | BY-S21-02 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-03-01 | 2026-03-01 | Meter technician |  | 170.81 | Completed | No
WO-26-001720 | 11.3 | Bayou | BY-S30-01 | New service - small | P3 within 10 days | 2026-02-19 | 2026-02-25 | 2026-03-01 | Underground crew |  | 3731.93 | Completed | No
WO-26-001721 | 12.4 | Bayou | BY-S05-02 | Pole replacement | P3 within 10 days | 2026-02-19 | 2026-02-22 | 2026-02-22 | Contract line | CT-03 | 1631.45 | Completed | No
WO-26-001722 | 15.7 | Bayou | BY-S09-02 | Pole replacement | P3 within 10 days | 2026-02-19 | 2026-02-25 | 2026-02-25 | Contract line | CT-04 | 3076.81 | Completed | No
WO-26-001723 | 7.4 | Bayou | BY-S20-01 | Preventive maintenance | P4 planned | 2026-02-19 | 2026-03-26 | 2026-03-27 | Contract line | CT-03 | 15.48 | Completed | No
WO-26-001724 | 4.7 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-02-19 | 2026-03-05 | 2026-03-05 | Underground crew |  | 244.13 | Completed | No
WO-26-001725 | 6.6 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-02-19 | 2026-03-19 | 2026-03-19 | Underground crew |  | 284.9 | Completed | No
WO-26-001726 | 1.3 | Bayou | BY-S18-04 | Service order - field | P3 within 10 days | 2026-02-19 | 2026-02-23 | 2026-02-25 | Meter technician |  | 2.85 | Completed | No
WO-26-001727 | 1 | Bayou | BY-S13-05 | Service order - field | P3 within 10 days | 2026-02-19 | 2026-02-27 | 2026-02-27 | Meter technician |  | 25.57 | Completed | No
WO-26-001728 | 0.5 | Bayou | BY-S15-04 | Service order - field | P3 within 10 days | 2026-02-19 | 2026-02-20 | 2026-02-20 | Meter technician |  | 22.51 | Completed | No
WO-26-001729 | 1.7 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-02-19 | 2026-02-19 | 2026-02-19 | Meter technician |  | 27.47 | Completed | No
WO-26-001730 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-19 | 2026-02-27 | 2026-03-07 | Contract line | CT-03 | 422.46 | Completed | No
WO-26-001731 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-19 | 2026-02-26 | 2026-02-27 | Contract line | CT-04 | 210.91 | Completed | No
WO-26-001732 | 7.4 | Bayou | BY-S23-02 | Transformer replacement | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Internal line |  | 4226.01 | Completed | No
WO-26-001733 | 5.9 | Bayou | BY-S21-05 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Internal line |  | 43.68 | Completed | No
WO-26-001734 | 4 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 232.76 | Completed | No
WO-26-001735 | 4.2 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 30.76 | Completed | No
WO-26-001736 | 3.9 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-02-19 | 2026-02-20 | 2026-02-20 | Troubleman |  | 178.39 | Completed | No
WO-26-001737 | 1.7 | Bayou | BY-S17-04 | Trouble - partial or voltage | P3 within 10 days | 2026-02-19 | 2026-02-27 | 2026-03-01 | Troubleman |  | 162.61 | Completed | No
WO-26-001738 | 3.4 | Bayou | BY-S23-01 | Trouble - partial or voltage | P2 same day | 2026-02-19 | 2026-02-20 | 2026-02-20 | Internal line |  | 40.68 | Completed | No
WO-26-001739 | 9.6 | Crossroads | CR-S02-03 | Corrective maintenance | P4 planned | 2026-02-19 | 2026-03-21 | 2026-03-21 | Internal line |  | 1127.2 | Completed | No
WO-26-001740 | 6.7 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-26 | 2026-02-27 | Underground crew |  | 2115.47 | Completed | No
WO-26-001741 | 9.2 | Crossroads | CR-S17-03 | Corrective maintenance | P4 planned | 2026-02-19 | 2026-04-13 | 2026-04-15 | Internal line |  | 1360.85 | Completed | No
WO-26-001742 | 11.6 | Crossroads | CR-S11-01 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-23 | 2026-02-23 | Internal line |  | 1554.61 | Completed | No
WO-26-001743 | 3.4 | Crossroads | CR-S14-04 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-21 | 2026-02-25 | Internal line |  | 2200.45 | Completed | No
WO-26-001744 | 10.3 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-02-19 | 2026-02-26 | 2026-02-26 | Internal line |  | 1891.16 | Completed | No
WO-26-001745 | 6.4 | Crossroads | CR-S14-03 | Corrective maintenance | P4 planned | 2026-02-19 | 2026-03-25 | 2026-03-26 | Contract line | CT-01 | 271.93 | Completed | No
WO-26-001746 | 1.5 | Crossroads | CR-S32-03 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-02-24 | 2026-02-26 | Meter technician |  | 113.28 | Completed | No
WO-26-001747 | 1 | Crossroads | CR-S01-01 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-02-21 | 2026-02-22 | Meter technician |  | 104.54 | Completed | No
WO-26-001748 | 1.5 | Crossroads | CR-S32-01 | Meter exchange | P4 planned | 2026-02-19 | 2026-03-30 | 2026-04-03 | Meter technician |  | 125.25 | Completed | No
WO-26-001749 | 1.4 | Crossroads | CR-S25-01 | Meter exchange | P4 planned | 2026-02-19 | 2026-04-15 | 2026-04-19 | Meter technician |  | 75.69 | Completed | No
WO-26-001750 | 1 | Crossroads | CR-S28-04 | Meter exchange | P3 within 10 days | 2026-02-19 | 2026-02-26 | 2026-02-26 | Meter technician |  | 70.65 | Completed | No
WO-26-001751 | 5.7 | Crossroads | CR-S17-01 | New service - small | P4 planned | 2026-02-19 | 2026-04-14 | 2026-04-22 | Internal line |  | 3673.89 | Completed | No
WO-26-001752 | 14.1 | Crossroads | CR-S10-01 | Pole replacement | P2 same day | 2026-02-19 | 2026-02-20 | 2026-02-20 | Contract line | CT-02 | 2570.13 | Completed | No
WO-26-001753 | 4.5 | Crossroads | CR-S08-02 | Preventive maintenance | P4 planned | 2026-02-19 | 2026-04-16 | 2026-04-16 | Underground crew |  | 26.16 | Completed | No
WO-26-001754 | 7 | Crossroads | CR-S12-01 | Preventive maintenance | P4 planned | 2026-02-19 | 2026-04-19 | 2026-04-23 | Internal line |  | 328.3 | Completed | No
WO-26-001755 | 4.9 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-02-19 | 2026-04-10 | 2026-04-11 | Contract line | CT-02 | 46.22 | Completed | No
WO-26-001756 | 0.5 | Crossroads | CR-S15-03 | Service order - field | P3 within 10 days | 2026-02-19 | 2026-02-22 | 2026-02-24 | Meter technician |  | 12 | Completed | No
WO-26-001757 | 2 | Crossroads | CR-S32-04 | Service order - field | P2 same day | 2026-02-19 | 2026-02-19 | 2026-02-19 | Meter technician |  | 8.52 | Completed | No
WO-26-001758 | 1.6 | Crossroads | CR-S26-03 | Service order - field | P3 within 10 days | 2026-02-19 | 2026-03-01 | 2026-03-02 | Meter technician |  | 2.22 | Completed | No
WO-26-001759 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-19 | 2026-03-01 | 2026-03-05 | Internal line |  | 342.68 | Completed | No
WO-26-001760 | 13.4 | Crossroads | CR-S17-01 | Transformer replacement | P2 same day | 2026-02-19 | 2026-02-20 | 2026-02-20 | Internal line |  | 6182.1 | Completed | No
WO-26-001761 |  | Crossroads | CR-S05-03 | Trouble - no power | P2 same day | 2026-02-19 | 2026-02-20 |  | Troubleman |  |  | Cancelled | No
WO-26-001762 | 4.7 | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 277.95 | Completed | No
WO-26-001763 | 5.7 | Crossroads | CR-S29-01 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 301.82 | Completed | No
WO-26-001764 | 5.7 | Crossroads | CR-S02-01 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 141.86 | Completed | No
WO-26-001765 | 4.5 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 231.9 | Completed | No
WO-26-001766 | 2.2 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 253.64 | Completed | No
WO-26-001767 | 2 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-02-19 | 2026-02-19 | 2026-02-19 | Troubleman |  | 193.18 | Completed | No
WO-26-001768 | 3.2 | Bayou | BY-S15-02 | Corrective maintenance | P4 planned | 2026-02-20 | 2026-03-12 | 2026-03-20 | Contract line | CT-03 | 1333.71 | Completed | No
WO-26-001769 | 6.9 | Bayou | BY-S29-03 | Corrective maintenance | P3 within 10 days | 2026-02-20 | 2026-02-23 | 2026-02-23 | Internal line |  | 879.71 | Completed | No
WO-26-001770 | 1.3 | Bayou | BY-S25-03 | Meter exchange | P3 within 10 days | 2026-02-20 | 2026-02-28 | 2026-02-28 | Meter technician |  | 145.62 | Completed | No
WO-26-001771 |  | Bayou | BY-S12-01 | Meter exchange | P4 planned | 2026-02-20 | 2026-03-06 |  | Meter technician |  |  | Cancelled | No
WO-26-001772 | 18 | Bayou | BY-S21-01 | Pole replacement | P3 within 10 days | 2026-02-20 | 2026-02-25 | 2026-03-01 | Contract line | CT-04 | 1945.79 | Completed | No
WO-26-001773 | 23.3 | Bayou | BY-S18-03 | Pole replacement | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Contract line | CT-04 | 2836.44 | Completed | No
WO-26-001774 | 1 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-02-20 | 2026-02-20 | 2026-02-20 | Meter technician |  | 12.11 | Completed | No
WO-26-001775 | 1.5 | Bayou |  | Streetlight | P4 planned | 2026-02-20 | 2026-03-14 | 2026-03-16 | Internal line |  | 305.47 | Completed | No
WO-26-001776 | 10.8 | Bayou | BY-S10-04 | Transformer replacement | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Contract line | CT-04 | 3459.01 | Completed | No
WO-26-001777 | 13.1 | Bayou | BY-S01-01 | Transformer replacement | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Internal line |  | 6889.06 | Completed | No
WO-26-001778 | 3.3 | Bayou | BY-S04-01 | Trouble - no power | P2 same day | 2026-02-20 | 2026-02-20 | 2026-02-20 | Internal line |  | 66.89 | Completed | No
WO-26-001779 | 2.7 | Bayou | BY-S12-02 | Trouble - no power | P1 emergency | 2026-02-20 | 2026-02-20 | 2026-02-20 | Internal line |  | 288.09 | Completed | No
WO-26-001780 | 5.3 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-02-20 | 2026-02-20 | 2026-02-20 | Troubleman |  | 220.45 | Completed | No
WO-26-001781 | 5 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-02-20 | 2026-02-20 | 2026-02-20 | Troubleman |  | 45.22 | Completed | No
WO-26-001782 | 3.8 | Bayou | BY-S28-02 | Trouble - no power | P1 emergency | 2026-02-20 | 2026-02-20 | 2026-02-20 | Troubleman |  | 219.77 | Completed | No
WO-26-001783 | 3.7 | Bayou | BY-S07-02 | Trouble - partial or voltage | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Troubleman |  | 26.45 | Completed | No
WO-26-001784 | 4.6 | Bayou | BY-S28-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-20 | 2026-02-24 | 2026-02-24 | Troubleman |  | 116.26 | Completed | No
WO-26-001785 | 7.4 | Crossroads | CR-S01-03 | Corrective maintenance | P3 within 10 days | 2026-02-20 | 2026-02-28 | 2026-02-28 | Internal line |  | 572.11 | Completed | No
WO-26-001786 | 3 | Crossroads | CR-S23-02 | Corrective maintenance | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Internal line |  | 2177.07 | Completed | No
WO-26-001787 | 5.4 | Crossroads | CR-S09-04 | Corrective maintenance | P3 within 10 days | 2026-02-20 | 2026-03-01 | 2026-03-02 | Internal line |  | 1729.33 | Completed | No
WO-26-001788 | 0.8 | Crossroads | CR-S13-03 | Meter exchange | P3 within 10 days | 2026-02-20 | 2026-03-02 | 2026-03-02 | Meter technician |  | 85.76 | Completed | No
WO-26-001789 | 0.8 | Crossroads | CR-S30-03 | Meter exchange | P3 within 10 days | 2026-02-20 | 2026-02-26 | 2026-02-27 | Meter technician |  | 79.88 | Completed | No
WO-26-001790 | 1.1 | Crossroads | CR-S27-04 | Meter exchange | P4 planned | 2026-02-20 | 2026-03-24 | 2026-03-24 | Meter technician |  | 116.73 | Completed | No
WO-26-001791 | 0.7 | Crossroads | CR-S12-03 | Meter exchange | P4 planned | 2026-02-20 | 2026-03-21 | 2026-03-21 | Meter technician |  | 84.24 | Completed | No
WO-26-001792 | 10.5 | Crossroads | CR-S25-01 | Pole replacement | P4 planned | 2026-02-20 | 2026-03-15 | 2026-03-16 | Contract line | CT-02 | 3192.81 | Completed | No
WO-26-001793 | 7.2 | Crossroads | CR-S04-01 | Preventive maintenance | P4 planned | 2026-02-20 | 2026-03-29 | 2026-03-29 | Internal line |  | 357.85 | Completed | No
WO-26-001794 | 5.3 | Crossroads | CR-S25-05 | Preventive maintenance | P4 planned | 2026-02-20 | 2026-03-26 | 2026-03-26 | Underground crew |  | 79.78 | Completed | No
WO-26-001795 | 1.9 | Crossroads | CR-S29-02 | Service order - field | P3 within 10 days | 2026-02-20 | 2026-03-01 | 2026-03-09 | Meter technician |  | 1.02 | Completed | No
WO-26-001796 | 1.3 | Crossroads | CR-S12-01 | Service order - field | P2 same day | 2026-02-20 | 2026-02-20 | 2026-02-20 | Meter technician |  | 34.46 | Completed | No
WO-26-001797 | 1.5 | Crossroads | CR-S21-01 | Service order - field | P3 within 10 days | 2026-02-20 | 2026-03-01 | 2026-03-02 | Meter technician |  | 21.33 | Completed | No
WO-26-001798 | 0.8 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Meter technician |  | 9.62 | Completed | No
WO-26-001799 | 0.9 | Crossroads | CR-S25-01 | Service order - field | P3 within 10 days | 2026-02-20 | 2026-02-23 | 2026-02-24 | Meter technician |  | 0.32 | Completed | No
WO-26-001800 | 1.3 | Crossroads |  | Streetlight | P4 planned | 2026-02-20 | 2026-03-28 | 2026-03-28 | Contract line | CT-01 | 93.99 | Completed | No
WO-26-001801 | 2.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-20 | 2026-02-27 | 2026-02-28 | Internal line |  | 87.3 | Completed | No
WO-26-001802 | 1.7 | Crossroads |  | Streetlight | P4 planned | 2026-02-20 | 2026-02-27 | 2026-02-27 | Internal line |  | 173.45 | Completed | No
WO-26-001803 | 7.4 | Crossroads | CR-S26-06 | Transformer replacement | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Contract line | CT-01 | 8320.88 | Completed | No
WO-26-001804 | 2.3 | Crossroads | CR-S11-01 | Trouble - no power | P1 emergency | 2026-02-20 | 2026-02-20 | 2026-02-20 | Troubleman |  | 263.22 | Completed | No
WO-26-001805 | 5.2 | Crossroads | CR-S02-05 | Trouble - no power | P1 emergency | 2026-02-20 | 2026-02-20 | 2026-02-20 | Troubleman |  | 30.46 | Completed | No
WO-26-001806 | 3.9 | Crossroads | CR-S18-05 | Trouble - partial or voltage | P2 same day | 2026-02-20 | 2026-02-21 | 2026-02-21 | Troubleman |  | 92.26 | Completed | No
WO-26-001807 | 0.5 | Bayou | BY-S21-04 | Service order - field | P2 same day | 2026-02-21 | 2026-02-21 | 2026-02-21 | Meter technician |  | 28.86 | Completed | No
WO-26-001808 | 8.8 | Bayou | BY-S16-04 | Transformer replacement | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Internal line |  | 4473.13 | Completed | No
WO-26-001809 | 11.8 | Bayou | BY-S20-02 | Transformer replacement | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Internal line |  | 7540.27 | Completed | No
WO-26-001810 | 9.3 | Bayou | BY-S07-01 | Transformer replacement | P2 same day | 2026-02-21 | 2026-02-22 | 2026-02-22 | Internal line |  | 11733.54 | Completed | No
WO-26-001811 |  | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-02-21 | 2026-02-21 |  | Internal line |  |  | Cancelled | No
WO-26-001812 | 2.6 | Bayou | BY-S24-03 | Trouble - no power | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Troubleman |  | 42.5 | Completed | No
WO-26-001813 | 6 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Troubleman |  | 181.19 | Completed | No
WO-26-001814 | 5.1 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Troubleman |  | 238.63 | Completed | No
WO-26-001815 | 1.5 | Bayou | BY-S04-02 | Trouble - partial or voltage | P2 same day | 2026-02-21 | 2026-02-22 | 2026-02-22 | Troubleman |  | 208.23 | Completed | No
WO-26-001816 | 5.4 | Crossroads | CR-S07-05 | Corrective maintenance | P2 same day | 2026-02-21 | 2026-02-22 | 2026-02-22 | Internal line |  | 1512.43 | Completed | No
WO-26-001817 | 3.8 | Crossroads | CR-S31-02 | Corrective maintenance | P2 same day | 2026-02-21 | 2026-02-21 | 2026-02-21 | Contract line | CT-02 | 1330.59 | Completed | No
WO-26-001818 | 10.8 | Crossroads | CR-S25-02 | Corrective maintenance | P2 same day | 2026-02-21 | 2026-02-21 | 2026-02-21 | Internal line |  | 1282.67 | Completed | No
WO-26-001819 | 1.3 | Crossroads | CR-S22-02 | Service order - field | P2 same day | 2026-02-21 | 2026-02-21 | 2026-02-21 | Meter technician |  | 15.2 | Completed | No
WO-26-001820 | 2.7 | Crossroads | CR-S10-02 | Trouble - no power | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Troubleman |  | 245.14 | Completed | No
WO-26-001821 | 5.4 | Crossroads | CR-S02-03 | Trouble - no power | P2 same day | 2026-02-21 | 2026-02-22 | 2026-02-22 | Troubleman |  | 208.23 | Completed | No
WO-26-001822 | 3.1 | Crossroads | CR-S20-01 | Trouble - no power | P2 same day | 2026-02-21 | 2026-02-21 | 2026-02-21 | Troubleman |  | 215.6 | Completed | No
WO-26-001823 | 3.2 | Crossroads | CR-S26-05 | Trouble - no power | P1 emergency | 2026-02-21 | 2026-02-21 | 2026-02-21 | Troubleman |  | 184.43 | Completed | No
WO-26-001824 | 2.1 | Crossroads | CR-S13-02 | Trouble - partial or voltage | P2 same day | 2026-02-21 | 2026-02-22 | 2026-02-22 | Troubleman |  | 66.44 | Completed | No
WO-26-001825 | 5.2 | Bayou | BY-S06-01 | Trouble - no power | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Internal line |  | 339.31 | Completed | No
WO-26-001826 | 3.9 | Bayou | BY-S05-02 | Trouble - no power | P1 emergency | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 187.78 | Completed | No
WO-26-001827 | 4.3 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 221.12 | Completed | No
WO-26-001828 | 3.1 | Bayou | BY-S15-03 | Trouble - no power | P1 emergency | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 113.26 | Completed | No
WO-26-001829 | 11.2 | Crossroads | CR-S07-07 | Corrective maintenance | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Internal line |  | 1998.88 | Completed | No
WO-26-001830 | 0.7 | Crossroads | CR-S20-05 | Service order - field | P2 same day | 2026-02-22 | 2026-02-23 | 2026-02-23 | Meter technician |  | 8.49 | Completed | No
WO-26-001831 | 1.2 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Meter technician |  | 37.85 | Completed | No
WO-26-001832 | 11.6 | Crossroads | CR-S30-05 | Transformer replacement | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Contract line | CT-02 | 10265.24 | Completed | No
WO-26-001833 | 4.3 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 311.6 | Completed | No
WO-26-001834 | 4.6 | Crossroads | CR-S20-03 | Trouble - no power | P1 emergency | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 29.13 | Completed | No
WO-26-001835 | 2.6 | Crossroads | CR-S26-03 | Trouble - no power | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 156.43 | Completed | No
WO-26-001836 | 5.8 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-02-22 | 2026-02-23 | 2026-02-23 | Internal line |  | 349.35 | Completed | No
WO-26-001837 | 2 | Crossroads | CR-S28-03 | Trouble - partial or voltage | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Internal line |  | 122.95 | Completed | No
WO-26-001838 | 4.9 | Crossroads | CR-S08-06 | Trouble - partial or voltage | P2 same day | 2026-02-22 | 2026-02-23 | 2026-02-23 | Troubleman |  | 221.73 | Completed | No
WO-26-001839 | 4.7 | Crossroads | CR-S07-07 | Trouble - partial or voltage | P2 same day | 2026-02-22 | 2026-02-22 | 2026-02-22 | Troubleman |  | 92.73 | Completed | No
WO-26-001840 | 6.6 | Bayou | BY-S27-06 | Corrective maintenance | P3 within 10 days | 2026-02-23 | 2026-03-01 | 2026-03-09 | Internal line |  | 1835.26 | Completed | No
WO-26-001841 | 5.6 | Bayou | BY-S29-04 | Corrective maintenance | P4 planned | 2026-02-23 | 2026-03-28 | 2026-03-28 | Internal line |  | 1174.01 | Completed | No
WO-26-001842 | 9.9 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-02-23 | 2026-02-27 | 2026-02-27 | Underground crew |  | 583.22 | Completed | No
WO-26-001843 | 6.2 | Bayou | BY-S13-04 | Corrective maintenance | P3 within 10 days | 2026-02-23 | 2026-03-01 | 2026-03-01 | Internal line |  | 922.77 | Completed | No
WO-26-001844 | 1.2 | Bayou | BY-S04-01 | Meter exchange | P4 planned | 2026-02-23 | 2026-04-17 | 2026-04-17 | Meter technician |  | 166.66 | Completed | No
WO-26-001845 | 1.4 | Bayou | BY-S19-03 | Meter exchange | P4 planned | 2026-02-23 | 2026-04-11 | 2026-04-11 | Meter technician |  | 125.01 | Completed | No
WO-26-001846 | 1.4 | Bayou | BY-S15-01 | Meter exchange | P3 within 10 days | 2026-02-23 | 2026-03-04 | 2026-03-05 | Meter technician |  | 149.09 | Completed | No
WO-26-001847 | 1.4 | Bayou | BY-S14-02 | Meter exchange | P4 planned | 2026-02-23 | 2026-03-10 | 2026-03-12 | Meter technician |  | 77.48 | Completed | No
WO-26-001848 | 10.9 | Bayou | BY-S26-05 | Pole replacement | P4 planned | 2026-02-23 | 2026-03-07 | 2026-03-07 | Contract line | CT-03 | 2499.18 | Completed | No
WO-26-001849 | 17.5 | Bayou | BY-S29-04 | Pole replacement | P4 planned | 2026-02-23 | 2026-03-03 | 2026-03-03 | Internal line |  | 1922.32 | Completed | No
WO-26-001850 | 19.3 | Bayou | BY-S26-05 | Pole replacement | P4 planned | 2026-02-23 | 2026-03-31 | 2026-03-31 | Internal line |  | 2614.61 | Completed | No
WO-26-001851 | 5.8 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-02-23 | 2026-04-16 | 2026-04-16 | Contract line | CT-03 | 262.75 | Completed | No
WO-26-001852 | 1 | Bayou | BY-S09-02 | Service order - field | P3 within 10 days | 2026-02-23 | 2026-03-05 | 2026-03-13 | Meter technician |  | 32.81 | Completed | No
WO-26-001853 | 2 | Bayou | BY-S07-03 | Service order - field | P3 within 10 days | 2026-02-23 | 2026-02-27 | 2026-02-27 | Meter technician |  | 10.63 | Completed | No
WO-26-001854 | 1.4 | Bayou | BY-S18-02 | Service order - field | P2 same day | 2026-02-23 | 2026-02-24 | 2026-02-24 | Meter technician |  | 35.13 | Completed | No
WO-26-001855 |  | Bayou | BY-S04-02 | Service order - field | P3 within 10 days | 2026-02-23 | 2026-03-01 |  | Meter technician |  |  | Cancelled | No
WO-26-001856 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-23 | 2026-03-05 | 2026-03-05 | Contract line | CT-04 | 120.79 | Completed | No
WO-26-001857 | 7.6 | Bayou | BY-S21-03 | Transformer replacement | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Internal line |  | 11364.71 | Completed | No
WO-26-001858 | 12.9 | Bayou | BY-S03-02 | Transformer replacement | P2 same day | 2026-02-23 | 2026-02-23 | 2026-02-23 | Contract line | CT-04 | 3216.69 | Completed | No
WO-26-001859 | 2.7 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Troubleman |  | 124.22 | Completed | No
WO-26-001860 | 3.7 | Bayou | BY-S11-01 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Internal line |  | 162.59 | Completed | No
WO-26-001861 | 4.4 | Bayou | BY-S04-01 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Troubleman |  | 164.6 | Completed | No
WO-26-001862 | 8.1 | Crossroads | CR-S04-02 | Corrective maintenance | P3 within 10 days | 2026-02-23 | 2026-02-28 | 2026-03-01 | Internal line |  | 469.22 | Completed | No
WO-26-001863 | 5.7 | Crossroads | CR-S27-03 | Corrective maintenance | P3 within 10 days | 2026-02-23 | 2026-03-03 | 2026-03-03 | Internal line |  | 314.4 | Completed | No
WO-26-001864 | 5.2 | Crossroads | CR-S04-01 | Corrective maintenance | P3 within 10 days | 2026-02-23 | 2026-02-28 | 2026-02-28 | Internal line |  | 1472.39 | Completed | No
WO-26-001865 | 1.1 | Crossroads | CR-S32-03 | Meter exchange | P3 within 10 days | 2026-02-23 | 2026-03-05 | 2026-03-09 | Meter technician |  | 171.12 | Completed | No
WO-26-001866 | 1.3 | Crossroads | CR-S04-06 | Meter exchange | P4 planned | 2026-02-23 | 2026-04-17 | 2026-04-25 | Meter technician |  | 86.97 | Completed | No
WO-26-001867 | 0.9 | Crossroads | CR-S19-03 | Meter exchange | P4 planned | 2026-02-23 | 2026-04-21 | 2026-04-21 | Meter technician |  | 134.42 | Completed | No
WO-26-001868 | 0.6 | Crossroads | CR-S14-03 | Meter exchange | P4 planned | 2026-02-23 | 2026-04-07 | 2026-04-09 | Meter technician |  | 89.16 | Completed | No
WO-26-001869 | 12.4 | Crossroads | CR-S09-02 | New service - small | P3 within 10 days | 2026-02-23 | 2026-03-03 | 2026-03-03 | Underground crew |  | 4029.69 | Completed | No
WO-26-001870 | 16.8 | Crossroads | CR-S24-03 | Pole replacement | P3 within 10 days | 2026-02-23 | 2026-02-26 | 2026-02-26 | Contract line | CT-02 | 2028.73 | Completed | No
WO-26-001871 | 3.4 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-02-23 | 2026-03-03 | 2026-03-04 | Internal line |  | 374.1 | Completed | No
WO-26-001872 | 3.5 | Crossroads | CR-S09-04 | Preventive maintenance | P4 planned | 2026-02-23 | 2026-04-14 | 2026-04-15 | Internal line |  | 473.37 | Completed | No
WO-26-001873 | 1.9 | Crossroads | CR-S04-06 | Service order - field | P3 within 10 days | 2026-02-23 | 2026-02-25 | 2026-02-25 | Meter technician |  | 13.64 | Completed | No
WO-26-001874 | 1.7 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-02-23 | 2026-02-24 | 2026-02-24 | Meter technician |  | 11.29 | Completed | No
WO-26-001875 | 1.6 | Crossroads | CR-S30-07 | Service order - field | P2 same day | 2026-02-23 | 2026-02-23 | 2026-02-23 | Meter technician |  | 0.94 | Completed | No
WO-26-001876 | 1.1 | Crossroads | CR-S24-03 | Service order - field | P3 within 10 days | 2026-02-23 | 2026-02-28 | 2026-03-01 | Meter technician |  | 12.88 | Completed | No
WO-26-001877 | 2.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-23 | 2026-03-03 | 2026-03-07 | Contract line | CT-02 | 268.2 | Completed | No
WO-26-001878 | 8 | Crossroads | CR-S03-01 | Transformer replacement | P2 same day | 2026-02-23 | 2026-02-24 | 2026-02-24 | Internal line |  | 11002.13 | Completed | No
WO-26-001879 | 5.7 | Crossroads | CR-S04-02 | Trouble - no power | P2 same day | 2026-02-23 | 2026-02-23 | 2026-02-23 | Troubleman |  | 74.24 | Completed | No
WO-26-001880 | 4 | Crossroads | CR-S08-02 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Troubleman |  | 29.99 | Completed | No
WO-26-001881 | 5.3 | Crossroads | CR-S26-05 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Internal line |  | 319.02 | Completed | No
WO-26-001882 | 3.4 | Crossroads | CR-S21-03 | Trouble - no power | P2 same day | 2026-02-23 | 2026-02-24 | 2026-02-24 | Troubleman |  | 109 | Completed | No
WO-26-001883 | 2 | Crossroads | CR-S07-02 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Troubleman |  | 185.51 | Completed | No
WO-26-001884 | 3.6 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Troubleman |  | 297.65 | Completed | No
WO-26-001885 | 3.7 | Crossroads | CR-S13-02 | Trouble - no power | P1 emergency | 2026-02-23 | 2026-02-23 | 2026-02-23 | Internal line |  | 294.14 | Completed | No
WO-26-001886 | 2.7 | Crossroads | CR-S17-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-23 | 2026-03-05 | 2026-03-09 | Troubleman |  | 89.61 | Completed | No
WO-26-001887 | 1.8 | Crossroads | CR-S24-03 | Trouble - partial or voltage | P2 same day | 2026-02-23 | 2026-02-24 | 2026-02-24 | Troubleman |  | 13.6 | Completed | No
WO-26-001888 | 4.6 | Bayou | BY-S18-07 | Corrective maintenance | P3 within 10 days | 2026-02-24 | 2026-02-27 | 2026-02-28 | Underground crew |  | 1124.63 | Completed | No
WO-26-001889 | 7.8 | Bayou | BY-S20-03 | Corrective maintenance | P3 within 10 days | 2026-02-24 | 2026-02-27 | 2026-02-28 | Contract line | CT-04 | 1959.87 | Completed | No
WO-26-001890 | 8.7 | Bayou | BY-S15-06 | Corrective maintenance | P3 within 10 days | 2026-02-24 | 2026-03-04 | 2026-03-04 | Contract line | CT-03 | 2350.11 | Completed | No
WO-26-001891 | 3.5 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-02-24 | 2026-03-04 | 2026-03-05 | Contract line | CT-04 | 1109.75 | Completed | No
WO-26-001892 | 8 | Bayou | BY-S10-03 | Corrective maintenance | P4 planned | 2026-02-24 | 2026-04-11 | 2026-04-13 | Internal line |  | 1046.02 | Completed | No
WO-26-001893 | 4.5 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-02-24 | 2026-02-28 | 2026-02-28 | Contract line | CT-03 | 333.11 | Completed | No
WO-26-001894 | 1.2 | Bayou | BY-S26-06 | Meter exchange | P3 within 10 days | 2026-02-24 | 2026-02-25 | 2026-02-25 | Meter technician |  | 145.24 | Completed | No
WO-26-001895 | 1.2 | Bayou | BY-S01-02 | Meter exchange | P3 within 10 days | 2026-02-24 | 2026-02-28 | 2026-02-28 | Meter technician |  | 139.18 | Completed | No
WO-26-001896 | 10.8 | Bayou | BY-S19-02 | New service - small | P3 within 10 days | 2026-02-24 | 2026-03-02 | 2026-03-02 | Contract line | CT-04 | 3436.25 | Completed | No
WO-26-001897 | 13.6 | Bayou | BY-S19-02 | New service - small | P4 planned | 2026-02-24 | 2026-03-08 | 2026-03-08 | Internal line |  | 3130.46 | Completed | No
WO-26-001898 | 15 | Bayou | BY-S10-01 | New service - small | P4 planned | 2026-02-24 | 2026-03-26 | 2026-03-30 | Contract line | CT-04 | 3752.63 | Completed | No
WO-26-001899 | 9.8 | Bayou | BY-S18-03 | New service - small | P4 planned | 2026-02-24 | 2026-03-25 | 2026-03-27 | Contract line | CT-04 | 1191.47 | Completed | No
WO-26-001900 | 10.2 | Bayou | BY-S05-02 | Pole replacement | P2 same day | 2026-02-24 | 2026-02-24 | 2026-02-24 | Contract line | CT-03 | 1951.83 | Completed | No
WO-26-001901 | 5.9 | Bayou | BY-S19-03 | Preventive maintenance | P4 planned | 2026-02-24 | 2026-03-23 | 2026-03-24 | Contract line | CT-04 | 79.29 | Completed | No
WO-26-001902 | 2.1 | Bayou | BY-S30-03 | Preventive maintenance | P4 planned | 2026-02-24 | 2026-03-19 | 2026-03-19 | Underground crew |  | 505.4 | Completed | No
WO-26-001903 | 6.7 | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-02-24 | 2026-04-14 | 2026-04-14 | Internal line |  | 514.24 | Completed | No
WO-26-001904 | 1.5 | Bayou | BY-S17-02 | Service order - field | P2 same day | 2026-02-24 | 2026-02-24 | 2026-02-24 | Meter technician |  | 35.44 | Completed | No
WO-26-001905 | 1.8 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-02-24 | 2026-02-25 | 2026-02-25 | Meter technician |  | 34.01 | Completed | No
WO-26-001906 | 1.5 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-02-24 | 2026-03-04 | 2026-03-04 | Meter technician |  | 8.78 | Completed | No
WO-26-001907 | 1.9 | Bayou | BY-S23-05 | Service order - field | P2 same day | 2026-02-24 | 2026-02-25 | 2026-02-25 | Meter technician |  | 34.68 | Completed | No
WO-26-001908 | 1.4 | Bayou | BY-S10-05 | Service order - field | P2 same day | 2026-02-24 | 2026-02-24 | 2026-02-24 | Meter technician |  | 14.19 | Completed | No
WO-26-001909 | 0.9 | Bayou | BY-S07-05 | Service order - field | P3 within 10 days | 2026-02-24 | 2026-02-25 | 2026-03-05 | Meter technician |  | 28.28 | Completed | No
WO-26-001910 | 1.9 | Bayou | BY-S15-01 | Service order - field | P2 same day | 2026-02-24 | 2026-02-24 | 2026-02-24 | Meter technician |  | 31.99 | Completed | No
WO-26-001911 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-24 | 2026-02-28 | 2026-02-28 | Contract line | CT-03 | 432.02 | Completed | No
WO-26-001912 | 10.6 | Bayou | BY-S25-05 | Transformer replacement | P3 within 10 days | 2026-02-24 | 2026-03-06 | 2026-03-10 | Internal line |  | 9564.16 | Completed | No
WO-26-001913 | 3.1 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-02-24 | 2026-02-24 | 2026-02-24 | Internal line |  | 22.44 | Completed | No
WO-26-001914 | 4.5 | Bayou | BY-S11-02 | Trouble - no power | P1 emergency | 2026-02-24 | 2026-02-24 | 2026-02-24 | Troubleman |  | 340.68 | Completed | No
WO-26-001915 | 4.5 | Bayou | BY-S06-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-24 | 2026-03-02 | 2026-03-02 | Troubleman |  | 147.35 | Completed | No
WO-26-001916 | 3 | Bayou | BY-S21-03 | Trouble - partial or voltage | P2 same day | 2026-02-24 | 2026-02-24 | 2026-02-24 | Troubleman |  | 95.11 | Completed | No
WO-26-001917 | 6.9 | Crossroads | CR-S04-04 | Corrective maintenance | P3 within 10 days | 2026-02-24 | 2026-03-04 | 2026-03-04 | Underground crew |  | 1970 | Completed | No
WO-26-001918 | 8.9 | Crossroads | CR-S22-03 | Corrective maintenance | P4 planned | 2026-02-24 | 2026-03-21 | 2026-03-21 | Underground crew |  | 1273.05 | Completed | No
WO-26-001919 | 6.3 | Crossroads | CR-S07-02 | Corrective maintenance | P4 planned | 2026-02-24 | 2026-04-20 | 2026-04-21 | Internal line |  | 1960.47 | Completed | No
WO-26-001920 | 0.5 | Crossroads | CR-S27-02 | Meter exchange | P4 planned | 2026-02-24 | 2026-03-26 | 2026-03-27 | Meter technician |  | 106.68 | Completed | No
WO-26-001921 | 15.2 | Crossroads | CR-S23-03 | Pole replacement | P4 planned | 2026-02-24 | 2026-03-17 | 2026-03-17 | Internal line |  | 2447.95 | Completed | No
WO-26-001922 | 5.9 | Crossroads | CR-S25-04 | Preventive maintenance | P4 planned | 2026-02-24 | 2026-04-25 | 2026-04-25 | Internal line |  | 404.84 | Completed | No
WO-26-001923 | 1.6 | Crossroads | CR-S29-03 | Service order - field | P3 within 10 days | 2026-02-24 | 2026-02-26 | 2026-02-26 | Meter technician |  | 13.94 | Completed | No
WO-26-001924 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-02-24 | 2026-03-06 | 2026-03-06 | Contract line | CT-02 | 83.41 | Completed | No
WO-26-001925 | 2.6 | Crossroads |  | Streetlight | P4 planned | 2026-02-24 | 2026-03-22 | 2026-03-26 | Internal line |  | 80.03 | Completed | No
WO-26-001926 | 1.2 | Crossroads |  | Streetlight | P4 planned | 2026-02-24 | 2026-03-13 | 2026-03-17 | Internal line |  | 179.26 | Completed | No
WO-26-001927 | 4.2 | Crossroads | CR-S16-05 | Trouble - no power | P1 emergency | 2026-02-24 | 2026-02-24 | 2026-02-24 | Troubleman |  | 30.3 | Completed | No
WO-26-001928 | 3.1 | Crossroads | CR-S04-02 | Trouble - no power | P1 emergency | 2026-02-24 | 2026-02-24 | 2026-02-24 | Troubleman |  | 309.59 | Completed | No
WO-26-001929 | 5.4 | Crossroads | CR-S09-03 | Trouble - no power | P1 emergency | 2026-02-24 | 2026-02-24 | 2026-02-24 | Troubleman |  | 27.35 | Completed | No
WO-26-001930 | 4.8 | Crossroads | CR-S23-02 | Trouble - no power | P2 same day | 2026-02-24 | 2026-02-25 | 2026-02-25 | Troubleman |  | 258.14 | Completed | No
WO-26-001931 | 4.4 | Crossroads | CR-S14-05 | Trouble - partial or voltage | P2 same day | 2026-02-24 | 2026-02-24 | 2026-02-24 | Internal line |  | 215.92 | Completed | No
WO-26-001932 |  | Bayou | BY-S20-02 | Corrective maintenance | P2 same day | 2026-02-25 | 2026-02-26 |  | Underground crew |  |  | Cancelled | No
WO-26-001933 | 4.7 | Bayou | BY-S12-04 | Corrective maintenance | P3 within 10 days | 2026-02-25 | 2026-03-03 | 2026-03-11 | Internal line |  | 1099.74 | Completed | No
WO-26-001934 | 8.8 | Bayou | BY-S05-03 | Corrective maintenance | P3 within 10 days | 2026-02-25 | 2026-03-03 | 2026-03-07 | Internal line |  | 1792.75 | Completed | No
WO-26-001935 | 4.9 | Bayou | BY-S15-06 | Corrective maintenance | P4 planned | 2026-02-25 | 2026-04-04 | 2026-04-04 | Contract line | CT-04 | 1605.56 | Completed | No
WO-26-001936 | 1.1 | Bayou | BY-S08-01 | Meter exchange | P3 within 10 days | 2026-02-25 | 2026-03-04 | 2026-03-08 | Meter technician |  | 132.25 | Completed | No
WO-26-001937 | 1.5 | Bayou | BY-S19-02 | Meter exchange | P4 planned | 2026-02-25 | 2026-03-19 | 2026-03-21 | Meter technician |  | 118.21 | Completed | No
WO-26-001938 | 1.3 | Bayou | BY-S04-03 | Meter exchange | P3 within 10 days | 2026-02-25 | 2026-03-07 | 2026-03-07 | Meter technician |  | 108.64 | Completed | No
WO-26-001939 | 1.5 | Bayou | BY-S11-03 | Meter exchange | P4 planned | 2026-02-25 | 2026-04-18 | 2026-04-18 | Meter technician |  | 160.72 | Completed | No
WO-26-001940 | 0.9 | Bayou | BY-S27-06 | Meter exchange | P4 planned | 2026-02-25 | 2026-03-12 | 2026-03-12 | Meter technician |  | 133.87 | Completed | No
WO-26-001941 | 1 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-02-25 | 2026-03-02 | 2026-03-02 | Meter technician |  | 127.74 | Completed | No
WO-26-001942 | 14 | Bayou | BY-S13-05 | New service - small | P4 planned | 2026-02-25 | 2026-03-22 | 2026-03-22 | Internal line |  | 1481.05 | Completed | No
WO-26-001943 | 18.4 | Bayou | BY-S23-03 | Pole replacement | P4 planned | 2026-02-25 | 2026-04-14 | 2026-04-14 | Contract line | CT-03 | 1289.54 | Completed | No
WO-26-001944 | 10.2 | Bayou | BY-S13-06 | Pole replacement | P4 planned | 2026-02-25 | 2026-04-06 | 2026-04-07 | Contract line | CT-04 | 2473.47 | Completed | No
WO-26-001945 | 6 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-02-25 | 2026-03-12 | 2026-03-13 | Internal line |  | 498.98 | Completed | No
WO-26-001946 | 4.6 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-02-25 | 2026-03-12 | 2026-03-16 | Internal line |  | 71.78 | Completed | No
WO-26-001947 | 1 | Bayou | BY-S18-01 | Service order - field | P3 within 10 days | 2026-02-25 | 2026-02-26 | 2026-03-06 | Meter technician |  | 28.77 | Completed | No
WO-26-001948 | 1.1 | Bayou | BY-S26-04 | Service order - field | P3 within 10 days | 2026-02-25 | 2026-02-28 | 2026-02-28 | Meter technician |  | 32.1 | Completed | No
WO-26-001949 | 1.9 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-02-25 | 2026-02-27 | 2026-02-27 | Meter technician |  | 25.65 | Completed | No
WO-26-001950 | 0.6 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-02-25 | 2026-02-26 | 2026-02-26 | Meter technician |  | 34.6 | Completed | No
WO-26-001951 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-25 | 2026-03-03 | 2026-03-04 | Contract line | CT-04 | 191.64 | Completed | No
WO-26-001952 | 5.9 | Bayou | BY-S18-07 | Trouble - no power | P1 emergency | 2026-02-25 | 2026-02-25 | 2026-02-25 | Troubleman |  | 202.86 | Completed | No
WO-26-001953 | 4.9 | Bayou | BY-S23-03 | Trouble - no power | P2 same day | 2026-02-25 | 2026-02-25 | 2026-02-25 | Troubleman |  | 253.25 | Completed | No
WO-26-001954 | 3.7 | Bayou | BY-S20-01 | Trouble - no power | P1 emergency | 2026-02-25 | 2026-02-25 | 2026-02-25 | Troubleman |  | 331.35 | Completed | No
WO-26-001955 | 5.5 | Bayou | BY-S09-02 | Trouble - no power | P1 emergency | 2026-02-25 | 2026-02-25 | 2026-02-25 | Troubleman |  | 323.33 | Completed | No
WO-26-001956 | 2.9 | Bayou | BY-S07-05 | Trouble - partial or voltage | P3 within 10 days | 2026-02-25 | 2026-02-26 | 2026-02-26 | Troubleman |  | 89.87 | Completed | No
WO-26-001957 | 3.1 | Bayou | BY-S18-03 | Trouble - partial or voltage | P3 within 10 days | 2026-02-25 | 2026-02-28 | 2026-03-08 | Troubleman |  | 110.44 | Completed | No
WO-26-001958 | 11.7 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-02-25 | 2026-03-04 | 2026-03-04 | Underground crew |  | 748.54 | Completed | No
WO-26-001959 | 11.4 | Crossroads | CR-S19-04 | Corrective maintenance | P2 same day | 2026-02-25 | 2026-02-25 | 2026-02-25 | Internal line |  | 208.51 | Completed | No
WO-26-001960 | 1.3 | Crossroads | CR-S12-01 | Meter exchange | P3 within 10 days | 2026-02-25 | 2026-03-05 | 2026-03-05 | Meter technician |  | 142.38 | Completed | No
WO-26-001961 | 1.3 | Crossroads | CR-S22-03 | Meter exchange | P3 within 10 days | 2026-02-25 | 2026-03-04 | 2026-03-04 | Meter technician |  | 177.52 | Completed | No
WO-26-001962 | 0.5 | Crossroads | CR-S08-03 | Meter exchange | P4 planned | 2026-02-25 | 2026-04-03 | 2026-04-04 | Meter technician |  | 138.1 | Completed | No
WO-26-001963 | 1 | Crossroads | CR-S23-01 | Meter exchange | P3 within 10 days | 2026-02-25 | 2026-02-27 | 2026-02-28 | Meter technician |  | 172.09 | Completed | No
WO-26-001964 | 0.9 | Crossroads | CR-S18-04 | Meter exchange | P4 planned | 2026-02-25 | 2026-03-09 | 2026-03-10 | Meter technician |  | 162.78 | Completed | No
WO-26-001965 | 14.4 | Crossroads | CR-S31-03 | New service - small | P4 planned | 2026-02-25 | 2026-04-17 | 2026-04-17 | Contract line | CT-02 | 382.38 | Completed | No
WO-26-001966 | 2 | Crossroads | CR-S04-06 | Preventive maintenance | P4 planned | 2026-02-25 | 2026-03-15 | 2026-03-16 | Internal line |  | 339.9 | Completed | No
WO-26-001967 | 2.1 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-02-25 | 2026-03-19 | 2026-03-21 | Underground crew |  | 421.17 | Completed | No
WO-26-001968 | 0.9 | Crossroads | CR-S16-05 | Service order - field | P3 within 10 days | 2026-02-25 | 2026-03-04 | 2026-03-04 | Meter technician |  | 19.94 | Completed | No
WO-26-001969 | 1.9 | Crossroads | CR-S18-02 | Service order - field | P2 same day | 2026-02-25 | 2026-02-26 | 2026-02-26 | Meter technician |  | 16.42 | Completed | No
WO-26-001970 | 1.3 | Crossroads | CR-S09-05 | Service order - field | P2 same day | 2026-02-25 | 2026-02-25 | 2026-02-25 | Meter technician |  | 11.42 | Completed | No
WO-26-001971 | 0.9 | Crossroads | CR-S30-07 | Service order - field | P3 within 10 days | 2026-02-25 | 2026-02-27 | 2026-02-27 | Meter technician |  | 10.17 | Completed | No
WO-26-001972 | 13.2 | Crossroads | CR-S07-05 | Transformer replacement | P3 within 10 days | 2026-02-25 | 2026-03-01 | 2026-03-01 | Internal line |  | 7897.74 | Completed | No
WO-26-001973 | 5.9 | Crossroads | CR-S27-03 | Trouble - no power | P1 emergency | 2026-02-25 | 2026-02-25 | 2026-02-25 | Troubleman |  | 193.91 | Completed | No
WO-26-001974 | 5 | Crossroads | CR-S30-07 | Trouble - no power | P1 emergency | 2026-02-25 | 2026-02-25 | 2026-02-25 | Internal line |  | 68.27 | Completed | No
WO-26-001975 | 4.7 | Crossroads | CR-S24-04 | Trouble - no power | P1 emergency | 2026-02-25 | 2026-02-25 | 2026-02-25 | Troubleman |  | 49.76 | Completed | No
WO-26-001976 | 1.7 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-02-25 | 2026-02-26 | 2026-02-26 | Troubleman |  | 61.49 | Completed | No
WO-26-001977 | 6 | Bayou | BY-S15-02 | Corrective maintenance | P3 within 10 days | 2026-02-26 | 2026-03-03 | 2026-03-04 | Internal line |  | 134.33 | Completed | No
WO-26-001978 | 0.9 | Bayou | BY-S25-02 | Meter exchange | P3 within 10 days | 2026-02-26 | 2026-03-03 | 2026-03-04 | Meter technician |  | 172.31 | Completed | No
WO-26-001979 | 1.1 | Bayou | BY-S12-02 | Meter exchange | P3 within 10 days | 2026-02-26 | 2026-03-04 | 2026-03-05 | Meter technician |  | 171.95 | Completed | No
WO-26-001980 | 1.1 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-02-26 | 2026-03-03 | 2026-03-04 | Meter technician |  | 179.14 | Completed | No
WO-26-001981 | 11.3 | Bayou | BY-S27-05 | New service - small | P4 planned | 2026-02-26 | 2026-03-08 | 2026-03-08 | Contract line | CT-03 | 3651.63 | Completed | No
WO-26-001982 | 5 | Bayou | BY-S26-04 | New service - small | P4 planned | 2026-02-26 | 2026-03-25 | 2026-03-29 | Contract line | CT-04 | 2812.84 | Completed | No
WO-26-001983 | 7.9 | Bayou | BY-S21-01 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-04-23 | 2026-04-24 | Underground crew |  | 25.07 | Completed | No
WO-26-001984 | 5.1 | Bayou | BY-S21-05 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-03-12 | 2026-03-12 | Underground crew |  | 465.55 | Completed | No
WO-26-001985 | 5.5 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-04-19 | 2026-04-19 | Contract line | CT-04 | 472.37 | Completed | No
WO-26-001986 | 5.4 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-04-23 | 2026-04-24 | Contract line | CT-03 | 47.71 | Completed | No
WO-26-001987 | 5 | Bayou | BY-S23-01 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-03-13 | 2026-03-13 | Internal line |  | 565.79 | Completed | No
WO-26-001988 | 1 | Bayou | BY-S19-01 | Service order - field | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Meter technician |  | 7.74 | Completed | No
WO-26-001989 | 1.5 | Bayou | BY-S13-06 | Service order - field | P3 within 10 days | 2026-02-26 | 2026-03-03 | 2026-03-03 | Meter technician |  | 9.79 | Completed | No
WO-26-001990 | 2 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Meter technician |  | 22.61 | Completed | No
WO-26-001991 |  | Bayou | BY-S28-01 | Service order - field | P2 same day | 2026-02-26 | 2026-02-26 |  | Meter technician |  |  | Cancelled | No
WO-26-001992 | 0.9 | Bayou | BY-S26-04 | Service order - field | P3 within 10 days | 2026-02-26 | 2026-03-06 | 2026-03-06 | Meter technician |  | 22.81 | Completed | No
WO-26-001993 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-26 | 2026-03-04 | 2026-03-06 | Contract line | CT-03 | 294.13 | Completed | No
WO-26-001994 | 13.3 | Bayou | BY-S13-02 | Transformer replacement | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Contract line | CT-04 | 8604.53 | Completed | No
WO-26-001995 | 12.9 | Bayou | BY-S04-01 | Transformer replacement | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Contract line | CT-04 | 7596.42 | Completed | No
WO-26-001996 | 2.8 | Bayou | BY-S23-05 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 85.6 | Completed | No
WO-26-001997 | 5.6 | Bayou | BY-S14-01 | Trouble - no power | P2 same day | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 46.68 | Completed | No
WO-26-001998 | 2.3 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 42.74 | Completed | No
WO-26-001999 | 3.6 | Bayou | BY-S17-01 | Trouble - no power | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Troubleman |  | 144.63 | Completed | No
WO-26-002000 | 5.6 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 142.72 | Completed | No
WO-26-002001 | 2.1 | Bayou | BY-S27-05 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 273.16 | Completed | No
WO-26-002002 | 2.2 | Bayou | BY-S21-02 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 347.43 | Completed | No
WO-26-002003 | 3.1 | Bayou | BY-S15-05 | Trouble - partial or voltage | P3 within 10 days | 2026-02-26 | 2026-03-05 | 2026-03-06 | Troubleman |  | 165.7 | Completed | No
WO-26-002004 | 5.5 | Crossroads | CR-S07-05 | Corrective maintenance | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Internal line |  | 1955.21 | Completed | No
WO-26-002005 | 7.4 | Crossroads | CR-S31-02 | Corrective maintenance | P3 within 10 days | 2026-02-26 | 2026-03-07 | 2026-03-07 | Contract line | CT-02 | 1780.48 | Completed | No
WO-26-002006 | 7.1 | Crossroads | CR-S24-04 | Corrective maintenance | P4 planned | 2026-02-26 | 2026-04-07 | 2026-04-09 | Underground crew |  | 1922.95 | Completed | No
WO-26-002007 | 7.5 | Crossroads | CR-S24-01 | Corrective maintenance | P2 same day | 2026-02-26 | 2026-02-26 | 2026-02-26 | Underground crew |  | 971.78 | Completed | No
WO-26-002008 | 7.6 | Crossroads | CR-S13-04 | Corrective maintenance | P2 same day | 2026-02-26 | 2026-02-26 | 2026-02-26 | Internal line |  | 700.78 | Completed | No
WO-26-002009 | 0.7 | Crossroads | CR-S17-02 | Meter exchange | P4 planned | 2026-02-26 | 2026-04-27 | 2026-05-01 | Meter technician |  | 77.83 | Completed | No
WO-26-002010 | 0.9 | Crossroads | CR-S23-04 | Meter exchange | P3 within 10 days | 2026-02-26 | 2026-03-02 | 2026-03-04 | Meter technician |  | 86.35 | Completed | No
WO-26-002011 | 0.7 | Crossroads | CR-S07-03 | Meter exchange | P3 within 10 days | 2026-02-26 | 2026-03-07 | 2026-03-08 | Meter technician |  | 152.82 | Completed | No
WO-26-002012 | 1.2 | Crossroads | CR-S31-01 | Meter exchange | P4 planned | 2026-02-26 | 2026-04-10 | 2026-04-10 | Meter technician |  | 160.41 | Completed | No
WO-26-002013 | 8.2 | Crossroads | CR-S22-03 | New service - small | P4 planned | 2026-02-26 | 2026-04-11 | 2026-04-12 | Internal line |  | 3418.83 | Completed | No
WO-26-002014 | 3.5 | Crossroads | CR-S23-01 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-03-22 | 2026-03-22 | Underground crew |  | 267 | Completed | No
WO-26-002015 | 3.7 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-02-26 | 2026-04-16 | 2026-04-16 | Internal line |  | 572.44 | Completed | No
WO-26-002016 | 1 | Crossroads | CR-S24-03 | Service order - field | P3 within 10 days | 2026-02-26 | 2026-03-03 | 2026-03-11 | Meter technician |  | 32.82 | Completed | No
WO-26-002017 | 1.1 | Crossroads | CR-S15-01 | Service order - field | P3 within 10 days | 2026-02-26 | 2026-03-04 | 2026-03-04 | Meter technician |  | 19 | Completed | No
WO-26-002018 | 2.7 | Crossroads | CR-S13-06 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 27.89 | Completed | No
WO-26-002019 | 4.3 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Internal line |  | 227.2 | Completed | No
WO-26-002020 | 4.9 | Crossroads | CR-S27-03 | Trouble - no power | P1 emergency | 2026-02-26 | 2026-02-26 | 2026-02-26 | Troubleman |  | 235.89 | Completed | No
WO-26-002021 | 2.6 | Crossroads | CR-S15-01 | Trouble - no power | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Troubleman |  | 27.47 | Completed | No
WO-26-002022 | 3.8 | Crossroads | CR-S18-01 | Trouble - no power | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Troubleman |  | 134.72 | Completed | No
WO-26-002023 | 1.7 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P2 same day | 2026-02-26 | 2026-02-27 | 2026-02-27 | Troubleman |  | 93.29 | Completed | No
WO-26-002024 | 4.9 | Bayou | BY-S17-04 | Corrective maintenance | P3 within 10 days | 2026-02-27 | 2026-03-09 | 2026-03-09 | Contract line | CT-04 | 1264.96 | Completed | No
WO-26-002025 | 3.1 | Bayou | BY-S10-04 | Corrective maintenance | P2 same day | 2026-02-27 | 2026-02-27 | 2026-02-27 | Internal line |  | 2396.89 | Completed | No
WO-26-002026 | 10.5 | Bayou | BY-S19-03 | Corrective maintenance | P3 within 10 days | 2026-02-27 | 2026-03-03 | 2026-03-03 | Internal line |  | 1968.98 | Completed | No
WO-26-002027 | 1.2 | Bayou | BY-S09-04 | Meter exchange | P3 within 10 days | 2026-02-27 | 2026-03-01 | 2026-03-01 | Meter technician |  | 134.01 | Completed | No
WO-26-002028 | 1.3 | Bayou | BY-S23-02 | Meter exchange | P3 within 10 days | 2026-02-27 | 2026-03-04 | 2026-03-04 | Meter technician |  | 162.74 | Completed | No
WO-26-002029 | 0.7 | Bayou | BY-S03-02 | Meter exchange | P4 planned | 2026-02-27 | 2026-03-11 | 2026-03-11 | Meter technician |  | 121.98 | Completed | No
WO-26-002030 | 1.4 | Bayou | BY-S28-03 | Meter exchange | P3 within 10 days | 2026-02-27 | 2026-02-28 | 2026-02-28 | Meter technician |  | 64.14 | Completed | No
WO-26-002031 | 8.8 | Bayou | BY-S12-03 | New service - small | P3 within 10 days | 2026-02-27 | 2026-03-05 | 2026-03-05 | Contract line | CT-04 | 3577.09 | Completed | No
WO-26-002032 | 5 | Bayou | BY-S13-05 | Preventive maintenance | P4 planned | 2026-02-27 | 2026-04-13 | 2026-04-17 | Internal line |  | 195.59 | Completed | No
WO-26-002033 | 6.2 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-02-27 | 2026-04-27 | 2026-05-01 | Internal line |  | 5.24 | Completed | No
WO-26-002034 | 1.9 | Bayou | BY-S09-03 | Service order - field | P2 same day | 2026-02-27 | 2026-02-28 | 2026-02-28 | Meter technician |  | 28.07 | Completed | No
WO-26-002035 |  | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-02-27 | 2026-02-28 |  | Meter technician |  |  | Cancelled | No
WO-26-002036 | 0.9 | Bayou | BY-S10-05 | Service order - field | P2 same day | 2026-02-27 | 2026-02-27 | 2026-02-27 | Meter technician |  | 8.57 | Completed | No
WO-26-002037 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-02-27 | 2026-03-07 | 2026-03-08 | Contract line | CT-03 | 310.25 | Completed | No
WO-26-002038 | 2.7 | Bayou |  | Streetlight | P4 planned | 2026-02-27 | 2026-04-12 | 2026-04-12 | Internal line |  | 440.37 | Completed | No
WO-26-002039 | 6 | Bayou | BY-S09-05 | Transformer replacement | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Contract line | CT-03 | 3317.65 | Completed | No
WO-26-002040 |  | Bayou | BY-S26-01 | Transformer replacement | P3 within 10 days | 2026-02-27 | 2026-02-28 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-002041 | 8.3 | Bayou | BY-S11-01 | Transformer replacement | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Internal line |  | 7683.06 | Completed | No
WO-26-002042 | 5.8 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Internal line |  | 170.82 | Completed | No
WO-26-002043 | 5.1 | Bayou | BY-S16-01 | Trouble - no power | P2 same day | 2026-02-27 | 2026-02-28 | 2026-02-28 | Troubleman |  | 211.11 | Completed | No
WO-26-002044 | 3.6 | Bayou | BY-S16-02 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Internal line |  | 308.53 | Completed | No
WO-26-002045 | 5.6 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 43.29 | Completed | No
WO-26-002046 | 2.3 | Bayou | BY-S07-05 | Trouble - partial or voltage | P2 same day | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 64.7 | Completed | No
WO-26-002047 | 4.3 | Bayou | BY-S11-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-27 | 2026-03-07 | 2026-03-07 | Troubleman |  | 119.89 | Completed | No
WO-26-002048 | 8.9 | Crossroads | CR-S28-02 | Corrective maintenance | P3 within 10 days | 2026-02-27 | 2026-03-01 | 2026-03-02 | Underground crew |  | 2275.23 | Completed | No
WO-26-002049 | 0.9 | Crossroads | CR-S01-03 | Meter exchange | P4 planned | 2026-02-27 | 2026-04-24 | 2026-04-24 | Meter technician |  | 80.08 | Completed | No
WO-26-002050 | 1.3 | Crossroads | CR-S28-01 | Meter exchange | P3 within 10 days | 2026-02-27 | 2026-02-28 | 2026-02-28 | Meter technician |  | 76.54 | Completed | No
WO-26-002051 | 12.9 | Crossroads | CR-S25-02 | New service - small | P3 within 10 days | 2026-02-27 | 2026-03-07 | 2026-03-09 | Internal line |  | 4165.15 | Completed | No
WO-26-002052 | 11 | Crossroads | CR-S25-01 | New service - small | P4 planned | 2026-02-27 | 2026-04-04 | 2026-04-06 | Contract line | CT-02 | 1261.22 | Completed | No
WO-26-002053 | 23.3 | Crossroads | CR-S17-03 | Pole replacement | P3 within 10 days | 2026-02-27 | 2026-03-01 | 2026-03-01 | Contract line | CT-01 | 3140.84 | Completed | No
WO-26-002054 | 4 | Crossroads | CR-S23-01 | Preventive maintenance | P4 planned | 2026-02-27 | 2026-04-10 | 2026-04-14 | Internal line |  | 119.06 | Completed | No
WO-26-002055 | 0.9 | Crossroads | CR-S06-02 | Service order - field | P3 within 10 days | 2026-02-27 | 2026-03-03 | 2026-03-03 | Meter technician |  | 24.84 | Completed | No
WO-26-002056 | 1.6 | Crossroads | CR-S08-02 | Service order - field | P2 same day | 2026-02-27 | 2026-02-28 | 2026-02-28 | Meter technician |  | 17.94 | Completed | No
WO-26-002057 | 1 | Crossroads | CR-S16-05 | Service order - field | P2 same day | 2026-02-27 | 2026-02-27 | 2026-02-27 | Meter technician |  | 33.1 | Completed | No
WO-26-002058 | 1.6 | Crossroads | CR-S19-04 | Service order - field | P2 same day | 2026-02-27 | 2026-02-28 | 2026-02-28 | Meter technician |  | 13.83 | Completed | No
WO-26-002059 | 1.7 | Crossroads | CR-S16-03 | Service order - field | P2 same day | 2026-02-27 | 2026-02-28 | 2026-02-28 | Meter technician |  | 17.8 | Completed | No
WO-26-002060 | 1.4 | Crossroads | CR-S09-05 | Service order - field | P2 same day | 2026-02-27 | 2026-02-27 | 2026-02-27 | Meter technician |  | 11.72 | Completed | No
WO-26-002061 | 6.1 | Crossroads | CR-S25-01 | Transformer replacement | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Contract line | CT-02 | 10290.87 | Completed | No
WO-26-002062 | 3.9 | Crossroads | CR-S12-02 | Trouble - no power | P2 same day | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 43.4 | Completed | No
WO-26-002063 | 3.2 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 43.89 | Completed | No
WO-26-002064 | 5.9 | Crossroads | CR-S24-04 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 139.42 | Completed | No
WO-26-002065 | 5.4 | Crossroads | CR-S07-01 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 59.44 | Completed | No
WO-26-002066 | 3.4 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Troubleman |  | 225.3 | Completed | No
WO-26-002067 | 2.2 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-02-27 | 2026-02-27 | 2026-02-27 | Internal line |  | 286.13 | Completed | No
WO-26-002068 | 3.4 | Crossroads | CR-S32-01 | Trouble - partial or voltage | P3 within 10 days | 2026-02-27 | 2026-03-02 | 2026-03-06 | Troubleman |  | 209.16 | Completed | No
WO-26-002069 | 3.2 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 222.95 | Completed | No
WO-26-002070 |  | Bayou | BY-S10-04 | Trouble - no power | P2 same day | 2026-02-28 | 2026-03-01 |  | Troubleman |  |  | Cancelled | No
WO-26-002071 | 4.3 | Bayou | BY-S01-01 | Trouble - no power | P2 same day | 2026-02-28 | 2026-03-01 | 2026-03-01 | Troubleman |  | 290.86 | Completed | No
WO-26-002072 | 2.9 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 263.01 | Completed | No
WO-26-002073 | 4.3 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 98.74 | Completed | No
WO-26-002074 | 3.1 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-02-28 | 2026-03-01 | 2026-03-01 | Troubleman |  | 117.26 | Completed | No
WO-26-002075 | 4.1 | Bayou | BY-S01-01 | Trouble - partial or voltage | P2 same day | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 1.17 | Completed | No
WO-26-002076 | 1.2 | Crossroads | CR-S14-04 | Service order - field | P2 same day | 2026-02-28 | 2026-03-01 | 2026-03-01 | Meter technician |  | 17.87 | Completed | No
WO-26-002077 | 3.1 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 317.78 | Completed | No
WO-26-002078 | 3.8 | Crossroads | CR-S15-03 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 111.8 | Completed | No
WO-26-002079 | 4.7 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 312.07 | Completed | No
WO-26-002080 | 4 | Crossroads | CR-S31-01 | Trouble - no power | P2 same day | 2026-02-28 | 2026-03-01 | 2026-03-01 | Troubleman |  | 315.41 | Completed | No
WO-26-002081 | 2.2 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 90.46 | Completed | No
WO-26-002082 | 5.9 | Crossroads | CR-S18-03 | Trouble - no power | P1 emergency | 2026-02-28 | 2026-02-28 | 2026-02-28 | Troubleman |  | 242.6 | Completed | No
WO-26-002083 | 2.9 | Crossroads | CR-S09-02 | Trouble - partial or voltage | P2 same day | 2026-02-28 | 2026-03-01 | 2026-03-01 | Internal line |  | 162.6 | Completed | No
WO-26-002084 | 2.8 | Crossroads | CR-S08-02 | Trouble - partial or voltage | P2 same day | 2026-02-28 | 2026-03-01 | 2026-03-01 | Troubleman |  | 175.71 | Completed | No
WO-26-002085 | 1.9 | Bayou | BY-S24-05 | Service order - field | P2 same day | 2026-03-01 | 2026-03-01 | 2026-03-01 | Meter technician |  | 24.95 | Completed | No
WO-26-002086 | 1.4 | Bayou | BY-S05-01 | Service order - field | P2 same day | 2026-03-01 | 2026-03-02 | 2026-03-02 | Meter technician |  | 0.72 | Completed | No
WO-26-002087 | 4 | Bayou | BY-S30-01 | Trouble - no power | P2 same day | 2026-03-01 | 2026-03-01 | 2026-03-01 | Troubleman |  | 6.23 | Completed | No
WO-26-002088 | 4.8 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-03-01 | 2026-03-01 | 2026-03-01 | Troubleman |  | 280.39 | Completed | No
WO-26-002089 | 3 | Bayou | BY-S30-01 | Trouble - no power | P2 same day | 2026-03-01 | 2026-03-01 | 2026-03-01 | Troubleman |  | 190.14 | Completed | No
WO-26-002090 | 5.5 | Bayou | BY-S23-01 | Trouble - no power | P1 emergency | 2026-03-01 | 2026-03-01 | 2026-03-01 | Internal line |  | 324.94 | Completed | No
WO-26-002091 | 1.7 | Bayou | BY-S16-06 | Trouble - partial or voltage | P2 same day | 2026-03-01 | 2026-03-01 | 2026-03-01 | Internal line |  | 3.1 | Completed | No
WO-26-002092 | 21.5 | Crossroads | CR-S03-03 | Pole replacement | P2 same day | 2026-03-01 | 2026-03-01 | 2026-03-01 | Internal line |  | 3109.54 | Completed | No
WO-26-002093 | 13 | Crossroads | CR-S07-03 | Transformer replacement | P1 emergency | 2026-03-01 | 2026-03-01 | 2026-03-01 | Internal line |  | 11615.75 | Completed | No
WO-26-002094 | 5.1 | Crossroads | CR-S24-03 | Trouble - no power | P2 same day | 2026-03-01 | 2026-03-01 | 2026-03-01 | Troubleman |  | 81.71 | Completed | No
WO-26-002095 | 5.5 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-03-01 | 2026-03-01 | 2026-03-01 | Troubleman |  | 104.2 | Completed | No
WO-26-002096 | 10.5 | Bayou | BY-S19-03 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-07 | 2026-03-07 | Contract line | CT-04 | 1919.8 | Completed | No
WO-26-002097 | 5 | Bayou | BY-S09-03 | Corrective maintenance | P2 same day | 2026-03-02 | 2026-03-02 | 2026-03-02 | Underground crew |  | 1216.23 | Completed | No
WO-26-002098 | 6.6 | Bayou | BY-S07-02 | Corrective maintenance | P2 same day | 2026-03-02 | 2026-03-03 | 2026-03-03 | Underground crew |  | 1371.41 | Completed | No
WO-26-002099 | 10.2 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-07 | 2026-03-07 | Contract line | CT-04 | 1414.12 | Completed | No
WO-26-002100 | 1.2 | Bayou | BY-S25-02 | Meter exchange | P4 planned | 2026-03-02 | 2026-03-27 | 2026-03-27 | Meter technician |  | 85.6 | Completed | No
WO-26-002101 | 1.3 | Bayou | BY-S23-02 | Meter exchange | P4 planned | 2026-03-02 | 2026-04-04 | 2026-04-06 | Meter technician |  | 139.09 | Completed | No
WO-26-002102 | 1.4 | Bayou | BY-S06-01 | Meter exchange | P3 within 10 days | 2026-03-02 | 2026-03-07 | 2026-03-07 | Meter technician |  | 167.27 | Completed | No
WO-26-002103 | 23.2 | Bayou | BY-S09-02 | Pole replacement | P3 within 10 days | 2026-03-02 | 2026-03-12 | 2026-03-12 | Internal line |  | 2509.42 | Completed | No
WO-26-002104 | 2.9 | Bayou | BY-S17-01 | Preventive maintenance | P4 planned | 2026-03-02 | 2026-04-14 | 2026-04-16 | Contract line | CT-04 | 100.49 | Completed | No
WO-26-002105 | 1.7 | Bayou | BY-S25-04 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-08 | 2026-03-08 | Meter technician |  | 3.37 | Completed | No
WO-26-002106 | 2 | Bayou | BY-S10-04 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-09 | 2026-03-11 | Meter technician |  | 16.82 | Completed | No
WO-26-002107 | 1.1 | Bayou | BY-S18-04 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-08 | 2026-03-09 | Meter technician |  | 33.85 | Completed | No
WO-26-002108 | 1.2 | Bayou | BY-S17-01 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-10 | 2026-03-11 | Meter technician |  | 24.4 | Completed | No
WO-26-002109 | 8.3 | Bayou | BY-S12-01 | Transformer replacement | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Internal line |  | 8439.61 | Completed | No
WO-26-002110 | 13.3 | Bayou | BY-S11-01 | Transformer replacement | P2 same day | 2026-03-02 | 2026-03-03 | 2026-03-03 | Internal line |  | 6073.24 | Completed | No
WO-26-002111 | 6.7 | Bayou | BY-S18-04 | Transformer replacement | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Contract line | CT-03 | 12210.72 | Completed | No
WO-26-002112 | 5.9 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Internal line |  | 339.82 | Completed | No
WO-26-002113 | 3.8 | Bayou | BY-S21-04 | Trouble - no power | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Troubleman |  | 339.74 | Completed | No
WO-26-002114 | 3.8 | Bayou | BY-S27-01 | Trouble - no power | P2 same day | 2026-03-02 | 2026-03-02 | 2026-03-02 | Troubleman |  | 296.53 | Completed | No
WO-26-002115 | 4.6 | Bayou | BY-S13-02 | Trouble - no power | P2 same day | 2026-03-02 | 2026-03-03 | 2026-03-03 | Troubleman |  | 163.65 | Completed | No
WO-26-002116 | 4.6 | Bayou | BY-S29-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-02 | 2026-03-04 | 2026-03-12 | Troubleman |  | 148.25 | Completed | No
WO-26-002117 | 3.7 | Bayou | BY-S16-06 | Trouble - partial or voltage | P2 same day | 2026-03-02 | 2026-03-03 | 2026-03-03 | Troubleman |  | 149.69 | Completed | No
WO-26-002118 | 3.8 | Bayou | BY-S15-02 | Trouble - partial or voltage | P2 same day | 2026-03-02 | 2026-03-03 | 2026-03-03 | Troubleman |  | 214.53 | Completed | No
WO-26-002119 | 2.9 | Bayou | BY-S27-04 | Trouble - partial or voltage | P3 within 10 days | 2026-03-02 | 2026-03-10 | 2026-03-10 | Troubleman |  | 98.88 | Completed | No
WO-26-002120 | 2.5 | Bayou | BY-S26-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-02 | 2026-03-09 | 2026-03-09 | Internal line |  | 127.91 | Completed | No
WO-26-002121 | 3.7 | Crossroads | CR-S30-07 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-04 | 2026-03-06 | Contract line | CT-02 | 1053.12 | Completed | No
WO-26-002122 | 9.3 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-03-02 | 2026-03-02 | 2026-03-02 | Contract line | CT-01 | 2006.01 | Completed | No
WO-26-002123 | 7.2 | Crossroads | CR-S12-01 | Corrective maintenance | P2 same day | 2026-03-02 | 2026-03-02 | 2026-03-02 | Internal line |  | 2031.02 | Completed | No
WO-26-002124 | 10.9 | Crossroads | CR-S03-01 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-06 | 2026-03-08 | Underground crew |  | 986.83 | Completed | No
WO-26-002125 | 7.1 | Crossroads | CR-S16-05 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-12 | 2026-03-12 | Internal line |  | 1583.99 | Completed | No
WO-26-002126 | 9.7 | Crossroads | CR-S07-01 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-03 | 2026-03-05 | Underground crew |  | 2119.88 | Completed | No
WO-26-002127 | 4.6 | Crossroads | CR-S09-01 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-12 | 2026-03-13 | Contract line | CT-02 | 1665.38 | Completed | No
WO-26-002128 | 9.5 | Crossroads | CR-S15-01 | Corrective maintenance | P3 within 10 days | 2026-03-02 | 2026-03-10 | 2026-03-11 | Contract line | CT-01 | 1204.06 | Completed | No
WO-26-002129 | 1.1 | Crossroads | CR-S24-01 | Meter exchange | P4 planned | 2026-03-02 | 2026-03-29 | 2026-03-30 | Meter technician |  | 160.82 | Completed | No
WO-26-002130 | 1.2 | Crossroads | CR-S19-04 | Meter exchange | P3 within 10 days | 2026-03-02 | 2026-03-04 | 2026-03-04 | Meter technician |  | 107.69 | Completed | No
WO-26-002131 | 0.6 | Crossroads | CR-S05-05 | Meter exchange | P4 planned | 2026-03-02 | 2026-03-27 | 2026-04-04 | Meter technician |  | 161.62 | Completed | No
WO-26-002132 | 13.2 | Crossroads | CR-S32-01 | New service - small | P4 planned | 2026-03-02 | 2026-04-10 | 2026-04-10 | Contract line | CT-02 | 907.42 | Completed | No
WO-26-002133 | 14.9 | Crossroads | CR-S18-04 | New service - small | P4 planned | 2026-03-02 | 2026-04-22 | 2026-04-24 | Contract line | CT-01 | 2920.07 | Completed | No
WO-26-002134 | 10.5 | Crossroads | CR-S20-05 | Pole replacement | P4 planned | 2026-03-02 | 2026-03-29 | 2026-03-30 | Contract line | CT-02 | 1562.6 | Completed | No
WO-26-002135 | 21.4 | Crossroads | CR-S27-04 | Pole replacement | P4 planned | 2026-03-02 | 2026-04-20 | 2026-04-24 | Contract line | CT-02 | 2972.94 | Completed | No
WO-26-002136 | 5.1 | Crossroads | CR-S05-02 | Preventive maintenance | P4 planned | 2026-03-02 | 2026-03-28 | 2026-03-30 | Internal line |  | 225.12 | Completed | No
WO-26-002137 | 7.9 | Crossroads | CR-S13-02 | Preventive maintenance | P4 planned | 2026-03-02 | 2026-03-24 | 2026-03-24 | Underground crew |  | 116.24 | Completed | No
WO-26-002138 | 5 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-03-02 | 2026-04-20 | 2026-04-20 | Internal line |  | 287.04 | Completed | No
WO-26-002139 | 0.5 | Crossroads | CR-S13-03 | Service order - field | P2 same day | 2026-03-02 | 2026-03-03 | 2026-03-03 | Meter technician |  | 10.38 | Completed | No
WO-26-002140 | 1.1 | Crossroads | CR-S19-04 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-11 | 2026-03-11 | Meter technician |  | 5.05 | Completed | No
WO-26-002141 | 1.2 | Crossroads | CR-S29-03 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-09 | 2026-03-09 | Meter technician |  | 8.15 | Completed | No
WO-26-002142 | 1.5 | Crossroads | CR-S21-02 | Service order - field | P2 same day | 2026-03-02 | 2026-03-02 | 2026-03-02 | Meter technician |  | 38.29 | Completed | No
WO-26-002143 | 2 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-06 | 2026-03-07 | Meter technician |  | 26.11 | Completed | No
WO-26-002144 | 1 | Crossroads | CR-S14-02 | Service order - field | P3 within 10 days | 2026-03-02 | 2026-03-06 | 2026-03-07 | Meter technician |  | 1.53 | Completed | No
WO-26-002145 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-02 | 2026-03-11 | 2026-03-11 | Contract line | CT-01 | 139.76 | Completed | No
WO-26-002146 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-03-02 | 2026-04-05 | 2026-04-05 | Internal line |  | 213.43 | Completed | No
WO-26-002147 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-02 | 2026-03-10 | 2026-03-10 | Internal line |  | 130.91 | Completed | No
WO-26-002148 | 2.6 | Crossroads | CR-S14-03 | Trouble - no power | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Internal line |  | 90.99 | Completed | No
WO-26-002149 | 4.9 | Crossroads | CR-S05-01 | Trouble - no power | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Troubleman |  | 262.17 | Completed | No
WO-26-002150 | 2.3 | Crossroads | CR-S04-02 | Trouble - no power | P1 emergency | 2026-03-02 | 2026-03-02 | 2026-03-02 | Internal line |  | 94.74 | Completed | No
WO-26-002151 | 2.6 | Crossroads | CR-S25-03 | Trouble - no power | P2 same day | 2026-03-02 | 2026-03-02 | 2026-03-02 | Troubleman |  | 112.75 | Completed | No
WO-26-002152 | 3.2 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-03-03 | 2026-03-06 | 2026-03-07 | Contract line | CT-04 | 1494.53 | Completed | No
WO-26-002153 | 10.4 | Bayou | BY-S13-02 | Corrective maintenance | P3 within 10 days | 2026-03-03 | 2026-03-11 | 2026-03-11 | Contract line | CT-04 | 1976.28 | Completed | No
WO-26-002154 | 4.6 | Bayou | BY-S20-01 | Corrective maintenance | P3 within 10 days | 2026-03-03 | 2026-03-07 | 2026-03-09 | Contract line | CT-03 | 1765.63 | Completed | No
WO-26-002155 | 0.5 | Bayou | BY-S09-02 | Meter exchange | P3 within 10 days | 2026-03-03 | 2026-03-06 | 2026-03-06 | Meter technician |  | 120.49 | Completed | No
WO-26-002156 | 1.4 | Bayou | BY-S17-03 | Meter exchange | P4 planned | 2026-03-03 | 2026-04-28 | 2026-04-28 | Meter technician |  | 141.85 | Completed | No
WO-26-002157 | 1.1 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-03-03 | 2026-03-06 | 2026-03-06 | Meter technician |  | 92.58 | Completed | No
WO-26-002158 | 1.2 | Bayou | BY-S26-02 | Meter exchange | P4 planned | 2026-03-03 | 2026-03-18 | 2026-03-18 | Meter technician |  | 139.76 | Completed | No
WO-26-002159 | 3.2 | Bayou | BY-S13-05 | Preventive maintenance | P4 planned | 2026-03-03 | 2026-03-26 | 2026-03-26 | Underground crew |  | 280.68 | Completed | No
WO-26-002160 | 1.5 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-03-03 | 2026-03-04 | 2026-03-04 | Meter technician |  | 39.16 | Completed | No
WO-26-002161 | 0.8 | Bayou | BY-S26-03 | Service order - field | P3 within 10 days | 2026-03-03 | 2026-03-06 | 2026-03-06 | Meter technician |  | 8.95 | Completed | No
WO-26-002162 | 1.8 | Bayou | BY-S10-02 | Service order - field | P2 same day | 2026-03-03 | 2026-03-03 | 2026-03-03 | Meter technician |  | 2.95 | Completed | No
WO-26-002163 | 1.8 | Bayou |  | Streetlight | P4 planned | 2026-03-03 | 2026-03-25 | 2026-03-27 | Contract line | CT-04 | 437.97 | Completed | No
WO-26-002164 | 4 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 79.24 | Completed | No
WO-26-002165 | 3.8 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 167.6 | Completed | No
WO-26-002166 | 2.5 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 16.18 | Completed | No
WO-26-002167 | 3 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 323.94 | Completed | No
WO-26-002168 | 3.9 | Bayou | BY-S12-01 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 286.62 | Completed | No
WO-26-002169 | 4.3 | Crossroads | CR-S27-04 | Corrective maintenance | P2 same day | 2026-03-03 | 2026-03-03 | 2026-03-03 | Internal line |  | 1373.03 | Completed | No
WO-26-002170 | 8.6 | Crossroads | CR-S20-01 | Corrective maintenance | P4 planned | 2026-03-03 | 2026-04-10 | 2026-04-10 | Internal line |  | 2379.77 | Completed | No
WO-26-002171 | 3.9 | Crossroads | CR-S27-04 | Corrective maintenance | P4 planned | 2026-03-03 | 2026-03-26 | 2026-03-28 | Underground crew |  | 1667.54 | Completed | No
WO-26-002172 | 1.4 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-03-03 | 2026-03-06 | 2026-03-07 | Meter technician |  | 153.84 | Completed | No
WO-26-002173 | 1.4 | Crossroads | CR-S15-01 | Meter exchange | P3 within 10 days | 2026-03-03 | 2026-03-06 | 2026-03-07 | Meter technician |  | 131.42 | Completed | No
WO-26-002174 | 1.1 | Crossroads | CR-S24-04 | Meter exchange | P3 within 10 days | 2026-03-03 | 2026-03-05 | 2026-03-07 | Meter technician |  | 153.24 | Completed | No
WO-26-002175 | 13.2 | Crossroads | CR-S02-04 | Pole replacement | P4 planned | 2026-03-03 | 2026-04-20 | 2026-04-20 | Contract line | CT-02 | 1869.16 | Completed | No
WO-26-002176 | 20.1 | Crossroads | CR-S31-03 | Pole replacement | P4 planned | 2026-03-03 | 2026-03-20 | 2026-03-24 | Internal line |  | 2547.04 | Completed | No
WO-26-002177 | 7.7 | Crossroads | CR-S20-02 | Preventive maintenance | P4 planned | 2026-03-03 | 2026-03-20 | 2026-03-24 | Internal line |  | 511.37 | Completed | No
WO-26-002178 | 0.9 | Crossroads | CR-S01-02 | Service order - field | P3 within 10 days | 2026-03-03 | 2026-03-12 | 2026-03-20 | Meter technician |  | 9.16 | Completed | No
WO-26-002179 | 1.7 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-03-03 | 2026-03-04 | 2026-03-04 | Meter technician |  | 16.8 | Completed | No
WO-26-002180 | 8.8 | Crossroads | CR-S25-01 | Transformer replacement | P2 same day | 2026-03-03 | 2026-03-04 | 2026-03-04 | Internal line |  | 4658.86 | Completed | No
WO-26-002181 | 6.8 | Crossroads | CR-S30-01 | Transformer replacement | P2 same day | 2026-03-03 | 2026-03-03 | 2026-03-03 | Contract line | CT-01 | 10311.89 | Completed | No
WO-26-002182 | 2.6 | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Internal line |  | 226.75 | Completed | No
WO-26-002183 | 5.8 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 43.74 | Completed | No
WO-26-002184 | 2.3 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 139 | Completed | No
WO-26-002185 | 5.5 | Crossroads | CR-S02-03 | Trouble - no power | P1 emergency | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 151.14 | Completed | No
WO-26-002186 | 2.6 | Crossroads | CR-S03-03 | Trouble - partial or voltage | P2 same day | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 248.4 | Completed | No
WO-26-002187 | 3.5 | Crossroads | CR-S32-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-03 | 2026-03-11 | 2026-03-12 | Troubleman |  | 78.65 | Completed | No
WO-26-002188 | 2.5 | Crossroads | CR-S20-03 | Trouble - partial or voltage | P2 same day | 2026-03-03 | 2026-03-03 | 2026-03-03 | Troubleman |  | 194.74 | Completed | No
WO-26-002189 | 3.3 | Bayou | BY-S16-04 | Corrective maintenance | P3 within 10 days | 2026-03-04 | 2026-03-11 | 2026-03-11 | Internal line |  | 2140.07 | Completed | No
WO-26-002190 | 5.1 | Bayou | BY-S23-04 | Corrective maintenance | P3 within 10 days | 2026-03-04 | 2026-03-12 | 2026-03-12 | Contract line | CT-04 | 191.02 | Completed | No
WO-26-002191 | 3.9 | Bayou | BY-S01-01 | Corrective maintenance | P4 planned | 2026-03-04 | 2026-04-25 | 2026-04-26 | Internal line |  | 860.47 | Completed | No
WO-26-002192 | 0.5 | Bayou | BY-S27-02 | Meter exchange | P3 within 10 days | 2026-03-04 | 2026-03-13 | 2026-03-13 | Meter technician |  | 79.66 | Completed | No
WO-26-002193 | 0.6 | Bayou | BY-S07-05 | Meter exchange | P3 within 10 days | 2026-03-04 | 2026-03-06 | 2026-03-06 | Meter technician |  | 140.64 | Completed | No
WO-26-002194 | 0.7 | Bayou | BY-S18-07 | Meter exchange | P4 planned | 2026-03-04 | 2026-04-21 | 2026-04-25 | Meter technician |  | 77.43 | Completed | No
WO-26-002195 | 1.2 | Bayou | BY-S18-03 | Meter exchange | P3 within 10 days | 2026-03-04 | 2026-03-13 | 2026-03-13 | Meter technician |  | 104 | Completed | No
WO-26-002196 | 6 | Bayou | BY-S16-02 | New service - small | P3 within 10 days | 2026-03-04 | 2026-03-11 | 2026-03-12 | Internal line |  | 1273.23 | Completed | No
WO-26-002197 | 3.7 | Bayou | BY-S02-01 | Preventive maintenance | P4 planned | 2026-03-04 | 2026-03-11 | 2026-03-15 | Internal line |  | 56.53 | Completed | No
WO-26-002198 | 1.9 | Bayou | BY-S19-03 | Service order - field | P3 within 10 days | 2026-03-04 | 2026-03-07 | 2026-03-07 | Meter technician |  | 10.55 | Completed | No
WO-26-002199 | 1.7 | Bayou | BY-S10-03 | Service order - field | P3 within 10 days | 2026-03-04 | 2026-03-14 | 2026-03-18 | Meter technician |  | 26.47 | Completed | No
WO-26-002200 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-04 | 2026-03-10 | 2026-03-11 | Contract line | CT-03 | 82.52 | Completed | No
WO-26-002201 | 8 | Bayou | BY-S17-02 | Transformer replacement | P1 emergency | 2026-03-04 | 2026-03-04 | 2026-03-04 | Contract line | CT-04 | 3826.71 | Completed | No
WO-26-002202 | 12.1 | Bayou | BY-S20-01 | Transformer replacement | P3 within 10 days | 2026-03-04 | 2026-03-08 | 2026-03-09 | Contract line | CT-04 | 7032.29 | Completed | No
WO-26-002203 | 10.1 | Bayou | BY-S30-02 | Transformer replacement | P2 same day | 2026-03-04 | 2026-03-04 | 2026-03-04 | Contract line | CT-03 | 4229.95 | Completed | No
WO-26-002204 | 10.8 | Bayou | BY-S10-04 | Transformer replacement | P2 same day | 2026-03-04 | 2026-03-05 | 2026-03-05 | Internal line |  | 9295.57 | Completed | No
WO-26-002205 | 2.4 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-03-04 | 2026-03-04 | 2026-03-04 | Troubleman |  | 32.83 | Completed | No
WO-26-002206 | 2.5 | Bayou | BY-S11-01 | Trouble - no power | P2 same day | 2026-03-04 | 2026-03-04 | 2026-03-04 | Troubleman |  | 274.37 | Completed | No
WO-26-002207 | 1.6 | Bayou | BY-S19-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-04 | 2026-03-10 | 2026-03-10 | Internal line |  | 193 | Completed | No
WO-26-002208 | 2.3 | Bayou | BY-S27-01 | Trouble - partial or voltage | P2 same day | 2026-03-04 | 2026-03-05 | 2026-03-05 | Troubleman |  | 126.9 | Completed | No
WO-26-002209 | 2.2 | Bayou | BY-S26-05 | Trouble - partial or voltage | P2 same day | 2026-03-04 | 2026-03-05 | 2026-03-05 | Internal line |  | 159.04 | Completed | No
WO-26-002210 | 10.9 | Crossroads | CR-S23-02 | Corrective maintenance | P2 same day | 2026-03-04 | 2026-03-05 | 2026-03-05 | Internal line |  | 2206.3 | Completed | No
WO-26-002211 | 8.3 | Crossroads | CR-S30-01 | Corrective maintenance | P3 within 10 days | 2026-03-04 | 2026-03-11 | 2026-03-11 | Contract line | CT-01 | 230.36 | Completed | No
WO-26-002212 | 4.7 | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-03-04 | 2026-03-14 | 2026-03-15 | Underground crew |  | 2321.8 | Completed | No
WO-26-002213 | 0.9 | Crossroads | CR-S30-02 | Meter exchange | P4 planned | 2026-03-04 | 2026-03-17 | 2026-03-17 | Meter technician |  | 68.24 | Completed | No
WO-26-002214 | 1.1 | Crossroads | CR-S07-01 | Meter exchange | P3 within 10 days | 2026-03-04 | 2026-03-10 | 2026-03-10 | Meter technician |  | 140 | Completed | No
WO-26-002215 | 1.3 | Crossroads | CR-S30-07 | Meter exchange | P4 planned | 2026-03-04 | 2026-04-17 | 2026-04-19 | Meter technician |  | 173.5 | Completed | No
WO-26-002216 | 1.4 | Crossroads | CR-S13-02 | Meter exchange | P4 planned | 2026-03-04 | 2026-03-22 | 2026-03-24 | Meter technician |  | 116.88 | Completed | No
WO-26-002217 | 2.8 | Crossroads | CR-S15-02 | Preventive maintenance | P4 planned | 2026-03-04 | 2026-04-12 | 2026-04-12 | Underground crew |  | 348.72 | Completed | No
WO-26-002218 | 4.1 | Crossroads | CR-S10-02 | Preventive maintenance | P4 planned | 2026-03-04 | 2026-04-07 | 2026-04-07 | Contract line | CT-01 | 437.03 | Completed | No
WO-26-002219 | 7.1 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-03-04 | 2026-04-06 | 2026-04-08 | Internal line |  | 172.78 | Completed | No
WO-26-002220 | 5 | Crossroads | CR-S14-03 | Preventive maintenance | P4 planned | 2026-03-04 | 2026-04-08 | 2026-04-08 | Internal line |  | 473.88 | Completed | No
WO-26-002221 | 6.1 | Crossroads | CR-S14-04 | Preventive maintenance | P4 planned | 2026-03-04 | 2026-04-12 | 2026-04-12 | Underground crew |  | 189.17 | Completed | No
WO-26-002222 |  | Crossroads | CR-S30-06 | Service order - field | P3 within 10 days | 2026-03-04 | 2026-03-11 |  | Meter technician |  |  | Cancelled | No
WO-26-002223 | 1.1 | Crossroads | CR-S19-04 | Service order - field | P2 same day | 2026-03-04 | 2026-03-04 | 2026-03-04 | Meter technician |  | 35.42 | Completed | No
WO-26-002224 | 8.1 | Crossroads | CR-S12-02 | Transformer replacement | P3 within 10 days | 2026-03-04 | 2026-03-11 | 2026-03-11 | Internal line |  | 11187.92 | Completed | No
WO-26-002225 | 13.1 | Crossroads | CR-S22-01 | Transformer replacement | P1 emergency | 2026-03-04 | 2026-03-04 | 2026-03-04 | Contract line | CT-02 | 11463.56 | Completed | No
WO-26-002226 | 2.1 | Crossroads | CR-S09-01 | Trouble - no power | P2 same day | 2026-03-04 | 2026-03-04 | 2026-03-04 | Troubleman |  | 47.73 | Completed | No
WO-26-002227 | 2.6 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-03-04 | 2026-03-04 | 2026-03-04 | Troubleman |  | 325.9 | Completed | No
WO-26-002228 | 4.9 | Crossroads | CR-S13-04 | Trouble - no power | P1 emergency | 2026-03-04 | 2026-03-04 | 2026-03-04 | Internal line |  | 309.18 | Completed | No
WO-26-002229 | 5.9 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-03-04 | 2026-03-04 | 2026-03-04 | Troubleman |  | 42.96 | Completed | No
WO-26-002230 | 3.9 | Crossroads | CR-S19-03 | Trouble - partial or voltage | P2 same day | 2026-03-04 | 2026-03-05 | 2026-03-05 | Troubleman |  | 139.29 | Completed | No
WO-26-002231 | 6.4 | Bayou | BY-S03-01 | Corrective maintenance | P3 within 10 days | 2026-03-05 | 2026-03-11 | 2026-03-11 | Internal line |  | 90.85 | Completed | No
WO-26-002232 | 6.6 | Bayou | BY-S19-04 | Corrective maintenance | P3 within 10 days | 2026-03-05 | 2026-03-13 | 2026-03-15 | Underground crew |  | 1392.54 | Completed | No
WO-26-002233 | 9.2 | Bayou | BY-S08-01 | Corrective maintenance | P3 within 10 days | 2026-03-05 | 2026-03-15 | 2026-03-17 | Contract line | CT-04 | 503.94 | Completed | No
WO-26-002234 | 5.4 | Bayou | BY-S30-03 | Corrective maintenance | P4 planned | 2026-03-05 | 2026-03-14 | 2026-03-15 | Contract line | CT-03 | 397.55 | Completed | No
WO-26-002235 | 0.6 | Bayou | BY-S07-02 | Meter exchange | P4 planned | 2026-03-05 | 2026-03-13 | 2026-03-21 | Meter technician |  | 126.63 | Completed | No
WO-26-002236 | 1.4 | Bayou | BY-S14-01 | Meter exchange | P4 planned | 2026-03-05 | 2026-03-22 | 2026-03-22 | Meter technician |  | 84.72 | Completed | No
WO-26-002237 | 10.2 | Bayou | BY-S25-04 | New service - small | P4 planned | 2026-03-05 | 2026-04-04 | 2026-04-06 | Contract line | CT-04 | 3726.79 | Completed | No
WO-26-002238 | 11.7 | Bayou | BY-S13-01 | New service - small | P4 planned | 2026-03-05 | 2026-04-06 | 2026-04-07 | Underground crew |  | 2789.26 | Completed | No
WO-26-002239 | 7 | Bayou | BY-S01-02 | Preventive maintenance | P4 planned | 2026-03-05 | 2026-03-14 | 2026-03-14 | Underground crew |  | 538.44 | Completed | No
WO-26-002240 | 2 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-03-05 | 2026-04-30 | 2026-04-30 | Underground crew |  | 559.43 | Completed | No
WO-26-002241 | 0.7 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-03-05 | 2026-03-05 | 2026-03-05 | Meter technician |  | 13.09 | Completed | No
WO-26-002242 | 0.6 | Bayou | BY-S13-05 | Service order - field | P3 within 10 days | 2026-03-05 | 2026-03-14 | 2026-03-15 | Meter technician |  | 5.81 | Completed | No
WO-26-002243 | 0.5 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-03-05 | 2026-03-08 | 2026-03-08 | Meter technician |  | 24.07 | Completed | No
WO-26-002244 | 0.8 | Bayou | BY-S12-03 | Service order - field | P3 within 10 days | 2026-03-05 | 2026-03-12 | 2026-03-13 | Meter technician |  | 5.01 | Completed | No
WO-26-002245 | 9.3 | Bayou | BY-S16-02 | Transformer replacement | P3 within 10 days | 2026-03-05 | 2026-03-07 | 2026-03-07 | Internal line |  | 5571.86 | Completed | No
WO-26-002246 | 5.4 | Bayou | BY-S18-01 | Trouble - no power | P2 same day | 2026-03-05 | 2026-03-06 | 2026-03-06 | Internal line |  | 87.71 | Completed | No
WO-26-002247 | 2 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Troubleman |  | 260.83 | Completed | No
WO-26-002248 | 2.5 | Bayou | BY-S18-01 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Troubleman |  | 160.7 | Completed | No
WO-26-002249 | 2.3 | Bayou | BY-S05-02 | Trouble - no power | P2 same day | 2026-03-05 | 2026-03-05 | 2026-03-05 | Internal line |  | 34.9 | Completed | No
WO-26-002250 | 5.7 | Bayou | BY-S27-05 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Troubleman |  | 116.44 | Completed | No
WO-26-002251 | 4.1 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Troubleman |  | 221.47 | Completed | No
WO-26-002252 | 4.4 | Bayou | BY-S27-06 | Trouble - partial or voltage | P3 within 10 days | 2026-03-05 | 2026-03-08 | 2026-03-12 | Troubleman |  | 187.79 | Completed | No
WO-26-002253 | 10.9 | Crossroads | CR-S26-02 | Corrective maintenance | P3 within 10 days | 2026-03-05 | 2026-03-12 | 2026-03-20 | Internal line |  | 612.74 | Completed | No
WO-26-002254 | 6.7 | Crossroads | CR-S18-04 | Corrective maintenance | P4 planned | 2026-03-05 | 2026-04-02 | 2026-04-02 | Contract line | CT-02 | 1942.99 | Completed | No
WO-26-002255 | 6.2 | Crossroads | CR-S14-05 | Corrective maintenance | P3 within 10 days | 2026-03-05 | 2026-03-10 | 2026-03-11 | Internal line |  | 155.6 | Completed | No
WO-26-002256 | 5.5 | Crossroads | CR-S08-02 | Corrective maintenance | P2 same day | 2026-03-05 | 2026-03-06 | 2026-03-06 | Contract line | CT-01 | 451.36 | Completed | No
WO-26-002257 | 3.1 | Crossroads | CR-S03-01 | Corrective maintenance | P3 within 10 days | 2026-03-05 | 2026-03-13 | 2026-03-13 | Internal line |  | 1192.51 | Completed | No
WO-26-002258 | 1.4 | Crossroads | CR-S07-05 | Meter exchange | P3 within 10 days | 2026-03-05 | 2026-03-06 | 2026-03-10 | Meter technician |  | 95.24 | Completed | No
WO-26-002259 | 0.6 | Crossroads | CR-S22-01 | Meter exchange | P3 within 10 days | 2026-03-05 | 2026-03-12 | 2026-03-14 | Meter technician |  | 83.2 | Completed | No
WO-26-002260 | 1.4 | Crossroads | CR-S13-06 | Meter exchange | P4 planned | 2026-03-05 | 2026-04-15 | 2026-04-16 | Meter technician |  | 62.85 | Completed | No
WO-26-002261 | 0.5 | Crossroads | CR-S11-01 | Meter exchange | P3 within 10 days | 2026-03-05 | 2026-03-06 | 2026-03-07 | Meter technician |  | 115.4 | Completed | No
WO-26-002262 | 17.9 | Crossroads | CR-S08-05 | Pole replacement | P3 within 10 days | 2026-03-05 | 2026-03-09 | 2026-03-09 | Internal line |  | 3203.67 | Completed | No
WO-26-002263 | 14.7 | Crossroads | CR-S29-03 | Pole replacement | P4 planned | 2026-03-05 | 2026-05-02 | 2026-05-02 | Contract line | CT-02 | 2104.66 | Completed | No
WO-26-002264 | 11.2 | Crossroads | CR-S11-01 | Pole replacement | P3 within 10 days | 2026-03-05 | 2026-03-10 | 2026-03-14 | Contract line | CT-01 | 2720.45 | Completed | No
WO-26-002265 |  | Crossroads | CR-S27-04 | Pole replacement | P2 same day | 2026-03-05 | 2026-03-06 |  | Internal line |  |  | Cancelled | No
WO-26-002266 | 3.3 | Crossroads | CR-S25-01 | Preventive maintenance | P4 planned | 2026-03-05 | 2026-05-04 | 2026-05-12 | Internal line |  | 562.52 | Completed | No
WO-26-002267 | 7.7 | Crossroads | CR-S26-02 | Preventive maintenance | P4 planned | 2026-03-05 | 2026-04-17 | 2026-04-17 | Internal line |  | 245.74 | Completed | No
WO-26-002268 | 5.1 | Crossroads | CR-S18-06 | Preventive maintenance | P4 planned | 2026-03-05 | 2026-04-18 | 2026-04-19 | Internal line |  | 344.65 | Completed | No
WO-26-002269 | 0.9 | Crossroads | CR-S27-02 | Service order - field | P2 same day | 2026-03-05 | 2026-03-06 | 2026-03-06 | Meter technician |  | 27.34 | Completed | No
WO-26-002270 | 1.1 | Crossroads | CR-S05-03 | Service order - field | P2 same day | 2026-03-05 | 2026-03-06 | 2026-03-06 | Meter technician |  | 5.97 | Completed | No
WO-26-002271 | 1.1 | Crossroads | CR-S26-03 | Service order - field | P2 same day | 2026-03-05 | 2026-03-06 | 2026-03-06 | Meter technician |  | 4.61 | Completed | No
WO-26-002272 | 0.7 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-03-05 | 2026-03-06 | 2026-03-07 | Meter technician |  | 32.56 | Completed | No
WO-26-002273 | 1.8 | Crossroads |  | Streetlight | P4 planned | 2026-03-05 | 2026-04-10 | 2026-04-10 | Contract line | CT-01 | 192.31 | Completed | No
WO-26-002274 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-05 | 2026-03-15 | 2026-03-15 | Contract line | CT-01 | 151.97 | Completed | No
WO-26-002275 | 6.2 | Crossroads | CR-S27-04 | Transformer replacement | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Contract line | CT-02 | 6831.12 | Completed | No
WO-26-002276 | 11.7 | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Internal line |  | 6092.24 | Completed | No
WO-26-002277 | 3.7 | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Troubleman |  | 248.4 | Completed | No
WO-26-002278 | 3.3 | Crossroads | CR-S25-02 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Internal line |  | 93.68 | Completed | No
WO-26-002279 | 2.4 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-03-05 | 2026-03-05 | 2026-03-05 | Troubleman |  | 189.65 | Completed | No
WO-26-002280 | 3.7 | Crossroads | CR-S07-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-05 | 2026-03-14 | 2026-03-15 | Troubleman |  | 34.29 | Completed | No
WO-26-002281 | 3.2 | Crossroads | CR-S27-02 | Trouble - partial or voltage | P2 same day | 2026-03-05 | 2026-03-06 | 2026-03-06 | Troubleman |  | 116.96 | Completed | No
WO-26-002282 | 9 | Bayou | BY-S19-03 | Corrective maintenance | P4 planned | 2026-03-06 | 2026-04-14 | 2026-04-16 | Internal line |  | 729.55 | Completed | No
WO-26-002283 | 1.1 | Bayou | BY-S18-06 | Meter exchange | P3 within 10 days | 2026-03-06 | 2026-03-15 | 2026-03-23 | Meter technician |  | 168.09 | Completed | No
WO-26-002284 | 0.9 | Bayou | BY-S07-03 | Meter exchange | P4 planned | 2026-03-06 | 2026-03-31 | 2026-04-04 | Meter technician |  | 118.98 | Completed | No
WO-26-002285 | 1.1 | Bayou | BY-S07-01 | Meter exchange | P3 within 10 days | 2026-03-06 | 2026-03-12 | 2026-03-13 | Meter technician |  | 168.86 | Completed | No
WO-26-002286 | 5.6 | Bayou | BY-S26-02 | New service - small | P4 planned | 2026-03-06 | 2026-04-27 | 2026-04-27 | Underground crew |  | 3382.71 | Completed | No
WO-26-002287 | 5.6 | Bayou | BY-S19-02 | New service - small | P3 within 10 days | 2026-03-06 | 2026-03-08 | 2026-03-16 | Internal line |  | 3996.55 | Completed | No
WO-26-002288 | 12.8 | Bayou | BY-S05-02 | New service - small | P4 planned | 2026-03-06 | 2026-03-28 | 2026-03-28 | Underground crew |  | 3847.67 | Completed | No
WO-26-002289 | 12.3 | Bayou | BY-S23-04 | Pole replacement | P4 planned | 2026-03-06 | 2026-04-17 | 2026-04-18 | Contract line | CT-03 | 2953.65 | Completed | No
WO-26-002290 | 3.7 | Bayou | BY-S07-03 | Preventive maintenance | P4 planned | 2026-03-06 | 2026-03-29 | 2026-03-30 | Underground crew |  | 213.17 | Completed | No
WO-26-002291 | 1 | Bayou | BY-S07-03 | Service order - field | P3 within 10 days | 2026-03-06 | 2026-03-09 | 2026-03-09 | Meter technician |  | 5.68 | Completed | No
WO-26-002292 | 0.7 | Bayou | BY-S16-03 | Service order - field | P2 same day | 2026-03-06 | 2026-03-07 | 2026-03-07 | Meter technician |  | 29.75 | Completed | No
WO-26-002293 | 0.6 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-03-06 | 2026-03-11 | 2026-03-11 | Meter technician |  | 9.15 | Completed | No
WO-26-002294 | 1 | Bayou |  | Streetlight | P4 planned | 2026-03-06 | 2026-03-23 | 2026-03-23 | Contract line | CT-03 | 395.31 | Completed | No
WO-26-002295 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-06 | 2026-03-11 | 2026-03-12 | Contract line | CT-04 | 317.51 | Completed | No
WO-26-002296 | 13.8 | Bayou | BY-S09-02 | Transformer replacement | P3 within 10 days | 2026-03-06 | 2026-03-07 | 2026-03-11 | Internal line |  | 5987.55 | Completed | No
WO-26-002297 | 10 | Bayou | BY-S16-06 | Transformer replacement | P2 same day | 2026-03-06 | 2026-03-06 | 2026-03-06 | Contract line | CT-04 | 9687.81 | Completed | No
WO-26-002298 | 4.9 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Internal line |  | 234.3 | Completed | No
WO-26-002299 | 3.8 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Troubleman |  | 169.5 | Completed | No
WO-26-002300 | 5.5 | Bayou | BY-S18-02 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Internal line |  | 139.66 | Completed | No
WO-26-002301 | 5.2 | Bayou | BY-S06-01 | Trouble - no power | P2 same day | 2026-03-06 | 2026-03-06 | 2026-03-06 | Troubleman |  | 89.07 | Completed | No
WO-26-002302 | 4.8 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Troubleman |  | 139.5 | Completed | No
WO-26-002303 | 4.6 | Bayou | BY-S09-01 | Trouble - partial or voltage | P2 same day | 2026-03-06 | 2026-03-07 | 2026-03-07 | Troubleman |  | 11.91 | Completed | No
WO-26-002304 | 3.2 | Bayou | BY-S16-06 | Trouble - partial or voltage | P3 within 10 days | 2026-03-06 | 2026-03-11 | 2026-03-11 | Troubleman |  | 27.21 | Completed | No
WO-26-002305 | 3.3 | Bayou | BY-S26-02 | Trouble - partial or voltage | P2 same day | 2026-03-06 | 2026-03-06 | 2026-03-06 | Troubleman |  | 50.28 | Completed | No
WO-26-002306 | 1.7 | Bayou | BY-S17-04 | Trouble - partial or voltage | P2 same day | 2026-03-06 | 2026-03-07 | 2026-03-07 | Internal line |  | 91.75 | Completed | No
WO-26-002307 | 5.8 | Crossroads | CR-S32-04 | Corrective maintenance | P3 within 10 days | 2026-03-06 | 2026-03-08 | 2026-03-08 | Internal line |  | 2296.19 | Completed | No
WO-26-002308 | 3.8 | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-03-06 | 2026-03-14 | 2026-03-16 | Underground crew |  | 291.42 | Completed | No
WO-26-002309 | 10.1 | Crossroads | CR-S32-02 | Corrective maintenance | P4 planned | 2026-03-06 | 2026-04-24 | 2026-04-25 | Internal line |  | 1953.55 | Completed | No
WO-26-002310 | 0.5 | Crossroads | CR-S27-02 | Meter exchange | P3 within 10 days | 2026-03-06 | 2026-03-10 | 2026-03-10 | Meter technician |  | 121.68 | Completed | No
WO-26-002311 | 1.1 | Crossroads | CR-S30-02 | Meter exchange | P3 within 10 days | 2026-03-06 | 2026-03-08 | 2026-03-09 | Meter technician |  | 79.32 | Completed | No
WO-26-002312 | 4.4 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-03-06 | 2026-04-06 | 2026-04-08 | Underground crew |  | 109.38 | Completed | No
WO-26-002313 | 6.5 | Crossroads | CR-S13-05 | Preventive maintenance | P4 planned | 2026-03-06 | 2026-04-24 | 2026-04-25 | Internal line |  | 223.5 | Completed | No
WO-26-002314 | 3 | Crossroads | CR-S07-01 | Preventive maintenance | P4 planned | 2026-03-06 | 2026-03-19 | 2026-03-19 | Internal line |  | 32.77 | Completed | No
WO-26-002315 | 0.7 | Crossroads | CR-S08-06 | Service order - field | P3 within 10 days | 2026-03-06 | 2026-03-10 | 2026-03-10 | Meter technician |  | 14.84 | Completed | No
WO-26-002316 | 1.1 | Crossroads | CR-S32-05 | Service order - field | P3 within 10 days | 2026-03-06 | 2026-03-09 | 2026-03-09 | Meter technician |  | 29.17 | Completed | No
WO-26-002317 | 1.5 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-03-06 | 2026-03-07 | 2026-03-07 | Meter technician |  | 27.11 | Completed | No
WO-26-002318 | 2.9 | Crossroads |  | Streetlight | P4 planned | 2026-03-06 | 2026-04-19 | 2026-04-19 | Contract line | CT-01 | 183.97 | Completed | No
WO-26-002319 | 2.9 | Crossroads |  | Streetlight | P4 planned | 2026-03-06 | 2026-03-30 | 2026-03-30 | Contract line | CT-02 | 321.37 | Completed | No
WO-26-002320 | 2.5 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Troubleman |  | 147.1 | Completed | No
WO-26-002321 | 2.7 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Internal line |  | 170.6 | Completed | No
WO-26-002322 | 4.9 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Troubleman |  | 192.12 | Completed | No
WO-26-002323 | 4.2 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Internal line |  | 241.07 | Completed | No
WO-26-002324 | 5.8 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-03-06 | 2026-03-06 | 2026-03-06 | Internal line |  | 324.31 | Completed | No
WO-26-002325 | 1.8 | Crossroads | CR-S13-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-06 | 2026-03-08 | 2026-03-12 | Troubleman |  | 196.09 | Completed | No
WO-26-002326 | 0.6 | Bayou | BY-S08-03 | Service order - field | P2 same day | 2026-03-07 | 2026-03-07 | 2026-03-07 | Meter technician |  | 11.9 | Completed | No
WO-26-002327 | 1.9 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-03-07 | 2026-03-07 | 2026-03-07 | Meter technician |  | 19.12 | Completed | No
WO-26-002328 | 9.5 | Bayou | BY-S03-02 | Transformer replacement | P2 same day | 2026-03-07 | 2026-03-07 | 2026-03-07 | Internal line |  | 5281.83 | Completed | No
WO-26-002329 | 4.4 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-03-07 | 2026-03-07 | 2026-03-07 | Troubleman |  | 63.26 | Completed | No
WO-26-002330 | 2.5 | Bayou | BY-S27-03 | Trouble - no power | P2 same day | 2026-03-07 | 2026-03-08 | 2026-03-08 | Internal line |  | 299.23 | Completed | No
WO-26-002331 | 5.2 | Bayou | BY-S11-01 | Trouble - no power | P1 emergency | 2026-03-07 | 2026-03-07 | 2026-03-07 | Troubleman |  | 77.84 | Completed | No
WO-26-002332 | 3.1 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-03-07 | 2026-03-07 | 2026-03-07 | Troubleman |  | 155.23 | Completed | No
WO-26-002333 | 3.4 | Bayou | BY-S27-05 | Trouble - partial or voltage | P2 same day | 2026-03-07 | 2026-03-08 | 2026-03-08 | Troubleman |  | 183.5 | Completed | No
WO-26-002334 | 1.3 | Crossroads | CR-S25-02 | Service order - field | P2 same day | 2026-03-07 | 2026-03-08 | 2026-03-08 | Meter technician |  | 21.14 | Completed | No
WO-26-002335 | 6.9 | Crossroads | CR-S26-06 | Transformer replacement | P1 emergency | 2026-03-07 | 2026-03-07 | 2026-03-07 | Internal line |  | 4527.48 | Completed | No
WO-26-002336 | 4.6 | Crossroads | CR-S22-01 | Trouble - no power | P1 emergency | 2026-03-07 | 2026-03-07 | 2026-03-07 | Troubleman |  | 100.25 | Completed | No
WO-26-002337 | 4.9 | Crossroads | CR-S14-02 | Trouble - no power | P2 same day | 2026-03-07 | 2026-03-07 | 2026-03-07 | Internal line |  | 184.73 | Completed | No
WO-26-002338 | 1.7 | Bayou | BY-S04-02 | Service order - field | P2 same day | 2026-03-08 | 2026-03-08 | 2026-03-08 | Meter technician |  | 6.11 | Completed | No
WO-26-002339 | 0.9 | Bayou | BY-S10-01 | Service order - field | P2 same day | 2026-03-08 | 2026-03-08 | 2026-03-08 | Meter technician |  | 33 | Completed | No
WO-26-002340 | 1.4 | Bayou | BY-S17-02 | Service order - field | P2 same day | 2026-03-08 | 2026-03-09 | 2026-03-09 | Meter technician |  | 35.45 | Completed | No
WO-26-002341 | 2.8 | Bayou | BY-S21-04 | Trouble - no power | P2 same day | 2026-03-08 | 2026-03-08 | 2026-03-08 | Internal line |  | 335.85 | Completed | No
WO-26-002342 | 2.6 | Bayou | BY-S30-02 | Trouble - partial or voltage | P2 same day | 2026-03-08 | 2026-03-08 | 2026-03-08 | Internal line |  | 42.73 | Completed | No
WO-26-002343 | 11.6 | Crossroads | CR-S19-04 | Pole replacement | P2 same day | 2026-03-08 | 2026-03-08 | 2026-03-08 | Contract line | CT-01 | 2371.02 | Completed | No
WO-26-002344 | 10 | Crossroads | CR-S22-03 | Transformer replacement | P2 same day | 2026-03-08 | 2026-03-08 | 2026-03-08 | Internal line |  | 10741.41 | Completed | No
WO-26-002345 | 5.5 | Crossroads | CR-S29-03 | Trouble - no power | P1 emergency | 2026-03-08 | 2026-03-08 | 2026-03-08 | Troubleman |  | 266.6 | Completed | No
WO-26-002346 | 2.4 | Crossroads | CR-S10-03 | Trouble - no power | P1 emergency | 2026-03-08 | 2026-03-08 | 2026-03-08 | Troubleman |  | 107.61 | Completed | No
WO-26-002347 | 3.2 | Crossroads | CR-S30-01 | Trouble - no power | P2 same day | 2026-03-08 | 2026-03-09 | 2026-03-09 | Troubleman |  | 297.84 | Completed | No
WO-26-002348 | 5.2 | Crossroads | CR-S19-02 | Trouble - no power | P1 emergency | 2026-03-08 | 2026-03-08 | 2026-03-08 | Troubleman |  | 31.29 | Completed | No
WO-26-002349 | 1.7 | Crossroads | CR-S17-03 | Trouble - partial or voltage | P2 same day | 2026-03-08 | 2026-03-09 | 2026-03-09 | Troubleman |  | 156.48 | Completed | No
WO-26-002350 | 5.8 | Bayou | BY-S22-04 | Corrective maintenance | P2 same day | 2026-03-09 | 2026-03-09 | 2026-03-09 | Internal line |  | 1839.22 | Completed | No
WO-26-002351 | 10.7 | Bayou | BY-S07-03 | Corrective maintenance | P4 planned | 2026-03-09 | 2026-04-19 | 2026-04-19 | Contract line | CT-04 | 1612.66 | Completed | No
WO-26-002352 | 5.1 | Bayou | BY-S29-03 | Corrective maintenance | P3 within 10 days | 2026-03-09 | 2026-03-18 | 2026-03-18 | Contract line | CT-04 | 208.27 | Completed | No
WO-26-002353 | 0.6 | Bayou | BY-S01-01 | Meter exchange | P4 planned | 2026-03-09 | 2026-04-08 | 2026-04-08 | Meter technician |  | 87.43 | Completed | No
WO-26-002354 | 1.4 | Bayou | BY-S26-03 | Meter exchange | P3 within 10 days | 2026-03-09 | 2026-03-13 | 2026-03-21 | Meter technician |  | 162.39 | Completed | No
WO-26-002355 | 0.8 | Bayou | BY-S07-03 | Meter exchange | P3 within 10 days | 2026-03-09 | 2026-03-15 | 2026-03-17 | Meter technician |  | 98.36 | Completed | No
WO-26-002356 |  | Bayou | BY-S14-01 | Pole replacement | P4 planned | 2026-03-09 | 2026-04-21 |  | Internal line |  |  | Cancelled | No
WO-26-002357 | 3.3 | Bayou | BY-S08-02 | Preventive maintenance | P4 planned | 2026-03-09 | 2026-04-09 | 2026-04-09 | Underground crew |  | 60.58 | Completed | No
WO-26-002358 | 4.9 | Bayou | BY-S05-02 | Preventive maintenance | P4 planned | 2026-03-09 | 2026-03-27 | 2026-03-27 | Underground crew |  | 165.08 | Completed | No
WO-26-002359 | 6.3 | Bayou | BY-S13-01 | Preventive maintenance | P4 planned | 2026-03-09 | 2026-04-11 | 2026-04-11 | Contract line | CT-03 | 57.85 | Completed | No
WO-26-002360 | 7.8 | Bayou | BY-S07-06 | Preventive maintenance | P4 planned | 2026-03-09 | 2026-04-10 | 2026-04-10 | Underground crew |  | 53.13 | Completed | No
WO-26-002361 | 5.8 | Bayou | BY-S30-03 | Preventive maintenance | P4 planned | 2026-03-09 | 2026-04-24 | 2026-04-24 | Contract line | CT-03 | 478.15 | Completed | No
WO-26-002362 | 1.6 | Bayou | BY-S22-03 | Service order - field | P3 within 10 days | 2026-03-09 | 2026-03-17 | 2026-03-17 | Meter technician |  | 13.94 | Completed | No
WO-26-002363 | 1.7 | Bayou | BY-S14-01 | Service order - field | P3 within 10 days | 2026-03-09 | 2026-03-19 | 2026-03-20 | Meter technician |  | 10.82 | Completed | No
WO-26-002364 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-09 | 2026-03-11 | 2026-03-12 | Contract line | CT-03 | 306.05 | Completed | No
WO-26-002365 | 12.7 | Bayou | BY-S24-05 | Transformer replacement | P2 same day | 2026-03-09 | 2026-03-09 | 2026-03-09 | Internal line |  | 3773.31 | Completed | No
WO-26-002366 | 8.3 | Bayou | BY-S18-01 | Transformer replacement | P1 emergency | 2026-03-09 | 2026-03-09 | 2026-03-09 | Internal line |  | 12007.62 | Completed | No
WO-26-002367 | 3.1 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-03-09 | 2026-03-09 | 2026-03-09 | Troubleman |  | 140.78 | Completed | No
WO-26-002368 | 3.5 | Bayou | BY-S26-03 | Trouble - no power | P2 same day | 2026-03-09 | 2026-03-10 | 2026-03-10 | Troubleman |  | 270.85 | Completed | No
WO-26-002369 | 2.4 | Bayou | BY-S07-01 | Trouble - no power | P1 emergency | 2026-03-09 | 2026-03-09 | 2026-03-09 | Troubleman |  | 205.64 | Completed | No
WO-26-002370 | 5.4 | Crossroads | CR-S12-03 | Corrective maintenance | P4 planned | 2026-03-09 | 2026-03-28 | 2026-03-28 | Underground crew |  | 1848.21 | Completed | No
WO-26-002371 | 7.6 | Crossroads | CR-S20-02 | Corrective maintenance | P3 within 10 days | 2026-03-09 | 2026-03-11 | 2026-03-11 | Underground crew |  | 411.5 | Completed | No
WO-26-002372 | 0.8 | Crossroads | CR-S04-05 | Meter exchange | P4 planned | 2026-03-09 | 2026-04-27 | 2026-04-28 | Meter technician |  | 163.51 | Completed | No
WO-26-002373 | 14.1 | Crossroads | CR-S04-03 | Pole replacement | P3 within 10 days | 2026-03-09 | 2026-03-10 | 2026-03-10 | Contract line | CT-02 | 3056.14 | Completed | No
WO-26-002374 | 22.4 | Crossroads | CR-S22-02 | Pole replacement | P4 planned | 2026-03-09 | 2026-04-10 | 2026-04-10 | Internal line |  | 3134.7 | Completed | No
WO-26-002375 | 21.8 | Crossroads | CR-S18-04 | Pole replacement | P4 planned | 2026-03-09 | 2026-04-22 | 2026-04-22 | Internal line |  | 1495.57 | Completed | No
WO-26-002376 | 6.2 | Crossroads | CR-S05-05 | Preventive maintenance | P4 planned | 2026-03-09 | 2026-03-30 | 2026-04-03 | Contract line | CT-02 | 358.05 | Completed | No
WO-26-002377 | 1 | Crossroads | CR-S08-04 | Service order - field | P2 same day | 2026-03-09 | 2026-03-10 | 2026-03-10 | Meter technician |  | 38.59 | Completed | No
WO-26-002378 |  | Crossroads | CR-S18-02 | Service order - field | P2 same day | 2026-03-09 | 2026-03-10 |  | Meter technician |  |  | Cancelled | No
WO-26-002379 | 1.6 | Crossroads | CR-S14-02 | Service order - field | P3 within 10 days | 2026-03-09 | 2026-03-17 | 2026-03-18 | Meter technician |  | 3.16 | Completed | No
WO-26-002380 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-09 | 2026-03-11 | 2026-03-19 | Contract line | CT-02 | 290.02 | Completed | No
WO-26-002381 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-09 | 2026-03-12 | 2026-03-12 | Contract line | CT-01 | 78.15 | Completed | No
WO-26-002382 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-09 | 2026-03-16 | 2026-03-16 | Internal line |  | 52.69 | Completed | No
WO-26-002383 | 11.8 | Crossroads | CR-S21-03 | Transformer replacement | P3 within 10 days | 2026-03-09 | 2026-03-10 | 2026-03-11 | Contract line | CT-02 | 12057.29 | Completed | No
WO-26-002384 | 5 | Crossroads | CR-S18-03 | Trouble - no power | P1 emergency | 2026-03-09 | 2026-03-09 | 2026-03-09 | Troubleman |  | 221.66 | Completed | No
WO-26-002385 | 10.1 | Bayou | BY-S06-02 | Corrective maintenance | P3 within 10 days | 2026-03-10 | 2026-03-19 | 2026-03-20 | Contract line | CT-03 | 1407.97 | Completed | No
WO-26-002386 | 4.4 | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-03-10 | 2026-03-20 | 2026-03-20 | Contract line | CT-03 | 1944.71 | Completed | No
WO-26-002387 | 1.4 | Bayou | BY-S23-01 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-20 | 2026-03-20 | Meter technician |  | 158.93 | Completed | No
WO-26-002388 | 1.4 | Bayou | BY-S18-02 | Meter exchange | P4 planned | 2026-03-10 | 2026-03-23 | 2026-03-23 | Meter technician |  | 133.53 | Completed | No
WO-26-002389 | 1 | Bayou | BY-S20-01 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-17 | 2026-03-19 | Meter technician |  | 178.53 | Completed | No
WO-26-002390 | 1.2 | Bayou | BY-S29-02 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-13 | 2026-03-13 | Meter technician |  | 119.59 | Completed | No
WO-26-002391 | 0.7 | Bayou | BY-S23-04 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-14 | 2026-03-14 | Meter technician |  | 146.9 | Completed | No
WO-26-002392 | 0.7 | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-18 | 2026-03-22 | Meter technician |  | 109.5 | Completed | No
WO-26-002393 | 4.8 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-03-10 | 2026-04-04 | 2026-04-04 | Internal line |  | 326.13 | Completed | No
WO-26-002394 | 2.5 | Bayou | BY-S02-02 | Preventive maintenance | P4 planned | 2026-03-10 | 2026-04-11 | 2026-04-11 | Underground crew |  | 535.23 | Completed | No
WO-26-002395 | 1.5 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Meter technician |  | 35.2 | Completed | No
WO-26-002396 | 1.1 | Bayou | BY-S27-02 | Service order - field | P3 within 10 days | 2026-03-10 | 2026-03-16 | 2026-03-16 | Meter technician |  | 3.28 | Completed | No
WO-26-002397 | 0.8 | Bayou | BY-S25-05 | Service order - field | P3 within 10 days | 2026-03-10 | 2026-03-14 | 2026-03-14 | Meter technician |  | 36.06 | Completed | No
WO-26-002398 | 1.6 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Meter technician |  | 24.47 | Completed | No
WO-26-002399 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-10 | 2026-03-19 | 2026-03-19 | Contract line | CT-04 | 365.37 | Completed | No
WO-26-002400 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-10 | 2026-03-15 | 2026-03-19 | Contract line | CT-04 | 339.48 | Completed | No
WO-26-002401 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-10 | 2026-03-19 | 2026-03-19 | Internal line |  | 265.21 | Completed | No
WO-26-002402 | 5.8 | Bayou | BY-S21-01 | Trouble - no power | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Troubleman |  | 303.16 | Completed | No
WO-26-002403 | 4.9 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-03-10 | 2026-03-10 | 2026-03-10 | Internal line |  | 229.07 | Completed | No
WO-26-002404 | 4.5 | Bayou | BY-S15-05 | Trouble - partial or voltage | P3 within 10 days | 2026-03-10 | 2026-03-18 | 2026-03-19 | Troubleman |  | 232.63 | Completed | No
WO-26-002405 | 10 | Crossroads | CR-S02-04 | Corrective maintenance | P3 within 10 days | 2026-03-10 | 2026-03-17 | 2026-03-17 | Internal line |  | 828.07 | Completed | No
WO-26-002406 | 7.9 | Crossroads | CR-S11-01 | Corrective maintenance | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Underground crew |  | 466.97 | Completed | No
WO-26-002407 | 1.3 | Crossroads | CR-S09-03 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-17 | 2026-03-18 | Meter technician |  | 145.36 | Completed | No
WO-26-002408 | 1.1 | Crossroads | CR-S14-02 | Meter exchange | P3 within 10 days | 2026-03-10 | 2026-03-19 | 2026-03-21 | Meter technician |  | 160.03 | Completed | No
WO-26-002409 | 14.1 | Crossroads | CR-S15-01 | New service - small | P3 within 10 days | 2026-03-10 | 2026-03-14 | 2026-03-14 | Underground crew |  | 432.07 | Completed | No
WO-26-002410 | 20.2 | Crossroads | CR-S19-03 | Pole replacement | P3 within 10 days | 2026-03-10 | 2026-03-20 | 2026-03-21 | Internal line |  | 2798.69 | Completed | No
WO-26-002411 | 17 | Crossroads | CR-S19-03 | Pole replacement | P3 within 10 days | 2026-03-10 | 2026-03-20 | 2026-03-20 | Internal line |  | 2862.72 | Completed | No
WO-26-002412 | 6.4 | Crossroads | CR-S23-04 | Preventive maintenance | P4 planned | 2026-03-10 | 2026-04-28 | 2026-04-28 | Underground crew |  | 88.19 | Completed | No
WO-26-002413 | 1.3 | Crossroads | CR-S04-06 | Service order - field | P3 within 10 days | 2026-03-10 | 2026-03-11 | 2026-03-13 | Meter technician |  | 35.97 | Completed | No
WO-26-002414 | 1 | Crossroads | CR-S04-03 | Service order - field | P3 within 10 days | 2026-03-10 | 2026-03-13 | 2026-03-13 | Meter technician |  | 11.9 | Completed | No
WO-26-002415 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-10 | 2026-03-11 | 2026-03-11 | Contract line | CT-02 | 239.81 | Completed | No
WO-26-002416 | 2.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-10 | 2026-03-17 | 2026-03-18 | Contract line | CT-02 | 388.06 | Completed | No
WO-26-002417 | 10.2 | Crossroads | CR-S30-03 | Transformer replacement | P3 within 10 days | 2026-03-10 | 2026-03-11 | 2026-03-12 | Internal line |  | 9963.18 | Completed | No
WO-26-002418 | 10 | Crossroads | CR-S09-04 | Transformer replacement | P1 emergency | 2026-03-10 | 2026-03-10 | 2026-03-10 | Internal line |  | 9855.81 | Completed | No
WO-26-002419 | 9.1 | Crossroads | CR-S18-01 | Transformer replacement | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Contract line | CT-02 | 3666.44 | Completed | No
WO-26-002420 | 2.3 | Crossroads | CR-S32-01 | Trouble - no power | P2 same day | 2026-03-10 | 2026-03-11 | 2026-03-11 | Troubleman |  | 110.38 | Completed | No
WO-26-002421 | 5.2 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-03-10 | 2026-03-10 | 2026-03-10 | Troubleman |  | 65.35 | Completed | No
WO-26-002422 | 5.9 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-03-10 | 2026-03-10 | 2026-03-10 | Troubleman |  | 339.69 | Completed | No
WO-26-002423 | 5 | Crossroads | CR-S30-07 | Trouble - no power | P1 emergency | 2026-03-10 | 2026-03-10 | 2026-03-10 | Troubleman |  | 73.79 | Completed | No
WO-26-002424 | 2.9 | Crossroads | CR-S14-01 | Trouble - partial or voltage | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Troubleman |  | 149.41 | Completed | No
WO-26-002425 | 4.5 | Crossroads | CR-S03-03 | Trouble - partial or voltage | P3 within 10 days | 2026-03-10 | 2026-03-20 | 2026-03-20 | Troubleman |  | 118.13 | Completed | No
WO-26-002426 | 4.6 | Crossroads | CR-S18-03 | Trouble - partial or voltage | P2 same day | 2026-03-10 | 2026-03-10 | 2026-03-10 | Troubleman |  | 122.52 | Completed | No
WO-26-002427 | 6.3 | Bayou | BY-S15-02 | Corrective maintenance | P3 within 10 days | 2026-03-11 | 2026-03-15 | 2026-03-15 | Contract line | CT-04 | 1283.08 | Completed | No
WO-26-002428 | 1.1 | Bayou | BY-S06-02 | Meter exchange | P3 within 10 days | 2026-03-11 | 2026-03-18 | 2026-03-20 | Meter technician |  | 122.16 | Completed | No
WO-26-002429 | 0.5 | Bayou | BY-S21-05 | Meter exchange | P4 planned | 2026-03-11 | 2026-04-04 | 2026-04-05 | Meter technician |  | 60.3 | Completed | No
WO-26-002430 | 0.9 | Bayou | BY-S09-03 | Meter exchange | P3 within 10 days | 2026-03-11 | 2026-03-21 | 2026-03-21 | Meter technician |  | 130.33 | Completed | No
WO-26-002431 | 0.8 | Bayou | BY-S30-03 | Meter exchange | P3 within 10 days | 2026-03-11 | 2026-03-15 | 2026-03-17 | Meter technician |  | 107.76 | Completed | No
WO-26-002432 | 0.9 | Bayou | BY-S01-01 | Meter exchange | P4 planned | 2026-03-11 | 2026-04-10 | 2026-04-12 | Meter technician |  | 154.87 | Completed | No
WO-26-002433 | 0.7 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-03-11 | 2026-03-15 | 2026-03-17 | Meter technician |  | 157.54 | Completed | No
WO-26-002434 | 12.4 | Bayou | BY-S05-01 | Pole replacement | P3 within 10 days | 2026-03-11 | 2026-03-14 | 2026-03-15 | Internal line |  | 2507.55 | Completed | No
WO-26-002435 | 3 | Bayou | BY-S08-02 | Preventive maintenance | P4 planned | 2026-03-11 | 2026-03-20 | 2026-03-21 | Underground crew |  | 26.65 | Completed | No
WO-26-002436 | 6.2 | Bayou | BY-S21-05 | Preventive maintenance | P4 planned | 2026-03-11 | 2026-03-22 | 2026-03-22 | Underground crew |  | 478.09 | Completed | No
WO-26-002437 | 4.9 | Bayou | BY-S04-02 | Preventive maintenance | P4 planned | 2026-03-11 | 2026-03-22 | 2026-03-24 | Internal line |  | 169.43 | Completed | No
WO-26-002438 | 1 | Bayou | BY-S24-02 | Service order - field | P3 within 10 days | 2026-03-11 | 2026-03-14 | 2026-03-14 | Meter technician |  | 34.94 | Completed | No
WO-26-002439 | 1.2 | Bayou | BY-S14-01 | Service order - field | P2 same day | 2026-03-11 | 2026-03-11 | 2026-03-11 | Meter technician |  | 25.48 | Completed | No
WO-26-002440 | 1.4 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Meter technician |  | 39.13 | Completed | No
WO-26-002441 | 1.2 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-03-11 | 2026-03-11 | 2026-03-11 | Meter technician |  | 25.56 | Completed | No
WO-26-002442 | 1 | Bayou | BY-S09-02 | Service order - field | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Meter technician |  | 22.27 | Completed | No
WO-26-002443 | 0.9 | Bayou | BY-S19-02 | Service order - field | P3 within 10 days | 2026-03-11 | 2026-03-13 | 2026-03-13 | Meter technician |  | 27.66 | Completed | No
WO-26-002444 | 1 | Bayou | BY-S26-06 | Service order - field | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Meter technician |  | 38.67 | Completed | No
WO-26-002445 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-11 | 2026-03-21 | 2026-03-22 | Contract line | CT-03 | 91.63 | Completed | No
WO-26-002446 | 2.6 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Troubleman |  | 179.06 | Completed | No
WO-26-002447 | 2.1 | Bayou | BY-S18-06 | Trouble - no power | P1 emergency | 2026-03-11 | 2026-03-11 | 2026-03-11 | Troubleman |  | 202.86 | Completed | No
WO-26-002448 | 3.9 | Bayou | BY-S15-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-11 | 2026-03-13 | 2026-03-15 | Troubleman |  | 126.19 | Completed | No
WO-26-002449 | 4.9 | Bayou | BY-S02-01 | Trouble - partial or voltage | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Troubleman |  | 173.57 | Completed | No
WO-26-002450 | 6.8 | Crossroads | CR-S08-04 | Corrective maintenance | P3 within 10 days | 2026-03-11 | 2026-03-20 | 2026-03-20 | Contract line | CT-02 | 1871.1 | Completed | No
WO-26-002451 | 9.4 | Crossroads | CR-S13-05 | Corrective maintenance | P4 planned | 2026-03-11 | 2026-03-28 | 2026-03-30 | Contract line | CT-01 | 1179.23 | Completed | No
WO-26-002452 | 11.2 | Crossroads | CR-S27-02 | Corrective maintenance | P3 within 10 days | 2026-03-11 | 2026-03-19 | 2026-03-21 | Underground crew |  | 695.09 | Completed | No
WO-26-002453 | 4.7 | Crossroads | CR-S13-04 | Corrective maintenance | P3 within 10 days | 2026-03-11 | 2026-03-20 | 2026-03-20 | Internal line |  | 2110.59 | Completed | No
WO-26-002454 | 1.1 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-03-11 | 2026-03-17 | 2026-03-18 | Meter technician |  | 131.2 | Completed | No
WO-26-002455 | 1.1 | Crossroads | CR-S11-02 | Meter exchange | P3 within 10 days | 2026-03-11 | 2026-03-18 | 2026-03-19 | Meter technician |  | 175.92 | Completed | No
WO-26-002456 | 11.4 | Crossroads | CR-S09-01 | Pole replacement | P4 planned | 2026-03-11 | 2026-04-05 | 2026-04-07 | Contract line | CT-01 | 2199.44 | Completed | No
WO-26-002457 | 3.9 | Crossroads | CR-S18-06 | Preventive maintenance | P4 planned | 2026-03-11 | 2026-03-20 | 2026-03-20 | Underground crew |  | 274.19 | Completed | No
WO-26-002458 | 0.6 | Crossroads | CR-S10-03 | Service order - field | P3 within 10 days | 2026-03-11 | 2026-03-17 | 2026-03-17 | Meter technician |  | 4.98 | Completed | No
WO-26-002459 | 1.9 | Crossroads | CR-S28-03 | Service order - field | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Meter technician |  | 8.77 | Completed | No
WO-26-002460 | 1.7 | Crossroads | CR-S19-02 | Service order - field | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Meter technician |  | 2.26 | Completed | No
WO-26-002461 | 1.4 | Crossroads | CR-S26-06 | Service order - field | P2 same day | 2026-03-11 | 2026-03-11 | 2026-03-11 | Meter technician |  | 26.34 | Completed | No
WO-26-002462 | 1.7 | Crossroads | CR-S12-03 | Service order - field | P3 within 10 days | 2026-03-11 | 2026-03-19 | 2026-03-20 | Meter technician |  | 8.84 | Completed | No
WO-26-002463 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-03-11 | 2026-03-29 | 2026-03-29 | Internal line |  | 251.68 | Completed | No
WO-26-002464 | 5.6 | Crossroads | CR-S29-02 | Trouble - no power | P1 emergency | 2026-03-11 | 2026-03-11 | 2026-03-11 | Troubleman |  | 276.51 | Completed | No
WO-26-002465 | 5 | Crossroads | CR-S24-02 | Trouble - no power | P1 emergency | 2026-03-11 | 2026-03-11 | 2026-03-11 | Troubleman |  | 10.86 | Completed | No
WO-26-002466 | 5.4 | Crossroads | CR-S11-01 | Trouble - no power | P1 emergency | 2026-03-11 | 2026-03-11 | 2026-03-11 | Troubleman |  | 94.81 | Completed | No
WO-26-002467 | 5.3 | Crossroads | CR-S16-04 | Trouble - no power | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Troubleman |  | 230.39 | Completed | No
WO-26-002468 | 1.5 | Crossroads | CR-S22-02 | Trouble - partial or voltage | P2 same day | 2026-03-11 | 2026-03-12 | 2026-03-12 | Troubleman |  | 195.67 | Completed | No
WO-26-002469 | 3.6 | Crossroads | CR-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-11 | 2026-03-13 | 2026-03-13 | Troubleman |  | 174.88 | Completed | No
WO-26-002470 | 4.8 | Bayou | BY-S11-01 | Corrective maintenance | P4 planned | 2026-03-12 | 2026-03-21 | 2026-03-21 | Internal line |  | 221.5 | Completed | No
WO-26-002471 | 9.4 | Bayou | BY-S18-05 | Corrective maintenance | P3 within 10 days | 2026-03-12 | 2026-03-16 | 2026-03-16 | Internal line |  | 1653.3 | Completed | No
WO-26-002472 | 11.7 | Bayou | BY-S09-02 | Corrective maintenance | P3 within 10 days | 2026-03-12 | 2026-03-16 | 2026-03-16 | Internal line |  | 1643.64 | Completed | No
WO-26-002473 | 1 | Bayou | BY-S01-01 | Meter exchange | P4 planned | 2026-03-12 | 2026-04-20 | 2026-04-20 | Meter technician |  | 155.15 | Completed | No
WO-26-002474 | 0.6 | Bayou | BY-S16-06 | Meter exchange | P4 planned | 2026-03-12 | 2026-04-06 | 2026-04-06 | Meter technician |  | 144.39 | Completed | No
WO-26-002475 | 1.1 | Bayou | BY-S16-06 | Meter exchange | P4 planned | 2026-03-12 | 2026-04-14 | 2026-04-16 | Meter technician |  | 133.5 | Completed | No
WO-26-002476 | 0.7 | Bayou | BY-S18-03 | Meter exchange | P4 planned | 2026-03-12 | 2026-05-09 | 2026-05-09 | Meter technician |  | 132.12 | Completed | No
WO-26-002477 | 22.5 | Bayou | BY-S21-02 | Pole replacement | P4 planned | 2026-03-12 | 2026-03-20 | 2026-03-20 | Contract line | CT-04 | 2798.14 | Completed | No
WO-26-002478 | 21.9 | Bayou | BY-S01-02 | Pole replacement | P4 planned | 2026-03-12 | 2026-05-09 | 2026-05-13 | Internal line |  | 1209.11 | Completed | No
WO-26-002479 |  | Bayou | BY-S17-03 | Preventive maintenance | P4 planned | 2026-03-12 | 2026-04-29 |  | Internal line |  |  | Cancelled | No
WO-26-002480 | 1 | Bayou | BY-S12-03 | Service order - field | P3 within 10 days | 2026-03-12 | 2026-03-17 | 2026-03-17 | Meter technician |  | 20.26 | Completed | No
WO-26-002481 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-12 | 2026-03-14 | 2026-03-16 | Internal line |  | 368.34 | Completed | No
WO-26-002482 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-12 | 2026-03-20 | 2026-03-20 | Internal line |  | 140.49 | Completed | No
WO-26-002483 | 1.2 | Bayou |  | Streetlight | P4 planned | 2026-03-12 | 2026-04-25 | 2026-04-25 | Contract line | CT-03 | 119.69 | Completed | No
WO-26-002484 | 9.1 | Bayou | BY-S07-06 | Transformer replacement | P3 within 10 days | 2026-03-12 | 2026-03-19 | 2026-03-27 | Contract line | CT-04 | 4423.08 | Completed | No
WO-26-002485 | 10 | Bayou | BY-S15-02 | Transformer replacement | P1 emergency | 2026-03-12 | 2026-03-12 | 2026-03-12 | Internal line |  | 12150.82 | Completed | No
WO-26-002486 | 10.7 | Bayou | BY-S27-06 | Transformer replacement | P2 same day | 2026-03-12 | 2026-03-13 | 2026-03-13 | Contract line | CT-04 | 9078.92 | Completed | No
WO-26-002487 | 4.3 | Bayou | BY-S17-02 | Trouble - no power | P2 same day | 2026-03-12 | 2026-03-13 | 2026-03-13 | Troubleman |  | 44.12 | Completed | No
WO-26-002488 | 5.5 | Bayou | BY-S05-02 | Trouble - no power | P1 emergency | 2026-03-12 | 2026-03-12 | 2026-03-12 | Troubleman |  | 237.85 | Completed | No
WO-26-002489 | 4.5 | Bayou | BY-S20-01 | Trouble - no power | P1 emergency | 2026-03-12 | 2026-03-12 | 2026-03-12 | Troubleman |  | 61.9 | Completed | No
WO-26-002490 | 4.7 | Bayou | BY-S10-04 | Trouble - no power | P1 emergency | 2026-03-12 | 2026-03-12 | 2026-03-12 | Troubleman |  | 63.72 | Completed | No
WO-26-002491 | 5.3 | Bayou | BY-S16-01 | Trouble - no power | P1 emergency | 2026-03-12 | 2026-03-12 | 2026-03-12 | Troubleman |  | 4.99 | Completed | No
WO-26-002492 | 3.4 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-03-12 | 2026-03-13 | 2026-03-13 | Troubleman |  | 262.7 | Completed | No
WO-26-002493 | 2.1 | Bayou | BY-S26-04 | Trouble - partial or voltage | P3 within 10 days | 2026-03-12 | 2026-03-18 | 2026-03-20 | Troubleman |  | 74.61 | Completed | No
WO-26-002494 | 3.6 | Crossroads | CR-S06-02 | Corrective maintenance | P2 same day | 2026-03-12 | 2026-03-12 | 2026-03-12 | Contract line | CT-02 | 368.63 | Completed | No
WO-26-002495 | 0.7 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-03-12 | 2026-03-21 | 2026-03-21 | Meter technician |  | 150.72 | Completed | No
WO-26-002496 | 8.2 | Crossroads | CR-S21-02 | New service - small | P4 planned | 2026-03-12 | 2026-05-07 | 2026-05-07 | Contract line | CT-02 | 2377 | Completed | No
WO-26-002497 | 15.4 | Crossroads | CR-S20-02 | New service - small | P4 planned | 2026-03-12 | 2026-04-03 | 2026-04-04 | Underground crew |  | 2213.98 | Completed | No
WO-26-002498 | 5.8 | Crossroads | CR-S24-02 | New service - small | P3 within 10 days | 2026-03-12 | 2026-03-21 | 2026-03-21 | Internal line |  | 4086.31 | Completed | No
WO-26-002499 | 22.6 | Crossroads | CR-S22-03 | Pole replacement | P3 within 10 days | 2026-03-12 | 2026-03-15 | 2026-03-15 | Contract line | CT-02 | 1455.77 | Completed | No
WO-26-002500 | 1.7 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-03-12 | 2026-03-13 | 2026-03-13 | Meter technician |  | 0.15 | Completed | No
WO-26-002501 | 1.1 | Crossroads | CR-S01-02 | Service order - field | P3 within 10 days | 2026-03-12 | 2026-03-13 | 2026-03-15 | Meter technician |  | 22.39 | Completed | No
WO-26-002502 | 2.4 | Crossroads |  | Streetlight | P4 planned | 2026-03-12 | 2026-05-01 | 2026-05-01 | Internal line |  | 394.25 | Completed | No
WO-26-002503 | 1.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-12 | 2026-03-14 | 2026-03-14 | Contract line | CT-01 | 384.12 | Completed | No
WO-26-002504 | 9.1 | Crossroads | CR-S32-01 | Transformer replacement | P3 within 10 days | 2026-03-12 | 2026-03-21 | 2026-03-21 | Internal line |  | 3716.79 | Completed | No
WO-26-002505 | 4.5 | Crossroads | CR-S07-05 | Trouble - no power | P2 same day | 2026-03-12 | 2026-03-13 | 2026-03-13 | Troubleman |  | 20.53 | Completed | No
WO-26-002506 | 2.8 | Crossroads | CR-S14-04 | Trouble - partial or voltage | P3 within 10 days | 2026-03-12 | 2026-03-14 | 2026-03-15 | Troubleman |  | 33.17 | Completed | No
WO-26-002507 | 1.5 | Crossroads | CR-S30-07 | Trouble - partial or voltage | P3 within 10 days | 2026-03-12 | 2026-03-14 | 2026-03-22 | Troubleman |  | 81.58 | Completed | No
WO-26-002508 | 2.4 | Crossroads | CR-S14-03 | Trouble - partial or voltage | P2 same day | 2026-03-12 | 2026-03-12 | 2026-03-12 | Troubleman |  | 247.26 | Completed | No
WO-26-002509 | 1.8 | Crossroads | CR-S24-04 | Trouble - partial or voltage | P2 same day | 2026-03-12 | 2026-03-13 | 2026-03-13 | Troubleman |  | 241.66 | Completed | No
WO-26-002510 | 3.1 | Crossroads | CR-S14-05 | Trouble - partial or voltage | P3 within 10 days | 2026-03-12 | 2026-03-20 | 2026-03-24 | Troubleman |  | 90.88 | Completed | No
WO-26-002511 | 4.8 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-03-13 | 2026-03-17 | 2026-03-18 | Contract line | CT-04 | 263.01 | Completed | No
WO-26-002512 | 1.5 | Bayou | BY-S23-02 | Meter exchange | P4 planned | 2026-03-13 | 2026-04-30 | 2026-05-04 | Meter technician |  | 136.77 | Completed | No
WO-26-002513 | 1.4 | Bayou | BY-S22-04 | Meter exchange | P3 within 10 days | 2026-03-13 | 2026-03-17 | 2026-03-17 | Meter technician |  | 64.41 | Completed | No
WO-26-002514 | 1.4 | Bayou | BY-S03-02 | Meter exchange | P4 planned | 2026-03-13 | 2026-04-27 | 2026-04-27 | Meter technician |  | 146.34 | Completed | No
WO-26-002515 | 11.2 | Bayou | BY-S15-06 | New service - small | P4 planned | 2026-03-13 | 2026-04-10 | 2026-04-14 | Internal line |  | 2052.09 | Completed | No
WO-26-002516 | 22.8 | Bayou | BY-S27-06 | Pole replacement | P4 planned | 2026-03-13 | 2026-04-14 | 2026-04-16 | Contract line | CT-03 | 2917.8 | Completed | No
WO-26-002517 |  | Bayou | BY-S07-01 | Pole replacement | P4 planned | 2026-03-13 | 2026-04-27 |  | Internal line |  |  | Cancelled | No
WO-26-002518 | 3.8 | Bayou | BY-S18-02 | Preventive maintenance | P4 planned | 2026-03-13 | 2026-03-27 | 2026-03-27 | Internal line |  | 200.82 | Completed | No
WO-26-002519 | 6.9 | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-03-13 | 2026-04-05 | 2026-04-05 | Underground crew |  | 154.54 | Completed | No
WO-26-002520 | 4.3 | Bayou | BY-S25-05 | Preventive maintenance | P4 planned | 2026-03-13 | 2026-05-10 | 2026-05-14 | Contract line | CT-04 | 165.53 | Completed | No
WO-26-002521 | 5.9 | Bayou | BY-S14-03 | Preventive maintenance | P4 planned | 2026-03-13 | 2026-04-17 | 2026-04-18 | Contract line | CT-04 | 368.32 | Completed | No
WO-26-002522 | 0.8 | Bayou | BY-S16-05 | Service order - field | P3 within 10 days | 2026-03-13 | 2026-03-15 | 2026-03-15 | Meter technician |  | 18.27 | Completed | No
WO-26-002523 | 1 | Bayou | BY-S06-02 | Service order - field | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Meter technician |  | 14.16 | Completed | No
WO-26-002524 | 1.6 | Bayou | BY-S07-06 | Service order - field | P3 within 10 days | 2026-03-13 | 2026-03-21 | 2026-03-23 | Meter technician |  | 9.32 | Completed | No
WO-26-002525 | 0.8 | Bayou | BY-S10-02 | Service order - field | P3 within 10 days | 2026-03-13 | 2026-03-14 | 2026-03-14 | Meter technician |  | 10.62 | Completed | No
WO-26-002526 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-13 | 2026-03-22 | 2026-03-26 | Contract line | CT-03 | 441.11 | Completed | No
WO-26-002527 | 9.4 | Bayou | BY-S29-01 | Transformer replacement | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Internal line |  | 12397.68 | Completed | No
WO-26-002528 | 3.9 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Internal line |  | 55.9 | Completed | No
WO-26-002529 | 3.8 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-03-13 | 2026-03-13 | 2026-03-13 | Troubleman |  | 74.08 | Completed | No
WO-26-002530 | 5.9 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Internal line |  | 251.3 | Completed | No
WO-26-002531 | 4.2 | Bayou | BY-S09-03 | Trouble - no power | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Troubleman |  | 198.63 | Completed | No
WO-26-002532 | 2.3 | Bayou | BY-S27-01 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Troubleman |  | 200.74 | Completed | No
WO-26-002533 | 5.4 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Troubleman |  | 317.86 | Completed | No
WO-26-002534 | 4.8 | Bayou | BY-S19-02 | Trouble - partial or voltage | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Troubleman |  | 116.19 | Completed | No
WO-26-002535 | 4.5 | Bayou | BY-S24-04 | Trouble - partial or voltage | P3 within 10 days | 2026-03-13 | 2026-03-23 | 2026-03-24 | Troubleman |  | 61.27 | Completed | No
WO-26-002536 | 8.2 | Crossroads | CR-S19-02 | Corrective maintenance | P3 within 10 days | 2026-03-13 | 2026-03-14 | 2026-03-14 | Underground crew |  | 88.36 | Completed | No
WO-26-002537 | 6.4 | Crossroads | CR-S09-03 | Corrective maintenance | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Contract line | CT-02 | 1758.65 | Completed | No
WO-26-002538 | 5.6 | Crossroads | CR-S05-01 | Corrective maintenance | P3 within 10 days | 2026-03-13 | 2026-03-19 | 2026-03-20 | Underground crew |  | 143.13 | Completed | No
WO-26-002539 | 10.1 | Crossroads | CR-S04-04 | Corrective maintenance | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Internal line |  | 1210.31 | Completed | No
WO-26-002540 | 3.5 | Crossroads | CR-S16-02 | Corrective maintenance | P4 planned | 2026-03-13 | 2026-04-17 | 2026-04-21 | Internal line |  | 1900.01 | Completed | No
WO-26-002541 | 1.2 | Crossroads | CR-S03-02 | Meter exchange | P3 within 10 days | 2026-03-13 | 2026-03-20 | 2026-03-24 | Meter technician |  | 135.97 | Completed | No
WO-26-002542 | 1.2 | Crossroads | CR-S12-01 | Meter exchange | P4 planned | 2026-03-13 | 2026-05-08 | 2026-05-08 | Meter technician |  | 117.52 | Completed | No
WO-26-002543 | 1 | Crossroads | CR-S30-04 | Meter exchange | P3 within 10 days | 2026-03-13 | 2026-03-18 | 2026-03-18 | Meter technician |  | 65 | Completed | No
WO-26-002544 | 0.8 | Crossroads | CR-S27-02 | Meter exchange | P4 planned | 2026-03-13 | 2026-04-25 | 2026-04-25 | Meter technician |  | 96.42 | Completed | No
WO-26-002545 | 1.3 | Crossroads | CR-S13-05 | Meter exchange | P3 within 10 days | 2026-03-13 | 2026-03-20 | 2026-03-20 | Meter technician |  | 89.43 | Completed | No
WO-26-002546 | 5.3 | Crossroads | CR-S20-03 | New service - small | P3 within 10 days | 2026-03-13 | 2026-03-15 | 2026-03-15 | Internal line |  | 1134.58 | Completed | No
WO-26-002547 | 4.4 | Crossroads | CR-S25-01 | Preventive maintenance | P4 planned | 2026-03-13 | 2026-04-23 | 2026-04-25 | Internal line |  | 255.38 | Completed | No
WO-26-002548 | 7.3 | Crossroads | CR-S31-01 | Preventive maintenance | P4 planned | 2026-03-13 | 2026-04-07 | 2026-04-07 | Internal line |  | 321.04 | Completed | No
WO-26-002549 | 1.8 | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Meter technician |  | 25.42 | Completed | No
WO-26-002550 | 2 | Crossroads | CR-S18-02 | Service order - field | P3 within 10 days | 2026-03-13 | 2026-03-19 | 2026-03-21 | Meter technician |  | 22.96 | Completed | No
WO-26-002551 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-13 | 2026-03-18 | 2026-03-19 | Contract line | CT-01 | 388.12 | Completed | No
WO-26-002552 | 3.2 | Crossroads | CR-S19-04 | Trouble - no power | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Troubleman |  | 315.14 | Completed | No
WO-26-002553 | 3.8 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Internal line |  | 118.88 | Completed | No
WO-26-002554 | 3 | Crossroads | CR-S01-04 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Troubleman |  | 185.54 | Completed | No
WO-26-002555 | 4.9 | Crossroads | CR-S09-02 | Trouble - no power | P1 emergency | 2026-03-13 | 2026-03-13 | 2026-03-13 | Troubleman |  | 162.32 | Completed | No
WO-26-002556 | 4.3 | Crossroads | CR-S27-02 | Trouble - no power | P2 same day | 2026-03-13 | 2026-03-13 | 2026-03-13 | Troubleman |  | 137.86 | Completed | No
WO-26-002557 | 2.3 | Crossroads | CR-S14-01 | Trouble - no power | P2 same day | 2026-03-13 | 2026-03-14 | 2026-03-14 | Troubleman |  | 226.41 | Completed | No
WO-26-002558 | 1.6 | Crossroads | CR-S07-05 | Trouble - partial or voltage | P3 within 10 days | 2026-03-13 | 2026-03-18 | 2026-03-18 | Troubleman |  | 171.45 | Completed | No
WO-26-002559 | 8.7 | Bayou | BY-S24-01 | Corrective maintenance | P2 same day | 2026-03-14 | 2026-03-15 | 2026-03-15 | Internal line |  | 242.13 | Completed | No
WO-26-002560 | 7.6 | Bayou | BY-S18-03 | Transformer replacement | P1 emergency | 2026-03-14 | 2026-03-14 | 2026-03-14 | Internal line |  | 8654.66 | Completed | No
WO-26-002561 | 3.5 | Bayou | BY-S21-03 | Trouble - no power | P1 emergency | 2026-03-14 | 2026-03-14 | 2026-03-14 | Troubleman |  | 280.5 | Completed | No
WO-26-002562 | 4.7 | Bayou | BY-S29-01 | Trouble - no power | P2 same day | 2026-03-14 | 2026-03-15 | 2026-03-15 | Internal line |  | 99.78 | Completed | No
WO-26-002563 | 21.7 | Crossroads | CR-S17-01 | Pole replacement | P2 same day | 2026-03-14 | 2026-03-14 | 2026-03-14 | Contract line | CT-01 | 2452.03 | Completed | No
WO-26-002564 | 11.3 | Crossroads | CR-S27-04 | Pole replacement | P2 same day | 2026-03-14 | 2026-03-15 | 2026-03-15 | Contract line | CT-01 | 3088.34 | Completed | No
WO-26-002565 | 1 | Crossroads | CR-S14-05 | Service order - field | P2 same day | 2026-03-14 | 2026-03-15 | 2026-03-15 | Meter technician |  | 4.9 | Completed | No
WO-26-002566 | 10.9 | Crossroads | CR-S21-03 | Transformer replacement | P2 same day | 2026-03-14 | 2026-03-14 | 2026-03-14 | Internal line |  | 7856.97 | Completed | No
WO-26-002567 | 4.5 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-03-14 | 2026-03-14 | 2026-03-14 | Troubleman |  | 155.97 | Completed | No
WO-26-002568 | 5.6 | Crossroads | CR-S09-01 | Trouble - no power | P2 same day | 2026-03-14 | 2026-03-14 | 2026-03-14 | Internal line |  | 105.56 | Completed | No
WO-26-002569 | 2.6 | Crossroads | CR-S09-01 | Trouble - no power | P2 same day | 2026-03-14 | 2026-03-15 | 2026-03-15 | Internal line |  | 277.18 | Completed | No
WO-26-002570 | 3 | Crossroads | CR-S05-03 | Trouble - no power | P1 emergency | 2026-03-14 | 2026-03-14 | 2026-03-14 | Troubleman |  | 276.03 | Completed | No
WO-26-002571 |  | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-03-15 | 2026-03-15 |  | Troubleman |  |  | Cancelled | No
WO-26-002572 | 5.1 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-03-15 | 2026-03-16 | 2026-03-16 | Troubleman |  | 101.95 | Completed | No
WO-26-002573 | 3.9 | Bayou | BY-S03-02 | Trouble - no power | P2 same day | 2026-03-15 | 2026-03-16 | 2026-03-16 | Internal line |  | 313.93 | Completed | No
WO-26-002574 | 4.4 | Bayou | BY-S27-06 | Trouble - partial or voltage | P2 same day | 2026-03-15 | 2026-03-15 | 2026-03-15 | Internal line |  | 59.21 | Completed | No
WO-26-002575 | 7.6 | Crossroads | CR-S20-05 | Transformer replacement | P1 emergency | 2026-03-15 | 2026-03-15 | 2026-03-15 | Internal line |  | 8988.89 | Completed | No
WO-26-002576 | 2.2 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-03-15 | 2026-03-15 | 2026-03-15 | Troubleman |  | 302.36 | Completed | No
WO-26-002577 | 5.1 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-03-15 | 2026-03-15 | 2026-03-15 | Troubleman |  | 138.45 | Completed | No
WO-26-002578 | 4.9 | Crossroads | CR-S06-02 | Trouble - no power | P2 same day | 2026-03-15 | 2026-03-16 | 2026-03-16 | Troubleman |  | 53.72 | Completed | No
WO-26-002579 | 4.5 | Crossroads | CR-S12-02 | Trouble - no power | P2 same day | 2026-03-15 | 2026-03-16 | 2026-03-16 | Internal line |  | 211.18 | Completed | No
WO-26-002580 | 5.4 | Crossroads | CR-S14-01 | Trouble - no power | P2 same day | 2026-03-15 | 2026-03-16 | 2026-03-16 | Troubleman |  | 272.97 | Completed | No
WO-26-002581 | 5 | Crossroads | CR-S02-01 | Trouble - no power | P1 emergency | 2026-03-15 | 2026-03-15 | 2026-03-15 | Troubleman |  | 77.22 | Completed | No
WO-26-002582 | 4.9 | Crossroads | CR-S13-02 | Trouble - no power | P1 emergency | 2026-03-15 | 2026-03-15 | 2026-03-15 | Troubleman |  | 159.76 | Completed | No
WO-26-002583 | 5.2 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-03-15 | 2026-03-15 | 2026-03-15 | Troubleman |  | 193.5 | Completed | No
WO-26-002584 | 3.8 | Crossroads | CR-S04-06 | Trouble - partial or voltage | P2 same day | 2026-03-15 | 2026-03-15 | 2026-03-15 | Troubleman |  | 79.01 | Completed | No
WO-26-002585 | 3.9 | Bayou | BY-S04-02 | Corrective maintenance | P4 planned | 2026-03-16 | 2026-05-11 | 2026-05-11 | Underground crew |  | 2185.22 | Completed | No
WO-26-002586 | 8.6 | Bayou | BY-S07-06 | Corrective maintenance | P3 within 10 days | 2026-03-16 | 2026-03-25 | 2026-03-25 | Internal line |  | 620.57 | Completed | No
WO-26-002587 | 1.1 | Bayou | BY-S18-04 | Meter exchange | P3 within 10 days | 2026-03-16 | 2026-03-19 | 2026-03-19 | Meter technician |  | 102.22 | Completed | No
WO-26-002588 | 1.3 | Bayou | BY-S18-06 | Meter exchange | P4 planned | 2026-03-16 | 2026-04-19 | 2026-04-23 | Meter technician |  | 80.42 | Completed | No
WO-26-002589 | 0.9 | Bayou | BY-S23-05 | Meter exchange | P4 planned | 2026-03-16 | 2026-03-24 | 2026-03-28 | Meter technician |  | 129.96 | Completed | No
WO-26-002590 | 7.4 | Bayou | BY-S18-01 | New service - small | P3 within 10 days | 2026-03-16 | 2026-03-26 | 2026-03-26 | Contract line | CT-04 | 932.72 | Completed | No
WO-26-002591 | 4.3 | Bayou | BY-S29-03 | Preventive maintenance | P4 planned | 2026-03-16 | 2026-05-02 | 2026-05-04 | Internal line |  | 391.33 | Completed | No
WO-26-002592 | 3.6 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-03-16 | 2026-04-28 | 2026-04-29 | Underground crew |  | 582.08 | Completed | No
WO-26-002593 | 2.4 | Bayou | BY-S22-01 | Preventive maintenance | P4 planned | 2026-03-16 | 2026-05-01 | 2026-05-03 | Internal line |  | 103.92 | Completed | No
WO-26-002594 | 1.4 | Bayou | BY-S05-01 | Service order - field | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Meter technician |  | 30.63 | Completed | No
WO-26-002595 | 0.6 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Meter technician |  | 15.76 | Completed | No
WO-26-002596 |  | Bayou | BY-S20-01 | Service order - field | P3 within 10 days | 2026-03-16 | 2026-03-18 |  | Meter technician |  |  | Cancelled | No
WO-26-002597 | 1.7 | Bayou | BY-S23-04 | Service order - field | P3 within 10 days | 2026-03-16 | 2026-03-18 | 2026-03-18 | Meter technician |  | 20.66 | Completed | No
WO-26-002598 | 1.4 | Bayou | BY-S18-06 | Service order - field | P3 within 10 days | 2026-03-16 | 2026-03-18 | 2026-03-19 | Meter technician |  | 27.58 | Completed | No
WO-26-002599 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-16 | 2026-03-23 | 2026-03-27 | Contract line | CT-04 | 150.77 | Completed | No
WO-26-002600 | 11.2 | Bayou | BY-S18-04 | Transformer replacement | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Internal line |  | 10104.55 | Completed | No
WO-26-002601 | 11.3 | Bayou | BY-S11-02 | Transformer replacement | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Contract line | CT-03 | 4590.26 | Completed | No
WO-26-002602 | 9.4 | Bayou | BY-S15-06 | Transformer replacement | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Contract line | CT-04 | 8571.12 | Completed | No
WO-26-002603 | 3.8 | Bayou | BY-S01-01 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 179.13 | Completed | No
WO-26-002604 | 5.4 | Bayou | BY-S07-06 | Trouble - no power | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 225.84 | Completed | No
WO-26-002605 | 4.4 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Internal line |  | 101.14 | Completed | No
WO-26-002606 | 4.3 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 176.6 | Completed | No
WO-26-002607 | 4.8 | Bayou | BY-S13-02 | Trouble - no power | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 211.15 | Completed | No
WO-26-002608 | 4 | Bayou | BY-S18-01 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 87.68 | Completed | No
WO-26-002609 | 4.8 | Bayou | BY-S21-03 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 309.51 | Completed | No
WO-26-002610 | 4.4 | Bayou | BY-S21-03 | Trouble - partial or voltage | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 8.53 | Completed | No
WO-26-002611 | 3.6 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 242.17 | Completed | No
WO-26-002612 | 4.8 | Bayou | BY-S18-01 | Trouble - partial or voltage | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 173.33 | Completed | No
WO-26-002613 | 3 | Bayou | BY-S06-02 | Trouble - partial or voltage | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 219.97 | Completed | No
WO-26-002614 | 9.6 | Crossroads | CR-S25-06 | Corrective maintenance | P3 within 10 days | 2026-03-16 | 2026-03-22 | 2026-03-26 | Internal line |  | 2232.88 | Completed | No
WO-26-002615 | 0.8 | Crossroads | CR-S16-01 | Meter exchange | P3 within 10 days | 2026-03-16 | 2026-03-17 | 2026-03-17 | Meter technician |  | 147.76 | Completed | No
WO-26-002616 | 0.7 | Crossroads | CR-S13-02 | Meter exchange | P3 within 10 days | 2026-03-16 | 2026-03-23 | 2026-03-31 | Meter technician |  | 127.35 | Completed | No
WO-26-002617 | 5.5 | Crossroads | CR-S18-06 | New service - small | P4 planned | 2026-03-16 | 2026-03-31 | 2026-03-31 | Internal line |  | 484.67 | Completed | No
WO-26-002618 | 3.4 | Crossroads | CR-S07-01 | Preventive maintenance | P4 planned | 2026-03-16 | 2026-05-12 | 2026-05-16 | Internal line |  | 219.91 | Completed | No
WO-26-002619 | 5.2 | Crossroads | CR-S13-05 | Preventive maintenance | P4 planned | 2026-03-16 | 2026-04-24 | 2026-04-26 | Internal line |  | 128.46 | Completed | No
WO-26-002620 | 1.5 | Crossroads | CR-S14-02 | Service order - field | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Meter technician |  | 11.22 | Completed | No
WO-26-002621 | 1.9 | Crossroads | CR-S32-01 | Service order - field | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Meter technician |  | 29.01 | Completed | No
WO-26-002622 | 1.7 | Crossroads | CR-S29-01 | Service order - field | P3 within 10 days | 2026-03-16 | 2026-03-21 | 2026-03-21 | Meter technician |  | 30.71 | Completed | No
WO-26-002623 | 1.5 | Crossroads | CR-S13-03 | Service order - field | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Meter technician |  | 37.86 | Completed | No
WO-26-002624 | 1.4 | Crossroads | CR-S09-03 | Service order - field | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Meter technician |  | 19.35 | Completed | No
WO-26-002625 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-16 | 2026-03-26 | 2026-03-30 | Contract line | CT-01 | 49.68 | Completed | No
WO-26-002626 | 2.7 | Crossroads |  | Streetlight | P4 planned | 2026-03-16 | 2026-04-17 | 2026-04-17 | Contract line | CT-01 | 135.74 | Completed | No
WO-26-002627 | 13.8 | Crossroads | CR-S15-01 | Transformer replacement | P3 within 10 days | 2026-03-16 | 2026-03-26 | 2026-03-26 | Contract line | CT-01 | 6385.07 | Completed | No
WO-26-002628 | 4.2 | Crossroads | CR-S32-04 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 112.49 | Completed | No
WO-26-002629 | 5.6 | Crossroads | CR-S13-04 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 175.18 | Completed | No
WO-26-002630 | 3.5 | Crossroads | CR-S25-05 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-16 | 2026-03-16 | Troubleman |  | 97.28 | Completed | No
WO-26-002631 | 2.6 | Crossroads | CR-S26-02 | Trouble - no power | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 196.12 | Completed | No
WO-26-002632 | 5.9 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-03-16 | 2026-03-16 | 2026-03-16 | Internal line |  | 164.13 | Completed | No
WO-26-002633 | 4.4 | Crossroads | CR-S20-04 | Trouble - partial or voltage | P3 within 10 days | 2026-03-16 | 2026-03-26 | 2026-03-27 | Troubleman |  | 108.1 | Completed | No
WO-26-002634 | 4.5 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-03-16 | 2026-03-17 | 2026-03-17 | Troubleman |  | 29.5 | Completed | No
WO-26-002635 | 9 | Bayou | BY-S22-04 | Corrective maintenance | P3 within 10 days | 2026-03-17 | 2026-03-25 | 2026-03-25 | Contract line | CT-03 | 867.35 | Completed | No
WO-26-002636 | 4.6 | Bayou | BY-S13-05 | Corrective maintenance | P2 same day | 2026-03-17 | 2026-03-18 | 2026-03-18 | Internal line |  | 1833.04 | Completed | No
WO-26-002637 | 4.1 | Bayou | BY-S16-05 | Corrective maintenance | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Underground crew |  | 418.03 | Completed | No
WO-26-002638 | 4.8 | Bayou | BY-S11-01 | Corrective maintenance | P3 within 10 days | 2026-03-17 | 2026-03-20 | 2026-03-20 | Contract line | CT-04 | 2232.81 | Completed | No
WO-26-002639 | 3.6 | Bayou | BY-S29-03 | Corrective maintenance | P3 within 10 days | 2026-03-17 | 2026-03-23 | 2026-03-24 | Contract line | CT-04 | 1738.39 | Completed | No
WO-26-002640 | 0.9 | Bayou | BY-S04-02 | Meter exchange | P4 planned | 2026-03-17 | 2026-04-29 | 2026-04-29 | Meter technician |  | 64.99 | Completed | No
WO-26-002641 | 1.1 | Bayou | BY-S07-01 | Meter exchange | P3 within 10 days | 2026-03-17 | 2026-03-25 | 2026-03-25 | Meter technician |  | 125.73 | Completed | No
WO-26-002642 | 6 | Bayou | BY-S15-01 | Preventive maintenance | P4 planned | 2026-03-17 | 2026-04-05 | 2026-04-05 | Internal line |  | 84.85 | Completed | No
WO-26-002643 | 3.9 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-03-17 | 2026-05-12 | 2026-05-14 | Underground crew |  | 401.76 | Completed | No
WO-26-002644 | 0.9 | Bayou | BY-S10-02 | Service order - field | P3 within 10 days | 2026-03-17 | 2026-03-19 | 2026-03-19 | Meter technician |  | 13.12 | Completed | No
WO-26-002645 | 2 | Bayou | BY-S07-03 | Service order - field | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Meter technician |  | 24.21 | Completed | No
WO-26-002646 | 1.9 | Bayou | BY-S10-01 | Service order - field | P3 within 10 days | 2026-03-17 | 2026-03-19 | 2026-03-21 | Meter technician |  | 34.17 | Completed | No
WO-26-002647 | 7 | Bayou | BY-S20-03 | Transformer replacement | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Contract line | CT-03 | 4697.55 | Completed | No
WO-26-002648 | 7.1 | Bayou | BY-S26-01 | Transformer replacement | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Contract line | CT-04 | 10204.03 | Completed | No
WO-26-002649 | 10.8 | Bayou | BY-S15-04 | Transformer replacement | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Internal line |  | 9531.19 | Completed | No
WO-26-002650 | 2.5 | Bayou | BY-S17-01 | Trouble - no power | P2 same day | 2026-03-17 | 2026-03-18 | 2026-03-18 | Troubleman |  | 252.58 | Completed | No
WO-26-002651 | 3.9 | Bayou | BY-S07-02 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Internal line |  | 194.66 | Completed | No
WO-26-002652 |  | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 |  | Troubleman |  |  | Cancelled | No
WO-26-002653 | 3.8 | Bayou | BY-S06-02 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Troubleman |  | 140.83 | Completed | No
WO-26-002654 | 5.4 | Bayou | BY-S14-02 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Internal line |  | 137.85 | Completed | No
WO-26-002655 | 5.1 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Troubleman |  | 2.82 | Completed | No
WO-26-002656 | 2.6 | Bayou | BY-S16-04 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Troubleman |  | 110.76 | Completed | No
WO-26-002657 | 3 | Bayou | BY-S03-01 | Trouble - partial or voltage | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Internal line |  | 22.24 | Completed | No
WO-26-002658 | 4.9 | Bayou | BY-S02-02 | Trouble - partial or voltage | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Internal line |  | 49.85 | Completed | No
WO-26-002659 | 4.6 | Bayou | BY-S13-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-17 | 2026-03-24 | 2026-03-24 | Troubleman |  | 145.9 | Completed | No
WO-26-002660 | 6.1 | Crossroads | CR-S07-01 | Corrective maintenance | P3 within 10 days | 2026-03-17 | 2026-03-27 | 2026-03-31 | Internal line |  | 1969.36 | Completed | No
WO-26-002661 | 11.5 | Crossroads | CR-S08-04 | Corrective maintenance | P4 planned | 2026-03-17 | 2026-04-22 | 2026-04-22 | Internal line |  | 553.92 | Completed | No
WO-26-002662 | 10.5 | Crossroads | CR-S27-04 | Corrective maintenance | P3 within 10 days | 2026-03-17 | 2026-03-26 | 2026-03-28 | Underground crew |  | 100.09 | Completed | No
WO-26-002663 | 9.8 | Crossroads | CR-S22-01 | Corrective maintenance | P3 within 10 days | 2026-03-17 | 2026-03-23 | 2026-03-23 | Underground crew |  | 517.16 | Completed | No
WO-26-002664 | 5.5 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-03-17 | 2026-03-18 | 2026-03-18 | Contract line | CT-02 | 850.21 | Completed | No
WO-26-002665 | 1.1 | Crossroads | CR-S29-01 | Meter exchange | P4 planned | 2026-03-17 | 2026-05-11 | 2026-05-11 | Meter technician |  | 166.33 | Completed | No
WO-26-002666 | 1.3 | Crossroads | CR-S18-01 | Meter exchange | P3 within 10 days | 2026-03-17 | 2026-03-21 | 2026-03-21 | Meter technician |  | 67.18 | Completed | No
WO-26-002667 | 1 | Crossroads | CR-S11-02 | Meter exchange | P3 within 10 days | 2026-03-17 | 2026-03-22 | 2026-03-22 | Meter technician |  | 92.16 | Completed | No
WO-26-002668 | 1.1 | Crossroads | CR-S07-07 | Meter exchange | P3 within 10 days | 2026-03-17 | 2026-03-19 | 2026-03-21 | Meter technician |  | 134.46 | Completed | No
WO-26-002669 | 6.5 | Crossroads | CR-S17-03 | New service - small | P4 planned | 2026-03-17 | 2026-05-12 | 2026-05-16 | Contract line | CT-02 | 1712.35 | Completed | No
WO-26-002670 | 6.5 | Crossroads | CR-S24-04 | Preventive maintenance | P4 planned | 2026-03-17 | 2026-04-01 | 2026-04-01 | Internal line |  | 69.9 | Completed | No
WO-26-002671 | 6.1 | Crossroads | CR-S27-04 | Preventive maintenance | P4 planned | 2026-03-17 | 2026-04-24 | 2026-04-24 | Underground crew |  | 279.87 | Completed | No
WO-26-002672 | 4.2 | Crossroads | CR-S26-02 | Preventive maintenance | P4 planned | 2026-03-17 | 2026-05-16 | 2026-05-16 | Underground crew |  | 380.41 | Completed | No
WO-26-002673 | 2 | Crossroads | CR-S26-05 | Service order - field | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Meter technician |  | 19.97 | Completed | No
WO-26-002674 | 1.7 | Crossroads | CR-S32-04 | Service order - field | P3 within 10 days | 2026-03-17 | 2026-03-18 | 2026-03-18 | Meter technician |  | 39.84 | Completed | No
WO-26-002675 | 1.6 | Crossroads | CR-S25-03 | Service order - field | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Meter technician |  | 5.44 | Completed | No
WO-26-002676 | 1.5 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-03-17 | 2026-03-18 | 2026-03-18 | Meter technician |  | 13.39 | Completed | No
WO-26-002677 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-17 | 2026-03-20 | 2026-03-20 | Contract line | CT-02 | 40.32 | Completed | No
WO-26-002678 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-17 | 2026-03-21 | 2026-03-21 | Contract line | CT-01 | 264.07 | Completed | No
WO-26-002679 | 3 | Crossroads |  | Streetlight | P4 planned | 2026-03-17 | 2026-03-31 | 2026-03-31 | Internal line |  | 370.07 | Completed | No
WO-26-002680 | 6.9 | Crossroads | CR-S30-04 | Transformer replacement | P3 within 10 days | 2026-03-17 | 2026-03-19 | 2026-03-20 | Internal line |  | 4164.52 | Completed | No
WO-26-002681 | 4.2 | Crossroads | CR-S05-04 | Trouble - no power | P2 same day | 2026-03-17 | 2026-03-17 | 2026-03-17 | Troubleman |  | 64.38 | Completed | No
WO-26-002682 | 6 | Crossroads | CR-S04-04 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Troubleman |  | 99.78 | Completed | No
WO-26-002683 | 5.4 | Crossroads | CR-S18-05 | Trouble - no power | P1 emergency | 2026-03-17 | 2026-03-17 | 2026-03-17 | Troubleman |  | 343.72 | Completed | No
WO-26-002684 | 4.2 | Crossroads | CR-S27-04 | Trouble - partial or voltage | P3 within 10 days | 2026-03-17 | 2026-03-27 | 2026-03-27 | Troubleman |  | 58.84 | Completed | No
WO-26-002685 | 2.6 | Crossroads | CR-S14-02 | Trouble - partial or voltage | P2 same day | 2026-03-17 | 2026-03-18 | 2026-03-18 | Internal line |  | 177.15 | Completed | No
WO-26-002686 | 8.5 | Bayou | BY-S29-02 | Corrective maintenance | P3 within 10 days | 2026-03-18 | 2026-03-25 | 2026-03-26 | Underground crew |  | 83.71 | Completed | No
WO-26-002687 | 11.5 | Bayou | BY-S17-02 | Corrective maintenance | P3 within 10 days | 2026-03-18 | 2026-03-28 | 2026-03-28 | Contract line | CT-04 | 2230.61 | Completed | No
WO-26-002688 | 1.1 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-03-18 | 2026-03-21 | 2026-03-21 | Meter technician |  | 83.33 | Completed | No
WO-26-002689 | 1.1 | Bayou | BY-S24-04 | Meter exchange | P4 planned | 2026-03-18 | 2026-04-07 | 2026-04-08 | Meter technician |  | 151.84 | Completed | No
WO-26-002690 | 14.4 | Bayou | BY-S18-04 | New service - small | P4 planned | 2026-03-18 | 2026-05-16 | 2026-05-17 | Contract line | CT-03 | 2437.62 | Completed | No
WO-26-002691 | 21.5 | Bayou | BY-S07-02 | Pole replacement | P4 planned | 2026-03-18 | 2026-04-17 | 2026-04-17 | Contract line | CT-03 | 2143.16 | Completed | No
WO-26-002692 | 1 | Bayou | BY-S01-01 | Service order - field | P2 same day | 2026-03-18 | 2026-03-19 | 2026-03-19 | Meter technician |  | 34.29 | Completed | No
WO-26-002693 | 0.8 | Bayou | BY-S21-03 | Service order - field | P3 within 10 days | 2026-03-18 | 2026-03-23 | 2026-03-23 | Meter technician |  | 19.73 | Completed | No
WO-26-002694 | 0.8 | Bayou | BY-S14-02 | Service order - field | P3 within 10 days | 2026-03-18 | 2026-03-22 | 2026-03-22 | Meter technician |  | 17.47 | Completed | No
WO-26-002695 | 1.4 | Bayou | BY-S09-03 | Service order - field | P3 within 10 days | 2026-03-18 | 2026-03-23 | 2026-03-23 | Meter technician |  | 7.1 | Completed | No
WO-26-002696 | 1.8 | Bayou | BY-S04-03 | Service order - field | P3 within 10 days | 2026-03-18 | 2026-03-24 | 2026-03-24 | Meter technician |  | 2.08 | Completed | No
WO-26-002697 | 1 | Bayou | BY-S04-01 | Service order - field | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Meter technician |  | 11.23 | Completed | No
WO-26-002698 | 1.2 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-03-18 | 2026-03-21 | 2026-03-22 | Meter technician |  | 9.02 | Completed | No
WO-26-002699 | 2.6 | Bayou |  | Streetlight | P4 planned | 2026-03-18 | 2026-04-28 | 2026-04-28 | Contract line | CT-03 | 417.92 | Completed | No
WO-26-002700 |  | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-03-18 | 2026-03-18 |  | Troubleman |  |  | Cancelled | No
WO-26-002701 | 5 | Bayou | BY-S06-03 | Trouble - no power | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Troubleman |  | 217.14 | Completed | No
WO-26-002702 |  | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-03-18 | 2026-03-18 |  | Troubleman |  |  | Cancelled | No
WO-26-002703 | 3.7 | Bayou | BY-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-18 | 2026-03-22 | 2026-03-22 | Troubleman |  | 194.36 | Completed | No
WO-26-002704 | 2.3 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Internal line |  | 206.52 | Completed | No
WO-26-002705 | 7.6 | Crossroads | CR-S23-03 | Corrective maintenance | P3 within 10 days | 2026-03-18 | 2026-03-25 | 2026-03-29 | Internal line |  | 1195.25 | Completed | No
WO-26-002706 | 7.2 | Crossroads | CR-S23-03 | Corrective maintenance | P3 within 10 days | 2026-03-18 | 2026-03-24 | 2026-03-25 | Underground crew |  | 520.02 | Completed | No
WO-26-002707 | 3.3 | Crossroads | CR-S16-01 | Corrective maintenance | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Underground crew |  | 641.27 | Completed | No
WO-26-002708 | 9.5 | Crossroads | CR-S32-01 | Corrective maintenance | P4 planned | 2026-03-18 | 2026-04-15 | 2026-04-15 | Contract line | CT-01 | 1507.33 | Completed | No
WO-26-002709 | 6.8 | Crossroads | CR-S25-05 | Corrective maintenance | P3 within 10 days | 2026-03-18 | 2026-03-20 | 2026-03-21 | Internal line |  | 620.73 | Completed | No
WO-26-002710 | 6.4 | Crossroads | CR-S05-02 | Corrective maintenance | P4 planned | 2026-03-18 | 2026-05-17 | 2026-05-17 | Underground crew |  | 109.36 | Completed | No
WO-26-002711 | 4.7 | Crossroads | CR-S30-05 | Corrective maintenance | P4 planned | 2026-03-18 | 2026-05-08 | 2026-05-08 | Internal line |  | 1268.12 | Completed | No
WO-26-002712 | 0.9 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-03-18 | 2026-03-26 | 2026-03-27 | Meter technician |  | 66.85 | Completed | No
WO-26-002713 | 0.6 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-03-18 | 2026-03-27 | 2026-03-31 | Meter technician |  | 102.66 | Completed | No
WO-26-002714 | 0.8 | Crossroads | CR-S16-04 | Meter exchange | P3 within 10 days | 2026-03-18 | 2026-03-22 | 2026-03-26 | Meter technician |  | 79.8 | Completed | No
WO-26-002715 | 1.2 | Crossroads | CR-S24-02 | Meter exchange | P4 planned | 2026-03-18 | 2026-04-01 | 2026-04-01 | Meter technician |  | 72.58 | Completed | No
WO-26-002716 | 12.8 | Crossroads | CR-S24-02 | Pole replacement | P2 same day | 2026-03-18 | 2026-03-19 | 2026-03-19 | Contract line | CT-02 | 2420.09 | Completed | No
WO-26-002717 | 3.4 | Crossroads | CR-S05-03 | Preventive maintenance | P4 planned | 2026-03-18 | 2026-05-16 | 2026-05-20 | Internal line |  | 557.5 | Completed | No
WO-26-002718 | 7.5 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-03-18 | 2026-04-18 | 2026-04-19 | Internal line |  | 363.32 | Completed | No
WO-26-002719 | 2.1 | Crossroads | CR-S20-03 | Preventive maintenance | P4 planned | 2026-03-18 | 2026-05-04 | 2026-05-04 | Internal line |  | 159.98 | Completed | No
WO-26-002720 | 1.6 | Crossroads | CR-S20-01 | Service order - field | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Meter technician |  | 7.51 | Completed | No
WO-26-002721 | 1 | Crossroads | CR-S25-03 | Service order - field | P3 within 10 days | 2026-03-18 | 2026-03-26 | 2026-03-26 | Meter technician |  | 32.87 | Completed | No
WO-26-002722 | 1.3 | Crossroads | CR-S18-05 | Service order - field | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Meter technician |  | 31.32 | Completed | No
WO-26-002723 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-18 | 2026-03-25 | 2026-03-29 | Contract line | CT-01 | 320.27 | Completed | No
WO-26-002724 | 3.2 | Crossroads | CR-S32-01 | Trouble - no power | P1 emergency | 2026-03-18 | 2026-03-18 | 2026-03-18 | Troubleman |  | 136.51 | Completed | No
WO-26-002725 | 4.4 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-03-18 | 2026-03-18 | 2026-03-18 | Troubleman |  | 242.86 | Completed | No
WO-26-002726 | 2.3 | Crossroads | CR-S06-03 | Trouble - no power | P2 same day | 2026-03-18 | 2026-03-19 | 2026-03-19 | Troubleman |  | 158.97 | Completed | No
WO-26-002727 | 5 | Crossroads | CR-S26-02 | Trouble - no power | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Troubleman |  | 85.46 | Completed | No
WO-26-002728 | 2.7 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-03-18 | 2026-03-18 | 2026-03-18 | Troubleman |  | 220.35 | Completed | No
WO-26-002729 |  | Bayou | BY-S14-02 | Corrective maintenance | P3 within 10 days | 2026-03-19 | 2026-03-24 |  | Internal line |  |  | Cancelled | No
WO-26-002730 | 3.9 | Bayou | BY-S27-05 | Corrective maintenance | P4 planned | 2026-03-19 | 2026-04-22 | 2026-04-24 | Internal line |  | 221.44 | Completed | No
WO-26-002731 | 7.9 | Bayou | BY-S30-01 | Corrective maintenance | P4 planned | 2026-03-19 | 2026-04-16 | 2026-04-16 | Internal line |  | 2061.56 | Completed | No
WO-26-002732 | 11.8 | Bayou | BY-S28-02 | Corrective maintenance | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Contract line | CT-04 | 1746.8 | Completed | No
WO-26-002733 | 5.9 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-03-19 | 2026-03-26 | 2026-03-27 | Internal line |  | 1773.46 | Completed | No
WO-26-002734 | 0.7 | Bayou | BY-S09-03 | Meter exchange | P3 within 10 days | 2026-03-19 | 2026-03-21 | 2026-03-23 | Meter technician |  | 159.79 | Completed | No
WO-26-002735 |  | Bayou | BY-S15-03 | New service - small | P4 planned | 2026-03-19 | 2026-04-30 |  | Internal line |  |  | Cancelled | No
WO-26-002736 | 3.4 | Bayou | BY-S10-04 | Preventive maintenance | P4 planned | 2026-03-19 | 2026-04-07 | 2026-04-08 | Internal line |  | 200.33 | Completed | No
WO-26-002737 | 0.8 | Bayou | BY-S18-03 | Service order - field | P2 same day | 2026-03-19 | 2026-03-20 | 2026-03-20 | Meter technician |  | 15.55 | Completed | No
WO-26-002738 | 1.2 | Bayou | BY-S15-04 | Service order - field | P3 within 10 days | 2026-03-19 | 2026-03-28 | 2026-03-29 | Meter technician |  | 35.24 | Completed | No
WO-26-002739 | 0.9 | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Meter technician |  | 38.38 | Completed | No
WO-26-002740 | 1.9 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Meter technician |  | 28.23 | Completed | No
WO-26-002741 | 1.7 | Bayou | BY-S30-02 | Service order - field | P3 within 10 days | 2026-03-19 | 2026-03-23 | 2026-03-23 | Meter technician |  | 9.77 | Completed | No
WO-26-002742 | 1.2 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-03-19 | 2026-03-20 | 2026-03-20 | Meter technician |  | 4.89 | Completed | No
WO-26-002743 | 1 | Bayou | BY-S07-03 | Service order - field | P3 within 10 days | 2026-03-19 | 2026-03-24 | 2026-03-25 | Meter technician |  | 5.26 | Completed | No
WO-26-002744 | 1.4 | Bayou |  | Streetlight | P4 planned | 2026-03-19 | 2026-04-13 | 2026-04-14 | Internal line |  | 64.09 | Completed | No
WO-26-002745 | 1.5 | Bayou |  | Streetlight | P4 planned | 2026-03-19 | 2026-04-20 | 2026-04-20 | Internal line |  | 265.88 | Completed | No
WO-26-002746 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-19 | 2026-03-27 | 2026-03-29 | Internal line |  | 46.31 | Completed | No
WO-26-002747 | 7.3 | Bayou | BY-S05-01 | Transformer replacement | P3 within 10 days | 2026-03-19 | 2026-03-27 | 2026-03-27 | Internal line |  | 8799.54 | Completed | No
WO-26-002748 | 9 | Bayou | BY-S06-02 | Transformer replacement | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Contract line | CT-03 | 5888.84 | Completed | No
WO-26-002749 | 3.7 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-03-19 | 2026-03-19 | 2026-03-19 | Troubleman |  | 227.86 | Completed | No
WO-26-002750 | 2.6 | Bayou | BY-S17-03 | Trouble - no power | P1 emergency | 2026-03-19 | 2026-03-19 | 2026-03-19 | Internal line |  | 152.92 | Completed | No
WO-26-002751 | 4.8 | Bayou | BY-S16-01 | Trouble - partial or voltage | P2 same day | 2026-03-19 | 2026-03-20 | 2026-03-20 | Troubleman |  | 41.34 | Completed | No
WO-26-002752 | 3.6 | Bayou | BY-S29-01 | Trouble - partial or voltage | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Troubleman |  | 115.64 | Completed | No
WO-26-002753 | 3.4 | Bayou | BY-S28-01 | Trouble - partial or voltage | P2 same day | 2026-03-19 | 2026-03-20 | 2026-03-20 | Troubleman |  | 85.52 | Completed | No
WO-26-002754 | 5.7 | Crossroads | CR-S23-02 | Corrective maintenance | P3 within 10 days | 2026-03-19 | 2026-03-24 | 2026-03-25 | Internal line |  | 1254.18 | Completed | No
WO-26-002755 | 10.1 | Crossroads | CR-S20-01 | Corrective maintenance | P3 within 10 days | 2026-03-19 | 2026-03-26 | 2026-03-28 | Internal line |  | 1818.7 | Completed | No
WO-26-002756 | 0.7 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-03-19 | 2026-03-23 | 2026-03-25 | Meter technician |  | 88.36 | Completed | No
WO-26-002757 | 0.6 | Crossroads | CR-S29-03 | Meter exchange | P3 within 10 days | 2026-03-19 | 2026-03-26 | 2026-03-26 | Meter technician |  | 141.78 | Completed | No
WO-26-002758 | 21 | Crossroads | CR-S30-01 | Pole replacement | P3 within 10 days | 2026-03-19 | 2026-03-26 | 2026-03-30 | Contract line | CT-02 | 3285.11 | Completed | No
WO-26-002759 | 17.1 | Crossroads | CR-S18-04 | Pole replacement | P4 planned | 2026-03-19 | 2026-05-04 | 2026-05-05 | Contract line | CT-02 | 2806.03 | Completed | No
WO-26-002760 | 5.9 | Crossroads | CR-S24-01 | Preventive maintenance | P4 planned | 2026-03-19 | 2026-04-29 | 2026-04-29 | Underground crew |  | 232.32 | Completed | No
WO-26-002761 | 1.1 | Crossroads | CR-S25-03 | Service order - field | P3 within 10 days | 2026-03-19 | 2026-03-28 | 2026-03-28 | Meter technician |  | 18.32 | Completed | No
WO-26-002762 | 1.2 | Crossroads | CR-S28-01 | Service order - field | P3 within 10 days | 2026-03-19 | 2026-03-22 | 2026-03-22 | Meter technician |  | 33.52 | Completed | No
WO-26-002763 | 0.7 | Crossroads | CR-S07-03 | Service order - field | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Meter technician |  | 6.35 | Completed | No
WO-26-002764 | 2.6 | Crossroads |  | Streetlight | P4 planned | 2026-03-19 | 2026-04-19 | 2026-04-19 | Contract line | CT-02 | 228 | Completed | No
WO-26-002765 | 4.3 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-03-19 | 2026-03-19 | 2026-03-19 | Troubleman |  | 285.88 | Completed | No
WO-26-002766 | 3 | Crossroads | CR-S32-05 | Trouble - no power | P1 emergency | 2026-03-19 | 2026-03-19 | 2026-03-19 | Troubleman |  | 267.82 | Completed | No
WO-26-002767 | 4.6 | Crossroads | CR-S15-01 | Trouble - partial or voltage | P2 same day | 2026-03-19 | 2026-03-19 | 2026-03-19 | Troubleman |  | 233.72 | Completed | No
WO-26-002768 | 3.5 | Crossroads | CR-S16-06 | Trouble - partial or voltage | P3 within 10 days | 2026-03-19 | 2026-03-26 | 2026-03-26 | Troubleman |  | 112.49 | Completed | No
WO-26-002769 | 7.8 | Bayou | BY-S12-02 | Corrective maintenance | P3 within 10 days | 2026-03-20 | 2026-03-23 | 2026-03-23 | Underground crew |  | 1866.59 | Completed | No
WO-26-002770 | 8.6 | Bayou | BY-S21-04 | Corrective maintenance | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Internal line |  | 1216.72 | Completed | No
WO-26-002771 | 0.6 | Bayou | BY-S19-03 | Meter exchange | P3 within 10 days | 2026-03-20 | 2026-03-30 | 2026-03-30 | Meter technician |  | 125.76 | Completed | No
WO-26-002772 | 0.6 | Bayou | BY-S13-06 | Meter exchange | P4 planned | 2026-03-20 | 2026-04-15 | 2026-04-15 | Meter technician |  | 89.32 | Completed | No
WO-26-002773 | 1 | Bayou | BY-S29-01 | Meter exchange | P4 planned | 2026-03-20 | 2026-04-27 | 2026-04-28 | Meter technician |  | 62.04 | Completed | No
WO-26-002774 | 1 | Bayou | BY-S13-01 | Meter exchange | P3 within 10 days | 2026-03-20 | 2026-03-22 | 2026-03-22 | Meter technician |  | 145.51 | Completed | No
WO-26-002775 | 11.1 | Bayou | BY-S22-04 | New service - small | P4 planned | 2026-03-20 | 2026-04-30 | 2026-05-04 | Contract line | CT-03 | 1605.76 | Completed | No
WO-26-002776 | 13 | Bayou | BY-S21-03 | New service - small | P3 within 10 days | 2026-03-20 | 2026-03-22 | 2026-03-22 | Contract line | CT-04 | 2887.8 | Completed | No
WO-26-002777 | 7.1 | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-03-20 | 2026-04-16 | 2026-04-17 | Underground crew |  | 450.73 | Completed | No
WO-26-002778 | 7.3 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-03-20 | 2026-04-26 | 2026-04-28 | Internal line |  | 115.94 | Completed | No
WO-26-002779 | 1.5 | Bayou | BY-S07-01 | Service order - field | P3 within 10 days | 2026-03-20 | 2026-03-24 | 2026-03-24 | Meter technician |  | 22.43 | Completed | No
WO-26-002780 | 12 | Bayou | BY-S05-02 | Transformer replacement | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Contract line | CT-03 | 12116.81 | Completed | No
WO-26-002781 | 8.7 | Bayou | BY-S13-01 | Transformer replacement | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Internal line |  | 6099.39 | Completed | No
WO-26-002782 | 10.6 | Bayou | BY-S12-04 | Transformer replacement | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Internal line |  | 11186.66 | Completed | No
WO-26-002783 | 10.1 | Bayou | BY-S20-02 | Transformer replacement | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Contract line | CT-03 | 10747.69 | Completed | No
WO-26-002784 | 2.5 | Bayou | BY-S27-03 | Trouble - no power | P1 emergency | 2026-03-20 | 2026-03-20 | 2026-03-20 | Internal line |  | 59.34 | Completed | No
WO-26-002785 | 4.3 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-03-20 | 2026-03-20 | 2026-03-20 | Troubleman |  | 11.88 | Completed | No
WO-26-002786 | 3.9 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-03-20 | 2026-03-20 | 2026-03-20 | Troubleman |  | 147.83 | Completed | No
WO-26-002787 | 3.7 | Bayou | BY-S11-03 | Trouble - no power | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Troubleman |  | 44.26 | Completed | No
WO-26-002788 | 3.6 | Bayou | BY-S14-02 | Trouble - no power | P1 emergency | 2026-03-20 | 2026-03-20 | 2026-03-20 | Internal line |  | 12.94 | Completed | No
WO-26-002789 | 2.1 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Troubleman |  | 302.54 | Completed | No
WO-26-002790 | 5.4 | Bayou | BY-S25-04 | Trouble - no power | P1 emergency | 2026-03-20 | 2026-03-20 | 2026-03-20 | Internal line |  | 160.29 | Completed | No
WO-26-002791 | 2.8 | Bayou | BY-S22-04 | Trouble - partial or voltage | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Troubleman |  | 73.38 | Completed | No
WO-26-002792 | 6.3 | Crossroads | CR-S24-04 | Corrective maintenance | P3 within 10 days | 2026-03-20 | 2026-03-26 | 2026-03-26 | Internal line |  | 1201.29 | Completed | No
WO-26-002793 | 9.3 | Crossroads | CR-S30-07 | Corrective maintenance | P3 within 10 days | 2026-03-20 | 2026-03-23 | 2026-03-27 | Internal line |  | 801.74 | Completed | No
WO-26-002794 | 11 | Crossroads | CR-S05-01 | Corrective maintenance | P4 planned | 2026-03-20 | 2026-04-13 | 2026-04-13 | Internal line |  | 639.46 | Completed | No
WO-26-002795 | 3.5 | Crossroads | CR-S31-02 | Corrective maintenance | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Underground crew |  | 1155.74 | Completed | No
WO-26-002796 | 0.7 | Crossroads | CR-S15-03 | Meter exchange | P4 planned | 2026-03-20 | 2026-04-29 | 2026-04-29 | Meter technician |  | 154.47 | Completed | No
WO-26-002797 | 1 | Crossroads | CR-S27-01 | Meter exchange | P3 within 10 days | 2026-03-20 | 2026-03-24 | 2026-03-25 | Meter technician |  | 161.9 | Completed | No
WO-26-002798 | 15.6 | Crossroads | CR-S19-02 | New service - small | P3 within 10 days | 2026-03-20 | 2026-03-29 | 2026-03-29 | Contract line | CT-01 | 1525.81 | Completed | No
WO-26-002799 | 17.2 | Crossroads | CR-S09-04 | Pole replacement | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Contract line | CT-02 | 1424.09 | Completed | No
WO-26-002800 | 23.1 | Crossroads | CR-S01-04 | Pole replacement | P4 planned | 2026-03-20 | 2026-04-14 | 2026-04-14 | Contract line | CT-01 | 2547.95 | Completed | No
WO-26-002801 | 18 | Crossroads | CR-S02-03 | Pole replacement | P4 planned | 2026-03-20 | 2026-04-20 | 2026-04-20 | Internal line |  | 1758.38 | Completed | No
WO-26-002802 |  | Crossroads | CR-S05-02 | Pole replacement | P3 within 10 days | 2026-03-20 | 2026-03-28 |  | Contract line | CT-01 |  | Cancelled | No
WO-26-002803 | 20.5 | Crossroads | CR-S24-03 | Pole replacement | P3 within 10 days | 2026-03-20 | 2026-03-26 | 2026-03-26 | Contract line | CT-02 | 3412.95 | Completed | No
WO-26-002804 | 7.2 | Crossroads | CR-S02-03 | Preventive maintenance | P4 planned | 2026-03-20 | 2026-04-24 | 2026-04-28 | Underground crew |  | 468.44 | Completed | No
WO-26-002805 | 3.2 | Crossroads | CR-S12-03 | Preventive maintenance | P4 planned | 2026-03-20 | 2026-04-13 | 2026-04-13 | Underground crew |  | 45.9 | Completed | No
WO-26-002806 | 7.4 | Crossroads | CR-S11-01 | Preventive maintenance | P4 planned | 2026-03-20 | 2026-03-29 | 2026-03-31 | Internal line |  | 249.89 | Completed | No
WO-26-002807 | 0.7 | Crossroads | CR-S13-05 | Service order - field | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Meter technician |  | 10.96 | Completed | No
WO-26-002808 | 1.3 | Crossroads | CR-S07-02 | Service order - field | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Meter technician |  | 29.17 | Completed | No
WO-26-002809 | 1.8 | Crossroads | CR-S14-05 | Service order - field | P3 within 10 days | 2026-03-20 | 2026-03-21 | 2026-03-21 | Meter technician |  | 31.77 | Completed | No
WO-26-002810 | 1 | Crossroads | CR-S32-02 | Service order - field | P3 within 10 days | 2026-03-20 | 2026-03-29 | 2026-03-29 | Meter technician |  | 11.6 | Completed | No
WO-26-002811 | 1.9 | Crossroads | CR-S20-03 | Service order - field | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Meter technician |  | 2.66 | Completed | No
WO-26-002812 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-20 | 2026-03-25 | 2026-03-26 | Contract line | CT-02 | 55.32 | Completed | No
WO-26-002813 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-20 | 2026-03-30 | 2026-03-30 | Internal line |  | 78.08 | Completed | No
WO-26-002814 | 10.3 | Crossroads | CR-S24-01 | Transformer replacement | P1 emergency | 2026-03-20 | 2026-03-20 | 2026-03-20 | Internal line |  | 5380.01 | Completed | No
WO-26-002815 | 4.3 | Crossroads | CR-S01-03 | Trouble - no power | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Troubleman |  | 256.76 | Completed | No
WO-26-002816 | 3.8 | Crossroads | CR-S19-04 | Trouble - no power | P2 same day | 2026-03-20 | 2026-03-20 | 2026-03-20 | Troubleman |  | 212.34 | Completed | No
WO-26-002817 | 1.7 | Crossroads | CR-S29-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-20 | 2026-03-22 | 2026-03-23 | Troubleman |  | 238.98 | Completed | No
WO-26-002818 | 4.1 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P2 same day | 2026-03-20 | 2026-03-21 | 2026-03-21 | Troubleman |  | 64.51 | Completed | No
WO-26-002819 | 11.7 | Bayou | BY-S04-02 | Corrective maintenance | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Internal line |  | 1637.4 | Completed | No
WO-26-002820 | 11.7 | Bayou | BY-S25-01 | Corrective maintenance | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Contract line | CT-04 | 1543.65 | Completed | No
WO-26-002821 | 0.6 | Bayou | BY-S14-02 | Service order - field | P2 same day | 2026-03-21 | 2026-03-22 | 2026-03-22 | Meter technician |  | 22.08 | Completed | No
WO-26-002822 | 1.3 | Bayou | BY-S15-01 | Service order - field | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Meter technician |  | 16.59 | Completed | No
WO-26-002823 | 1 | Bayou | BY-S09-04 | Service order - field | P2 same day | 2026-03-21 | 2026-03-22 | 2026-03-22 | Meter technician |  | 18.81 | Completed | No
WO-26-002824 | 4.3 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-03-21 | 2026-03-21 | 2026-03-21 | Troubleman |  | 346.37 | Completed | No
WO-26-002825 | 4.6 | Bayou | BY-S14-02 | Trouble - no power | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Internal line |  | 24.75 | Completed | No
WO-26-002826 | 4.3 | Bayou | BY-S21-04 | Trouble - no power | P1 emergency | 2026-03-21 | 2026-03-21 | 2026-03-21 | Troubleman |  | 145.88 | Completed | No
WO-26-002827 | 5 | Bayou | BY-S03-01 | Trouble - no power | P1 emergency | 2026-03-21 | 2026-03-21 | 2026-03-21 | Troubleman |  | 227.77 | Completed | No
WO-26-002828 | 2.4 | Bayou | BY-S09-01 | Trouble - partial or voltage | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Troubleman |  | 59.34 | Completed | No
WO-26-002829 | 2.2 | Bayou | BY-S16-04 | Trouble - partial or voltage | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Internal line |  | 0.21 | Completed | No
WO-26-002830 | 1.9 | Crossroads | CR-S26-03 | Service order - field | P2 same day | 2026-03-21 | 2026-03-22 | 2026-03-22 | Meter technician |  | 4.19 | Completed | No
WO-26-002831 | 1.5 | Crossroads | CR-S18-04 | Service order - field | P2 same day | 2026-03-21 | 2026-03-22 | 2026-03-22 | Meter technician |  | 37.23 | Completed | No
WO-26-002832 | 10.3 | Crossroads | CR-S32-03 | Transformer replacement | P1 emergency | 2026-03-21 | 2026-03-21 | 2026-03-21 | Internal line |  | 5309.74 | Completed | No
WO-26-002833 | 7.1 | Crossroads | CR-S05-02 | Transformer replacement | P2 same day | 2026-03-21 | 2026-03-21 | 2026-03-21 | Internal line |  | 3337.92 | Completed | No
WO-26-002834 | 5.7 | Crossroads | CR-S20-03 | Trouble - no power | P1 emergency | 2026-03-21 | 2026-03-21 | 2026-03-21 | Troubleman |  | 329.75 | Completed | No
WO-26-002835 | 4.8 | Crossroads | CR-S02-05 | Trouble - no power | P2 same day | 2026-03-21 | 2026-03-22 | 2026-03-22 | Troubleman |  | 255.24 | Completed | No
WO-26-002836 | 11.2 | Bayou | BY-S26-02 | Corrective maintenance | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Underground crew |  | 265.87 | Completed | No
WO-26-002837 | 21.2 | Bayou | BY-S25-02 | Pole replacement | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Internal line |  | 2030.05 | Completed | No
WO-26-002838 | 1 | Bayou | BY-S15-06 | Service order - field | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Meter technician |  | 27.24 | Completed | No
WO-26-002839 | 9.3 | Bayou | BY-S26-01 | Transformer replacement | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Contract line | CT-04 | 4518.01 | Completed | No
WO-26-002840 | 6.5 | Bayou | BY-S24-01 | Transformer replacement | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Internal line |  | 11176.57 | Completed | No
WO-26-002841 | 3.3 | Bayou | BY-S06-03 | Trouble - no power | P2 same day | 2026-03-22 | 2026-03-22 | 2026-03-22 | Internal line |  | 136.4 | Completed | No
WO-26-002842 | 5.7 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-03-22 | 2026-03-22 | 2026-03-22 | Troubleman |  | 241.56 | Completed | No
WO-26-002843 | 4.6 | Bayou | BY-S18-03 | Trouble - no power | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Troubleman |  | 340.25 | Completed | No
WO-26-002844 | 3.7 | Bayou | BY-S25-03 | Trouble - no power | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Troubleman |  | 47.17 | Completed | No
WO-26-002845 | 3 | Bayou | BY-S24-05 | Trouble - no power | P1 emergency | 2026-03-22 | 2026-03-22 | 2026-03-22 | Troubleman |  | 140.64 | Completed | No
WO-26-002846 | 5.7 | Bayou | BY-S18-02 | Trouble - no power | P1 emergency | 2026-03-22 | 2026-03-22 | 2026-03-22 | Internal line |  | 221.31 | Completed | No
WO-26-002847 | 1.9 | Crossroads | CR-S01-01 | Service order - field | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Meter technician |  | 13.05 | Completed | No
WO-26-002848 | 2 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-03-22 | 2026-03-22 | 2026-03-22 | Meter technician |  | 3.86 | Completed | No
WO-26-002849 | 7.3 | Crossroads | CR-S20-04 | Transformer replacement | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Internal line |  | 9538.03 | Completed | No
WO-26-002850 | 10.7 | Crossroads | CR-S19-03 | Transformer replacement | P1 emergency | 2026-03-22 | 2026-03-22 | 2026-03-22 | Contract line | CT-01 | 4025.76 | Completed | No
WO-26-002851 | 3.9 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-03-22 | 2026-03-22 | 2026-03-22 | Troubleman |  | 45.98 | Completed | No
WO-26-002852 | 2.9 | Crossroads | CR-S32-01 | Trouble - no power | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Troubleman |  | 158.92 | Completed | No
WO-26-002853 | 3.8 | Crossroads | CR-S28-03 | Trouble - no power | P2 same day | 2026-03-22 | 2026-03-23 | 2026-03-23 | Troubleman |  | 242.74 | Completed | No
WO-26-002854 | 1.4 | Bayou | BY-S25-03 | Meter exchange | P4 planned | 2026-03-23 | 2026-05-13 | 2026-05-17 | Meter technician |  | 107.36 | Completed | No
WO-26-002855 | 1 | Bayou | BY-S12-01 | Meter exchange | P4 planned | 2026-03-23 | 2026-04-13 | 2026-04-17 | Meter technician |  | 129.92 | Completed | No
WO-26-002856 | 7 | Bayou | BY-S25-03 | New service - small | P4 planned | 2026-03-23 | 2026-04-02 | 2026-04-02 | Internal line |  | 1597.21 | Completed | No
WO-26-002857 | 11.7 | Bayou | BY-S17-04 | Pole replacement | P3 within 10 days | 2026-03-23 | 2026-03-31 | 2026-04-01 | Contract line | CT-04 | 3014.68 | Completed | No
WO-26-002858 | 3.1 | Bayou | BY-S24-01 | Preventive maintenance | P4 planned | 2026-03-23 | 2026-05-14 | 2026-05-14 | Internal line |  | 243.17 | Completed | No
WO-26-002859 | 4.5 | Bayou | BY-S13-03 | Preventive maintenance | P4 planned | 2026-03-23 | 2026-04-21 | 2026-04-23 | Underground crew |  | 7.99 | Completed | No
WO-26-002860 | 5.6 | Bayou | BY-S08-01 | Preventive maintenance | P4 planned | 2026-03-23 | 2026-05-20 | 2026-05-22 | Internal line |  | 230.78 | Completed | No
WO-26-002861 | 1.5 | Bayou | BY-S28-01 | Service order - field | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Meter technician |  | 33.14 | Completed | No
WO-26-002862 | 1.6 | Bayou | BY-S23-04 | Service order - field | P3 within 10 days | 2026-03-23 | 2026-04-01 | 2026-04-02 | Meter technician |  | 4.78 | Completed | No
WO-26-002863 | 1.4 | Bayou | BY-S21-01 | Service order - field | P3 within 10 days | 2026-03-23 | 2026-03-27 | 2026-03-27 | Meter technician |  | 30.55 | Completed | No
WO-26-002864 | 1.2 | Bayou | BY-S24-02 | Service order - field | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Meter technician |  | 29.78 | Completed | No
WO-26-002865 | 1.4 | Bayou | BY-S11-01 | Service order - field | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Meter technician |  | 36.71 | Completed | No
WO-26-002866 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-23 | 2026-03-24 | 2026-03-24 | Internal line |  | 131.87 | Completed | No
WO-26-002867 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-23 | 2026-03-28 | 2026-03-28 | Internal line |  | 272.51 | Completed | No
WO-26-002868 | 3.9 | Bayou | BY-S12-04 | Trouble - no power | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Troubleman |  | 294.37 | Completed | No
WO-26-002869 | 2.3 | Bayou | BY-S20-02 | Trouble - no power | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Troubleman |  | 68.9 | Completed | No
WO-26-002870 | 9.4 | Crossroads | CR-S21-03 | Corrective maintenance | P4 planned | 2026-03-23 | 2026-04-26 | 2026-04-27 | Internal line |  | 2370.02 | Completed | No
WO-26-002871 | 1 | Crossroads | CR-S28-04 | Meter exchange | P4 planned | 2026-03-23 | 2026-05-18 | 2026-05-19 | Meter technician |  | 103.34 | Completed | No
WO-26-002872 | 1.2 | Crossroads | CR-S29-01 | Meter exchange | P3 within 10 days | 2026-03-23 | 2026-03-27 | 2026-03-28 | Meter technician |  | 155.54 | Completed | No
WO-26-002873 | 1.3 | Crossroads | CR-S13-01 | Meter exchange | P3 within 10 days | 2026-03-23 | 2026-03-25 | 2026-03-27 | Meter technician |  | 161.52 | Completed | No
WO-26-002874 | 1.3 | Crossroads | CR-S16-01 | Meter exchange | P3 within 10 days | 2026-03-23 | 2026-03-29 | 2026-03-31 | Meter technician |  | 64.94 | Completed | No
WO-26-002875 | 1.1 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-03-23 | 2026-03-25 | 2026-03-29 | Meter technician |  | 139.38 | Completed | No
WO-26-002876 | 11.7 | Crossroads | CR-S10-02 | New service - small | P4 planned | 2026-03-23 | 2026-05-15 | 2026-05-15 | Underground crew |  | 465.36 | Completed | No
WO-26-002877 | 5.4 | Crossroads | CR-S29-02 | New service - small | P3 within 10 days | 2026-03-23 | 2026-03-30 | 2026-03-31 | Contract line | CT-01 | 464.72 | Completed | No
WO-26-002878 | 17.2 | Crossroads | CR-S17-01 | Pole replacement | P4 planned | 2026-03-23 | 2026-04-04 | 2026-04-04 | Contract line | CT-02 | 2735.17 | Completed | No
WO-26-002879 | 5.9 | Crossroads | CR-S27-02 | Preventive maintenance | P4 planned | 2026-03-23 | 2026-04-15 | 2026-04-23 | Underground crew |  | 413.04 | Completed | No
WO-26-002880 | 6.2 | Crossroads | CR-S26-03 | Preventive maintenance | P4 planned | 2026-03-23 | 2026-05-13 | 2026-05-17 | Internal line |  | 43.58 | Completed | No
WO-26-002881 | 2 | Crossroads | CR-S15-01 | Service order - field | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Meter technician |  | 31.93 | Completed | No
WO-26-002882 |  | Crossroads | CR-S13-02 | Trouble - no power | P1 emergency | 2026-03-23 | 2026-03-23 |  | Troubleman |  |  | Cancelled | No
WO-26-002883 |  | Crossroads | CR-S30-03 | Trouble - no power | P2 same day | 2026-03-23 | 2026-03-23 |  | Troubleman |  |  | Cancelled | No
WO-26-002884 | 3.7 | Crossroads | CR-S17-03 | Trouble - partial or voltage | P3 within 10 days | 2026-03-23 | 2026-03-27 | 2026-03-28 | Internal line |  | 195.71 | Completed | No
WO-26-002885 | 2 | Crossroads | CR-S20-05 | Trouble - partial or voltage | P2 same day | 2026-03-23 | 2026-03-24 | 2026-03-24 | Troubleman |  | 171.66 | Completed | No
WO-26-002886 | 9.9 | Bayou | BY-S26-05 | Corrective maintenance | P3 within 10 days | 2026-03-24 | 2026-03-28 | 2026-03-29 | Underground crew |  | 1934.19 | Completed | No
WO-26-002887 | 6.1 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-03-24 | 2026-04-01 | 2026-04-01 | Internal line |  | 885.19 | Completed | No
WO-26-002888 | 1.4 | Bayou | BY-S25-02 | Meter exchange | P3 within 10 days | 2026-03-24 | 2026-03-31 | 2026-03-31 | Meter technician |  | 129.07 | Completed | No
WO-26-002889 | 1 | Bayou | BY-S27-06 | Meter exchange | P4 planned | 2026-03-24 | 2026-04-03 | 2026-04-07 | Meter technician |  | 134.22 | Completed | No
WO-26-002890 | 14.8 | Bayou | BY-S20-02 | New service - small | P3 within 10 days | 2026-03-24 | 2026-03-28 | 2026-03-29 | Underground crew |  | 2539.65 | Completed | No
WO-26-002891 | 15.8 | Bayou | BY-S23-05 | New service - small | P4 planned | 2026-03-24 | 2026-05-18 | 2026-05-20 | Underground crew |  | 506.68 | Completed | No
WO-26-002892 | 21.1 | Bayou | BY-S01-01 | Pole replacement | P3 within 10 days | 2026-03-24 | 2026-03-31 | 2026-03-31 | Internal line |  | 2855.1 | Completed | No
WO-26-002893 | 15.6 | Bayou | BY-S24-03 | Pole replacement | P3 within 10 days | 2026-03-24 | 2026-04-01 | 2026-04-03 | Contract line | CT-04 | 3014.19 | Completed | No
WO-26-002894 | 2.7 | Bayou | BY-S16-03 | Preventive maintenance | P4 planned | 2026-03-24 | 2026-04-21 | 2026-04-21 | Underground crew |  | 79.76 | Completed | No
WO-26-002895 | 7.2 | Bayou | BY-S13-06 | Preventive maintenance | P4 planned | 2026-03-24 | 2026-04-11 | 2026-04-15 | Internal line |  | 528.36 | Completed | No
WO-26-002896 | 1.8 | Bayou |  | Streetlight | P4 planned | 2026-03-24 | 2026-04-15 | 2026-04-19 | Contract line | CT-04 | 75.85 | Completed | No
WO-26-002897 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-24 | 2026-03-26 | 2026-03-26 | Internal line |  | 308.16 | Completed | No
WO-26-002898 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-24 | 2026-04-03 | 2026-04-03 | Internal line |  | 383.42 | Completed | No
WO-26-002899 | 10.2 | Bayou | BY-S06-02 | Transformer replacement | P1 emergency | 2026-03-24 | 2026-03-24 | 2026-03-24 | Contract line | CT-03 | 3134.66 | Completed | No
WO-26-002900 | 11 | Bayou | BY-S12-02 | Transformer replacement | P3 within 10 days | 2026-03-24 | 2026-03-31 | 2026-04-02 | Internal line |  | 10936.31 | Completed | No
WO-26-002901 | 5.6 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-03-24 | 2026-03-24 | 2026-03-24 | Troubleman |  | 291.85 | Completed | No
WO-26-002902 | 2.3 | Bayou | BY-S25-04 | Trouble - no power | P1 emergency | 2026-03-24 | 2026-03-24 | 2026-03-24 | Troubleman |  | 98.13 | Completed | No
WO-26-002903 | 3.3 | Bayou | BY-S10-05 | Trouble - partial or voltage | P3 within 10 days | 2026-03-24 | 2026-03-27 | 2026-03-28 | Troubleman |  | 44.66 | Completed | No
WO-26-002904 | 5.4 | Crossroads | CR-S24-04 | Corrective maintenance | P3 within 10 days | 2026-03-24 | 2026-04-02 | 2026-04-03 | Internal line |  | 793.15 | Completed | No
WO-26-002905 | 8 | Crossroads | CR-S09-04 | Corrective maintenance | P3 within 10 days | 2026-03-24 | 2026-03-25 | 2026-03-25 | Contract line | CT-01 | 2040.07 | Completed | No
WO-26-002906 | 6 | Crossroads | CR-S01-03 | Corrective maintenance | P3 within 10 days | 2026-03-24 | 2026-03-26 | 2026-03-26 | Underground crew |  | 2193.76 | Completed | No
WO-26-002907 | 1.3 | Crossroads | CR-S09-05 | Meter exchange | P4 planned | 2026-03-24 | 2026-04-07 | 2026-04-08 | Meter technician |  | 80.2 | Completed | No
WO-26-002908 | 0.8 | Crossroads | CR-S29-02 | Meter exchange | P3 within 10 days | 2026-03-24 | 2026-03-31 | 2026-03-31 | Meter technician |  | 176.64 | Completed | No
WO-26-002909 | 1.1 | Crossroads | CR-S02-01 | Meter exchange | P3 within 10 days | 2026-03-24 | 2026-03-28 | 2026-03-28 | Meter technician |  | 91 | Completed | No
WO-26-002910 | 1.1 | Crossroads | CR-S28-04 | Meter exchange | P4 planned | 2026-03-24 | 2026-05-01 | 2026-05-03 | Meter technician |  | 112.15 | Completed | No
WO-26-002911 | 1.1 | Crossroads | CR-S25-03 | Meter exchange | P3 within 10 days | 2026-03-24 | 2026-04-01 | 2026-04-02 | Meter technician |  | 95.58 | Completed | No
WO-26-002912 | 1 | Crossroads | CR-S14-01 | Meter exchange | P4 planned | 2026-03-24 | 2026-04-05 | 2026-04-05 | Meter technician |  | 93.45 | Completed | No
WO-26-002913 | 15.8 | Crossroads | CR-S32-02 | New service - small | P4 planned | 2026-03-24 | 2026-04-27 | 2026-04-27 | Internal line |  | 3527.63 | Completed | No
WO-26-002914 | 22.8 | Crossroads | CR-S25-03 | Pole replacement | P3 within 10 days | 2026-03-24 | 2026-04-03 | 2026-04-03 | Contract line | CT-02 | 2746.6 | Completed | No
WO-26-002915 | 13.5 | Crossroads | CR-S16-02 | Pole replacement | P4 planned | 2026-03-24 | 2026-05-21 | 2026-05-23 | Contract line | CT-01 | 1767.1 | Completed | No
WO-26-002916 | 21.1 | Crossroads | CR-S23-02 | Pole replacement | P2 same day | 2026-03-24 | 2026-03-24 | 2026-03-24 | Contract line | CT-02 | 2909.01 | Completed | No
WO-26-002917 | 14.8 | Crossroads | CR-S07-03 | Pole replacement | P3 within 10 days | 2026-03-24 | 2026-03-29 | 2026-03-29 | Internal line |  | 2452.12 | Completed | No
WO-26-002918 | 2.5 | Crossroads | CR-S01-04 | Preventive maintenance | P4 planned | 2026-03-24 | 2026-05-04 | 2026-05-04 | Internal line |  | 182.19 | Completed | No
WO-26-002919 | 7.1 | Crossroads | CR-S02-03 | Preventive maintenance | P4 planned | 2026-03-24 | 2026-04-17 | 2026-04-18 | Internal line |  | 219.71 | Completed | No
WO-26-002920 | 6 | Crossroads | CR-S23-02 | Preventive maintenance | P4 planned | 2026-03-24 | 2026-05-23 | 2026-05-31 | Internal line |  | 304.53 | Completed | No
WO-26-002921 | 2.2 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-03-24 | 2026-04-27 | 2026-04-27 | Internal line |  | 533.63 | Completed | No
WO-26-002922 | 1.7 | Crossroads | CR-S16-04 | Service order - field | P2 same day | 2026-03-24 | 2026-03-24 | 2026-03-24 | Meter technician |  | 26.17 | Completed | No
WO-26-002923 | 1 | Crossroads | CR-S13-05 | Service order - field | P2 same day | 2026-03-24 | 2026-03-25 | 2026-03-25 | Meter technician |  | 5.79 | Completed | No
WO-26-002924 | 1.1 | Crossroads | CR-S29-02 | Service order - field | P3 within 10 days | 2026-03-24 | 2026-04-01 | 2026-04-03 | Meter technician |  | 22.76 | Completed | No
WO-26-002925 |  | Crossroads | CR-S21-01 | Transformer replacement | P2 same day | 2026-03-24 | 2026-03-24 |  | Internal line |  |  | Cancelled | No
WO-26-002926 | 3.8 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-03-24 | 2026-03-24 | 2026-03-24 | Troubleman |  | 112.66 | Completed | No
WO-26-002927 | 2.8 | Crossroads | CR-S15-02 | Trouble - no power | P1 emergency | 2026-03-24 | 2026-03-24 | 2026-03-24 | Internal line |  | 147.97 | Completed | No
WO-26-002928 | 4.8 | Crossroads | CR-S15-03 | Trouble - no power | P1 emergency | 2026-03-24 | 2026-03-24 | 2026-03-24 | Troubleman |  | 175.25 | Completed | No
WO-26-002929 | 1.7 | Crossroads | CR-S30-06 | Trouble - partial or voltage | P2 same day | 2026-03-24 | 2026-03-24 | 2026-03-24 | Troubleman |  | 178.49 | Completed | No
WO-26-002930 | 3.4 | Crossroads | CR-S04-01 | Trouble - partial or voltage | P2 same day | 2026-03-24 | 2026-03-24 | 2026-03-24 | Internal line |  | 99.44 | Completed | No
WO-26-002931 | 6.5 | Bayou | BY-S15-02 | Corrective maintenance | P3 within 10 days | 2026-03-25 | 2026-03-31 | 2026-03-31 | Contract line | CT-04 | 1289.83 | Completed | No
WO-26-002932 | 7.6 | Bayou | BY-S16-01 | Corrective maintenance | P4 planned | 2026-03-25 | 2026-04-19 | 2026-04-21 | Contract line | CT-03 | 1164.47 | Completed | No
WO-26-002933 | 7.5 | Bayou | BY-S21-01 | Corrective maintenance | P2 same day | 2026-03-25 | 2026-03-25 | 2026-03-25 | Internal line |  | 1091.15 | Completed | No
WO-26-002934 | 7.7 | Bayou | BY-S24-04 | Corrective maintenance | P2 same day | 2026-03-25 | 2026-03-25 | 2026-03-25 | Internal line |  | 1885.21 | Completed | No
WO-26-002935 | 0.9 | Bayou | BY-S18-02 | Meter exchange | P3 within 10 days | 2026-03-25 | 2026-04-04 | 2026-04-04 | Meter technician |  | 110.46 | Completed | No
WO-26-002936 | 1 | Bayou | BY-S07-03 | Meter exchange | P4 planned | 2026-03-25 | 2026-05-21 | 2026-05-25 | Meter technician |  | 123.03 | Completed | No
WO-26-002937 | 0.7 | Bayou | BY-S21-01 | Meter exchange | P4 planned | 2026-03-25 | 2026-05-15 | 2026-05-16 | Meter technician |  | 144.67 | Completed | No
WO-26-002938 | 0.8 | Bayou | BY-S06-01 | Meter exchange | P4 planned | 2026-03-25 | 2026-04-17 | 2026-04-17 | Meter technician |  | 131.38 | Completed | No
WO-26-002939 | 11 | Bayou | BY-S23-04 | New service - small | P4 planned | 2026-03-25 | 2026-05-18 | 2026-05-18 | Contract line | CT-03 | 1304.15 | Completed | No
WO-26-002940 | 15.6 | Bayou | BY-S12-03 | New service - small | P3 within 10 days | 2026-03-25 | 2026-03-29 | 2026-03-29 | Internal line |  | 2037.52 | Completed | No
WO-26-002941 |  | Bayou | BY-S18-03 | New service - small | P3 within 10 days | 2026-03-25 | 2026-03-26 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-002942 | 0.9 | Bayou | BY-S07-02 | Service order - field | P3 within 10 days | 2026-03-25 | 2026-03-31 | 2026-04-01 | Meter technician |  | 25.94 | Completed | No
WO-26-002943 | 1.8 | Bayou | BY-S21-03 | Service order - field | P3 within 10 days | 2026-03-25 | 2026-03-28 | 2026-03-29 | Meter technician |  | 8.23 | Completed | No
WO-26-002944 | 2.1 | Bayou |  | Streetlight | P4 planned | 2026-03-25 | 2026-05-12 | 2026-05-12 | Internal line |  | 149.46 | Completed | No
WO-26-002945 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-25 | 2026-03-28 | 2026-03-28 | Contract line | CT-04 | 388.77 | Completed | No
WO-26-002946 | 11.2 | Bayou | BY-S27-06 | Transformer replacement | P2 same day | 2026-03-25 | 2026-03-25 | 2026-03-25 | Internal line |  | 6102.76 | Completed | No
WO-26-002947 | 11.1 | Bayou | BY-S11-02 | Transformer replacement | P2 same day | 2026-03-25 | 2026-03-25 | 2026-03-25 | Internal line |  | 5173.22 | Completed | No
WO-26-002948 | 5.7 | Bayou | BY-S29-02 | Trouble - no power | P2 same day | 2026-03-25 | 2026-03-26 | 2026-03-26 | Troubleman |  | 59.17 | Completed | No
WO-26-002949 | 3.4 | Bayou | BY-S08-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-25 | 2026-03-27 | 2026-03-27 | Troubleman |  | 104.62 | Completed | No
WO-26-002950 | 7.2 | Crossroads | CR-S27-04 | Corrective maintenance | P3 within 10 days | 2026-03-25 | 2026-03-31 | 2026-03-31 | Internal line |  | 904.68 | Completed | No
WO-26-002951 | 6.2 | Crossroads | CR-S07-01 | Corrective maintenance | P4 planned | 2026-03-25 | 2026-05-23 | 2026-05-23 | Internal line |  | 933.25 | Completed | No
WO-26-002952 | 8.9 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-03-25 | 2026-03-27 | 2026-03-27 | Internal line |  | 1790.9 | Completed | No
WO-26-002953 | 7.3 | Crossroads | CR-S04-01 | Corrective maintenance | P3 within 10 days | 2026-03-25 | 2026-03-28 | 2026-03-28 | Internal line |  | 239.13 | Completed | No
WO-26-002954 | 6.5 | Crossroads | CR-S09-01 | Corrective maintenance | P3 within 10 days | 2026-03-25 | 2026-04-01 | 2026-04-01 | Internal line |  | 2374.3 | Completed | No
WO-26-002955 | 1.2 | Crossroads | CR-S25-02 | Meter exchange | P4 planned | 2026-03-25 | 2026-05-19 | 2026-05-19 | Meter technician |  | 104.39 | Completed | No
WO-26-002956 | 1 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-03-25 | 2026-04-02 | 2026-04-06 | Meter technician |  | 95.41 | Completed | No
WO-26-002957 |  | Crossroads | CR-S31-02 | Meter exchange | P4 planned | 2026-03-25 | 2026-04-18 |  | Meter technician |  |  | Cancelled | No
WO-26-002958 | 5.9 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-03-25 | 2026-05-14 | 2026-05-18 | Internal line |  | 475.12 | Completed | No
WO-26-002959 | 3.2 | Crossroads | CR-S25-06 | Preventive maintenance | P4 planned | 2026-03-25 | 2026-04-05 | 2026-04-06 | Internal line |  | 331.54 | Completed | No
WO-26-002960 | 1.2 | Crossroads | CR-S14-02 | Service order - field | P2 same day | 2026-03-25 | 2026-03-26 | 2026-03-26 | Meter technician |  | 7.15 | Completed | No
WO-26-002961 | 1.7 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-03-25 | 2026-04-04 | 2026-04-05 | Meter technician |  | 10.56 | Completed | No
WO-26-002962 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-03-25 | 2026-04-29 | 2026-04-29 | Internal line |  | 66.01 | Completed | No
WO-26-002963 | 4.3 | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-03-25 | 2026-03-25 | 2026-03-25 | Troubleman |  | 258.66 | Completed | No
WO-26-002964 | 4.5 | Crossroads | CR-S30-02 | Trouble - partial or voltage | P2 same day | 2026-03-25 | 2026-03-25 | 2026-03-25 | Internal line |  | 172.55 | Completed | No
WO-26-002965 | 5.9 | Bayou | BY-S02-01 | Corrective maintenance | P4 planned | 2026-03-26 | 2026-04-27 | 2026-04-27 | Internal line |  | 1035.83 | Completed | No
WO-26-002966 | 7.2 | Bayou | BY-S07-03 | Corrective maintenance | P4 planned | 2026-03-26 | 2026-05-03 | 2026-05-07 | Internal line |  | 1386.02 | Completed | No
WO-26-002967 | 7.9 | Bayou | BY-S15-02 | Corrective maintenance | P4 planned | 2026-03-26 | 2026-04-14 | 2026-04-15 | Contract line | CT-04 | 1630.08 | Completed | No
WO-26-002968 | 1.5 | Bayou | BY-S09-04 | Meter exchange | P4 planned | 2026-03-26 | 2026-04-23 | 2026-04-25 | Meter technician |  | 143.28 | Completed | No
WO-26-002969 | 0.6 | Bayou | BY-S21-03 | Meter exchange | P3 within 10 days | 2026-03-26 | 2026-03-28 | 2026-03-28 | Meter technician |  | 102.62 | Completed | No
WO-26-002970 | 14.1 | Bayou | BY-S11-01 | New service - small | P4 planned | 2026-03-26 | 2026-04-17 | 2026-04-18 | Internal line |  | 3210.58 | Completed | No
WO-26-002971 | 3.1 | Bayou | BY-S27-04 | Preventive maintenance | P4 planned | 2026-03-26 | 2026-05-09 | 2026-05-11 | Internal line |  | 151.78 | Completed | No
WO-26-002972 | 7.2 | Bayou | BY-S30-03 | Preventive maintenance | P4 planned | 2026-03-26 | 2026-05-11 | 2026-05-11 | Internal line |  | 142.14 | Completed | No
WO-26-002973 | 4.4 | Bayou | BY-S05-01 | Preventive maintenance | P4 planned | 2026-03-26 | 2026-05-04 | 2026-05-04 | Internal line |  | 426.07 | Completed | No
WO-26-002974 | 1.1 | Bayou | BY-S12-02 | Service order - field | P2 same day | 2026-03-26 | 2026-03-26 | 2026-03-26 | Meter technician |  | 14.77 | Completed | No
WO-26-002975 | 0.6 | Bayou | BY-S06-03 | Service order - field | P3 within 10 days | 2026-03-26 | 2026-03-31 | 2026-03-31 | Meter technician |  | 28.44 | Completed | No
WO-26-002976 |  | Bayou | BY-S10-03 | Service order - field | P3 within 10 days | 2026-03-26 | 2026-03-27 |  | Meter technician |  |  | Cancelled | No
WO-26-002977 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-26 | 2026-04-04 | 2026-04-06 | Contract line | CT-04 | 261.64 | Completed | No
WO-26-002978 | 1.3 | Bayou |  | Streetlight | P4 planned | 2026-03-26 | 2026-04-10 | 2026-04-12 | Contract line | CT-03 | 262.22 | Completed | No
WO-26-002979 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-26 | 2026-04-01 | 2026-04-01 | Contract line | CT-04 | 439.27 | Completed | No
WO-26-002980 | 3.1 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 284.29 | Completed | No
WO-26-002981 | 4.4 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 227.35 | Completed | No
WO-26-002982 | 4.3 | Bayou | BY-S08-03 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 323.97 | Completed | No
WO-26-002983 | 5.6 | Bayou | BY-S11-03 | Trouble - no power | P2 same day | 2026-03-26 | 2026-03-27 | 2026-03-27 | Troubleman |  | 65.73 | Completed | No
WO-26-002984 | 2.5 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 326.66 | Completed | No
WO-26-002985 | 5.8 | Bayou | BY-S03-01 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 295 | Completed | No
WO-26-002986 | 5.2 | Bayou | BY-S11-02 | Trouble - no power | P2 same day | 2026-03-26 | 2026-03-27 | 2026-03-27 | Internal line |  | 175.18 | Completed | No
WO-26-002987 | 3.9 | Bayou | BY-S27-01 | Trouble - partial or voltage | P2 same day | 2026-03-26 | 2026-03-27 | 2026-03-27 | Troubleman |  | 234.54 | Completed | No
WO-26-002988 | 4.1 | Bayou | BY-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-26 | 2026-04-01 | 2026-04-09 | Troubleman |  | 8.54 | Completed | No
WO-26-002989 | 3.3 | Crossroads | CR-S26-05 | Corrective maintenance | P3 within 10 days | 2026-03-26 | 2026-04-04 | 2026-04-04 | Underground crew |  | 2373.49 | Completed | No
WO-26-002990 | 11.7 | Crossroads | CR-S23-05 | Corrective maintenance | P2 same day | 2026-03-26 | 2026-03-27 | 2026-03-27 | Contract line | CT-01 | 1660 | Completed | No
WO-26-002991 | 6.9 | Crossroads | CR-S24-04 | Corrective maintenance | P3 within 10 days | 2026-03-26 | 2026-03-28 | 2026-03-28 | Internal line |  | 857.67 | Completed | No
WO-26-002992 | 0.9 | Crossroads | CR-S04-01 | Meter exchange | P4 planned | 2026-03-26 | 2026-04-08 | 2026-04-08 | Meter technician |  | 127.14 | Completed | No
WO-26-002993 | 1 | Crossroads | CR-S27-03 | Meter exchange | P4 planned | 2026-03-26 | 2026-04-15 | 2026-04-15 | Meter technician |  | 152.47 | Completed | No
WO-26-002994 | 1 | Crossroads | CR-S09-01 | Meter exchange | P4 planned | 2026-03-26 | 2026-04-08 | 2026-04-16 | Meter technician |  | 177.41 | Completed | No
WO-26-002995 | 0.9 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-03-26 | 2026-03-30 | 2026-03-30 | Meter technician |  | 81.8 | Completed | No
WO-26-002996 | 0.8 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-03-26 | 2026-04-05 | 2026-04-06 | Meter technician |  | 120.47 | Completed | No
WO-26-002997 | 0.6 | Crossroads | CR-S26-03 | Meter exchange | P4 planned | 2026-03-26 | 2026-05-16 | 2026-05-16 | Meter technician |  | 136.74 | Completed | No
WO-26-002998 | 1.3 | Crossroads | CR-S18-03 | Meter exchange | P4 planned | 2026-03-26 | 2026-04-20 | 2026-04-28 | Meter technician |  | 164.64 | Completed | No
WO-26-002999 | 4.5 | Crossroads | CR-S30-07 | Preventive maintenance | P4 planned | 2026-03-26 | 2026-04-12 | 2026-04-20 | Internal line |  | 92.55 | Completed | No
WO-26-003000 | 0.8 | Crossroads | CR-S06-02 | Service order - field | P2 same day | 2026-03-26 | 2026-03-26 | 2026-03-26 | Meter technician |  | 19.77 | Completed | No
WO-26-003001 | 1.1 | Crossroads | CR-S20-02 | Service order - field | P3 within 10 days | 2026-03-26 | 2026-04-04 | 2026-04-04 | Meter technician |  | 32.49 | Completed | No
WO-26-003002 | 1.2 | Crossroads | CR-S30-03 | Service order - field | P3 within 10 days | 2026-03-26 | 2026-04-05 | 2026-04-05 | Meter technician |  | 29.01 | Completed | No
WO-26-003003 | 1.3 | Crossroads | CR-S21-02 | Service order - field | P3 within 10 days | 2026-03-26 | 2026-04-04 | 2026-04-04 | Meter technician |  | 18.12 | Completed | No
WO-26-003004 | 0.7 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-03-26 | 2026-04-02 | 2026-04-02 | Meter technician |  | 29.94 | Completed | No
WO-26-003005 | 1.4 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-03-26 | 2026-03-26 | 2026-03-26 | Meter technician |  | 21.34 | Completed | No
WO-26-003006 | 3 | Crossroads |  | Streetlight | P4 planned | 2026-03-26 | 2026-04-22 | 2026-04-30 | Internal line |  | 303.22 | Completed | No
WO-26-003007 | 1.3 | Crossroads |  | Streetlight | P4 planned | 2026-03-26 | 2026-04-26 | 2026-04-26 | Contract line | CT-02 | 330.07 | Completed | No
WO-26-003008 | 2.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-26 | 2026-03-28 | 2026-03-28 | Internal line |  | 136.02 | Completed | No
WO-26-003009 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-26 | 2026-04-05 | 2026-04-05 | Contract line | CT-02 | 447.76 | Completed | No
WO-26-003010 | 13.6 | Crossroads | CR-S12-03 | Transformer replacement | P2 same day | 2026-03-26 | 2026-03-26 | 2026-03-26 | Internal line |  | 5595.15 | Completed | No
WO-26-003011 | 8.6 | Crossroads | CR-S27-02 | Transformer replacement | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Contract line | CT-02 | 3129.56 | Completed | No
WO-26-003012 | 9 | Crossroads | CR-S20-01 | Transformer replacement | P3 within 10 days | 2026-03-26 | 2026-04-05 | 2026-04-07 | Contract line | CT-01 | 9450.98 | Completed | No
WO-26-003013 | 2.5 | Crossroads | CR-S20-04 | Trouble - no power | P2 same day | 2026-03-26 | 2026-03-27 | 2026-03-27 | Troubleman |  | 64.35 | Completed | No
WO-26-003014 | 4.4 | Crossroads | CR-S08-03 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 222.7 | Completed | No
WO-26-003015 | 3.2 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 226.58 | Completed | No
WO-26-003016 | 4.1 | Crossroads | CR-S04-06 | Trouble - partial or voltage | P2 same day | 2026-03-26 | 2026-03-26 | 2026-03-26 | Troubleman |  | 35.4 | Completed | No
WO-26-003017 | 2.3 | Crossroads | CR-S27-03 | Trouble - partial or voltage | P2 same day | 2026-03-26 | 2026-03-27 | 2026-03-27 | Troubleman |  | 83.68 | Completed | No
WO-26-003018 | 3.3 | Crossroads | CR-S29-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-26 | 2026-04-02 | 2026-04-02 | Troubleman |  | 171.56 | Completed | No
WO-26-003019 | 10.6 | Bayou | BY-S16-01 | Corrective maintenance | P3 within 10 days | 2026-03-27 | 2026-04-03 | 2026-04-04 | Internal line |  | 1361.57 | Completed | No
WO-26-003020 | 6.9 | Bayou | BY-S23-05 | Corrective maintenance | P3 within 10 days | 2026-03-27 | 2026-04-02 | 2026-04-03 | Contract line | CT-04 | 1114.33 | Completed | No
WO-26-003021 | 1.2 | Bayou | BY-S01-02 | Meter exchange | P3 within 10 days | 2026-03-27 | 2026-04-05 | 2026-04-07 | Meter technician |  | 128.78 | Completed | No
WO-26-003022 | 1.4 | Bayou | BY-S05-01 | Meter exchange | P3 within 10 days | 2026-03-27 | 2026-04-02 | 2026-04-02 | Meter technician |  | 82.82 | Completed | No
WO-26-003023 | 0.8 | Bayou | BY-S18-04 | Meter exchange | P3 within 10 days | 2026-03-27 | 2026-03-31 | 2026-03-31 | Meter technician |  | 124.31 | Completed | No
WO-26-003024 | 11.9 | Bayou | BY-S18-06 | Pole replacement | P4 planned | 2026-03-27 | 2026-04-06 | 2026-04-06 | Contract line | CT-03 | 1869.7 | Completed | No
WO-26-003025 | 18.6 | Bayou | BY-S09-02 | Pole replacement | P2 same day | 2026-03-27 | 2026-03-27 | 2026-03-27 | Internal line |  | 2721.19 | Completed | No
WO-26-003026 | 4.1 | Bayou | BY-S23-02 | Preventive maintenance | P4 planned | 2026-03-27 | 2026-04-15 | 2026-04-17 | Internal line |  | 105.8 | Completed | No
WO-26-003027 | 7.4 | Bayou | BY-S22-03 | Preventive maintenance | P4 planned | 2026-03-27 | 2026-05-10 | 2026-05-12 | Contract line | CT-03 | 465.49 | Completed | No
WO-26-003028 | 1.7 | Bayou | BY-S06-02 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-04-02 | 2026-04-06 | Meter technician |  | 27.91 | Completed | No
WO-26-003029 | 1.9 | Bayou | BY-S01-01 | Service order - field | P2 same day | 2026-03-27 | 2026-03-28 | 2026-03-28 | Meter technician |  | 2.74 | Completed | No
WO-26-003030 | 1.6 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-03-27 | 2026-03-27 | 2026-03-27 | Meter technician |  | 35.36 | Completed | No
WO-26-003031 | 1.4 | Bayou | BY-S15-02 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-03-31 | 2026-04-02 | Meter technician |  | 18.96 | Completed | No
WO-26-003032 | 1.3 | Bayou | BY-S04-01 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-04-01 | 2026-04-01 | Meter technician |  | 25.95 | Completed | No
WO-26-003033 | 1.6 | Bayou | BY-S29-05 | Service order - field | P2 same day | 2026-03-27 | 2026-03-28 | 2026-03-28 | Meter technician |  | 27.17 | Completed | No
WO-26-003034 | 1.2 | Bayou | BY-S17-01 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-04-03 | 2026-04-03 | Meter technician |  | 6.02 | Completed | No
WO-26-003035 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-27 | 2026-04-05 | 2026-04-09 | Contract line | CT-03 | 347.59 | Completed | No
WO-26-003036 | 3.7 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-03-27 | 2026-03-27 | 2026-03-27 | Troubleman |  | 206.16 | Completed | No
WO-26-003037 | 3.2 | Bayou | BY-S27-04 | Trouble - no power | P1 emergency | 2026-03-27 | 2026-03-27 | 2026-03-27 | Internal line |  | 246.31 | Completed | No
WO-26-003038 | 3.4 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-03-27 | 2026-03-27 | 2026-03-27 | Internal line |  | 299.16 | Completed | No
WO-26-003039 | 9 | Crossroads | CR-S27-04 | Corrective maintenance | P2 same day | 2026-03-27 | 2026-03-27 | 2026-03-27 | Internal line |  | 401.23 | Completed | No
WO-26-003040 | 0.5 | Crossroads | CR-S22-03 | Meter exchange | P3 within 10 days | 2026-03-27 | 2026-03-28 | 2026-03-28 | Meter technician |  | 169.49 | Completed | No
WO-26-003041 | 0.5 | Crossroads | CR-S22-01 | Meter exchange | P3 within 10 days | 2026-03-27 | 2026-04-04 | 2026-04-04 | Meter technician |  | 107.54 | Completed | No
WO-26-003042 | 0.6 | Crossroads | CR-S07-05 | Meter exchange | P4 planned | 2026-03-27 | 2026-04-06 | 2026-04-07 | Meter technician |  | 143.78 | Completed | No
WO-26-003043 | 1.1 | Crossroads | CR-S28-03 | Meter exchange | P4 planned | 2026-03-27 | 2026-04-04 | 2026-04-04 | Meter technician |  | 106.85 | Completed | No
WO-26-003044 | 0.6 | Crossroads | CR-S07-01 | Meter exchange | P4 planned | 2026-03-27 | 2026-05-11 | 2026-05-11 | Meter technician |  | 87.2 | Completed | No
WO-26-003045 | 1 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-03-27 | 2026-03-28 | 2026-03-30 | Meter technician |  | 81.14 | Completed | No
WO-26-003046 | 0.8 | Crossroads | CR-S08-05 | Meter exchange | P4 planned | 2026-03-27 | 2026-05-21 | 2026-05-22 | Meter technician |  | 177.95 | Completed | No
WO-26-003047 | 5.7 | Crossroads | CR-S08-02 | New service - small | P4 planned | 2026-03-27 | 2026-05-20 | 2026-05-21 | Contract line | CT-02 | 3285.14 | Completed | No
WO-26-003048 | 14.1 | Crossroads | CR-S14-02 | New service - small | P4 planned | 2026-03-27 | 2026-04-16 | 2026-04-16 | Internal line |  | 2283.39 | Completed | No
WO-26-003049 | 13.7 | Crossroads | CR-S32-02 | Pole replacement | P3 within 10 days | 2026-03-27 | 2026-04-03 | 2026-04-03 | Contract line | CT-02 | 2633.69 | Completed | No
WO-26-003050 | 5.5 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-03-27 | 2026-04-06 | 2026-04-10 | Contract line | CT-02 | 463.25 | Completed | No
WO-26-003051 | 5.6 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-03-27 | 2026-04-14 | 2026-04-14 | Underground crew |  | 23.46 | Completed | No
WO-26-003052 | 0.6 | Crossroads | CR-S07-04 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-04-06 | 2026-04-08 | Meter technician |  | 36.34 | Completed | No
WO-26-003053 | 1.3 | Crossroads | CR-S05-04 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-03-30 | 2026-03-30 | Meter technician |  | 28.38 | Completed | No
WO-26-003054 | 1.7 | Crossroads | CR-S16-05 | Service order - field | P3 within 10 days | 2026-03-27 | 2026-04-06 | 2026-04-06 | Meter technician |  | 17.63 | Completed | No
WO-26-003055 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-27 | 2026-03-31 | 2026-03-31 | Contract line | CT-01 | 138.07 | Completed | No
WO-26-003056 | 3.3 | Crossroads | CR-S15-02 | Trouble - no power | P1 emergency | 2026-03-27 | 2026-03-27 | 2026-03-27 | Troubleman |  | 72.52 | Completed | No
WO-26-003057 | 5.3 | Crossroads | CR-S24-04 | Trouble - no power | P1 emergency | 2026-03-27 | 2026-03-27 | 2026-03-27 | Troubleman |  | 75.56 | Completed | No
WO-26-003058 | 3.7 | Crossroads | CR-S18-05 | Trouble - no power | P2 same day | 2026-03-27 | 2026-03-27 | 2026-03-27 | Troubleman |  | 60.35 | Completed | No
WO-26-003059 | 5.2 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-03-27 | 2026-03-27 | 2026-03-27 | Internal line |  | 289.33 | Completed | No
WO-26-003060 | 4.3 | Crossroads | CR-S20-01 | Trouble - partial or voltage | P3 within 10 days | 2026-03-27 | 2026-04-05 | 2026-04-05 | Internal line |  | 136.46 | Completed | No
WO-26-003061 | 3.5 | Crossroads | CR-S19-03 | Trouble - partial or voltage | P2 same day | 2026-03-27 | 2026-03-28 | 2026-03-28 | Troubleman |  | 49.61 | Completed | No
WO-26-003062 | 4 | Bayou | BY-S24-03 | Corrective maintenance | P2 same day | 2026-03-28 | 2026-03-28 | 2026-03-28 | Internal line |  | 1601.53 | Completed | No
WO-26-003063 | 1.7 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-03-28 | 2026-03-29 | 2026-03-29 | Meter technician |  | 38.51 | Completed | No
WO-26-003064 | 0.6 | Bayou | BY-S11-03 | Service order - field | P2 same day | 2026-03-28 | 2026-03-28 | 2026-03-28 | Meter technician |  | 28.66 | Completed | No
WO-26-003065 | 6.8 | Bayou | BY-S02-02 | Transformer replacement | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Internal line |  | 3558.97 | Completed | No
WO-26-003066 |  | Bayou | BY-S09-03 | Trouble - no power | P2 same day | 2026-03-28 | 2026-03-28 |  | Troubleman |  |  | Cancelled | No
WO-26-003067 | 3.6 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Troubleman |  | 208.35 | Completed | No
WO-26-003068 | 3.1 | Bayou | BY-S06-02 | Trouble - no power | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Troubleman |  | 118.19 | Completed | No
WO-26-003069 | 4.3 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Troubleman |  | 229.93 | Completed | No
WO-26-003070 | 4.6 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Troubleman |  | 228.95 | Completed | No
WO-26-003071 | 7.7 | Crossroads | CR-S05-05 | Corrective maintenance | P2 same day | 2026-03-28 | 2026-03-28 | 2026-03-28 | Internal line |  | 1504.72 | Completed | No
WO-26-003072 | 1.8 | Crossroads | CR-S20-01 | Service order - field | P2 same day | 2026-03-28 | 2026-03-28 | 2026-03-28 | Meter technician |  | 10.94 | Completed | No
WO-26-003073 | 0.9 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-03-28 | 2026-03-28 | 2026-03-28 | Meter technician |  | 39.49 | Completed | No
WO-26-003074 | 13 | Crossroads | CR-S30-02 | Transformer replacement | P2 same day | 2026-03-28 | 2026-03-29 | 2026-03-29 | Internal line |  | 4869.3 | Completed | No
WO-26-003075 | 4.9 | Crossroads | CR-S04-04 | Trouble - no power | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Internal line |  | 283.92 | Completed | No
WO-26-003076 | 5.2 | Crossroads | CR-S05-02 | Trouble - no power | P1 emergency | 2026-03-28 | 2026-03-28 | 2026-03-28 | Troubleman |  | 66.72 | Completed | No
WO-26-003077 | 2.4 | Crossroads | CR-S12-01 | Trouble - no power | P2 same day | 2026-03-28 | 2026-03-29 | 2026-03-29 | Troubleman |  | 224.73 | Completed | No
WO-26-003078 | 1.1 | Bayou | BY-S06-03 | Service order - field | P2 same day | 2026-03-29 | 2026-03-29 | 2026-03-29 | Meter technician |  | 22.32 | Completed | No
WO-26-003079 | 0.5 | Bayou | BY-S22-02 | Service order - field | P2 same day | 2026-03-29 | 2026-03-29 | 2026-03-29 | Meter technician |  | 2.45 | Completed | No
WO-26-003080 | 1 | Bayou | BY-S26-01 | Service order - field | P2 same day | 2026-03-29 | 2026-03-30 | 2026-03-30 | Meter technician |  | 16.13 | Completed | No
WO-26-003081 | 9.5 | Bayou | BY-S03-02 | Transformer replacement | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Contract line | CT-04 | 11166.24 | Completed | No
WO-26-003082 | 3.2 | Bayou | BY-S23-04 | Trouble - no power | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Troubleman |  | 174.94 | Completed | No
WO-26-003083 | 3.7 | Bayou | BY-S14-01 | Trouble - no power | P2 same day | 2026-03-29 | 2026-03-29 | 2026-03-29 | Troubleman |  | 70.53 | Completed | No
WO-26-003084 | 4 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Troubleman |  | 289.6 | Completed | No
WO-26-003085 | 0.6 | Crossroads | CR-S18-03 | Service order - field | P2 same day | 2026-03-29 | 2026-03-29 | 2026-03-29 | Meter technician |  | 20.88 | Completed | No
WO-26-003086 | 8.5 | Crossroads | CR-S02-05 | Transformer replacement | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Internal line |  | 9946.82 | Completed | No
WO-26-003087 | 12 | Crossroads | CR-S11-02 | Transformer replacement | P2 same day | 2026-03-29 | 2026-03-30 | 2026-03-30 | Contract line | CT-01 | 9764.81 | Completed | No
WO-26-003088 | 5.2 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Internal line |  | 45.13 | Completed | No
WO-26-003089 | 2.7 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Troubleman |  | 105.29 | Completed | No
WO-26-003090 | 4.1 | Crossroads | CR-S04-05 | Trouble - no power | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Troubleman |  | 90.68 | Completed | No
WO-26-003091 | 3.9 | Crossroads | CR-S19-02 | Trouble - no power | P1 emergency | 2026-03-29 | 2026-03-29 | 2026-03-29 | Troubleman |  | 4.78 | Completed | No
WO-26-003092 | 7.4 | Bayou | BY-S07-05 | Corrective maintenance | P3 within 10 days | 2026-03-30 | 2026-04-02 | 2026-04-06 | Internal line |  | 243.83 | Completed | No
WO-26-003093 | 6.4 | Bayou | BY-S16-04 | Corrective maintenance | P2 same day | 2026-03-30 | 2026-03-30 | 2026-03-30 | Internal line |  | 1479.86 | Completed | No
WO-26-003094 | 3.5 | Bayou | BY-S09-03 | Corrective maintenance | P4 planned | 2026-03-30 | 2026-05-01 | 2026-05-02 | Internal line |  | 1753.53 | Completed | No
WO-26-003095 |  | Bayou | BY-S28-03 | Meter exchange | P4 planned | 2026-03-30 | 2026-04-09 |  | Meter technician |  |  | Cancelled | No
WO-26-003096 | 0.8 | Bayou | BY-S21-04 | Meter exchange | P3 within 10 days | 2026-03-30 | 2026-04-01 | 2026-04-01 | Meter technician |  | 125.86 | Completed | No
WO-26-003097 | 0.6 | Bayou | BY-S09-04 | Meter exchange | P3 within 10 days | 2026-03-30 | 2026-04-04 | 2026-04-05 | Meter technician |  | 167.02 | Completed | No
WO-26-003098 | 0.7 | Bayou | BY-S23-03 | Meter exchange | P3 within 10 days | 2026-03-30 | 2026-04-07 | 2026-04-08 | Meter technician |  | 170.11 | Completed | No
WO-26-003099 | 0.8 | Bayou | BY-S09-02 | Meter exchange | P3 within 10 days | 2026-03-30 | 2026-04-07 | 2026-04-07 | Meter technician |  | 157.93 | Completed | No
WO-26-003100 | 1.2 | Bayou | BY-S04-02 | Meter exchange | P4 planned | 2026-03-30 | 2026-04-22 | 2026-04-22 | Meter technician |  | 74.04 | Completed | No
WO-26-003101 | 8.1 | Bayou | BY-S15-02 | New service - small | P4 planned | 2026-03-30 | 2026-04-28 | 2026-05-02 | Underground crew |  | 1253.85 | Completed | No
WO-26-003102 | 2.2 | Bayou | BY-S07-02 | Preventive maintenance | P4 planned | 2026-03-30 | 2026-05-18 | 2026-05-19 | Underground crew |  | 506.7 | Completed | No
WO-26-003103 | 5.1 | Bayou | BY-S22-04 | Preventive maintenance | P4 planned | 2026-03-30 | 2026-05-07 | 2026-05-11 | Internal line |  | 587.65 | Completed | No
WO-26-003104 | 0.7 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-03-30 | 2026-03-30 | 2026-03-30 | Meter technician |  | 34.81 | Completed | No
WO-26-003105 | 0.8 | Bayou | BY-S07-03 | Service order - field | P3 within 10 days | 2026-03-30 | 2026-04-05 | 2026-04-05 | Meter technician |  | 20.41 | Completed | No
WO-26-003106 | 2 | Bayou | BY-S01-02 | Service order - field | P2 same day | 2026-03-30 | 2026-03-30 | 2026-03-30 | Meter technician |  | 11.69 | Completed | No
WO-26-003107 | 12.1 | Bayou | BY-S08-01 | Transformer replacement | P2 same day | 2026-03-30 | 2026-03-31 | 2026-03-31 | Internal line |  | 10069.13 | Completed | No
WO-26-003108 | 6 | Bayou | BY-S04-03 | Trouble - no power | P2 same day | 2026-03-30 | 2026-03-31 | 2026-03-31 | Internal line |  | 236.88 | Completed | No
WO-26-003109 | 5.8 | Bayou | BY-S03-01 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 234.08 | Completed | No
WO-26-003110 | 5.8 | Bayou | BY-S06-03 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 14.16 | Completed | No
WO-26-003111 | 5.1 | Bayou | BY-S03-02 | Trouble - no power | P2 same day | 2026-03-30 | 2026-03-31 | 2026-03-31 | Troubleman |  | 5.45 | Completed | No
WO-26-003112 |  | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 |  | Troubleman |  |  | Cancelled | No
WO-26-003113 | 4.5 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 156.03 | Completed | No
WO-26-003114 | 1.6 | Bayou | BY-S07-03 | Trouble - partial or voltage | P2 same day | 2026-03-30 | 2026-03-31 | 2026-03-31 | Troubleman |  | 57.66 | Completed | No
WO-26-003115 | 8.5 | Crossroads | CR-S31-03 | Corrective maintenance | P3 within 10 days | 2026-03-30 | 2026-04-08 | 2026-04-09 | Contract line | CT-01 | 991.17 | Completed | No
WO-26-003116 | 10.4 | Crossroads | CR-S18-06 | Corrective maintenance | P3 within 10 days | 2026-03-30 | 2026-04-05 | 2026-04-09 | Underground crew |  | 434.86 | Completed | No
WO-26-003117 | 4.6 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-03-30 | 2026-04-06 | 2026-04-06 | Contract line | CT-01 | 293.73 | Completed | No
WO-26-003118 | 4.8 | Crossroads | CR-S19-02 | Corrective maintenance | P3 within 10 days | 2026-03-30 | 2026-04-08 | 2026-04-08 | Contract line | CT-02 | 1288.68 | Completed | No
WO-26-003119 | 1.2 | Crossroads | CR-S12-03 | Meter exchange | P4 planned | 2026-03-30 | 2026-04-06 | 2026-04-06 | Meter technician |  | 148.94 | Completed | No
WO-26-003120 | 0.8 | Crossroads | CR-S10-01 | Meter exchange | P4 planned | 2026-03-30 | 2026-04-21 | 2026-04-22 | Meter technician |  | 129.92 | Completed | No
WO-26-003121 | 1.1 | Crossroads | CR-S23-01 | Meter exchange | P4 planned | 2026-03-30 | 2026-04-13 | 2026-04-13 | Meter technician |  | 61.45 | Completed | No
WO-26-003122 | 1 | Crossroads | CR-S24-04 | Meter exchange | P3 within 10 days | 2026-03-30 | 2026-04-09 | 2026-04-10 | Meter technician |  | 118.91 | Completed | No
WO-26-003123 | 15.7 | Crossroads | CR-S19-03 | Pole replacement | P3 within 10 days | 2026-03-30 | 2026-04-01 | 2026-04-02 | Contract line | CT-02 | 1519.45 | Completed | No
WO-26-003124 | 1.2 | Crossroads | CR-S21-02 | Service order - field | P3 within 10 days | 2026-03-30 | 2026-04-06 | 2026-04-08 | Meter technician |  | 21.7 | Completed | No
WO-26-003125 | 1.9 | Crossroads | CR-S26-06 | Service order - field | P2 same day | 2026-03-30 | 2026-03-31 | 2026-03-31 | Meter technician |  | 0.14 | Completed | No
WO-26-003126 | 1.4 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-03-30 | 2026-04-07 | 2026-04-07 | Meter technician |  | 25.94 | Completed | No
WO-26-003127 | 1.6 | Crossroads | CR-S20-05 | Service order - field | P2 same day | 2026-03-30 | 2026-03-30 | 2026-03-30 | Meter technician |  | 18.04 | Completed | No
WO-26-003128 | 1.1 | Crossroads | CR-S04-02 | Service order - field | P2 same day | 2026-03-30 | 2026-03-30 | 2026-03-30 | Meter technician |  | 8.74 | Completed | No
WO-26-003129 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-30 | 2026-04-02 | 2026-04-03 | Contract line | CT-02 | 61.05 | Completed | No
WO-26-003130 | 3.4 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 320.57 | Completed | No
WO-26-003131 | 4.2 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 13.95 | Completed | No
WO-26-003132 | 5.3 | Crossroads | CR-S26-06 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 50.6 | Completed | No
WO-26-003133 | 2 | Crossroads | CR-S32-05 | Trouble - no power | P1 emergency | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 125.75 | Completed | No
WO-26-003134 | 3.6 | Crossroads | CR-S22-04 | Trouble - no power | P2 same day | 2026-03-30 | 2026-03-31 | 2026-03-31 | Troubleman |  | 236.36 | Completed | No
WO-26-003135 | 4.6 | Crossroads | CR-S25-02 | Trouble - partial or voltage | P2 same day | 2026-03-30 | 2026-03-30 | 2026-03-30 | Troubleman |  | 175.32 | Completed | No
WO-26-003136 | 4.6 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-03-30 | 2026-04-03 | 2026-04-03 | Troubleman |  | 212.23 | Completed | No
WO-26-003137 | 7.5 | Bayou | BY-S08-01 | Corrective maintenance | P3 within 10 days | 2026-03-31 | 2026-04-08 | 2026-04-08 | Contract line | CT-03 | 618.55 | Completed | No
WO-26-003138 | 8.8 | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-03-31 | 2026-05-17 | 2026-05-21 | Underground crew |  | 1996.15 | Completed | No
WO-26-003139 | 10.1 | Bayou | BY-S15-01 | Corrective maintenance | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Contract line | CT-03 | 115.98 | Completed | No
WO-26-003140 | 7 | Bayou | BY-S13-01 | Corrective maintenance | P4 planned | 2026-03-31 | 2026-04-24 | 2026-04-26 | Internal line |  | 1791.17 | Completed | No
WO-26-003141 | 9.2 | Bayou | BY-S15-06 | Corrective maintenance | P3 within 10 days | 2026-03-31 | 2026-04-07 | 2026-04-07 | Internal line |  | 2380.73 | Completed | No
WO-26-003142 |  | Bayou | BY-S14-02 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-10 |  | Meter technician |  |  | Cancelled | No
WO-26-003143 | 1.2 | Bayou | BY-S13-01 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-02 | 2026-04-02 | Meter technician |  | 91.45 | Completed | No
WO-26-003144 | 1 | Bayou | BY-S11-03 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-02 | 2026-04-10 | Meter technician |  | 69.16 | Completed | No
WO-26-003145 | 1.1 | Bayou | BY-S19-02 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-05 | 2026-04-05 | Meter technician |  | 79.54 | Completed | No
WO-26-003146 | 0.8 | Bayou | BY-S09-04 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-09 | 2026-04-09 | Meter technician |  | 75.54 | Completed | No
WO-26-003147 | 22.7 | Bayou | BY-S05-03 | Pole replacement | P3 within 10 days | 2026-03-31 | 2026-04-09 | 2026-04-11 | Contract line | CT-03 | 1506.11 | Completed | No
WO-26-003148 | 23.5 | Bayou | BY-S04-03 | Pole replacement | P3 within 10 days | 2026-03-31 | 2026-04-02 | 2026-04-02 | Contract line | CT-03 | 1629.54 | Completed | No
WO-26-003149 | 12.4 | Bayou | BY-S14-02 | Pole replacement | P4 planned | 2026-03-31 | 2026-05-15 | 2026-05-15 | Contract line | CT-03 | 1708.91 | Completed | No
WO-26-003150 | 5.2 | Bayou | BY-S16-04 | Preventive maintenance | P4 planned | 2026-03-31 | 2026-04-11 | 2026-04-15 | Internal line |  | 165.39 | Completed | No
WO-26-003151 | 2.1 | Bayou | BY-S27-06 | Preventive maintenance | P4 planned | 2026-03-31 | 2026-04-14 | 2026-04-15 | Underground crew |  | 390.38 | Completed | No
WO-26-003152 | 1.9 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-03-31 | 2026-04-01 | 2026-04-01 | Meter technician |  | 34.01 | Completed | No
WO-26-003153 | 1.1 | Bayou | BY-S18-03 | Service order - field | P3 within 10 days | 2026-03-31 | 2026-04-01 | 2026-04-02 | Meter technician |  | 14.07 | Completed | No
WO-26-003154 | 1.2 | Bayou | BY-S25-05 | Service order - field | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Meter technician |  | 6.36 | Completed | No
WO-26-003155 | 1.8 | Bayou | BY-S16-04 | Service order - field | P2 same day | 2026-03-31 | 2026-04-01 | 2026-04-01 | Meter technician |  | 0.01 | Completed | No
WO-26-003156 | 1.1 | Bayou | BY-S10-03 | Service order - field | P3 within 10 days | 2026-03-31 | 2026-04-08 | 2026-04-08 | Meter technician |  | 32.45 | Completed | No
WO-26-003157 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-31 | 2026-04-02 | 2026-04-02 | Contract line | CT-03 | 140.34 | Completed | No
WO-26-003158 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-03-31 | 2026-04-02 | 2026-04-06 | Internal line |  | 303.68 | Completed | No
WO-26-003159 | 12.5 | Bayou | BY-S16-02 | Transformer replacement | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Internal line |  | 6769.61 | Completed | No
WO-26-003160 | 3.7 | Bayou | BY-S15-06 | Trouble - no power | P1 emergency | 2026-03-31 | 2026-03-31 | 2026-03-31 | Troubleman |  | 106.59 | Completed | No
WO-26-003161 | 4.7 | Bayou | BY-S14-02 | Trouble - no power | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Troubleman |  | 116.05 | Completed | No
WO-26-003162 | 6 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-03-31 | 2026-03-31 | 2026-03-31 | Internal line |  | 97.63 | Completed | No
WO-26-003163 | 5.3 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-03-31 | 2026-03-31 | 2026-03-31 | Internal line |  | 42.39 | Completed | No
WO-26-003164 | 5.8 | Bayou | BY-S08-02 | Trouble - no power | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Troubleman |  | 96.22 | Completed | No
WO-26-003165 | 4.3 | Bayou | BY-S16-05 | Trouble - partial or voltage | P3 within 10 days | 2026-03-31 | 2026-04-10 | 2026-04-10 | Troubleman |  | 194.89 | Completed | No
WO-26-003166 | 8.6 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-03-31 | 2026-04-01 | 2026-04-02 | Underground crew |  | 1449.57 | Completed | No
WO-26-003167 | 11.4 | Crossroads | CR-S14-03 | Corrective maintenance | P3 within 10 days | 2026-03-31 | 2026-04-02 | 2026-04-02 | Internal line |  | 1387.94 | Completed | No
WO-26-003168 | 8.5 | Crossroads | CR-S20-01 | Corrective maintenance | P3 within 10 days | 2026-03-31 | 2026-04-06 | 2026-04-06 | Underground crew |  | 893.13 | Completed | No
WO-26-003169 | 0.9 | Crossroads | CR-S14-03 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-05 | 2026-04-05 | Meter technician |  | 95.18 | Completed | No
WO-26-003170 | 0.8 | Crossroads | CR-S30-07 | Meter exchange | P3 within 10 days | 2026-03-31 | 2026-04-09 | 2026-04-09 | Meter technician |  | 75.09 | Completed | No
WO-26-003171 | 7.7 | Crossroads | CR-S06-02 | New service - small | P3 within 10 days | 2026-03-31 | 2026-04-10 | 2026-04-10 | Contract line | CT-01 | 2117.64 | Completed | No
WO-26-003172 | 6.7 | Crossroads | CR-S02-01 | Preventive maintenance | P4 planned | 2026-03-31 | 2026-05-21 | 2026-05-29 | Internal line |  | 407.65 | Completed | No
WO-26-003173 | 1.4 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-03-31 | 2026-04-08 | 2026-04-08 | Meter technician |  | 23.23 | Completed | No
WO-26-003174 | 1.3 | Crossroads | CR-S16-05 | Service order - field | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Meter technician |  | 2.74 | Completed | No
WO-26-003175 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-31 | 2026-04-07 | 2026-04-07 | Contract line | CT-01 | 172.62 | Completed | No
WO-26-003176 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-03-31 | 2026-04-07 | 2026-04-11 | Contract line | CT-01 | 183.34 | Completed | No
WO-26-003177 |  | Crossroads |  | Streetlight | P4 planned | 2026-03-31 | 2026-04-26 |  | Internal line |  |  | Cancelled | No
WO-26-003178 | 9.9 | Crossroads | CR-S22-01 | Transformer replacement | P1 emergency | 2026-03-31 | 2026-03-31 | 2026-03-31 | Internal line |  | 9759.86 | Completed | No
WO-26-003179 | 5.7 | Crossroads | CR-S26-02 | Trouble - no power | P1 emergency | 2026-03-31 | 2026-03-31 | 2026-03-31 | Troubleman |  | 205.15 | Completed | No
WO-26-003180 | 3.1 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P2 same day | 2026-03-31 | 2026-03-31 | 2026-03-31 | Troubleman |  | 160.99 | Completed | No
WO-26-003181 | 3 | Crossroads | CR-S03-02 | Trouble - partial or voltage | P3 within 10 days | 2026-03-31 | 2026-04-07 | 2026-04-07 | Troubleman |  | 196.09 | Completed | No
WO-26-003182 | 8.1 | Bayou | BY-S12-03 | Corrective maintenance | P3 within 10 days | 2026-04-01 | 2026-04-06 | 2026-04-10 | Internal line |  | 2022.52 | Completed | No
WO-26-003183 | 6.6 | Bayou | BY-S24-01 | Corrective maintenance | P4 planned | 2026-04-01 | 2026-04-23 | 2026-04-23 | Internal line |  | 1253.62 | Completed | No
WO-26-003184 |  | Bayou | BY-S23-05 | Corrective maintenance | P2 same day | 2026-04-01 | 2026-04-01 |  | Internal line |  |  | Cancelled | No
WO-26-003185 | 11.5 | Bayou | BY-S20-01 | Corrective maintenance | P3 within 10 days | 2026-04-01 | 2026-04-09 | 2026-04-13 | Internal line |  | 1709.38 | Completed | No
WO-26-003186 | 8.7 | Bayou | BY-S15-01 | Corrective maintenance | P3 within 10 days | 2026-04-01 | 2026-04-07 | 2026-04-08 | Contract line | CT-03 | 2348.36 | Completed | No
WO-26-003187 | 1.5 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-04-01 | 2026-04-08 | 2026-04-08 | Meter technician |  | 92.44 | Completed | No
WO-26-003188 | 1.4 | Bayou | BY-S15-01 | Meter exchange | P3 within 10 days | 2026-04-01 | 2026-04-09 | 2026-04-09 | Meter technician |  | 76.36 | Completed | No
WO-26-003189 | 0.8 | Bayou | BY-S16-06 | Meter exchange | P4 planned | 2026-04-01 | 2026-04-10 | 2026-04-10 | Meter technician |  | 93.51 | Completed | No
WO-26-003190 | 1.4 | Bayou | BY-S29-05 | Meter exchange | P3 within 10 days | 2026-04-01 | 2026-04-05 | 2026-04-13 | Meter technician |  | 178.66 | Completed | No
WO-26-003191 | 1.4 | Bayou | BY-S04-02 | Meter exchange | P3 within 10 days | 2026-04-01 | 2026-04-10 | 2026-04-11 | Meter technician |  | 159.18 | Completed | No
WO-26-003192 | 2.5 | Bayou | BY-S23-02 | Preventive maintenance | P4 planned | 2026-04-01 | 2026-04-12 | 2026-04-20 | Underground crew |  | 292.15 | Completed | No
WO-26-003193 |  | Bayou | BY-S15-04 | Preventive maintenance | P4 planned | 2026-04-01 | 2026-05-23 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-003194 | 0.8 | Bayou | BY-S18-05 | Service order - field | P2 same day | 2026-04-01 | 2026-04-01 | 2026-04-01 | Meter technician |  | 18.39 | Completed | No
WO-26-003195 | 2 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-04-01 | 2026-04-03 | 2026-04-04 | Meter technician |  | 29 | Completed | No
WO-26-003196 | 1 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-04-01 | 2026-04-01 | 2026-04-01 | Meter technician |  | 5.34 | Completed | No
WO-26-003197 | 0.8 | Bayou | BY-S11-03 | Service order - field | P3 within 10 days | 2026-04-01 | 2026-04-10 | 2026-04-10 | Meter technician |  | 12.01 | Completed | No
WO-26-003198 | 0.9 | Bayou | BY-S27-04 | Service order - field | P3 within 10 days | 2026-04-01 | 2026-04-09 | 2026-04-13 | Meter technician |  | 13.15 | Completed | No
WO-26-003199 | 2.9 | Bayou |  | Streetlight | P4 planned | 2026-04-01 | 2026-05-28 | 2026-06-01 | Internal line |  | 220.22 | Completed | No
WO-26-003200 | 1.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-01 | 2026-04-02 | 2026-04-02 | Contract line | CT-03 | 447.99 | Completed | No
WO-26-003201 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-01 | 2026-04-10 | 2026-04-10 | Contract line | CT-04 | 298.07 | Completed | No
WO-26-003202 | 4 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 218.82 | Completed | No
WO-26-003203 | 2.3 | Bayou | BY-S09-04 | Trouble - no power | P2 same day | 2026-04-01 | 2026-04-02 | 2026-04-02 | Troubleman |  | 328.99 | Completed | No
WO-26-003204 | 2.2 | Bayou | BY-S15-04 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 65.21 | Completed | No
WO-26-003205 | 3.5 | Bayou | BY-S12-01 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 7.99 | Completed | No
WO-26-003206 | 5.5 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 122.1 | Completed | No
WO-26-003207 | 4.1 | Crossroads | CR-S07-07 | Corrective maintenance | P2 same day | 2026-04-01 | 2026-04-01 | 2026-04-01 | Internal line |  | 1120.77 | Completed | No
WO-26-003208 |  | Crossroads | CR-S30-02 | Corrective maintenance | P3 within 10 days | 2026-04-01 | 2026-04-11 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-003209 | 8.2 | Crossroads | CR-S24-02 | Corrective maintenance | P3 within 10 days | 2026-04-01 | 2026-04-05 | 2026-04-06 | Internal line |  | 1997.83 | Completed | No
WO-26-003210 | 0.5 | Crossroads | CR-S01-02 | Meter exchange | P3 within 10 days | 2026-04-01 | 2026-04-09 | 2026-04-09 | Meter technician |  | 170.78 | Completed | No
WO-26-003211 | 13.9 | Crossroads | CR-S02-01 | New service - small | P4 planned | 2026-04-01 | 2026-05-28 | 2026-05-29 | Underground crew |  | 4032.33 | Completed | No
WO-26-003212 | 13.9 | Crossroads | CR-S23-01 | Pole replacement | P3 within 10 days | 2026-04-01 | 2026-04-11 | 2026-04-11 | Internal line |  | 1813.01 | Completed | No
WO-26-003213 | 4.2 | Crossroads | CR-S15-03 | Preventive maintenance | P4 planned | 2026-04-01 | 2026-04-11 | 2026-04-11 | Underground crew |  | 120 | Completed | No
WO-26-003214 | 1.8 | Crossroads | CR-S18-03 | Service order - field | P3 within 10 days | 2026-04-01 | 2026-04-11 | 2026-04-15 | Meter technician |  | 15.93 | Completed | No
WO-26-003215 | 0.7 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-04-01 | 2026-04-02 | 2026-04-02 | Meter technician |  | 6.4 | Completed | No
WO-26-003216 | 1 | Crossroads | CR-S01-01 | Service order - field | P3 within 10 days | 2026-04-01 | 2026-04-11 | 2026-04-12 | Meter technician |  | 34.01 | Completed | No
WO-26-003217 | 1 | Crossroads | CR-S07-01 | Service order - field | P2 same day | 2026-04-01 | 2026-04-01 | 2026-04-01 | Meter technician |  | 36.78 | Completed | No
WO-26-003218 | 1.6 | Crossroads | CR-S24-02 | Service order - field | P2 same day | 2026-04-01 | 2026-04-02 | 2026-04-02 | Meter technician |  | 21.96 | Completed | No
WO-26-003219 | 1.7 | Crossroads | CR-S30-01 | Service order - field | P3 within 10 days | 2026-04-01 | 2026-04-03 | 2026-04-11 | Meter technician |  | 9.4 | Completed | No
WO-26-003220 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-04-01 | 2026-04-28 | 2026-05-02 | Internal line |  | 151.73 | Completed | No
WO-26-003221 | 1.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-01 | 2026-04-08 | 2026-04-09 | Internal line |  | 313.1 | Completed | No
WO-26-003222 | 12.8 | Crossroads | CR-S22-03 | Transformer replacement | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Internal line |  | 11995.4 | Completed | No
WO-26-003223 | 7.1 | Crossroads | CR-S14-02 | Transformer replacement | P2 same day | 2026-04-01 | 2026-04-01 | 2026-04-01 | Contract line | CT-02 | 2902.08 | Completed | No
WO-26-003224 |  | Crossroads | CR-S07-04 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 |  | Troubleman |  |  | Cancelled | No
WO-26-003225 | 2.4 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 12.25 | Completed | No
WO-26-003226 | 4.4 | Crossroads | CR-S06-01 | Trouble - no power | P2 same day | 2026-04-01 | 2026-04-02 | 2026-04-02 | Troubleman |  | 281 | Completed | No
WO-26-003227 | 3.6 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 321.6 | Completed | No
WO-26-003228 | 2.9 | Crossroads | CR-S01-02 | Trouble - no power | P1 emergency | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 244.57 | Completed | No
WO-26-003229 | 4.4 | Crossroads | CR-S07-02 | Trouble - partial or voltage | P2 same day | 2026-04-01 | 2026-04-01 | 2026-04-01 | Troubleman |  | 75.71 | Completed | No
WO-26-003230 | 8.9 | Bayou | BY-S17-02 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-10 | 2026-04-10 | Internal line |  | 1617.87 | Completed | No
WO-26-003231 | 3.2 | Bayou | BY-S20-03 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-07 | 2026-04-11 | Internal line |  | 373.97 | Completed | No
WO-26-003232 | 7.8 | Bayou | BY-S10-03 | Corrective maintenance | P4 planned | 2026-04-02 | 2026-05-20 | 2026-05-20 | Internal line |  | 326.31 | Completed | No
WO-26-003233 | 10 | Bayou | BY-S03-02 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-07 | 2026-04-07 | Underground crew |  | 1162.17 | Completed | No
WO-26-003234 | 7.2 | Bayou | BY-S16-01 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-04 | 2026-04-04 | Contract line | CT-03 | 296.04 | Completed | No
WO-26-003235 | 9.2 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-12 | 2026-04-13 | Internal line |  | 1697.06 | Completed | No
WO-26-003236 | 4.7 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-08 | 2026-04-09 | Underground crew |  | 244.84 | Completed | No
WO-26-003237 | 0.6 | Bayou | BY-S25-05 | Meter exchange | P3 within 10 days | 2026-04-02 | 2026-04-03 | 2026-04-03 | Meter technician |  | 85.13 | Completed | No
WO-26-003238 | 1.3 | Bayou | BY-S27-02 | Meter exchange | P4 planned | 2026-04-02 | 2026-05-08 | 2026-05-12 | Meter technician |  | 116.67 | Completed | No
WO-26-003239 | 0.9 | Bayou | BY-S16-03 | Meter exchange | P3 within 10 days | 2026-04-02 | 2026-04-04 | 2026-04-04 | Meter technician |  | 77.22 | Completed | No
WO-26-003240 | 8 | Bayou | BY-S17-02 | New service - small | P4 planned | 2026-04-02 | 2026-04-12 | 2026-04-14 | Internal line |  | 3967.13 | Completed | No
WO-26-003241 | 7.5 | Bayou | BY-S15-03 | New service - small | P4 planned | 2026-04-02 | 2026-04-09 | 2026-04-09 | Contract line | CT-04 | 1579.27 | Completed | No
WO-26-003242 | 6.8 | Bayou | BY-S24-01 | Preventive maintenance | P4 planned | 2026-04-02 | 2026-05-19 | 2026-05-19 | Internal line |  | 505.72 | Completed | No
WO-26-003243 | 7.1 | Bayou | BY-S17-01 | Preventive maintenance | P4 planned | 2026-04-02 | 2026-05-20 | 2026-05-21 | Internal line |  | 303.06 | Completed | No
WO-26-003244 | 3.5 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-04-02 | 2026-04-11 | 2026-04-11 | Internal line |  | 522.19 | Completed | No
WO-26-003245 | 2.3 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-04-02 | 2026-04-29 | 2026-04-30 | Underground crew |  | 75.66 | Completed | No
WO-26-003246 | 5.8 | Bayou | BY-S05-01 | Preventive maintenance | P4 planned | 2026-04-02 | 2026-05-27 | 2026-05-29 | Internal line |  | 558.65 | Completed | No
WO-26-003247 | 1.3 | Bayou | BY-S03-01 | Service order - field | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Meter technician |  | 12.44 | Completed | No
WO-26-003248 | 0.9 | Bayou | BY-S23-03 | Service order - field | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Meter technician |  | 4.65 | Completed | No
WO-26-003249 | 1.9 | Bayou | BY-S07-02 | Service order - field | P3 within 10 days | 2026-04-02 | 2026-04-06 | 2026-04-07 | Meter technician |  | 6.81 | Completed | No
WO-26-003250 | 0.8 | Bayou | BY-S24-02 | Service order - field | P3 within 10 days | 2026-04-02 | 2026-04-10 | 2026-04-10 | Meter technician |  | 35.99 | Completed | No
WO-26-003251 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-02 | 2026-04-08 | 2026-04-08 | Contract line | CT-03 | 52.64 | Completed | No
WO-26-003252 | 6.6 | Bayou | BY-S20-01 | Transformer replacement | P3 within 10 days | 2026-04-02 | 2026-04-09 | 2026-04-09 | Internal line |  | 7776.49 | Completed | No
WO-26-003253 | 4.1 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-04-02 | 2026-04-02 | 2026-04-02 | Troubleman |  | 59.48 | Completed | No
WO-26-003254 | 3.4 | Bayou | BY-S28-01 | Trouble - no power | P1 emergency | 2026-04-02 | 2026-04-02 | 2026-04-02 | Troubleman |  | 174.47 | Completed | No
WO-26-003255 | 2.2 | Bayou | BY-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-02 | 2026-04-08 | 2026-04-09 | Troubleman |  | 221.98 | Completed | No
WO-26-003256 |  | Bayou | BY-S18-04 | Trouble - partial or voltage | P2 same day | 2026-04-02 | 2026-04-03 |  | Internal line |  |  | Cancelled | No
WO-26-003257 | 4.5 | Bayou | BY-S15-04 | Trouble - partial or voltage | P3 within 10 days | 2026-04-02 | 2026-04-09 | 2026-04-17 | Troubleman |  | 161.96 | Completed | No
WO-26-003258 | 6.7 | Crossroads | CR-S23-02 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-07 | 2026-04-15 | Contract line | CT-01 | 1702.27 | Completed | No
WO-26-003259 | 5 | Crossroads | CR-S07-02 | Corrective maintenance | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Internal line |  | 727.93 | Completed | No
WO-26-003260 | 8.5 | Crossroads | CR-S18-01 | Corrective maintenance | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Internal line |  | 687.39 | Completed | No
WO-26-003261 | 7.8 | Crossroads | CR-S26-04 | Corrective maintenance | P2 same day | 2026-04-02 | 2026-04-03 | 2026-04-03 | Contract line | CT-02 | 2021 | Completed | No
WO-26-003262 | 11.9 | Crossroads | CR-S14-02 | Corrective maintenance | P2 same day | 2026-04-02 | 2026-04-03 | 2026-04-03 | Internal line |  | 333.11 | Completed | No
WO-26-003263 | 8.2 | Crossroads | CR-S16-04 | Corrective maintenance | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Underground crew |  | 1660.28 | Completed | No
WO-26-003264 | 6.9 | Crossroads | CR-S22-01 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-05 | 2026-04-06 | Internal line |  | 1649.26 | Completed | No
WO-26-003265 | 8.3 | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-04-02 | 2026-04-07 | 2026-04-08 | Internal line |  | 1571.18 | Completed | No
WO-26-003266 | 1.1 | Crossroads | CR-S19-04 | Meter exchange | P4 planned | 2026-04-02 | 2026-05-04 | 2026-05-08 | Meter technician |  | 83.45 | Completed | No
WO-26-003267 | 1.5 | Crossroads | CR-S06-03 | Meter exchange | P3 within 10 days | 2026-04-02 | 2026-04-07 | 2026-04-08 | Meter technician |  | 107.99 | Completed | No
WO-26-003268 | 8.4 | Crossroads | CR-S10-02 | New service - small | P4 planned | 2026-04-02 | 2026-05-19 | 2026-05-19 | Internal line |  | 950.79 | Completed | No
WO-26-003269 | 11 | Crossroads | CR-S07-07 | Pole replacement | P4 planned | 2026-04-02 | 2026-05-07 | 2026-05-09 | Contract line | CT-01 | 1278.66 | Completed | No
WO-26-003270 | 4.5 | Crossroads | CR-S07-02 | Preventive maintenance | P4 planned | 2026-04-02 | 2026-05-05 | 2026-05-05 | Underground crew |  | 342.82 | Completed | No
WO-26-003271 | 1.1 | Crossroads | CR-S14-02 | Service order - field | P2 same day | 2026-04-02 | 2026-04-03 | 2026-04-03 | Meter technician |  | 34.4 | Completed | No
WO-26-003272 | 1.7 | Crossroads | CR-S23-04 | Service order - field | P3 within 10 days | 2026-04-02 | 2026-04-10 | 2026-04-11 | Meter technician |  | 13.66 | Completed | No
WO-26-003273 | 1.7 | Crossroads | CR-S23-01 | Service order - field | P3 within 10 days | 2026-04-02 | 2026-04-12 | 2026-04-13 | Meter technician |  | 6.19 | Completed | No
WO-26-003274 | 1.3 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Meter technician |  | 24.59 | Completed | No
WO-26-003275 | 0.6 | Crossroads | CR-S18-03 | Service order - field | P3 within 10 days | 2026-04-02 | 2026-04-07 | 2026-04-09 | Meter technician |  | 5.54 | Completed | No
WO-26-003276 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-02 | 2026-04-11 | 2026-04-15 | Internal line |  | 227.03 | Completed | No
WO-26-003277 | 11.8 | Crossroads | CR-S26-02 | Transformer replacement | P2 same day | 2026-04-02 | 2026-04-02 | 2026-04-02 | Internal line |  | 7696.09 | Completed | No
WO-26-003278 | 5.7 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-04-02 | 2026-04-02 | 2026-04-02 | Internal line |  | 31.67 | Completed | No
WO-26-003279 | 3.9 | Crossroads | CR-S18-03 | Trouble - no power | P1 emergency | 2026-04-02 | 2026-04-02 | 2026-04-02 | Internal line |  | 166.6 | Completed | No
WO-26-003280 | 2.6 | Crossroads | CR-S20-03 | Trouble - no power | P1 emergency | 2026-04-02 | 2026-04-02 | 2026-04-02 | Troubleman |  | 112.68 | Completed | No
WO-26-003281 | 3.3 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-02 | 2026-04-08 | 2026-04-08 | Troubleman |  | 168.69 | Completed | No
WO-26-003282 | 4.5 | Crossroads | CR-S07-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-02 | 2026-04-12 | 2026-04-14 | Internal line |  | 164.03 | Completed | No
WO-26-003283 | 4.5 | Crossroads | CR-S02-05 | Trouble - partial or voltage | P2 same day | 2026-04-02 | 2026-04-03 | 2026-04-03 | Internal line |  | 85.33 | Completed | No
WO-26-003284 | 2.4 | Crossroads | CR-S08-04 | Trouble - partial or voltage | P2 same day | 2026-04-02 | 2026-04-03 | 2026-04-03 | Troubleman |  | 122.83 | Completed | No
WO-26-003285 | 7.1 | Bayou | BY-S21-03 | Corrective maintenance | P3 within 10 days | 2026-04-03 | 2026-04-08 | 2026-04-08 | Contract line | CT-03 | 2136.46 | Completed | No
WO-26-003286 | 6.4 | Bayou | BY-S10-01 | Corrective maintenance | P3 within 10 days | 2026-04-03 | 2026-04-13 | 2026-04-15 | Contract line | CT-04 | 1527.64 | Completed | No
WO-26-003287 | 3.9 | Bayou | BY-S08-03 | Corrective maintenance | P3 within 10 days | 2026-04-03 | 2026-04-12 | 2026-04-14 | Contract line | CT-04 | 975.45 | Completed | No
WO-26-003288 | 6.4 | Bayou | BY-S26-03 | Corrective maintenance | P3 within 10 days | 2026-04-03 | 2026-04-07 | 2026-04-07 | Internal line |  | 809.28 | Completed | No
WO-26-003289 | 10.6 | Bayou | BY-S03-01 | Corrective maintenance | P3 within 10 days | 2026-04-03 | 2026-04-13 | 2026-04-13 | Contract line | CT-03 | 1069.59 | Completed | No
WO-26-003290 | 1.4 | Bayou | BY-S25-02 | Meter exchange | P4 planned | 2026-04-03 | 2026-06-01 | 2026-06-01 | Meter technician |  | 167.67 | Completed | No
WO-26-003291 | 1.1 | Bayou | BY-S08-03 | Meter exchange | P4 planned | 2026-04-03 | 2026-04-23 | 2026-04-23 | Meter technician |  | 89.23 | Completed | No
WO-26-003292 | 12.3 | Bayou | BY-S25-04 | New service - small | P3 within 10 days | 2026-04-03 | 2026-04-07 | 2026-04-08 | Internal line |  | 1683.04 | Completed | No
WO-26-003293 | 12.2 | Bayou | BY-S19-03 | Pole replacement | P3 within 10 days | 2026-04-03 | 2026-04-06 | 2026-04-06 | Internal line |  | 3248.43 | Completed | No
WO-26-003294 | 4.6 | Bayou | BY-S14-03 | Preventive maintenance | P4 planned | 2026-04-03 | 2026-04-29 | 2026-05-01 | Internal line |  | 574.92 | Completed | No
WO-26-003295 | 1.3 | Bayou | BY-S30-01 | Service order - field | P3 within 10 days | 2026-04-03 | 2026-04-10 | 2026-04-10 | Meter technician |  | 34.2 | Completed | No
WO-26-003296 | 1.6 | Bayou | BY-S10-05 | Service order - field | P2 same day | 2026-04-03 | 2026-04-03 | 2026-04-03 | Meter technician |  | 29.87 | Completed | No
WO-26-003297 | 0.8 | Bayou | BY-S29-04 | Service order - field | P3 within 10 days | 2026-04-03 | 2026-04-10 | 2026-04-11 | Meter technician |  | 39.35 | Completed | No
WO-26-003298 | 1.8 | Bayou |  | Streetlight | P4 planned | 2026-04-03 | 2026-04-13 | 2026-04-13 | Contract line | CT-03 | 257.06 | Completed | No
WO-26-003299 | 14 | Bayou | BY-S30-03 | Transformer replacement | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Internal line |  | 10539.98 | Completed | No
WO-26-003300 | 7.9 | Bayou | BY-S19-02 | Transformer replacement | P2 same day | 2026-04-03 | 2026-04-03 | 2026-04-03 | Internal line |  | 4425.87 | Completed | No
WO-26-003301 | 5.7 | Bayou | BY-S14-02 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 177.43 | Completed | No
WO-26-003302 | 2.5 | Bayou | BY-S06-03 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 210.26 | Completed | No
WO-26-003303 | 5.4 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 281.86 | Completed | No
WO-26-003304 | 4.3 | Bayou | BY-S18-04 | Trouble - no power | P2 same day | 2026-04-03 | 2026-04-04 | 2026-04-04 | Internal line |  | 48.33 | Completed | No
WO-26-003305 | 5.7 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 193.38 | Completed | No
WO-26-003306 | 2.6 | Bayou | BY-S09-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-03 | 2026-04-07 | 2026-04-08 | Internal line |  | 20.4 | Completed | No
WO-26-003307 | 2.8 | Bayou | BY-S27-02 | Trouble - partial or voltage | P2 same day | 2026-04-03 | 2026-04-04 | 2026-04-04 | Troubleman |  | 220.81 | Completed | No
WO-26-003308 | 1 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-04-03 | 2026-04-09 | 2026-04-13 | Meter technician |  | 163.8 | Completed | No
WO-26-003309 | 0.9 | Crossroads | CR-S15-01 | Meter exchange | P3 within 10 days | 2026-04-03 | 2026-04-10 | 2026-04-10 | Meter technician |  | 91.9 | Completed | No
WO-26-003310 | 6.9 | Crossroads | CR-S12-01 | Preventive maintenance | P4 planned | 2026-04-03 | 2026-04-29 | 2026-04-30 | Contract line | CT-01 | 392.37 | Completed | No
WO-26-003311 | 7.9 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-04-03 | 2026-05-03 | 2026-05-03 | Internal line |  | 267.67 | Completed | No
WO-26-003312 | 7.2 | Crossroads | CR-S16-03 | Preventive maintenance | P4 planned | 2026-04-03 | 2026-05-14 | 2026-05-14 | Underground crew |  | 23.54 | Completed | No
WO-26-003313 | 7.6 | Crossroads | CR-S12-01 | Preventive maintenance | P4 planned | 2026-04-03 | 2026-05-07 | 2026-05-07 | Contract line | CT-02 | 81.73 | Completed | No
WO-26-003314 | 3.2 | Crossroads | CR-S26-02 | Preventive maintenance | P4 planned | 2026-04-03 | 2026-04-23 | 2026-04-25 | Internal line |  | 142.11 | Completed | No
WO-26-003315 | 2 | Crossroads | CR-S30-06 | Service order - field | P3 within 10 days | 2026-04-03 | 2026-04-09 | 2026-04-11 | Meter technician |  | 2.06 | Completed | No
WO-26-003316 | 1.7 | Crossroads | CR-S13-03 | Service order - field | P2 same day | 2026-04-03 | 2026-04-03 | 2026-04-03 | Meter technician |  | 38.67 | Completed | No
WO-26-003317 | 2 | Crossroads | CR-S07-03 | Service order - field | P3 within 10 days | 2026-04-03 | 2026-04-04 | 2026-04-05 | Meter technician |  | 20.44 | Completed | No
WO-26-003318 | 0.5 | Crossroads | CR-S11-01 | Service order - field | P3 within 10 days | 2026-04-03 | 2026-04-07 | 2026-04-08 | Meter technician |  | 38.55 | Completed | No
WO-26-003319 | 1.9 | Crossroads | CR-S23-04 | Service order - field | P2 same day | 2026-04-03 | 2026-04-03 | 2026-04-03 | Meter technician |  | 17.11 | Completed | No
WO-26-003320 | 13.7 | Crossroads | CR-S22-04 | Transformer replacement | P3 within 10 days | 2026-04-03 | 2026-04-12 | 2026-04-13 | Internal line |  | 11520.37 | Completed | No
WO-26-003321 | 6.1 | Crossroads | CR-S30-05 | Transformer replacement | P2 same day | 2026-04-03 | 2026-04-03 | 2026-04-03 | Internal line |  | 12019.79 | Completed | No
WO-26-003322 | 8.2 | Crossroads | CR-S19-04 | Transformer replacement | P2 same day | 2026-04-03 | 2026-04-04 | 2026-04-04 | Internal line |  | 8488.29 | Completed | No
WO-26-003323 | 5.8 | Crossroads | CR-S03-03 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 34.24 | Completed | No
WO-26-003324 | 4.9 | Crossroads | CR-S17-03 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 147.16 | Completed | No
WO-26-003325 | 2.7 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 246.6 | Completed | No
WO-26-003326 | 5 | Crossroads | CR-S07-02 | Trouble - no power | P1 emergency | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 323.47 | Completed | No
WO-26-003327 | 1.5 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P2 same day | 2026-04-03 | 2026-04-03 | 2026-04-03 | Troubleman |  | 112.48 | Completed | No
WO-26-003328 | 4.1 | Crossroads | CR-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-03 | 2026-04-06 | 2026-04-06 | Troubleman |  | 214.22 | Completed | No
WO-26-003329 | 0.7 | Bayou | BY-S27-03 | Service order - field | P2 same day | 2026-04-04 | 2026-04-04 | 2026-04-04 | Meter technician |  | 14.35 | Completed | No
WO-26-003330 | 1.9 | Bayou | BY-S09-03 | Service order - field | P2 same day | 2026-04-04 | 2026-04-05 | 2026-04-05 | Meter technician |  | 21.14 | Completed | No
WO-26-003331 | 1.9 | Bayou | BY-S23-05 | Service order - field | P2 same day | 2026-04-04 | 2026-04-05 | 2026-04-05 | Meter technician |  | 3.53 | Completed | No
WO-26-003332 | 1.2 | Bayou | BY-S05-02 | Service order - field | P2 same day | 2026-04-04 | 2026-04-04 | 2026-04-04 | Meter technician |  | 8.21 | Completed | No
WO-26-003333 | 3.1 | Bayou | BY-S21-03 | Trouble - no power | P2 same day | 2026-04-04 | 2026-04-04 | 2026-04-04 | Internal line |  | 293.79 | Completed | No
WO-26-003334 | 4.4 | Bayou | BY-S19-03 | Trouble - no power | P2 same day | 2026-04-04 | 2026-04-05 | 2026-04-05 | Troubleman |  | 299.46 | Completed | No
WO-26-003335 | 5.4 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-04-04 | 2026-04-04 | 2026-04-04 | Troubleman |  | 295.77 | Completed | No
WO-26-003336 | 3.1 | Bayou | BY-S24-02 | Trouble - no power | P2 same day | 2026-04-04 | 2026-04-05 | 2026-04-05 | Internal line |  | 282.94 | Completed | No
WO-26-003337 | 11.1 | Crossroads | CR-S06-02 | Corrective maintenance | P2 same day | 2026-04-04 | 2026-04-05 | 2026-04-05 | Internal line |  | 1600.48 | Completed | No
WO-26-003338 | 9.2 | Crossroads | CR-S16-02 | Transformer replacement | P2 same day | 2026-04-04 | 2026-04-05 | 2026-04-05 | Internal line |  | 7477.2 | Completed | No
WO-26-003339 | 9 | Crossroads | CR-S26-06 | Transformer replacement | P1 emergency | 2026-04-04 | 2026-04-04 | 2026-04-04 | Internal line |  | 3874.27 | Completed | No
WO-26-003340 | 11.2 | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-04-04 | 2026-04-04 | 2026-04-04 | Internal line |  | 6930.02 | Completed | No
WO-26-003341 | 2.3 | Crossroads | CR-S08-02 | Trouble - no power | P1 emergency | 2026-04-04 | 2026-04-04 | 2026-04-04 | Troubleman |  | 147.01 | Completed | No
WO-26-003342 | 3.6 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-04-04 | 2026-04-04 | 2026-04-04 | Troubleman |  | 51.79 | Completed | No
WO-26-003343 | 5.3 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-04-04 | 2026-04-04 | 2026-04-04 | Troubleman |  | 36.53 | Completed | No
WO-26-003344 | 19.7 | Bayou | BY-S17-03 | Pole replacement | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Contract line | CT-04 | 3099.19 | Completed | No
WO-26-003345 | 0.6 | Bayou | BY-S23-01 | Service order - field | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Meter technician |  | 3.22 | Completed | No
WO-26-003346 | 1 | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Meter technician |  | 11.26 | Completed | No
WO-26-003347 | 1.3 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Meter technician |  | 10.58 | Completed | No
WO-26-003348 | 3.5 | Bayou | BY-S04-03 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Internal line |  | 64.26 | Completed | No
WO-26-003349 | 4.6 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 176.45 | Completed | No
WO-26-003350 | 4.4 | Bayou | BY-S08-02 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 29.24 | Completed | No
WO-26-003351 | 4.8 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Internal line |  | 145.52 | Completed | No
WO-26-003352 | 2.5 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 207.59 | Completed | No
WO-26-003353 | 1.9 | Bayou | BY-S29-03 | Trouble - partial or voltage | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Troubleman |  | 70.82 | Completed | No
WO-26-003354 | 3.4 | Bayou | BY-S14-01 | Trouble - partial or voltage | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Troubleman |  | 80.34 | Completed | No
WO-26-003355 | 11.6 | Crossroads | CR-S04-02 | Corrective maintenance | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Underground crew |  | 1174.35 | Completed | No
WO-26-003356 | 8.3 | Crossroads | CR-S02-03 | Corrective maintenance | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Internal line |  | 1439.68 | Completed | No
WO-26-003357 | 2 | Crossroads | CR-S19-02 | Service order - field | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Meter technician |  | 28.83 | Completed | No
WO-26-003358 | 8.3 | Crossroads | CR-S05-03 | Transformer replacement | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Internal line |  | 12100.96 | Completed | No
WO-26-003359 | 5.3 | Crossroads | CR-S15-01 | Trouble - no power | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 136.34 | Completed | No
WO-26-003360 | 4.4 | Crossroads | CR-S20-05 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 89.9 | Completed | No
WO-26-003361 | 3.2 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 33.89 | Completed | No
WO-26-003362 |  | Crossroads | CR-S29-02 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 |  | Troubleman |  |  | Cancelled | No
WO-26-003363 | 2.7 | Crossroads | CR-S32-01 | Trouble - no power | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Internal line |  | 241.53 | Completed | No
WO-26-003364 | 3 | Crossroads | CR-S02-03 | Trouble - no power | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 45.54 | Completed | No
WO-26-003365 | 2.6 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Troubleman |  | 300.22 | Completed | No
WO-26-003366 | 2.7 | Crossroads | CR-S22-01 | Trouble - no power | P1 emergency | 2026-04-05 | 2026-04-05 | 2026-04-05 | Internal line |  | 91.25 | Completed | No
WO-26-003367 | 3 | Crossroads | CR-S13-01 | Trouble - partial or voltage | P2 same day | 2026-04-05 | 2026-04-06 | 2026-04-06 | Internal line |  | 201.18 | Completed | No
WO-26-003368 | 2.9 | Crossroads | CR-S03-01 | Trouble - partial or voltage | P2 same day | 2026-04-05 | 2026-04-05 | 2026-04-05 | Internal line |  | 242.9 | Completed | No
WO-26-003369 | 7.5 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-04-06 | 2026-04-09 | 2026-04-09 | Contract line | CT-03 | 2285.1 | Completed | No
WO-26-003370 | 5.3 | Bayou | BY-S16-01 | Corrective maintenance | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Internal line |  | 961.8 | Completed | No
WO-26-003371 | 0.8 | Bayou | BY-S30-02 | Meter exchange | P4 planned | 2026-04-06 | 2026-04-20 | 2026-04-20 | Meter technician |  | 120.77 | Completed | No
WO-26-003372 |  | Bayou | BY-S30-01 | Meter exchange | P3 within 10 days | 2026-04-06 | 2026-04-14 |  | Meter technician |  |  | Cancelled | No
WO-26-003373 | 12.3 | Bayou | BY-S18-05 | New service - small | P4 planned | 2026-04-06 | 2026-06-04 | 2026-06-04 | Contract line | CT-03 | 3539.01 | Completed | No
WO-26-003374 | 15.1 | Bayou | BY-S02-01 | Pole replacement | P3 within 10 days | 2026-04-06 | 2026-04-13 | 2026-04-13 | Internal line |  | 3032.31 | Completed | No
WO-26-003375 | 15.7 | Bayou | BY-S10-01 | Pole replacement | P3 within 10 days | 2026-04-06 | 2026-04-12 | 2026-04-12 | Contract line | CT-03 | 2500.65 | Completed | No
WO-26-003376 | 6 | Bayou | BY-S16-04 | Preventive maintenance | P4 planned | 2026-04-06 | 2026-05-13 | 2026-05-15 | Underground crew |  | 565.54 | Completed | No
WO-26-003377 | 1.1 | Bayou | BY-S09-04 | Service order - field | P3 within 10 days | 2026-04-06 | 2026-04-16 | 2026-04-16 | Meter technician |  | 34.07 | Completed | No
WO-26-003378 | 1.9 | Bayou | BY-S25-04 | Service order - field | P3 within 10 days | 2026-04-06 | 2026-04-10 | 2026-04-10 | Meter technician |  | 3.76 | Completed | No
WO-26-003379 | 1.1 | Bayou | BY-S10-05 | Service order - field | P2 same day | 2026-04-06 | 2026-04-06 | 2026-04-06 | Meter technician |  | 8.52 | Completed | No
WO-26-003380 | 1.3 | Bayou | BY-S08-01 | Service order - field | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Meter technician |  | 34.42 | Completed | No
WO-26-003381 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-06 | 2026-04-14 | 2026-04-18 | Contract line | CT-03 | 444.33 | Completed | No
WO-26-003382 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-06 | 2026-04-12 | 2026-04-16 | Contract line | CT-03 | 259.85 | Completed | No
WO-26-003383 |  | Bayou | BY-S02-01 | Transformer replacement | P3 within 10 days | 2026-04-06 | 2026-04-15 |  | Internal line |  |  | Cancelled | No
WO-26-003384 | 7.4 | Bayou | BY-S06-02 | Transformer replacement | P2 same day | 2026-04-06 | 2026-04-06 | 2026-04-06 | Internal line |  | 9827.82 | Completed | No
WO-26-003385 | 5.4 | Bayou | BY-S11-01 | Trouble - no power | P2 same day | 2026-04-06 | 2026-04-06 | 2026-04-06 | Internal line |  | 65.3 | Completed | No
WO-26-003386 | 3.3 | Bayou | BY-S24-01 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Troubleman |  | 70.62 | Completed | No
WO-26-003387 | 3.8 | Bayou | BY-S10-04 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Troubleman |  | 55.1 | Completed | No
WO-26-003388 | 4.7 | Bayou | BY-S26-02 | Trouble - partial or voltage | P2 same day | 2026-04-06 | 2026-04-06 | 2026-04-06 | Troubleman |  | 102.01 | Completed | No
WO-26-003389 | 11.8 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-04-06 | 2026-04-13 | 2026-04-21 | Underground crew |  | 2264.19 | Completed | No
WO-26-003390 | 0.6 | Crossroads | CR-S29-02 | Meter exchange | P3 within 10 days | 2026-04-06 | 2026-04-12 | 2026-04-13 | Meter technician |  | 69.25 | Completed | No
WO-26-003391 | 0.7 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-04-06 | 2026-04-12 | 2026-04-12 | Meter technician |  | 158.44 | Completed | No
WO-26-003392 | 1.1 | Crossroads | CR-S14-05 | Meter exchange | P3 within 10 days | 2026-04-06 | 2026-04-09 | 2026-04-09 | Meter technician |  | 76.51 | Completed | No
WO-26-003393 | 4.7 | Crossroads | CR-S16-05 | New service - small | P4 planned | 2026-04-06 | 2026-04-19 | 2026-04-20 | Internal line |  | 1540.14 | Completed | No
WO-26-003394 | 4.1 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-04-06 | 2026-05-17 | 2026-05-21 | Internal line |  | 66.71 | Completed | No
WO-26-003395 | 7.8 | Crossroads | CR-S22-01 | Preventive maintenance | P4 planned | 2026-04-06 | 2026-05-21 | 2026-05-21 | Internal line |  | 112.41 | Completed | No
WO-26-003396 | 5.4 | Crossroads | CR-S04-03 | Preventive maintenance | P4 planned | 2026-04-06 | 2026-04-18 | 2026-04-18 | Internal line |  | 361.1 | Completed | No
WO-26-003397 | 0.7 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Meter technician |  | 25.63 | Completed | No
WO-26-003398 | 0.7 | Crossroads | CR-S12-03 | Service order - field | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Meter technician |  | 6.32 | Completed | No
WO-26-003399 | 1.4 | Crossroads | CR-S30-05 | Service order - field | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Meter technician |  | 1.7 | Completed | No
WO-26-003400 | 1.3 | Crossroads | CR-S07-05 | Service order - field | P3 within 10 days | 2026-04-06 | 2026-04-14 | 2026-04-14 | Meter technician |  | 25.98 | Completed | No
WO-26-003401 | 1.9 | Crossroads | CR-S28-02 | Service order - field | P3 within 10 days | 2026-04-06 | 2026-04-07 | 2026-04-07 | Meter technician |  | 25.71 | Completed | No
WO-26-003402 | 0.6 | Crossroads | CR-S03-03 | Service order - field | P3 within 10 days | 2026-04-06 | 2026-04-12 | 2026-04-12 | Meter technician |  | 25.81 | Completed | No
WO-26-003403 | 1.5 | Crossroads | CR-S07-07 | Service order - field | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Meter technician |  | 26.92 | Completed | No
WO-26-003404 | 1.6 | Crossroads | CR-S10-02 | Service order - field | P3 within 10 days | 2026-04-06 | 2026-04-16 | 2026-04-16 | Meter technician |  | 12.82 | Completed | No
WO-26-003405 | 14 | Crossroads | CR-S19-01 | Transformer replacement | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Internal line |  | 4781.84 | Completed | No
WO-26-003406 |  | Crossroads | CR-S06-03 | Transformer replacement | P1 emergency | 2026-04-06 | 2026-04-06 |  | Internal line |  |  | Cancelled | No
WO-26-003407 | 2.9 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Troubleman |  | 25.53 | Completed | No
WO-26-003408 | 4.1 | Crossroads | CR-S16-02 | Trouble - no power | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Internal line |  | 92.73 | Completed | No
WO-26-003409 | 5.8 | Crossroads | CR-S22-01 | Trouble - no power | P2 same day | 2026-04-06 | 2026-04-07 | 2026-04-07 | Troubleman |  | 276.11 | Completed | No
WO-26-003410 | 2.3 | Crossroads | CR-S13-01 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Internal line |  | 262.99 | Completed | No
WO-26-003411 | 5.8 | Crossroads | CR-S27-03 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Internal line |  | 340.86 | Completed | No
WO-26-003412 | 3.7 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Troubleman |  | 241.18 | Completed | No
WO-26-003413 | 2.5 | Crossroads | CR-S10-03 | Trouble - no power | P1 emergency | 2026-04-06 | 2026-04-06 | 2026-04-06 | Internal line |  | 90.84 | Completed | No
WO-26-003414 | 2 | Crossroads | CR-S32-04 | Trouble - partial or voltage | P2 same day | 2026-04-06 | 2026-04-06 | 2026-04-06 | Troubleman |  | 17.7 | Completed | No
WO-26-003415 | 3.6 | Crossroads | CR-S13-04 | Trouble - partial or voltage | P3 within 10 days | 2026-04-06 | 2026-04-16 | 2026-04-16 | Troubleman |  | 201.58 | Completed | No
WO-26-003416 | 4 | Crossroads | CR-S07-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-06 | 2026-04-13 | 2026-04-14 | Troubleman |  | 222.45 | Completed | No
WO-26-003417 | 5.5 | Bayou | BY-S07-05 | Corrective maintenance | P3 within 10 days | 2026-04-07 | 2026-04-08 | 2026-04-12 | Internal line |  | 1743.65 | Completed | No
WO-26-003418 | 10 | Bayou | BY-S24-02 | Corrective maintenance | P4 planned | 2026-04-07 | 2026-05-10 | 2026-05-10 | Internal line |  | 1675.53 | Completed | No
WO-26-003419 | 0.9 | Bayou | BY-S17-02 | Meter exchange | P4 planned | 2026-04-07 | 2026-05-12 | 2026-05-12 | Meter technician |  | 145.85 | Completed | No
WO-26-003420 | 1 | Bayou | BY-S25-02 | Meter exchange | P3 within 10 days | 2026-04-07 | 2026-04-10 | 2026-04-10 | Meter technician |  | 89.69 | Completed | No
WO-26-003421 | 0.5 | Bayou | BY-S15-03 | Meter exchange | P3 within 10 days | 2026-04-07 | 2026-04-14 | 2026-04-14 | Meter technician |  | 68.46 | Completed | No
WO-26-003422 | 0.6 | Bayou | BY-S23-01 | Meter exchange | P4 planned | 2026-04-07 | 2026-05-21 | 2026-05-21 | Meter technician |  | 89.36 | Completed | No
WO-26-003423 | 14.2 | Bayou | BY-S17-04 | Pole replacement | P3 within 10 days | 2026-04-07 | 2026-04-14 | 2026-04-14 | Contract line | CT-04 | 2343.37 | Completed | No
WO-26-003424 | 16.9 | Bayou | BY-S07-01 | Pole replacement | P3 within 10 days | 2026-04-07 | 2026-04-14 | 2026-04-14 | Contract line | CT-04 | 2035.48 | Completed | No
WO-26-003425 | 4 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-04-07 | 2026-05-20 | 2026-05-21 | Contract line | CT-04 | 489.23 | Completed | No
WO-26-003426 | 4.9 | Bayou | BY-S03-01 | Preventive maintenance | P4 planned | 2026-04-07 | 2026-05-20 | 2026-05-22 | Internal line |  | 414.77 | Completed | No
WO-26-003427 | 2.8 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-04-07 | 2026-05-21 | 2026-05-23 | Internal line |  | 329.57 | Completed | No
WO-26-003428 | 7.7 | Bayou | BY-S16-02 | Preventive maintenance | P4 planned | 2026-04-07 | 2026-04-14 | 2026-04-16 | Underground crew |  | 141.75 | Completed | No
WO-26-003429 | 4.5 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-04-07 | 2026-05-04 | 2026-05-06 | Internal line |  | 20.56 | Completed | No
WO-26-003430 | 1 | Bayou | BY-S23-01 | Service order - field | P3 within 10 days | 2026-04-07 | 2026-04-16 | 2026-04-16 | Meter technician |  | 3.45 | Completed | No
WO-26-003431 | 1.9 | Bayou | BY-S12-04 | Service order - field | P3 within 10 days | 2026-04-07 | 2026-04-11 | 2026-04-11 | Meter technician |  | 29.58 | Completed | No
WO-26-003432 | 1.2 | Bayou | BY-S13-05 | Service order - field | P3 within 10 days | 2026-04-07 | 2026-04-13 | 2026-04-14 | Meter technician |  | 2.75 | Completed | No
WO-26-003433 | 1.6 | Bayou | BY-S16-02 | Service order - field | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Meter technician |  | 39.68 | Completed | No
WO-26-003434 | 0.7 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-04-07 | 2026-04-16 | 2026-04-16 | Meter technician |  | 18.05 | Completed | No
WO-26-003435 | 0.5 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-04-07 | 2026-04-08 | 2026-04-08 | Meter technician |  | 16.16 | Completed | No
WO-26-003436 | 1.7 | Bayou | BY-S25-01 | Service order - field | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Meter technician |  | 5.4 | Completed | No
WO-26-003437 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-07 | 2026-04-09 | 2026-04-09 | Contract line | CT-03 | 334.34 | Completed | No
WO-26-003438 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-07 | 2026-04-11 | 2026-04-15 | Contract line | CT-04 | 232.05 | Completed | No
WO-26-003439 | 2.4 | Bayou | BY-S13-06 | Trouble - no power | P2 same day | 2026-04-07 | 2026-04-08 | 2026-04-08 | Internal line |  | 62.72 | Completed | No
WO-26-003440 | 5 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 145.54 | Completed | No
WO-26-003441 | 3.4 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 213.9 | Completed | No
WO-26-003442 | 1.8 | Bayou | BY-S07-02 | Trouble - partial or voltage | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 118.83 | Completed | No
WO-26-003443 | 2.9 | Bayou | BY-S25-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-07 | 2026-04-14 | 2026-04-14 | Troubleman |  | 159.61 | Completed | No
WO-26-003444 | 2.3 | Bayou | BY-S17-01 | Trouble - partial or voltage | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 195.02 | Completed | No
WO-26-003445 | 7.4 | Crossroads | CR-S24-02 | Corrective maintenance | P3 within 10 days | 2026-04-07 | 2026-04-13 | 2026-04-17 | Internal line |  | 1997.63 | Completed | No
WO-26-003446 | 4.8 | Crossroads | CR-S20-01 | Corrective maintenance | P3 within 10 days | 2026-04-07 | 2026-04-17 | 2026-04-19 | Contract line | CT-02 | 681.13 | Completed | No
WO-26-003447 | 0.9 | Crossroads | CR-S01-04 | Meter exchange | P3 within 10 days | 2026-04-07 | 2026-04-09 | 2026-04-09 | Meter technician |  | 156.09 | Completed | No
WO-26-003448 | 0.8 | Crossroads | CR-S10-03 | Meter exchange | P3 within 10 days | 2026-04-07 | 2026-04-11 | 2026-04-11 | Meter technician |  | 86.86 | Completed | No
WO-26-003449 | 0.7 | Crossroads | CR-S16-02 | Meter exchange | P4 planned | 2026-04-07 | 2026-05-10 | 2026-05-10 | Meter technician |  | 142.69 | Completed | No
WO-26-003450 | 1.3 | Crossroads | CR-S19-03 | Meter exchange | P3 within 10 days | 2026-04-07 | 2026-04-09 | 2026-04-17 | Meter technician |  | 81.74 | Completed | No
WO-26-003451 | 0.9 | Crossroads | CR-S12-02 | Meter exchange | P3 within 10 days | 2026-04-07 | 2026-04-16 | 2026-04-16 | Meter technician |  | 98.38 | Completed | No
WO-26-003452 | 0.7 | Crossroads | CR-S20-02 | Meter exchange | P4 planned | 2026-04-07 | 2026-06-01 | 2026-06-01 | Meter technician |  | 80.29 | Completed | No
WO-26-003453 | 0.7 | Crossroads | CR-S13-05 | Meter exchange | P4 planned | 2026-04-07 | 2026-05-28 | 2026-05-29 | Meter technician |  | 171.43 | Completed | No
WO-26-003454 | 1 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-04-07 | 2026-04-17 | 2026-04-18 | Meter technician |  | 3.73 | Completed | No
WO-26-003455 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-07 | 2026-04-08 | 2026-04-08 | Contract line | CT-01 | 373.36 | Completed | No
WO-26-003456 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-07 | 2026-04-09 | 2026-04-10 | Contract line | CT-02 | 344.14 | Completed | No
WO-26-003457 | 3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-07 | 2026-04-14 | 2026-04-14 | Contract line | CT-01 | 384.49 | Completed | No
WO-26-003458 | 10.1 | Crossroads | CR-S03-01 | Transformer replacement | P2 same day | 2026-04-07 | 2026-04-08 | 2026-04-08 | Internal line |  | 3643.49 | Completed | No
WO-26-003459 | 2.9 | Crossroads | CR-S32-02 | Trouble - no power | P1 emergency | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 190.44 | Completed | No
WO-26-003460 | 3.1 | Crossroads | CR-S21-02 | Trouble - no power | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 230.6 | Completed | No
WO-26-003461 | 4 | Crossroads | CR-S28-03 | Trouble - no power | P2 same day | 2026-04-07 | 2026-04-08 | 2026-04-08 | Troubleman |  | 281.49 | Completed | No
WO-26-003462 |  | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-04-07 | 2026-04-07 |  | Troubleman |  |  | Cancelled | No
WO-26-003463 | 3.7 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-04-07 | 2026-04-07 | 2026-04-07 | Internal line |  | 58.44 | Completed | No
WO-26-003464 | 5.8 | Crossroads | CR-S17-03 | Trouble - no power | P1 emergency | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 304.8 | Completed | No
WO-26-003465 | 3.9 | Crossroads | CR-S28-03 | Trouble - no power | P2 same day | 2026-04-07 | 2026-04-07 | 2026-04-07 | Troubleman |  | 279.61 | Completed | No
WO-26-003466 | 2.7 | Crossroads | CR-S18-06 | Trouble - no power | P2 same day | 2026-04-07 | 2026-04-08 | 2026-04-08 | Troubleman |  | 101.45 | Completed | No
WO-26-003467 | 4.3 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-04-07 | 2026-04-07 | 2026-04-07 | Internal line |  | 223.58 | Completed | No
WO-26-003468 | 4.9 | Crossroads | CR-S21-03 | Trouble - partial or voltage | P3 within 10 days | 2026-04-07 | 2026-04-16 | 2026-04-16 | Troubleman |  | 113.51 | Completed | No
WO-26-003469 | 3.5 | Crossroads | CR-S30-07 | Trouble - partial or voltage | P3 within 10 days | 2026-04-07 | 2026-04-17 | 2026-04-17 | Internal line |  | 177.03 | Completed | No
WO-26-003470 | 3.7 | Crossroads | CR-S30-05 | Trouble - partial or voltage | P3 within 10 days | 2026-04-07 | 2026-04-13 | 2026-04-17 | Troubleman |  | 174.55 | Completed | No
WO-26-003471 | 10.7 | Bayou | BY-S26-02 | Corrective maintenance | P2 same day | 2026-04-08 | 2026-04-08 | 2026-04-08 | Internal line |  | 1162.97 | Completed | No
WO-26-003472 | 7.1 | Bayou | BY-S07-03 | Corrective maintenance | P3 within 10 days | 2026-04-08 | 2026-04-16 | 2026-04-20 | Underground crew |  | 2015.5 | Completed | No
WO-26-003473 | 5.3 | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-04-08 | 2026-04-14 | 2026-04-15 | Internal line |  | 1628.19 | Completed | No
WO-26-003474 | 11.7 | Bayou | BY-S05-03 | Corrective maintenance | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Internal line |  | 1921.77 | Completed | No
WO-26-003475 | 4.1 | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-04-08 | 2026-04-16 | 2026-04-17 | Internal line |  | 482.5 | Completed | No
WO-26-003476 | 5.9 | Bayou | BY-S20-03 | Corrective maintenance | P3 within 10 days | 2026-04-08 | 2026-04-18 | 2026-04-18 | Contract line | CT-03 | 1065.04 | Completed | No
WO-26-003477 | 0.8 | Bayou | BY-S19-04 | Meter exchange | P3 within 10 days | 2026-04-08 | 2026-04-11 | 2026-04-15 | Meter technician |  | 76.77 | Completed | No
WO-26-003478 | 0.5 | Bayou | BY-S15-05 | Meter exchange | P3 within 10 days | 2026-04-08 | 2026-04-12 | 2026-04-12 | Meter technician |  | 176.92 | Completed | No
WO-26-003479 | 1 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-04-08 | 2026-04-14 | 2026-04-14 | Meter technician |  | 73.45 | Completed | No
WO-26-003480 | 0.6 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-04-08 | 2026-04-12 | 2026-04-14 | Meter technician |  | 81.56 | Completed | No
WO-26-003481 |  | Bayou | BY-S16-02 | New service - small | P4 planned | 2026-04-08 | 2026-04-30 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-003482 | 21.3 | Bayou | BY-S05-01 | Pole replacement | P4 planned | 2026-04-08 | 2026-05-02 | 2026-05-02 | Contract line | CT-03 | 1993.4 | Completed | No
WO-26-003483 | 6.5 | Bayou | BY-S04-02 | Preventive maintenance | P4 planned | 2026-04-08 | 2026-05-10 | 2026-05-12 | Underground crew |  | 223.71 | Completed | No
WO-26-003484 | 0.9 | Bayou | BY-S26-03 | Service order - field | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Meter technician |  | 1.45 | Completed | No
WO-26-003485 | 0.9 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-04-08 | 2026-04-11 | 2026-04-12 | Meter technician |  | 29.31 | Completed | No
WO-26-003486 | 1.5 | Bayou | BY-S25-04 | Service order - field | P2 same day | 2026-04-08 | 2026-04-08 | 2026-04-08 | Meter technician |  | 32.07 | Completed | No
WO-26-003487 | 1.4 | Bayou | BY-S15-02 | Service order - field | P3 within 10 days | 2026-04-08 | 2026-04-12 | 2026-04-12 | Meter technician |  | 32.95 | Completed | No
WO-26-003488 | 0.7 | Bayou | BY-S21-01 | Service order - field | P3 within 10 days | 2026-04-08 | 2026-04-13 | 2026-04-14 | Meter technician |  | 0.33 | Completed | No
WO-26-003489 | 0.7 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-04-08 | 2026-04-08 | 2026-04-08 | Meter technician |  | 13.69 | Completed | No
WO-26-003490 | 1.4 | Bayou | BY-S04-03 | Service order - field | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Meter technician |  | 23.33 | Completed | No
WO-26-003491 | 0.9 | Bayou | BY-S18-07 | Service order - field | P3 within 10 days | 2026-04-08 | 2026-04-18 | 2026-04-18 | Meter technician |  | 25.85 | Completed | No
WO-26-003492 | 1.7 | Bayou | BY-S19-03 | Service order - field | P3 within 10 days | 2026-04-08 | 2026-04-15 | 2026-04-16 | Meter technician |  | 18.56 | Completed | No
WO-26-003493 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-08 | 2026-04-14 | 2026-04-14 | Contract line | CT-03 | 434.35 | Completed | No
WO-26-003494 | 2.3 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-04-08 | 2026-04-08 | 2026-04-08 | Troubleman |  | 206.47 | Completed | No
WO-26-003495 | 3.1 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-04-08 | 2026-04-08 | 2026-04-08 | Internal line |  | 85.93 | Completed | No
WO-26-003496 | 5.5 | Bayou | BY-S01-02 | Trouble - no power | P1 emergency | 2026-04-08 | 2026-04-08 | 2026-04-08 | Troubleman |  | 90.46 | Completed | No
WO-26-003497 | 4.4 | Bayou | BY-S07-01 | Trouble - no power | P1 emergency | 2026-04-08 | 2026-04-08 | 2026-04-08 | Troubleman |  | 308.62 | Completed | No
WO-26-003498 | 3.3 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-04-08 | 2026-04-08 | 2026-04-08 | Troubleman |  | 6.26 | Completed | No
WO-26-003499 | 2.3 | Bayou | BY-S17-04 | Trouble - partial or voltage | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Troubleman |  | 36.91 | Completed | No
WO-26-003500 | 5.6 | Crossroads | CR-S14-02 | Corrective maintenance | P3 within 10 days | 2026-04-08 | 2026-04-17 | 2026-04-21 | Internal line |  | 2293.89 | Completed | No
WO-26-003501 | 11.9 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-04-08 | 2026-04-13 | 2026-04-13 | Contract line | CT-02 | 1319.5 | Completed | No
WO-26-003502 | 1.4 | Crossroads | CR-S27-02 | Meter exchange | P3 within 10 days | 2026-04-08 | 2026-04-17 | 2026-04-25 | Meter technician |  | 131.44 | Completed | No
WO-26-003503 | 3.4 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-04-08 | 2026-04-21 | 2026-04-21 | Underground crew |  | 140.99 | Completed | No
WO-26-003504 | 7.5 | Crossroads | CR-S32-05 | Preventive maintenance | P4 planned | 2026-04-08 | 2026-04-29 | 2026-04-30 | Contract line | CT-01 | 116.75 | Completed | No
WO-26-003505 | 7.2 | Crossroads | CR-S30-02 | Preventive maintenance | P4 planned | 2026-04-08 | 2026-05-12 | 2026-05-12 | Contract line | CT-01 | 287.94 | Completed | No
WO-26-003506 | 1 | Crossroads | CR-S23-04 | Service order - field | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Meter technician |  | 19.95 | Completed | No
WO-26-003507 | 0.6 | Crossroads | CR-S17-03 | Service order - field | P3 within 10 days | 2026-04-08 | 2026-04-17 | 2026-04-17 | Meter technician |  | 10.59 | Completed | No
WO-26-003508 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-08 | 2026-04-12 | 2026-04-12 | Contract line | CT-02 | 265.27 | Completed | No
WO-26-003509 | 13.7 | Crossroads | CR-S25-05 | Transformer replacement | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Contract line | CT-01 | 10351.26 | Completed | No
WO-26-003510 | 7.3 | Crossroads | CR-S27-02 | Transformer replacement | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Internal line |  | 9649.3 | Completed | No
WO-26-003511 | 5.8 | Crossroads | CR-S09-01 | Trouble - no power | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Troubleman |  | 234.53 | Completed | No
WO-26-003512 | 2.3 | Crossroads | CR-S26-02 | Trouble - no power | P1 emergency | 2026-04-08 | 2026-04-08 | 2026-04-08 | Internal line |  | 181.22 | Completed | No
WO-26-003513 | 4.6 | Crossroads | CR-S16-06 | Trouble - no power | P1 emergency | 2026-04-08 | 2026-04-08 | 2026-04-08 | Troubleman |  | 337.16 | Completed | No
WO-26-003514 | 4.1 | Crossroads | CR-S28-03 | Trouble - partial or voltage | P2 same day | 2026-04-08 | 2026-04-09 | 2026-04-09 | Troubleman |  | 99.91 | Completed | No
WO-26-003515 | 5.2 | Bayou | BY-S15-05 | Corrective maintenance | P4 planned | 2026-04-09 | 2026-04-27 | 2026-04-29 | Internal line |  | 1216.83 | Completed | No
WO-26-003516 | 6.6 | Bayou | BY-S04-01 | Corrective maintenance | P3 within 10 days | 2026-04-09 | 2026-04-15 | 2026-04-15 | Contract line | CT-04 | 1749.02 | Completed | No
WO-26-003517 | 1.3 | Bayou | BY-S03-03 | Meter exchange | P3 within 10 days | 2026-04-09 | 2026-04-10 | 2026-04-10 | Meter technician |  | 176.91 | Completed | No
WO-26-003518 | 1 | Bayou | BY-S21-02 | Meter exchange | P4 planned | 2026-04-09 | 2026-04-24 | 2026-04-24 | Meter technician |  | 172.33 | Completed | No
WO-26-003519 | 21.9 | Bayou | BY-S23-01 | Pole replacement | P4 planned | 2026-04-09 | 2026-04-22 | 2026-04-22 | Contract line | CT-03 | 2595.91 | Completed | No
WO-26-003520 | 2.5 | Bayou | BY-S16-03 | Preventive maintenance | P4 planned | 2026-04-09 | 2026-05-19 | 2026-05-19 | Internal line |  | 272.24 | Completed | No
WO-26-003521 | 1.8 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Meter technician |  | 39.1 | Completed | No
WO-26-003522 | 1.7 | Bayou | BY-S27-04 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-19 | 2026-04-19 | Meter technician |  | 19.8 | Completed | No
WO-26-003523 | 1.4 | Bayou | BY-S29-03 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-15 | 2026-04-15 | Meter technician |  | 27.07 | Completed | No
WO-26-003524 | 1.3 | Bayou | BY-S18-05 | Service order - field | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Meter technician |  | 28.12 | Completed | No
WO-26-003525 | 1.9 | Bayou | BY-S23-03 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-16 | 2026-04-16 | Meter technician |  | 2.89 | Completed | No
WO-26-003526 | 1.7 | Bayou | BY-S16-02 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-17 | 2026-04-17 | Meter technician |  | 1.57 | Completed | No
WO-26-003527 | 1.2 | Bayou | BY-S28-03 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-13 | 2026-04-14 | Meter technician |  | 2.59 | Completed | No
WO-26-003528 | 1.7 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-04-09 | 2026-04-09 | 2026-04-09 | Meter technician |  | 9.54 | Completed | No
WO-26-003529 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-09 | 2026-04-13 | 2026-04-14 | Contract line | CT-03 | 238.32 | Completed | No
WO-26-003530 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-09 | 2026-04-10 | 2026-04-11 | Internal line |  | 297.99 | Completed | No
WO-26-003531 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-09 | 2026-04-17 | 2026-04-18 | Internal line |  | 377.76 | Completed | No
WO-26-003532 | 9.5 | Bayou | BY-S11-02 | Transformer replacement | P2 same day | 2026-04-09 | 2026-04-09 | 2026-04-09 | Internal line |  | 3075.49 | Completed | No
WO-26-003533 | 5.2 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Internal line |  | 186.71 | Completed | No
WO-26-003534 | 5 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 310.12 | Completed | No
WO-26-003535 | 5.5 | Bayou | BY-S09-02 | Trouble - no power | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Troubleman |  | 68.79 | Completed | No
WO-26-003536 | 3.8 | Bayou | BY-S12-04 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 106.74 | Completed | No
WO-26-003537 | 3.8 | Bayou | BY-S16-01 | Trouble - no power | P2 same day | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 206.07 | Completed | No
WO-26-003538 | 3.3 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 314.15 | Completed | No
WO-26-003539 |  | Bayou | BY-S15-01 | Trouble - partial or voltage | P2 same day | 2026-04-09 | 2026-04-09 |  | Troubleman |  |  | Cancelled | No
WO-26-003540 | 4.6 | Bayou | BY-S21-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-09 | 2026-04-17 | 2026-04-25 | Internal line |  | 117.82 | Completed | No
WO-26-003541 | 3.3 | Crossroads | CR-S17-03 | Corrective maintenance | P3 within 10 days | 2026-04-09 | 2026-04-13 | 2026-04-13 | Contract line | CT-02 | 629.26 | Completed | No
WO-26-003542 | 0.6 | Crossroads | CR-S01-03 | Meter exchange | P3 within 10 days | 2026-04-09 | 2026-04-17 | 2026-04-17 | Meter technician |  | 124.21 | Completed | No
WO-26-003543 | 0.7 | Crossroads | CR-S25-04 | Meter exchange | P4 planned | 2026-04-09 | 2026-05-18 | 2026-05-19 | Meter technician |  | 102.33 | Completed | No
WO-26-003544 | 1.1 | Crossroads | CR-S05-02 | Meter exchange | P3 within 10 days | 2026-04-09 | 2026-04-14 | 2026-04-15 | Meter technician |  | 100.06 | Completed | No
WO-26-003545 | 1.3 | Crossroads | CR-S14-03 | Meter exchange | P4 planned | 2026-04-09 | 2026-04-28 | 2026-05-02 | Meter technician |  | 179.47 | Completed | No
WO-26-003546 | 14.1 | Crossroads | CR-S26-04 | New service - small | P3 within 10 days | 2026-04-09 | 2026-04-14 | 2026-04-16 | Internal line |  | 1134.89 | Completed | No
WO-26-003547 | 6.7 | Crossroads | CR-S16-01 | New service - small | P3 within 10 days | 2026-04-09 | 2026-04-11 | 2026-04-11 | Underground crew |  | 1442.64 | Completed | No
WO-26-003548 | 14 | Crossroads | CR-S30-07 | Pole replacement | P4 planned | 2026-04-09 | 2026-05-27 | 2026-05-27 | Internal line |  | 1253.62 | Completed | No
WO-26-003549 | 1.5 | Crossroads | CR-S23-01 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-13 | 2026-04-13 | Meter technician |  | 1.48 | Completed | No
WO-26-003550 | 1.6 | Crossroads | CR-S02-01 | Service order - field | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Meter technician |  | 22.17 | Completed | No
WO-26-003551 | 1.3 | Crossroads | CR-S19-02 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-12 | 2026-04-13 | Meter technician |  | 9.34 | Completed | No
WO-26-003552 | 1.8 | Crossroads | CR-S13-06 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-15 | 2026-04-15 | Meter technician |  | 37.55 | Completed | No
WO-26-003553 | 1.7 | Crossroads | CR-S07-02 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-10 | 2026-04-11 | Meter technician |  | 38.59 | Completed | No
WO-26-003554 | 1.5 | Crossroads | CR-S30-07 | Service order - field | P3 within 10 days | 2026-04-09 | 2026-04-13 | 2026-04-17 | Meter technician |  | 34.69 | Completed | No
WO-26-003555 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-09 | 2026-04-18 | 2026-04-19 | Contract line | CT-02 | 87.69 | Completed | No
WO-26-003556 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-09 | 2026-04-18 | 2026-04-26 | Contract line | CT-01 | 333.78 | Completed | No
WO-26-003557 | 4.3 | Crossroads | CR-S06-01 | Trouble - no power | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Troubleman |  | 114.43 | Completed | No
WO-26-003558 | 3 | Crossroads | CR-S09-04 | Trouble - no power | P2 same day | 2026-04-09 | 2026-04-09 | 2026-04-09 | Internal line |  | 288.23 | Completed | No
WO-26-003559 | 3.6 | Crossroads | CR-S02-01 | Trouble - no power | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Troubleman |  | 151.57 | Completed | No
WO-26-003560 | 2.2 | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 46.85 | Completed | No
WO-26-003561 | 5 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Internal line |  | 299.46 | Completed | No
WO-26-003562 | 2.6 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 189.7 | Completed | No
WO-26-003563 | 2.3 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 337.6 | Completed | No
WO-26-003564 | 4.5 | Crossroads | CR-S13-05 | Trouble - no power | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Troubleman |  | 238.59 | Completed | No
WO-26-003565 | 4.6 | Crossroads | CR-S02-03 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Internal line |  | 95.83 | Completed | No
WO-26-003566 | 5.8 | Crossroads | CR-S07-07 | Trouble - no power | P1 emergency | 2026-04-09 | 2026-04-09 | 2026-04-09 | Troubleman |  | 20.88 | Completed | No
WO-26-003567 | 2.9 | Crossroads | CR-S07-05 | Trouble - partial or voltage | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Troubleman |  | 133.82 | Completed | No
WO-26-003568 | 3.8 | Crossroads | CR-S24-03 | Trouble - partial or voltage | P2 same day | 2026-04-09 | 2026-04-10 | 2026-04-10 | Troubleman |  | 120.58 | Completed | No
WO-26-003569 | 9.3 | Bayou | BY-S18-01 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-17 | 2026-04-18 | Internal line |  | 1168.5 | Completed | No
WO-26-003570 | 4.1 | Bayou | BY-S16-01 | Corrective maintenance | P2 same day | 2026-04-10 | 2026-04-10 | 2026-04-10 | Contract line | CT-04 | 1727.49 | Completed | No
WO-26-003571 | 10 | Bayou | BY-S30-01 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-15 | 2026-04-23 | Contract line | CT-03 | 1941.16 | Completed | No
WO-26-003572 | 10.5 | Bayou | BY-S07-06 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-13 | 2026-04-13 | Underground crew |  | 2007.82 | Completed | No
WO-26-003573 | 1 | Bayou | BY-S24-03 | Meter exchange | P4 planned | 2026-04-10 | 2026-04-21 | 2026-04-22 | Meter technician |  | 75.77 | Completed | No
WO-26-003574 | 1.1 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-04-10 | 2026-04-17 | 2026-04-21 | Meter technician |  | 67.32 | Completed | No
WO-26-003575 | 0.8 | Bayou | BY-S03-01 | Meter exchange | P4 planned | 2026-04-10 | 2026-06-06 | 2026-06-06 | Meter technician |  | 74.64 | Completed | No
WO-26-003576 | 1.2 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-04-10 | 2026-04-12 | 2026-04-12 | Meter technician |  | 169.27 | Completed | No
WO-26-003577 | 22.3 | Bayou | BY-S12-03 | Pole replacement | P3 within 10 days | 2026-04-10 | 2026-04-12 | 2026-04-13 | Contract line | CT-04 | 1772.45 | Completed | No
WO-26-003578 | 2.3 | Bayou | BY-S19-04 | Preventive maintenance | P4 planned | 2026-04-10 | 2026-04-23 | 2026-04-25 | Internal line |  | 11.79 | Completed | No
WO-26-003579 | 3.6 | Bayou | BY-S07-03 | Preventive maintenance | P4 planned | 2026-04-10 | 2026-06-02 | 2026-06-06 | Contract line | CT-04 | 520.99 | Completed | No
WO-26-003580 | 5.3 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-04-10 | 2026-06-08 | 2026-06-08 | Contract line | CT-04 | 45.23 | Completed | No
WO-26-003581 | 0.9 | Bayou | BY-S16-04 | Service order - field | P3 within 10 days | 2026-04-10 | 2026-04-15 | 2026-04-17 | Meter technician |  | 38.94 | Completed | No
WO-26-003582 | 1 | Bayou | BY-S15-01 | Service order - field | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Meter technician |  | 15.08 | Completed | No
WO-26-003583 | 2 | Bayou | BY-S18-02 | Service order - field | P2 same day | 2026-04-10 | 2026-04-10 | 2026-04-10 | Meter technician |  | 9.7 | Completed | No
WO-26-003584 | 1.2 | Bayou | BY-S07-06 | Service order - field | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Meter technician |  | 34.08 | Completed | No
WO-26-003585 | 1.2 | Bayou | BY-S20-03 | Service order - field | P3 within 10 days | 2026-04-10 | 2026-04-12 | 2026-04-12 | Meter technician |  | 0.96 | Completed | No
WO-26-003586 | 1.6 | Bayou |  | Streetlight | P4 planned | 2026-04-10 | 2026-05-06 | 2026-05-10 | Internal line |  | 230.03 | Completed | No
WO-26-003587 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-10 | 2026-04-16 | 2026-04-16 | Internal line |  | 149.76 | Completed | No
WO-26-003588 | 13.6 | Bayou | BY-S14-03 | Transformer replacement | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Contract line | CT-04 | 9302.97 | Completed | No
WO-26-003589 | 2.3 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-04-10 | 2026-04-10 | 2026-04-10 | Troubleman |  | 160.85 | Completed | No
WO-26-003590 | 5.6 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-04-10 | 2026-04-10 | 2026-04-10 | Troubleman |  | 95.11 | Completed | No
WO-26-003591 | 2.2 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Troubleman |  | 39.74 | Completed | No
WO-26-003592 | 4 | Bayou | BY-S16-01 | Trouble - partial or voltage | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Troubleman |  | 51.56 | Completed | No
WO-26-003593 | 10.8 | Crossroads | CR-S25-01 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-11 | 2026-04-11 | Underground crew |  | 1627.03 | Completed | No
WO-26-003594 | 3.4 | Crossroads | CR-S24-01 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-12 | 2026-04-16 | Contract line | CT-02 | 2311.05 | Completed | No
WO-26-003595 | 11.7 | Crossroads | CR-S21-02 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-18 | 2026-04-19 | Underground crew |  | 87.06 | Completed | No
WO-26-003596 | 4.3 | Crossroads | CR-S02-01 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-13 | 2026-04-14 | Internal line |  | 308.33 | Completed | No
WO-26-003597 | 10 | Crossroads | CR-S28-01 | Corrective maintenance | P3 within 10 days | 2026-04-10 | 2026-04-18 | 2026-04-20 | Contract line | CT-02 | 1213.74 | Completed | No
WO-26-003598 | 0.7 | Crossroads | CR-S14-04 | Meter exchange | P3 within 10 days | 2026-04-10 | 2026-04-19 | 2026-04-19 | Meter technician |  | 140.63 | Completed | No
WO-26-003599 | 1.4 | Crossroads | CR-S16-04 | Meter exchange | P3 within 10 days | 2026-04-10 | 2026-04-15 | 2026-04-15 | Meter technician |  | 88.68 | Completed | No
WO-26-003600 | 1.1 | Crossroads | CR-S08-06 | Meter exchange | P4 planned | 2026-04-10 | 2026-04-20 | 2026-04-20 | Meter technician |  | 142.3 | Completed | No
WO-26-003601 | 0.6 | Crossroads | CR-S30-05 | Meter exchange | P3 within 10 days | 2026-04-10 | 2026-04-20 | 2026-04-20 | Meter technician |  | 97.98 | Completed | No
WO-26-003602 | 0.7 | Crossroads | CR-S09-01 | Meter exchange | P4 planned | 2026-04-10 | 2026-05-30 | 2026-05-31 | Meter technician |  | 122.29 | Completed | No
WO-26-003603 | 9.7 | Crossroads | CR-S08-06 | New service - small | P3 within 10 days | 2026-04-10 | 2026-04-16 | 2026-04-16 | Underground crew |  | 1967.2 | Completed | No
WO-26-003604 | 5.6 | Crossroads | CR-S09-04 | Preventive maintenance | P4 planned | 2026-04-10 | 2026-05-16 | 2026-05-16 | Internal line |  | 247.51 | Completed | No
WO-26-003605 | 1.6 | Crossroads | CR-S31-02 | Service order - field | P3 within 10 days | 2026-04-10 | 2026-04-17 | 2026-04-21 | Meter technician |  | 24.26 | Completed | No
WO-26-003606 | 0.9 | Crossroads | CR-S23-02 | Service order - field | P3 within 10 days | 2026-04-10 | 2026-04-13 | 2026-04-13 | Meter technician |  | 37.3 | Completed | No
WO-26-003607 | 0.9 | Crossroads | CR-S03-01 | Service order - field | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Meter technician |  | 15.98 | Completed | No
WO-26-003608 | 1.7 | Crossroads | CR-S25-04 | Service order - field | P2 same day | 2026-04-10 | 2026-04-10 | 2026-04-10 | Meter technician |  | 20.53 | Completed | No
WO-26-003609 | 1.6 | Crossroads |  | Streetlight | P4 planned | 2026-04-10 | 2026-05-15 | 2026-05-15 | Contract line | CT-01 | 153.9 | Completed | No
WO-26-003610 | 1.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-10 | 2026-04-12 | 2026-04-16 | Contract line | CT-02 | 340.95 | Completed | No
WO-26-003611 | 3.8 | Crossroads | CR-S24-03 | Trouble - no power | P1 emergency | 2026-04-10 | 2026-04-10 | 2026-04-10 | Internal line |  | 73.72 | Completed | No
WO-26-003612 | 3.4 | Crossroads | CR-S13-02 | Trouble - no power | P2 same day | 2026-04-10 | 2026-04-11 | 2026-04-11 | Troubleman |  | 230.64 | Completed | No
WO-26-003613 | 1.6 | Crossroads | CR-S08-01 | Trouble - partial or voltage | P2 same day | 2026-04-10 | 2026-04-10 | 2026-04-10 | Troubleman |  | 178.4 | Completed | No
WO-26-003614 | 3.8 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-10 | 2026-04-14 | 2026-04-14 | Internal line |  | 215.12 | Completed | No
WO-26-003615 | 6.4 | Bayou | BY-S06-02 | Corrective maintenance | P2 same day | 2026-04-11 | 2026-04-11 | 2026-04-11 | Internal line |  | 381.33 | Completed | No
WO-26-003616 | 1.5 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-04-11 | 2026-04-11 | 2026-04-11 | Meter technician |  | 38.89 | Completed | No
WO-26-003617 | 0.7 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-04-11 | 2026-04-12 | 2026-04-12 | Meter technician |  | 33.52 | Completed | No
WO-26-003618 | 11.6 | Bayou | BY-S03-02 | Transformer replacement | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Contract line | CT-03 | 9394.44 | Completed | No
WO-26-003619 | 3.8 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 9.54 | Completed | No
WO-26-003620 | 2.5 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 275.93 | Completed | No
WO-26-003621 | 5.8 | Crossroads | CR-S28-01 | Corrective maintenance | P2 same day | 2026-04-11 | 2026-04-12 | 2026-04-12 | Contract line | CT-02 | 968.47 | Completed | No
WO-26-003622 | 0.8 | Crossroads | CR-S29-02 | Service order - field | P2 same day | 2026-04-11 | 2026-04-11 | 2026-04-11 | Meter technician |  | 39.98 | Completed | No
WO-26-003623 | 1 | Crossroads | CR-S12-02 | Service order - field | P2 same day | 2026-04-11 | 2026-04-12 | 2026-04-12 | Meter technician |  | 34.28 | Completed | No
WO-26-003624 | 3.8 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 316.64 | Completed | No
WO-26-003625 | 3.5 | Crossroads | CR-S04-05 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 325.73 | Completed | No
WO-26-003626 | 5.5 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 99.5 | Completed | No
WO-26-003627 | 2.5 | Crossroads | CR-S29-02 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 311.62 | Completed | No
WO-26-003628 | 2.3 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 28.02 | Completed | No
WO-26-003629 | 4.2 | Crossroads | CR-S24-03 | Trouble - no power | P2 same day | 2026-04-11 | 2026-04-12 | 2026-04-12 | Internal line |  | 17.7 | Completed | No
WO-26-003630 | 2.4 | Crossroads | CR-S15-02 | Trouble - no power | P2 same day | 2026-04-11 | 2026-04-11 | 2026-04-11 | Troubleman |  | 288.59 | Completed | No
WO-26-003631 | 0.7 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Meter technician |  | 2.84 | Completed | No
WO-26-003632 | 1.6 | Bayou | BY-S06-02 | Service order - field | P2 same day | 2026-04-12 | 2026-04-13 | 2026-04-13 | Meter technician |  | 17.2 | Completed | No
WO-26-003633 | 13.8 | Bayou | BY-S16-06 | Transformer replacement | P1 emergency | 2026-04-12 | 2026-04-12 | 2026-04-12 | Internal line |  | 3108.08 | Completed | No
WO-26-003634 | 11.8 | Bayou | BY-S04-03 | Transformer replacement | P1 emergency | 2026-04-12 | 2026-04-12 | 2026-04-12 | Contract line | CT-03 | 11843.28 | Completed | No
WO-26-003635 | 2.5 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-04-12 | 2026-04-12 | 2026-04-12 | Troubleman |  | 298.55 | Completed | No
WO-26-003636 | 3.6 | Bayou | BY-S11-02 | Trouble - no power | P1 emergency | 2026-04-12 | 2026-04-12 | 2026-04-12 | Troubleman |  | 272.64 | Completed | No
WO-26-003637 | 2.8 | Bayou | BY-S23-03 | Trouble - partial or voltage | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Troubleman |  | 244.1 | Completed | No
WO-26-003638 | 18.9 | Crossroads | CR-S25-05 | Pole replacement | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Internal line |  | 2957.73 | Completed | No
WO-26-003639 | 1.7 | Crossroads | CR-S22-01 | Service order - field | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Meter technician |  | 32.5 | Completed | No
WO-26-003640 | 6.1 | Crossroads | CR-S06-02 | Transformer replacement | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Internal line |  | 5613.32 | Completed | No
WO-26-003641 | 10 | Crossroads | CR-S16-01 | Transformer replacement | P1 emergency | 2026-04-12 | 2026-04-12 | 2026-04-12 | Contract line | CT-02 | 3213.52 | Completed | No
WO-26-003642 | 3.8 | Crossroads | CR-S29-03 | Trouble - no power | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Troubleman |  | 150.31 | Completed | No
WO-26-003643 | 3.4 | Crossroads | CR-S10-02 | Trouble - no power | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Troubleman |  | 189.38 | Completed | No
WO-26-003644 | 5 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-04-12 | 2026-04-12 | 2026-04-12 | Troubleman |  | 18.05 | Completed | No
WO-26-003645 | 5.1 | Crossroads | CR-S32-04 | Trouble - no power | P2 same day | 2026-04-12 | 2026-04-12 | 2026-04-12 | Internal line |  | 252.11 | Completed | No
WO-26-003646 | 10.8 | Bayou | BY-S11-01 | Corrective maintenance | P3 within 10 days | 2026-04-13 | 2026-04-22 | 2026-04-23 | Underground crew |  | 1174.48 | Completed | No
WO-26-003647 | 0.9 | Bayou | BY-S29-01 | Meter exchange | P3 within 10 days | 2026-04-13 | 2026-04-23 | 2026-04-24 | Meter technician |  | 118.24 | Completed | No
WO-26-003648 | 1.2 | Bayou | BY-S11-01 | Meter exchange | P3 within 10 days | 2026-04-13 | 2026-04-23 | 2026-05-01 | Meter technician |  | 90.96 | Completed | No
WO-26-003649 | 1 | Bayou | BY-S06-03 | Meter exchange | P4 planned | 2026-04-13 | 2026-04-30 | 2026-04-30 | Meter technician |  | 105.78 | Completed | No
WO-26-003650 | 7.1 | Bayou | BY-S25-04 | New service - small | P4 planned | 2026-04-13 | 2026-05-15 | 2026-05-17 | Contract line | CT-03 | 992 | Completed | No
WO-26-003651 | 7.5 | Bayou | BY-S30-01 | Preventive maintenance | P4 planned | 2026-04-13 | 2026-06-10 | 2026-06-10 | Internal line |  | 411.86 | Completed | No
WO-26-003652 | 0.8 | Bayou | BY-S06-01 | Service order - field | P3 within 10 days | 2026-04-13 | 2026-04-20 | 2026-04-24 | Meter technician |  | 13.5 | Completed | No
WO-26-003653 | 1.1 | Bayou | BY-S17-02 | Service order - field | P2 same day | 2026-04-13 | 2026-04-13 | 2026-04-13 | Meter technician |  | 19.92 | Completed | No
WO-26-003654 | 1.7 | Bayou | BY-S25-05 | Service order - field | P2 same day | 2026-04-13 | 2026-04-13 | 2026-04-13 | Meter technician |  | 22.7 | Completed | No
WO-26-003655 | 8.8 | Bayou | BY-S04-01 | Transformer replacement | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Contract line | CT-03 | 5183.19 | Completed | No
WO-26-003656 | 5.8 | Bayou | BY-S07-06 | Trouble - no power | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 321.68 | Completed | No
WO-26-003657 | 2.5 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Internal line |  | 170.74 | Completed | No
WO-26-003658 | 2.5 | Bayou | BY-S12-04 | Trouble - no power | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 232.49 | Completed | No
WO-26-003659 | 7.2 | Crossroads | CR-S28-02 | Corrective maintenance | P3 within 10 days | 2026-04-13 | 2026-04-18 | 2026-04-22 | Contract line | CT-02 | 723.34 | Completed | No
WO-26-003660 | 9.2 | Crossroads | CR-S26-02 | Corrective maintenance | P3 within 10 days | 2026-04-13 | 2026-04-14 | 2026-04-14 | Internal line |  | 406.79 | Completed | No
WO-26-003661 | 6.8 | Crossroads | CR-S10-03 | Corrective maintenance | P3 within 10 days | 2026-04-13 | 2026-04-22 | 2026-04-30 | Underground crew |  | 849.1 | Completed | No
WO-26-003662 | 3.9 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-04-13 | 2026-04-14 | 2026-04-14 | Underground crew |  | 2381.92 | Completed | No
WO-26-003663 | 8.9 | Crossroads | CR-S16-01 | Corrective maintenance | P2 same day | 2026-04-13 | 2026-04-13 | 2026-04-13 | Underground crew |  | 709.54 | Completed | No
WO-26-003664 | 1.1 | Crossroads | CR-S14-02 | Meter exchange | P4 planned | 2026-04-13 | 2026-05-30 | 2026-05-31 | Meter technician |  | 113.07 | Completed | No
WO-26-003665 | 14.9 | Crossroads | CR-S29-01 | New service - small | P4 planned | 2026-04-13 | 2026-05-17 | 2026-05-17 | Contract line | CT-02 | 2137.63 | Completed | No
WO-26-003666 | 2.8 | Crossroads | CR-S23-02 | Preventive maintenance | P4 planned | 2026-04-13 | 2026-05-14 | 2026-05-14 | Underground crew |  | 552.49 | Completed | No
WO-26-003667 | 2.9 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-04-13 | 2026-04-21 | 2026-04-21 | Internal line |  | 372.41 | Completed | No
WO-26-003668 | 4.7 | Crossroads | CR-S22-02 | Preventive maintenance | P4 planned | 2026-04-13 | 2026-04-22 | 2026-04-22 | Internal line |  | 267.71 | Completed | No
WO-26-003669 | 1.5 | Crossroads | CR-S16-02 | Service order - field | P3 within 10 days | 2026-04-13 | 2026-04-23 | 2026-04-24 | Meter technician |  | 8.06 | Completed | No
WO-26-003670 | 0.7 | Crossroads | CR-S17-03 | Service order - field | P2 same day | 2026-04-13 | 2026-04-14 | 2026-04-14 | Meter technician |  | 11.86 | Completed | No
WO-26-003671 | 0.9 | Crossroads | CR-S13-03 | Service order - field | P2 same day | 2026-04-13 | 2026-04-14 | 2026-04-14 | Meter technician |  | 11.84 | Completed | No
WO-26-003672 | 1.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-13 | 2026-04-23 | 2026-04-23 | Contract line | CT-01 | 301.67 | Completed | No
WO-26-003673 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-13 | 2026-04-22 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-003674 | 12.6 | Crossroads | CR-S23-03 | Transformer replacement | P2 same day | 2026-04-13 | 2026-04-14 | 2026-04-14 | Internal line |  | 6735.92 | Completed | No
WO-26-003675 | 10.4 | Crossroads | CR-S15-01 | Transformer replacement | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Internal line |  | 8353.63 | Completed | No
WO-26-003676 | 3 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 116.66 | Completed | No
WO-26-003677 | 5.7 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 137.44 | Completed | No
WO-26-003678 | 5.8 | Crossroads | CR-S18-04 | Trouble - no power | P2 same day | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 228.39 | Completed | No
WO-26-003679 | 5.5 | Crossroads | CR-S05-04 | Trouble - no power | P1 emergency | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 27.98 | Completed | No
WO-26-003680 | 1.6 | Crossroads | CR-S28-03 | Trouble - partial or voltage | P2 same day | 2026-04-13 | 2026-04-13 | 2026-04-13 | Troubleman |  | 13.74 | Completed | No
WO-26-003681 |  | Crossroads | CR-S15-01 | Trouble - partial or voltage | P2 same day | 2026-04-13 | 2026-04-13 |  | Internal line |  |  | Cancelled | No
WO-26-003682 | 4.5 | Crossroads | CR-S27-04 | Trouble - partial or voltage | P2 same day | 2026-04-13 | 2026-04-14 | 2026-04-14 | Internal line |  | 240.11 | Completed | No
WO-26-003683 | 2.8 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-13 | 2026-04-22 | 2026-04-22 | Troubleman |  | 143.11 | Completed | No
WO-26-003684 | 8.6 | Bayou | BY-S16-01 | Corrective maintenance | P3 within 10 days | 2026-04-14 | 2026-04-18 | 2026-04-20 | Internal line |  | 1307.98 | Completed | No
WO-26-003685 | 5.4 | Bayou | BY-S11-01 | Corrective maintenance | P2 same day | 2026-04-14 | 2026-04-15 | 2026-04-15 | Internal line |  | 366.68 | Completed | No
WO-26-003686 | 15.1 | Bayou | BY-S14-03 | New service - small | P4 planned | 2026-04-14 | 2026-05-05 | 2026-05-05 | Internal line |  | 3051.2 | Completed | No
WO-26-003687 | 13.2 | Bayou | BY-S26-02 | New service - small | P4 planned | 2026-04-14 | 2026-06-10 | 2026-06-10 | Contract line | CT-04 | 1519.81 | Completed | No
WO-26-003688 | 8.1 | Bayou | BY-S28-02 | New service - small | P4 planned | 2026-04-14 | 2026-06-12 | 2026-06-12 | Internal line |  | 2915.12 | Completed | No
WO-26-003689 | 11 | Bayou | BY-S16-01 | Pole replacement | P3 within 10 days | 2026-04-14 | 2026-04-19 | 2026-04-23 | Internal line |  | 3346.31 | Completed | No
WO-26-003690 | 5.2 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-04-14 | 2026-06-04 | 2026-06-06 | Underground crew |  | 359.67 | Completed | No
WO-26-003691 | 2.3 | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-04-14 | 2026-05-22 | 2026-05-22 | Underground crew |  | 329.34 | Completed | No
WO-26-003692 | 7 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-04-14 | 2026-04-25 | 2026-04-27 | Internal line |  | 59.03 | Completed | No
WO-26-003693 | 0.9 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-04-14 | 2026-04-15 | 2026-04-15 | Meter technician |  | 29.01 | Completed | No
WO-26-003694 | 1 | Bayou | BY-S12-03 | Service order - field | P3 within 10 days | 2026-04-14 | 2026-04-15 | 2026-04-15 | Meter technician |  | 25.19 | Completed | No
WO-26-003695 | 1.8 | Bayou | BY-S21-04 | Service order - field | P3 within 10 days | 2026-04-14 | 2026-04-24 | 2026-04-24 | Meter technician |  | 13.07 | Completed | No
WO-26-003696 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-14 | 2026-04-21 | 2026-04-23 | Contract line | CT-04 | 316.94 | Completed | No
WO-26-003697 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-04-14 | 2026-04-20 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-003698 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-14 | 2026-04-22 | 2026-04-23 | Internal line |  | 144.51 | Completed | No
WO-26-003699 | 3.9 | Bayou | BY-S16-01 | Trouble - no power | P2 same day | 2026-04-14 | 2026-04-15 | 2026-04-15 | Internal line |  | 267.38 | Completed | No
WO-26-003700 | 3.3 | Bayou | BY-S16-03 | Trouble - no power | P2 same day | 2026-04-14 | 2026-04-14 | 2026-04-14 | Troubleman |  | 159.73 | Completed | No
WO-26-003701 | 4.5 | Bayou | BY-S23-01 | Trouble - no power | P1 emergency | 2026-04-14 | 2026-04-14 | 2026-04-14 | Troubleman |  | 194.82 | Completed | No
WO-26-003702 | 2.5 | Bayou | BY-S14-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-14 | 2026-04-17 | 2026-04-17 | Troubleman |  | 204.96 | Completed | No
WO-26-003703 | 3.7 | Crossroads | CR-S18-06 | Corrective maintenance | P3 within 10 days | 2026-04-14 | 2026-04-21 | 2026-04-21 | Internal line |  | 651.32 | Completed | No
WO-26-003704 | 4.5 | Crossroads | CR-S17-03 | Corrective maintenance | P3 within 10 days | 2026-04-14 | 2026-04-20 | 2026-04-20 | Internal line |  | 1073.29 | Completed | No
WO-26-003705 | 1 | Crossroads | CR-S04-01 | Meter exchange | P3 within 10 days | 2026-04-14 | 2026-04-19 | 2026-04-21 | Meter technician |  | 88.52 | Completed | No
WO-26-003706 | 0.6 | Crossroads | CR-S04-01 | Meter exchange | P4 planned | 2026-04-14 | 2026-04-21 | 2026-04-29 | Meter technician |  | 143.58 | Completed | No
WO-26-003707 | 6.1 | Crossroads | CR-S26-02 | Preventive maintenance | P4 planned | 2026-04-14 | 2026-05-16 | 2026-05-18 | Underground crew |  | 453.2 | Completed | No
WO-26-003708 | 5.1 | Crossroads | CR-S14-01 | Preventive maintenance | P4 planned | 2026-04-14 | 2026-04-26 | 2026-04-30 | Contract line | CT-02 | 320.31 | Completed | No
WO-26-003709 | 7.7 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-04-14 | 2026-06-13 | 2026-06-15 | Internal line |  | 116.17 | Completed | No
WO-26-003710 | 2 | Crossroads | CR-S27-02 | Service order - field | P2 same day | 2026-04-14 | 2026-04-14 | 2026-04-14 | Meter technician |  | 3.07 | Completed | No
WO-26-003711 |  | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-04-14 | 2026-04-15 |  | Meter technician |  |  | Cancelled | No
WO-26-003712 | 1.2 | Crossroads | CR-S14-01 | Service order - field | P2 same day | 2026-04-14 | 2026-04-14 | 2026-04-14 | Meter technician |  | 39.86 | Completed | No
WO-26-003713 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-14 | 2026-04-22 | 2026-04-23 | Contract line | CT-02 | 74.33 | Completed | No
WO-26-003714 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-04-14 | 2026-05-05 | 2026-05-05 | Internal line |  | 114.76 | Completed | No
WO-26-003715 | 4.1 | Crossroads | CR-S09-04 | Trouble - no power | P1 emergency | 2026-04-14 | 2026-04-14 | 2026-04-14 | Troubleman |  | 291.02 | Completed | No
WO-26-003716 | 4.4 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-04-14 | 2026-04-14 | 2026-04-14 | Troubleman |  | 5.59 | Completed | No
WO-26-003717 | 4.6 | Crossroads | CR-S05-06 | Trouble - no power | P1 emergency | 2026-04-14 | 2026-04-14 | 2026-04-14 | Troubleman |  | 176.43 | Completed | No
WO-26-003718 | 4.2 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P2 same day | 2026-04-14 | 2026-04-14 | 2026-04-14 | Internal line |  | 221.12 | Completed | No
WO-26-003719 | 5 | Bayou | BY-S01-01 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-25 | 2026-04-27 | Internal line |  | 1840.88 | Completed | No
WO-26-003720 | 11.3 | Bayou | BY-S02-01 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-23 | 2026-04-24 | Internal line |  | 432.22 | Completed | No
WO-26-003721 | 6.4 | Bayou | BY-S26-06 | Corrective maintenance | P4 planned | 2026-04-15 | 2026-05-20 | 2026-05-24 | Underground crew |  | 334.69 | Completed | No
WO-26-003722 | 9 | Bayou | BY-S29-04 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-19 | 2026-04-20 | Contract line | CT-03 | 2122.33 | Completed | No
WO-26-003723 | 7.6 | Bayou | BY-S06-01 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-18 | 2026-04-22 | Contract line | CT-03 | 534.84 | Completed | No
WO-26-003724 | 1.4 | Bayou | BY-S16-05 | Meter exchange | P3 within 10 days | 2026-04-15 | 2026-04-21 | 2026-04-25 | Meter technician |  | 146.54 | Completed | No
WO-26-003725 | 22.9 | Bayou | BY-S26-06 | Pole replacement | P3 within 10 days | 2026-04-15 | 2026-04-25 | 2026-04-25 | Internal line |  | 2594.87 | Completed | No
WO-26-003726 | 6.8 | Bayou | BY-S04-02 | Preventive maintenance | P4 planned | 2026-04-15 | 2026-04-22 | 2026-04-22 | Contract line | CT-04 | 514.93 | Completed | No
WO-26-003727 | 5.7 | Bayou | BY-S16-02 | Preventive maintenance | P4 planned | 2026-04-15 | 2026-04-27 | 2026-05-01 | Contract line | CT-04 | 506.26 | Completed | No
WO-26-003728 | 1 | Bayou | BY-S10-02 | Service order - field | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Meter technician |  | 10.63 | Completed | No
WO-26-003729 | 0.8 | Bayou | BY-S21-04 | Service order - field | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Meter technician |  | 1.82 | Completed | No
WO-26-003730 | 0.9 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-04-15 | 2026-04-16 | 2026-04-16 | Meter technician |  | 13.83 | Completed | No
WO-26-003731 | 1.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-15 | 2026-04-16 | 2026-04-16 | Contract line | CT-03 | 401.16 | Completed | No
WO-26-003732 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-15 | 2026-04-18 | 2026-04-19 | Internal line |  | 225.59 | Completed | No
WO-26-003733 | 5.1 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 257.93 | Completed | No
WO-26-003734 | 3.8 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 323.79 | Completed | No
WO-26-003735 | 3.5 | Bayou | BY-S07-05 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 262.54 | Completed | No
WO-26-003736 | 2.2 | Bayou | BY-S15-01 | Trouble - partial or voltage | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 34.9 | Completed | No
WO-26-003737 | 2.8 | Bayou | BY-S29-04 | Trouble - partial or voltage | P3 within 10 days | 2026-04-15 | 2026-04-16 | 2026-04-17 | Troubleman |  | 92.02 | Completed | No
WO-26-003738 | 2.8 | Bayou | BY-S18-03 | Trouble - partial or voltage | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 136.2 | Completed | No
WO-26-003739 | 6.4 | Crossroads | CR-S29-02 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-16 | 2026-04-20 | Contract line | CT-02 | 1336.28 | Completed | No
WO-26-003740 | 4.4 | Crossroads | CR-S32-03 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-16 | 2026-04-18 | Underground crew |  | 899.58 | Completed | No
WO-26-003741 | 9.6 | Crossroads | CR-S01-04 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-21 | 2026-04-21 | Contract line | CT-01 | 1095.7 | Completed | No
WO-26-003742 | 11.5 | Crossroads | CR-S16-03 | Corrective maintenance | P3 within 10 days | 2026-04-15 | 2026-04-23 | 2026-04-24 | Internal line |  | 2370.73 | Completed | No
WO-26-003743 | 1.2 | Crossroads | CR-S07-05 | Meter exchange | P4 planned | 2026-04-15 | 2026-04-25 | 2026-04-25 | Meter technician |  | 120.74 | Completed | No
WO-26-003744 | 1.2 | Crossroads | CR-S13-04 | Meter exchange | P3 within 10 days | 2026-04-15 | 2026-04-22 | 2026-04-22 | Meter technician |  | 110.83 | Completed | No
WO-26-003745 | 1.1 | Crossroads | CR-S27-02 | Meter exchange | P4 planned | 2026-04-15 | 2026-05-10 | 2026-05-10 | Meter technician |  | 79.83 | Completed | No
WO-26-003746 | 0.8 | Crossroads | CR-S31-01 | Meter exchange | P3 within 10 days | 2026-04-15 | 2026-04-16 | 2026-04-20 | Meter technician |  | 77.12 | Completed | No
WO-26-003747 | 15.3 | Crossroads | CR-S11-02 | Pole replacement | P3 within 10 days | 2026-04-15 | 2026-04-19 | 2026-04-27 | Internal line |  | 1293.41 | Completed | No
WO-26-003748 | 0.5 | Crossroads | CR-S09-02 | Service order - field | P2 same day | 2026-04-15 | 2026-04-16 | 2026-04-16 | Meter technician |  | 9.64 | Completed | No
WO-26-003749 | 1.2 | Crossroads | CR-S28-04 | Service order - field | P3 within 10 days | 2026-04-15 | 2026-04-17 | 2026-04-17 | Meter technician |  | 7.83 | Completed | No
WO-26-003750 | 0.6 | Crossroads | CR-S02-05 | Service order - field | P3 within 10 days | 2026-04-15 | 2026-04-18 | 2026-04-20 | Meter technician |  | 9.81 | Completed | No
WO-26-003751 | 0.9 | Crossroads | CR-S20-02 | Service order - field | P3 within 10 days | 2026-04-15 | 2026-04-21 | 2026-04-23 | Meter technician |  | 14.97 | Completed | No
WO-26-003752 | 1 | Crossroads | CR-S07-05 | Service order - field | P3 within 10 days | 2026-04-15 | 2026-04-20 | 2026-04-20 | Meter technician |  | 29.68 | Completed | No
WO-26-003753 | 0.5 | Crossroads | CR-S15-03 | Service order - field | P3 within 10 days | 2026-04-15 | 2026-04-24 | 2026-04-24 | Meter technician |  | 27.97 | Completed | No
WO-26-003754 | 0.6 | Crossroads | CR-S12-01 | Service order - field | P3 within 10 days | 2026-04-15 | 2026-04-17 | 2026-04-17 | Meter technician |  | 15.54 | Completed | No
WO-26-003755 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-15 | 2026-04-19 | 2026-04-19 | Internal line |  | 123.59 | Completed | No
WO-26-003756 | 1.8 | Crossroads |  | Streetlight | P4 planned | 2026-04-15 | 2026-05-10 | 2026-05-10 | Contract line | CT-02 | 413.86 | Completed | No
WO-26-003757 | 10.2 | Crossroads | CR-S31-02 | Transformer replacement | P2 same day | 2026-04-15 | 2026-04-16 | 2026-04-16 | Internal line |  | 4261.45 | Completed | No
WO-26-003758 | 6.6 | Crossroads | CR-S14-02 | Transformer replacement | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Contract line | CT-01 | 10590.35 | Completed | No
WO-26-003759 | 5.9 | Crossroads | CR-S01-03 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 217.77 | Completed | No
WO-26-003760 | 5.6 | Crossroads | CR-S23-02 | Trouble - no power | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 52.93 | Completed | No
WO-26-003761 | 4.7 | Crossroads | CR-S32-02 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Internal line |  | 141.7 | Completed | No
WO-26-003762 | 3.7 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 125.1 | Completed | No
WO-26-003763 | 5.7 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 284.44 | Completed | No
WO-26-003764 | 1.9 | Crossroads | CR-S15-03 | Trouble - partial or voltage | P2 same day | 2026-04-15 | 2026-04-15 | 2026-04-15 | Troubleman |  | 16.57 | Completed | No
WO-26-003765 | 2.3 | Crossroads | CR-S16-03 | Trouble - partial or voltage | P3 within 10 days | 2026-04-15 | 2026-04-24 | 2026-04-24 | Troubleman |  | 84.53 | Completed | No
WO-26-003766 | 5.8 | Bayou | BY-S29-05 | Corrective maintenance | P3 within 10 days | 2026-04-16 | 2026-04-19 | 2026-04-20 | Internal line |  | 1074.94 | Completed | No
WO-26-003767 | 5.6 | Bayou | BY-S15-01 | Corrective maintenance | P4 planned | 2026-04-16 | 2026-05-30 | 2026-05-30 | Underground crew |  | 80.43 | Completed | No
WO-26-003768 | 0.7 | Bayou | BY-S21-01 | Meter exchange | P4 planned | 2026-04-16 | 2026-05-10 | 2026-05-11 | Meter technician |  | 177.67 | Completed | No
WO-26-003769 | 0.8 | Bayou | BY-S17-04 | Meter exchange | P3 within 10 days | 2026-04-16 | 2026-04-25 | 2026-04-26 | Meter technician |  | 126.68 | Completed | No
WO-26-003770 | 1.3 | Bayou | BY-S05-01 | Meter exchange | P3 within 10 days | 2026-04-16 | 2026-04-24 | 2026-04-28 | Meter technician |  | 75.1 | Completed | No
WO-26-003771 | 11.9 | Bayou | BY-S08-01 | Pole replacement | P3 within 10 days | 2026-04-16 | 2026-04-22 | 2026-04-22 | Contract line | CT-04 | 2616.9 | Completed | No
WO-26-003772 | 2 | Bayou | BY-S25-03 | Service order - field | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Meter technician |  | 2.91 | Completed | No
WO-26-003773 | 1.1 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Meter technician |  | 33.61 | Completed | No
WO-26-003774 | 2.2 | Bayou |  | Streetlight | P4 planned | 2026-04-16 | 2026-04-27 | 2026-05-05 | Internal line |  | 138.05 | Completed | No
WO-26-003775 | 1.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-16 | 2026-04-25 | 2026-04-25 | Internal line |  | 167.32 | Completed | No
WO-26-003776 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-16 | 2026-04-22 | 2026-04-24 | Contract line | CT-03 | 90.69 | Completed | No
WO-26-003777 | 3.2 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Internal line |  | 344.01 | Completed | No
WO-26-003778 | 4.8 | Bayou | BY-S10-01 | Trouble - no power | P2 same day | 2026-04-16 | 2026-04-17 | 2026-04-17 | Internal line |  | 278.37 | Completed | No
WO-26-003779 | 5 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Troubleman |  | 79.15 | Completed | No
WO-26-003780 | 4.3 | Bayou | BY-S20-03 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Troubleman |  | 142.41 | Completed | No
WO-26-003781 | 5 | Bayou | BY-S09-01 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Troubleman |  | 114.57 | Completed | No
WO-26-003782 | 2 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Troubleman |  | 180.25 | Completed | No
WO-26-003783 | 4 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Internal line |  | 166.6 | Completed | No
WO-26-003784 | 7.8 | Crossroads | CR-S28-01 | Corrective maintenance | P3 within 10 days | 2026-04-16 | 2026-04-18 | 2026-04-19 | Internal line |  | 484.19 | Completed | No
WO-26-003785 | 10.5 | Crossroads | CR-S20-02 | Corrective maintenance | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Contract line | CT-02 | 1206.79 | Completed | No
WO-26-003786 | 10.6 | Crossroads | CR-S20-02 | Corrective maintenance | P3 within 10 days | 2026-04-16 | 2026-04-20 | 2026-04-24 | Underground crew |  | 846.19 | Completed | No
WO-26-003787 | 3.9 | Crossroads | CR-S16-02 | Corrective maintenance | P4 planned | 2026-04-16 | 2026-05-27 | 2026-05-27 | Internal line |  | 2365.05 | Completed | No
WO-26-003788 | 5 | Crossroads | CR-S25-05 | Corrective maintenance | P2 same day | 2026-04-16 | 2026-04-17 | 2026-04-17 | Underground crew |  | 1666.97 | Completed | No
WO-26-003789 | 5.5 | Crossroads | CR-S20-03 | Corrective maintenance | P3 within 10 days | 2026-04-16 | 2026-04-26 | 2026-04-26 | Contract line | CT-02 | 2044.15 | Completed | No
WO-26-003790 | 0.6 | Crossroads | CR-S30-07 | Meter exchange | P3 within 10 days | 2026-04-16 | 2026-04-21 | 2026-04-21 | Meter technician |  | 73.15 | Completed | No
WO-26-003791 | 0.6 | Crossroads | CR-S26-04 | Meter exchange | P3 within 10 days | 2026-04-16 | 2026-04-22 | 2026-04-22 | Meter technician |  | 79.54 | Completed | No
WO-26-003792 | 4.2 | Crossroads | CR-S29-02 | Preventive maintenance | P4 planned | 2026-04-16 | 2026-04-26 | 2026-04-27 | Underground crew |  | 443.84 | Completed | No
WO-26-003793 | 3 | Crossroads | CR-S18-05 | Preventive maintenance | P4 planned | 2026-04-16 | 2026-05-03 | 2026-05-03 | Contract line | CT-01 | 496.99 | Completed | No
WO-26-003794 | 0.5 | Crossroads | CR-S21-01 | Service order - field | P3 within 10 days | 2026-04-16 | 2026-04-24 | 2026-04-24 | Meter technician |  | 37.93 | Completed | No
WO-26-003795 | 1.5 | Crossroads | CR-S02-02 | Service order - field | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Meter technician |  | 2.67 | Completed | No
WO-26-003796 | 1.2 | Crossroads | CR-S07-05 | Service order - field | P3 within 10 days | 2026-04-16 | 2026-04-19 | 2026-04-20 | Meter technician |  | 10.37 | Completed | No
WO-26-003797 | 0.9 | Crossroads | CR-S13-01 | Service order - field | P2 same day | 2026-04-16 | 2026-04-16 | 2026-04-16 | Meter technician |  | 8.28 | Completed | No
WO-26-003798 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-16 | 2026-04-26 | 2026-04-27 | Internal line |  | 411.26 | Completed | No
WO-26-003799 | 2.7 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Troubleman |  | 250.83 | Completed | No
WO-26-003800 | 2.2 | Crossroads | CR-S26-04 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Internal line |  | 239.36 | Completed | No
WO-26-003801 | 4.9 | Crossroads | CR-S17-02 | Trouble - no power | P2 same day | 2026-04-16 | 2026-04-17 | 2026-04-17 | Troubleman |  | 44.5 | Completed | No
WO-26-003802 |  | Crossroads | CR-S11-01 | Trouble - no power | P2 same day | 2026-04-16 | 2026-04-16 |  | Troubleman |  |  | Cancelled | No
WO-26-003803 | 3.2 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-04-16 | 2026-04-16 | 2026-04-16 | Troubleman |  | 201.9 | Completed | No
WO-26-003804 | 4.7 | Crossroads | CR-S30-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-16 | 2026-04-26 | 2026-04-27 | Troubleman |  | 229.01 | Completed | No
WO-26-003805 | 4.9 | Bayou | BY-S14-02 | Corrective maintenance | P3 within 10 days | 2026-04-17 | 2026-04-22 | 2026-04-24 | Internal line |  | 1051.69 | Completed | No
WO-26-003806 | 10 | Bayou | BY-S15-06 | Corrective maintenance | P3 within 10 days | 2026-04-17 | 2026-04-25 | 2026-04-25 | Internal line |  | 287.86 | Completed | No
WO-26-003807 | 3.4 | Bayou | BY-S04-02 | Corrective maintenance | P3 within 10 days | 2026-04-17 | 2026-04-19 | 2026-04-19 | Contract line | CT-03 | 1268.73 | Completed | No
WO-26-003808 | 11.4 | Bayou | BY-S22-04 | Corrective maintenance | P3 within 10 days | 2026-04-17 | 2026-04-24 | 2026-04-26 | Underground crew |  | 1206.03 | Completed | No
WO-26-003809 | 0.6 | Bayou | BY-S29-02 | Meter exchange | P3 within 10 days | 2026-04-17 | 2026-04-18 | 2026-04-18 | Meter technician |  | 135.02 | Completed | No
WO-26-003810 | 0.8 | Bayou | BY-S16-01 | Meter exchange | P4 planned | 2026-04-17 | 2026-05-16 | 2026-05-16 | Meter technician |  | 123.97 | Completed | No
WO-26-003811 | 0.6 | Bayou | BY-S06-02 | Meter exchange | P3 within 10 days | 2026-04-17 | 2026-04-22 | 2026-04-22 | Meter technician |  | 72.09 | Completed | No
WO-26-003812 | 6.8 | Bayou | BY-S26-04 | New service - small | P4 planned | 2026-04-17 | 2026-06-13 | 2026-06-14 | Contract line | CT-04 | 2194.56 | Completed | No
WO-26-003813 | 14.5 | Bayou | BY-S19-03 | Pole replacement | P4 planned | 2026-04-17 | 2026-04-30 | 2026-04-30 | Contract line | CT-03 | 1304.48 | Completed | No
WO-26-003814 | 6.9 | Bayou | BY-S16-04 | Preventive maintenance | P4 planned | 2026-04-17 | 2026-06-12 | 2026-06-12 | Internal line |  | 117.16 | Completed | No
WO-26-003815 | 7.3 | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-04-17 | 2026-04-25 | 2026-04-29 | Underground crew |  | 152.21 | Completed | No
WO-26-003816 | 1 | Bayou | BY-S26-01 | Service order - field | P3 within 10 days | 2026-04-17 | 2026-04-18 | 2026-04-20 | Meter technician |  | 29.78 | Completed | No
WO-26-003817 | 1.8 | Bayou | BY-S19-03 | Service order - field | P3 within 10 days | 2026-04-17 | 2026-04-27 | 2026-04-27 | Meter technician |  | 23.4 | Completed | No
WO-26-003818 | 1.5 | Bayou | BY-S21-03 | Service order - field | P3 within 10 days | 2026-04-17 | 2026-04-22 | 2026-04-23 | Meter technician |  | 12.89 | Completed | No
WO-26-003819 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-17 | 2026-04-25 | 2026-04-27 | Contract line | CT-03 | 417.58 | Completed | No
WO-26-003820 | 12.4 | Bayou | BY-S24-03 | Transformer replacement | P1 emergency | 2026-04-17 | 2026-04-17 | 2026-04-17 | Contract line | CT-04 | 4535.64 | Completed | No
WO-26-003821 | 13.4 | Bayou | BY-S24-04 | Transformer replacement | P1 emergency | 2026-04-17 | 2026-04-17 | 2026-04-17 | Contract line | CT-03 | 6122.34 | Completed | No
WO-26-003822 | 12.5 | Bayou | BY-S29-01 | Transformer replacement | P2 same day | 2026-04-17 | 2026-04-17 | 2026-04-17 | Contract line | CT-03 | 6842.03 | Completed | No
WO-26-003823 | 5.1 | Bayou | BY-S15-03 | Trouble - no power | P2 same day | 2026-04-17 | 2026-04-17 | 2026-04-17 | Troubleman |  | 340.71 | Completed | No
WO-26-003824 | 2.6 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-04-17 | 2026-04-17 | 2026-04-17 | Troubleman |  | 177.61 | Completed | No
WO-26-003825 | 4.5 | Bayou | BY-S26-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-17 | 2026-04-18 | 2026-04-18 | Troubleman |  | 72.14 | Completed | No
WO-26-003826 | 7.9 | Crossroads | CR-S24-04 | Corrective maintenance | P4 planned | 2026-04-17 | 2026-06-02 | 2026-06-02 | Internal line |  | 2030.21 | Completed | No
WO-26-003827 | 3.7 | Crossroads | CR-S07-05 | Corrective maintenance | P4 planned | 2026-04-17 | 2026-06-02 | 2026-06-03 | Internal line |  | 1080.65 | Completed | No
WO-26-003828 | 3.6 | Crossroads | CR-S13-04 | Corrective maintenance | P4 planned | 2026-04-17 | 2026-05-15 | 2026-05-16 | Internal line |  | 1749.73 | Completed | No
WO-26-003829 | 7.1 | Crossroads | CR-S31-02 | Corrective maintenance | P3 within 10 days | 2026-04-17 | 2026-04-21 | 2026-04-21 | Underground crew |  | 913.45 | Completed | No
WO-26-003830 | 3.3 | Crossroads | CR-S28-03 | Corrective maintenance | P3 within 10 days | 2026-04-17 | 2026-04-24 | 2026-04-24 | Contract line | CT-01 | 1477.2 | Completed | No
WO-26-003831 | 1.3 | Crossroads | CR-S04-02 | Meter exchange | P4 planned | 2026-04-17 | 2026-04-29 | 2026-04-29 | Meter technician |  | 68.86 | Completed | No
WO-26-003832 | 0.8 | Crossroads | CR-S18-05 | Meter exchange | P4 planned | 2026-04-17 | 2026-05-20 | 2026-05-21 | Meter technician |  | 165.47 | Completed | No
WO-26-003833 | 0.7 | Crossroads | CR-S16-06 | Meter exchange | P3 within 10 days | 2026-04-17 | 2026-04-26 | 2026-04-27 | Meter technician |  | 118.24 | Completed | No
WO-26-003834 | 10.9 | Crossroads | CR-S14-02 | New service - small | P4 planned | 2026-04-17 | 2026-04-26 | 2026-04-30 | Contract line | CT-01 | 2011.29 | Completed | No
WO-26-003835 | 12 | Crossroads | CR-S07-03 | Pole replacement | P3 within 10 days | 2026-04-17 | 2026-04-27 | 2026-04-27 | Contract line | CT-01 | 1832.52 | Completed | No
WO-26-003836 | 11.5 | Crossroads | CR-S11-01 | Pole replacement | P3 within 10 days | 2026-04-17 | 2026-04-26 | 2026-04-27 | Internal line |  | 2353.04 | Completed | No
WO-26-003837 | 4.2 | Crossroads | CR-S32-05 | Preventive maintenance | P4 planned | 2026-04-17 | 2026-05-10 | 2026-05-11 | Internal line |  | 157.89 | Completed | No
WO-26-003838 | 5.5 | Crossroads | CR-S08-01 | Preventive maintenance | P4 planned | 2026-04-17 | 2026-05-07 | 2026-05-11 | Internal line |  | 23.53 | Completed | No
WO-26-003839 | 7.6 | Crossroads | CR-S10-03 | Preventive maintenance | P4 planned | 2026-04-17 | 2026-05-27 | 2026-05-27 | Underground crew |  | 412.24 | Completed | No
WO-26-003840 | 1 | Crossroads | CR-S01-04 | Service order - field | P2 same day | 2026-04-17 | 2026-04-17 | 2026-04-17 | Meter technician |  | 29.55 | Completed | No
WO-26-003841 | 1.3 | Crossroads | CR-S28-01 | Service order - field | P3 within 10 days | 2026-04-17 | 2026-04-24 | 2026-04-24 | Meter technician |  | 33.14 | Completed | No
WO-26-003842 | 1.7 | Crossroads | CR-S32-02 | Service order - field | P3 within 10 days | 2026-04-17 | 2026-04-26 | 2026-04-26 | Meter technician |  | 28.43 | Completed | No
WO-26-003843 | 1.1 | Crossroads | CR-S26-02 | Service order - field | P2 same day | 2026-04-17 | 2026-04-17 | 2026-04-17 | Meter technician |  | 6.03 | Completed | No
WO-26-003844 | 2.7 | Crossroads |  | Streetlight | P4 planned | 2026-04-17 | 2026-06-16 | 2026-06-16 | Internal line |  | 263.34 | Completed | No
WO-26-003845 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-17 | 2026-04-23 | 2026-04-24 | Contract line | CT-01 | 342.7 | Completed | No
WO-26-003846 | 10.8 | Crossroads | CR-S16-06 | Transformer replacement | P1 emergency | 2026-04-17 | 2026-04-17 | 2026-04-17 | Internal line |  | 12317.79 | Completed | No
WO-26-003847 | 5.6 | Crossroads | CR-S17-03 | Trouble - no power | P1 emergency | 2026-04-17 | 2026-04-17 | 2026-04-17 | Troubleman |  | 122.87 | Completed | No
WO-26-003848 | 2.4 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-04-17 | 2026-04-17 | 2026-04-17 | Troubleman |  | 116.27 | Completed | No
WO-26-003849 | 5.1 | Crossroads | CR-S30-01 | Trouble - no power | P2 same day | 2026-04-17 | 2026-04-18 | 2026-04-18 | Troubleman |  | 310.07 | Completed | No
WO-26-003850 | 3.7 | Crossroads | CR-S21-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-17 | 2026-04-19 | 2026-04-19 | Troubleman |  | 213.56 | Completed | No
WO-26-003851 | 0.7 | Bayou | BY-S10-03 | Service order - field | P2 same day | 2026-04-18 | 2026-04-18 | 2026-04-18 | Meter technician |  | 10.59 | Completed | No
WO-26-003852 | 0.5 | Bayou | BY-S13-03 | Service order - field | P2 same day | 2026-04-18 | 2026-04-18 | 2026-04-18 | Meter technician |  | 16.04 | Completed | No
WO-26-003853 | 6.7 | Bayou | BY-S05-02 | Transformer replacement | P2 same day | 2026-04-18 | 2026-04-18 | 2026-04-18 | Internal line |  | 9352.39 | Completed | No
WO-26-003854 | 13.2 | Bayou | BY-S23-01 | Transformer replacement | P1 emergency | 2026-04-18 | 2026-04-18 | 2026-04-18 | Contract line | CT-04 | 7854.25 | Completed | No
WO-26-003855 | 5.8 | Bayou | BY-S26-01 | Trouble - no power | P1 emergency | 2026-04-18 | 2026-04-18 | 2026-04-18 | Internal line |  | 193.28 | Completed | No
WO-26-003856 | 4.2 | Bayou | BY-S15-01 | Trouble - no power | P2 same day | 2026-04-18 | 2026-04-18 | 2026-04-18 | Troubleman |  | 256.33 | Completed | No
WO-26-003857 | 4.4 | Bayou | BY-S23-01 | Trouble - no power | P2 same day | 2026-04-18 | 2026-04-19 | 2026-04-19 | Troubleman |  | 330.28 | Completed | No
WO-26-003858 | 5.9 | Bayou | BY-S18-02 | Trouble - no power | P2 same day | 2026-04-18 | 2026-04-19 | 2026-04-19 | Internal line |  | 32.86 | Completed | No
WO-26-003859 | 3.4 | Bayou | BY-S11-03 | Trouble - no power | P1 emergency | 2026-04-18 | 2026-04-18 | 2026-04-18 | Troubleman |  | 63.87 | Completed | No
WO-26-003860 | 4.5 | Bayou | BY-S28-02 | Trouble - partial or voltage | P2 same day | 2026-04-18 | 2026-04-19 | 2026-04-19 | Troubleman |  | 22.65 | Completed | No
WO-26-003861 | 4.9 | Crossroads | CR-S04-06 | Corrective maintenance | P2 same day | 2026-04-18 | 2026-04-19 | 2026-04-19 | Internal line |  | 1194.35 | Completed | No
WO-26-003862 | 1.1 | Crossroads | CR-S14-03 | Service order - field | P2 same day | 2026-04-18 | 2026-04-19 | 2026-04-19 | Meter technician |  | 12.71 | Completed | No
WO-26-003863 | 0.8 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-04-18 | 2026-04-19 | 2026-04-19 | Meter technician |  | 23.27 | Completed | No
WO-26-003864 | 10.1 | Crossroads | CR-S17-01 | Transformer replacement | P2 same day | 2026-04-18 | 2026-04-18 | 2026-04-18 | Contract line | CT-02 | 9156.01 | Completed | No
WO-26-003865 | 3.4 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-04-18 | 2026-04-18 | 2026-04-18 | Troubleman |  | 107.5 | Completed | No
WO-26-003866 | 3.4 | Crossroads | CR-S18-05 | Trouble - no power | P1 emergency | 2026-04-18 | 2026-04-18 | 2026-04-18 | Internal line |  | 84.1 | Completed | No
WO-26-003867 | 2.2 | Crossroads | CR-S25-01 | Trouble - no power | P1 emergency | 2026-04-18 | 2026-04-18 | 2026-04-18 | Troubleman |  | 324.21 | Completed | No
WO-26-003868 | 2.1 | Crossroads | CR-S04-05 | Trouble - no power | P2 same day | 2026-04-18 | 2026-04-18 | 2026-04-18 | Troubleman |  | 234.46 | Completed | No
WO-26-003869 | 8.5 | Bayou | BY-S18-05 | Corrective maintenance | P2 same day | 2026-04-19 | 2026-04-20 | 2026-04-20 | Internal line |  | 166.5 | Completed | No
WO-26-003870 | 1 | Bayou | BY-S16-03 | Service order - field | P2 same day | 2026-04-19 | 2026-04-20 | 2026-04-20 | Meter technician |  | 10.03 | Completed | No
WO-26-003871 | 7.6 | Bayou | BY-S27-01 | Transformer replacement | P2 same day | 2026-04-19 | 2026-04-20 | 2026-04-20 | Contract line | CT-03 | 6996.44 | Completed | No
WO-26-003872 | 12.9 | Bayou | BY-S13-06 | Transformer replacement | P2 same day | 2026-04-19 | 2026-04-20 | 2026-04-20 | Contract line | CT-04 | 11802.48 | Completed | No
WO-26-003873 | 2.8 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 117.36 | Completed | No
WO-26-003874 | 5.8 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 84.42 | Completed | No
WO-26-003875 | 2.8 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 244.48 | Completed | No
WO-26-003876 | 4.5 | Bayou | BY-S18-04 | Trouble - no power | P2 same day | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 271.45 | Completed | No
WO-26-003877 | 2.8 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 304.89 | Completed | No
WO-26-003878 | 3.9 | Crossroads | CR-S06-02 | Corrective maintenance | P2 same day | 2026-04-19 | 2026-04-20 | 2026-04-20 | Contract line | CT-02 | 1261.89 | Completed | No
WO-26-003879 | 0.7 | Crossroads | CR-S25-06 | Service order - field | P2 same day | 2026-04-19 | 2026-04-19 | 2026-04-19 | Meter technician |  | 34.53 | Completed | No
WO-26-003880 |  | Crossroads | CR-S14-05 | Service order - field | P2 same day | 2026-04-19 | 2026-04-20 |  | Meter technician |  |  | Cancelled | No
WO-26-003881 | 8 | Crossroads | CR-S30-05 | Transformer replacement | P1 emergency | 2026-04-19 | 2026-04-19 | 2026-04-19 | Internal line |  | 9357.31 | Completed | No
WO-26-003882 | 2.2 | Crossroads | CR-S03-02 | Trouble - no power | P2 same day | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 236.78 | Completed | No
WO-26-003883 | 3.9 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-04-19 | 2026-04-19 | 2026-04-19 | Internal line |  | 46.86 | Completed | No
WO-26-003884 | 4.7 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-04-19 | 2026-04-19 | 2026-04-19 | Troubleman |  | 212.22 | Completed | No
WO-26-003885 | 10.5 | Bayou | BY-S26-02 | Corrective maintenance | P4 planned | 2026-04-20 | 2026-05-04 | 2026-05-04 | Underground crew |  | 1957.91 | Completed | No
WO-26-003886 | 4.7 | Bayou | BY-S25-02 | Corrective maintenance | P3 within 10 days | 2026-04-20 | 2026-04-24 | 2026-04-24 | Internal line |  | 1933.03 | Completed | No
WO-26-003887 | 0.7 | Bayou | BY-S18-01 | Meter exchange | P3 within 10 days | 2026-04-20 | 2026-04-30 | 2026-05-01 | Meter technician |  | 145.97 | Completed | No
WO-26-003888 | 5.2 | Bayou | BY-S09-04 | New service - small | P3 within 10 days | 2026-04-20 | 2026-04-21 | 2026-04-23 | Internal line |  | 2001.05 | Completed | No
WO-26-003889 | 15.8 | Bayou | BY-S26-06 | Pole replacement | P3 within 10 days | 2026-04-20 | 2026-04-30 | 2026-04-30 | Contract line | CT-03 | 1412.11 | Completed | No
WO-26-003890 | 19.7 | Bayou | BY-S21-05 | Pole replacement | P3 within 10 days | 2026-04-20 | 2026-04-30 | 2026-05-04 | Contract line | CT-04 | 2127.17 | Completed | No
WO-26-003891 | 11.9 | Bayou | BY-S29-01 | Pole replacement | P3 within 10 days | 2026-04-20 | 2026-04-28 | 2026-04-29 | Internal line |  | 1789.71 | Completed | No
WO-26-003892 | 2.1 | Bayou | BY-S05-02 | Preventive maintenance | P4 planned | 2026-04-20 | 2026-06-18 | 2026-06-26 | Internal line |  | 105.44 | Completed | No
WO-26-003893 | 6.9 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-04-20 | 2026-05-14 | 2026-05-15 | Internal line |  | 333.74 | Completed | No
WO-26-003894 | 1.7 | Bayou | BY-S15-06 | Service order - field | P3 within 10 days | 2026-04-20 | 2026-04-21 | 2026-04-22 | Meter technician |  | 23.31 | Completed | No
WO-26-003895 | 1.5 | Bayou | BY-S21-04 | Service order - field | P3 within 10 days | 2026-04-20 | 2026-04-28 | 2026-04-28 | Meter technician |  | 22.76 | Completed | No
WO-26-003896 | 1.5 | Bayou | BY-S19-02 | Service order - field | P3 within 10 days | 2026-04-20 | 2026-04-30 | 2026-05-04 | Meter technician |  | 17.33 | Completed | No
WO-26-003897 | 2.6 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 252.93 | Completed | No
WO-26-003898 | 5.7 | Bayou | BY-S27-04 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Internal line |  | 335.13 | Completed | No
WO-26-003899 | 4.8 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 161.93 | Completed | No
WO-26-003900 | 2.1 | Bayou | BY-S28-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-20 | 2026-04-27 | 2026-05-01 | Internal line |  | 146.6 | Completed | No
WO-26-003901 | 2.3 | Bayou | BY-S20-01 | Trouble - partial or voltage | P2 same day | 2026-04-20 | 2026-04-21 | 2026-04-21 | Troubleman |  | 180 | Completed | No
WO-26-003902 | 1.6 | Bayou | BY-S05-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-20 | 2026-04-21 | 2026-04-22 | Troubleman |  | 156.05 | Completed | No
WO-26-003903 | 4.1 | Bayou | BY-S26-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-20 | 2026-04-28 | 2026-04-28 | Troubleman |  | 3.52 | Completed | No
WO-26-003904 | 5.5 | Crossroads | CR-S10-02 | Corrective maintenance | P2 same day | 2026-04-20 | 2026-04-21 | 2026-04-21 | Contract line | CT-02 | 1319.15 | Completed | No
WO-26-003905 | 10.2 | Crossroads | CR-S27-02 | Corrective maintenance | P3 within 10 days | 2026-04-20 | 2026-04-24 | 2026-04-24 | Internal line |  | 494.9 | Completed | No
WO-26-003906 | 9 | Crossroads | CR-S25-02 | Corrective maintenance | P3 within 10 days | 2026-04-20 | 2026-04-30 | 2026-04-30 | Internal line |  | 829.07 | Completed | No
WO-26-003907 |  | Crossroads | CR-S17-01 | Pole replacement | P2 same day | 2026-04-20 | 2026-04-20 |  | Contract line | CT-01 |  | Cancelled | No
WO-26-003908 | 19.6 | Crossroads | CR-S20-02 | Pole replacement | P4 planned | 2026-04-20 | 2026-06-12 | 2026-06-12 | Internal line |  | 3425.07 | Completed | No
WO-26-003909 | 1.9 | Crossroads | CR-S27-02 | Service order - field | P2 same day | 2026-04-20 | 2026-04-20 | 2026-04-20 | Meter technician |  | 0.64 | Completed | No
WO-26-003910 | 1.5 | Crossroads | CR-S18-04 | Service order - field | P2 same day | 2026-04-20 | 2026-04-20 | 2026-04-20 | Meter technician |  | 36.59 | Completed | No
WO-26-003911 | 8.4 | Crossroads | CR-S32-05 | Transformer replacement | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Contract line | CT-01 | 10349.45 | Completed | No
WO-26-003912 | 6.6 | Crossroads | CR-S29-02 | Transformer replacement | P3 within 10 days | 2026-04-20 | 2026-04-24 | 2026-04-24 | Internal line |  | 5124.13 | Completed | No
WO-26-003913 | 8.9 | Crossroads | CR-S19-03 | Transformer replacement | P3 within 10 days | 2026-04-20 | 2026-04-24 | 2026-04-24 | Internal line |  | 8498.96 | Completed | No
WO-26-003914 | 2.9 | Crossroads | CR-S32-05 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 91.86 | Completed | No
WO-26-003915 | 2.8 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 345.61 | Completed | No
WO-26-003916 | 3.1 | Crossroads | CR-S30-05 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 217.55 | Completed | No
WO-26-003917 | 5.4 | Crossroads | CR-S20-02 | Trouble - no power | P2 same day | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 227.03 | Completed | No
WO-26-003918 | 2.4 | Crossroads | CR-S20-03 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 118.22 | Completed | No
WO-26-003919 | 3 | Crossroads | CR-S05-01 | Trouble - no power | P1 emergency | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 340.41 | Completed | No
WO-26-003920 | 3.7 | Crossroads | CR-S13-01 | Trouble - partial or voltage | P2 same day | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 188.07 | Completed | No
WO-26-003921 | 4.8 | Crossroads | CR-S08-01 | Trouble - partial or voltage | P2 same day | 2026-04-20 | 2026-04-20 | 2026-04-20 | Troubleman |  | 237.86 | Completed | No
WO-26-003922 | 9.4 | Bayou | BY-S08-02 | Corrective maintenance | P3 within 10 days | 2026-04-21 | 2026-04-22 | 2026-04-22 | Contract line | CT-04 | 2346.09 | Completed | No
WO-26-003923 | 6.5 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-04-21 | 2026-04-25 | 2026-04-25 | Internal line |  | 872.17 | Completed | No
WO-26-003924 | 8.7 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-04-21 | 2026-04-23 | 2026-04-23 | Underground crew |  | 207.97 | Completed | No
WO-26-003925 | 1.1 | Bayou | BY-S14-03 | Meter exchange | P4 planned | 2026-04-21 | 2026-05-23 | 2026-05-25 | Meter technician |  | 103.2 | Completed | No
WO-26-003926 | 1.2 | Bayou | BY-S07-02 | Meter exchange | P4 planned | 2026-04-21 | 2026-06-06 | 2026-06-06 | Meter technician |  | 86.2 | Completed | No
WO-26-003927 | 7 | Bayou | BY-S09-02 | New service - small | P4 planned | 2026-04-21 | 2026-06-07 | 2026-06-09 | Contract line | CT-04 | 2650.21 | Completed | No
WO-26-003928 | 21 | Bayou | BY-S21-01 | Pole replacement | P2 same day | 2026-04-21 | 2026-04-22 | 2026-04-22 | Contract line | CT-03 | 1411.48 | Completed | No
WO-26-003929 | 10.1 | Bayou | BY-S03-02 | Pole replacement | P3 within 10 days | 2026-04-21 | 2026-04-26 | 2026-04-28 | Contract line | CT-03 | 2576.86 | Completed | No
WO-26-003930 | 5.3 | Bayou | BY-S13-01 | Preventive maintenance | P4 planned | 2026-04-21 | 2026-06-18 | 2026-06-18 | Contract line | CT-03 | 324.84 | Completed | No
WO-26-003931 | 1.3 | Bayou | BY-S28-02 | Service order - field | P3 within 10 days | 2026-04-21 | 2026-04-28 | 2026-04-28 | Meter technician |  | 36.45 | Completed | No
WO-26-003932 | 1.7 | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-04-21 | 2026-04-22 | 2026-04-22 | Meter technician |  | 3.74 | Completed | No
WO-26-003933 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-21 | 2026-04-23 | 2026-04-23 | Contract line | CT-03 | 403.26 | Completed | No
WO-26-003934 | 2.7 | Bayou |  | Streetlight | P4 planned | 2026-04-21 | 2026-05-29 | 2026-05-29 | Internal line |  | 154.96 | Completed | No
WO-26-003935 | 11.4 | Bayou | BY-S18-02 | Transformer replacement | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Internal line |  | 3179.37 | Completed | No
WO-26-003936 | 5.7 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 146.16 | Completed | No
WO-26-003937 | 3.3 | Bayou | BY-S03-01 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 208.33 | Completed | No
WO-26-003938 | 3.6 | Bayou | BY-S12-01 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 202.13 | Completed | No
WO-26-003939 | 3.1 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 247.23 | Completed | No
WO-26-003940 | 2.9 | Bayou | BY-S05-02 | Trouble - no power | P2 same day | 2026-04-21 | 2026-04-22 | 2026-04-22 | Troubleman |  | 89.38 | Completed | No
WO-26-003941 | 2.2 | Bayou | BY-S06-02 | Trouble - no power | P2 same day | 2026-04-21 | 2026-04-22 | 2026-04-22 | Troubleman |  | 177.55 | Completed | No
WO-26-003942 | 2.3 | Bayou | BY-S20-03 | Trouble - no power | P2 same day | 2026-04-21 | 2026-04-22 | 2026-04-22 | Troubleman |  | 232.74 | Completed | No
WO-26-003943 | 3.8 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 272.11 | Completed | No
WO-26-003944 | 4.6 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Internal line |  | 345.12 | Completed | No
WO-26-003945 | 1.6 | Bayou | BY-S17-02 | Trouble - partial or voltage | P2 same day | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 193.66 | Completed | No
WO-26-003946 | 11.3 | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-04-21 | 2026-04-22 | 2026-04-22 | Contract line | CT-02 | 188.84 | Completed | No
WO-26-003947 |  | Crossroads | CR-S02-03 | Meter exchange | P4 planned | 2026-04-21 | 2026-06-18 |  | Meter technician |  |  | Cancelled | No
WO-26-003948 | 1.2 | Crossroads | CR-S03-01 | Meter exchange | P3 within 10 days | 2026-04-21 | 2026-04-26 | 2026-05-04 | Meter technician |  | 156.07 | Completed | No
WO-26-003949 | 1.5 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-04-21 | 2026-04-28 | 2026-04-28 | Meter technician |  | 169.42 | Completed | No
WO-26-003950 | 0.7 | Crossroads | CR-S04-04 | Meter exchange | P4 planned | 2026-04-21 | 2026-05-16 | 2026-05-16 | Meter technician |  | 144.09 | Completed | No
WO-26-003951 | 0.6 | Crossroads | CR-S04-04 | Meter exchange | P3 within 10 days | 2026-04-21 | 2026-04-25 | 2026-04-25 | Meter technician |  | 65.71 | Completed | No
WO-26-003952 | 1.2 | Crossroads | CR-S14-03 | Meter exchange | P3 within 10 days | 2026-04-21 | 2026-04-28 | 2026-04-29 | Meter technician |  | 61.34 | Completed | No
WO-26-003953 | 17.7 | Crossroads | CR-S19-03 | Pole replacement | P3 within 10 days | 2026-04-21 | 2026-05-01 | 2026-05-01 | Internal line |  | 2830.19 | Completed | No
WO-26-003954 | 2.4 | Crossroads | CR-S23-01 | Preventive maintenance | P4 planned | 2026-04-21 | 2026-06-11 | 2026-06-15 | Internal line |  | 114.87 | Completed | No
WO-26-003955 | 7.3 | Crossroads | CR-S28-02 | Preventive maintenance | P4 planned | 2026-04-21 | 2026-06-07 | 2026-06-07 | Contract line | CT-02 | 526.61 | Completed | No
WO-26-003956 | 2.8 | Crossroads | CR-S20-02 | Preventive maintenance | P4 planned | 2026-04-21 | 2026-06-08 | 2026-06-08 | Contract line | CT-01 | 492.22 | Completed | No
WO-26-003957 | 1.9 | Crossroads | CR-S23-02 | Service order - field | P3 within 10 days | 2026-04-21 | 2026-04-27 | 2026-04-29 | Meter technician |  | 26.44 | Completed | No
WO-26-003958 | 2.8 | Crossroads |  | Streetlight | P4 planned | 2026-04-21 | 2026-05-08 | 2026-05-08 | Internal line |  | 352.3 | Completed | No
WO-26-003959 | 13.7 | Crossroads | CR-S27-04 | Transformer replacement | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Internal line |  | 3862.06 | Completed | No
WO-26-003960 | 4.6 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Internal line |  | 99.03 | Completed | No
WO-26-003961 | 5.6 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 30.57 | Completed | No
WO-26-003962 | 3.6 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-04-21 | 2026-04-21 | 2026-04-21 | Troubleman |  | 113.11 | Completed | No
WO-26-003963 | 4.8 | Crossroads | CR-S19-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-21 | 2026-04-23 | 2026-04-23 | Troubleman |  | 246.22 | Completed | No
WO-26-003964 | 1.6 | Crossroads | CR-S07-07 | Trouble - partial or voltage | P3 within 10 days | 2026-04-21 | 2026-04-28 | 2026-05-02 | Troubleman |  | 123.44 | Completed | No
WO-26-003965 | 5.4 | Bayou | BY-S22-04 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-04-27 | 2026-04-27 | Underground crew |  | 1175.69 | Completed | No
WO-26-003966 | 4.6 | Bayou | BY-S08-03 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-05-02 | 2026-05-02 | Contract line | CT-04 | 1754.39 | Completed | No
WO-26-003967 | 0.9 | Bayou | BY-S24-02 | Meter exchange | P4 planned | 2026-04-22 | 2026-05-10 | 2026-05-10 | Meter technician |  | 61.97 | Completed | No
WO-26-003968 | 0.8 | Bayou | BY-S14-01 | Meter exchange | P3 within 10 days | 2026-04-22 | 2026-05-01 | 2026-05-01 | Meter technician |  | 162.23 | Completed | No
WO-26-003969 | 0.8 | Bayou | BY-S15-06 | Meter exchange | P4 planned | 2026-04-22 | 2026-05-18 | 2026-05-18 | Meter technician |  | 157.98 | Completed | No
WO-26-003970 | 7.6 | Bayou | BY-S13-02 | Preventive maintenance | P4 planned | 2026-04-22 | 2026-05-31 | 2026-06-01 | Underground crew |  | 361.91 | Completed | No
WO-26-003971 | 1.4 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-04-22 | 2026-04-23 | 2026-04-23 | Meter technician |  | 12.1 | Completed | No
WO-26-003972 | 1.6 | Bayou | BY-S30-01 | Service order - field | P2 same day | 2026-04-22 | 2026-04-22 | 2026-04-22 | Meter technician |  | 5.43 | Completed | No
WO-26-003973 | 0.8 | Bayou | BY-S27-03 | Service order - field | P3 within 10 days | 2026-04-22 | 2026-04-29 | 2026-04-30 | Meter technician |  | 4.44 | Completed | No
WO-26-003974 | 1.9 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-04-22 | 2026-04-23 | 2026-04-23 | Meter technician |  | 35.36 | Completed | No
WO-26-003975 | 0.7 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-04-22 | 2026-04-23 | 2026-04-23 | Meter technician |  | 31.37 | Completed | No
WO-26-003976 |  | Bayou | BY-S11-02 | Transformer replacement | P1 emergency | 2026-04-22 | 2026-04-22 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-003977 | 2.4 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 100.28 | Completed | No
WO-26-003978 | 5.7 | Bayou | BY-S11-01 | Trouble - no power | P2 same day | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 6.67 | Completed | No
WO-26-003979 | 4.8 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 315.7 | Completed | No
WO-26-003980 | 4.9 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 151.72 | Completed | No
WO-26-003981 | 3.2 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 63.46 | Completed | No
WO-26-003982 | 4.1 | Bayou | BY-S07-03 | Trouble - partial or voltage | P2 same day | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 121.11 | Completed | No
WO-26-003983 | 3.8 | Crossroads | CR-S22-01 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-05-02 | 2026-05-02 | Contract line | CT-01 | 752.91 | Completed | No
WO-26-003984 | 6.4 | Crossroads | CR-S30-02 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-04-30 | 2026-04-30 | Internal line |  | 381.24 | Completed | No
WO-26-003985 | 5.2 | Crossroads | CR-S16-04 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-05-02 | 2026-05-03 | Underground crew |  | 133.99 | Completed | No
WO-26-003986 | 7.6 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-04-22 | 2026-04-22 | 2026-04-22 | Contract line | CT-01 | 520.19 | Completed | No
WO-26-003987 |  | Crossroads | CR-S29-03 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-04-30 |  | Underground crew |  |  | Cancelled | No
WO-26-003988 | 9.4 | Crossroads | CR-S24-01 | Corrective maintenance | P3 within 10 days | 2026-04-22 | 2026-05-02 | 2026-05-10 | Underground crew |  | 1091.23 | Completed | No
WO-26-003989 | 1.1 | Crossroads | CR-S17-01 | Meter exchange | P4 planned | 2026-04-22 | 2026-06-12 | 2026-06-13 | Meter technician |  | 140.55 | Completed | No
WO-26-003990 | 1.1 | Crossroads | CR-S07-03 | Meter exchange | P4 planned | 2026-04-22 | 2026-05-10 | 2026-05-14 | Meter technician |  | 156.26 | Completed | No
WO-26-003991 | 1 | Crossroads | CR-S27-01 | Meter exchange | P3 within 10 days | 2026-04-22 | 2026-04-26 | 2026-04-26 | Meter technician |  | 126.88 | Completed | No
WO-26-003992 | 1.4 | Crossroads | CR-S25-05 | Meter exchange | P4 planned | 2026-04-22 | 2026-06-18 | 2026-06-18 | Meter technician |  | 151.78 | Completed | No
WO-26-003993 | 10 | Crossroads | CR-S15-01 | New service - small | P4 planned | 2026-04-22 | 2026-05-21 | 2026-05-22 | Contract line | CT-01 | 2687.71 | Completed | No
WO-26-003994 | 2.6 | Crossroads | CR-S08-06 | Preventive maintenance | P4 planned | 2026-04-22 | 2026-06-11 | 2026-06-11 | Internal line |  | 359.85 | Completed | No
WO-26-003995 | 4.7 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-04-22 | 2026-05-14 | 2026-05-15 | Internal line |  | 561.45 | Completed | No
WO-26-003996 | 7.7 | Crossroads | CR-S11-01 | Preventive maintenance | P4 planned | 2026-04-22 | 2026-06-14 | 2026-06-14 | Internal line |  | 311.26 | Completed | No
WO-26-003997 | 1 | Crossroads | CR-S16-03 | Service order - field | P2 same day | 2026-04-22 | 2026-04-23 | 2026-04-23 | Meter technician |  | 17.13 | Completed | No
WO-26-003998 | 1.4 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-04-22 | 2026-04-22 | 2026-04-22 | Meter technician |  | 27.98 | Completed | No
WO-26-003999 | 1.7 | Crossroads | CR-S24-04 | Service order - field | P2 same day | 2026-04-22 | 2026-04-23 | 2026-04-23 | Meter technician |  | 10.12 | Completed | No
WO-26-004000 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-22 | 2026-04-24 | 2026-05-02 | Internal line |  | 57 | Completed | No
WO-26-004001 | 7.5 | Crossroads | CR-S19-04 | Transformer replacement | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Internal line |  | 7706.88 | Completed | No
WO-26-004002 | 2.9 | Crossroads | CR-S16-03 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Internal line |  | 192.09 | Completed | No
WO-26-004003 | 4.6 | Crossroads | CR-S28-01 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 75.21 | Completed | No
WO-26-004004 | 3.6 | Crossroads | CR-S13-01 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Internal line |  | 322.94 | Completed | No
WO-26-004005 | 3.4 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 241.81 | Completed | No
WO-26-004006 | 6 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-04-22 | 2026-04-22 | 2026-04-22 | Troubleman |  | 343.75 | Completed | No
WO-26-004007 | 3 | Crossroads | CR-S24-03 | Trouble - partial or voltage | P3 within 10 days | 2026-04-22 | 2026-05-01 | 2026-05-01 | Troubleman |  | 43.55 | Completed | No
WO-26-004008 | 5.4 | Bayou | BY-S16-06 | Corrective maintenance | P4 planned | 2026-04-23 | 2026-05-14 | 2026-05-18 | Contract line | CT-04 | 2160.54 | Completed | No
WO-26-004009 | 11.7 | Bayou | BY-S09-02 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-04-28 | 2026-04-30 | Contract line | CT-04 | 487.85 | Completed | No
WO-26-004010 | 10 | Bayou | BY-S01-02 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-04-27 | 2026-04-27 | Contract line | CT-04 | 2237.74 | Completed | No
WO-26-004011 | 1.1 | Bayou | BY-S05-03 | Meter exchange | P4 planned | 2026-04-23 | 2026-06-01 | 2026-06-02 | Meter technician |  | 98.63 | Completed | No
WO-26-004012 | 0.6 | Bayou | BY-S10-01 | Meter exchange | P3 within 10 days | 2026-04-23 | 2026-05-01 | 2026-05-02 | Meter technician |  | 169.82 | Completed | No
WO-26-004013 | 0.9 | Bayou | BY-S10-04 | Meter exchange | P3 within 10 days | 2026-04-23 | 2026-04-27 | 2026-04-28 | Meter technician |  | 158.53 | Completed | No
WO-26-004014 | 1.1 | Bayou | BY-S20-03 | Meter exchange | P3 within 10 days | 2026-04-23 | 2026-04-28 | 2026-04-28 | Meter technician |  | 61.67 | Completed | No
WO-26-004015 | 5.6 | Bayou | BY-S10-02 | Preventive maintenance | P4 planned | 2026-04-23 | 2026-05-11 | 2026-05-13 | Contract line | CT-04 | 186.96 | Completed | No
WO-26-004016 |  | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-04-23 | 2026-06-08 |  | Internal line |  |  | Cancelled | No
WO-26-004017 | 1 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-04-23 | 2026-04-23 | 2026-04-23 | Meter technician |  | 2.2 | Completed | No
WO-26-004018 | 1.8 | Bayou | BY-S09-02 | Service order - field | P3 within 10 days | 2026-04-23 | 2026-04-28 | 2026-04-28 | Meter technician |  | 8.51 | Completed | No
WO-26-004019 | 1.1 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-04-23 | 2026-04-24 | 2026-04-24 | Meter technician |  | 25.41 | Completed | No
WO-26-004020 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-23 | 2026-04-26 | 2026-04-26 | Internal line |  | 53.13 | Completed | No
WO-26-004021 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-23 | 2026-05-01 | 2026-05-02 | Contract line | CT-04 | 359.82 | Completed | No
WO-26-004022 | 8.6 | Bayou | BY-S17-02 | Transformer replacement | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Internal line |  | 6112.68 | Completed | No
WO-26-004023 | 3 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 222.51 | Completed | No
WO-26-004024 | 2.3 | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 145.74 | Completed | No
WO-26-004025 | 4.8 | Bayou | BY-S16-01 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 214.94 | Completed | No
WO-26-004026 | 2.1 | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 283.81 | Completed | No
WO-26-004027 |  | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-05-01 |  | Internal line |  |  | Cancelled | No
WO-26-004028 | 7.6 | Crossroads | CR-S26-03 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-04-30 | 2026-05-04 | Internal line |  | 1236.11 | Completed | No
WO-26-004029 | 3.9 | Crossroads | CR-S08-04 | Corrective maintenance | P4 planned | 2026-04-23 | 2026-05-15 | 2026-05-15 | Underground crew |  | 2002.8 | Completed | No
WO-26-004030 | 11 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-05-01 | 2026-05-05 | Contract line | CT-01 | 899.65 | Completed | No
WO-26-004031 | 11.1 | Crossroads | CR-S19-03 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-05-01 | 2026-05-03 | Contract line | CT-01 | 1272.12 | Completed | No
WO-26-004032 | 8.4 | Crossroads | CR-S30-07 | Corrective maintenance | P4 planned | 2026-04-23 | 2026-05-02 | 2026-05-02 | Underground crew |  | 1382.06 | Completed | No
WO-26-004033 | 11.4 | Crossroads | CR-S18-04 | Corrective maintenance | P4 planned | 2026-04-23 | 2026-05-20 | 2026-05-20 | Contract line | CT-01 | 2293.53 | Completed | No
WO-26-004034 | 9.1 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-04-23 | 2026-04-25 | 2026-05-03 | Underground crew |  | 1741.72 | Completed | No
WO-26-004035 | 1.4 | Crossroads | CR-S05-05 | Meter exchange | P3 within 10 days | 2026-04-23 | 2026-05-03 | 2026-05-07 | Meter technician |  | 119.22 | Completed | No
WO-26-004036 | 6.9 | Crossroads | CR-S09-02 | New service - small | P4 planned | 2026-04-23 | 2026-05-29 | 2026-05-31 | Internal line |  | 3851.5 | Completed | No
WO-26-004037 | 14.3 | Crossroads | CR-S05-01 | New service - small | P4 planned | 2026-04-23 | 2026-06-15 | 2026-06-15 | Underground crew |  | 2564.34 | Completed | No
WO-26-004038 | 8.3 | Crossroads | CR-S28-02 | New service - small | P3 within 10 days | 2026-04-23 | 2026-04-25 | 2026-04-27 | Contract line | CT-01 | 791.57 | Completed | No
WO-26-004039 | 4.2 | Crossroads | CR-S26-02 | Preventive maintenance | P4 planned | 2026-04-23 | 2026-05-20 | 2026-05-20 | Underground crew |  | 32.91 | Completed | No
WO-26-004040 | 2.4 | Crossroads | CR-S22-02 | Preventive maintenance | P4 planned | 2026-04-23 | 2026-05-22 | 2026-05-22 | Internal line |  | 171 | Completed | No
WO-26-004041 | 7.4 | Crossroads | CR-S30-07 | Preventive maintenance | P4 planned | 2026-04-23 | 2026-06-12 | 2026-06-12 | Internal line |  | 478.28 | Completed | No
WO-26-004042 | 3.4 | Crossroads | CR-S25-04 | Preventive maintenance | P4 planned | 2026-04-23 | 2026-05-15 | 2026-05-19 | Internal line |  | 425.25 | Completed | No
WO-26-004043 | 1.5 | Crossroads | CR-S12-02 | Service order - field | P2 same day | 2026-04-23 | 2026-04-24 | 2026-04-24 | Meter technician |  | 1.92 | Completed | No
WO-26-004044 | 0.9 | Crossroads | CR-S02-03 | Service order - field | P3 within 10 days | 2026-04-23 | 2026-04-26 | 2026-04-27 | Meter technician |  | 35.21 | Completed | No
WO-26-004045 |  | Crossroads | CR-S16-04 | Service order - field | P3 within 10 days | 2026-04-23 | 2026-05-03 |  | Meter technician |  |  | Cancelled | No
WO-26-004046 | 1.2 | Crossroads | CR-S17-03 | Service order - field | P2 same day | 2026-04-23 | 2026-04-23 | 2026-04-23 | Meter technician |  | 28.92 | Completed | No
WO-26-004047 | 0.7 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-04-23 | 2026-05-03 | 2026-05-03 | Meter technician |  | 3.62 | Completed | No
WO-26-004048 | 0.8 | Crossroads | CR-S10-01 | Service order - field | P2 same day | 2026-04-23 | 2026-04-23 | 2026-04-23 | Meter technician |  | 24.12 | Completed | No
WO-26-004049 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-23 | 2026-04-29 | 2026-04-29 | Internal line |  | 220.23 | Completed | No
WO-26-004050 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-23 | 2026-04-29 | 2026-04-29 | Contract line | CT-02 | 428.71 | Completed | No
WO-26-004051 | 1.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-23 | 2026-04-26 | 2026-05-04 | Internal line |  | 215.09 | Completed | No
WO-26-004052 | 9.5 | Crossroads | CR-S27-04 | Transformer replacement | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Internal line |  | 4761.55 | Completed | No
WO-26-004053 | 5.5 | Crossroads | CR-S25-01 | Trouble - no power | P2 same day | 2026-04-23 | 2026-04-24 | 2026-04-24 | Internal line |  | 349.6 | Completed | No
WO-26-004054 | 5 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 100.06 | Completed | No
WO-26-004055 | 6 | Crossroads | CR-S10-02 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 318.83 | Completed | No
WO-26-004056 | 3.2 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Troubleman |  | 322.56 | Completed | No
WO-26-004057 | 3.6 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-04-23 | 2026-04-23 | 2026-04-23 | Internal line |  | 261.66 | Completed | No
WO-26-004058 |  | Crossroads | CR-S04-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-23 | 2026-04-29 |  | Internal line |  |  | Cancelled | No
WO-26-004059 | 11 | Bayou | BY-S20-01 | Corrective maintenance | P3 within 10 days | 2026-04-24 | 2026-05-01 | 2026-05-03 | Internal line |  | 126.53 | Completed | No
WO-26-004060 | 0.9 | Bayou | BY-S17-01 | Meter exchange | P4 planned | 2026-04-24 | 2026-06-01 | 2026-06-05 | Meter technician |  | 176.24 | Completed | No
WO-26-004061 | 1.4 | Bayou | BY-S04-03 | Meter exchange | P4 planned | 2026-04-24 | 2026-05-26 | 2026-06-03 | Meter technician |  | 70.2 | Completed | No
WO-26-004062 | 0.8 | Bayou | BY-S10-04 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-05-02 | 2026-05-03 | Meter technician |  | 155.2 | Completed | No
WO-26-004063 | 0.7 | Bayou | BY-S18-01 | Meter exchange | P4 planned | 2026-04-24 | 2026-05-10 | 2026-05-11 | Meter technician |  | 159.8 | Completed | No
WO-26-004064 | 1.2 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-04-30 | 2026-05-01 | Meter technician |  | 71.73 | Completed | No
WO-26-004065 | 1.2 | Bayou | BY-S02-02 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-04-26 | 2026-04-30 | Meter technician |  | 61.41 | Completed | No
WO-26-004066 | 0.9 | Bayou | BY-S26-02 | Meter exchange | P4 planned | 2026-04-24 | 2026-06-11 | 2026-06-11 | Meter technician |  | 156.82 | Completed | No
WO-26-004067 | 13.4 | Bayou | BY-S23-05 | New service - small | P3 within 10 days | 2026-04-24 | 2026-04-25 | 2026-04-25 | Contract line | CT-04 | 1392.4 | Completed | No
WO-26-004068 | 1.3 | Bayou | BY-S10-01 | Service order - field | P2 same day | 2026-04-24 | 2026-04-25 | 2026-04-25 | Meter technician |  | 5.5 | Completed | No
WO-26-004069 | 1.7 | Bayou | BY-S18-07 | Service order - field | P3 within 10 days | 2026-04-24 | 2026-04-29 | 2026-05-03 | Meter technician |  | 25.76 | Completed | No
WO-26-004070 | 2.3 | Bayou |  | Streetlight | P4 planned | 2026-04-24 | 2026-05-13 | 2026-05-14 | Contract line | CT-04 | 434.53 | Completed | No
WO-26-004071 | 1 | Bayou |  | Streetlight | P4 planned | 2026-04-24 | 2026-05-21 | 2026-05-21 | Contract line | CT-03 | 244.57 | Completed | No
WO-26-004072 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-24 | 2026-05-04 | 2026-05-04 | Internal line |  | 166.4 | Completed | No
WO-26-004073 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-24 | 2026-05-03 | 2026-05-11 | Contract line | CT-03 | 327.55 | Completed | No
WO-26-004074 | 1.7 | Bayou |  | Streetlight | P4 planned | 2026-04-24 | 2026-05-19 | 2026-05-21 | Contract line | CT-03 | 425.87 | Completed | No
WO-26-004075 | 9.4 | Bayou | BY-S16-01 | Transformer replacement | P1 emergency | 2026-04-24 | 2026-04-24 | 2026-04-24 | Internal line |  | 3132.65 | Completed | No
WO-26-004076 | 6.1 | Bayou | BY-S10-03 | Transformer replacement | P1 emergency | 2026-04-24 | 2026-04-24 | 2026-04-24 | Internal line |  | 5001.09 | Completed | No
WO-26-004077 | 4.9 | Bayou | BY-S06-01 | Trouble - no power | P2 same day | 2026-04-24 | 2026-04-24 | 2026-04-24 | Troubleman |  | 124.97 | Completed | No
WO-26-004078 | 4.5 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-04-24 | 2026-04-24 | 2026-04-24 | Troubleman |  | 214.57 | Completed | No
WO-26-004079 | 2.3 | Bayou | BY-S21-04 | Trouble - no power | P2 same day | 2026-04-24 | 2026-04-24 | 2026-04-24 | Troubleman |  | 263.69 | Completed | No
WO-26-004080 | 6.5 | Crossroads | CR-S08-06 | Corrective maintenance | P3 within 10 days | 2026-04-24 | 2026-05-01 | 2026-05-01 | Underground crew |  | 438.92 | Completed | No
WO-26-004081 | 8.3 | Crossroads | CR-S21-03 | Corrective maintenance | P4 planned | 2026-04-24 | 2026-05-23 | 2026-05-24 | Contract line | CT-01 | 469.38 | Completed | No
WO-26-004082 | 9.3 | Crossroads | CR-S13-04 | Corrective maintenance | P3 within 10 days | 2026-04-24 | 2026-05-01 | 2026-05-01 | Contract line | CT-02 | 1737.37 | Completed | No
WO-26-004083 | 0.8 | Crossroads | CR-S22-01 | Meter exchange | P4 planned | 2026-04-24 | 2026-05-29 | 2026-06-02 | Meter technician |  | 134.34 | Completed | No
WO-26-004084 |  | Crossroads | CR-S27-02 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-04-25 |  | Meter technician |  |  | Cancelled | No
WO-26-004085 | 1.4 | Crossroads | CR-S24-03 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-04-28 | 2026-04-28 | Meter technician |  | 89.14 | Completed | No
WO-26-004086 | 0.8 | Crossroads | CR-S19-04 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-05-04 | 2026-05-04 | Meter technician |  | 122.38 | Completed | No
WO-26-004087 | 1.4 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-05-04 | 2026-05-06 | Meter technician |  | 167.29 | Completed | No
WO-26-004088 | 1.4 | Crossroads | CR-S30-06 | Meter exchange | P3 within 10 days | 2026-04-24 | 2026-05-04 | 2026-05-05 | Meter technician |  | 154.51 | Completed | No
WO-26-004089 | 10.9 | Crossroads | CR-S32-03 | New service - small | P3 within 10 days | 2026-04-24 | 2026-04-26 | 2026-04-27 | Contract line | CT-01 | 2835.44 | Completed | No
WO-26-004090 | 19.6 | Crossroads | CR-S26-02 | Pole replacement | P2 same day | 2026-04-24 | 2026-04-25 | 2026-04-25 | Contract line | CT-01 | 1201.9 | Completed | No
WO-26-004091 | 22.7 | Crossroads | CR-S15-01 | Pole replacement | P3 within 10 days | 2026-04-24 | 2026-04-29 | 2026-04-29 | Internal line |  | 1233.43 | Completed | No
WO-26-004092 | 23.6 | Crossroads | CR-S09-01 | Pole replacement | P3 within 10 days | 2026-04-24 | 2026-04-29 | 2026-04-30 | Internal line |  | 2717.65 | Completed | No
WO-26-004093 | 5.9 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-04-24 | 2026-05-10 | 2026-05-10 | Contract line | CT-02 | 73.17 | Completed | No
WO-26-004094 | 6.6 | Crossroads | CR-S19-03 | Preventive maintenance | P4 planned | 2026-04-24 | 2026-05-04 | 2026-05-08 | Contract line | CT-01 | 479.29 | Completed | No
WO-26-004095 | 3 | Crossroads | CR-S16-06 | Preventive maintenance | P4 planned | 2026-04-24 | 2026-06-14 | 2026-06-14 | Internal line |  | 179.61 | Completed | No
WO-26-004096 | 0.6 | Crossroads | CR-S30-04 | Service order - field | P3 within 10 days | 2026-04-24 | 2026-05-04 | 2026-05-04 | Meter technician |  | 21.3 | Completed | No
WO-26-004097 | 1.8 | Crossroads | CR-S28-01 | Service order - field | P3 within 10 days | 2026-04-24 | 2026-05-04 | 2026-05-08 | Meter technician |  | 28.96 | Completed | No
WO-26-004098 |  | Crossroads | CR-S08-02 | Service order - field | P2 same day | 2026-04-24 | 2026-04-24 |  | Meter technician |  |  | Cancelled | No
WO-26-004099 | 1 | Crossroads |  | Streetlight | P4 planned | 2026-04-24 | 2026-06-14 | 2026-06-14 | Contract line | CT-02 | 236.32 | Completed | No
WO-26-004100 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-04-24 | 2026-05-24 | 2026-06-01 | Contract line | CT-01 | 312.77 | Completed | No
WO-26-004101 | 2.8 | Crossroads |  | Streetlight | P4 planned | 2026-04-24 | 2026-06-01 | 2026-06-01 | Contract line | CT-02 | 402.94 | Completed | No
WO-26-004102 | 9.8 | Crossroads | CR-S11-01 | Transformer replacement | P1 emergency | 2026-04-24 | 2026-04-24 | 2026-04-24 | Internal line |  | 10842.96 | Completed | No
WO-26-004103 | 9.6 | Crossroads | CR-S02-05 | Transformer replacement | P3 within 10 days | 2026-04-24 | 2026-04-29 | 2026-04-29 | Internal line |  | 5129.3 | Completed | No
WO-26-004104 | 2.9 | Crossroads | CR-S25-03 | Trouble - no power | P1 emergency | 2026-04-24 | 2026-04-24 | 2026-04-24 | Troubleman |  | 189.18 | Completed | No
WO-26-004105 | 5 | Crossroads | CR-S13-06 | Trouble - no power | P2 same day | 2026-04-24 | 2026-04-24 | 2026-04-24 | Troubleman |  | 18.34 | Completed | No
WO-26-004106 | 2.8 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-04-24 | 2026-04-25 | 2026-04-25 | Troubleman |  | 160.93 | Completed | No
WO-26-004107 | 1.5 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Meter technician |  | 12.7 | Completed | No
WO-26-004108 | 1 | Bayou | BY-S18-05 | Service order - field | P2 same day | 2026-04-25 | 2026-04-25 | 2026-04-25 | Meter technician |  | 22.68 | Completed | No
WO-26-004109 | 2.2 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 152.97 | Completed | No
WO-26-004110 | 4.2 | Bayou | BY-S18-05 | Trouble - no power | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Troubleman |  | 226.27 | Completed | No
WO-26-004111 | 5 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 330.63 | Completed | No
WO-26-004112 | 5.8 | Bayou | BY-S25-01 | Trouble - no power | P2 same day | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 145.01 | Completed | No
WO-26-004113 | 1.8 | Bayou | BY-S25-01 | Trouble - partial or voltage | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Internal line |  | 91.12 | Completed | No
WO-26-004114 | 3.9 | Bayou | BY-S17-02 | Trouble - partial or voltage | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Troubleman |  | 183.68 | Completed | No
WO-26-004115 | 0.8 | Crossroads | CR-S03-01 | Service order - field | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Meter technician |  | 14.26 | Completed | No
WO-26-004116 | 1 | Crossroads | CR-S09-03 | Service order - field | P2 same day | 2026-04-25 | 2026-04-25 | 2026-04-25 | Meter technician |  | 2.83 | Completed | No
WO-26-004117 | 4.9 | Crossroads | CR-S21-03 | Trouble - no power | P2 same day | 2026-04-25 | 2026-04-25 | 2026-04-25 | Internal line |  | 120.29 | Completed | No
WO-26-004118 | 2.8 | Crossroads | CR-S07-06 | Trouble - no power | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Troubleman |  | 326.99 | Completed | No
WO-26-004119 | 3 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 148.91 | Completed | No
WO-26-004120 | 3.5 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-04-25 | 2026-04-26 | 2026-04-26 | Troubleman |  | 221.3 | Completed | No
WO-26-004121 | 5.8 | Crossroads | CR-S25-03 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Internal line |  | 309.36 | Completed | No
WO-26-004122 | 2.2 | Crossroads | CR-S27-01 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 157.29 | Completed | No
WO-26-004123 | 2.5 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 161.66 | Completed | No
WO-26-004124 | 3.9 | Crossroads | CR-S11-02 | Trouble - no power | P2 same day | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 346.3 | Completed | No
WO-26-004125 | 2.2 | Crossroads | CR-S09-04 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 200.83 | Completed | No
WO-26-004126 | 4 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 107.61 | Completed | No
WO-26-004127 | 4.8 | Crossroads | CR-S19-04 | Trouble - partial or voltage | P2 same day | 2026-04-25 | 2026-04-25 | 2026-04-25 | Troubleman |  | 194.24 | Completed | No
WO-26-004128 | 2 | Bayou | BY-S04-03 | Service order - field | P2 same day | 2026-04-26 | 2026-04-26 | 2026-04-26 | Meter technician |  | 5.85 | Completed | No
WO-26-004129 | 1.5 | Bayou | BY-S14-01 | Service order - field | P2 same day | 2026-04-26 | 2026-04-26 | 2026-04-26 | Meter technician |  | 31.29 | Completed | No
WO-26-004130 | 2.8 | Bayou | BY-S28-03 | Trouble - no power | P1 emergency | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 60.81 | Completed | No
WO-26-004131 | 4.4 | Bayou | BY-S14-02 | Trouble - no power | P2 same day | 2026-04-26 | 2026-04-27 | 2026-04-27 | Troubleman |  | 220.01 | Completed | No
WO-26-004132 | 2.3 | Bayou | BY-S05-02 | Trouble - no power | P1 emergency | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 184.54 | Completed | No
WO-26-004133 | 2.8 | Bayou | BY-S09-03 | Trouble - no power | P1 emergency | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 68.14 | Completed | No
WO-26-004134 | 3.6 | Bayou | BY-S27-03 | Trouble - no power | P1 emergency | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 50.38 | Completed | No
WO-26-004135 | 2.9 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 220.45 | Completed | No
WO-26-004136 | 3.2 | Bayou | BY-S07-03 | Trouble - partial or voltage | P2 same day | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 45.37 | Completed | No
WO-26-004137 | 7.5 | Crossroads | CR-S30-06 | Corrective maintenance | P2 same day | 2026-04-26 | 2026-04-27 | 2026-04-27 | Internal line |  | 2235.99 | Completed | No
WO-26-004138 | 4 | Crossroads | CR-S27-04 | Corrective maintenance | P2 same day | 2026-04-26 | 2026-04-26 | 2026-04-26 | Underground crew |  | 2180.26 | Completed | No
WO-26-004139 | 1.7 | Crossroads | CR-S09-02 | Service order - field | P2 same day | 2026-04-26 | 2026-04-27 | 2026-04-27 | Meter technician |  | 18.89 | Completed | No
WO-26-004140 | 14 | Crossroads | CR-S21-03 | Transformer replacement | P2 same day | 2026-04-26 | 2026-04-27 | 2026-04-27 | Internal line |  | 12390.5 | Completed | No
WO-26-004141 | 6.4 | Crossroads | CR-S09-05 | Transformer replacement | P2 same day | 2026-04-26 | 2026-04-27 | 2026-04-27 | Contract line | CT-02 | 12200.23 | Completed | No
WO-26-004142 | 4 | Crossroads | CR-S22-01 | Trouble - no power | P2 same day | 2026-04-26 | 2026-04-27 | 2026-04-27 | Troubleman |  | 264.88 | Completed | No
WO-26-004143 | 2.4 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 281.1 | Completed | No
WO-26-004144 | 4.2 | Crossroads | CR-S04-02 | Trouble - no power | P2 same day | 2026-04-26 | 2026-04-26 | 2026-04-26 | Troubleman |  | 116.26 | Completed | No
WO-26-004145 | 7.5 | Bayou | BY-S18-07 | Corrective maintenance | P3 within 10 days | 2026-04-27 | 2026-05-06 | 2026-05-06 | Underground crew |  | 741.99 | Completed | No
WO-26-004146 |  | Bayou | BY-S12-01 | Corrective maintenance | P3 within 10 days | 2026-04-27 | 2026-04-30 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-004147 | 1.2 | Bayou | BY-S12-04 | Meter exchange | P3 within 10 days | 2026-04-27 | 2026-04-30 | 2026-04-30 | Meter technician |  | 162.55 | Completed | No
WO-26-004148 | 1.3 | Bayou | BY-S07-06 | Meter exchange | P4 planned | 2026-04-27 | 2026-06-15 | 2026-06-19 | Meter technician |  | 174.57 | Completed | No
WO-26-004149 | 1.2 | Bayou | BY-S23-04 | Meter exchange | P4 planned | 2026-04-27 | 2026-05-08 | 2026-05-09 | Meter technician |  | 91.8 | Completed | No
WO-26-004150 | 0.9 | Bayou | BY-S01-01 | Meter exchange | P3 within 10 days | 2026-04-27 | 2026-05-04 | 2026-05-06 | Meter technician |  | 127.77 | Completed | No
WO-26-004151 | 6.2 | Bayou | BY-S25-03 | New service - small | P4 planned | 2026-04-27 | 2026-06-07 | 2026-06-07 | Internal line |  | 2508.19 | Completed | No
WO-26-004152 | 5.8 | Bayou | BY-S16-01 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-05-10 | 2026-05-12 | Internal line |  | 353.98 | Completed | No
WO-26-004153 | 4.5 | Bayou | BY-S19-03 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-05-27 | 2026-05-27 | Contract line | CT-04 | 526.53 | Completed | No
WO-26-004154 | 6.3 | Bayou | BY-S12-03 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-06-08 | 2026-06-08 | Contract line | CT-03 | 598.03 | Completed | No
WO-26-004155 | 1.7 | Bayou | BY-S24-01 | Service order - field | P2 same day | 2026-04-27 | 2026-04-27 | 2026-04-27 | Meter technician |  | 26.47 | Completed | No
WO-26-004156 | 1.8 | Bayou | BY-S07-01 | Service order - field | P2 same day | 2026-04-27 | 2026-04-28 | 2026-04-28 | Meter technician |  | 25.63 | Completed | No
WO-26-004157 | 0.5 | Bayou | BY-S19-01 | Service order - field | P2 same day | 2026-04-27 | 2026-04-28 | 2026-04-28 | Meter technician |  | 10.34 | Completed | No
WO-26-004158 | 3.7 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Internal line |  | 212.3 | Completed | No
WO-26-004159 | 2.1 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 76.45 | Completed | No
WO-26-004160 | 4.3 | Bayou | BY-S28-03 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Internal line |  | 83.68 | Completed | No
WO-26-004161 | 2.9 | Bayou | BY-S25-02 | Trouble - no power | P2 same day | 2026-04-27 | 2026-04-28 | 2026-04-28 | Troubleman |  | 226.13 | Completed | No
WO-26-004162 | 6.6 | Crossroads | CR-S32-02 | Corrective maintenance | P4 planned | 2026-04-27 | 2026-06-23 | 2026-07-01 | Internal line |  | 2079.18 | Completed | No
WO-26-004163 | 4.4 | Crossroads | CR-S25-01 | Corrective maintenance | P2 same day | 2026-04-27 | 2026-04-28 | 2026-04-28 | Underground crew |  | 1804.39 | Completed | No
WO-26-004164 | 0.9 | Crossroads | CR-S32-05 | Meter exchange | P3 within 10 days | 2026-04-27 | 2026-05-05 | 2026-05-13 | Meter technician |  | 71.18 | Completed | No
WO-26-004165 | 1.1 | Crossroads | CR-S16-04 | Meter exchange | P4 planned | 2026-04-27 | 2026-05-29 | 2026-05-29 | Meter technician |  | 104.62 | Completed | No
WO-26-004166 | 1.4 | Crossroads | CR-S25-02 | Meter exchange | P4 planned | 2026-04-27 | 2026-05-27 | 2026-05-29 | Meter technician |  | 102.6 | Completed | No
WO-26-004167 | 0.9 | Crossroads | CR-S13-03 | Meter exchange | P3 within 10 days | 2026-04-27 | 2026-05-01 | 2026-05-01 | Meter technician |  | 131.1 | Completed | No
WO-26-004168 | 0.7 | Crossroads | CR-S03-01 | Meter exchange | P3 within 10 days | 2026-04-27 | 2026-05-04 | 2026-05-04 | Meter technician |  | 99.54 | Completed | No
WO-26-004169 | 20.1 | Crossroads | CR-S07-07 | Pole replacement | P4 planned | 2026-04-27 | 2026-05-11 | 2026-05-11 | Internal line |  | 1633.85 | Completed | No
WO-26-004170 | 7.9 | Crossroads | CR-S19-03 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-05-05 | 2026-05-05 | Contract line | CT-01 | 549.88 | Completed | No
WO-26-004171 | 7.5 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-05-06 | 2026-05-07 | Underground crew |  | 96.5 | Completed | No
WO-26-004172 | 4.9 | Crossroads | CR-S01-01 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-05-14 | 2026-05-14 | Underground crew |  | 21.57 | Completed | No
WO-26-004173 | 4.9 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-04-27 | 2026-05-29 | 2026-06-06 | Internal line |  | 67.54 | Completed | No
WO-26-004174 |  | Crossroads | CR-S28-04 | Service order - field | P3 within 10 days | 2026-04-27 | 2026-04-29 |  | Meter technician |  |  | Cancelled | No
WO-26-004175 | 0.7 | Crossroads | CR-S17-02 | Service order - field | P2 same day | 2026-04-27 | 2026-04-28 | 2026-04-28 | Meter technician |  | 23 | Completed | No
WO-26-004176 | 2.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-27 | 2026-05-03 | 2026-05-03 | Contract line | CT-01 | 139.02 | Completed | No
WO-26-004177 | 5.1 | Crossroads | CR-S30-01 | Trouble - no power | P2 same day | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 125.26 | Completed | No
WO-26-004178 | 5.2 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 211.28 | Completed | No
WO-26-004179 |  | Crossroads | CR-S05-01 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 |  | Troubleman |  |  | Cancelled | No
WO-26-004180 | 2.7 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 274.69 | Completed | No
WO-26-004181 | 5.7 | Crossroads | CR-S13-01 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 137.66 | Completed | No
WO-26-004182 | 5.6 | Crossroads | CR-S30-06 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 89.75 | Completed | No
WO-26-004183 | 4.2 | Crossroads | CR-S05-06 | Trouble - no power | P2 same day | 2026-04-27 | 2026-04-28 | 2026-04-28 | Troubleman |  | 11.33 | Completed | No
WO-26-004184 | 4.8 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 115.13 | Completed | No
WO-26-004185 | 2.1 | Crossroads | CR-S27-03 | Trouble - partial or voltage | P3 within 10 days | 2026-04-27 | 2026-05-05 | 2026-05-05 | Troubleman |  | 134.8 | Completed | No
WO-26-004186 | 2.1 | Crossroads | CR-S07-05 | Trouble - partial or voltage | P3 within 10 days | 2026-04-27 | 2026-05-03 | 2026-05-03 | Internal line |  | 82.75 | Completed | No
WO-26-004187 | 3.5 | Crossroads | CR-S31-03 | Trouble - partial or voltage | P2 same day | 2026-04-27 | 2026-04-27 | 2026-04-27 | Troubleman |  | 126.23 | Completed | No
WO-26-004188 | 4.4 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-27 | 2026-05-04 | 2026-05-08 | Troubleman |  | 46.08 | Completed | No
WO-26-004189 | 8.5 | Bayou | BY-S25-04 | Corrective maintenance | P3 within 10 days | 2026-04-28 | 2026-05-05 | 2026-05-05 | Internal line |  | 879.22 | Completed | No
WO-26-004190 | 6.9 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-04-28 | 2026-04-29 | 2026-04-30 | Underground crew |  | 1787.26 | Completed | No
WO-26-004191 | 11.5 | Bayou | BY-S16-02 | Corrective maintenance | P2 same day | 2026-04-28 | 2026-04-29 | 2026-04-29 | Internal line |  | 2127.44 | Completed | No
WO-26-004192 | 8.6 | Bayou | BY-S12-01 | Corrective maintenance | P3 within 10 days | 2026-04-28 | 2026-05-03 | 2026-05-03 | Internal line |  | 1581.4 | Completed | No
WO-26-004193 | 6.6 | Bayou | BY-S30-01 | Corrective maintenance | P4 planned | 2026-04-28 | 2026-06-24 | 2026-06-24 | Contract line | CT-03 | 1481.56 | Completed | No
WO-26-004194 | 1.5 | Bayou | BY-S29-04 | Meter exchange | P4 planned | 2026-04-28 | 2026-05-16 | 2026-05-17 | Meter technician |  | 96.54 | Completed | No
WO-26-004195 | 1.4 | Bayou | BY-S03-03 | Meter exchange | P4 planned | 2026-04-28 | 2026-06-20 | 2026-06-20 | Meter technician |  | 65.04 | Completed | No
WO-26-004196 | 0.6 | Bayou | BY-S11-01 | Meter exchange | P4 planned | 2026-04-28 | 2026-05-09 | 2026-05-13 | Meter technician |  | 114.39 | Completed | No
WO-26-004197 | 1 | Bayou | BY-S18-03 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-04-30 | 2026-04-30 | Meter technician |  | 154.89 | Completed | No
WO-26-004198 | 1.1 | Bayou | BY-S09-04 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-05-08 | 2026-05-09 | Meter technician |  | 119.22 | Completed | No
WO-26-004199 | 0.9 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-05-01 | 2026-05-03 | Meter technician |  | 139.58 | Completed | No
WO-26-004200 | 1.1 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-04-30 | 2026-04-30 | Meter technician |  | 133.84 | Completed | No
WO-26-004201 | 14.7 | Bayou | BY-S30-01 | New service - small | P4 planned | 2026-04-28 | 2026-06-01 | 2026-06-01 | Contract line | CT-03 | 2656.25 | Completed | No
WO-26-004202 |  | Bayou | BY-S06-01 | New service - small | P4 planned | 2026-04-28 | 2026-06-17 |  | Internal line |  |  | Cancelled | No
WO-26-004203 | 2.3 | Bayou | BY-S21-02 | Preventive maintenance | P4 planned | 2026-04-28 | 2026-06-25 | 2026-06-25 | Underground crew |  | 225.74 | Completed | No
WO-26-004204 | 2.8 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-04-28 | 2026-06-26 | 2026-06-26 | Contract line | CT-04 | 84.65 | Completed | No
WO-26-004205 | 1.3 | Bayou | BY-S21-01 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-05-03 | 2026-05-04 | Meter technician |  | 6.28 | Completed | No
WO-26-004206 | 0.5 | Bayou | BY-S16-02 | Service order - field | P2 same day | 2026-04-28 | 2026-04-28 | 2026-04-28 | Meter technician |  | 0.75 | Completed | No
WO-26-004207 | 1.1 | Bayou |  | Streetlight | P4 planned | 2026-04-28 | 2026-05-19 | 2026-05-19 | Contract line | CT-03 | 408.3 | Completed | No
WO-26-004208 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-28 | 2026-05-06 | 2026-05-10 | Contract line | CT-04 | 244.9 | Completed | No
WO-26-004209 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-04-28 | 2026-05-07 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-004210 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-04-28 | 2026-05-08 | 2026-05-08 | Contract line | CT-04 | 286.22 | Completed | No
WO-26-004211 | 13.7 | Bayou | BY-S27-03 | Transformer replacement | P3 within 10 days | 2026-04-28 | 2026-05-03 | 2026-05-03 | Contract line | CT-04 | 6722.34 | Completed | No
WO-26-004212 | 13.7 | Bayou | BY-S21-02 | Transformer replacement | P1 emergency | 2026-04-28 | 2026-04-28 | 2026-04-28 | Internal line |  | 9166.09 | Completed | No
WO-26-004213 | 3.5 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 335.51 | Completed | No
WO-26-004214 | 4.8 | Bayou | BY-S29-02 | Trouble - no power | P2 same day | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 108.01 | Completed | No
WO-26-004215 | 2.6 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-04-28 | 2026-04-28 | 2026-04-28 | Internal line |  | 16.5 | Completed | No
WO-26-004216 | 10.6 | Crossroads | CR-S20-04 | Corrective maintenance | P3 within 10 days | 2026-04-28 | 2026-05-04 | 2026-05-04 | Internal line |  | 2273.08 | Completed | No
WO-26-004217 | 4.9 | Crossroads | CR-S04-02 | Corrective maintenance | P4 planned | 2026-04-28 | 2026-06-20 | 2026-06-20 | Underground crew |  | 1484.2 | Completed | No
WO-26-004218 | 10.6 | Crossroads | CR-S18-04 | Corrective maintenance | P3 within 10 days | 2026-04-28 | 2026-05-08 | 2026-05-08 | Internal line |  | 1978.16 | Completed | No
WO-26-004219 | 6 | Crossroads | CR-S04-06 | Corrective maintenance | P4 planned | 2026-04-28 | 2026-05-28 | 2026-05-29 | Internal line |  | 1540.92 | Completed | No
WO-26-004220 | 8 | Crossroads | CR-S08-02 | Corrective maintenance | P3 within 10 days | 2026-04-28 | 2026-05-07 | 2026-05-11 | Underground crew |  | 1264.79 | Completed | No
WO-26-004221 | 0.8 | Crossroads | CR-S20-01 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-05-04 | 2026-05-04 | Meter technician |  | 102.21 | Completed | No
WO-26-004222 | 0.5 | Crossroads | CR-S23-03 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-05-05 | 2026-05-05 | Meter technician |  | 119.55 | Completed | No
WO-26-004223 | 0.9 | Crossroads | CR-S01-01 | Meter exchange | P3 within 10 days | 2026-04-28 | 2026-05-06 | 2026-05-06 | Meter technician |  | 102.76 | Completed | No
WO-26-004224 | 16.4 | Crossroads | CR-S02-01 | Pole replacement | P4 planned | 2026-04-28 | 2026-05-14 | 2026-05-14 | Contract line | CT-02 | 3087.52 | Completed | No
WO-26-004225 | 5.9 | Crossroads | CR-S18-03 | Preventive maintenance | P4 planned | 2026-04-28 | 2026-05-29 | 2026-05-29 | Underground crew |  | 79.22 | Completed | No
WO-26-004226 | 2.9 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-04-28 | 2026-06-23 | 2026-06-23 | Underground crew |  | 427.7 | Completed | No
WO-26-004227 | 1.7 | Crossroads | CR-S32-02 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-05-03 | 2026-05-04 | Meter technician |  | 3.34 | Completed | No
WO-26-004228 | 1.2 | Crossroads | CR-S25-05 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-05-02 | 2026-05-02 | Meter technician |  | 20.74 | Completed | No
WO-26-004229 | 1.3 | Crossroads | CR-S30-02 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-05-08 | 2026-05-10 | Meter technician |  | 38.47 | Completed | No
WO-26-004230 | 1.1 | Crossroads | CR-S09-01 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-04-29 | 2026-04-30 | Meter technician |  | 10.74 | Completed | No
WO-26-004231 | 0.9 | Crossroads | CR-S19-04 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-05-05 | 2026-05-05 | Meter technician |  | 30.06 | Completed | No
WO-26-004232 | 1.9 | Crossroads | CR-S10-02 | Service order - field | P3 within 10 days | 2026-04-28 | 2026-05-05 | 2026-05-05 | Meter technician |  | 9.79 | Completed | No
WO-26-004233 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-28 | 2026-05-03 | 2026-05-04 | Internal line |  | 179.18 | Completed | No
WO-26-004234 | 3.6 | Crossroads | CR-S24-02 | Trouble - no power | P1 emergency | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 278.5 | Completed | No
WO-26-004235 | 5.8 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 248.71 | Completed | No
WO-26-004236 | 5.3 | Crossroads | CR-S04-02 | Trouble - no power | P1 emergency | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 219.88 | Completed | No
WO-26-004237 | 2.3 | Crossroads | CR-S04-05 | Trouble - no power | P1 emergency | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 215.04 | Completed | No
WO-26-004238 | 5.2 | Crossroads | CR-S20-01 | Trouble - no power | P2 same day | 2026-04-28 | 2026-04-29 | 2026-04-29 | Troubleman |  | 228.85 | Completed | No
WO-26-004239 | 3.3 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P2 same day | 2026-04-28 | 2026-04-28 | 2026-04-28 | Troubleman |  | 44.05 | Completed | No
WO-26-004240 | 8.5 | Bayou | BY-S19-03 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-05-08 | 2026-05-08 | Internal line |  | 543.05 | Completed | No
WO-26-004241 | 9.8 | Bayou | BY-S10-02 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-05-04 | 2026-05-04 | Contract line | CT-03 | 1975.47 | Completed | No
WO-26-004242 | 7.9 | Bayou | BY-S13-05 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-05-08 | 2026-05-09 | Internal line |  | 85.8 | Completed | No
WO-26-004243 | 3.9 | Bayou | BY-S26-05 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-05-09 | 2026-05-09 | Underground crew |  | 1961.44 | Completed | No
WO-26-004244 | 1.1 | Bayou | BY-S28-01 | Meter exchange | P3 within 10 days | 2026-04-29 | 2026-05-08 | 2026-05-08 | Meter technician |  | 61.53 | Completed | No
WO-26-004245 | 1 | Bayou | BY-S11-02 | Meter exchange | P3 within 10 days | 2026-04-29 | 2026-05-02 | 2026-05-02 | Meter technician |  | 63.57 | Completed | No
WO-26-004246 | 1.3 | Bayou | BY-S12-03 | Meter exchange | P4 planned | 2026-04-29 | 2026-05-14 | 2026-05-22 | Meter technician |  | 84.2 | Completed | No
WO-26-004247 | 21.2 | Bayou | BY-S13-06 | Pole replacement | P3 within 10 days | 2026-04-29 | 2026-05-01 | 2026-05-09 | Contract line | CT-04 | 2671.04 | Completed | No
WO-26-004248 | 19.2 | Bayou | BY-S27-03 | Pole replacement | P4 planned | 2026-04-29 | 2026-06-05 | 2026-06-05 | Contract line | CT-03 | 2500.39 | Completed | No
WO-26-004249 | 3.8 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-04-29 | 2026-05-28 | 2026-05-28 | Underground crew |  | 14.32 | Completed | No
WO-26-004250 | 6 | Bayou | BY-S18-02 | Preventive maintenance | P4 planned | 2026-04-29 | 2026-06-24 | 2026-06-24 | Internal line |  | 387.27 | Completed | No
WO-26-004251 | 1.1 | Bayou | BY-S09-03 | Service order - field | P2 same day | 2026-04-29 | 2026-04-30 | 2026-04-30 | Meter technician |  | 9.48 | Completed | No
WO-26-004252 | 0.8 | Bayou | BY-S23-01 | Service order - field | P3 within 10 days | 2026-04-29 | 2026-05-06 | 2026-05-06 | Meter technician |  | 38.77 | Completed | No
WO-26-004253 | 1.8 | Bayou | BY-S08-01 | Service order - field | P2 same day | 2026-04-29 | 2026-04-30 | 2026-04-30 | Meter technician |  | 3.49 | Completed | No
WO-26-004254 | 2.6 | Bayou | BY-S16-01 | Trouble - no power | P2 same day | 2026-04-29 | 2026-04-30 | 2026-04-30 | Internal line |  | 21.48 | Completed | No
WO-26-004255 | 3.2 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 58.87 | Completed | No
WO-26-004256 | 2.6 | Bayou | BY-S10-05 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 317.05 | Completed | No
WO-26-004257 | 5.9 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 102.99 | Completed | No
WO-26-004258 | 2.5 | Bayou | BY-S30-03 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 184.65 | Completed | No
WO-26-004259 | 4.6 | Bayou | BY-S29-05 | Trouble - partial or voltage | P2 same day | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 53.1 | Completed | No
WO-26-004260 | 3.1 | Bayou | BY-S30-01 | Trouble - partial or voltage | P3 within 10 days | 2026-04-29 | 2026-05-09 | 2026-05-11 | Troubleman |  | 86.35 | Completed | No
WO-26-004261 | 3.3 | Bayou | BY-S10-01 | Trouble - partial or voltage | P2 same day | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 211.73 | Completed | No
WO-26-004262 | 3.8 | Bayou | BY-S10-01 | Trouble - partial or voltage | P2 same day | 2026-04-29 | 2026-04-30 | 2026-04-30 | Troubleman |  | 54.98 | Completed | No
WO-26-004263 | 6.6 | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-04-30 | 2026-05-02 | Internal line |  | 2314.77 | Completed | No
WO-26-004264 | 11.3 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-05-07 | 2026-05-07 | Internal line |  | 2133.98 | Completed | No
WO-26-004265 | 9.4 | Crossroads | CR-S13-04 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-04-30 | 2026-05-02 | Underground crew |  | 236.35 | Completed | No
WO-26-004266 | 10.4 | Crossroads | CR-S04-03 | Corrective maintenance | P4 planned | 2026-04-29 | 2026-06-12 | 2026-06-12 | Internal line |  | 567.32 | Completed | No
WO-26-004267 | 6.5 | Crossroads | CR-S26-03 | Corrective maintenance | P2 same day | 2026-04-29 | 2026-04-29 | 2026-04-29 | Internal line |  | 802.59 | Completed | No
WO-26-004268 | 6.2 | Crossroads | CR-S03-02 | Corrective maintenance | P3 within 10 days | 2026-04-29 | 2026-05-02 | 2026-05-02 | Underground crew |  | 1653.68 | Completed | No
WO-26-004269 | 1 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-04-29 | 2026-05-05 | 2026-05-05 | Meter technician |  | 77.11 | Completed | No
WO-26-004270 | 1.1 | Crossroads | CR-S23-02 | Meter exchange | P4 planned | 2026-04-29 | 2026-05-14 | 2026-05-15 | Meter technician |  | 176.97 | Completed | No
WO-26-004271 | 0.5 | Crossroads | CR-S24-04 | Meter exchange | P3 within 10 days | 2026-04-29 | 2026-04-30 | 2026-04-30 | Meter technician |  | 158.71 | Completed | No
WO-26-004272 | 0.9 | Crossroads | CR-S10-02 | Meter exchange | P3 within 10 days | 2026-04-29 | 2026-05-08 | 2026-05-08 | Meter technician |  | 148.51 | Completed | No
WO-26-004273 | 12.3 | Crossroads | CR-S28-01 | New service - small | P4 planned | 2026-04-29 | 2026-06-23 | 2026-06-25 | Internal line |  | 3035.42 | Completed | No
WO-26-004274 | 16.6 | Crossroads | CR-S07-01 | Pole replacement | P4 planned | 2026-04-29 | 2026-06-21 | 2026-06-21 | Internal line |  | 2489.33 | Completed | No
WO-26-004275 | 7.1 | Crossroads | CR-S27-02 | Preventive maintenance | P4 planned | 2026-04-29 | 2026-05-21 | 2026-05-29 | Underground crew |  | 366.49 | Completed | No
WO-26-004276 | 2 | Crossroads |  | Streetlight | P4 planned | 2026-04-29 | 2026-05-11 | 2026-05-11 | Contract line | CT-02 | 360.24 | Completed | No
WO-26-004277 | 1.1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-29 | 2026-05-04 | 2026-05-12 | Internal line |  | 98.65 | Completed | No
WO-26-004278 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-29 | 2026-05-03 | 2026-05-03 | Contract line | CT-01 | 75.79 | Completed | No
WO-26-004279 | 10.1 | Crossroads | CR-S10-02 | Transformer replacement | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Internal line |  | 8997.5 | Completed | No
WO-26-004280 |  | Crossroads | CR-S02-05 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 |  | Troubleman |  |  | Cancelled | No
WO-26-004281 | 2.9 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 207.52 | Completed | No
WO-26-004282 | 3.2 | Crossroads | CR-S08-06 | Trouble - no power | P2 same day | 2026-04-29 | 2026-04-30 | 2026-04-30 | Internal line |  | 77.7 | Completed | No
WO-26-004283 | 4 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 194.55 | Completed | No
WO-26-004284 | 3.8 | Crossroads | CR-S05-03 | Trouble - no power | P1 emergency | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 119.95 | Completed | No
WO-26-004285 | 2.8 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 122.9 | Completed | No
WO-26-004286 | 1.7 | Crossroads | CR-S13-04 | Trouble - partial or voltage | P2 same day | 2026-04-29 | 2026-04-29 | 2026-04-29 | Troubleman |  | 157.15 | Completed | No
WO-26-004287 | 3.4 | Crossroads | CR-S10-02 | Trouble - partial or voltage | P2 same day | 2026-04-29 | 2026-04-30 | 2026-04-30 | Troubleman |  | 95 | Completed | No
WO-26-004288 | 3.3 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-29 | 2026-04-30 | 2026-04-30 | Troubleman |  | 60.74 | Completed | No
WO-26-004289 | 6.3 | Bayou | BY-S29-01 | Corrective maintenance | P3 within 10 days | 2026-04-30 | 2026-05-02 | 2026-05-02 | Contract line | CT-04 | 1813.13 | Completed | No
WO-26-004290 | 3.9 | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-04-30 | 2026-05-09 | 2026-05-10 | Underground crew |  | 1517.66 | Completed | No
WO-26-004291 | 10.1 | Bayou | BY-S21-05 | Corrective maintenance | P3 within 10 days | 2026-04-30 | 2026-05-04 | 2026-05-04 | Internal line |  | 693.56 | Completed | No
WO-26-004292 | 0.6 | Bayou | BY-S13-05 | Meter exchange | P3 within 10 days | 2026-04-30 | 2026-05-08 | 2026-05-08 | Meter technician |  | 158.83 | Completed | No
WO-26-004293 | 1.4 | Bayou | BY-S17-01 | Meter exchange | P4 planned | 2026-04-30 | 2026-06-04 | 2026-06-04 | Meter technician |  | 147.62 | Completed | No
WO-26-004294 | 0.7 | Bayou | BY-S08-03 | Meter exchange | P3 within 10 days | 2026-04-30 | 2026-05-01 | 2026-05-01 | Meter technician |  | 138.7 | Completed | No
WO-26-004295 | 0.6 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-04-30 | 2026-05-05 | 2026-05-05 | Meter technician |  | 94.38 | Completed | No
WO-26-004296 | 7.2 | Bayou | BY-S22-01 | Preventive maintenance | P4 planned | 2026-04-30 | 2026-05-26 | 2026-05-27 | Internal line |  | 359.2 | Completed | No
WO-26-004297 | 2 | Bayou | BY-S29-03 | Preventive maintenance | P4 planned | 2026-04-30 | 2026-06-29 | 2026-06-29 | Internal line |  | 509.07 | Completed | No
WO-26-004298 | 1.2 | Bayou | BY-S26-05 | Service order - field | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Meter technician |  | 40 | Completed | No
WO-26-004299 | 6.9 | Bayou | BY-S10-04 | Transformer replacement | P3 within 10 days | 2026-04-30 | 2026-05-07 | 2026-05-07 | Internal line |  | 11901.51 | Completed | No
WO-26-004300 | 9.4 | Bayou | BY-S27-01 | Transformer replacement | P1 emergency | 2026-04-30 | 2026-04-30 | 2026-04-30 | Internal line |  | 11857.44 | Completed | No
WO-26-004301 | 5.9 | Bayou | BY-S09-02 | Trouble - no power | P1 emergency | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 343.73 | Completed | No
WO-26-004302 | 2 | Bayou | BY-S03-03 | Trouble - no power | P1 emergency | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 158.38 | Completed | No
WO-26-004303 | 4.5 | Bayou | BY-S08-03 | Trouble - no power | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 153.74 | Completed | No
WO-26-004304 | 2.8 | Bayou | BY-S26-04 | Trouble - no power | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Internal line |  | 277.1 | Completed | No
WO-26-004305 | 3.2 | Bayou | BY-S13-01 | Trouble - partial or voltage | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 136.26 | Completed | No
WO-26-004306 | 11.5 | Crossroads | CR-S27-01 | Corrective maintenance | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Internal line |  | 658.51 | Completed | No
WO-26-004307 | 5.1 | Crossroads | CR-S01-03 | Corrective maintenance | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Underground crew |  | 1611.88 | Completed | No
WO-26-004308 | 11.4 | Crossroads | CR-S14-02 | Corrective maintenance | P3 within 10 days | 2026-04-30 | 2026-05-04 | 2026-05-05 | Underground crew |  | 1136.99 | Completed | No
WO-26-004309 | 7.5 | Crossroads | CR-S17-01 | Corrective maintenance | P3 within 10 days | 2026-04-30 | 2026-05-08 | 2026-05-08 | Internal line |  | 2240.48 | Completed | No
WO-26-004310 | 6.2 | Crossroads | CR-S03-01 | Corrective maintenance | P4 planned | 2026-04-30 | 2026-06-19 | 2026-06-19 | Internal line |  | 351.42 | Completed | No
WO-26-004311 | 1.2 | Crossroads | CR-S01-03 | Meter exchange | P4 planned | 2026-04-30 | 2026-06-12 | 2026-06-12 | Meter technician |  | 125.84 | Completed | No
WO-26-004312 | 0.7 | Crossroads | CR-S21-01 | Meter exchange | P4 planned | 2026-04-30 | 2026-06-18 | 2026-06-18 | Meter technician |  | 88.43 | Completed | No
WO-26-004313 | 4 | Crossroads | CR-S05-03 | New service - small | P3 within 10 days | 2026-04-30 | 2026-05-02 | 2026-05-02 | Contract line | CT-01 | 4118.93 | Completed | No
WO-26-004314 | 8.5 | Crossroads | CR-S03-03 | New service - small | P4 planned | 2026-04-30 | 2026-06-22 | 2026-06-22 | Underground crew |  | 998.09 | Completed | No
WO-26-004315 | 20.8 | Crossroads | CR-S23-04 | Pole replacement | P4 planned | 2026-04-30 | 2026-06-27 | 2026-06-27 | Internal line |  | 1802.97 | Completed | No
WO-26-004316 | 7.5 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-04-30 | 2026-05-21 | 2026-05-21 | Internal line |  | 554.7 | Completed | No
WO-26-004317 | 2.4 | Crossroads | CR-S04-04 | Preventive maintenance | P4 planned | 2026-04-30 | 2026-06-29 | 2026-06-29 | Internal line |  | 275.17 | Completed | No
WO-26-004318 | 1.5 | Crossroads | CR-S25-06 | Service order - field | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Meter technician |  | 8.09 | Completed | No
WO-26-004319 | 1.3 | Crossroads | CR-S25-01 | Service order - field | P2 same day | 2026-04-30 | 2026-04-30 | 2026-04-30 | Meter technician |  | 18.2 | Completed | No
WO-26-004320 | 0.6 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-04-30 | 2026-05-06 | 2026-05-06 | Meter technician |  | 32.31 | Completed | No
WO-26-004321 | 0.5 | Crossroads | CR-S29-03 | Service order - field | P2 same day | 2026-04-30 | 2026-05-01 | 2026-05-01 | Meter technician |  | 34.67 | Completed | No
WO-26-004322 | 1.1 | Crossroads | CR-S05-03 | Service order - field | P3 within 10 days | 2026-04-30 | 2026-05-02 | 2026-05-10 | Meter technician |  | 14.92 | Completed | No
WO-26-004323 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-30 | 2026-05-05 | 2026-05-09 | Contract line | CT-02 | 40.51 | Completed | No
WO-26-004324 | 1.2 | Crossroads |  | Streetlight | P4 planned | 2026-04-30 | 2026-05-09 | 2026-05-10 | Contract line | CT-02 | 148.04 | Completed | No
WO-26-004325 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-04-30 | 2026-05-08 | 2026-05-09 | Contract line | CT-02 | 446.73 | Completed | No
WO-26-004326 | 7.4 | Crossroads | CR-S04-04 | Transformer replacement | P2 same day | 2026-04-30 | 2026-05-01 | 2026-05-01 | Contract line | CT-02 | 8678 | Completed | No
WO-26-004327 | 6.4 | Crossroads | CR-S21-02 | Transformer replacement | P3 within 10 days | 2026-04-30 | 2026-05-05 | 2026-05-05 | Internal line |  | 3848.28 | Completed | No
WO-26-004328 | 12.7 | Crossroads | CR-S26-06 | Transformer replacement | P2 same day | 2026-04-30 | 2026-05-01 | 2026-05-01 | Internal line |  | 7112.73 | Completed | No
WO-26-004329 | 4 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 235.99 | Completed | No
WO-26-004330 | 5.3 | Crossroads | CR-S26-02 | Trouble - no power | P1 emergency | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 307.4 | Completed | No
WO-26-004331 | 2.1 | Crossroads | CR-S18-05 | Trouble - no power | P1 emergency | 2026-04-30 | 2026-04-30 | 2026-04-30 | Troubleman |  | 253.71 | Completed | No
WO-26-004332 | 3.7 | Crossroads | CR-S14-03 | Trouble - partial or voltage | P3 within 10 days | 2026-04-30 | 2026-05-05 | 2026-05-05 | Internal line |  | 64.52 | Completed | No
WO-26-004333 | 1.6 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P3 within 10 days | 2026-04-30 | 2026-05-04 | 2026-05-04 | Internal line |  | 243.51 | Completed | No
WO-26-004334 | 3.8 | Bayou | BY-S04-03 | Corrective maintenance | P3 within 10 days | 2026-05-01 | 2026-05-10 | 2026-05-18 | Internal line |  | 1033.37 | Completed | No
WO-26-004335 | 7.8 | Bayou | BY-S09-04 | Corrective maintenance | P4 planned | 2026-05-01 | 2026-05-21 | 2026-05-21 | Internal line |  | 753.83 | Completed | No
WO-26-004336 | 8.3 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-05-01 | 2026-05-02 | 2026-05-03 | Contract line | CT-04 | 553.72 | Completed | No
WO-26-004337 | 1.3 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-05-01 | 2026-05-02 | 2026-05-04 | Meter technician |  | 60.37 | Completed | No
WO-26-004338 | 1.4 | Bayou | BY-S08-03 | Meter exchange | P4 planned | 2026-05-01 | 2026-05-26 | 2026-05-30 | Meter technician |  | 130.18 | Completed | No
WO-26-004339 | 21.8 | Bayou | BY-S01-02 | Pole replacement | P3 within 10 days | 2026-05-01 | 2026-05-07 | 2026-05-11 | Internal line |  | 2902.61 | Completed | No
WO-26-004340 | 15.6 | Bayou | BY-S07-03 | Pole replacement | P4 planned | 2026-05-01 | 2026-05-29 | 2026-05-30 | Contract line | CT-03 | 1815.32 | Completed | No
WO-26-004341 | 21.4 | Bayou | BY-S27-03 | Pole replacement | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Contract line | CT-03 | 2639.38 | Completed | No
WO-26-004342 | 5.3 | Bayou | BY-S16-01 | Preventive maintenance | P4 planned | 2026-05-01 | 2026-05-28 | 2026-05-28 | Contract line | CT-04 | 107.27 | Completed | No
WO-26-004343 | 4.9 | Bayou | BY-S21-05 | Preventive maintenance | P4 planned | 2026-05-01 | 2026-06-14 | 2026-06-14 | Contract line | CT-04 | 384.67 | Completed | No
WO-26-004344 | 1 | Bayou | BY-S07-02 | Service order - field | P3 within 10 days | 2026-05-01 | 2026-05-07 | 2026-05-07 | Meter technician |  | 16.01 | Completed | No
WO-26-004345 | 1.1 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Meter technician |  | 29.07 | Completed | No
WO-26-004346 | 1.2 | Bayou | BY-S05-02 | Service order - field | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Meter technician |  | 14.7 | Completed | No
WO-26-004347 | 1.8 | Bayou | BY-S10-02 | Service order - field | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Meter technician |  | 8.28 | Completed | No
WO-26-004348 | 1.7 | Bayou | BY-S12-04 | Service order - field | P3 within 10 days | 2026-05-01 | 2026-05-02 | 2026-05-04 | Meter technician |  | 2.78 | Completed | No
WO-26-004349 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-01 | 2026-05-05 | 2026-05-09 | Contract line | CT-04 | 128.92 | Completed | No
WO-26-004350 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-01 | 2026-05-10 | 2026-05-14 | Internal line |  | 171.1 | Completed | No
WO-26-004351 | 1.9 | Bayou |  | Streetlight | P4 planned | 2026-05-01 | 2026-06-03 | 2026-06-04 | Internal line |  | 167.15 | Completed | No
WO-26-004352 | 13.6 | Bayou | BY-S26-05 | Transformer replacement | P3 within 10 days | 2026-05-01 | 2026-05-02 | 2026-05-06 | Internal line |  | 10261.95 | Completed | No
WO-26-004353 | 4.5 | Bayou | BY-S11-01 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 69.98 | Completed | No
WO-26-004354 | 5.8 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 188.78 | Completed | No
WO-26-004355 | 2.4 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 15.03 | Completed | No
WO-26-004356 | 2.6 | Bayou | BY-S10-04 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 313.46 | Completed | No
WO-26-004357 | 2.6 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 136.22 | Completed | No
WO-26-004358 | 2.4 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 36.88 | Completed | No
WO-26-004359 | 2.3 | Bayou | BY-S14-02 | Trouble - partial or voltage | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Troubleman |  | 150.25 | Completed | No
WO-26-004360 | 4.4 | Bayou | BY-S16-01 | Trouble - partial or voltage | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Internal line |  | 184.41 | Completed | No
WO-26-004361 | 1.7 | Bayou | BY-S06-02 | Trouble - partial or voltage | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Troubleman |  | 68.88 | Completed | No
WO-26-004362 | 8.7 | Crossroads | CR-S20-01 | Corrective maintenance | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Contract line | CT-02 | 208.42 | Completed | No
WO-26-004363 | 11 | Crossroads | CR-S25-06 | Corrective maintenance | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Underground crew |  | 325.47 | Completed | No
WO-26-004364 | 6.9 | Crossroads | CR-S26-04 | Corrective maintenance | P3 within 10 days | 2026-05-01 | 2026-05-08 | 2026-05-08 | Internal line |  | 806.14 | Completed | No
WO-26-004365 | 1.3 | Crossroads | CR-S25-03 | Meter exchange | P3 within 10 days | 2026-05-01 | 2026-05-05 | 2026-05-13 | Meter technician |  | 117.36 | Completed | No
WO-26-004366 | 0.9 | Crossroads | CR-S01-02 | Meter exchange | P3 within 10 days | 2026-05-01 | 2026-05-02 | 2026-05-02 | Meter technician |  | 74.5 | Completed | No
WO-26-004367 | 0.8 | Crossroads | CR-S17-03 | Meter exchange | P4 planned | 2026-05-01 | 2026-05-28 | 2026-06-01 | Meter technician |  | 83.56 | Completed | No
WO-26-004368 | 0.6 | Crossroads | CR-S04-04 | Meter exchange | P3 within 10 days | 2026-05-01 | 2026-05-07 | 2026-05-07 | Meter technician |  | 129.79 | Completed | No
WO-26-004369 | 1.4 | Crossroads | CR-S25-06 | Meter exchange | P4 planned | 2026-05-01 | 2026-06-22 | 2026-06-22 | Meter technician |  | 171.9 | Completed | No
WO-26-004370 | 1.2 | Crossroads | CR-S20-04 | Service order - field | P3 within 10 days | 2026-05-01 | 2026-05-09 | 2026-05-13 | Meter technician |  | 17.97 | Completed | No
WO-26-004371 |  | Crossroads | CR-S20-04 | Service order - field | P3 within 10 days | 2026-05-01 | 2026-05-02 |  | Meter technician |  |  | Cancelled | No
WO-26-004372 | 0.6 | Crossroads | CR-S20-03 | Service order - field | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Meter technician |  | 2.45 | Completed | No
WO-26-004373 | 1.6 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Meter technician |  | 25 | Completed | No
WO-26-004374 | 1.8 | Crossroads | CR-S26-02 | Service order - field | P3 within 10 days | 2026-05-01 | 2026-05-07 | 2026-05-07 | Meter technician |  | 34.82 | Completed | No
WO-26-004375 | 0.8 | Crossroads | CR-S31-01 | Service order - field | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Meter technician |  | 32.21 | Completed | No
WO-26-004376 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-01 | 2026-05-02 | 2026-05-03 | Contract line | CT-02 | 305.57 | Completed | No
WO-26-004377 | 13.4 | Crossroads | CR-S30-07 | Transformer replacement | P3 within 10 days | 2026-05-01 | 2026-05-06 | 2026-05-07 | Internal line |  | 4627.01 | Completed | No
WO-26-004378 | 7.8 | Crossroads | CR-S13-04 | Transformer replacement | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Contract line | CT-02 | 7111.48 | Completed | No
WO-26-004379 | 5 | Crossroads | CR-S28-04 | Trouble - no power | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Troubleman |  | 20.77 | Completed | No
WO-26-004380 | 4.9 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 285.97 | Completed | No
WO-26-004381 | 2.1 | Crossroads | CR-S30-05 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 99.69 | Completed | No
WO-26-004382 | 5.6 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-05-01 | 2026-05-02 | 2026-05-02 | Troubleman |  | 61 | Completed | No
WO-26-004383 | 2.7 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Internal line |  | 48.36 | Completed | No
WO-26-004384 | 5.6 | Crossroads | CR-S23-04 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 300.84 | Completed | No
WO-26-004385 | 5.4 | Crossroads | CR-S23-01 | Trouble - no power | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 37.79 | Completed | No
WO-26-004386 | 5.8 | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 311.57 | Completed | No
WO-26-004387 | 2.6 | Crossroads | CR-S29-03 | Trouble - no power | P1 emergency | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 155.27 | Completed | No
WO-26-004388 | 1.8 | Crossroads | CR-S05-06 | Trouble - partial or voltage | P3 within 10 days | 2026-05-01 | 2026-05-11 | 2026-05-11 | Troubleman |  | 17.05 | Completed | No
WO-26-004389 | 3.7 | Crossroads | CR-S14-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-01 | 2026-05-05 | 2026-05-09 | Troubleman |  | 188.7 | Completed | No
WO-26-004390 | 4.7 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P2 same day | 2026-05-01 | 2026-05-01 | 2026-05-01 | Troubleman |  | 97.68 | Completed | No
WO-26-004391 | 8.6 | Bayou | BY-S22-04 | Corrective maintenance | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Contract line | CT-04 | 2295.78 | Completed | No
WO-26-004392 | 0.8 | Bayou | BY-S21-03 | Service order - field | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Meter technician |  | 19.35 | Completed | No
WO-26-004393 | 1.1 | Bayou | BY-S06-02 | Service order - field | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Meter technician |  | 1.51 | Completed | No
WO-26-004394 | 1.2 | Bayou | BY-S02-02 | Service order - field | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Meter technician |  | 26.13 | Completed | No
WO-26-004395 | 1.2 | Bayou | BY-S11-02 | Service order - field | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Meter technician |  | 13 | Completed | No
WO-26-004396 | 7.9 | Bayou | BY-S04-02 | Transformer replacement | P1 emergency | 2026-05-02 | 2026-05-02 | 2026-05-02 | Internal line |  | 3906.24 | Completed | No
WO-26-004397 | 4 | Bayou | BY-S05-03 | Trouble - no power | P1 emergency | 2026-05-02 | 2026-05-02 | 2026-05-02 | Troubleman |  | 187.92 | Completed | No
WO-26-004398 | 2.3 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Troubleman |  | 237.05 | Completed | No
WO-26-004399 | 3.5 | Bayou | BY-S08-03 | Trouble - no power | P1 emergency | 2026-05-02 | 2026-05-02 | 2026-05-02 | Troubleman |  | 38.97 | Completed | No
WO-26-004400 |  | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-05-02 | 2026-05-02 |  | Troubleman |  |  | Cancelled | No
WO-26-004401 | 4.6 | Bayou | BY-S01-02 | Trouble - no power | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Troubleman |  | 335.62 | Completed | No
WO-26-004402 | 4.9 | Crossroads | CR-S30-05 | Corrective maintenance | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Internal line |  | 1137.91 | Completed | No
WO-26-004403 | 7 | Crossroads | CR-S06-03 | Corrective maintenance | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Contract line | CT-02 | 1960.75 | Completed | No
WO-26-004404 | 0.5 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Meter technician |  | 14.39 | Completed | No
WO-26-004405 | 4.2 | Crossroads | CR-S20-04 | Trouble - no power | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Troubleman |  | 172.26 | Completed | No
WO-26-004406 | 4.7 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-05-02 | 2026-05-02 | 2026-05-02 | Internal line |  | 250.2 | Completed | No
WO-26-004407 | 4.9 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Internal line |  | 58.23 | Completed | No
WO-26-004408 | 1.7 | Crossroads | CR-S03-02 | Trouble - partial or voltage | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Troubleman |  | 26.52 | Completed | No
WO-26-004409 | 2.2 | Crossroads | CR-S29-01 | Trouble - partial or voltage | P2 same day | 2026-05-02 | 2026-05-02 | 2026-05-02 | Internal line |  | 31.33 | Completed | No
WO-26-004410 | 4.7 | Crossroads | CR-S13-02 | Trouble - partial or voltage | P2 same day | 2026-05-02 | 2026-05-03 | 2026-05-03 | Troubleman |  | 139.1 | Completed | No
WO-26-004411 | 1.6 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Meter technician |  | 17.57 | Completed | No
WO-26-004412 | 1.4 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-05-03 | 2026-05-03 | 2026-05-03 | Meter technician |  | 1.81 | Completed | No
WO-26-004413 | 0.6 | Bayou | BY-S12-02 | Service order - field | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Meter technician |  | 1.4 | Completed | No
WO-26-004414 | 2.5 | Bayou | BY-S21-03 | Trouble - no power | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Internal line |  | 349.11 | Completed | No
WO-26-004415 | 5.1 | Bayou | BY-S06-02 | Trouble - no power | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Internal line |  | 259.21 | Completed | No
WO-26-004416 | 3.9 | Bayou | BY-S19-04 | Trouble - no power | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Troubleman |  | 199.48 | Completed | No
WO-26-004417 | 4.6 | Bayou | BY-S26-06 | Trouble - no power | P1 emergency | 2026-05-03 | 2026-05-03 | 2026-05-03 | Troubleman |  | 187.87 | Completed | No
WO-26-004418 | 4.2 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-05-03 | 2026-05-03 | 2026-05-03 | Troubleman |  | 314.46 | Completed | No
WO-26-004419 | 1.1 | Crossroads | CR-S02-03 | Service order - field | P2 same day | 2026-05-03 | 2026-05-03 | 2026-05-03 | Meter technician |  | 31.47 | Completed | No
WO-26-004420 | 0.6 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-05-03 | 2026-05-03 | 2026-05-03 | Meter technician |  | 12.02 | Completed | No
WO-26-004421 | 1.4 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-05-03 | 2026-05-03 | 2026-05-03 | Meter technician |  | 23.34 | Completed | No
WO-26-004422 | 1.3 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-05-03 | 2026-05-03 | 2026-05-03 | Meter technician |  | 15.5 | Completed | No
WO-26-004423 | 9.8 | Crossroads | CR-S05-04 | Transformer replacement | P1 emergency | 2026-05-03 | 2026-05-03 | 2026-05-03 | Internal line |  | 3679.54 | Completed | No
WO-26-004424 |  | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-05-03 | 2026-05-03 |  | Troubleman |  |  | Cancelled | No
WO-26-004425 | 3.7 | Crossroads | CR-S06-01 | Trouble - no power | P1 emergency | 2026-05-03 | 2026-05-03 | 2026-05-03 | Troubleman |  | 40.69 | Completed | No
WO-26-004426 | 3 | Crossroads | CR-S16-04 | Trouble - no power | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Troubleman |  | 119.85 | Completed | No
WO-26-004427 | 2.6 | Crossroads | CR-S16-01 | Trouble - partial or voltage | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Troubleman |  | 45.62 | Completed | No
WO-26-004428 | 2.1 | Crossroads | CR-S15-03 | Trouble - partial or voltage | P2 same day | 2026-05-03 | 2026-05-04 | 2026-05-04 | Troubleman |  | 160.25 | Completed | No
WO-26-004429 | 5 | Bayou | BY-S27-05 | Corrective maintenance | P4 planned | 2026-05-04 | 2026-07-01 | 2026-07-01 | Contract line | CT-04 | 1634.04 | Completed | No
WO-26-004430 | 11.1 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-05-04 | 2026-05-13 | 2026-05-13 | Underground crew |  | 597.42 | Completed | No
WO-26-004431 | 6.8 | Bayou | BY-S18-05 | Corrective maintenance | P3 within 10 days | 2026-05-04 | 2026-05-07 | 2026-05-07 | Internal line |  | 1328.87 | Completed | No
WO-26-004432 | 8.2 | Bayou | BY-S29-01 | Corrective maintenance | P3 within 10 days | 2026-05-04 | 2026-05-07 | 2026-05-07 | Contract line | CT-04 | 484.58 | Completed | No
WO-26-004433 | 1.3 | Bayou | BY-S25-03 | Meter exchange | P4 planned | 2026-05-04 | 2026-06-08 | 2026-06-08 | Meter technician |  | 131.51 | Completed | No
WO-26-004434 | 1.5 | Bayou | BY-S03-01 | Meter exchange | P4 planned | 2026-05-04 | 2026-05-30 | 2026-05-30 | Meter technician |  | 108.66 | Completed | No
WO-26-004435 | 0.7 | Bayou | BY-S18-06 | Meter exchange | P3 within 10 days | 2026-05-04 | 2026-05-12 | 2026-05-16 | Meter technician |  | 119.85 | Completed | No
WO-26-004436 | 0.8 | Bayou | BY-S15-03 | Meter exchange | P3 within 10 days | 2026-05-04 | 2026-05-06 | 2026-05-06 | Meter technician |  | 69.87 | Completed | No
WO-26-004437 | 1.3 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-05-04 | 2026-05-07 | 2026-05-07 | Meter technician |  | 107.67 | Completed | No
WO-26-004438 | 0.7 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-05-04 | 2026-05-06 | 2026-05-06 | Meter technician |  | 102.68 | Completed | No
WO-26-004439 | 1.4 | Bayou | BY-S29-02 | Meter exchange | P4 planned | 2026-05-04 | 2026-06-29 | 2026-06-29 | Meter technician |  | 89.97 | Completed | No
WO-26-004440 | 5.2 | Bayou | BY-S29-01 | New service - small | P3 within 10 days | 2026-05-04 | 2026-05-11 | 2026-05-15 | Contract line | CT-03 | 3837.47 | Completed | No
WO-26-004441 | 14.5 | Bayou | BY-S10-04 | New service - small | P4 planned | 2026-05-04 | 2026-06-09 | 2026-06-09 | Contract line | CT-03 | 2488.63 | Completed | No
WO-26-004442 | 12.9 | Bayou | BY-S08-03 | Pole replacement | P4 planned | 2026-05-04 | 2026-06-03 | 2026-06-04 | Internal line |  | 1864.23 | Completed | No
WO-26-004443 | 4 | Bayou | BY-S30-03 | Preventive maintenance | P4 planned | 2026-05-04 | 2026-05-31 | 2026-06-02 | Internal line |  | 316.87 | Completed | No
WO-26-004444 | 5.3 | Bayou | BY-S21-02 | Preventive maintenance | P4 planned | 2026-05-04 | 2026-06-10 | 2026-06-11 | Internal line |  | 89.37 | Completed | No
WO-26-004445 | 7.9 | Bayou | BY-S21-05 | Preventive maintenance | P4 planned | 2026-05-04 | 2026-06-19 | 2026-06-20 | Internal line |  | 116.5 | Completed | No
WO-26-004446 | 2.5 | Bayou | BY-S29-05 | Preventive maintenance | P4 planned | 2026-05-04 | 2026-06-26 | 2026-06-30 | Internal line |  | 410.31 | Completed | No
WO-26-004447 | 0.8 | Bayou | BY-S01-02 | Service order - field | P3 within 10 days | 2026-05-04 | 2026-05-09 | 2026-05-10 | Meter technician |  | 25.81 | Completed | No
WO-26-004448 | 0.6 | Bayou | BY-S05-03 | Service order - field | P3 within 10 days | 2026-05-04 | 2026-05-05 | 2026-05-05 | Meter technician |  | 34.27 | Completed | No
WO-26-004449 | 1.6 | Bayou | BY-S21-03 | Service order - field | P2 same day | 2026-05-04 | 2026-05-04 | 2026-05-04 | Meter technician |  | 16.5 | Completed | No
WO-26-004450 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-07 | 2026-05-09 | Internal line |  | 80.64 | Completed | No
WO-26-004451 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-10 | 2026-05-12 | Contract line | CT-03 | 120.81 | Completed | No
WO-26-004452 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-07 | 2026-05-07 | Internal line |  | 372.15 | Completed | No
WO-26-004453 | 1 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-06 | 2026-05-07 | Internal line |  | 273.3 | Completed | No
WO-26-004454 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-11 | 2026-05-15 | Contract line | CT-03 | 114.94 | Completed | No
WO-26-004455 | 13 | Bayou | BY-S08-01 | Transformer replacement | P2 same day | 2026-05-04 | 2026-05-05 | 2026-05-05 | Contract line | CT-04 | 9471.69 | Completed | No
WO-26-004456 | 13.2 | Bayou | BY-S07-03 | Transformer replacement | P3 within 10 days | 2026-05-04 | 2026-05-10 | 2026-05-12 | Internal line |  | 10672.49 | Completed | No
WO-26-004457 | 4.6 | Bayou | BY-S16-01 | Trouble - no power | P2 same day | 2026-05-04 | 2026-05-04 | 2026-05-04 | Troubleman |  | 91.76 | Completed | No
WO-26-004458 | 4.5 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Troubleman |  | 137.12 | Completed | No
WO-26-004459 |  | Bayou | BY-S30-01 | Trouble - no power | P2 same day | 2026-05-04 | 2026-05-04 |  | Troubleman |  |  | Cancelled | No
WO-26-004460 | 2.8 | Bayou | BY-S18-04 | Trouble - partial or voltage | P3 within 10 days | 2026-05-04 | 2026-05-14 | 2026-05-18 | Troubleman |  | 108.75 | Completed | No
WO-26-004461 | 4.2 | Bayou | BY-S14-01 | Trouble - partial or voltage | P2 same day | 2026-05-04 | 2026-05-05 | 2026-05-05 | Troubleman |  | 18.24 | Completed | No
WO-26-004462 | 11.3 | Crossroads | CR-S32-02 | Corrective maintenance | P4 planned | 2026-05-04 | 2026-05-27 | 2026-05-27 | Contract line | CT-02 | 953.41 | Completed | No
WO-26-004463 | 7.1 | Crossroads | CR-S13-06 | Corrective maintenance | P3 within 10 days | 2026-05-04 | 2026-05-14 | 2026-05-14 | Underground crew |  | 486.89 | Completed | No
WO-26-004464 | 3.1 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-05-04 | 2026-05-08 | 2026-05-12 | Underground crew |  | 577.55 | Completed | No
WO-26-004465 | 1.1 | Crossroads | CR-S24-03 | Meter exchange | P4 planned | 2026-05-04 | 2026-06-28 | 2026-06-30 | Meter technician |  | 98.79 | Completed | No
WO-26-004466 | 1.1 | Crossroads | CR-S30-02 | Meter exchange | P4 planned | 2026-05-04 | 2026-06-28 | 2026-06-29 | Meter technician |  | 134.71 | Completed | No
WO-26-004467 | 7.8 | Crossroads | CR-S06-03 | New service - small | P4 planned | 2026-05-04 | 2026-05-22 | 2026-05-22 | Contract line | CT-02 | 2455.35 | Completed | No
WO-26-004468 | 5.8 | Crossroads | CR-S02-04 | New service - small | P3 within 10 days | 2026-05-04 | 2026-05-06 | 2026-05-07 | Contract line | CT-01 | 2250.24 | Completed | No
WO-26-004469 | 12.8 | Crossroads | CR-S15-03 | Pole replacement | P4 planned | 2026-05-04 | 2026-06-16 | 2026-06-17 | Internal line |  | 2667.39 | Completed | No
WO-26-004470 | 6.6 | Crossroads | CR-S20-01 | Preventive maintenance | P4 planned | 2026-05-04 | 2026-06-08 | 2026-06-10 | Underground crew |  | 71.65 | Completed | No
WO-26-004471 | 2.9 | Crossroads | CR-S20-02 | Preventive maintenance | P4 planned | 2026-05-04 | 2026-06-16 | 2026-06-24 | Internal line |  | 283.82 | Completed | No
WO-26-004472 | 1.9 | Crossroads | CR-S14-01 | Service order - field | P2 same day | 2026-05-04 | 2026-05-04 | 2026-05-04 | Meter technician |  | 1.69 | Completed | No
WO-26-004473 | 1 | Crossroads | CR-S19-03 | Service order - field | P3 within 10 days | 2026-05-04 | 2026-05-06 | 2026-05-06 | Meter technician |  | 15.13 | Completed | No
WO-26-004474 | 0.5 | Crossroads | CR-S15-03 | Service order - field | P3 within 10 days | 2026-05-04 | 2026-05-08 | 2026-05-09 | Meter technician |  | 7.88 | Completed | No
WO-26-004475 | 0.6 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-05-04 | 2026-05-04 | 2026-05-04 | Meter technician |  | 24.07 | Completed | No
WO-26-004476 | 1.8 | Crossroads | CR-S31-03 | Service order - field | P2 same day | 2026-05-04 | 2026-05-05 | 2026-05-05 | Meter technician |  | 14.17 | Completed | No
WO-26-004477 | 1.1 | Crossroads | CR-S19-02 | Service order - field | P2 same day | 2026-05-04 | 2026-05-05 | 2026-05-05 | Meter technician |  | 16.63 | Completed | No
WO-26-004478 | 1.5 | Crossroads | CR-S07-01 | Service order - field | P3 within 10 days | 2026-05-04 | 2026-05-12 | 2026-05-12 | Meter technician |  | 9.36 | Completed | No
WO-26-004479 | 0.6 | Crossroads | CR-S13-05 | Service order - field | P3 within 10 days | 2026-05-04 | 2026-05-05 | 2026-05-05 | Meter technician |  | 15.45 | Completed | No
WO-26-004480 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-07 | 2026-05-07 | Internal line |  | 379.31 | Completed | No
WO-26-004481 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-08 | 2026-05-08 | Internal line |  | 111.48 | Completed | No
WO-26-004482 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-04 | 2026-05-11 | 2026-05-11 | Contract line | CT-02 | 249.33 | Completed | No
WO-26-004483 | 1.6 | Crossroads |  | Streetlight | P4 planned | 2026-05-04 | 2026-06-20 | 2026-06-24 | Internal line |  | 140.03 | Completed | No
WO-26-004484 | 9.8 | Crossroads | CR-S25-03 | Transformer replacement | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Contract line | CT-02 | 3888 | Completed | No
WO-26-004485 | 12.9 | Crossroads | CR-S01-03 | Transformer replacement | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Internal line |  | 12404.51 | Completed | No
WO-26-004486 | 2.1 | Crossroads | CR-S16-06 | Trouble - no power | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Internal line |  | 314.37 | Completed | No
WO-26-004487 | 3 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Troubleman |  | 135.29 | Completed | No
WO-26-004488 | 4.6 | Crossroads | CR-S14-02 | Trouble - no power | P2 same day | 2026-05-04 | 2026-05-05 | 2026-05-05 | Internal line |  | 34.94 | Completed | No
WO-26-004489 | 4.4 | Crossroads | CR-S20-02 | Trouble - no power | P2 same day | 2026-05-04 | 2026-05-04 | 2026-05-04 | Troubleman |  | 245.2 | Completed | No
WO-26-004490 | 5.2 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Troubleman |  | 158.19 | Completed | No
WO-26-004491 | 3.7 | Crossroads | CR-S27-01 | Trouble - no power | P1 emergency | 2026-05-04 | 2026-05-04 | 2026-05-04 | Troubleman |  | 256.69 | Completed | No
WO-26-004492 | 9.1 | Bayou | BY-S24-04 | Corrective maintenance | P2 same day | 2026-05-05 | 2026-05-06 | 2026-05-06 | Internal line |  | 430.96 | Completed | No
WO-26-004493 | 10.9 | Bayou | BY-S17-02 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-11 | 2026-05-12 | Contract line | CT-04 | 1112.44 | Completed | No
WO-26-004494 | 6.5 | Bayou | BY-S16-04 | Corrective maintenance | P4 planned | 2026-05-05 | 2026-05-15 | 2026-05-19 | Internal line |  | 2028.04 | Completed | No
WO-26-004495 | 10.9 | Bayou | BY-S07-02 | Corrective maintenance | P2 same day | 2026-05-05 | 2026-05-06 | 2026-05-06 | Internal line |  | 874.67 | Completed | No
WO-26-004496 | 11.9 | Bayou | BY-S24-03 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-11 | 2026-05-11 | Internal line |  | 2293.7 | Completed | No
WO-26-004497 | 10.4 | Bayou | BY-S06-01 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-09 | 2026-05-09 | Underground crew |  | 2283.51 | Completed | No
WO-26-004498 | 5.1 | Bayou | BY-S29-04 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-13 | 2026-05-14 | Contract line | CT-04 | 1395.34 | Completed | No
WO-26-004499 | 11.8 | Bayou | BY-S16-04 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-14 | Contract line | CT-03 | 808.82 | Completed | No
WO-26-004500 | 4.9 | Bayou | BY-S21-04 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-12 | 2026-05-13 | Contract line | CT-03 | 1476.19 | Completed | No
WO-26-004501 | 1 | Bayou | BY-S24-01 | Meter exchange | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-14 | Meter technician |  | 108.11 | Completed | No
WO-26-004502 | 1 | Bayou | BY-S17-04 | Meter exchange | P3 within 10 days | 2026-05-05 | 2026-05-07 | 2026-05-08 | Meter technician |  | 78.49 | Completed | No
WO-26-004503 | 4.8 | Bayou | BY-S22-03 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-06-07 | 2026-06-08 | Contract line | CT-04 | 404.06 | Completed | No
WO-26-004504 | 6.9 | Bayou | BY-S21-01 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-05-17 | 2026-05-19 | Underground crew |  | 193.82 | Completed | No
WO-26-004505 | 7.4 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-06-12 | 2026-06-13 | Underground crew |  | 421.63 | Completed | No
WO-26-004506 | 4.5 | Bayou | BY-S03-02 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-05-27 | 2026-05-31 | Internal line |  | 22.44 | Completed | No
WO-26-004507 | 1.2 | Bayou | BY-S21-05 | Service order - field | P2 same day | 2026-05-05 | 2026-05-06 | 2026-05-06 | Meter technician |  | 16.74 | Completed | No
WO-26-004508 | 1.2 | Bayou | BY-S09-04 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-08 | 2026-05-08 | Meter technician |  | 30.54 | Completed | No
WO-26-004509 | 1 | Bayou | BY-S24-05 | Service order - field | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Meter technician |  | 33.65 | Completed | No
WO-26-004510 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-05 | 2026-05-09 | 2026-05-09 | Internal line |  | 351.46 | Completed | No
WO-26-004511 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-05 | 2026-05-14 | 2026-05-14 | Contract line | CT-04 | 365.91 | Completed | No
WO-26-004512 | 13.2 | Bayou | BY-S13-01 | Transformer replacement | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Contract line | CT-04 | 6484.04 | Completed | No
WO-26-004513 | 11.7 | Bayou | BY-S19-03 | Transformer replacement | P3 within 10 days | 2026-05-05 | 2026-05-06 | 2026-05-14 | Internal line |  | 4456.24 | Completed | No
WO-26-004514 | 4.9 | Bayou | BY-S22-01 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Internal line |  | 77.41 | Completed | No
WO-26-004515 | 2.1 | Bayou | BY-S08-02 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 7.56 | Completed | No
WO-26-004516 | 2.1 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 166.19 | Completed | No
WO-26-004517 | 4 | Bayou | BY-S21-04 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Internal line |  | 256.93 | Completed | No
WO-26-004518 | 4.1 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 47.75 | Completed | No
WO-26-004519 | 3.2 | Bayou | BY-S11-01 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 118.02 | Completed | No
WO-26-004520 | 3.2 | Bayou | BY-S24-05 | Trouble - partial or voltage | P3 within 10 days | 2026-05-05 | 2026-05-12 | 2026-05-12 | Troubleman |  | 219.29 | Completed | No
WO-26-004521 | 3.8 | Bayou | BY-S15-05 | Trouble - partial or voltage | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-10 | Internal line |  | 209.03 | Completed | No
WO-26-004522 | 3.2 | Bayou | BY-S12-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-05 | 2026-05-13 | 2026-05-15 | Troubleman |  | 91.67 | Completed | No
WO-26-004523 | 4.5 | Bayou | BY-S13-06 | Trouble - partial or voltage | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 124.21 | Completed | No
WO-26-004524 | 7.2 | Crossroads | CR-S32-05 | Corrective maintenance | P4 planned | 2026-05-05 | 2026-06-07 | 2026-06-07 | Contract line | CT-02 | 1089.25 | Completed | No
WO-26-004525 | 6.1 | Crossroads | CR-S26-06 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-12 | Underground crew |  | 300.24 | Completed | No
WO-26-004526 | 3.7 | Crossroads | CR-S08-04 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-10 | Underground crew |  | 1900.33 | Completed | No
WO-26-004527 | 10.2 | Crossroads | CR-S28-01 | Corrective maintenance | P4 planned | 2026-05-05 | 2026-06-30 | 2026-07-02 | Internal line |  | 294.76 | Completed | No
WO-26-004528 | 11.4 | Crossroads | CR-S14-04 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-12 | 2026-05-13 | Contract line | CT-02 | 1025.67 | Completed | No
WO-26-004529 | 6.3 | Crossroads | CR-S23-02 | Corrective maintenance | P2 same day | 2026-05-05 | 2026-05-06 | 2026-05-06 | Underground crew |  | 2225.26 | Completed | No
WO-26-004530 | 7.9 | Crossroads | CR-S12-01 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-12 | 2026-05-12 | Internal line |  | 335.33 | Completed | No
WO-26-004531 | 8.3 | Crossroads | CR-S02-03 | Corrective maintenance | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-12 | Internal line |  | 1006.55 | Completed | No
WO-26-004532 | 0.7 | Crossroads | CR-S19-02 | Meter exchange | P4 planned | 2026-05-05 | 2026-05-29 | 2026-05-31 | Meter technician |  | 108.41 | Completed | No
WO-26-004533 | 1.2 | Crossroads | CR-S10-01 | Meter exchange | P3 within 10 days | 2026-05-05 | 2026-05-07 | 2026-05-08 | Meter technician |  | 89.41 | Completed | No
WO-26-004534 | 1.1 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-05-05 | 2026-05-06 | 2026-05-06 | Meter technician |  | 160.39 | Completed | No
WO-26-004535 | 15.8 | Crossroads | CR-S15-03 | New service - small | P3 within 10 days | 2026-05-05 | 2026-05-13 | 2026-05-13 | Contract line | CT-02 | 3906.77 | Completed | No
WO-26-004536 | 12.7 | Crossroads | CR-S10-02 | Pole replacement | P3 within 10 days | 2026-05-05 | 2026-05-06 | 2026-05-10 | Internal line |  | 2781.2 | Completed | No
WO-26-004537 | 12.3 | Crossroads | CR-S28-01 | Pole replacement | P4 planned | 2026-05-05 | 2026-07-02 | 2026-07-02 | Contract line | CT-01 | 3492.28 | Completed | No
WO-26-004538 | 5.4 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-05-23 | 2026-05-23 | Internal line |  | 355.57 | Completed | No
WO-26-004539 | 4 | Crossroads | CR-S19-04 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-05-24 | 2026-05-25 | Internal line |  | 511.33 | Completed | No
WO-26-004540 | 3.8 | Crossroads | CR-S27-03 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-06-25 | 2026-06-29 | Underground crew |  | 201.04 | Completed | No
WO-26-004541 | 7.5 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-05-05 | 2026-05-21 | 2026-05-23 | Internal line |  | 263.96 | Completed | No
WO-26-004542 | 0.9 | Crossroads | CR-S12-02 | Service order - field | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Meter technician |  | 31.48 | Completed | No
WO-26-004543 | 0.9 | Crossroads | CR-S02-02 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-15 | 2026-05-16 | Meter technician |  | 30.61 | Completed | No
WO-26-004544 | 1.4 | Crossroads | CR-S09-03 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-13 | 2026-05-13 | Meter technician |  | 33.61 | Completed | No
WO-26-004545 | 2 | Crossroads | CR-S04-04 | Service order - field | P2 same day | 2026-05-05 | 2026-05-06 | 2026-05-06 | Meter technician |  | 5.49 | Completed | No
WO-26-004546 | 0.9 | Crossroads | CR-S13-02 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-11 | 2026-05-11 | Meter technician |  | 1.61 | Completed | No
WO-26-004547 | 2 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-10 | 2026-05-10 | Meter technician |  | 33.26 | Completed | No
WO-26-004548 | 1.5 | Crossroads | CR-S06-02 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-06 | 2026-05-06 | Meter technician |  | 10.37 | Completed | No
WO-26-004549 | 1.3 | Crossroads | CR-S23-03 | Service order - field | P3 within 10 days | 2026-05-05 | 2026-05-14 | 2026-05-14 | Meter technician |  | 32.53 | Completed | No
WO-26-004550 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-05 | 2026-05-08 | 2026-05-08 | Contract line | CT-01 | 201.05 | Completed | No
WO-26-004551 | 9.2 | Crossroads | CR-S27-02 | Transformer replacement | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Internal line |  | 3101.38 | Completed | No
WO-26-004552 | 6.2 | Crossroads | CR-S26-02 | Transformer replacement | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Internal line |  | 9059.73 | Completed | No
WO-26-004553 | 5.8 | Crossroads | CR-S15-02 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 60.61 | Completed | No
WO-26-004554 | 4.6 | Crossroads | CR-S05-05 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 198.78 | Completed | No
WO-26-004555 | 2.5 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 310.15 | Completed | No
WO-26-004556 | 2.3 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 326.47 | Completed | No
WO-26-004557 | 5.7 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Internal line |  | 340.36 | Completed | No
WO-26-004558 | 5.6 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Internal line |  | 59.84 | Completed | No
WO-26-004559 |  | Crossroads | CR-S04-04 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 |  | Internal line |  |  | Cancelled | No
WO-26-004560 |  | Crossroads | CR-S25-02 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 |  | Troubleman |  |  | Cancelled | No
WO-26-004561 | 2.7 | Crossroads | CR-S32-04 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-06 | 2026-05-06 | Troubleman |  | 280.45 | Completed | No
WO-26-004562 | 5.1 | Crossroads | CR-S12-03 | Trouble - no power | P2 same day | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 197.26 | Completed | No
WO-26-004563 | 5.8 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-05-05 | 2026-05-05 | 2026-05-05 | Troubleman |  | 49.75 | Completed | No
WO-26-004564 | 3.7 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-05 | 2026-05-09 | 2026-05-09 | Troubleman |  | 16.8 | Completed | No
WO-26-004565 | 2.7 | Crossroads | CR-S17-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-05 | 2026-05-07 | 2026-05-07 | Troubleman |  | 48.37 | Completed | No
WO-26-004566 | 11.9 | Bayou | BY-S27-05 | Corrective maintenance | P2 same day | 2026-05-06 | 2026-05-07 | 2026-05-07 | Internal line |  | 401.48 | Completed | No
WO-26-004567 | 7.2 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-10 | 2026-05-10 | Internal line |  | 1992.61 | Completed | No
WO-26-004568 | 0.9 | Bayou | BY-S29-02 | Meter exchange | P4 planned | 2026-05-06 | 2026-07-03 | 2026-07-03 | Meter technician |  | 155.85 | Completed | No
WO-26-004569 | 1.4 | Bayou | BY-S10-04 | Meter exchange | P3 within 10 days | 2026-05-06 | 2026-05-14 | 2026-05-22 | Meter technician |  | 120.05 | Completed | No
WO-26-004570 | 4.6 | Bayou | BY-S22-04 | Preventive maintenance | P4 planned | 2026-05-06 | 2026-06-12 | 2026-06-16 | Internal line |  | 532.32 | Completed | No
WO-26-004571 | 6.2 | Bayou | BY-S21-03 | Preventive maintenance | P4 planned | 2026-05-06 | 2026-05-23 | 2026-05-23 | Internal line |  | 241.08 | Completed | No
WO-26-004572 | 6.8 | Bayou | BY-S19-04 | Preventive maintenance | P4 planned | 2026-05-06 | 2026-06-24 | 2026-06-25 | Internal line |  | 337.49 | Completed | No
WO-26-004573 | 6.1 | Bayou | BY-S26-05 | Preventive maintenance | P4 planned | 2026-05-06 | 2026-06-17 | 2026-06-21 | Internal line |  | 487.56 | Completed | No
WO-26-004574 | 1.6 | Bayou | BY-S15-01 | Service order - field | P2 same day | 2026-05-06 | 2026-05-07 | 2026-05-07 | Meter technician |  | 15.2 | Completed | No
WO-26-004575 | 1.8 | Bayou | BY-S18-01 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-14 | 2026-05-18 | Meter technician |  | 6.55 | Completed | No
WO-26-004576 | 1.8 | Bayou | BY-S04-02 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-12 | 2026-05-13 | Meter technician |  | 4.95 | Completed | No
WO-26-004577 | 2.7 | Bayou |  | Streetlight | P4 planned | 2026-05-06 | 2026-05-29 | 2026-06-02 | Internal line |  | 109.84 | Completed | No
WO-26-004578 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-06 | 2026-05-07 | 2026-05-08 | Internal line |  | 61.5 | Completed | No
WO-26-004579 | 5.5 | Bayou | BY-S28-01 | Trouble - no power | P2 same day | 2026-05-06 | 2026-05-07 | 2026-05-07 | Troubleman |  | 111.88 | Completed | No
WO-26-004580 | 3.1 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 62.23 | Completed | No
WO-26-004581 | 5.4 | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 320.28 | Completed | No
WO-26-004582 | 3.1 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Internal line |  | 330.6 | Completed | No
WO-26-004583 | 2.7 | Bayou | BY-S02-01 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 78.05 | Completed | No
WO-26-004584 | 5.8 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Internal line |  | 95.86 | Completed | No
WO-26-004585 | 7.4 | Crossroads | CR-S12-03 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-15 | 2026-05-16 | Underground crew |  | 994.56 | Completed | No
WO-26-004586 | 3.2 | Crossroads | CR-S29-01 | Corrective maintenance | P4 planned | 2026-05-06 | 2026-05-14 | 2026-05-14 | Underground crew |  | 671.88 | Completed | No
WO-26-004587 | 3 | Crossroads | CR-S16-04 | Corrective maintenance | P4 planned | 2026-05-06 | 2026-06-25 | 2026-06-25 | Internal line |  | 2268.29 | Completed | No
WO-26-004588 | 11.4 | Crossroads | CR-S24-01 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-12 | 2026-05-12 | Contract line | CT-02 | 1186.47 | Completed | No
WO-26-004589 | 10.5 | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-13 | 2026-05-13 | Internal line |  | 97.3 | Completed | No
WO-26-004590 | 11.6 | Crossroads | CR-S18-04 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-10 | 2026-05-10 | Underground crew |  | 283.57 | Completed | No
WO-26-004591 | 7.3 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-07 | 2026-05-07 | Underground crew |  | 2153.06 | Completed | No
WO-26-004592 | 10.9 | Crossroads | CR-S17-01 | Corrective maintenance | P3 within 10 days | 2026-05-06 | 2026-05-07 | 2026-05-07 | Internal line |  | 246.05 | Completed | No
WO-26-004593 | 1.1 | Crossroads | CR-S32-03 | Meter exchange | P4 planned | 2026-05-06 | 2026-06-19 | 2026-06-20 | Meter technician |  | 141.22 | Completed | No
WO-26-004594 | 1.1 | Crossroads | CR-S17-03 | Meter exchange | P4 planned | 2026-05-06 | 2026-05-21 | 2026-05-21 | Meter technician |  | 163.69 | Completed | No
WO-26-004595 | 1 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-05-06 | 2026-05-11 | 2026-05-11 | Meter technician |  | 163.16 | Completed | No
WO-26-004596 | 16.4 | Crossroads | CR-S09-04 | Pole replacement | P4 planned | 2026-05-06 | 2026-07-01 | 2026-07-02 | Internal line |  | 3291.7 | Completed | No
WO-26-004597 | 5.4 | Crossroads | CR-S07-03 | Preventive maintenance | P4 planned | 2026-05-06 | 2026-06-21 | 2026-06-25 | Contract line | CT-01 | 411.39 | Completed | No
WO-26-004598 | 7.7 | Crossroads | CR-S08-06 | Preventive maintenance | P4 planned | 2026-05-06 | 2026-06-25 | 2026-06-29 | Underground crew |  | 120.08 | Completed | No
WO-26-004599 | 1 | Crossroads | CR-S14-03 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-15 | 2026-05-15 | Meter technician |  | 25.99 | Completed | No
WO-26-004600 | 1.2 | Crossroads | CR-S31-01 | Service order - field | P2 same day | 2026-05-06 | 2026-05-07 | 2026-05-07 | Meter technician |  | 20.33 | Completed | No
WO-26-004601 | 0.8 | Crossroads | CR-S29-02 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-14 | 2026-05-16 | Meter technician |  | 30.21 | Completed | No
WO-26-004602 | 0.7 | Crossroads | CR-S09-01 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-07 | 2026-05-11 | Meter technician |  | 26.46 | Completed | No
WO-26-004603 | 1.4 | Crossroads | CR-S25-05 | Service order - field | P2 same day | 2026-05-06 | 2026-05-07 | 2026-05-07 | Meter technician |  | 38.95 | Completed | No
WO-26-004604 | 0.9 | Crossroads | CR-S14-03 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-13 | 2026-05-13 | Meter technician |  | 11.18 | Completed | No
WO-26-004605 | 1.7 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-05-06 | 2026-05-06 | 2026-05-06 | Meter technician |  | 31.42 | Completed | No
WO-26-004606 | 1 | Crossroads | CR-S16-02 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-15 | 2026-05-15 | Meter technician |  | 32.88 | Completed | No
WO-26-004607 | 1.6 | Crossroads | CR-S13-06 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-12 | 2026-05-13 | Meter technician |  | 24.72 | Completed | No
WO-26-004608 | 2 | Crossroads | CR-S20-01 | Service order - field | P3 within 10 days | 2026-05-06 | 2026-05-08 | 2026-05-08 | Meter technician |  | 29.92 | Completed | No
WO-26-004609 | 1.8 | Crossroads |  | Streetlight | P4 planned | 2026-05-06 | 2026-06-11 | 2026-06-11 | Internal line |  | 225.3 | Completed | No
WO-26-004610 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-06 | 2026-05-09 | 2026-05-10 | Contract line | CT-02 | 320.09 | Completed | No
WO-26-004611 | 13.4 | Crossroads | CR-S07-06 | Transformer replacement | P2 same day | 2026-05-06 | 2026-05-06 | 2026-05-06 | Internal line |  | 10880.28 | Completed | No
WO-26-004612 | 12.7 | Crossroads | CR-S05-02 | Transformer replacement | P3 within 10 days | 2026-05-06 | 2026-05-08 | 2026-05-08 | Internal line |  | 4230.96 | Completed | No
WO-26-004613 | 7.9 | Crossroads | CR-S22-02 | Transformer replacement | P2 same day | 2026-05-06 | 2026-05-06 | 2026-05-06 | Contract line | CT-01 | 3471.93 | Completed | No
WO-26-004614 | 9.6 | Crossroads | CR-S24-01 | Transformer replacement | P2 same day | 2026-05-06 | 2026-05-07 | 2026-05-07 | Internal line |  | 4650 | Completed | No
WO-26-004615 | 4.3 | Crossroads | CR-S26-04 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 310.67 | Completed | No
WO-26-004616 | 2.9 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 178.67 | Completed | No
WO-26-004617 | 3.6 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 160.05 | Completed | No
WO-26-004618 | 5.5 | Crossroads | CR-S02-03 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 1.23 | Completed | No
WO-26-004619 | 4 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 33.51 | Completed | No
WO-26-004620 | 5.8 | Crossroads | CR-S20-01 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 120.54 | Completed | No
WO-26-004621 | 4.1 | Crossroads | CR-S07-02 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Internal line |  | 211.27 | Completed | No
WO-26-004622 | 5 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 333.67 | Completed | No
WO-26-004623 | 4.8 | Crossroads | CR-S28-02 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 33.15 | Completed | No
WO-26-004624 | 3.9 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-05-06 | 2026-05-06 | 2026-05-06 | Internal line |  | 298.55 | Completed | No
WO-26-004625 | 3 | Crossroads | CR-S32-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-06 | 2026-05-15 | 2026-05-17 | Troubleman |  | 93.3 | Completed | No
WO-26-004626 | 2.2 | Crossroads | CR-S14-02 | Trouble - partial or voltage | P2 same day | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 191.15 | Completed | No
WO-26-004627 | 2.5 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P2 same day | 2026-05-06 | 2026-05-06 | 2026-05-06 | Troubleman |  | 58.46 | Completed | No
WO-26-004628 | 6.5 | Bayou | BY-S02-01 | Corrective maintenance | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Contract line | CT-03 | 2031.35 | Completed | No
WO-26-004629 | 5.2 | Bayou | BY-S19-03 | Corrective maintenance | P3 within 10 days | 2026-05-07 | 2026-05-08 | 2026-05-08 | Internal line |  | 2215.89 | Completed | No
WO-26-004630 | 8.4 | Bayou | BY-S18-04 | Corrective maintenance | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Contract line | CT-04 | 1911.3 | Completed | No
WO-26-004631 | 10.5 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-05-07 | 2026-05-15 | 2026-05-15 | Contract line | CT-03 | 744.5 | Completed | No
WO-26-004632 | 0.7 | Bayou | BY-S02-01 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-14 | 2026-05-15 | Meter technician |  | 150.18 | Completed | No
WO-26-004633 | 1.1 | Bayou | BY-S05-02 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-09 | 2026-05-13 | Meter technician |  | 67.91 | Completed | No
WO-26-004634 | 0.8 | Bayou | BY-S22-03 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-08 | 2026-05-08 | Meter technician |  | 116.38 | Completed | No
WO-26-004635 | 0.8 | Bayou | BY-S16-06 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-17 | 2026-05-18 | Meter technician |  | 67.54 | Completed | No
WO-26-004636 | 0.6 | Bayou | BY-S18-01 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-13 | 2026-05-15 | Meter technician |  | 97.06 | Completed | No
WO-26-004637 | 3.9 | Bayou | BY-S21-05 | Preventive maintenance | P4 planned | 2026-05-07 | 2026-06-29 | 2026-07-01 | Internal line |  | 426.77 | Completed | No
WO-26-004638 | 2.6 | Bayou | BY-S27-06 | Preventive maintenance | P4 planned | 2026-05-07 | 2026-06-16 | 2026-06-16 | Internal line |  | 290.09 | Completed | No
WO-26-004639 | 2.5 | Bayou | BY-S10-03 | Preventive maintenance | P4 planned | 2026-05-07 | 2026-05-15 | 2026-05-15 | Internal line |  | 310.32 | Completed | No
WO-26-004640 | 4.8 | Bayou | BY-S19-01 | Preventive maintenance | P4 planned | 2026-05-07 | 2026-06-24 | 2026-06-24 | Underground crew |  | 409.8 | Completed | No
WO-26-004641 | 1.4 | Bayou | BY-S27-03 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-13 | 2026-05-17 | Meter technician |  | 31.08 | Completed | No
WO-26-004642 | 1 | Bayou | BY-S15-04 | Service order - field | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Meter technician |  | 25.58 | Completed | No
WO-26-004643 | 0.9 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Meter technician |  | 28.98 | Completed | No
WO-26-004644 | 1.9 | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Meter technician |  | 38.75 | Completed | No
WO-26-004645 | 1.2 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-12 | 2026-05-12 | Meter technician |  | 35.54 | Completed | No
WO-26-004646 | 1 | Bayou | BY-S27-04 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-16 | 2026-05-16 | Meter technician |  | 24.98 | Completed | No
WO-26-004647 | 1.4 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Meter technician |  | 18.72 | Completed | No
WO-26-004648 | 0.7 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Meter technician |  | 19.35 | Completed | No
WO-26-004649 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-07 | 2026-05-08 | 2026-05-10 | Internal line |  | 350 | Completed | No
WO-26-004650 | 7.7 | Bayou | BY-S12-03 | Transformer replacement | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Internal line |  | 6415.61 | Completed | No
WO-26-004651 | 13.8 | Bayou | BY-S18-01 | Transformer replacement | P2 same day | 2026-05-07 | 2026-05-08 | 2026-05-08 | Internal line |  | 9876.2 | Completed | No
WO-26-004652 | 4.6 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 146.91 | Completed | No
WO-26-004653 | 4.8 | Bayou | BY-S21-03 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 179.56 | Completed | No
WO-26-004654 | 5.8 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 118.11 | Completed | No
WO-26-004655 | 4.2 | Bayou | BY-S29-02 | Trouble - no power | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 84.32 | Completed | No
WO-26-004656 | 3 | Bayou | BY-S06-02 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 294.33 | Completed | No
WO-26-004657 | 5 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 140.53 | Completed | No
WO-26-004658 | 5.6 | Bayou | BY-S24-05 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 128.11 | Completed | No
WO-26-004659 | 2.7 | Bayou | BY-S24-05 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 147.55 | Completed | No
WO-26-004660 | 4.3 | Bayou | BY-S20-03 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 30.23 | Completed | No
WO-26-004661 | 2.2 | Bayou | BY-S15-04 | Trouble - partial or voltage | P3 within 10 days | 2026-05-07 | 2026-05-17 | 2026-05-17 | Troubleman |  | 27.19 | Completed | No
WO-26-004662 | 2.7 | Bayou | BY-S21-01 | Trouble - partial or voltage | P2 same day | 2026-05-07 | 2026-05-08 | 2026-05-08 | Troubleman |  | 123.87 | Completed | No
WO-26-004663 | 7.6 | Crossroads | CR-S07-03 | Corrective maintenance | P2 same day | 2026-05-07 | 2026-05-08 | 2026-05-08 | Underground crew |  | 166.5 | Completed | No
WO-26-004664 | 6.5 | Crossroads | CR-S04-03 | Corrective maintenance | P3 within 10 days | 2026-05-07 | 2026-05-12 | 2026-05-12 | Underground crew |  | 2336.04 | Completed | No
WO-26-004665 | 7.3 | Crossroads | CR-S27-01 | Corrective maintenance | P4 planned | 2026-05-07 | 2026-05-26 | 2026-05-26 | Underground crew |  | 294.3 | Completed | No
WO-26-004666 | 6.5 | Crossroads | CR-S02-05 | Corrective maintenance | P3 within 10 days | 2026-05-07 | 2026-05-09 | 2026-05-11 | Internal line |  | 900.66 | Completed | No
WO-26-004667 | 4.1 | Crossroads | CR-S20-05 | Corrective maintenance | P4 planned | 2026-05-07 | 2026-05-27 | 2026-05-27 | Internal line |  | 1837.94 | Completed | No
WO-26-004668 |  | Crossroads | CR-S04-03 | Corrective maintenance | P2 same day | 2026-05-07 | 2026-05-08 |  | Internal line |  |  | Cancelled | No
WO-26-004669 | 8.5 | Crossroads | CR-S09-01 | Corrective maintenance | P3 within 10 days | 2026-05-07 | 2026-05-15 | 2026-05-15 | Underground crew |  | 194.16 | Completed | No
WO-26-004670 | 0.6 | Crossroads | CR-S32-04 | Meter exchange | P4 planned | 2026-05-07 | 2026-06-09 | 2026-06-17 | Meter technician |  | 91.29 | Completed | No
WO-26-004671 | 1.4 | Crossroads | CR-S05-02 | Meter exchange | P4 planned | 2026-05-07 | 2026-06-03 | 2026-06-04 | Meter technician |  | 143.18 | Completed | No
WO-26-004672 | 1.1 | Crossroads | CR-S31-03 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-15 | 2026-05-15 | Meter technician |  | 67.71 | Completed | No
WO-26-004673 | 0.6 | Crossroads | CR-S05-03 | Meter exchange | P3 within 10 days | 2026-05-07 | 2026-05-09 | 2026-05-09 | Meter technician |  | 118.18 | Completed | No
WO-26-004674 | 1.1 | Crossroads | CR-S16-04 | Meter exchange | P4 planned | 2026-05-07 | 2026-06-01 | 2026-06-03 | Meter technician |  | 63.29 | Completed | No
WO-26-004675 | 0.8 | Crossroads | CR-S28-03 | Meter exchange | P4 planned | 2026-05-07 | 2026-06-12 | 2026-06-13 | Meter technician |  | 159.11 | Completed | No
WO-26-004676 | 21.7 | Crossroads | CR-S14-05 | Pole replacement | P4 planned | 2026-05-07 | 2026-06-19 | 2026-06-20 | Internal line |  | 2141.26 | Completed | No
WO-26-004677 | 4.7 | Crossroads | CR-S12-03 | Preventive maintenance | P4 planned | 2026-05-07 | 2026-05-20 | 2026-05-20 | Underground crew |  | 160.15 | Completed | No
WO-26-004678 | 3.5 | Crossroads | CR-S03-01 | Preventive maintenance | P4 planned | 2026-05-07 | 2026-06-05 | 2026-06-05 | Underground crew |  | 506.07 | Completed | No
WO-26-004679 | 1.7 | Crossroads | CR-S23-02 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-13 | 2026-05-15 | Meter technician |  | 37.84 | Completed | No
WO-26-004680 | 1.7 | Crossroads | CR-S07-07 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-10 | 2026-05-14 | Meter technician |  | 30.05 | Completed | No
WO-26-004681 | 0.9 | Crossroads | CR-S23-01 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-14 | 2026-05-16 | Meter technician |  | 32.53 | Completed | No
WO-26-004682 | 0.9 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Meter technician |  | 36.93 | Completed | No
WO-26-004683 | 1.8 | Crossroads | CR-S16-02 | Service order - field | P3 within 10 days | 2026-05-07 | 2026-05-13 | 2026-05-13 | Meter technician |  | 8.78 | Completed | No
WO-26-004684 | 2.2 | Crossroads |  | Streetlight | P4 planned | 2026-05-07 | 2026-05-31 | 2026-06-01 | Contract line | CT-02 | 333.31 | Completed | No
WO-26-004685 | 2.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-07 | 2026-05-10 | 2026-05-12 | Contract line | CT-01 | 151.98 | Completed | No
WO-26-004686 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-07 | 2026-05-16 | 2026-05-18 | Internal line |  | 62.27 | Completed | No
WO-26-004687 | 6.3 | Crossroads | CR-S19-03 | Transformer replacement | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Internal line |  | 5231.9 | Completed | No
WO-26-004688 | 8.3 | Crossroads | CR-S32-04 | Transformer replacement | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Contract line | CT-01 | 5267.42 | Completed | No
WO-26-004689 |  | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-05-07 | 2026-05-07 |  | Troubleman |  |  | Cancelled | No
WO-26-004690 | 3.4 | Crossroads | CR-S22-01 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 49.09 | Completed | No
WO-26-004691 | 5.9 | Crossroads | CR-S28-02 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 70.95 | Completed | No
WO-26-004692 | 2.8 | Crossroads | CR-S18-01 | Trouble - no power | P2 same day | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 255.04 | Completed | No
WO-26-004693 | 4 | Crossroads | CR-S30-04 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 328.03 | Completed | No
WO-26-004694 | 4.2 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-05-07 | 2026-05-07 | 2026-05-07 | Troubleman |  | 102.57 | Completed | No
WO-26-004695 | 1.8 | Crossroads | CR-S06-02 | Trouble - partial or voltage | P2 same day | 2026-05-07 | 2026-05-08 | 2026-05-08 | Troubleman |  | 0.91 | Completed | No
WO-26-004696 | 1.5 | Crossroads | CR-S10-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-07 | 2026-05-10 | 2026-05-11 | Troubleman |  | 152.15 | Completed | No
WO-26-004697 | 11.1 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-05-08 | 2026-05-10 | 2026-05-10 | Underground crew |  | 309.86 | Completed | No
WO-26-004698 | 8.4 | Bayou | BY-S06-01 | Corrective maintenance | P3 within 10 days | 2026-05-08 | 2026-05-12 | 2026-05-14 | Internal line |  | 2065.86 | Completed | No
WO-26-004699 | 4.5 | Bayou | BY-S14-01 | Corrective maintenance | P3 within 10 days | 2026-05-08 | 2026-05-11 | 2026-05-11 | Contract line | CT-04 | 329.37 | Completed | No
WO-26-004700 |  | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-05-08 | 2026-05-17 |  | Internal line |  |  | Cancelled | No
WO-26-004701 | 4.6 | Bayou | BY-S19-02 | Corrective maintenance | P4 planned | 2026-05-08 | 2026-07-01 | 2026-07-03 | Internal line |  | 1939.01 | Completed | No
WO-26-004702 | 6.9 | Bayou | BY-S28-01 | Corrective maintenance | P3 within 10 days | 2026-05-08 | 2026-05-18 | 2026-05-18 | Underground crew |  | 2380.13 | Completed | No
WO-26-004703 | 1.5 | Bayou | BY-S22-04 | Meter exchange | P3 within 10 days | 2026-05-08 | 2026-05-09 | 2026-05-09 | Meter technician |  | 149.94 | Completed | No
WO-26-004704 | 0.9 | Bayou | BY-S18-02 | Meter exchange | P3 within 10 days | 2026-05-08 | 2026-05-14 | 2026-05-16 | Meter technician |  | 65.76 | Completed | No
WO-26-004705 | 0.7 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-05-08 | 2026-05-15 | 2026-05-15 | Meter technician |  | 105.9 | Completed | No
WO-26-004706 | 0.7 | Bayou | BY-S18-02 | Meter exchange | P3 within 10 days | 2026-05-08 | 2026-05-11 | 2026-05-11 | Meter technician |  | 67.29 | Completed | No
WO-26-004707 | 4.2 | Bayou | BY-S13-01 | New service - small | P4 planned | 2026-05-08 | 2026-06-29 | 2026-07-01 | Contract line | CT-03 | 3156.62 | Completed | No
WO-26-004708 | 10.1 | Bayou | BY-S10-01 | New service - small | P4 planned | 2026-05-08 | 2026-05-27 | 2026-05-27 | Underground crew |  | 2192.61 | Completed | No
WO-26-004709 | 12.5 | Bayou | BY-S23-01 | Pole replacement | P4 planned | 2026-05-08 | 2026-05-28 | 2026-05-30 | Contract line | CT-03 | 2350.77 | Completed | No
WO-26-004710 | 2.8 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-05-17 | 2026-05-17 | Underground crew |  | 468.1 | Completed | No
WO-26-004711 | 3.1 | Bayou | BY-S11-01 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-06-17 | 2026-06-21 | Internal line |  | 543.9 | Completed | No
WO-26-004712 | 2.6 | Bayou | BY-S16-02 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-07-05 | 2026-07-06 | Internal line |  | 117.76 | Completed | No
WO-26-004713 | 5.9 | Bayou | BY-S26-04 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-06-02 | 2026-06-04 | Underground crew |  | 336.73 | Completed | No
WO-26-004714 | 0.9 | Bayou | BY-S23-01 | Service order - field | P3 within 10 days | 2026-05-08 | 2026-05-11 | 2026-05-11 | Meter technician |  | 16.01 | Completed | No
WO-26-004715 | 1.9 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-05-08 | 2026-05-18 | 2026-05-18 | Meter technician |  | 18.34 | Completed | No
WO-26-004716 | 0.7 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-05-08 | 2026-05-08 | 2026-05-08 | Meter technician |  | 19.41 | Completed | No
WO-26-004717 | 1.6 | Bayou | BY-S23-05 | Service order - field | P2 same day | 2026-05-08 | 2026-05-09 | 2026-05-09 | Meter technician |  | 19.94 | Completed | No
WO-26-004718 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-08 | 2026-05-16 | 2026-05-20 | Contract line | CT-04 | 225.23 | Completed | No
WO-26-004719 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-08 | 2026-05-16 | 2026-05-16 | Contract line | CT-04 | 100.62 | Completed | No
WO-26-004720 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-08 | 2026-05-16 | 2026-05-17 | Contract line | CT-03 | 411.6 | Completed | No
WO-26-004721 | 8.7 | Bayou | BY-S24-05 | Transformer replacement | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Internal line |  | 5375.77 | Completed | No
WO-26-004722 | 3.8 | Bayou | BY-S04-02 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 29.31 | Completed | No
WO-26-004723 | 2.2 | Bayou | BY-S15-02 | Trouble - no power | P2 same day | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 322.48 | Completed | No
WO-26-004724 | 5.5 | Bayou | BY-S18-04 | Trouble - no power | P2 same day | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 159.86 | Completed | No
WO-26-004725 | 4.4 | Bayou | BY-S18-07 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 217.38 | Completed | No
WO-26-004726 | 2.5 | Bayou | BY-S25-04 | Trouble - partial or voltage | P2 same day | 2026-05-08 | 2026-05-09 | 2026-05-09 | Troubleman |  | 192.2 | Completed | No
WO-26-004727 | 3.5 | Bayou | BY-S04-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-08 | 2026-05-16 | 2026-05-16 | Troubleman |  | 84.1 | Completed | No
WO-26-004728 | 2.2 | Bayou | BY-S09-01 | Trouble - partial or voltage | P2 same day | 2026-05-08 | 2026-05-09 | 2026-05-09 | Troubleman |  | 3.99 | Completed | No
WO-26-004729 | 7.7 | Crossroads | CR-S08-02 | Corrective maintenance | P4 planned | 2026-05-08 | 2026-05-19 | 2026-05-19 | Underground crew |  | 1557.01 | Completed | No
WO-26-004730 | 4.7 | Crossroads | CR-S09-01 | Corrective maintenance | P4 planned | 2026-05-08 | 2026-06-07 | 2026-06-07 | Contract line | CT-01 | 575.38 | Completed | No
WO-26-004731 | 5.5 | Crossroads | CR-S29-03 | Corrective maintenance | P4 planned | 2026-05-08 | 2026-05-16 | 2026-05-16 | Contract line | CT-01 | 1911.76 | Completed | No
WO-26-004732 | 9.4 | Crossroads | CR-S30-06 | Corrective maintenance | P3 within 10 days | 2026-05-08 | 2026-05-15 | 2026-05-15 | Contract line | CT-01 | 1364.06 | Completed | No
WO-26-004733 | 1.4 | Crossroads | CR-S21-01 | Meter exchange | P3 within 10 days | 2026-05-08 | 2026-05-15 | 2026-05-17 | Meter technician |  | 103.26 | Completed | No
WO-26-004734 | 1.1 | Crossroads | CR-S14-04 | Meter exchange | P4 planned | 2026-05-08 | 2026-05-26 | 2026-05-26 | Meter technician |  | 64.21 | Completed | No
WO-26-004735 | 0.5 | Crossroads | CR-S09-01 | Meter exchange | P4 planned | 2026-05-08 | 2026-06-07 | 2026-06-09 | Meter technician |  | 78.83 | Completed | No
WO-26-004736 | 13.9 | Crossroads | CR-S18-01 | Pole replacement | P4 planned | 2026-05-08 | 2026-05-17 | 2026-05-17 | Contract line | CT-02 | 1499.03 | Completed | No
WO-26-004737 | 6.5 | Crossroads | CR-S12-02 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-05-26 | 2026-05-26 | Internal line |  | 152.37 | Completed | No
WO-26-004738 | 7.7 | Crossroads | CR-S28-03 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-06-19 | 2026-06-19 | Internal line |  | 245 | Completed | No
WO-26-004739 | 5 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-05-08 | 2026-06-11 | 2026-06-19 | Internal line |  | 53.42 | Completed | No
WO-26-004740 | 0.6 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-05-08 | 2026-05-10 | 2026-05-11 | Meter technician |  | 30.09 | Completed | No
WO-26-004741 | 1.2 | Crossroads | CR-S12-01 | Service order - field | P3 within 10 days | 2026-05-08 | 2026-05-15 | 2026-05-15 | Meter technician |  | 14.03 | Completed | No
WO-26-004742 | 0.6 | Crossroads | CR-S16-04 | Service order - field | P3 within 10 days | 2026-05-08 | 2026-05-16 | 2026-05-18 | Meter technician |  | 23.15 | Completed | No
WO-26-004743 | 1.3 | Crossroads | CR-S19-04 | Service order - field | P3 within 10 days | 2026-05-08 | 2026-05-09 | 2026-05-09 | Meter technician |  | 31.52 | Completed | No
WO-26-004744 | 13.4 | Crossroads | CR-S28-01 | Transformer replacement | P3 within 10 days | 2026-05-08 | 2026-05-18 | 2026-05-20 | Internal line |  | 9699.49 | Completed | No
WO-26-004745 | 5.2 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 302.6 | Completed | No
WO-26-004746 | 5.6 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 344.61 | Completed | No
WO-26-004747 | 3.9 | Crossroads | CR-S27-03 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 231.02 | Completed | No
WO-26-004748 | 4.1 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Internal line |  | 299.02 | Completed | No
WO-26-004749 | 4.5 | Crossroads | CR-S13-02 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 44.95 | Completed | No
WO-26-004750 | 5.4 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-05-08 | 2026-05-08 | 2026-05-08 | Troubleman |  | 226.87 | Completed | No
WO-26-004751 | 3 | Crossroads | CR-S02-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-08 | 2026-05-17 | 2026-05-17 | Troubleman |  | 181.07 | Completed | No
WO-26-004752 | 1.7 | Crossroads | CR-S14-03 | Trouble - partial or voltage | P2 same day | 2026-05-08 | 2026-05-09 | 2026-05-09 | Troubleman |  | 127.88 | Completed | No
WO-26-004753 | 4.2 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-08 | 2026-05-09 | 2026-05-09 | Troubleman |  | 52.56 | Completed | No
WO-26-004754 | 3.1 | Crossroads | CR-S07-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-08 | 2026-05-16 | 2026-05-16 | Troubleman |  | 108.71 | Completed | No
WO-26-004755 | 4.9 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-08 | 2026-05-17 | 2026-05-17 | Troubleman |  | 221.05 | Completed | No
WO-26-004756 | 7.6 | Bayou | BY-S13-05 | Corrective maintenance | P2 same day | 2026-05-09 | 2026-05-09 | 2026-05-09 | Internal line |  | 895.99 | Completed | No
WO-26-004757 | 2 | Bayou | BY-S18-01 | Service order - field | P2 same day | 2026-05-09 | 2026-05-09 | 2026-05-09 | Meter technician |  | 12.54 | Completed | No
WO-26-004758 | 1 | Bayou | BY-S07-02 | Service order - field | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Meter technician |  | 28.01 | Completed | No
WO-26-004759 | 12.8 | Bayou | BY-S19-02 | Transformer replacement | P2 same day | 2026-05-09 | 2026-05-09 | 2026-05-09 | Contract line | CT-04 | 6913.98 | Completed | No
WO-26-004760 | 3.2 | Bayou | BY-S15-02 | Trouble - no power | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Troubleman |  | 239.85 | Completed | No
WO-26-004761 | 4.6 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Internal line |  | 97.33 | Completed | No
WO-26-004762 | 5.4 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-05-09 | 2026-05-09 | 2026-05-09 | Troubleman |  | 122.33 | Completed | No
WO-26-004763 | 2 | Bayou | BY-S30-03 | Trouble - no power | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Troubleman |  | 48.7 | Completed | No
WO-26-004764 | 5.9 | Bayou | BY-S10-01 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Troubleman |  | 342.34 | Completed | No
WO-26-004765 | 5.6 | Bayou | BY-S15-03 | Trouble - no power | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Troubleman |  | 131.4 | Completed | No
WO-26-004766 | 5.8 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Troubleman |  | 304.97 | Completed | No
WO-26-004767 | 2.2 | Bayou | BY-S05-02 | Trouble - partial or voltage | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Troubleman |  | 6.49 | Completed | No
WO-26-004768 | 5.3 | Crossroads | CR-S15-01 | Corrective maintenance | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Underground crew |  | 98.28 | Completed | No
WO-26-004769 | 1.8 | Crossroads | CR-S11-01 | Service order - field | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Meter technician |  | 26.04 | Completed | No
WO-26-004770 | 1.3 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-05-09 | 2026-05-09 | 2026-05-09 | Meter technician |  | 0.08 | Completed | No
WO-26-004771 | 1.3 | Crossroads | CR-S19-01 | Service order - field | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Meter technician |  | 9.64 | Completed | No
WO-26-004772 | 5.8 | Crossroads | CR-S08-02 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Troubleman |  | 21.41 | Completed | No
WO-26-004773 | 5.9 | Crossroads | CR-S17-03 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Troubleman |  | 39.04 | Completed | No
WO-26-004774 | 5.1 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Internal line |  | 101.25 | Completed | No
WO-26-004775 | 2.7 | Crossroads | CR-S18-05 | Trouble - no power | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Troubleman |  | 313.34 | Completed | No
WO-26-004776 | 2.2 | Crossroads | CR-S25-01 | Trouble - no power | P2 same day | 2026-05-09 | 2026-05-10 | 2026-05-10 | Troubleman |  | 194.81 | Completed | No
WO-26-004777 | 5.6 | Crossroads | CR-S27-01 | Trouble - no power | P1 emergency | 2026-05-09 | 2026-05-09 | 2026-05-09 | Troubleman |  | 101.39 | Completed | No
WO-26-004778 | 21.5 | Bayou | BY-S19-03 | Pole replacement | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Contract line | CT-03 | 2259.77 | Completed | No
WO-26-004779 | 1 | Bayou | BY-S22-02 | Service order - field | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Meter technician |  | 20.26 | Completed | No
WO-26-004780 | 2 | Bayou | BY-S08-02 | Service order - field | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Meter technician |  | 2.62 | Completed | No
WO-26-004781 | 9.3 | Bayou | BY-S18-05 | Transformer replacement | P2 same day | 2026-05-10 | 2026-05-10 | 2026-05-10 | Internal line |  | 3289.66 | Completed | No
WO-26-004782 | 5.1 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 302.82 | Completed | No
WO-26-004783 | 4.4 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 230.98 | Completed | No
WO-26-004784 | 8.6 | Crossroads | CR-S23-02 | Corrective maintenance | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Internal line |  | 1545.71 | Completed | No
WO-26-004785 | 3.3 | Crossroads | CR-S13-06 | Corrective maintenance | P2 same day | 2026-05-10 | 2026-05-10 | 2026-05-10 | Internal line |  | 768.01 | Completed | No
WO-26-004786 | 1.9 | Crossroads | CR-S24-01 | Service order - field | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Meter technician |  | 28.77 | Completed | No
WO-26-004787 | 0.9 | Crossroads | CR-S05-06 | Service order - field | P2 same day | 2026-05-10 | 2026-05-10 | 2026-05-10 | Meter technician |  | 5.52 | Completed | No
WO-26-004788 | 1 | Crossroads | CR-S08-06 | Service order - field | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Meter technician |  | 24.02 | Completed | No
WO-26-004789 | 8.9 | Crossroads | CR-S04-06 | Transformer replacement | P2 same day | 2026-05-10 | 2026-05-10 | 2026-05-10 | Internal line |  | 4575.76 | Completed | No
WO-26-004790 | 7.4 | Crossroads | CR-S17-01 | Transformer replacement | P2 same day | 2026-05-10 | 2026-05-10 | 2026-05-10 | Internal line |  | 4547.26 | Completed | No
WO-26-004791 | 4 | Crossroads | CR-S08-04 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 164 | Completed | No
WO-26-004792 | 5.4 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-05-10 | 2026-05-11 | 2026-05-11 | Troubleman |  | 28.63 | Completed | No
WO-26-004793 | 2.2 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 306.84 | Completed | No
WO-26-004794 | 2.3 | Crossroads | CR-S14-03 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 193.74 | Completed | No
WO-26-004795 | 4.3 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 68.42 | Completed | No
WO-26-004796 | 2.4 | Crossroads | CR-S08-02 | Trouble - no power | P2 same day | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 251.19 | Completed | No
WO-26-004797 | 4.6 | Crossroads | CR-S20-04 | Trouble - no power | P1 emergency | 2026-05-10 | 2026-05-10 | 2026-05-10 | Troubleman |  | 269.51 | Completed | No
WO-26-004798 | 9.2 | Bayou | BY-S16-06 | Corrective maintenance | P4 planned | 2026-05-11 | 2026-06-28 | 2026-06-29 | Internal line |  | 963 | Completed | No
WO-26-004799 | 8.4 | Bayou | BY-S29-01 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-14 | 2026-05-15 | Contract line | CT-03 | 1965.85 | Completed | No
WO-26-004800 | 3.4 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-17 | 2026-05-18 | Internal line |  | 779.16 | Completed | No
WO-26-004801 | 9.5 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-21 | 2026-05-23 | Contract line | CT-04 | 281.17 | Completed | No
WO-26-004802 | 5.8 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-20 | 2026-05-21 | Internal line |  | 1429.39 | Completed | No
WO-26-004803 | 1 | Bayou | BY-S04-03 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-13 | 2026-05-17 | Meter technician |  | 104.54 | Completed | No
WO-26-004804 | 0.9 | Bayou | BY-S25-05 | Meter exchange | P4 planned | 2026-05-11 | 2026-06-26 | 2026-06-30 | Meter technician |  | 60.71 | Completed | No
WO-26-004805 | 1.4 | Bayou | BY-S09-03 | Meter exchange | P4 planned | 2026-05-11 | 2026-06-21 | 2026-06-21 | Meter technician |  | 61.32 | Completed | No
WO-26-004806 |  | Bayou | BY-S16-06 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-13 |  | Meter technician |  |  | Cancelled | No
WO-26-004807 | 0.7 | Bayou | BY-S10-01 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-19 | 2026-05-20 | Meter technician |  | 60.6 | Completed | No
WO-26-004808 | 1.3 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-21 | 2026-05-21 | Meter technician |  | 161.56 | Completed | No
WO-26-004809 | 1.4 | Bayou | BY-S13-06 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-13 | 2026-05-14 | Meter technician |  | 161.39 | Completed | No
WO-26-004810 | 0.5 | Bayou | BY-S22-04 | Meter exchange | P4 planned | 2026-05-11 | 2026-07-01 | 2026-07-05 | Meter technician |  | 67.6 | Completed | No
WO-26-004811 | 1.1 | Bayou | BY-S19-01 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-20 | 2026-05-20 | Meter technician |  | 174.37 | Completed | No
WO-26-004812 | 0.9 | Bayou | BY-S18-04 | Meter exchange | P4 planned | 2026-05-11 | 2026-05-21 | 2026-05-21 | Meter technician |  | 69.24 | Completed | No
WO-26-004813 | 3.2 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-05-11 | 2026-07-01 | 2026-07-01 | Underground crew |  | 505.05 | Completed | No
WO-26-004814 | 4.3 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-05-11 | 2026-05-20 | 2026-05-20 | Internal line |  | 200.03 | Completed | No
WO-26-004815 | 2 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-12 | 2026-05-13 | Meter technician |  | 18.71 | Completed | No
WO-26-004816 | 0.6 | Bayou | BY-S05-03 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-13 | 2026-05-13 | Meter technician |  | 19.22 | Completed | No
WO-26-004817 | 0.7 | Bayou | BY-S03-03 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-19 | 2026-05-19 | Meter technician |  | 38.72 | Completed | No
WO-26-004818 | 0.6 | Bayou | BY-S17-02 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-15 | 2026-05-16 | Meter technician |  | 31.57 | Completed | No
WO-26-004819 | 3.8 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Internal line |  | 179.28 | Completed | No
WO-26-004820 | 2.3 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 264.13 | Completed | No
WO-26-004821 | 5.3 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Internal line |  | 262.04 | Completed | No
WO-26-004822 | 4.4 | Bayou | BY-S28-02 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 296.2 | Completed | No
WO-26-004823 | 4.9 | Bayou | BY-S03-01 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Internal line |  | 168.65 | Completed | No
WO-26-004824 | 3.8 | Bayou | BY-S14-02 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 295.65 | Completed | No
WO-26-004825 | 4.2 | Bayou | BY-S17-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-11 | 2026-05-15 | 2026-05-16 | Troubleman |  | 95.06 | Completed | No
WO-26-004826 | 2.8 | Bayou | BY-S27-06 | Trouble - partial or voltage | P3 within 10 days | 2026-05-11 | 2026-05-20 | 2026-05-24 | Troubleman |  | 23.42 | Completed | No
WO-26-004827 | 2.4 | Bayou | BY-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-11 | 2026-05-16 | 2026-05-16 | Troubleman |  | 56.21 | Completed | No
WO-26-004828 | 7.9 | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-20 | 2026-05-21 | Contract line | CT-02 | 601.82 | Completed | No
WO-26-004829 | 9.9 | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-12 | 2026-05-13 | Internal line |  | 1416.59 | Completed | No
WO-26-004830 | 11.6 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-05-11 | 2026-05-16 | 2026-05-17 | Internal line |  | 360.84 | Completed | No
WO-26-004831 | 1.4 | Crossroads | CR-S32-04 | Meter exchange | P4 planned | 2026-05-11 | 2026-06-21 | 2026-06-21 | Meter technician |  | 95.81 | Completed | No
WO-26-004832 | 1.4 | Crossroads | CR-S25-03 | Meter exchange | P4 planned | 2026-05-11 | 2026-06-21 | 2026-06-22 | Meter technician |  | 103.15 | Completed | No
WO-26-004833 | 0.8 | Crossroads | CR-S20-01 | Meter exchange | P4 planned | 2026-05-11 | 2026-06-07 | 2026-06-07 | Meter technician |  | 141.35 | Completed | No
WO-26-004834 | 1.3 | Crossroads | CR-S10-01 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-17 | 2026-05-21 | Meter technician |  | 161.68 | Completed | No
WO-26-004835 | 0.7 | Crossroads | CR-S27-01 | Meter exchange | P3 within 10 days | 2026-05-11 | 2026-05-13 | 2026-05-13 | Meter technician |  | 71.97 | Completed | No
WO-26-004836 | 11.4 | Crossroads | CR-S27-02 | New service - small | P3 within 10 days | 2026-05-11 | 2026-05-19 | 2026-05-21 | Contract line | CT-01 | 1522.16 | Completed | No
WO-26-004837 | 22.6 | Crossroads | CR-S09-02 | Pole replacement | P3 within 10 days | 2026-05-11 | 2026-05-21 | 2026-05-22 | Internal line |  | 2401.9 | Completed | No
WO-26-004838 | 18.5 | Crossroads | CR-S29-03 | Pole replacement | P4 planned | 2026-05-11 | 2026-06-08 | 2026-06-08 | Internal line |  | 2991.87 | Completed | No
WO-26-004839 | 4.7 | Crossroads | CR-S01-03 | Preventive maintenance | P4 planned | 2026-05-11 | 2026-05-25 | 2026-05-27 | Contract line | CT-02 | 78.46 | Completed | No
WO-26-004840 | 3.5 | Crossroads | CR-S04-03 | Preventive maintenance | P4 planned | 2026-05-11 | 2026-06-25 | 2026-06-26 | Underground crew |  | 203.23 | Completed | No
WO-26-004841 | 5.2 | Crossroads | CR-S18-01 | Preventive maintenance | P4 planned | 2026-05-11 | 2026-05-19 | 2026-05-19 | Underground crew |  | 350.17 | Completed | No
WO-26-004842 | 2.7 | Crossroads | CR-S02-03 | Preventive maintenance | P4 planned | 2026-05-11 | 2026-06-08 | 2026-06-08 | Underground crew |  | 29.31 | Completed | No
WO-26-004843 | 1.8 | Crossroads | CR-S24-01 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-15 | 2026-05-17 | Meter technician |  | 11.92 | Completed | No
WO-26-004844 | 0.6 | Crossroads | CR-S04-06 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-17 | 2026-05-17 | Meter technician |  | 28.69 | Completed | No
WO-26-004845 | 1.3 | Crossroads | CR-S25-02 | Service order - field | P3 within 10 days | 2026-05-11 | 2026-05-12 | 2026-05-12 | Meter technician |  | 26.75 | Completed | No
WO-26-004846 | 1.1 | Crossroads | CR-S23-05 | Service order - field | P2 same day | 2026-05-11 | 2026-05-11 | 2026-05-11 | Meter technician |  | 17.36 | Completed | No
WO-26-004847 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-11 | 2026-05-21 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-004848 | 3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-11 | 2026-05-21 | 2026-05-21 | Internal line |  | 263.42 | Completed | No
WO-26-004849 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-11 | 2026-05-17 | 2026-05-17 | Internal line |  | 220.89 | Completed | No
WO-26-004850 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-11 | 2026-05-14 | 2026-05-15 | Contract line | CT-01 | 70.22 | Completed | No
WO-26-004851 | 7.4 | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Internal line |  | 6236.65 | Completed | No
WO-26-004852 | 9 | Crossroads | CR-S22-04 | Transformer replacement | P2 same day | 2026-05-11 | 2026-05-12 | 2026-05-12 | Internal line |  | 4811.07 | Completed | No
WO-26-004853 | 4.4 | Crossroads | CR-S18-01 | Trouble - no power | P2 same day | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 243.5 | Completed | No
WO-26-004854 | 5.3 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 206.13 | Completed | No
WO-26-004855 | 6 | Crossroads | CR-S21-03 | Trouble - no power | P2 same day | 2026-05-11 | 2026-05-12 | 2026-05-12 | Troubleman |  | 94.14 | Completed | No
WO-26-004856 | 5.5 | Crossroads | CR-S02-04 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 64.93 | Completed | No
WO-26-004857 | 3.2 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 24.32 | Completed | No
WO-26-004858 | 3.5 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 265.68 | Completed | No
WO-26-004859 | 5 | Crossroads | CR-S18-04 | Trouble - no power | P2 same day | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 240.16 | Completed | No
WO-26-004860 | 1.7 | Crossroads | CR-S32-05 | Trouble - partial or voltage | P2 same day | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 11.71 | Completed | No
WO-26-004861 | 1.9 | Crossroads | CR-S15-02 | Trouble - partial or voltage | P2 same day | 2026-05-11 | 2026-05-11 | 2026-05-11 | Troubleman |  | 244.12 | Completed | No
WO-26-004862 | 4.6 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P2 same day | 2026-05-11 | 2026-05-11 | 2026-05-11 | Internal line |  | 182.22 | Completed | No
WO-26-004863 | 4.9 | Crossroads | CR-S01-03 | Trouble - partial or voltage | P2 same day | 2026-05-11 | 2026-05-12 | 2026-05-12 | Troubleman |  | 62.3 | Completed | No
WO-26-004864 | 2.1 | Crossroads | CR-S32-03 | Trouble - partial or voltage | P2 same day | 2026-05-11 | 2026-05-12 | 2026-05-12 | Troubleman |  | 126.25 | Completed | No
WO-26-004865 |  | Bayou | BY-S04-03 | Corrective maintenance | P4 planned | 2026-05-12 | 2026-05-31 |  | Internal line |  |  | Cancelled | No
WO-26-004866 | 11.1 | Bayou | BY-S05-01 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-17 | 2026-05-18 | Internal line |  | 475.85 | Completed | No
WO-26-004867 | 8.4 | Bayou | BY-S29-01 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-19 | 2026-05-21 | Internal line |  | 380.58 | Completed | No
WO-26-004868 |  | Bayou | BY-S14-01 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-15 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-004869 | 10.1 | Bayou | BY-S19-01 | Corrective maintenance | P2 same day | 2026-05-12 | 2026-05-13 | 2026-05-13 | Underground crew |  | 122.62 | Completed | No
WO-26-004870 | 9 | Bayou | BY-S19-03 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-21 | 2026-05-21 | Contract line | CT-04 | 764.78 | Completed | No
WO-26-004871 | 8.4 | Bayou | BY-S26-03 | Corrective maintenance | P4 planned | 2026-05-12 | 2026-05-28 | 2026-05-28 | Contract line | CT-03 | 1192.43 | Completed | No
WO-26-004872 | 8.3 | Bayou | BY-S07-04 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-19 | 2026-05-19 | Internal line |  | 452.62 | Completed | No
WO-26-004873 | 11.7 | Bayou | BY-S30-02 | Corrective maintenance | P4 planned | 2026-05-12 | 2026-05-31 | 2026-05-31 | Internal line |  | 287.36 | Completed | No
WO-26-004874 | 1.5 | Bayou | BY-S22-04 | Meter exchange | P3 within 10 days | 2026-05-12 | 2026-05-14 | 2026-05-14 | Meter technician |  | 172.75 | Completed | No
WO-26-004875 | 0.7 | Bayou | BY-S17-02 | Meter exchange | P4 planned | 2026-05-12 | 2026-07-09 | 2026-07-13 | Meter technician |  | 141.43 | Completed | No
WO-26-004876 | 0.8 | Bayou | BY-S23-03 | Meter exchange | P3 within 10 days | 2026-05-12 | 2026-05-13 | 2026-05-21 | Meter technician |  | 179.43 | Completed | No
WO-26-004877 | 6.4 | Bayou | BY-S25-02 | New service - small | P4 planned | 2026-05-12 | 2026-06-12 | 2026-06-16 | Contract line | CT-04 | 3182.64 | Completed | No
WO-26-004878 | 11.1 | Bayou | BY-S12-03 | Pole replacement | P3 within 10 days | 2026-05-12 | 2026-05-20 | 2026-05-20 | Contract line | CT-03 | 1384.24 | Completed | No
WO-26-004879 | 5.8 | Bayou | BY-S11-03 | Preventive maintenance | P4 planned | 2026-05-12 | 2026-06-17 | 2026-06-17 | Internal line |  | 203.19 | Completed | No
WO-26-004880 | 1.6 | Bayou | BY-S07-05 | Service order - field | P2 same day | 2026-05-12 | 2026-05-13 | 2026-05-13 | Meter technician |  | 9.5 | Completed | No
WO-26-004881 | 1.3 | Bayou | BY-S25-03 | Service order - field | P3 within 10 days | 2026-05-12 | 2026-05-17 | 2026-05-17 | Meter technician |  | 37.07 | Completed | No
WO-26-004882 | 1.9 | Bayou |  | Streetlight | P4 planned | 2026-05-12 | 2026-06-24 | 2026-07-02 | Contract line | CT-04 | 356.38 | Completed | No
WO-26-004883 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-12 | 2026-05-14 | 2026-05-14 | Internal line |  | 56.76 | Completed | No
WO-26-004884 | 1 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-12 | 2026-05-14 | 2026-05-22 | Contract line | CT-04 | 118.14 | Completed | No
WO-26-004885 | 4.4 | Bayou | BY-S20-02 | Trouble - no power | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 26.51 | Completed | No
WO-26-004886 | 3.4 | Bayou | BY-S22-03 | Trouble - no power | P2 same day | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 99.46 | Completed | No
WO-26-004887 | 3.5 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 337.75 | Completed | No
WO-26-004888 | 4.9 | Bayou | BY-S21-03 | Trouble - no power | P2 same day | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 188.95 | Completed | No
WO-26-004889 | 4.8 | Bayou | BY-S21-05 | Trouble - no power | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 158.55 | Completed | No
WO-26-004890 | 4.1 | Bayou | BY-S04-02 | Trouble - no power | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 39.91 | Completed | No
WO-26-004891 | 2.1 | Bayou | BY-S03-01 | Trouble - no power | P2 same day | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 69.17 | Completed | No
WO-26-004892 | 3.6 | Bayou | BY-S10-04 | Trouble - partial or voltage | P3 within 10 days | 2026-05-12 | 2026-05-19 | 2026-05-20 | Internal line |  | 118.25 | Completed | No
WO-26-004893 | 10.4 | Crossroads | CR-S09-05 | Corrective maintenance | P4 planned | 2026-05-12 | 2026-05-24 | 2026-05-25 | Underground crew |  | 2006.78 | Completed | No
WO-26-004894 | 7.1 | Crossroads | CR-S04-05 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-15 | 2026-05-17 | Underground crew |  | 711.68 | Completed | No
WO-26-004895 | 10.8 | Crossroads | CR-S21-03 | Corrective maintenance | P2 same day | 2026-05-12 | 2026-05-12 | 2026-05-12 | Internal line |  | 1111.02 | Completed | No
WO-26-004896 | 7.5 | Crossroads | CR-S32-01 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-20 | 2026-05-24 | Underground crew |  | 1446.7 | Completed | No
WO-26-004897 | 5.4 | Crossroads | CR-S24-03 | Corrective maintenance | P4 planned | 2026-05-12 | 2026-05-29 | 2026-05-30 | Internal line |  | 438.94 | Completed | No
WO-26-004898 | 4.1 | Crossroads | CR-S02-01 | Corrective maintenance | P3 within 10 days | 2026-05-12 | 2026-05-19 | 2026-05-21 | Internal line |  | 1702.33 | Completed | No
WO-26-004899 | 1.4 | Crossroads | CR-S27-02 | Meter exchange | P4 planned | 2026-05-12 | 2026-05-30 | 2026-05-30 | Meter technician |  | 89.43 | Completed | No
WO-26-004900 | 4.6 | Crossroads | CR-S32-02 | New service - small | P3 within 10 days | 2026-05-12 | 2026-05-21 | 2026-05-21 | Underground crew |  | 368.2 | Completed | No
WO-26-004901 | 13.2 | Crossroads | CR-S07-03 | New service - small | P4 planned | 2026-05-12 | 2026-05-27 | 2026-05-27 | Underground crew |  | 1327.5 | Completed | No
WO-26-004902 | 14.2 | Crossroads | CR-S14-04 | New service - small | P4 planned | 2026-05-12 | 2026-06-04 | 2026-06-06 | Internal line |  | 1547.29 | Completed | No
WO-26-004903 | 10.3 | Crossroads | CR-S19-04 | Pole replacement | P4 planned | 2026-05-12 | 2026-06-06 | 2026-06-10 | Internal line |  | 1990.32 | Completed | No
WO-26-004904 | 6.2 | Crossroads | CR-S31-03 | Preventive maintenance | P4 planned | 2026-05-12 | 2026-06-05 | 2026-06-06 | Underground crew |  | 372.84 | Completed | No
WO-26-004905 | 5.4 | Crossroads | CR-S22-02 | Preventive maintenance | P4 planned | 2026-05-12 | 2026-05-21 | 2026-05-22 | Underground crew |  | 256.36 | Completed | No
WO-26-004906 | 0.5 | Crossroads | CR-S19-03 | Service order - field | P3 within 10 days | 2026-05-12 | 2026-05-16 | 2026-05-17 | Meter technician |  | 23.22 | Completed | No
WO-26-004907 | 1.1 | Crossroads | CR-S08-06 | Service order - field | P3 within 10 days | 2026-05-12 | 2026-05-13 | 2026-05-21 | Meter technician |  | 32.29 | Completed | No
WO-26-004908 | 1.4 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-05-12 | 2026-05-21 | 2026-05-21 | Meter technician |  | 22.99 | Completed | No
WO-26-004909 | 1 | Crossroads | CR-S14-02 | Service order - field | P3 within 10 days | 2026-05-12 | 2026-05-22 | 2026-05-22 | Meter technician |  | 15.63 | Completed | No
WO-26-004910 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-12 | 2026-05-13 | 2026-05-15 | Internal line |  | 430.44 | Completed | No
WO-26-004911 | 13 | Crossroads | CR-S27-03 | Transformer replacement | P2 same day | 2026-05-12 | 2026-05-13 | 2026-05-13 | Internal line |  | 9029.08 | Completed | No
WO-26-004912 | 7 | Crossroads | CR-S04-03 | Transformer replacement | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Internal line |  | 9616.09 | Completed | No
WO-26-004913 | 4.7 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 67.6 | Completed | No
WO-26-004914 | 2.8 | Crossroads | CR-S07-01 | Trouble - no power | P1 emergency | 2026-05-12 | 2026-05-12 | 2026-05-12 | Troubleman |  | 254.58 | Completed | No
WO-26-004915 | 4 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-05-12 | 2026-05-13 | 2026-05-13 | Internal line |  | 44.12 | Completed | No
WO-26-004916 | 2.5 | Crossroads | CR-S21-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-12 | 2026-05-16 | 2026-05-16 | Internal line |  | 186.31 | Completed | No
WO-26-004917 | 11.8 | Bayou | BY-S19-02 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-15 | 2026-05-17 | Internal line |  | 947.47 | Completed | No
WO-26-004918 | 5.4 | Bayou | BY-S11-01 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-21 | 2026-05-22 | Internal line |  | 1178.71 | Completed | No
WO-26-004919 | 8.2 | Bayou | BY-S27-04 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-19 | 2026-05-20 | Internal line |  | 486.57 | Completed | No
WO-26-004920 | 3.5 | Bayou | BY-S15-06 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-22 | 2026-05-22 | Contract line | CT-03 | 276.01 | Completed | No
WO-26-004921 | 11.2 | Bayou | BY-S15-01 | Corrective maintenance | P4 planned | 2026-05-13 | 2026-06-29 | 2026-06-30 | Contract line | CT-04 | 1361.87 | Completed | No
WO-26-004922 | 10.1 | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-05-13 | 2026-07-06 | 2026-07-06 | Internal line |  | 1309.26 | Completed | No
WO-26-004923 | 3.6 | Bayou | BY-S16-04 | Corrective maintenance | P2 same day | 2026-05-13 | 2026-05-13 | 2026-05-13 | Underground crew |  | 1652.22 | Completed | No
WO-26-004924 | 7.9 | Bayou | BY-S29-02 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-15 | 2026-05-19 | Contract line | CT-03 | 961.89 | Completed | No
WO-26-004925 | 0.9 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-05-13 | 2026-05-19 | 2026-05-23 | Meter technician |  | 174.69 | Completed | No
WO-26-004926 | 8.9 | Bayou | BY-S19-04 | New service - small | P3 within 10 days | 2026-05-13 | 2026-05-18 | 2026-05-20 | Contract line | CT-04 | 4181.6 | Completed | No
WO-26-004927 | 14.3 | Bayou | BY-S13-05 | New service - small | P4 planned | 2026-05-13 | 2026-06-16 | 2026-06-17 | Internal line |  | 3310.26 | Completed | No
WO-26-004928 | 11 | Bayou | BY-S30-02 | New service - small | P4 planned | 2026-05-13 | 2026-07-09 | 2026-07-11 | Contract line | CT-04 | 2048.31 | Completed | No
WO-26-004929 | 5.3 | Bayou | BY-S05-03 | Preventive maintenance | P4 planned | 2026-05-13 | 2026-07-10 | 2026-07-18 | Internal line |  | 559.33 | Completed | No
WO-26-004930 | 4.5 | Bayou | BY-S09-01 | Preventive maintenance | P4 planned | 2026-05-13 | 2026-06-02 | 2026-06-02 | Internal line |  | 333.41 | Completed | No
WO-26-004931 | 6.7 | Bayou | BY-S12-03 | Preventive maintenance | P4 planned | 2026-05-13 | 2026-06-03 | 2026-06-04 | Internal line |  | 574.35 | Completed | No
WO-26-004932 | 0.6 | Bayou | BY-S27-01 | Service order - field | P3 within 10 days | 2026-05-13 | 2026-05-19 | 2026-05-23 | Meter technician |  | 33.32 | Completed | No
WO-26-004933 | 1.9 | Bayou | BY-S08-01 | Service order - field | P3 within 10 days | 2026-05-13 | 2026-05-14 | 2026-05-14 | Meter technician |  | 7.26 | Completed | No
WO-26-004934 | 1.5 | Bayou |  | Streetlight | P4 planned | 2026-05-13 | 2026-05-28 | 2026-05-28 | Internal line |  | 199.37 | Completed | No
WO-26-004935 | 3.7 | Bayou | BY-S09-04 | Trouble - no power | P2 same day | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 226.26 | Completed | No
WO-26-004936 | 4.6 | Bayou | BY-S09-03 | Trouble - no power | P1 emergency | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 169.34 | Completed | No
WO-26-004937 | 4.6 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 326.81 | Completed | No
WO-26-004938 | 5.8 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-05-13 | 2026-05-14 | 2026-05-14 | Internal line |  | 86.59 | Completed | No
WO-26-004939 | 5.6 | Bayou | BY-S16-06 | Trouble - no power | P2 same day | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 237.36 | Completed | No
WO-26-004940 | 3.3 | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 171.11 | Completed | No
WO-26-004941 | 3 | Bayou | BY-S19-01 | Trouble - partial or voltage | P2 same day | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 222.29 | Completed | No
WO-26-004942 | 2.5 | Bayou | BY-S07-04 | Trouble - partial or voltage | P3 within 10 days | 2026-05-13 | 2026-05-21 | 2026-05-21 | Troubleman |  | 88.65 | Completed | No
WO-26-004943 | 6.6 | Crossroads | CR-S30-03 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-21 | 2026-05-22 | Internal line |  | 1318.09 | Completed | No
WO-26-004944 | 9.8 | Crossroads | CR-S18-02 | Corrective maintenance | P3 within 10 days | 2026-05-13 | 2026-05-22 | 2026-05-26 | Contract line | CT-02 | 1377.13 | Completed | No
WO-26-004945 | 4.4 | Crossroads | CR-S15-01 | Corrective maintenance | P4 planned | 2026-05-13 | 2026-07-02 | 2026-07-10 | Internal line |  | 2271.27 | Completed | No
WO-26-004946 | 0.9 | Crossroads | CR-S20-02 | Meter exchange | P4 planned | 2026-05-13 | 2026-06-26 | 2026-06-27 | Meter technician |  | 146.23 | Completed | No
WO-26-004947 | 1.3 | Crossroads | CR-S28-02 | Meter exchange | P4 planned | 2026-05-13 | 2026-06-19 | 2026-06-23 | Meter technician |  | 154.8 | Completed | No
WO-26-004948 | 0.9 | Crossroads | CR-S30-02 | Meter exchange | P4 planned | 2026-05-13 | 2026-06-08 | 2026-06-16 | Meter technician |  | 125.03 | Completed | No
WO-26-004949 | 1 | Crossroads | CR-S13-04 | Meter exchange | P3 within 10 days | 2026-05-13 | 2026-05-23 | 2026-05-23 | Meter technician |  | 81.21 | Completed | No
WO-26-004950 | 0.6 | Crossroads | CR-S13-05 | Meter exchange | P3 within 10 days | 2026-05-13 | 2026-05-14 | 2026-05-22 | Meter technician |  | 123.38 | Completed | No
WO-26-004951 | 1.2 | Crossroads | CR-S08-03 | Meter exchange | P4 planned | 2026-05-13 | 2026-05-20 | 2026-05-20 | Meter technician |  | 133.51 | Completed | No
WO-26-004952 | 15.3 | Crossroads | CR-S19-02 | New service - small | P4 planned | 2026-05-13 | 2026-05-21 | 2026-05-23 | Contract line | CT-01 | 3469.33 | Completed | No
WO-26-004953 | 10.2 | Crossroads | CR-S23-01 | New service - small | P3 within 10 days | 2026-05-13 | 2026-05-16 | 2026-05-20 | Contract line | CT-02 | 1726.36 | Completed | No
WO-26-004954 | 21.4 | Crossroads | CR-S22-02 | Pole replacement | P4 planned | 2026-05-13 | 2026-07-02 | 2026-07-02 | Contract line | CT-02 | 3049.59 | Completed | No
WO-26-004955 | 16.3 | Crossroads | CR-S09-03 | Pole replacement | P4 planned | 2026-05-13 | 2026-05-21 | 2026-05-25 | Contract line | CT-02 | 1242.01 | Completed | No
WO-26-004956 | 2.7 | Crossroads | CR-S21-01 | Preventive maintenance | P4 planned | 2026-05-13 | 2026-06-18 | 2026-06-19 | Underground crew |  | 304.63 | Completed | No
WO-26-004957 | 3.2 | Crossroads | CR-S07-03 | Preventive maintenance | P4 planned | 2026-05-13 | 2026-06-14 | 2026-06-14 | Underground crew |  | 255.61 | Completed | No
WO-26-004958 | 3.7 | Crossroads | CR-S17-01 | Preventive maintenance | P4 planned | 2026-05-13 | 2026-05-20 | 2026-05-20 | Internal line |  | 141.37 | Completed | No
WO-26-004959 | 2 | Crossroads | CR-S27-01 | Service order - field | P2 same day | 2026-05-13 | 2026-05-13 | 2026-05-13 | Meter technician |  | 3.53 | Completed | No
WO-26-004960 | 1.6 | Crossroads | CR-S12-03 | Service order - field | P3 within 10 days | 2026-05-13 | 2026-05-23 | 2026-05-23 | Meter technician |  | 11.07 | Completed | No
WO-26-004961 | 2.8 | Crossroads |  | Streetlight | P4 planned | 2026-05-13 | 2026-07-03 | 2026-07-05 | Contract line | CT-01 | 418.45 | Completed | No
WO-26-004962 | 1.3 | Crossroads |  | Streetlight | P4 planned | 2026-05-13 | 2026-05-29 | 2026-05-31 | Contract line | CT-02 | 300.58 | Completed | No
WO-26-004963 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-13 | 2026-05-21 | 2026-05-21 | Contract line | CT-01 | 44.8 | Completed | No
WO-26-004964 | 5.9 | Crossroads | CR-S16-03 | Trouble - no power | P1 emergency | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 208.83 | Completed | No
WO-26-004965 | 2.6 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-05-13 | 2026-05-13 | 2026-05-13 | Troubleman |  | 340.66 | Completed | No
WO-26-004966 | 5.4 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-05-13 | 2026-05-14 | 2026-05-14 | Troubleman |  | 182.59 | Completed | No
WO-26-004967 | 1.6 | Crossroads | CR-S14-05 | Trouble - partial or voltage | P3 within 10 days | 2026-05-13 | 2026-05-23 | 2026-05-23 | Troubleman |  | 209.19 | Completed | No
WO-26-004968 | 4.6 | Crossroads | CR-S29-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-13 | 2026-05-15 | 2026-05-19 | Troubleman |  | 224.74 | Completed | No
WO-26-004969 | 8.5 | Bayou | BY-S08-01 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-15 | 2026-05-16 | Internal line |  | 2295.42 | Completed | No
WO-26-004970 | 3.4 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-24 | 2026-05-24 | Internal line |  | 524.87 | Completed | No
WO-26-004971 | 9.6 | Bayou | BY-S07-04 | Corrective maintenance | P4 planned | 2026-05-14 | 2026-07-05 | 2026-07-05 | Internal line |  | 604.58 | Completed | No
WO-26-004972 | 8.3 | Bayou | BY-S20-02 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-24 | 2026-05-26 | Contract line | CT-03 | 550.06 | Completed | No
WO-26-004973 | 1.3 | Bayou | BY-S13-01 | Meter exchange | P4 planned | 2026-05-14 | 2026-07-13 | 2026-07-17 | Meter technician |  | 148.36 | Completed | No
WO-26-004974 | 1.1 | Bayou | BY-S11-01 | Meter exchange | P4 planned | 2026-05-14 | 2026-07-06 | 2026-07-07 | Meter technician |  | 139.4 | Completed | No
WO-26-004975 | 13 | Bayou | BY-S05-01 | New service - small | P4 planned | 2026-05-14 | 2026-07-08 | 2026-07-09 | Contract line | CT-04 | 2267.35 | Completed | No
WO-26-004976 | 5.7 | Bayou | BY-S06-01 | Preventive maintenance | P4 planned | 2026-05-14 | 2026-07-03 | 2026-07-03 | Contract line | CT-03 | 74.39 | Completed | No
WO-26-004977 | 0.9 | Bayou | BY-S27-06 | Service order - field | P3 within 10 days | 2026-05-14 | 2026-05-21 | 2026-05-22 | Meter technician |  | 34.66 | Completed | No
WO-26-004978 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-14 | 2026-05-15 | 2026-05-15 | Internal line |  | 436.49 | Completed | No
WO-26-004979 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-14 | 2026-05-23 | 2026-05-24 | Contract line | CT-04 | 298.52 | Completed | No
WO-26-004980 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-14 | 2026-05-15 | 2026-05-15 | Internal line |  | 102.4 | Completed | No
WO-26-004981 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-14 | 2026-05-23 | 2026-05-23 | Internal line |  | 159.43 | Completed | No
WO-26-004982 | 4.1 | Bayou | BY-S24-05 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 147.2 | Completed | No
WO-26-004983 | 5.8 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 229.65 | Completed | No
WO-26-004984 | 4 | Bayou | BY-S27-03 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 121.27 | Completed | No
WO-26-004985 | 11.4 | Crossroads | CR-S08-06 | Corrective maintenance | P4 planned | 2026-05-14 | 2026-05-23 | 2026-05-23 | Internal line |  | 1440.47 | Completed | No
WO-26-004986 | 4.1 | Crossroads | CR-S03-03 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-17 | 2026-05-17 | Internal line |  | 1239.02 | Completed | No
WO-26-004987 | 7.9 | Crossroads | CR-S08-03 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-19 | 2026-05-21 | Contract line | CT-01 | 163.05 | Completed | No
WO-26-004988 | 6.2 | Crossroads | CR-S29-03 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-24 | 2026-05-25 | Contract line | CT-01 | 1356.23 | Completed | No
WO-26-004989 | 5.1 | Crossroads | CR-S12-03 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-16 | 2026-05-20 | Contract line | CT-01 | 296.22 | Completed | No
WO-26-004990 | 8.4 | Crossroads | CR-S25-01 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-20 | 2026-05-24 | Internal line |  | 936.09 | Completed | No
WO-26-004991 | 8.1 | Crossroads | CR-S30-01 | Corrective maintenance | P3 within 10 days | 2026-05-14 | 2026-05-16 | 2026-05-20 | Underground crew |  | 1653.15 | Completed | No
WO-26-004992 | 0.8 | Crossroads | CR-S07-03 | Meter exchange | P3 within 10 days | 2026-05-14 | 2026-05-19 | 2026-05-19 | Meter technician |  | 114.09 | Completed | No
WO-26-004993 | 1.2 | Crossroads | CR-S01-02 | Meter exchange | P3 within 10 days | 2026-05-14 | 2026-05-24 | 2026-05-25 | Meter technician |  | 118.33 | Completed | No
WO-26-004994 | 1.2 | Crossroads | CR-S02-01 | Meter exchange | P3 within 10 days | 2026-05-14 | 2026-05-18 | 2026-05-18 | Meter technician |  | 111.07 | Completed | No
WO-26-004995 | 15.3 | Crossroads | CR-S09-05 | Pole replacement | P3 within 10 days | 2026-05-14 | 2026-05-22 | 2026-05-22 | Contract line | CT-02 | 1836.03 | Completed | No
WO-26-004996 | 19.7 | Crossroads | CR-S30-06 | Pole replacement | P4 planned | 2026-05-14 | 2026-06-20 | 2026-06-20 | Internal line |  | 1807.13 | Completed | No
WO-26-004997 | 23.9 | Crossroads | CR-S13-06 | Pole replacement | P4 planned | 2026-05-14 | 2026-07-03 | 2026-07-07 | Contract line | CT-01 | 1431.44 | Completed | No
WO-26-004998 | 7.6 | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-05-14 | 2026-06-16 | 2026-06-17 | Underground crew |  | 352.53 | Completed | No
WO-26-004999 | 5.7 | Crossroads | CR-S03-01 | Preventive maintenance | P4 planned | 2026-05-14 | 2026-06-29 | 2026-06-30 | Internal line |  | 426.63 | Completed | No
WO-26-005000 | 1.9 | Crossroads | CR-S16-04 | Service order - field | P3 within 10 days | 2026-05-14 | 2026-05-21 | 2026-05-21 | Meter technician |  | 33.57 | Completed | No
WO-26-005001 | 1.8 | Crossroads | CR-S07-02 | Service order - field | P3 within 10 days | 2026-05-14 | 2026-05-16 | 2026-05-18 | Meter technician |  | 18.27 | Completed | No
WO-26-005002 | 1.1 | Crossroads | CR-S24-04 | Service order - field | P3 within 10 days | 2026-05-14 | 2026-05-15 | 2026-05-15 | Meter technician |  | 31.44 | Completed | No
WO-26-005003 | 0.8 | Crossroads | CR-S30-03 | Service order - field | P2 same day | 2026-05-14 | 2026-05-14 | 2026-05-14 | Meter technician |  | 6.72 | Completed | No
WO-26-005004 | 0.6 | Crossroads | CR-S20-05 | Service order - field | P2 same day | 2026-05-14 | 2026-05-15 | 2026-05-15 | Meter technician |  | 6.15 | Completed | No
WO-26-005005 | 12.4 | Crossroads | CR-S14-02 | Transformer replacement | P2 same day | 2026-05-14 | 2026-05-14 | 2026-05-14 | Internal line |  | 2944.05 | Completed | No
WO-26-005006 | 3.7 | Crossroads | CR-S05-04 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 123.64 | Completed | No
WO-26-005007 | 4.3 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 201.22 | Completed | No
WO-26-005008 | 2.5 | Crossroads | CR-S09-03 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Internal line |  | 164.77 | Completed | No
WO-26-005009 | 5.1 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 316.54 | Completed | No
WO-26-005010 | 5 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 272.89 | Completed | No
WO-26-005011 | 2.9 | Crossroads | CR-S20-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-14 | 2026-05-23 | 2026-05-31 | Internal line |  | 26.55 | Completed | No
WO-26-005012 | 3.5 | Crossroads | CR-S20-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-14 | 2026-05-17 | 2026-05-17 | Troubleman |  | 122.94 | Completed | No
WO-26-005013 | 3.9 | Crossroads | CR-S30-02 | Trouble - partial or voltage | P2 same day | 2026-05-14 | 2026-05-14 | 2026-05-14 | Internal line |  | 144.21 | Completed | No
WO-26-005014 | 2.7 | Crossroads | CR-S16-06 | Trouble - partial or voltage | P2 same day | 2026-05-14 | 2026-05-14 | 2026-05-14 | Troubleman |  | 18.37 | Completed | No
WO-26-005015 | 9.1 | Bayou | BY-S07-04 | Corrective maintenance | P3 within 10 days | 2026-05-15 | 2026-05-25 | 2026-05-25 | Internal line |  | 1489.73 | Completed | No
WO-26-005016 | 8.1 | Bayou | BY-S12-03 | Corrective maintenance | P4 planned | 2026-05-15 | 2026-07-11 | 2026-07-13 | Internal line |  | 2035.82 | Completed | No
WO-26-005017 | 5 | Bayou | BY-S21-01 | Corrective maintenance | P4 planned | 2026-05-15 | 2026-05-22 | 2026-05-23 | Underground crew |  | 663.42 | Completed | No
WO-26-005018 | 6.1 | Bayou | BY-S14-02 | Corrective maintenance | P3 within 10 days | 2026-05-15 | 2026-05-25 | 2026-06-02 | Internal line |  | 1185.32 | Completed | No
WO-26-005019 | 11.6 | Bayou | BY-S29-05 | Corrective maintenance | P3 within 10 days | 2026-05-15 | 2026-05-24 | 2026-05-28 | Underground crew |  | 808.66 | Completed | No
WO-26-005020 | 1.4 | Bayou | BY-S29-01 | Meter exchange | P3 within 10 days | 2026-05-15 | 2026-05-18 | 2026-05-18 | Meter technician |  | 133.82 | Completed | No
WO-26-005021 | 0.7 | Bayou | BY-S08-01 | Meter exchange | P4 planned | 2026-05-15 | 2026-07-03 | 2026-07-11 | Meter technician |  | 179.38 | Completed | No
WO-26-005022 | 0.9 | Bayou | BY-S27-01 | Meter exchange | P3 within 10 days | 2026-05-15 | 2026-05-23 | 2026-05-25 | Meter technician |  | 60.91 | Completed | No
WO-26-005023 | 1.2 | Bayou | BY-S09-04 | Meter exchange | P4 planned | 2026-05-15 | 2026-06-13 | 2026-06-17 | Meter technician |  | 63.57 | Completed | No
WO-26-005024 | 0.6 | Bayou | BY-S19-01 | Meter exchange | P3 within 10 days | 2026-05-15 | 2026-05-18 | 2026-05-18 | Meter technician |  | 144.18 | Completed | No
WO-26-005025 | 1.5 | Bayou | BY-S18-02 | Meter exchange | P4 planned | 2026-05-15 | 2026-07-05 | 2026-07-05 | Meter technician |  | 123.49 | Completed | No
WO-26-005026 | 14.6 | Bayou | BY-S23-05 | New service - small | P4 planned | 2026-05-15 | 2026-07-12 | 2026-07-16 | Contract line | CT-03 | 1897.73 | Completed | No
WO-26-005027 | 11.1 | Bayou | BY-S26-03 | Pole replacement | P4 planned | 2026-05-15 | 2026-06-12 | 2026-06-12 | Contract line | CT-04 | 1755.29 | Completed | No
WO-26-005028 | 6.7 | Bayou | BY-S29-04 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-06-16 | 2026-06-16 | Underground crew |  | 460.41 | Completed | No
WO-26-005029 | 5.8 | Bayou | BY-S03-01 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-06-23 | 2026-06-24 | Internal line |  | 67.21 | Completed | No
WO-26-005030 | 4.9 | Bayou | BY-S21-03 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-06-21 | 2026-06-25 | Underground crew |  | 71.36 | Completed | No
WO-26-005031 | 3.3 | Bayou | BY-S04-03 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-05-28 | 2026-05-28 | Internal line |  | 581.28 | Completed | No
WO-26-005032 | 3.6 | Bayou | BY-S07-05 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-07-06 | 2026-07-06 | Internal line |  | 10.01 | Completed | No
WO-26-005033 | 7.4 | Bayou | BY-S08-01 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-05-28 | 2026-05-28 | Internal line |  | 113.76 | Completed | No
WO-26-005034 | 1.8 | Bayou | BY-S22-01 | Service order - field | P2 same day | 2026-05-15 | 2026-05-16 | 2026-05-16 | Meter technician |  | 27.01 | Completed | No
WO-26-005035 | 1.9 | Bayou | BY-S11-03 | Service order - field | P3 within 10 days | 2026-05-15 | 2026-05-25 | 2026-05-27 | Meter technician |  | 36.89 | Completed | No
WO-26-005036 | 1.2 | Bayou | BY-S03-02 | Service order - field | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Meter technician |  | 26.68 | Completed | No
WO-26-005037 | 0.6 | Bayou | BY-S22-04 | Service order - field | P3 within 10 days | 2026-05-15 | 2026-05-19 | 2026-05-19 | Meter technician |  | 38.6 | Completed | No
WO-26-005038 | 6.6 | Bayou | BY-S18-02 | Transformer replacement | P2 same day | 2026-05-15 | 2026-05-16 | 2026-05-16 | Contract line | CT-04 | 5992.13 | Completed | No
WO-26-005039 | 13 | Bayou | BY-S16-03 | Transformer replacement | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Contract line | CT-03 | 6253.86 | Completed | No
WO-26-005040 | 4.6 | Bayou | BY-S09-02 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 95.03 | Completed | No
WO-26-005041 | 3.4 | Bayou | BY-S02-02 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 247.45 | Completed | No
WO-26-005042 | 3 | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Internal line |  | 309.71 | Completed | No
WO-26-005043 | 5.9 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 334.07 | Completed | No
WO-26-005044 | 2.4 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 246.37 | Completed | No
WO-26-005045 | 2.9 | Bayou | BY-S22-01 | Trouble - partial or voltage | P2 same day | 2026-05-15 | 2026-05-16 | 2026-05-16 | Troubleman |  | 190.39 | Completed | No
WO-26-005046 | 10.3 | Crossroads | CR-S02-04 | Corrective maintenance | P3 within 10 days | 2026-05-15 | 2026-05-23 | 2026-05-23 | Underground crew |  | 1430.41 | Completed | No
WO-26-005047 | 5.8 | Crossroads | CR-S12-03 | Corrective maintenance | P4 planned | 2026-05-15 | 2026-06-10 | 2026-06-11 | Underground crew |  | 1467.9 | Completed | No
WO-26-005048 | 8.7 | Crossroads | CR-S14-02 | Corrective maintenance | P4 planned | 2026-05-15 | 2026-06-28 | 2026-07-02 | Internal line |  | 1893.87 | Completed | No
WO-26-005049 | 0.7 | Crossroads | CR-S17-03 | Meter exchange | P4 planned | 2026-05-15 | 2026-05-26 | 2026-05-27 | Meter technician |  | 131.67 | Completed | No
WO-26-005050 | 0.6 | Crossroads | CR-S05-01 | Meter exchange | P3 within 10 days | 2026-05-15 | 2026-05-25 | 2026-05-26 | Meter technician |  | 165 | Completed | No
WO-26-005051 | 1.4 | Crossroads | CR-S18-04 | Meter exchange | P3 within 10 days | 2026-05-15 | 2026-05-24 | 2026-05-24 | Meter technician |  | 61.28 | Completed | No
WO-26-005052 | 1.3 | Crossroads | CR-S21-02 | Meter exchange | P4 planned | 2026-05-15 | 2026-05-28 | 2026-06-01 | Meter technician |  | 99.13 | Completed | No
WO-26-005053 | 1 | Crossroads | CR-S02-04 | Meter exchange | P3 within 10 days | 2026-05-15 | 2026-05-24 | 2026-05-26 | Meter technician |  | 147.52 | Completed | No
WO-26-005054 | 14.3 | Crossroads | CR-S13-04 | New service - small | P3 within 10 days | 2026-05-15 | 2026-05-22 | 2026-05-23 | Underground crew |  | 2275.6 | Completed | No
WO-26-005055 | 2.3 | Crossroads | CR-S04-06 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-07-04 | 2026-07-12 | Underground crew |  | 489.26 | Completed | No
WO-26-005056 | 4.2 | Crossroads | CR-S14-01 | Preventive maintenance | P4 planned | 2026-05-15 | 2026-05-22 | 2026-05-22 | Internal line |  | 225.38 | Completed | No
WO-26-005057 | 2 | Crossroads | CR-S29-02 | Service order - field | P3 within 10 days | 2026-05-15 | 2026-05-24 | 2026-05-28 | Meter technician |  | 14.6 | Completed | No
WO-26-005058 | 1.8 | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Meter technician |  | 27.48 | Completed | No
WO-26-005059 | 0.9 | Crossroads | CR-S30-04 | Service order - field | P3 within 10 days | 2026-05-15 | 2026-05-20 | 2026-05-20 | Meter technician |  | 9.37 | Completed | No
WO-26-005060 | 1.4 | Crossroads | CR-S08-03 | Service order - field | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Meter technician |  | 38.66 | Completed | No
WO-26-005061 | 1.4 | Crossroads | CR-S21-01 | Service order - field | P3 within 10 days | 2026-05-15 | 2026-05-24 | 2026-05-24 | Meter technician |  | 35.53 | Completed | No
WO-26-005062 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-15 | 2026-05-23 | 2026-05-24 | Contract line | CT-01 | 383.59 | Completed | No
WO-26-005063 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-15 | 2026-05-18 | 2026-05-18 | Contract line | CT-01 | 226.77 | Completed | No
WO-26-005064 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-15 | 2026-05-22 | 2026-05-26 | Internal line |  | 169.35 | Completed | No
WO-26-005065 | 1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-15 | 2026-05-24 | 2026-05-24 | Internal line |  | 59.45 | Completed | No
WO-26-005066 | 8.6 | Crossroads | CR-S05-05 | Transformer replacement | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Contract line | CT-01 | 5416.4 | Completed | No
WO-26-005067 | 13.7 | Crossroads | CR-S18-06 | Transformer replacement | P3 within 10 days | 2026-05-15 | 2026-05-22 | 2026-05-22 | Contract line | CT-01 | 7219.91 | Completed | No
WO-26-005068 | 2.8 | Crossroads | CR-S31-02 | Trouble - no power | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 184.79 | Completed | No
WO-26-005069 | 2.5 | Crossroads | CR-S30-04 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Internal line |  | 22.71 | Completed | No
WO-26-005070 | 4.6 | Crossroads | CR-S03-02 | Trouble - no power | P1 emergency | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 55.2 | Completed | No
WO-26-005071 | 2.1 | Crossroads | CR-S27-02 | Trouble - no power | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 162.62 | Completed | No
WO-26-005072 | 2.7 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P2 same day | 2026-05-15 | 2026-05-16 | 2026-05-16 | Troubleman |  | 5.77 | Completed | No
WO-26-005073 | 3.7 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Internal line |  | 161.95 | Completed | No
WO-26-005074 | 2.3 | Crossroads | CR-S18-04 | Trouble - partial or voltage | P2 same day | 2026-05-15 | 2026-05-15 | 2026-05-15 | Troubleman |  | 28.41 | Completed | No
WO-26-005075 | 3.6 | Crossroads | CR-S04-06 | Trouble - partial or voltage | P2 same day | 2026-05-15 | 2026-05-16 | 2026-05-16 | Troubleman |  | 150.78 | Completed | No
WO-26-005076 | 1.1 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Meter technician |  | 22.67 | Completed | No
WO-26-005077 | 1.1 | Bayou | BY-S18-04 | Service order - field | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Meter technician |  | 35.21 | Completed | No
WO-26-005078 | 6.4 | Bayou | BY-S26-01 | Transformer replacement | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Internal line |  | 8067.97 | Completed | No
WO-26-005079 | 5.2 | Bayou | BY-S13-02 | Trouble - no power | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Internal line |  | 60.6 | Completed | No
WO-26-005080 | 3.4 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 298.57 | Completed | No
WO-26-005081 | 4.1 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 56.32 | Completed | No
WO-26-005082 | 4.7 | Bayou | BY-S15-01 | Trouble - partial or voltage | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 69.05 | Completed | No
WO-26-005083 | 1.6 | Bayou | BY-S16-02 | Trouble - partial or voltage | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 40.14 | Completed | No
WO-26-005084 | 3.5 | Bayou | BY-S05-03 | Trouble - partial or voltage | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 98.27 | Completed | No
WO-26-005085 | 2 | Bayou | BY-S15-02 | Trouble - partial or voltage | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 49.44 | Completed | No
WO-26-005086 | 1 | Crossroads | CR-S26-03 | Service order - field | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Meter technician |  | 27.07 | Completed | No
WO-26-005087 | 0.7 | Crossroads | CR-S14-05 | Service order - field | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Meter technician |  | 22.38 | Completed | No
WO-26-005088 | 1.8 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Meter technician |  | 38.97 | Completed | No
WO-26-005089 | 0.8 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Meter technician |  | 28.44 | Completed | No
WO-26-005090 | 7.2 | Crossroads | CR-S30-02 | Transformer replacement | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Contract line | CT-02 | 4763.84 | Completed | No
WO-26-005091 | 11.7 | Crossroads | CR-S31-03 | Transformer replacement | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Internal line |  | 6130.58 | Completed | No
WO-26-005092 | 3.8 | Crossroads | CR-S23-01 | Trouble - no power | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Troubleman |  | 21.68 | Completed | No
WO-26-005093 | 4.5 | Crossroads | CR-S18-06 | Trouble - no power | P2 same day | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 343.52 | Completed | No
WO-26-005094 | 3.6 | Crossroads | CR-S19-02 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 156.85 | Completed | No
WO-26-005095 | 4.8 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 112.22 | Completed | No
WO-26-005096 | 4.7 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 239.06 | Completed | No
WO-26-005097 | 2.3 | Crossroads | CR-S30-04 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 151.53 | Completed | No
WO-26-005098 | 3.7 | Crossroads | CR-S25-03 | Trouble - no power | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Troubleman |  | 174.06 | Completed | No
WO-26-005099 | 2 | Crossroads | CR-S07-01 | Trouble - no power | P1 emergency | 2026-05-16 | 2026-05-16 | 2026-05-16 | Troubleman |  | 272.48 | Completed | No
WO-26-005100 | 3.2 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-05-16 | 2026-05-17 | 2026-05-17 | Troubleman |  | 73.95 | Completed | No
WO-26-005101 | 8.2 | Bayou | BY-S13-03 | Corrective maintenance | P2 same day | 2026-05-17 | 2026-05-17 | 2026-05-17 | Underground crew |  | 2370.17 | Completed | No
WO-26-005102 | 6.6 | Bayou | BY-S12-03 | Transformer replacement | P2 same day | 2026-05-17 | 2026-05-17 | 2026-05-17 | Contract line | CT-04 | 9841.89 | Completed | No
WO-26-005103 | 10 | Bayou | BY-S21-01 | Transformer replacement | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Contract line | CT-04 | 6632.52 | Completed | No
WO-26-005104 | 10.1 | Bayou | BY-S17-04 | Transformer replacement | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Internal line |  | 9104.45 | Completed | No
WO-26-005105 | 5.6 | Bayou | BY-S29-05 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 331.89 | Completed | No
WO-26-005106 | 3.7 | Bayou | BY-S30-03 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 68.21 | Completed | No
WO-26-005107 | 3.8 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 26.95 | Completed | No
WO-26-005108 | 2.7 | Bayou | BY-S04-03 | Trouble - no power | P2 same day | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 123.34 | Completed | No
WO-26-005109 | 5.3 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 52.13 | Completed | No
WO-26-005110 | 2.6 | Bayou | BY-S27-05 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 53.83 | Completed | No
WO-26-005111 | 5.2 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Internal line |  | 284.23 | Completed | No
WO-26-005112 | 5 | Bayou | BY-S06-03 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 155.38 | Completed | No
WO-26-005113 | 3 | Bayou | BY-S29-05 | Trouble - partial or voltage | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Troubleman |  | 95.88 | Completed | No
WO-26-005114 | 4.6 | Bayou | BY-S26-01 | Trouble - partial or voltage | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Troubleman |  | 89.96 | Completed | No
WO-26-005115 |  | Bayou | BY-S21-03 | Trouble - partial or voltage | P2 same day | 2026-05-17 | 2026-05-18 |  | Troubleman |  |  | Cancelled | No
WO-26-005116 | 0.7 | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-05-17 | 2026-05-17 | 2026-05-17 | Meter technician |  | 18.58 | Completed | No
WO-26-005117 | 1.7 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-05-17 | 2026-05-17 | 2026-05-17 | Meter technician |  | 7.95 | Completed | No
WO-26-005118 | 1.7 | Crossroads | CR-S14-06 | Service order - field | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Meter technician |  | 20.73 | Completed | No
WO-26-005119 | 7.3 | Crossroads | CR-S30-05 | Transformer replacement | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Internal line |  | 11613.72 | Completed | No
WO-26-005120 | 10.6 | Crossroads | CR-S14-03 | Transformer replacement | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Internal line |  | 7438.75 | Completed | No
WO-26-005121 | 12.8 | Crossroads | CR-S19-04 | Transformer replacement | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Internal line |  | 8062.63 | Completed | No
WO-26-005122 | 2.1 | Crossroads | CR-S13-06 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 76.47 | Completed | No
WO-26-005123 | 2.5 | Crossroads | CR-S29-03 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 68.59 | Completed | No
WO-26-005124 | 5.5 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Internal line |  | 136.71 | Completed | No
WO-26-005125 | 5.5 | Crossroads | CR-S26-02 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 249.56 | Completed | No
WO-26-005126 |  | Crossroads | CR-S10-03 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 |  | Internal line |  |  | Cancelled | No
WO-26-005127 | 5.8 | Crossroads | CR-S27-01 | Trouble - no power | P1 emergency | 2026-05-17 | 2026-05-17 | 2026-05-17 | Troubleman |  | 195.47 | Completed | No
WO-26-005128 | 1.7 | Crossroads | CR-S32-05 | Trouble - partial or voltage | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Troubleman |  | 25.4 | Completed | No
WO-26-005129 | 4.9 | Crossroads | CR-S04-06 | Trouble - partial or voltage | P2 same day | 2026-05-17 | 2026-05-18 | 2026-05-18 | Troubleman |  | 138.09 | Completed | No
WO-26-005130 | 3.1 | Bayou | BY-S01-01 | Corrective maintenance | P3 within 10 days | 2026-05-18 | 2026-05-28 | 2026-05-28 | Internal line |  | 1700.99 | Completed | No
WO-26-005131 | 7.1 | Bayou | BY-S13-06 | Corrective maintenance | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Internal line |  | 949.19 | Completed | No
WO-26-005132 | 1.3 | Bayou | BY-S19-04 | Meter exchange | P3 within 10 days | 2026-05-18 | 2026-05-22 | 2026-05-26 | Meter technician |  | 93.33 | Completed | No
WO-26-005133 | 0.6 | Bayou | BY-S01-01 | Meter exchange | P4 planned | 2026-05-18 | 2026-07-16 | 2026-07-16 | Meter technician |  | 78.51 | Completed | No
WO-26-005134 | 0.7 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-05-18 | 2026-05-19 | 2026-05-21 | Meter technician |  | 112.56 | Completed | No
WO-26-005135 | 0.5 | Bayou | BY-S29-01 | Meter exchange | P3 within 10 days | 2026-05-18 | 2026-05-28 | 2026-05-28 | Meter technician |  | 169.18 | Completed | No
WO-26-005136 | 1.4 | Bayou | BY-S29-03 | Meter exchange | P4 planned | 2026-05-18 | 2026-05-30 | 2026-05-30 | Meter technician |  | 126.4 | Completed | No
WO-26-005137 | 8.3 | Bayou | BY-S20-01 | New service - small | P3 within 10 days | 2026-05-18 | 2026-05-19 | 2026-05-27 | Contract line | CT-04 | 1713 | Completed | No
WO-26-005138 | 10.5 | Bayou | BY-S29-02 | New service - small | P4 planned | 2026-05-18 | 2026-06-17 | 2026-06-17 | Underground crew |  | 1339.89 | Completed | No
WO-26-005139 | 22.1 | Bayou | BY-S21-03 | Pole replacement | P3 within 10 days | 2026-05-18 | 2026-05-26 | 2026-05-26 | Contract line | CT-04 | 3415.05 | Completed | No
WO-26-005140 | 16.6 | Bayou | BY-S18-02 | Pole replacement | P4 planned | 2026-05-18 | 2026-06-11 | 2026-06-11 | Contract line | CT-04 | 2866.49 | Completed | No
WO-26-005141 | 3.2 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-05-18 | 2026-06-14 | 2026-06-16 | Contract line | CT-03 | 553.01 | Completed | No
WO-26-005142 | 3.8 | Bayou | BY-S16-02 | Preventive maintenance | P4 planned | 2026-05-18 | 2026-06-26 | 2026-07-04 | Internal line |  | 421.5 | Completed | No
WO-26-005143 | 6.9 | Bayou | BY-S04-01 | Preventive maintenance | P4 planned | 2026-05-18 | 2026-07-16 | 2026-07-16 | Internal line |  | 239.73 | Completed | No
WO-26-005144 | 6 | Bayou | BY-S08-01 | Preventive maintenance | P4 planned | 2026-05-18 | 2026-06-06 | 2026-06-06 | Internal line |  | 86.78 | Completed | No
WO-26-005145 | 0.9 | Bayou | BY-S11-02 | Service order - field | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Meter technician |  | 12.87 | Completed | No
WO-26-005146 | 1.5 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Meter technician |  | 9.38 | Completed | No
WO-26-005147 | 1.4 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Meter technician |  | 24.46 | Completed | No
WO-26-005148 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-18 | 2026-05-19 | 2026-05-20 | Contract line | CT-04 | 72.12 | Completed | No
WO-26-005149 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-18 | 2026-05-20 | 2026-05-20 | Contract line | CT-04 | 176.91 | Completed | No
WO-26-005150 | 2 | Bayou |  | Streetlight | P4 planned | 2026-05-18 | 2026-07-03 | 2026-07-03 | Contract line | CT-04 | 273.74 | Completed | No
WO-26-005151 | 2.3 | Bayou |  | Streetlight | P4 planned | 2026-05-18 | 2026-05-25 | 2026-05-26 | Internal line |  | 98.1 | Completed | No
WO-26-005152 | 10.3 | Bayou | BY-S18-05 | Transformer replacement | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Internal line |  | 5639.63 | Completed | No
WO-26-005153 | 4.3 | Bayou | BY-S04-01 | Trouble - no power | P1 emergency | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 1.15 | Completed | No
WO-26-005154 | 5.3 | Bayou | BY-S13-05 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Troubleman |  | 141.5 | Completed | No
WO-26-005155 | 4.6 | Bayou | BY-S15-03 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Internal line |  | 267.7 | Completed | No
WO-26-005156 | 5.4 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-05-18 | 2026-05-18 | 2026-05-18 | Internal line |  | 178.47 | Completed | No
WO-26-005157 | 2.8 | Bayou | BY-S16-06 | Trouble - partial or voltage | P3 within 10 days | 2026-05-18 | 2026-05-24 | 2026-05-24 | Troubleman |  | 67.51 | Completed | No
WO-26-005158 | 10.8 | Crossroads | CR-S27-04 | Corrective maintenance | P3 within 10 days | 2026-05-18 | 2026-05-26 | 2026-05-30 | Contract line | CT-01 | 2396.36 | Completed | No
WO-26-005159 | 11 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-05-18 | 2026-05-23 | 2026-05-23 | Internal line |  | 251.09 | Completed | No
WO-26-005160 | 6.1 | Crossroads | CR-S14-04 | Corrective maintenance | P3 within 10 days | 2026-05-18 | 2026-05-20 | 2026-05-28 | Underground crew |  | 2328.1 | Completed | No
WO-26-005161 | 1 | Crossroads | CR-S31-01 | Meter exchange | P3 within 10 days | 2026-05-18 | 2026-05-19 | 2026-05-21 | Meter technician |  | 86.26 | Completed | No
WO-26-005162 | 1.2 | Crossroads | CR-S06-03 | Meter exchange | P4 planned | 2026-05-18 | 2026-07-07 | 2026-07-08 | Meter technician |  | 108.69 | Completed | No
WO-26-005163 | 0.8 | Crossroads | CR-S31-02 | Meter exchange | P4 planned | 2026-05-18 | 2026-06-13 | 2026-06-13 | Meter technician |  | 139.63 | Completed | No
WO-26-005164 | 0.5 | Crossroads | CR-S24-01 | Meter exchange | P4 planned | 2026-05-18 | 2026-05-25 | 2026-05-27 | Meter technician |  | 79.5 | Completed | No
WO-26-005165 | 7.2 | Crossroads | CR-S01-03 | New service - small | P4 planned | 2026-05-18 | 2026-07-09 | 2026-07-09 | Contract line | CT-02 | 2796.52 | Completed | No
WO-26-005166 | 8.7 | Crossroads | CR-S02-03 | New service - small | P3 within 10 days | 2026-05-18 | 2026-05-27 | 2026-05-31 | Underground crew |  | 3731.47 | Completed | No
WO-26-005167 | 3.2 | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-05-18 | 2026-06-16 | 2026-06-16 | Contract line | CT-01 | 578.89 | Completed | No
WO-26-005168 | 6.7 | Crossroads | CR-S05-02 | Preventive maintenance | P4 planned | 2026-05-18 | 2026-06-18 | 2026-06-18 | Internal line |  | 202.51 | Completed | No
WO-26-005169 | 1.6 | Crossroads | CR-S10-01 | Service order - field | P3 within 10 days | 2026-05-18 | 2026-05-20 | 2026-05-20 | Meter technician |  | 14.65 | Completed | No
WO-26-005170 | 1.4 | Crossroads | CR-S01-03 | Service order - field | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Meter technician |  | 6.1 | Completed | No
WO-26-005171 | 0.8 | Crossroads | CR-S23-05 | Service order - field | P3 within 10 days | 2026-05-18 | 2026-05-25 | 2026-05-26 | Meter technician |  | 34.42 | Completed | No
WO-26-005172 | 1.1 | Crossroads | CR-S20-03 | Service order - field | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Meter technician |  | 31.37 | Completed | No
WO-26-005173 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-18 | 2026-05-27 | 2026-05-27 | Contract line | CT-02 | 73.97 | Completed | No
WO-26-005174 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-18 | 2026-05-23 | 2026-05-24 | Internal line |  | 265.2 | Completed | No
WO-26-005175 | 13 | Crossroads | CR-S22-03 | Transformer replacement | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Internal line |  | 6742.72 | Completed | No
WO-26-005176 | 9.2 | Crossroads | CR-S21-03 | Transformer replacement | P1 emergency | 2026-05-18 | 2026-05-18 | 2026-05-18 | Contract line | CT-01 | 4768.09 | Completed | No
WO-26-005177 | 5.7 | Crossroads | CR-S07-01 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 113.94 | Completed | No
WO-26-005178 | 3.2 | Crossroads | CR-S04-02 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Troubleman |  | 232.5 | Completed | No
WO-26-005179 | 5.4 | Crossroads | CR-S15-02 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 4.24 | Completed | No
WO-26-005180 | 3.3 | Crossroads | CR-S26-02 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Troubleman |  | 55.08 | Completed | No
WO-26-005181 | 5 | Crossroads | CR-S07-01 | Trouble - no power | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 50.29 | Completed | No
WO-26-005182 | 4.6 | Crossroads | CR-S27-04 | Trouble - partial or voltage | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 5.21 | Completed | No
WO-26-005183 | 1.5 | Crossroads | CR-S28-04 | Trouble - partial or voltage | P2 same day | 2026-05-18 | 2026-05-19 | 2026-05-19 | Troubleman |  | 25.09 | Completed | No
WO-26-005184 | 2.9 | Crossroads | CR-S20-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-18 | 2026-05-24 | 2026-05-24 | Troubleman |  | 45.59 | Completed | No
WO-26-005185 | 4 | Crossroads | CR-S14-05 | Trouble - partial or voltage | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 93.08 | Completed | No
WO-26-005186 | 4 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-18 | 2026-05-28 | 2026-05-28 | Internal line |  | 108.3 | Completed | No
WO-26-005187 | 2 | Crossroads | CR-S23-04 | Trouble - partial or voltage | P2 same day | 2026-05-18 | 2026-05-18 | 2026-05-18 | Troubleman |  | 175.5 | Completed | No
WO-26-005188 | 12.4 | Bayou | BY-S09-01 | Corrective maintenance | P3 within 10 days | 2026-05-19 | 2026-05-24 | 2026-05-24 | Contract line | CT-03 | 1086.95 | Completed | Yes
WO-26-005189 | 0.9 | Bayou | BY-S30-01 | Meter exchange | P3 within 10 days | 2026-05-19 | 2026-05-29 | 2026-05-29 | Meter technician |  | 69.62 | Completed | No
WO-26-005190 | 1.1 | Bayou | BY-S11-01 | Meter exchange | P3 within 10 days | 2026-05-19 | 2026-05-25 | 2026-05-25 | Meter technician |  | 123.12 | Completed | No
WO-26-005191 | 1.3 | Bayou | BY-S11-01 | Meter exchange | P3 within 10 days | 2026-05-19 | 2026-05-24 | 2026-05-24 | Meter technician |  | 157.5 | Completed | No
WO-26-005192 | 0.8 | Bayou | BY-S29-02 | Meter exchange | P4 planned | 2026-05-19 | 2026-05-26 | 2026-05-30 | Meter technician |  | 166.13 | Completed | No
WO-26-005193 | 0.8 | Bayou | BY-S17-04 | Meter exchange | P3 within 10 days | 2026-05-19 | 2026-05-29 | 2026-05-31 | Meter technician |  | 102.99 | Completed | No
WO-26-005194 | 1.2 | Bayou | BY-S04-02 | Meter exchange | P4 planned | 2026-05-19 | 2026-07-14 | 2026-07-14 | Meter technician |  | 129.51 | Completed | No
WO-26-005195 | 14.9 | Bayou | BY-S14-03 | New service - small | P4 planned | 2026-05-19 | 2026-07-02 | 2026-07-03 | Contract line | CT-04 | 3925.97 | Completed | No
WO-26-005196 | 10.3 | Bayou | BY-S07-02 | New service - small | P4 planned | 2026-05-19 | 2026-06-27 | 2026-07-01 | Contract line | CT-03 | 3598.84 | Completed | No
WO-26-005197 | 4.5 | Bayou | BY-S07-06 | New service - small | P3 within 10 days | 2026-05-19 | 2026-05-24 | 2026-05-24 | Contract line | CT-03 | 4008.72 | Completed | No
WO-26-005198 | 23.2 | Bayou | BY-S13-06 | Pole replacement | P3 within 10 days | 2026-05-19 | 2026-05-25 | 2026-05-26 | Internal line |  | 1992.64 | Completed | Yes
WO-26-005199 | 21.3 | Bayou | BY-S06-01 | Pole replacement | P3 within 10 days | 2026-05-19 | 2026-05-25 | 2026-05-25 | Contract line | CT-03 | 2001.08 | Completed | No
WO-26-005200 | 6.1 | Bayou | BY-S16-04 | Preventive maintenance | P4 planned | 2026-05-19 | 2026-06-25 | 2026-06-25 | Contract line | CT-03 | 277.06 | Completed | No
WO-26-005201 | 1.9 | Bayou | BY-S15-06 | Service order - field | P2 same day | 2026-05-19 | 2026-05-19 | 2026-05-19 | Meter technician |  | 9.79 | Completed | No
WO-26-005202 | 1.8 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-05-19 | 2026-05-19 | 2026-05-19 | Meter technician |  | 17.81 | Completed | No
WO-26-005203 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-19 | 2026-05-29 | 2026-05-29 | Internal line |  | 311.97 | Completed | No
WO-26-005204 | 11.9 | Bayou | BY-S19-02 | Transformer replacement | P3 within 10 days | 2026-05-19 | 2026-05-29 | 2026-05-29 | Internal line |  | 11701.12 | Completed | Yes
WO-26-005205 | 6 | Bayou | BY-S25-04 | Trouble - no power | P1 emergency | 2026-05-19 | 2026-05-19 | 2026-05-19 | Troubleman |  | 71.32 | Completed | No
WO-26-005206 | 2.7 | Bayou | BY-S08-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-19 | 2026-05-22 | 2026-05-23 | Troubleman |  | 156.69 | Completed | No
WO-26-005207 | 1.8 | Bayou | BY-S25-05 | Trouble - partial or voltage | P3 within 10 days | 2026-05-19 | 2026-05-24 | 2026-05-24 | Troubleman |  | 212.3 | Completed | No
WO-26-005208 | 6.9 | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-05-19 | 2026-05-23 | 2026-05-25 | Underground crew |  | 2320.17 | Completed | Yes
WO-26-005209 | 9.1 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-05-19 | 2026-05-23 | 2026-05-23 | Internal line |  | 2345.5 | Completed | Yes
WO-26-005210 | 12.1 | Crossroads | CR-S06-01 | Corrective maintenance | P4 planned | 2026-05-19 | 2026-06-05 | 2026-06-06 | Contract line | CT-02 | 1408.2 | Completed | Yes
WO-26-005211 | 0.9 | Crossroads | CR-S01-01 | Meter exchange | P4 planned | 2026-05-19 | 2026-07-04 | 2026-07-04 | Meter technician |  | 79.98 | Completed | No
WO-26-005212 | 0.9 | Crossroads | CR-S19-03 | Meter exchange | P4 planned | 2026-05-19 | 2026-07-07 | 2026-07-07 | Meter technician |  | 111 | Completed | No
WO-26-005213 | 0.6 | Crossroads | CR-S19-03 | Meter exchange | P4 planned | 2026-05-19 | 2026-06-26 | 2026-06-26 | Meter technician |  | 162.95 | Completed | No
WO-26-005214 | 1.4 | Crossroads | CR-S26-02 | Meter exchange | P3 within 10 days | 2026-05-19 | 2026-05-20 | 2026-05-20 | Meter technician |  | 110.35 | Completed | No
WO-26-005215 | 1.4 | Crossroads | CR-S08-05 | Meter exchange | P3 within 10 days | 2026-05-19 | 2026-05-22 | 2026-05-23 | Meter technician |  | 82.6 | Completed | No
WO-26-005216 | 16 | Crossroads | CR-S32-04 | New service - small | P4 planned | 2026-05-19 | 2026-06-14 | 2026-06-14 | Internal line |  | 3248.11 | Completed | No
WO-26-005217 | 19.6 | Crossroads | CR-S09-03 | Pole replacement | P3 within 10 days | 2026-05-19 | 2026-05-21 | 2026-05-23 | Internal line |  | 3120.26 | Completed | Yes
WO-26-005218 | 16 | Crossroads | CR-S08-04 | Pole replacement | P2 same day | 2026-05-19 | 2026-05-19 | 2026-05-19 | Contract line | CT-01 | 2559.04 | Completed | No
WO-26-005219 | 2.9 | Crossroads | CR-S03-02 | Preventive maintenance | P4 planned | 2026-05-19 | 2026-06-17 | 2026-06-18 | Internal line |  | 546.9 | Completed | No
WO-26-005220 | 3.1 | Crossroads | CR-S23-02 | Preventive maintenance | P4 planned | 2026-05-19 | 2026-07-15 | 2026-07-15 | Underground crew |  | 539.97 | Completed | No
WO-26-005221 | 3 | Crossroads | CR-S24-01 | Preventive maintenance | P4 planned | 2026-05-19 | 2026-07-17 | 2026-07-17 | Underground crew |  | 5.6 | Completed | No
WO-26-005222 | 1.4 | Crossroads | CR-S31-02 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-26 | 2026-05-30 | Meter technician |  | 15.3 | Completed | No
WO-26-005223 | 1.9 | Crossroads | CR-S04-03 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-29 | 2026-05-30 | Meter technician |  | 19.54 | Completed | No
WO-26-005224 | 0.9 | Crossroads | CR-S01-03 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-24 | 2026-05-25 | Meter technician |  | 17.85 | Completed | No
WO-26-005225 | 1.8 | Crossroads | CR-S15-02 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-20 | 2026-05-20 | Meter technician |  | 2.11 | Completed | No
WO-26-005226 | 1.3 | Crossroads | CR-S23-05 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-28 | 2026-05-29 | Meter technician |  | 2.22 | Completed | No
WO-26-005227 | 1.3 | Crossroads | CR-S24-03 | Service order - field | P2 same day | 2026-05-19 | 2026-05-19 | 2026-05-19 | Meter technician |  | 17.07 | Completed | No
WO-26-005228 | 1.3 | Crossroads | CR-S13-04 | Service order - field | P2 same day | 2026-05-19 | 2026-05-19 | 2026-05-19 | Meter technician |  | 22.77 | Completed | No
WO-26-005229 | 1.5 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-28 | 2026-05-29 | Meter technician |  | 28.6 | Completed | No
WO-26-005230 | 1 | Crossroads | CR-S10-02 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-26 | 2026-05-30 | Meter technician |  | 8.3 | Completed | No
WO-26-005231 | 1 | Crossroads | CR-S02-03 | Service order - field | P3 within 10 days | 2026-05-19 | 2026-05-22 | 2026-05-22 | Meter technician |  | 4.35 | Completed | No
WO-26-005232 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-19 | 2026-05-27 | 2026-06-04 | Internal line |  | 63.69 | Completed | No
WO-26-005233 | 6 | Crossroads | CR-S09-02 | Trouble - no power | P1 emergency | 2026-05-19 | 2026-05-19 | 2026-05-19 | Troubleman |  | 282.04 | Completed | No
WO-26-005234 | 3.9 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-05-19 | 2026-05-19 | 2026-05-19 | Troubleman |  | 168.91 | Completed | No
WO-26-005235 | 11.1 | Bayou | BY-S07-02 | Corrective maintenance | P3 within 10 days | 2026-05-20 | 2026-05-27 | 2026-05-27 | Internal line |  | 2198.31 | Completed | No
WO-26-005236 | 6.6 | Bayou | BY-S29-02 | Corrective maintenance | P2 same day | 2026-05-20 | 2026-05-21 | 2026-05-21 | Contract line | CT-03 | 217.93 | Completed | No
WO-26-005237 | 4.8 | Bayou | BY-S23-04 | Corrective maintenance | P3 within 10 days | 2026-05-20 | 2026-05-21 | 2026-05-23 | Internal line |  | 1223.2 | Completed | Yes
WO-26-005238 | 13.6 | Bayou | BY-S15-01 | Corrective maintenance | P2 same day | 2026-05-20 | 2026-05-21 | 2026-05-21 | Internal line |  | 1892.27 | Completed | Yes
WO-26-005239 | 9.8 | Bayou | BY-S03-02 | Corrective maintenance | P3 within 10 days | 2026-05-20 | 2026-05-25 | 2026-05-25 | Internal line |  | 2201.6 | Completed | No
WO-26-005240 | 5.5 | Bayou | BY-S21-04 | Corrective maintenance | P4 planned | 2026-05-20 | 2026-06-06 | 2026-06-07 | Underground crew |  | 1804.66 | Completed | Yes
WO-26-005241 | 13 | Bayou | BY-S07-05 | Corrective maintenance | P3 within 10 days | 2026-05-20 | 2026-05-27 | 2026-05-27 | Underground crew |  | 1965.27 | Completed | Yes
WO-26-005242 | 1.2 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-05-20 | 2026-05-30 | 2026-05-30 | Meter technician |  | 137.59 | Completed | No
WO-26-005243 | 0.9 | Bayou | BY-S01-01 | Meter exchange | P3 within 10 days | 2026-05-20 | 2026-05-23 | 2026-05-24 | Meter technician |  | 70.22 | Completed | No
WO-26-005244 | 0.6 | Bayou | BY-S22-04 | Meter exchange | P3 within 10 days | 2026-05-20 | 2026-05-23 | 2026-05-24 | Meter technician |  | 109.37 | Completed | No
WO-26-005245 | 6.7 | Bayou | BY-S27-06 | New service - small | P4 planned | 2026-05-20 | 2026-05-30 | 2026-05-30 | Contract line | CT-04 | 3524.69 | Completed | No
WO-26-005246 | 3.7 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-05-20 | 2026-07-17 | 2026-07-17 | Contract line | CT-03 | 47.56 | Completed | No
WO-26-005247 | 1.9 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-05-20 | 2026-05-21 | 2026-05-21 | Meter technician |  | 34.04 | Completed | No
WO-26-005248 | 0.6 | Bayou | BY-S06-03 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-29 | 2026-05-30 | Meter technician |  | 36.53 | Completed | No
WO-26-005249 | 1.9 | Bayou | BY-S11-02 | Service order - field | P2 same day | 2026-05-20 | 2026-05-20 | 2026-05-20 | Meter technician |  | 0.91 | Completed | No
WO-26-005250 | 0.9 | Bayou | BY-S18-07 | Service order - field | P2 same day | 2026-05-20 | 2026-05-20 | 2026-05-20 | Meter technician |  | 12.69 | Completed | No
WO-26-005251 | 1.1 | Bayou | BY-S16-01 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-28 | 2026-05-28 | Meter technician |  | 15.4 | Completed | No
WO-26-005252 | 1 | Bayou | BY-S10-01 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-27 | 2026-05-27 | Meter technician |  | 19.41 | Completed | No
WO-26-005253 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-20 | 2026-05-22 | 2026-05-30 | Contract line | CT-04 | 284.57 | Completed | No
WO-26-005254 | 12.6 | Bayou | BY-S10-03 | Transformer replacement | P1 emergency | 2026-05-20 | 2026-05-20 | 2026-05-20 | Internal line |  | 11181.93 | Completed | Yes
WO-26-005255 | 3.7 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-05-20 | 2026-05-20 | 2026-05-20 | Troubleman |  | 23.97 | Completed | No
WO-26-005256 | 4.3 | Bayou | BY-S18-03 | Trouble - partial or voltage | P2 same day | 2026-05-20 | 2026-05-20 | 2026-05-20 | Troubleman |  | 247.51 | Completed | No
WO-26-005257 | 5 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-05-20 | 2026-05-21 | 2026-05-21 | Internal line |  | 2191.81 | Completed | No
WO-26-005258 | 6.8 | Crossroads | CR-S32-05 | Corrective maintenance | P2 same day | 2026-05-20 | 2026-05-21 | 2026-05-21 | Internal line |  | 289.82 | Completed | No
WO-26-005259 | 10.7 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-05-20 | 2026-05-26 | 2026-05-26 | Internal line |  | 1032.59 | Completed | Yes
WO-26-005260 | 9.9 | Crossroads | CR-S01-03 | Corrective maintenance | P2 same day | 2026-05-20 | 2026-05-20 | 2026-05-20 | Internal line |  | 1005.37 | Completed | Yes
WO-26-005261 | 4.9 | Crossroads | CR-S13-06 | Corrective maintenance | P3 within 10 days | 2026-05-20 | 2026-05-21 | 2026-05-21 | Internal line |  | 2312.51 | Completed | No
WO-26-005262 | 0.6 | Crossroads | CR-S04-01 | Meter exchange | P3 within 10 days | 2026-05-20 | 2026-05-27 | 2026-05-27 | Meter technician |  | 115.17 | Completed | No
WO-26-005263 | 1.2 | Crossroads | CR-S09-01 | Meter exchange | P4 planned | 2026-05-20 | 2026-07-12 | 2026-07-20 | Meter technician |  | 158.38 | Completed | No
WO-26-005264 | 14.4 | Crossroads | CR-S08-06 | New service - small | P4 planned | 2026-05-20 | 2026-06-14 | 2026-06-14 | Contract line | CT-02 | 2582.65 | Completed | No
WO-26-005265 | 2.2 | Crossroads | CR-S01-04 | Preventive maintenance | P4 planned | 2026-05-20 | 2026-07-14 | 2026-07-15 | Internal line |  | 252.59 | Completed | No
WO-26-005266 | 3.6 | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-05-20 | 2026-06-24 | 2026-06-26 | Underground crew |  | 527.11 | Completed | No
WO-26-005267 | 4.4 | Crossroads | CR-S30-02 | Preventive maintenance | P4 planned | 2026-05-20 | 2026-06-25 | 2026-06-25 | Contract line | CT-01 | 585.38 | Completed | No
WO-26-005268 | 5.3 | Crossroads | CR-S16-04 | Preventive maintenance | P4 planned | 2026-05-20 | 2026-07-14 | 2026-07-14 | Internal line |  | 493.73 | Completed | No
WO-26-005269 | 2 | Crossroads | CR-S18-06 | Preventive maintenance | P4 planned | 2026-05-20 | 2026-06-03 | 2026-06-03 | Underground crew |  | 310.7 | Completed | No
WO-26-005270 | 1.5 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-24 | 2026-06-01 | Meter technician |  | 36.27 | Completed | No
WO-26-005271 | 1.4 | Crossroads | CR-S16-02 | Service order - field | P2 same day | 2026-05-20 | 2026-05-21 | 2026-05-21 | Meter technician |  | 21.81 | Completed | No
WO-26-005272 | 0.7 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-05-20 | 2026-05-20 | 2026-05-20 | Meter technician |  | 18.12 | Completed | No
WO-26-005273 | 1.2 | Crossroads | CR-S07-03 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-29 | 2026-05-29 | Meter technician |  | 17.53 | Completed | No
WO-26-005274 | 1.6 | Crossroads | CR-S27-03 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-24 | 2026-05-24 | Meter technician |  | 14.82 | Completed | No
WO-26-005275 | 1.6 | Crossroads | CR-S18-03 | Service order - field | P3 within 10 days | 2026-05-20 | 2026-05-22 | 2026-05-24 | Meter technician |  | 24.38 | Completed | No
WO-26-005276 | 2.4 | Crossroads |  | Streetlight | P4 planned | 2026-05-20 | 2026-07-06 | 2026-07-07 | Internal line |  | 199.7 | Completed | No
WO-26-005277 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-20 | 2026-05-28 | 2026-05-30 | Contract line | CT-02 | 410.47 | Completed | No
WO-26-005278 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-20 | 2026-05-27 | 2026-05-31 | Contract line | CT-02 | 428.79 | Completed | No
WO-26-005279 | 2 | Crossroads |  | Streetlight | P4 planned | 2026-05-20 | 2026-07-03 | 2026-07-07 | Internal line |  | 185.62 | Completed | No
WO-26-005280 | 6.3 | Crossroads | CR-S09-05 | Transformer replacement | P1 emergency | 2026-05-20 | 2026-05-20 | 2026-05-20 | Contract line | CT-01 | 12287.65 | Completed | No
WO-26-005281 | 7 | Crossroads | CR-S20-01 | Transformer replacement | P1 emergency | 2026-05-20 | 2026-05-20 | 2026-05-20 | Internal line |  | 7962.73 | Completed | No
WO-26-005282 | 14.6 | Crossroads | CR-S14-05 | Transformer replacement | P3 within 10 days | 2026-05-20 | 2026-05-24 | 2026-05-24 | Contract line | CT-01 | 3591.45 | Completed | Yes
WO-26-005283 | 8.2 | Crossroads | CR-S24-03 | Transformer replacement | P1 emergency | 2026-05-20 | 2026-05-20 | 2026-05-20 | Contract line | CT-02 | 4183.34 | Completed | Yes
WO-26-005284 | 15.4 | Crossroads | CR-S20-01 | Transformer replacement | P3 within 10 days | 2026-05-20 | 2026-05-27 | 2026-05-27 | Contract line | CT-02 | 3571.59 | Completed | Yes
WO-26-005285 | 4.5 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-05-20 | 2026-05-20 | 2026-05-20 | Troubleman |  | 314.76 | Completed | No
WO-26-005286 | 2.9 | Crossroads | CR-S06-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-20 | 2026-05-29 | 2026-05-29 | Troubleman |  | 23.48 | Completed | No
WO-26-005287 | 9.5 | Bayou | BY-S15-03 | Corrective maintenance | P3 within 10 days | 2026-05-21 | 2026-05-27 | 2026-05-27 | Contract line | CT-03 | 1680.62 | Completed | No
WO-26-005288 | 4 | Bayou | BY-S11-03 | Corrective maintenance | P4 planned | 2026-05-21 | 2026-07-09 | 2026-07-09 | Underground crew |  | 1211.37 | Completed | Yes
WO-26-005289 | 1.2 | Bayou | BY-S14-02 | Meter exchange | P3 within 10 days | 2026-05-21 | 2026-05-28 | 2026-05-28 | Meter technician |  | 152.91 | Completed | No
WO-26-005290 | 0.7 | Bayou | BY-S03-01 | Meter exchange | P3 within 10 days | 2026-05-21 | 2026-05-27 | 2026-05-27 | Meter technician |  | 166.39 | Completed | No
WO-26-005291 | 0.6 | Bayou | BY-S24-03 | Meter exchange | P3 within 10 days | 2026-05-21 | 2026-05-22 | 2026-05-24 | Meter technician |  | 104.3 | Completed | No
WO-26-005292 | 1.5 | Bayou | BY-S25-03 | Meter exchange | P3 within 10 days | 2026-05-21 | 2026-05-25 | 2026-05-25 | Meter technician |  | 85.57 | Completed | No
WO-26-005293 | 16.5 | Bayou | BY-S07-05 | Pole replacement | P3 within 10 days | 2026-05-21 | 2026-05-30 | 2026-05-30 | Internal line |  | 1851.61 | Completed | No
WO-26-005294 | 29.7 | Bayou | BY-S18-02 | Pole replacement | P2 same day | 2026-05-21 | 2026-05-22 | 2026-05-22 | Internal line |  | 2170.32 | Completed | Yes
WO-26-005295 | 4.3 | Bayou | BY-S04-02 | Preventive maintenance | P4 planned | 2026-05-21 | 2026-06-12 | 2026-06-12 | Internal line |  | 177.25 | Completed | No
WO-26-005296 | 3.3 | Bayou | BY-S27-06 | Preventive maintenance | P4 planned | 2026-05-21 | 2026-07-15 | 2026-07-19 | Underground crew |  | 211.19 | Completed | No
WO-26-005297 | 0.9 | Bayou | BY-S27-02 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-24 | 2026-05-25 | Meter technician |  | 2.44 | Completed | No
WO-26-005298 | 1.3 | Bayou | BY-S18-02 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-24 | 2026-05-24 | Meter technician |  | 9.18 | Completed | No
WO-26-005299 | 0.7 | Bayou | BY-S13-06 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-27 | 2026-05-28 | Meter technician |  | 19.36 | Completed | No
WO-26-005300 | 1.2 | Bayou | BY-S25-02 | Service order - field | P2 same day | 2026-05-21 | 2026-05-21 | 2026-05-21 | Meter technician |  | 14.37 | Completed | No
WO-26-005301 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-21 | 2026-05-23 | 2026-05-23 | Contract line | CT-03 | 284.25 | Completed | No
WO-26-005302 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-21 | 2026-05-23 | 2026-05-23 | Contract line | CT-04 | 446.94 | Completed | No
WO-26-005303 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-21 | 2026-05-28 | 2026-05-28 | Internal line |  | 432.73 | Completed | No
WO-26-005304 | 8.8 | Bayou | BY-S30-01 | Transformer replacement | P1 emergency | 2026-05-21 | 2026-05-21 | 2026-05-21 | Internal line |  | 11307.19 | Completed | No
WO-26-005305 | 10.5 | Bayou | BY-S29-04 | Transformer replacement | P1 emergency | 2026-05-21 | 2026-05-21 | 2026-05-21 | Internal line |  | 7535.4 | Completed | No
WO-26-005306 | 2.7 | Bayou | BY-S24-03 | Trouble - partial or voltage | P2 same day | 2026-05-21 | 2026-05-22 | 2026-05-22 | Troubleman |  | 156.55 | Completed | No
WO-26-005307 | 7 | Crossroads | CR-S26-02 | Corrective maintenance | P3 within 10 days | 2026-05-21 | 2026-05-23 | 2026-05-23 | Internal line |  | 2004.48 | Completed | No
WO-26-005308 | 5.1 | Crossroads | CR-S28-02 | Corrective maintenance | P3 within 10 days | 2026-05-21 | 2026-05-23 | 2026-05-23 | Contract line | CT-02 | 1149.86 | Completed | No
WO-26-005309 | 15.6 | Crossroads | CR-S08-04 | Corrective maintenance | P4 planned | 2026-05-21 | 2026-06-03 | 2026-06-04 | Internal line |  | 426.59 | Completed | Yes
WO-26-005310 | 9.6 | Crossroads | CR-S30-01 | Corrective maintenance | P4 planned | 2026-05-21 | 2026-06-18 | 2026-06-22 | Underground crew |  | 1550.8 | Completed | No
WO-26-005311 | 0.9 | Crossroads | CR-S29-01 | Meter exchange | P4 planned | 2026-05-21 | 2026-05-29 | 2026-05-29 | Meter technician |  | 61.69 | Completed | No
WO-26-005312 | 0.7 | Crossroads | CR-S08-06 | Meter exchange | P3 within 10 days | 2026-05-21 | 2026-05-23 | 2026-05-23 | Meter technician |  | 137.67 | Completed | No
WO-26-005313 | 0.8 | Crossroads | CR-S20-02 | Meter exchange | P4 planned | 2026-05-21 | 2026-06-23 | 2026-06-27 | Meter technician |  | 88.07 | Completed | No
WO-26-005314 | 20.9 | Crossroads | CR-S05-02 | Pole replacement | P3 within 10 days | 2026-05-21 | 2026-05-30 | 2026-05-30 | Internal line |  | 1657.01 | Completed | Yes
WO-26-005315 | 7.1 | Crossroads | CR-S11-02 | Preventive maintenance | P4 planned | 2026-05-21 | 2026-05-31 | 2026-06-04 | Underground crew |  | 500.25 | Completed | No
WO-26-005316 | 1.4 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-29 | 2026-06-06 | Meter technician |  | 5.83 | Completed | No
WO-26-005317 | 0.7 | Crossroads | CR-S07-07 | Service order - field | P2 same day | 2026-05-21 | 2026-05-21 | 2026-05-21 | Meter technician |  | 2.37 | Completed | No
WO-26-005318 | 1.6 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-05-21 | 2026-05-22 | 2026-05-22 | Meter technician |  | 18.55 | Completed | No
WO-26-005319 | 1.7 | Crossroads | CR-S11-02 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-31 | 2026-05-31 | Meter technician |  | 24 | Completed | No
WO-26-005320 | 1.7 | Crossroads | CR-S08-06 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-27 | 2026-05-28 | Meter technician |  | 26.88 | Completed | No
WO-26-005321 | 1.4 | Crossroads | CR-S07-05 | Service order - field | P2 same day | 2026-05-21 | 2026-05-21 | 2026-05-21 | Meter technician |  | 32.4 | Completed | No
WO-26-005322 | 2 | Crossroads | CR-S12-01 | Service order - field | P2 same day | 2026-05-21 | 2026-05-21 | 2026-05-21 | Meter technician |  | 23.96 | Completed | No
WO-26-005323 | 1.9 | Crossroads | CR-S05-02 | Service order - field | P2 same day | 2026-05-21 | 2026-05-22 | 2026-05-22 | Meter technician |  | 3.07 | Completed | No
WO-26-005324 | 0.9 | Crossroads | CR-S16-04 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-31 | 2026-06-02 | Meter technician |  | 22.48 | Completed | No
WO-26-005325 | 1.8 | Crossroads | CR-S03-01 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-27 | 2026-05-31 | Meter technician |  | 38.82 | Completed | No
WO-26-005326 | 1.3 | Crossroads | CR-S03-01 | Service order - field | P3 within 10 days | 2026-05-21 | 2026-05-24 | 2026-05-24 | Meter technician |  | 16.16 | Completed | No
WO-26-005327 | 8 | Crossroads | CR-S01-03 | Transformer replacement | P1 emergency | 2026-05-21 | 2026-05-21 | 2026-05-21 | Contract line | CT-02 | 8528.28 | Completed | No
WO-26-005328 | 9.3 | Crossroads | CR-S14-02 | Transformer replacement | P1 emergency | 2026-05-21 | 2026-05-21 | 2026-05-21 | Internal line |  | 12247.54 | Completed | No
WO-26-005329 | 9.9 | Crossroads | CR-S04-06 | Transformer replacement | P3 within 10 days | 2026-05-21 | 2026-05-25 | 2026-05-25 | Internal line |  | 3194.67 | Completed | Yes
WO-26-005330 | 4.7 | Crossroads | CR-S23-04 | Trouble - partial or voltage | P2 same day | 2026-05-21 | 2026-05-21 | 2026-05-21 | Troubleman |  | 69.14 | Completed | No
WO-26-005331 | 4.4 | Bayou | BY-S30-01 | Corrective maintenance | P2 same day | 2026-05-22 | 2026-05-23 | 2026-05-23 | Internal line |  | 1550.29 | Completed | Yes
WO-26-005332 | 10 | Bayou | BY-S28-03 | Corrective maintenance | P4 planned | 2026-05-22 | 2026-06-14 | 2026-06-14 | Internal line |  | 807.75 | Completed | No
WO-26-005333 | 10 | Bayou | BY-S29-01 | Corrective maintenance | P3 within 10 days | 2026-05-22 | 2026-05-28 | 2026-06-01 | Internal line |  | 2370.03 | Completed | Yes
WO-26-005334 | 7 | Bayou | BY-S06-02 | Corrective maintenance | P3 within 10 days | 2026-05-22 | 2026-05-25 | 2026-06-02 | Internal line |  | 560.75 | Completed | Yes
WO-26-005335 | 5 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-05-22 | 2026-05-29 | 2026-06-06 | Underground crew |  | 2282.9 | Completed | Yes
WO-26-005336 | 5.3 | Bayou | BY-S21-02 | Corrective maintenance | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Internal line |  | 1037.94 | Completed | Yes
WO-26-005337 | 5.6 | Bayou | BY-S26-05 | Corrective maintenance | P2 same day | 2026-05-22 | 2026-05-23 | 2026-05-23 | Internal line |  | 1272.29 | Completed | Yes
WO-26-005338 | 8.1 | Bayou | BY-S23-01 | Corrective maintenance | P2 same day | 2026-05-22 | 2026-05-23 | 2026-05-23 | Underground crew |  | 1857.5 | Completed | Yes
WO-26-005339 | 14.7 | Bayou | BY-S06-02 | Corrective maintenance | P3 within 10 days | 2026-05-22 | 2026-06-01 | 2026-06-01 | Internal line |  | 1822.8 | Completed | Yes
WO-26-005340 | 1.4 | Bayou | BY-S09-01 | Meter exchange | P3 within 10 days | 2026-05-22 | 2026-06-01 | 2026-06-01 | Meter technician |  | 145.8 | Completed | No
WO-26-005341 | 1 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-05-22 | 2026-05-28 | 2026-06-01 | Meter technician |  | 133.59 | Completed | No
WO-26-005342 | 1.1 | Bayou | BY-S10-01 | Meter exchange | P4 planned | 2026-05-22 | 2026-06-09 | 2026-06-13 | Meter technician |  | 70.94 | Completed | No
WO-26-005343 | 1 | Bayou | BY-S29-04 | Meter exchange | P4 planned | 2026-05-22 | 2026-07-03 | 2026-07-03 | Meter technician |  | 95.6 | Completed | No
WO-26-005344 | 15.9 | Bayou | BY-S08-03 | Pole replacement | P4 planned | 2026-05-22 | 2026-07-08 | 2026-07-16 | Internal line |  | 3148.22 | Completed | No
WO-26-005345 | 6.7 | Bayou | BY-S06-02 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-06-08 | 2026-06-09 | Internal line |  | 262.24 | Completed | No
WO-26-005346 |  | Bayou | BY-S23-05 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-07-14 |  | Internal line |  |  | Cancelled | No
WO-26-005347 | 2.9 | Bayou | BY-S16-05 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-06-19 | 2026-06-23 | Contract line | CT-04 | 483.26 | Completed | No
WO-26-005348 | 6.1 | Bayou | BY-S25-05 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-07-14 | 2026-07-14 | Underground crew |  | 404.45 | Completed | No
WO-26-005349 | 3.6 | Bayou | BY-S30-01 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-05-30 | 2026-05-31 | Underground crew |  | 597.73 | Completed | No
WO-26-005350 | 0.6 | Bayou | BY-S07-05 | Service order - field | P2 same day | 2026-05-22 | 2026-05-23 | 2026-05-23 | Meter technician |  | 14.52 | Completed | No
WO-26-005351 | 1.1 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Meter technician |  | 14.04 | Completed | No
WO-26-005352 | 1.6 | Bayou | BY-S30-02 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-31 | 2026-05-31 | Meter technician |  | 18.63 | Completed | No
WO-26-005353 | 1.3 | Bayou | BY-S22-04 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-23 | 2026-05-31 | Meter technician |  | 15.5 | Completed | No
WO-26-005354 | 1.7 | Bayou | BY-S25-01 | Service order - field | P2 same day | 2026-05-22 | 2026-05-23 | 2026-05-23 | Meter technician |  | 37.66 | Completed | No
WO-26-005355 | 1.4 | Bayou | BY-S23-04 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-31 | 2026-05-31 | Meter technician |  | 12.2 | Completed | No
WO-26-005356 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-22 | 2026-05-27 | 2026-05-29 | Internal line |  | 234.85 | Completed | No
WO-26-005357 | 5 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-05-22 | 2026-05-22 | 2026-05-22 | Troubleman |  | 228.06 | Completed | No
WO-26-005358 | 5.4 | Crossroads | CR-S14-04 | Corrective maintenance | P2 same day | 2026-05-22 | 2026-05-23 | 2026-05-23 | Internal line |  | 773.09 | Completed | No
WO-26-005359 | 14.7 | Crossroads | CR-S25-06 | Corrective maintenance | P4 planned | 2026-05-22 | 2026-06-20 | 2026-06-21 | Underground crew |  | 1735.83 | Completed | Yes
WO-26-005360 | 5.3 | Crossroads | CR-S32-05 | Corrective maintenance | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Underground crew |  | 1154.5 | Completed | Yes
WO-26-005361 | 0.5 | Crossroads | CR-S32-04 | Meter exchange | P3 within 10 days | 2026-05-22 | 2026-05-23 | 2026-05-23 | Meter technician |  | 97.91 | Completed | No
WO-26-005362 | 1.2 | Crossroads | CR-S20-05 | Meter exchange | P3 within 10 days | 2026-05-22 | 2026-05-30 | 2026-06-01 | Meter technician |  | 158.44 | Completed | No
WO-26-005363 | 1.2 | Crossroads | CR-S14-01 | Meter exchange | P4 planned | 2026-05-22 | 2026-06-18 | 2026-06-18 | Meter technician |  | 60.42 | Completed | No
WO-26-005364 | 13.5 | Crossroads | CR-S12-01 | New service - small | P4 planned | 2026-05-22 | 2026-06-05 | 2026-06-05 | Internal line |  | 3925.11 | Completed | No
WO-26-005365 | 18.7 | Crossroads | CR-S28-04 | Pole replacement | P4 planned | 2026-05-22 | 2026-06-14 | 2026-06-16 | Internal line |  | 2837.25 | Completed | Yes
WO-26-005366 | 19.4 | Crossroads | CR-S15-02 | Pole replacement | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Contract line | CT-01 | 2557.73 | Completed | Yes
WO-26-005367 | 4.6 | Crossroads | CR-S25-02 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-06-25 | 2026-06-25 | Internal line |  | 519.29 | Completed | No
WO-26-005368 | 3.4 | Crossroads | CR-S16-06 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-06-23 | 2026-07-01 | Internal line |  | 210.67 | Completed | No
WO-26-005369 | 3.9 | Crossroads | CR-S04-02 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-06-28 | 2026-06-28 | Internal line |  | 476.13 | Completed | No
WO-26-005370 | 5.5 | Crossroads | CR-S19-04 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-07-04 | 2026-07-06 | Internal line |  | 94.32 | Completed | No
WO-26-005371 | 4.1 | Crossroads | CR-S27-04 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-07-07 | 2026-07-08 | Internal line |  | 561.01 | Completed | No
WO-26-005372 | 7.9 | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-06-02 | 2026-06-03 | Internal line |  | 61.39 | Completed | No
WO-26-005373 | 5.4 | Crossroads | CR-S13-04 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-07-19 | 2026-07-19 | Internal line |  | 364.73 | Completed | No
WO-26-005374 | 4.2 | Crossroads | CR-S26-03 | Preventive maintenance | P4 planned | 2026-05-22 | 2026-07-19 | 2026-07-20 | Internal line |  | 235.26 | Completed | No
WO-26-005375 | 1.8 | Crossroads | CR-S02-01 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-31 | 2026-05-31 | Meter technician |  | 14.92 | Completed | No
WO-26-005376 | 1.8 | Crossroads | CR-S30-02 | Service order - field | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Meter technician |  | 13.05 | Completed | No
WO-26-005377 | 1.1 | Crossroads | CR-S14-05 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-24 | 2026-05-24 | Meter technician |  | 6.71 | Completed | No
WO-26-005378 | 1.1 | Crossroads | CR-S15-01 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-26 | 2026-05-26 | Meter technician |  | 34.71 | Completed | No
WO-26-005379 | 1.7 | Crossroads | CR-S20-01 | Service order - field | P3 within 10 days | 2026-05-22 | 2026-05-28 | 2026-05-29 | Meter technician |  | 24.46 | Completed | No
WO-26-005380 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-22 | 2026-05-30 | 2026-05-30 | Internal line |  | 109.83 | Completed | No
WO-26-005381 | 2.3 | Crossroads |  | Streetlight | P4 planned | 2026-05-22 | 2026-05-31 | 2026-05-31 | Internal line |  | 388.19 | Completed | No
WO-26-005382 | 1.3 | Crossroads |  | Streetlight | P4 planned | 2026-05-22 | 2026-06-22 | 2026-06-22 | Contract line | CT-01 | 45.9 | Completed | No
WO-26-005383 | 13.2 | Crossroads | CR-S01-04 | Transformer replacement | P1 emergency | 2026-05-22 | 2026-05-22 | 2026-05-22 | Internal line |  | 8869.2 | Completed | Yes
WO-26-005384 | 3.7 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Troubleman |  | 212.42 | Completed | No
WO-26-005385 | 3.1 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P2 same day | 2026-05-22 | 2026-05-22 | 2026-05-22 | Troubleman |  | 193.91 | Completed | No
WO-26-005386 | 1.4 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-05-23 | 2026-05-24 | 2026-05-24 | Meter technician |  | 26.72 | Completed | No
WO-26-005387 | 1.6 | Bayou | BY-S07-02 | Service order - field | P2 same day | 2026-05-23 | 2026-05-24 | 2026-05-24 | Meter technician |  | 13.62 | Completed | No
WO-26-005388 | 11.7 | Bayou | BY-S15-02 | Transformer replacement | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Internal line |  | 8174.14 | Completed | Yes
WO-26-005389 | 10.4 | Bayou | BY-S10-05 | Transformer replacement | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Contract line | CT-04 | 12174.65 | Completed | Yes
WO-26-005390 | 5.7 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Internal line |  | 48.29 | Completed | No
WO-26-005391 | 5.7 | Bayou | BY-S29-05 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Internal line |  | 347.18 | Completed | No
WO-26-005392 | 4.9 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Internal line |  | 41.22 | Completed | No
WO-26-005393 | 3.5 | Bayou | BY-S23-05 | Trouble - partial or voltage | P2 same day | 2026-05-23 | 2026-05-24 | 2026-05-24 | Troubleman |  | 159.79 | Completed | No
WO-26-005394 | 10.7 | Crossroads | CR-S19-02 | Corrective maintenance | P2 same day | 2026-05-23 | 2026-05-24 | 2026-05-24 | Internal line |  | 1016.16 | Completed | No
WO-26-005395 |  | Crossroads | CR-S25-03 | Pole replacement | P2 same day | 2026-05-23 | 2026-05-24 |  | Contract line | CT-01 |  | Cancelled | Yes
WO-26-005396 | 21.6 | Crossroads | CR-S11-01 | Pole replacement | P2 same day | 2026-05-23 | 2026-05-24 | 2026-05-24 | Contract line | CT-02 | 1284.33 | Completed | Yes
WO-26-005397 | 1.3 | Crossroads | CR-S08-02 | Service order - field | P2 same day | 2026-05-23 | 2026-05-23 | 2026-05-23 | Meter technician |  | 16.12 | Completed | No
WO-26-005398 | 5.7 | Crossroads | CR-S32-05 | Trouble - no power | P2 same day | 2026-05-23 | 2026-05-24 | 2026-05-24 | Troubleman |  | 237.71 | Completed | No
WO-26-005399 | 3.1 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Troubleman |  | 207.91 | Completed | No
WO-26-005400 | 2.9 | Crossroads | CR-S12-02 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Troubleman |  | 43.48 | Completed | No
WO-26-005401 | 3 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Troubleman |  | 253.66 | Completed | No
WO-26-005402 | 2.2 | Crossroads | CR-S32-05 | Trouble - no power | P1 emergency | 2026-05-23 | 2026-05-23 | 2026-05-23 | Troubleman |  | 23.95 | Completed | No
WO-26-005403 | 7.3 | Bayou | BY-S16-01 | Corrective maintenance | P2 same day | 2026-05-24 | 2026-05-25 | 2026-05-25 | Contract line | CT-03 | 150.99 | Completed | Yes
WO-26-005404 | 1.3 | Bayou | BY-S18-04 | Service order - field | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Meter technician |  | 23.8 | Completed | No
WO-26-005405 | 1.4 | Bayou | BY-S09-01 | Service order - field | P2 same day | 2026-05-24 | 2026-05-25 | 2026-05-25 | Meter technician |  | 28.36 | Completed | No
WO-26-005406 | 1.2 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-05-24 | 2026-05-25 | 2026-05-25 | Meter technician |  | 32.73 | Completed | No
WO-26-005407 | 10.4 | Bayou | BY-S29-03 | Transformer replacement | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Contract line | CT-04 | 9652.96 | Completed | Yes
WO-26-005408 |  | Bayou | BY-S25-04 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 |  | Troubleman |  |  | Cancelled | No
WO-26-005409 | 4.3 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 279.6 | Completed | No
WO-26-005410 | 2.7 | Bayou | BY-S18-01 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 215.04 | Completed | No
WO-26-005411 | 3.1 | Bayou | BY-S17-04 | Trouble - no power | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 69.89 | Completed | No
WO-26-005412 | 3.7 | Bayou | BY-S01-01 | Trouble - no power | P2 same day | 2026-05-24 | 2026-05-25 | 2026-05-25 | Troubleman |  | 280.57 | Completed | No
WO-26-005413 | 4 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Internal line |  | 194.63 | Completed | No
WO-26-005414 | 2.9 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 165.67 | Completed | No
WO-26-005415 | 5.7 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 235.24 | Completed | No
WO-26-005416 | 1.6 | Crossroads | CR-S30-07 | Service order - field | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Meter technician |  | 12.63 | Completed | No
WO-26-005417 | 1 | Crossroads | CR-S16-03 | Service order - field | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Meter technician |  | 19.03 | Completed | No
WO-26-005418 | 3.1 | Crossroads | CR-S02-01 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 233 | Completed | No
WO-26-005419 | 4.4 | Crossroads | CR-S19-01 | Trouble - no power | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Internal line |  | 313.1 | Completed | No
WO-26-005420 | 4.6 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 166.82 | Completed | No
WO-26-005421 | 2.7 | Crossroads | CR-S07-06 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 125.68 | Completed | No
WO-26-005422 | 6 | Crossroads | CR-S23-05 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Internal line |  | 186.44 | Completed | No
WO-26-005423 | 2.9 | Crossroads | CR-S25-02 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 261.88 | Completed | No
WO-26-005424 | 3 | Crossroads | CR-S09-02 | Trouble - no power | P1 emergency | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 63.06 | Completed | No
WO-26-005425 | 4.4 | Crossroads | CR-S29-03 | Trouble - partial or voltage | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 207.9 | Completed | No
WO-26-005426 | 3.4 | Crossroads | CR-S06-02 | Trouble - partial or voltage | P2 same day | 2026-05-24 | 2026-05-24 | 2026-05-24 | Troubleman |  | 191.06 | Completed | No
WO-26-005427 | 4.3 | Crossroads | CR-S27-03 | Trouble - partial or voltage | P2 same day | 2026-05-24 | 2026-05-25 | 2026-05-25 | Troubleman |  | 20.86 | Completed | No
WO-26-005428 | 6.4 | Bayou | BY-S30-03 | Corrective maintenance | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Internal line |  | 1468.97 | Completed | Yes
WO-26-005429 | 7.6 | Bayou | BY-S20-01 | Corrective maintenance | P3 within 10 days | 2026-05-25 | 2026-06-03 | 2026-06-03 | Contract line | CT-03 | 918.73 | Completed | No
WO-26-005430 | 7 | Bayou | BY-S27-06 | Corrective maintenance | P3 within 10 days | 2026-05-25 | 2026-05-31 | 2026-06-02 | Contract line | CT-03 | 1351.33 | Completed | No
WO-26-005431 | 5.4 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-05-25 | 2026-05-31 | 2026-06-01 | Underground crew |  | 301.97 | Completed | No
WO-26-005432 | 8.7 | Bayou | BY-S24-04 | Corrective maintenance | P3 within 10 days | 2026-05-25 | 2026-05-29 | 2026-05-29 | Internal line |  | 335.33 | Completed | Yes
WO-26-005433 | 1.4 | Bayou | BY-S16-02 | Meter exchange | P4 planned | 2026-05-25 | 2026-06-15 | 2026-06-15 | Meter technician |  | 128.28 | Completed | No
WO-26-005434 | 0.8 | Bayou | BY-S29-02 | Meter exchange | P4 planned | 2026-05-25 | 2026-07-18 | 2026-07-18 | Meter technician |  | 140.71 | Completed | No
WO-26-005435 | 1.3 | Bayou | BY-S12-02 | Meter exchange | P3 within 10 days | 2026-05-25 | 2026-05-31 | 2026-05-31 | Meter technician |  | 92.26 | Completed | No
WO-26-005436 | 1.2 | Bayou | BY-S16-05 | Meter exchange | P4 planned | 2026-05-25 | 2026-07-06 | 2026-07-06 | Meter technician |  | 111.07 | Completed | No
WO-26-005437 | 1 | Bayou | BY-S20-02 | Meter exchange | P3 within 10 days | 2026-05-25 | 2026-06-03 | 2026-06-03 | Meter technician |  | 91.55 | Completed | No
WO-26-005438 | 1.3 | Bayou | BY-S18-05 | Meter exchange | P4 planned | 2026-05-25 | 2026-06-20 | 2026-06-20 | Meter technician |  | 79.84 | Completed | No
WO-26-005439 | 6.9 | Bayou | BY-S17-04 | New service - small | P4 planned | 2026-05-25 | 2026-07-03 | 2026-07-03 | Internal line |  | 2483.98 | Completed | No
WO-26-005440 | 16 | Bayou | BY-S10-03 | New service - small | P3 within 10 days | 2026-05-25 | 2026-05-29 | 2026-05-29 | Contract line | CT-03 | 372.29 | Completed | No
WO-26-005441 | 21.5 | Bayou | BY-S24-03 | Pole replacement | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Contract line | CT-04 | 2213.51 | Completed | No
WO-26-005442 | 29 | Bayou | BY-S23-02 | Pole replacement | P3 within 10 days | 2026-05-25 | 2026-06-02 | 2026-06-02 | Internal line |  | 2303.99 | Completed | Yes
WO-26-005443 | 15.1 | Bayou | BY-S27-05 | Pole replacement | P4 planned | 2026-05-25 | 2026-07-05 | 2026-07-09 | Internal line |  | 1370.27 | Completed | Yes
WO-26-005444 | 7 | Bayou | BY-S25-04 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-06-03 | 2026-06-03 | Underground crew |  | 264.21 | Completed | No
WO-26-005445 | 6.2 | Bayou | BY-S10-01 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-06-29 | 2026-06-29 | Contract line | CT-04 | 279.45 | Completed | No
WO-26-005446 | 3.1 | Bayou | BY-S27-02 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-07-03 | 2026-07-07 | Internal line |  | 287.27 | Completed | No
WO-26-005447 | 6.8 | Bayou | BY-S25-01 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-06-14 | 2026-06-15 | Internal line |  | 130.73 | Completed | No
WO-26-005448 | 7.1 | Bayou | BY-S27-03 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-07-12 | 2026-07-12 | Contract line | CT-04 | 509.21 | Completed | No
WO-26-005449 | 0.6 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Meter technician |  | 38.01 | Completed | No
WO-26-005450 | 1.9 | Bayou | BY-S02-02 | Service order - field | P3 within 10 days | 2026-05-25 | 2026-05-26 | 2026-05-26 | Meter technician |  | 36.17 | Completed | No
WO-26-005451 | 0.9 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-05-25 | 2026-06-04 | 2026-06-05 | Meter technician |  | 26.07 | Completed | No
WO-26-005452 | 1.8 | Bayou | BY-S17-02 | Service order - field | P3 within 10 days | 2026-05-25 | 2026-06-01 | 2026-06-02 | Meter technician |  | 13.44 | Completed | No
WO-26-005453 |  | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-05-25 | 2026-05-27 |  | Meter technician |  |  | Cancelled | No
WO-26-005454 | 1.1 | Bayou | BY-S24-03 | Service order - field | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Meter technician |  | 21.46 | Completed | No
WO-26-005455 | 1.3 | Bayou | BY-S17-02 | Service order - field | P3 within 10 days | 2026-05-25 | 2026-05-29 | 2026-05-30 | Meter technician |  | 32.56 | Completed | No
WO-26-005456 | 1.4 | Bayou | BY-S03-01 | Service order - field | P3 within 10 days | 2026-05-25 | 2026-05-31 | 2026-05-31 | Meter technician |  | 25.21 | Completed | No
WO-26-005457 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-25 | 2026-06-04 | 2026-06-08 | Contract line | CT-03 | 155.15 | Completed | No
WO-26-005458 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-25 | 2026-05-29 | 2026-05-29 | Contract line | CT-04 | 311.59 | Completed | No
WO-26-005459 | 12.3 | Bayou | BY-S06-03 | Transformer replacement | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Internal line |  | 10103.46 | Completed | Yes
WO-26-005460 | 13.5 | Bayou | BY-S15-02 | Transformer replacement | P2 same day | 2026-05-25 | 2026-05-25 | 2026-05-25 | Internal line |  | 11232.52 | Completed | Yes
WO-26-005461 | 8.1 | Bayou | BY-S20-03 | Transformer replacement | P2 same day | 2026-05-25 | 2026-05-25 | 2026-05-25 | Internal line |  | 5915.45 | Completed | Yes
WO-26-005462 | 7.8 | Bayou | BY-S17-02 | Transformer replacement | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Contract line | CT-03 | 11830.47 | Completed | No
WO-26-005463 | 4.4 | Bayou | BY-S23-01 | Trouble - no power | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Troubleman |  | 338.62 | Completed | No
WO-26-005464 | 2.3 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 343.32 | Completed | No
WO-26-005465 | 2.7 | Bayou | BY-S15-04 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 76.69 | Completed | No
WO-26-005466 | 5.9 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 197.02 | Completed | No
WO-26-005467 | 5 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 93.64 | Completed | No
WO-26-005468 | 4.7 | Bayou | BY-S28-03 | Trouble - partial or voltage | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Internal line |  | 248.83 | Completed | No
WO-26-005469 | 3.7 | Bayou | BY-S10-04 | Trouble - partial or voltage | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Troubleman |  | 238.06 | Completed | No
WO-26-005470 | 1.6 | Bayou | BY-S10-04 | Trouble - partial or voltage | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Troubleman |  | 180.49 | Completed | No
WO-26-005471 | 4 | Bayou | BY-S02-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-25 | 2026-06-03 | 2026-06-05 | Troubleman |  | 66.36 | Completed | No
WO-26-005472 | 4 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 133.21 | Completed | No
WO-26-005473 | 12.6 | Crossroads | CR-S22-04 | Corrective maintenance | P3 within 10 days | 2026-05-25 | 2026-05-31 | 2026-05-31 | Contract line | CT-01 | 1267.53 | Completed | Yes
WO-26-005474 | 5.9 | Crossroads | CR-S07-02 | Corrective maintenance | P2 same day | 2026-05-25 | 2026-05-26 | 2026-05-26 | Internal line |  | 517.04 | Completed | No
WO-26-005475 | 7.9 | Crossroads | CR-S21-01 | Corrective maintenance | P3 within 10 days | 2026-05-25 | 2026-05-29 | 2026-05-30 | Underground crew |  | 1374.12 | Completed | Yes
WO-26-005476 | 1.2 | Crossroads | CR-S10-03 | Meter exchange | P4 planned | 2026-05-25 | 2026-07-06 | 2026-07-06 | Meter technician |  | 174.35 | Completed | No
WO-26-005477 | 1.4 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-05-25 | 2026-05-31 | 2026-06-02 | Meter technician |  | 156.86 | Completed | No
WO-26-005478 | 9.7 | Crossroads | CR-S09-05 | New service - small | P4 planned | 2026-05-25 | 2026-06-06 | 2026-06-06 | Internal line |  | 1822.78 | Completed | No
WO-26-005479 | 12.1 | Crossroads | CR-S19-02 | Pole replacement | P3 within 10 days | 2026-05-25 | 2026-06-01 | 2026-06-01 | Internal line |  | 3070.46 | Completed | No
WO-26-005480 | 20.1 | Crossroads | CR-S04-06 | Pole replacement | P3 within 10 days | 2026-05-25 | 2026-06-04 | 2026-06-06 | Contract line | CT-01 | 2949.49 | Completed | No
WO-26-005481 | 3.1 | Crossroads | CR-S25-01 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-07-23 | 2026-07-23 | Underground crew |  | 30.31 | Completed | No
WO-26-005482 | 6.1 | Crossroads | CR-S32-04 | Preventive maintenance | P4 planned | 2026-05-25 | 2026-06-20 | 2026-06-24 | Internal line |  | 382.36 | Completed | No
WO-26-005483 | 2.9 | Crossroads |  | Streetlight | P4 planned | 2026-05-25 | 2026-06-29 | 2026-06-29 | Contract line | CT-02 | 275.58 | Completed | No
WO-26-005484 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-25 | 2026-05-27 | 2026-05-31 | Internal line |  | 123.57 | Completed | No
WO-26-005485 | 5.4 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 233.3 | Completed | No
WO-26-005486 | 4.3 | Crossroads | CR-S05-05 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 130.47 | Completed | No
WO-26-005487 | 3.7 | Crossroads | CR-S08-04 | Trouble - no power | P1 emergency | 2026-05-25 | 2026-05-25 | 2026-05-25 | Troubleman |  | 174.11 | Completed | No
WO-26-005488 | 4.3 | Crossroads | CR-S07-05 | Trouble - no power | P2 same day | 2026-05-25 | 2026-05-25 | 2026-05-25 | Internal line |  | 136 | Completed | No
WO-26-005489 | 4.6 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-25 | 2026-06-01 | 2026-06-01 | Troubleman |  | 87.59 | Completed | No
WO-26-005490 | 10 | Bayou | BY-S03-01 | Corrective maintenance | P3 within 10 days | 2026-05-26 | 2026-06-02 | 2026-06-02 | Contract line | CT-03 | 495.79 | Completed | No
WO-26-005491 | 1 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-05-26 | 2026-06-02 | 2026-06-03 | Meter technician |  | 126.58 | Completed | No
WO-26-005492 | 1.1 | Bayou | BY-S16-06 | Meter exchange | P4 planned | 2026-05-26 | 2026-06-13 | 2026-06-14 | Meter technician |  | 118.58 | Completed | No
WO-26-005493 | 0.7 | Bayou | BY-S10-05 | Meter exchange | P4 planned | 2026-05-26 | 2026-07-15 | 2026-07-15 | Meter technician |  | 111.59 | Completed | No
WO-26-005494 | 1.3 | Bayou | BY-S14-01 | Meter exchange | P4 planned | 2026-05-26 | 2026-06-08 | 2026-06-08 | Meter technician |  | 161.85 | Completed | No
WO-26-005495 | 5.4 | Bayou | BY-S12-03 | New service - small | P3 within 10 days | 2026-05-26 | 2026-05-30 | 2026-05-31 | Underground crew |  | 2785.88 | Completed | No
WO-26-005496 |  | Bayou | BY-S01-01 | New service - small | P4 planned | 2026-05-26 | 2026-07-07 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-005497 | 22 | Bayou | BY-S26-04 | Pole replacement | P3 within 10 days | 2026-05-26 | 2026-06-01 | 2026-06-01 | Contract line | CT-04 | 2358.55 | Completed | Yes
WO-26-005498 | 2.5 | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-06-05 | 2026-06-13 | Internal line |  | 429.87 | Completed | No
WO-26-005499 | 6.6 | Bayou | BY-S23-04 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-06-26 | 2026-06-30 | Internal line |  | 327.56 | Completed | No
WO-26-005500 | 3 | Bayou | BY-S02-01 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-07-13 | 2026-07-13 | Underground crew |  | 273.72 | Completed | No
WO-26-005501 | 0.7 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-06-05 | 2026-06-05 | Meter technician |  | 39.9 | Completed | No
WO-26-005502 | 0.9 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Meter technician |  | 11.94 | Completed | No
WO-26-005503 | 1.3 | Bayou | BY-S15-06 | Service order - field | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Meter technician |  | 36.25 | Completed | No
WO-26-005504 | 0.9 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Meter technician |  | 15.23 | Completed | No
WO-26-005505 | 1.9 | Bayou | BY-S03-01 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-05-31 | 2026-05-31 | Meter technician |  | 34.77 | Completed | No
WO-26-005506 | 0.9 | Bayou | BY-S03-03 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-06-02 | 2026-06-06 | Meter technician |  | 24.04 | Completed | No
WO-26-005507 | 1.6 | Bayou | BY-S22-02 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-06-03 | 2026-06-03 | Meter technician |  | 20.03 | Completed | No
WO-26-005508 | 0.5 | Bayou | BY-S23-05 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-06-03 | 2026-06-03 | Meter technician |  | 34.44 | Completed | No
WO-26-005509 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-05-26 | 2026-06-03 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-005510 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-26 | 2026-06-04 | 2026-06-04 | Contract line | CT-04 | 41.21 | Completed | No
WO-26-005511 | 1.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-26 | 2026-06-02 | 2026-06-04 | Contract line | CT-04 | 342.32 | Completed | No
WO-26-005512 | 1.1 | Bayou |  | Streetlight | P4 planned | 2026-05-26 | 2026-06-19 | 2026-06-23 | Contract line | CT-04 | 403.2 | Completed | No
WO-26-005513 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-26 | 2026-05-28 | 2026-05-28 | Contract line | CT-03 | 288.07 | Completed | No
WO-26-005514 | 2.6 | Bayou |  | Streetlight | P4 planned | 2026-05-26 | 2026-07-12 | 2026-07-12 | Internal line |  | 350.66 | Completed | No
WO-26-005515 | 15.1 | Bayou | BY-S26-02 | Transformer replacement | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Internal line |  | 10818.71 | Completed | Yes
WO-26-005516 | 13.6 | Bayou | BY-S15-02 | Transformer replacement | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 5187.28 | Completed | Yes
WO-26-005517 | 17.6 | Bayou | BY-S01-01 | Transformer replacement | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Internal line |  | 3267.24 | Completed | Yes
WO-26-005518 | 4.1 | Bayou | BY-S21-03 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Internal line |  | 295.64 | Completed | No
WO-26-005519 | 3.1 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 119.42 | Completed | No
WO-26-005520 | 2.9 | Bayou | BY-S30-01 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 278.42 | Completed | No
WO-26-005521 | 5 | Bayou | BY-S26-01 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 129.35 | Completed | No
WO-26-005522 | 2.2 | Bayou | BY-S19-03 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 200.63 | Completed | No
WO-26-005523 | 2.4 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 151.92 | Completed | No
WO-26-005524 | 2.2 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 137.1 | Completed | No
WO-26-005525 | 5.2 | Bayou | BY-S18-01 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 157.58 | Completed | No
WO-26-005526 | 5.8 | Bayou | BY-S16-05 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 12.18 | Completed | No
WO-26-005527 | 3.8 | Bayou | BY-S29-02 | Trouble - partial or voltage | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Internal line |  | 11.6 | Completed | No
WO-26-005528 | 1.6 | Bayou | BY-S19-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-26 | 2026-06-02 | 2026-06-04 | Troubleman |  | 77.24 | Completed | No
WO-26-005529 | 3.6 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 90.96 | Completed | No
WO-26-005530 | 8.5 | Crossroads | CR-S19-02 | Corrective maintenance | P3 within 10 days | 2026-05-26 | 2026-06-05 | 2026-06-09 | Underground crew |  | 833.86 | Completed | Yes
WO-26-005531 | 6 | Crossroads | CR-S07-05 | Corrective maintenance | P3 within 10 days | 2026-05-26 | 2026-06-03 | 2026-06-03 | Internal line |  | 2318.99 | Completed | No
WO-26-005532 | 14.8 | Crossroads | CR-S23-05 | Corrective maintenance | P3 within 10 days | 2026-05-26 | 2026-05-28 | 2026-05-28 | Internal line |  | 1789.84 | Completed | Yes
WO-26-005533 | 10.4 | Crossroads | CR-S08-02 | Corrective maintenance | P3 within 10 days | 2026-05-26 | 2026-05-29 | 2026-05-29 | Internal line |  | 1151.46 | Completed | Yes
WO-26-005534 | 12.8 | Crossroads | CR-S04-06 | Corrective maintenance | P4 planned | 2026-05-26 | 2026-07-01 | 2026-07-01 | Contract line | CT-01 | 1325.89 | Completed | Yes
WO-26-005535 | 4.7 | Crossroads | CR-S17-03 | Corrective maintenance | P4 planned | 2026-05-26 | 2026-07-14 | 2026-07-14 | Underground crew |  | 458.57 | Completed | Yes
WO-26-005536 | 7.2 | Crossroads | CR-S22-01 | Corrective maintenance | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Internal line |  | 89.33 | Completed | Yes
WO-26-005537 | 9.9 | Crossroads | CR-S25-03 | New service - small | P4 planned | 2026-05-26 | 2026-07-17 | 2026-07-17 | Contract line | CT-01 | 3378.95 | Completed | No
WO-26-005538 | 30.5 | Crossroads | CR-S25-01 | Pole replacement | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Internal line |  | 1620.05 | Completed | Yes
WO-26-005539 | 2.2 | Crossroads | CR-S25-01 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-07-14 | 2026-07-14 | Internal line |  | 524.81 | Completed | No
WO-26-005540 | 3.1 | Crossroads | CR-S23-05 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-07-04 | 2026-07-04 | Internal line |  | 450.45 | Completed | No
WO-26-005541 | 4.5 | Crossroads | CR-S25-02 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-07-03 | 2026-07-07 | Internal line |  | 118.58 | Completed | No
WO-26-005542 | 3.8 | Crossroads | CR-S28-04 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-07-05 | 2026-07-05 | Underground crew |  | 402.53 | Completed | No
WO-26-005543 | 5.4 | Crossroads | CR-S20-01 | Preventive maintenance | P4 planned | 2026-05-26 | 2026-06-27 | 2026-06-27 | Underground crew |  | 303.5 | Completed | No
WO-26-005544 | 1.3 | Crossroads | CR-S07-05 | Service order - field | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Meter technician |  | 19.08 | Completed | No
WO-26-005545 | 1.9 | Crossroads | CR-S14-03 | Service order - field | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Meter technician |  | 7.9 | Completed | No
WO-26-005546 | 1 | Crossroads | CR-S09-02 | Service order - field | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Meter technician |  | 29.42 | Completed | No
WO-26-005547 | 0.8 | Crossroads | CR-S16-02 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-05-28 | 2026-05-28 | Meter technician |  | 2.91 | Completed | No
WO-26-005548 | 0.9 | Crossroads | CR-S07-01 | Service order - field | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Meter technician |  | 18.66 | Completed | No
WO-26-005549 | 1.8 | Crossroads | CR-S18-06 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-06-04 | 2026-06-06 | Meter technician |  | 33.13 | Completed | No
WO-26-005550 | 1 | Crossroads | CR-S13-03 | Service order - field | P3 within 10 days | 2026-05-26 | 2026-05-28 | 2026-05-29 | Meter technician |  | 28.16 | Completed | No
WO-26-005551 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-26 | 2026-05-27 | 2026-05-31 | Internal line |  | 227.28 | Completed | No
WO-26-005552 | 1.3 | Crossroads |  | Streetlight | P4 planned | 2026-05-26 | 2026-06-08 | 2026-06-08 | Contract line | CT-01 | 385.19 | Completed | No
WO-26-005553 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-26 | 2026-06-01 | 2026-06-02 | Contract line | CT-02 | 149.15 | Completed | No
WO-26-005554 | 6.8 | Crossroads | CR-S15-01 | Transformer replacement | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 7275.84 | Completed | No
WO-26-005555 | 13.6 | Crossroads | CR-S01-02 | Transformer replacement | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 9331.58 | Completed | Yes
WO-26-005556 | 9.2 | Crossroads | CR-S02-05 | Transformer replacement | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Contract line | CT-02 | 4345.67 | Completed | Yes
WO-26-005557 | 5 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 217.57 | Completed | No
WO-26-005558 | 5.4 | Crossroads | CR-S26-06 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-27 | 2026-05-27 | Troubleman |  | 220.46 | Completed | No
WO-26-005559 | 5.8 | Crossroads | CR-S11-01 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 172.74 | Completed | No
WO-26-005560 | 2.1 | Crossroads | CR-S22-01 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 207.63 | Completed | No
WO-26-005561 | 2.5 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Internal line |  | 36.38 | Completed | No
WO-26-005562 | 3.4 | Crossroads | CR-S18-04 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 341.62 | Completed | No
WO-26-005563 | 3.5 | Crossroads | CR-S04-04 | Trouble - no power | P1 emergency | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 254.51 | Completed | No
WO-26-005564 | 2.2 | Crossroads | CR-S30-03 | Trouble - no power | P2 same day | 2026-05-26 | 2026-05-26 | 2026-05-26 | Troubleman |  | 274.37 | Completed | No
WO-26-005565 | 3.1 | Crossroads | CR-S11-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-26 | 2026-05-30 | 2026-05-30 | Troubleman |  | 152.93 | Completed | No
WO-26-005566 | 2.7 | Crossroads | CR-S10-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-26 | 2026-05-27 | 2026-05-27 | Troubleman |  | 94.73 | Completed | No
WO-26-005567 | 4.3 | Bayou | BY-S23-01 | Corrective maintenance | P3 within 10 days | 2026-05-27 | 2026-06-05 | 2026-06-09 | Internal line |  | 2027.27 | Completed | Yes
WO-26-005568 | 4.1 | Bayou | BY-S24-03 | Corrective maintenance | P4 planned | 2026-05-27 | 2026-06-11 | 2026-06-11 | Internal line |  | 141.13 | Completed | Yes
WO-26-005569 | 4.8 | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-05-27 | 2026-06-30 | 2026-06-30 | Contract line | CT-04 | 83.18 | Completed | Yes
WO-26-005570 | 5.3 | Bayou | BY-S15-06 | Corrective maintenance | P4 planned | 2026-05-27 | 2026-06-29 | 2026-07-01 | Contract line | CT-03 | 662.18 | Completed | Yes
WO-26-005571 | 0.8 | Bayou | BY-S17-04 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-06-02 | 2026-06-03 | Meter technician |  | 116.31 | Completed | No
WO-26-005572 | 1 | Bayou | BY-S29-03 | Meter exchange | P4 planned | 2026-05-27 | 2026-06-07 | 2026-06-09 | Meter technician |  | 97.27 | Completed | No
WO-26-005573 | 1.1 | Bayou | BY-S25-04 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-06-06 | 2026-06-06 | Meter technician |  | 178.05 | Completed | No
WO-26-005574 | 0.8 | Bayou | BY-S12-04 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-05-29 | 2026-05-29 | Meter technician |  | 115.49 | Completed | No
WO-26-005575 | 1.1 | Bayou | BY-S25-05 | Meter exchange | P4 planned | 2026-05-27 | 2026-06-14 | 2026-06-22 | Meter technician |  | 163.29 | Completed | No
WO-26-005576 | 1.2 | Bayou | BY-S18-04 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-05-31 | 2026-05-31 | Meter technician |  | 83.97 | Completed | No
WO-26-005577 | 1 | Bayou | BY-S16-03 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-05-28 | 2026-05-29 | Meter technician |  | 88.28 | Completed | No
WO-26-005578 | 1.4 | Bayou | BY-S08-02 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-06-02 | 2026-06-02 | Meter technician |  | 152.43 | Completed | No
WO-26-005579 | 7.4 | Bayou | BY-S21-03 | New service - small | P4 planned | 2026-05-27 | 2026-07-06 | 2026-07-06 | Internal line |  | 3695.55 | Completed | No
WO-26-005580 | 5.3 | Bayou | BY-S15-01 | Preventive maintenance | P4 planned | 2026-05-27 | 2026-07-07 | 2026-07-11 | Underground crew |  | 307.01 | Completed | No
WO-26-005581 | 6.3 | Bayou | BY-S29-03 | Preventive maintenance | P4 planned | 2026-05-27 | 2026-06-17 | 2026-06-17 | Underground crew |  | 292.54 | Completed | No
WO-26-005582 | 0.8 | Bayou | BY-S23-05 | Service order - field | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 33.76 | Completed | No
WO-26-005583 | 0.7 | Bayou | BY-S28-01 | Service order - field | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 20.6 | Completed | No
WO-26-005584 | 1.4 | Bayou | BY-S09-01 | Service order - field | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 34.89 | Completed | No
WO-26-005585 | 1.1 | Bayou | BY-S26-02 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-06-05 | 2026-06-09 | Meter technician |  | 13.53 | Completed | No
WO-26-005586 | 2 | Bayou | BY-S21-04 | Service order - field | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 14.91 | Completed | No
WO-26-005587 | 1.8 | Bayou | BY-S10-02 | Service order - field | P2 same day | 2026-05-27 | 2026-05-27 | 2026-05-27 | Meter technician |  | 14.25 | Completed | No
WO-26-005588 | 1.8 | Bayou | BY-S19-02 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-06-06 | 2026-06-06 | Meter technician |  | 10.28 | Completed | No
WO-26-005589 | 0.9 | Bayou | BY-S22-04 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 6.04 | Completed | No
WO-26-005590 | 0.9 | Bayou | BY-S01-01 | Service order - field | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 17.79 | Completed | No
WO-26-005591 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-27 | 2026-05-29 | 2026-05-30 | Contract line | CT-04 | 275.78 | Completed | No
WO-26-005592 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-27 | 2026-05-29 | 2026-06-02 | Internal line |  | 173.81 | Completed | No
WO-26-005593 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-27 | 2026-05-30 | 2026-05-31 | Contract line | CT-04 | 215.62 | Completed | No
WO-26-005594 | 8.2 | Bayou | BY-S16-01 | Transformer replacement | P2 same day | 2026-05-27 | 2026-05-27 | 2026-05-27 | Contract line | CT-04 | 4856.88 | Completed | Yes
WO-26-005595 | 2.8 | Bayou | BY-S23-03 | Trouble - no power | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Troubleman |  | 151.19 | Completed | No
WO-26-005596 | 2.6 | Bayou | BY-S07-05 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 91.2 | Completed | No
WO-26-005597 | 3.3 | Bayou | BY-S07-04 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Internal line |  | 241.74 | Completed | No
WO-26-005598 | 3.6 | Bayou | BY-S17-04 | Trouble - no power | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Troubleman |  | 197.27 | Completed | No
WO-26-005599 | 2.4 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Internal line |  | 118.91 | Completed | No
WO-26-005600 | 3.6 | Bayou | BY-S29-04 | Trouble - partial or voltage | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Troubleman |  | 46.09 | Completed | No
WO-26-005601 | 2.8 | Bayou | BY-S10-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-27 | 2026-06-01 | 2026-06-02 | Troubleman |  | 113.26 | Completed | No
WO-26-005602 | 3.1 | Bayou | BY-S23-03 | Trouble - partial or voltage | P3 within 10 days | 2026-05-27 | 2026-06-04 | 2026-06-06 | Troubleman |  | 20.06 | Completed | No
WO-26-005603 | 13.6 | Crossroads | CR-S29-02 | Corrective maintenance | P3 within 10 days | 2026-05-27 | 2026-06-05 | 2026-06-13 | Internal line |  | 2215.18 | Completed | Yes
WO-26-005604 | 10.6 | Crossroads | CR-S28-02 | Corrective maintenance | P3 within 10 days | 2026-05-27 | 2026-05-31 | 2026-05-31 | Contract line | CT-02 | 1713.48 | Completed | Yes
WO-26-005605 | 1.4 | Crossroads | CR-S21-02 | Meter exchange | P4 planned | 2026-05-27 | 2026-07-17 | 2026-07-18 | Meter technician |  | 126.51 | Completed | No
WO-26-005606 |  | Crossroads | CR-S17-03 | Meter exchange | P4 planned | 2026-05-27 | 2026-06-06 |  | Meter technician |  |  | Cancelled | No
WO-26-005607 | 0.8 | Crossroads | CR-S15-01 | Meter exchange | P3 within 10 days | 2026-05-27 | 2026-06-04 | 2026-06-04 | Meter technician |  | 97.05 | Completed | No
WO-26-005608 | 13 | Crossroads | CR-S26-05 | New service - small | P4 planned | 2026-05-27 | 2026-06-20 | 2026-06-24 | Contract line | CT-02 | 3296.17 | Completed | No
WO-26-005609 | 29.3 | Crossroads | CR-S14-06 | Pole replacement | P4 planned | 2026-05-27 | 2026-06-23 | 2026-07-01 | Contract line | CT-02 | 3430.99 | Completed | Yes
WO-26-005610 | 21.2 | Crossroads | CR-S09-01 | Pole replacement | P2 same day | 2026-05-27 | 2026-05-27 | 2026-05-27 | Internal line |  | 2102.83 | Completed | No
WO-26-005611 | 4.6 | Crossroads | CR-S13-06 | Preventive maintenance | P4 planned | 2026-05-27 | 2026-06-06 | 2026-06-10 | Internal line |  | 317.04 | Completed | No
WO-26-005612 | 5.1 | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-05-27 | 2026-06-10 | 2026-06-11 | Underground crew |  | 23.91 | Completed | No
WO-26-005613 | 7.6 | Crossroads | CR-S28-03 | Preventive maintenance | P4 planned | 2026-05-27 | 2026-07-07 | 2026-07-15 | Internal line |  | 599.07 | Completed | No
WO-26-005614 | 2 | Crossroads | CR-S25-03 | Preventive maintenance | P4 planned | 2026-05-27 | 2026-07-04 | 2026-07-05 | Internal line |  | 481.16 | Completed | No
WO-26-005615 | 1.9 | Crossroads | CR-S01-03 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-06-01 | 2026-06-01 | Meter technician |  | 2.26 | Completed | No
WO-26-005616 | 1 | Crossroads | CR-S22-02 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-05-31 | 2026-05-31 | Meter technician |  | 30.22 | Completed | No
WO-26-005617 | 1.5 | Crossroads | CR-S05-01 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-05-31 | 2026-05-31 | Meter technician |  | 11.03 | Completed | No
WO-26-005618 | 1 | Crossroads | CR-S15-03 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 34.31 | Completed | No
WO-26-005619 | 1.4 | Crossroads | CR-S20-04 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-05-29 | 2026-06-02 | Meter technician |  | 17.63 | Completed | No
WO-26-005620 | 1.9 | Crossroads | CR-S08-02 | Service order - field | P3 within 10 days | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 36.59 | Completed | No
WO-26-005621 | 1.1 | Crossroads | CR-S13-02 | Service order - field | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Meter technician |  | 20.4 | Completed | No
WO-26-005622 | 1.2 | Crossroads |  | Streetlight | P4 planned | 2026-05-27 | 2026-06-13 | 2026-06-21 | Contract line | CT-01 | 71.81 | Completed | No
WO-26-005623 | 9.3 | Crossroads | CR-S21-01 | Transformer replacement | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Internal line |  | 11055.21 | Completed | Yes
WO-26-005624 | 9.1 | Crossroads | CR-S19-03 | Transformer replacement | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Internal line |  | 3118.89 | Completed | No
WO-26-005625 | 5.2 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 181.22 | Completed | No
WO-26-005626 | 2 | Crossroads | CR-S32-01 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 326.05 | Completed | No
WO-26-005627 | 3.1 | Crossroads | CR-S25-04 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 337.87 | Completed | No
WO-26-005628 | 5 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 88.18 | Completed | No
WO-26-005629 | 3.7 | Crossroads | CR-S29-01 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 15.3 | Completed | No
WO-26-005630 |  | Crossroads | CR-S09-04 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 |  | Troubleman |  |  | Cancelled | No
WO-26-005631 | 5.6 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 330.34 | Completed | No
WO-26-005632 | 5.8 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-05-27 | 2026-05-27 | 2026-05-27 | Troubleman |  | 319.13 | Completed | No
WO-26-005633 | 2.9 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-27 | 2026-05-30 | 2026-05-30 | Troubleman |  | 2.6 | Completed | No
WO-26-005634 | 4.9 | Crossroads | CR-S16-03 | Trouble - partial or voltage | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Troubleman |  | 101.83 | Completed | No
WO-26-005635 | 3.5 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P2 same day | 2026-05-27 | 2026-05-28 | 2026-05-28 | Internal line |  | 138.44 | Completed | No
WO-26-005636 | 2.7 | Crossroads | CR-S11-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-27 | 2026-05-29 | 2026-05-30 | Troubleman |  | 174.58 | Completed | No
WO-26-005637 | 3.3 | Bayou | BY-S27-04 | Corrective maintenance | P3 within 10 days | 2026-05-28 | 2026-06-05 | 2026-06-06 | Underground crew |  | 1875.46 | Completed | No
WO-26-005638 | 12.5 | Bayou | BY-S09-04 | Corrective maintenance | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 659.43 | Completed | Yes
WO-26-005639 | 7.2 | Bayou | BY-S05-02 | Corrective maintenance | P3 within 10 days | 2026-05-28 | 2026-05-29 | 2026-05-29 | Contract line | CT-03 | 2112.83 | Completed | No
WO-26-005640 | 6.1 | Bayou | BY-S07-02 | Corrective maintenance | P2 same day | 2026-05-28 | 2026-05-29 | 2026-05-29 | Underground crew |  | 1585.17 | Completed | Yes
WO-26-005641 | 8.3 | Bayou | BY-S25-01 | Corrective maintenance | P3 within 10 days | 2026-05-28 | 2026-05-29 | 2026-05-29 | Contract line | CT-04 | 1403.64 | Completed | Yes
WO-26-005642 | 10.7 | Bayou | BY-S13-05 | Corrective maintenance | P3 within 10 days | 2026-05-28 | 2026-05-31 | 2026-05-31 | Contract line | CT-04 | 542.49 | Completed | Yes
WO-26-005643 | 15.5 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-05-28 | 2026-06-06 | 2026-06-14 | Underground crew |  | 1427.3 | Completed | Yes
WO-26-005644 | 14.4 | Bayou | BY-S21-02 | Corrective maintenance | P3 within 10 days | 2026-05-28 | 2026-06-04 | 2026-06-04 | Underground crew |  | 1041.62 | Completed | Yes
WO-26-005645 | 1 | Bayou | BY-S25-04 | Meter exchange | P3 within 10 days | 2026-05-28 | 2026-06-07 | 2026-06-07 | Meter technician |  | 117.25 | Completed | No
WO-26-005646 | 1 | Bayou | BY-S15-06 | Meter exchange | P4 planned | 2026-05-28 | 2026-06-29 | 2026-06-29 | Meter technician |  | 149.32 | Completed | No
WO-26-005647 | 1.5 | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-05-28 | 2026-06-01 | 2026-06-09 | Meter technician |  | 62.62 | Completed | No
WO-26-005648 | 1.5 | Bayou | BY-S11-03 | Meter exchange | P3 within 10 days | 2026-05-28 | 2026-06-03 | 2026-06-04 | Meter technician |  | 108.5 | Completed | No
WO-26-005649 | 0.7 | Bayou | BY-S28-02 | Meter exchange | P3 within 10 days | 2026-05-28 | 2026-06-03 | 2026-06-03 | Meter technician |  | 153.47 | Completed | No
WO-26-005650 | 0.9 | Bayou | BY-S22-04 | Meter exchange | P4 planned | 2026-05-28 | 2026-06-17 | 2026-06-17 | Meter technician |  | 73.26 | Completed | No
WO-26-005651 | 1.3 | Bayou | BY-S07-03 | Meter exchange | P3 within 10 days | 2026-05-28 | 2026-06-07 | 2026-06-08 | Meter technician |  | 107.23 | Completed | No
WO-26-005652 | 0.7 | Bayou | BY-S13-06 | Meter exchange | P4 planned | 2026-05-28 | 2026-06-08 | 2026-06-16 | Meter technician |  | 71.42 | Completed | No
WO-26-005653 | 28.9 | Bayou | BY-S12-04 | Pole replacement | P3 within 10 days | 2026-05-28 | 2026-06-06 | 2026-06-07 | Contract line | CT-03 | 2938.7 | Completed | Yes
WO-26-005654 | 17 | Bayou | BY-S10-02 | Pole replacement | P3 within 10 days | 2026-05-28 | 2026-06-03 | 2026-06-05 | Internal line |  | 1214.07 | Completed | Yes
WO-26-005655 | 7 | Bayou | BY-S08-02 | Preventive maintenance | P4 planned | 2026-05-28 | 2026-06-20 | 2026-06-28 | Internal line |  | 46.02 | Completed | No
WO-26-005656 | 2.2 | Bayou | BY-S18-07 | Preventive maintenance | P4 planned | 2026-05-28 | 2026-07-22 | 2026-07-22 | Internal line |  | 339.22 | Completed | No
WO-26-005657 | 2.8 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-05-28 | 2026-06-08 | 2026-06-12 | Contract line | CT-03 | 572.27 | Completed | No
WO-26-005658 | 1 | Bayou | BY-S18-05 | Service order - field | P2 same day | 2026-05-28 | 2026-05-29 | 2026-05-29 | Meter technician |  | 27.12 | Completed | No
WO-26-005659 | 1.6 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Meter technician |  | 22.05 | Completed | No
WO-26-005660 | 16.7 | Bayou | BY-S25-02 | Transformer replacement | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 11037.15 | Completed | Yes
WO-26-005661 | 3.5 | Bayou | BY-S20-01 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 309.34 | Completed | No
WO-26-005662 | 3.3 | Bayou | BY-S10-01 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 160.35 | Completed | No
WO-26-005663 | 2.6 | Bayou | BY-S15-04 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 66.65 | Completed | No
WO-26-005664 | 5 | Bayou | BY-S27-06 | Trouble - no power | P2 same day | 2026-05-28 | 2026-05-29 | 2026-05-29 | Troubleman |  | 58.22 | Completed | No
WO-26-005665 | 2.8 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 33.97 | Completed | No
WO-26-005666 | 2.4 | Bayou | BY-S27-02 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 192.67 | Completed | No
WO-26-005667 | 2.8 | Bayou | BY-S07-01 | Trouble - partial or voltage | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 23.62 | Completed | No
WO-26-005668 | 6.3 | Crossroads | CR-S06-01 | Corrective maintenance | P4 planned | 2026-05-28 | 2026-06-30 | 2026-06-30 | Contract line | CT-01 | 2170.81 | Completed | Yes
WO-26-005669 | 5 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Contract line | CT-02 | 2341.53 | Completed | No
WO-26-005670 | 0.5 | Crossroads | CR-S15-03 | Meter exchange | P4 planned | 2026-05-28 | 2026-06-18 | 2026-06-18 | Meter technician |  | 121.15 | Completed | No
WO-26-005671 | 0.6 | Crossroads | CR-S19-03 | Meter exchange | P4 planned | 2026-05-28 | 2026-06-09 | 2026-06-09 | Meter technician |  | 178.01 | Completed | No
WO-26-005672 | 10.5 | Crossroads | CR-S22-03 | New service - small | P4 planned | 2026-05-28 | 2026-07-07 | 2026-07-07 | Contract line | CT-01 | 813.99 | Completed | No
WO-26-005673 | 11.5 | Crossroads | CR-S17-01 | New service - small | P4 planned | 2026-05-28 | 2026-06-20 | 2026-06-20 | Contract line | CT-01 | 1596.85 | Completed | No
WO-26-005674 | 25.7 | Crossroads | CR-S19-04 | Pole replacement | P4 planned | 2026-05-28 | 2026-07-26 | 2026-07-26 | Contract line | CT-02 | 2174.92 | Completed | Yes
WO-26-005675 | 7.1 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-05-28 | 2026-06-22 | 2026-06-22 | Underground crew |  | 494.96 | Completed | No
WO-26-005676 | 3.6 | Crossroads | CR-S30-07 | Preventive maintenance | P4 planned | 2026-05-28 | 2026-07-22 | 2026-07-23 | Internal line |  | 395.73 | Completed | No
WO-26-005677 | 4.9 | Crossroads | CR-S32-05 | Preventive maintenance | P4 planned | 2026-05-28 | 2026-06-17 | 2026-06-17 | Internal line |  | 186.52 | Completed | No
WO-26-005678 | 1.3 | Crossroads | CR-S28-02 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-05-31 | 2026-06-01 | Meter technician |  | 6.16 | Completed | No
WO-26-005679 | 1 | Crossroads | CR-S01-03 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-05-30 | 2026-06-01 | Meter technician |  | 23.77 | Completed | No
WO-26-005680 | 1.3 | Crossroads | CR-S28-02 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-06-04 | 2026-06-05 | Meter technician |  | 2.63 | Completed | No
WO-26-005681 | 0.6 | Crossroads | CR-S20-02 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-06-04 | 2026-06-08 | Meter technician |  | 17.36 | Completed | No
WO-26-005682 | 1.1 | Crossroads | CR-S10-02 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-05-31 | 2026-05-31 | Meter technician |  | 4.44 | Completed | No
WO-26-005683 | 0.5 | Crossroads | CR-S10-01 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-05-29 | 2026-05-29 | Meter technician |  | 27.23 | Completed | No
WO-26-005684 | 1.8 | Crossroads | CR-S30-06 | Service order - field | P3 within 10 days | 2026-05-28 | 2026-06-04 | 2026-06-12 | Meter technician |  | 27.36 | Completed | No
WO-26-005685 | 0.8 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-05-28 | 2026-05-29 | 2026-05-29 | Meter technician |  | 13.57 | Completed | No
WO-26-005686 | 0.9 | Crossroads | CR-S12-01 | Service order - field | P2 same day | 2026-05-28 | 2026-05-29 | 2026-05-29 | Meter technician |  | 38.34 | Completed | No
WO-26-005687 | 1.3 | Crossroads | CR-S06-01 | Service order - field | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Meter technician |  | 3.54 | Completed | No
WO-26-005688 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-28 | 2026-06-07 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-005689 | 1.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-05-28 | 2026-06-05 | 2026-06-13 | Contract line | CT-01 | 41.1 | Completed | No
WO-26-005690 | 13.9 | Crossroads | CR-S26-06 | Transformer replacement | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Contract line | CT-01 | 10799.56 | Completed | Yes
WO-26-005691 | 8.9 | Crossroads | CR-S30-04 | Transformer replacement | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 10453.55 | Completed | Yes
WO-26-005692 | 16.1 | Crossroads | CR-S29-01 | Transformer replacement | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 6341.05 | Completed | Yes
WO-26-005693 | 17.1 | Crossroads | CR-S07-07 | Transformer replacement | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 3717.04 | Completed | Yes
WO-26-005694 | 10.4 | Crossroads | CR-S26-02 | Transformer replacement | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 5556.98 | Completed | Yes
WO-26-005695 | 5.9 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 276.66 | Completed | No
WO-26-005696 | 4 | Crossroads | CR-S14-01 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 102.09 | Completed | No
WO-26-005697 | 4.4 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 198.98 | Completed | No
WO-26-005698 | 3.1 | Crossroads | CR-S11-02 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 10.19 | Completed | No
WO-26-005699 | 5 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-05-28 | 2026-05-29 | 2026-05-29 | Troubleman |  | 223.5 | Completed | No
WO-26-005700 | 4.9 | Crossroads | CR-S25-02 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 315.16 | Completed | No
WO-26-005701 | 4.1 | Crossroads | CR-S04-05 | Trouble - no power | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 120.62 | Completed | No
WO-26-005702 | 4.8 | Crossroads | CR-S28-02 | Trouble - no power | P1 emergency | 2026-05-28 | 2026-05-28 | 2026-05-28 | Internal line |  | 28.1 | Completed | No
WO-26-005703 | 4.2 | Crossroads | CR-S32-01 | Trouble - partial or voltage | P2 same day | 2026-05-28 | 2026-05-28 | 2026-05-28 | Troubleman |  | 213.26 | Completed | No
WO-26-005704 | 5 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P3 within 10 days | 2026-05-28 | 2026-05-31 | 2026-06-02 | Troubleman |  | 129.97 | Completed | No
WO-26-005705 | 8.5 | Bayou | BY-S23-05 | Corrective maintenance | P4 planned | 2026-05-29 | 2026-07-25 | 2026-07-25 | Internal line |  | 1876.66 | Completed | No
WO-26-005706 | 11.9 | Bayou | BY-S21-03 | Corrective maintenance | P3 within 10 days | 2026-05-29 | 2026-06-04 | 2026-06-12 | Internal line |  | 1847.24 | Completed | No
WO-26-005707 | 4.5 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-05-29 | 2026-06-02 | 2026-06-04 | Contract line | CT-03 | 270.11 | Completed | No
WO-26-005708 | 8.8 | Bayou | BY-S04-03 | Corrective maintenance | P3 within 10 days | 2026-05-29 | 2026-05-31 | 2026-06-02 | Internal line |  | 823.69 | Completed | Yes
WO-26-005709 | 8.5 | Bayou | BY-S13-06 | Corrective maintenance | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Internal line |  | 1213.44 | Completed | Yes
WO-26-005710 | 0.7 | Bayou | BY-S09-01 | Meter exchange | P3 within 10 days | 2026-05-29 | 2026-05-30 | 2026-05-30 | Meter technician |  | 137.85 | Completed | No
WO-26-005711 | 1.5 | Bayou | BY-S15-01 | Meter exchange | P3 within 10 days | 2026-05-29 | 2026-06-04 | 2026-06-04 | Meter technician |  | 149.6 | Completed | No
WO-26-005712 | 0.9 | Bayou | BY-S19-01 | Meter exchange | P4 planned | 2026-05-29 | 2026-06-23 | 2026-06-23 | Meter technician |  | 101.76 | Completed | No
WO-26-005713 | 1.2 | Bayou | BY-S21-01 | Meter exchange | P3 within 10 days | 2026-05-29 | 2026-06-03 | 2026-06-05 | Meter technician |  | 149.17 | Completed | No
WO-26-005714 | 11.7 | Bayou | BY-S13-04 | New service - small | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-10 | Contract line | CT-03 | 3380.95 | Completed | No
WO-26-005715 | 29.2 | Bayou | BY-S07-03 | Pole replacement | P4 planned | 2026-05-29 | 2026-07-25 | 2026-07-25 | Internal line |  | 1914.61 | Completed | Yes
WO-26-005716 | 4.7 | Bayou | BY-S22-02 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-07-26 | 2026-07-27 | Underground crew |  | 119.23 | Completed | No
WO-26-005717 | 5.6 | Bayou | BY-S18-01 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-06-24 | 2026-06-24 | Underground crew |  | 81.39 | Completed | No
WO-26-005718 | 1.4 | Bayou | BY-S25-04 | Service order - field | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-08 | Meter technician |  | 0.05 | Completed | No
WO-26-005719 | 0.9 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Meter technician |  | 22.79 | Completed | No
WO-26-005720 | 1.1 | Bayou | BY-S11-03 | Service order - field | P3 within 10 days | 2026-05-29 | 2026-06-03 | 2026-06-03 | Meter technician |  | 25.98 | Completed | No
WO-26-005721 | 0.9 | Bayou | BY-S15-03 | Service order - field | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-10 | Meter technician |  | 18.03 | Completed | No
WO-26-005722 | 0.9 | Bayou | BY-S11-02 | Service order - field | P2 same day | 2026-05-29 | 2026-05-29 | 2026-05-29 | Meter technician |  | 32.15 | Completed | No
WO-26-005723 | 1.7 | Bayou | BY-S08-01 | Service order - field | P3 within 10 days | 2026-05-29 | 2026-05-30 | 2026-05-30 | Meter technician |  | 3.63 | Completed | No
WO-26-005724 | 1.3 | Bayou | BY-S12-03 | Service order - field | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Meter technician |  | 24.73 | Completed | No
WO-26-005725 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-29 | 2026-06-04 | 2026-06-12 | Contract line | CT-04 | 105.52 | Completed | No
WO-26-005726 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-08 | Internal line |  | 221.32 | Completed | No
WO-26-005727 | 3.8 | Bayou | BY-S21-01 | Trouble - no power | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Troubleman |  | 95.69 | Completed | No
WO-26-005728 | 5.9 | Bayou | BY-S06-02 | Trouble - no power | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Troubleman |  | 308.23 | Completed | No
WO-26-005729 | 3.4 | Bayou | BY-S13-01 | Trouble - partial or voltage | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Troubleman |  | 150.18 | Completed | No
WO-26-005730 | 8.2 | Crossroads | CR-S25-05 | Corrective maintenance | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-08 | Underground crew |  | 635.7 | Completed | Yes
WO-26-005731 | 11.7 | Crossroads | CR-S27-04 | Corrective maintenance | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-09 | Internal line |  | 1313.05 | Completed | Yes
WO-26-005732 | 4.9 | Crossroads | CR-S16-06 | Corrective maintenance | P3 within 10 days | 2026-05-29 | 2026-06-05 | 2026-06-06 | Underground crew |  | 1690.12 | Completed | Yes
WO-26-005733 | 11.7 | Crossroads | CR-S28-02 | Corrective maintenance | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Internal line |  | 738.58 | Completed | Yes
WO-26-005734 | 1.1 | Crossroads | CR-S16-06 | Meter exchange | P3 within 10 days | 2026-05-29 | 2026-06-05 | 2026-06-05 | Meter technician |  | 73.61 | Completed | No
WO-26-005735 |  | Crossroads | CR-S26-01 | Meter exchange | P4 planned | 2026-05-29 | 2026-06-05 |  | Meter technician |  |  | Cancelled | No
WO-26-005736 |  | Crossroads | CR-S18-04 | Meter exchange | P4 planned | 2026-05-29 | 2026-07-25 |  | Meter technician |  |  | Cancelled | No
WO-26-005737 | 1 | Crossroads | CR-S24-01 | Meter exchange | P3 within 10 days | 2026-05-29 | 2026-06-07 | 2026-06-15 | Meter technician |  | 95.11 | Completed | No
WO-26-005738 | 6.1 | Crossroads | CR-S07-01 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-06-16 | 2026-06-24 | Internal line |  | 309.86 | Completed | No
WO-26-005739 | 5.3 | Crossroads | CR-S25-01 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-06-13 | 2026-06-17 | Contract line | CT-02 | 327.19 | Completed | No
WO-26-005740 | 7.2 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-07-09 | 2026-07-09 | Internal line |  | 581.89 | Completed | No
WO-26-005741 | 5.1 | Crossroads | CR-S32-02 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-06-11 | 2026-06-12 | Contract line | CT-01 | 591.89 | Completed | No
WO-26-005742 | 3.1 | Crossroads | CR-S19-03 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-07-23 | 2026-07-25 | Underground crew |  | 479.74 | Completed | No
WO-26-005743 | 2.5 | Crossroads | CR-S04-03 | Preventive maintenance | P4 planned | 2026-05-29 | 2026-07-10 | 2026-07-11 | Contract line | CT-02 | 254.65 | Completed | No
WO-26-005744 | 0.9 | Crossroads | CR-S04-02 | Service order - field | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Meter technician |  | 7.55 | Completed | No
WO-26-005745 | 1 | Crossroads | CR-S22-01 | Service order - field | P3 within 10 days | 2026-05-29 | 2026-06-08 | 2026-06-16 | Meter technician |  | 0.77 | Completed | No
WO-26-005746 | 16.2 | Crossroads | CR-S19-04 | Transformer replacement | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Contract line | CT-02 | 8985.33 | Completed | Yes
WO-26-005747 | 10.2 | Crossroads | CR-S15-01 | Transformer replacement | P2 same day | 2026-05-29 | 2026-05-29 | 2026-05-29 | Internal line |  | 7405.01 | Completed | Yes
WO-26-005748 | 14.4 | Crossroads | CR-S19-01 | Transformer replacement | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Internal line |  | 4384.12 | Completed | Yes
WO-26-005749 | 15.1 | Crossroads | CR-S10-03 | Transformer replacement | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Internal line |  | 11934.19 | Completed | Yes
WO-26-005750 | 2.6 | Crossroads | CR-S07-05 | Trouble - no power | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Internal line |  | 162.29 | Completed | No
WO-26-005751 | 3.2 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Internal line |  | 193.18 | Completed | No
WO-26-005752 | 3.3 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Troubleman |  | 2.23 | Completed | No
WO-26-005753 | 2.5 | Crossroads | CR-S31-03 | Trouble - no power | P2 same day | 2026-05-29 | 2026-05-29 | 2026-05-29 | Troubleman |  | 39.08 | Completed | No
WO-26-005754 | 5.7 | Crossroads | CR-S09-05 | Trouble - no power | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Troubleman |  | 282.96 | Completed | No
WO-26-005755 | 4.1 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Troubleman |  | 112.01 | Completed | No
WO-26-005756 | 3 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-05-29 | 2026-05-29 | 2026-05-29 | Troubleman |  | 331.3 | Completed | No
WO-26-005757 | 3.3 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P3 within 10 days | 2026-05-29 | 2026-06-01 | 2026-06-01 | Internal line |  | 127.12 | Completed | No
WO-26-005758 | 3.7 | Crossroads | CR-S20-02 | Trouble - partial or voltage | P2 same day | 2026-05-29 | 2026-05-30 | 2026-05-30 | Troubleman |  | 37.51 | Completed | No
WO-26-005759 | 1.3 | Bayou | BY-S25-05 | Service order - field | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Meter technician |  | 6.25 | Completed | No
WO-26-005760 | 1.6 | Bayou | BY-S06-03 | Service order - field | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Meter technician |  | 11.58 | Completed | No
WO-26-005761 | 1.8 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Meter technician |  | 1.55 | Completed | No
WO-26-005762 | 2 | Bayou | BY-S07-03 | Service order - field | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Meter technician |  | 1.78 | Completed | No
WO-26-005763 | 1.1 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Meter technician |  | 1 | Completed | No
WO-26-005764 | 5.7 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Internal line |  | 349.8 | Completed | No
WO-26-005765 | 5.2 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 282.47 | Completed | No
WO-26-005766 | 2.2 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Internal line |  | 204.43 | Completed | No
WO-26-005767 | 5.6 | Bayou | BY-S12-04 | Trouble - no power | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 110.76 | Completed | No
WO-26-005768 | 3.1 | Bayou | BY-S13-06 | Trouble - no power | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 225.2 | Completed | No
WO-26-005769 | 3.8 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 156.01 | Completed | No
WO-26-005770 | 5.1 | Bayou | BY-S05-03 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 314 | Completed | No
WO-26-005771 | 4.9 | Bayou | BY-S04-03 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 34.66 | Completed | No
WO-26-005772 | 1.6 | Bayou | BY-S16-03 | Trouble - partial or voltage | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Troubleman |  | 247.76 | Completed | No
WO-26-005773 | 13.1 | Crossroads | CR-S05-02 | Pole replacement | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Contract line | CT-01 | 1377.55 | Completed | No
WO-26-005774 | 1.5 | Crossroads | CR-S31-01 | Service order - field | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Meter technician |  | 29.34 | Completed | No
WO-26-005775 | 2 | Crossroads | CR-S18-03 | Service order - field | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Meter technician |  | 34.13 | Completed | No
WO-26-005776 | 1 | Crossroads | CR-S01-03 | Service order - field | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Meter technician |  | 7.05 | Completed | No
WO-26-005777 | 1.2 | Crossroads | CR-S04-02 | Service order - field | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Meter technician |  | 26.41 | Completed | No
WO-26-005778 | 13.1 | Crossroads | CR-S24-04 | Transformer replacement | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Internal line |  | 11842.62 | Completed | Yes
WO-26-005779 | 10.3 | Crossroads | CR-S15-01 | Transformer replacement | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Internal line |  | 6366.16 | Completed | No
WO-26-005780 | 2.7 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Troubleman |  | 333.16 | Completed | No
WO-26-005781 | 2 | Crossroads | CR-S24-03 | Trouble - no power | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 258.33 | Completed | No
WO-26-005782 | 5.2 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Internal line |  | 204.66 | Completed | No
WO-26-005783 | 4.5 | Crossroads | CR-S02-05 | Trouble - no power | P2 same day | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 196.35 | Completed | No
WO-26-005784 | 4.9 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 304.71 | Completed | No
WO-26-005785 | 5.6 | Crossroads | CR-S02-05 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 117.08 | Completed | No
WO-26-005786 | 2.3 | Crossroads | CR-S05-02 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 77.96 | Completed | No
WO-26-005787 | 4.1 | Crossroads | CR-S23-02 | Trouble - no power | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Troubleman |  | 76.29 | Completed | No
WO-26-005788 | 3.2 | Crossroads | CR-S09-03 | Trouble - no power | P1 emergency | 2026-05-30 | 2026-05-30 | 2026-05-30 | Troubleman |  | 222.63 | Completed | No
WO-26-005789 | 2.5 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P2 same day | 2026-05-30 | 2026-05-31 | 2026-05-31 | Troubleman |  | 249.02 | Completed | No
WO-26-005790 | 1.1 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Meter technician |  | 19.07 | Completed | No
WO-26-005791 | 10.6 | Bayou | BY-S26-02 | Transformer replacement | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Internal line |  | 7636.87 | Completed | Yes
WO-26-005792 | 3.5 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 296.49 | Completed | No
WO-26-005793 | 3.8 | Bayou | BY-S14-03 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 168.82 | Completed | No
WO-26-005794 | 4.5 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 233.32 | Completed | No
WO-26-005795 | 5.5 | Bayou | BY-S29-03 | Trouble - no power | P2 same day | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 155.74 | Completed | No
WO-26-005796 | 5.6 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 35.68 | Completed | No
WO-26-005797 | 2.4 | Bayou | BY-S23-01 | Trouble - no power | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Troubleman |  | 192.48 | Completed | No
WO-26-005798 | 3.4 | Bayou | BY-S29-05 | Trouble - partial or voltage | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Troubleman |  | 200.28 | Completed | No
WO-26-005799 | 3.1 | Bayou | BY-S03-01 | Trouble - partial or voltage | P2 same day | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 16.41 | Completed | No
WO-26-005800 | 13.6 | Crossroads | CR-S32-04 | Pole replacement | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Contract line | CT-02 | 1868.01 | Completed | Yes
WO-26-005801 | 1.9 | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-05-31 | 2026-05-31 | 2026-05-31 | Meter technician |  | 21.57 | Completed | No
WO-26-005802 | 3.8 | Crossroads | CR-S07-04 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 3.05 | Completed | No
WO-26-005803 | 5 | Crossroads | CR-S10-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 122.11 | Completed | No
WO-26-005804 | 6 | Crossroads | CR-S09-01 | Trouble - no power | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Internal line |  | 178.78 | Completed | No
WO-26-005805 | 2.4 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 241.4 | Completed | No
WO-26-005806 | 4.3 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Troubleman |  | 66.99 | Completed | No
WO-26-005807 | 2.6 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Internal line |  | 99.04 | Completed | No
WO-26-005808 | 4.3 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 255.09 | Completed | No
WO-26-005809 | 5.8 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 146.55 | Completed | No
WO-26-005810 | 2.9 | Crossroads | CR-S08-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 231.02 | Completed | No
WO-26-005811 | 3 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 269.84 | Completed | No
WO-26-005812 | 2.5 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-05-31 | 2026-05-31 | 2026-05-31 | Troubleman |  | 72.45 | Completed | No
WO-26-005813 | 2.6 | Crossroads | CR-S27-02 | Trouble - no power | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Troubleman |  | 109.31 | Completed | No
WO-26-005814 | 4.1 | Crossroads | CR-S15-02 | Trouble - no power | P2 same day | 2026-05-31 | 2026-06-01 | 2026-06-01 | Troubleman |  | 181.01 | Completed | No
WO-26-005815 | 10.4 | Bayou | BY-S24-05 | Corrective maintenance | P3 within 10 days | 2026-06-01 | 2026-06-07 | 2026-06-07 | Contract line | CT-04 | 1047.27 | Completed | No
WO-26-005816 | 6.5 | Bayou | BY-S28-01 | Corrective maintenance | P3 within 10 days | 2026-06-01 | 2026-06-11 | 2026-06-13 | Contract line | CT-03 | 1834.11 | Completed | No
WO-26-005817 | 7.7 | Bayou | BY-S19-02 | Corrective maintenance | P3 within 10 days | 2026-06-01 | 2026-06-09 | 2026-06-09 | Underground crew |  | 844.57 | Completed | No
WO-26-005818 | 6.5 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-06-01 | 2026-06-09 | 2026-06-09 | Internal line |  | 1140.79 | Completed | No
WO-26-005819 | 1.4 | Bayou | BY-S30-03 | Meter exchange | P4 planned | 2026-06-01 | 2026-07-03 | 2026-07-07 | Meter technician |  | 92.58 | Completed | No
WO-26-005820 | 0.9 | Bayou | BY-S16-04 | Meter exchange | P4 planned | 2026-06-01 | 2026-07-06 | 2026-07-06 | Meter technician |  | 117.51 | Completed | No
WO-26-005821 | 4.6 | Bayou | BY-S10-01 | New service - small | P3 within 10 days | 2026-06-01 | 2026-06-08 | 2026-06-08 | Underground crew |  | 717.31 | Completed | No
WO-26-005822 | 10.7 | Bayou | BY-S04-02 | Pole replacement | P3 within 10 days | 2026-06-01 | 2026-06-08 | 2026-06-10 | Internal line |  | 2135.79 | Completed | No
WO-26-005823 | 5.7 | Bayou | BY-S12-03 | Preventive maintenance | P4 planned | 2026-06-01 | 2026-07-25 | 2026-07-26 | Underground crew |  | 441.14 | Completed | No
WO-26-005824 |  | Bayou | BY-S17-02 | Preventive maintenance | P4 planned | 2026-06-01 | 2026-06-09 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-005825 | 7.9 | Bayou | BY-S27-02 | Preventive maintenance | P4 planned | 2026-06-01 | 2026-07-13 | 2026-07-15 | Internal line |  | 547.23 | Completed | No
WO-26-005826 | 2 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Meter technician |  | 3.58 | Completed | No
WO-26-005827 | 1.4 | Bayou | BY-S26-03 | Service order - field | P3 within 10 days | 2026-06-01 | 2026-06-05 | 2026-06-06 | Meter technician |  | 20.87 | Completed | No
WO-26-005828 | 1.3 | Bayou | BY-S06-03 | Service order - field | P3 within 10 days | 2026-06-01 | 2026-06-07 | 2026-06-15 | Meter technician |  | 9.62 | Completed | No
WO-26-005829 | 0.8 | Bayou | BY-S27-06 | Service order - field | P3 within 10 days | 2026-06-01 | 2026-06-08 | 2026-06-08 | Meter technician |  | 20.16 | Completed | No
WO-26-005830 | 0.6 | Bayou | BY-S16-05 | Service order - field | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Meter technician |  | 10.65 | Completed | No
WO-26-005831 | 0.9 | Bayou | BY-S22-03 | Service order - field | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Meter technician |  | 26.79 | Completed | No
WO-26-005832 | 1.6 | Bayou | BY-S02-01 | Service order - field | P3 within 10 days | 2026-06-01 | 2026-06-05 | 2026-06-05 | Meter technician |  | 20.75 | Completed | No
WO-26-005833 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-01 | 2026-06-04 | 2026-06-05 | Contract line | CT-04 | 57.67 | Completed | No
WO-26-005834 | 1.6 | Bayou |  | Streetlight | P4 planned | 2026-06-01 | 2026-07-29 | 2026-08-02 | Internal line |  | 56.86 | Completed | No
WO-26-005835 | 6.7 | Bayou | BY-S07-02 | Transformer replacement | P3 within 10 days | 2026-06-01 | 2026-06-02 | 2026-06-02 | Internal line |  | 10698.29 | Completed | No
WO-26-005836 | 4.7 | Bayou | BY-S29-02 | Trouble - no power | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Troubleman |  | 274.29 | Completed | No
WO-26-005837 | 4.2 | Bayou | BY-S10-04 | Trouble - no power | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 342.65 | Completed | No
WO-26-005838 | 2.9 | Bayou | BY-S21-04 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 152.25 | Completed | No
WO-26-005839 | 4.1 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 43.28 | Completed | No
WO-26-005840 |  | Bayou | BY-S04-01 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 |  | Troubleman |  |  | Cancelled | No
WO-26-005841 |  | Bayou | BY-S29-01 | Trouble - partial or voltage | P3 within 10 days | 2026-06-01 | 2026-06-02 |  | Troubleman |  |  | Cancelled | No
WO-26-005842 | 1.5 | Bayou | BY-S03-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-01 | 2026-06-08 | 2026-06-10 | Internal line |  | 178.07 | Completed | No
WO-26-005843 | 9.3 | Crossroads | CR-S08-06 | Corrective maintenance | P3 within 10 days | 2026-06-01 | 2026-06-11 | 2026-06-15 | Contract line | CT-01 | 543.13 | Completed | No
WO-26-005844 | 8.1 | Crossroads | CR-S17-01 | Corrective maintenance | P3 within 10 days | 2026-06-01 | 2026-06-09 | 2026-06-09 | Internal line |  | 1113.82 | Completed | No
WO-26-005845 | 1.3 | Crossroads | CR-S07-03 | Meter exchange | P4 planned | 2026-06-01 | 2026-07-11 | 2026-07-11 | Meter technician |  | 151.42 | Completed | No
WO-26-005846 | 1 | Crossroads | CR-S15-03 | Meter exchange | P4 planned | 2026-06-01 | 2026-06-23 | 2026-06-23 | Meter technician |  | 97.11 | Completed | No
WO-26-005847 | 5.6 | Crossroads | CR-S14-01 | New service - small | P4 planned | 2026-06-01 | 2026-06-09 | 2026-06-10 | Contract line | CT-02 | 1147.73 | Completed | No
WO-26-005848 |  | Crossroads | CR-S08-06 | Pole replacement | P3 within 10 days | 2026-06-01 | 2026-06-11 |  | Internal line |  |  | Cancelled | No
WO-26-005849 | 17.6 | Crossroads | CR-S30-07 | Pole replacement | P3 within 10 days | 2026-06-01 | 2026-06-06 | 2026-06-06 | Contract line | CT-01 | 2183.22 | Completed | No
WO-26-005850 | 21.3 | Crossroads | CR-S31-02 | Pole replacement | P3 within 10 days | 2026-06-01 | 2026-06-07 | 2026-06-07 | Internal line |  | 2624.52 | Completed | No
WO-26-005851 | 5.5 | Crossroads | CR-S05-01 | Preventive maintenance | P4 planned | 2026-06-01 | 2026-07-20 | 2026-07-20 | Internal line |  | 225.92 | Completed | No
WO-26-005852 | 3.9 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-06-01 | 2026-06-11 | 2026-06-12 | Internal line |  | 107.8 | Completed | No
WO-26-005853 | 5.9 | Crossroads | CR-S32-04 | Preventive maintenance | P4 planned | 2026-06-01 | 2026-07-10 | 2026-07-14 | Underground crew |  | 76.75 | Completed | No
WO-26-005854 | 1.1 | Crossroads | CR-S30-03 | Service order - field | P3 within 10 days | 2026-06-01 | 2026-06-06 | 2026-06-06 | Meter technician |  | 37.15 | Completed | No
WO-26-005855 | 0.8 | Crossroads | CR-S05-06 | Service order - field | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Meter technician |  | 31.87 | Completed | No
WO-26-005856 | 1.7 | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Meter technician |  | 28.28 | Completed | No
WO-26-005857 | 1.3 | Crossroads | CR-S05-04 | Service order - field | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Meter technician |  | 10.68 | Completed | No
WO-26-005858 | 0.8 | Crossroads | CR-S04-05 | Service order - field | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Meter technician |  | 32.89 | Completed | No
WO-26-005859 | 1.1 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Meter technician |  | 34.33 | Completed | No
WO-26-005860 | 0.7 | Crossroads | CR-S05-05 | Service order - field | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Meter technician |  | 24.55 | Completed | No
WO-26-005861 |  | Crossroads | CR-S11-01 | Transformer replacement | P1 emergency | 2026-06-01 | 2026-06-01 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-005862 | 4.4 | Crossroads | CR-S19-04 | Trouble - no power | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 163.48 | Completed | No
WO-26-005863 | 5 | Crossroads | CR-S04-01 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 220.88 | Completed | No
WO-26-005864 | 3.1 | Crossroads | CR-S10-01 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 | 2026-06-01 | Internal line |  | 100.41 | Completed | No
WO-26-005865 | 3.3 | Crossroads | CR-S07-02 | Trouble - no power | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 168.49 | Completed | No
WO-26-005866 | 5.4 | Crossroads | CR-S07-02 | Trouble - no power | P2 same day | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 275.67 | Completed | No
WO-26-005867 | 3.5 | Crossroads | CR-S28-01 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 | 2026-06-01 | Troubleman |  | 198.57 | Completed | No
WO-26-005868 | 4.3 | Crossroads | CR-S23-05 | Trouble - no power | P1 emergency | 2026-06-01 | 2026-06-01 | 2026-06-01 | Internal line |  | 32.07 | Completed | No
WO-26-005869 | 4.5 | Crossroads | CR-S16-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-01 | 2026-06-03 | 2026-06-04 | Internal line |  | 2.11 | Completed | No
WO-26-005870 | 2 | Crossroads | CR-S25-04 | Trouble - partial or voltage | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Troubleman |  | 62.81 | Completed | No
WO-26-005871 | 2.7 | Crossroads | CR-S27-02 | Trouble - partial or voltage | P2 same day | 2026-06-01 | 2026-06-02 | 2026-06-02 | Troubleman |  | 113.01 | Completed | No
WO-26-005872 | 4.2 | Bayou | BY-S21-01 | Corrective maintenance | P4 planned | 2026-06-02 | 2026-06-24 | 2026-06-24 | Internal line |  | 1778.3 | Completed | No
WO-26-005873 | 1.4 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-06-02 | 2026-06-07 | 2026-06-11 | Meter technician |  | 61.28 | Completed | No
WO-26-005874 | 4.7 | Bayou | BY-S19-03 | New service - small | P4 planned | 2026-06-02 | 2026-07-13 | 2026-07-17 | Internal line |  | 684.27 | Completed | No
WO-26-005875 | 2.1 | Bayou | BY-S09-05 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-06-18 | 2026-06-19 | Internal line |  | 397.42 | Completed | No
WO-26-005876 | 4.8 | Bayou | BY-S22-04 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-06-17 | 2026-06-17 | Contract line | CT-04 | 349.87 | Completed | No
WO-26-005877 | 3.3 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-07-10 | 2026-07-14 | Internal line |  | 306.59 | Completed | No
WO-26-005878 | 5.8 | Bayou | BY-S13-02 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-06-27 | 2026-06-27 | Underground crew |  | 544.48 | Completed | No
WO-26-005879 | 0.9 | Bayou | BY-S18-04 | Service order - field | P2 same day | 2026-06-02 | 2026-06-02 | 2026-06-02 | Meter technician |  | 29.7 | Completed | No
WO-26-005880 | 1.9 | Bayou | BY-S13-06 | Service order - field | P3 within 10 days | 2026-06-02 | 2026-06-03 | 2026-06-03 | Meter technician |  | 9.19 | Completed | No
WO-26-005881 | 1.9 | Bayou | BY-S15-06 | Service order - field | P3 within 10 days | 2026-06-02 | 2026-06-03 | 2026-06-04 | Meter technician |  | 33.56 | Completed | No
WO-26-005882 |  | Bayou | BY-S19-03 | Service order - field | P2 same day | 2026-06-02 | 2026-06-03 |  | Meter technician |  |  | Cancelled | No
WO-26-005883 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-02 | 2026-06-04 | 2026-06-04 | Contract line | CT-03 | 283.94 | Completed | No
WO-26-005884 | 13.9 | Bayou | BY-S16-01 | Transformer replacement | P3 within 10 days | 2026-06-02 | 2026-06-03 | 2026-06-05 | Internal line |  | 5836.16 | Completed | No
WO-26-005885 | 7.7 | Bayou | BY-S18-05 | Transformer replacement | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Contract line | CT-03 | 3464.47 | Completed | No
WO-26-005886 | 12.6 | Bayou | BY-S27-06 | Transformer replacement | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Internal line |  | 3931 | Completed | No
WO-26-005887 | 13 | Bayou | BY-S03-02 | Transformer replacement | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Contract line | CT-03 | 3486.55 | Completed | No
WO-26-005888 | 3.2 | Bayou | BY-S11-03 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 48.7 | Completed | No
WO-26-005889 | 3.4 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 279.62 | Completed | No
WO-26-005890 | 2.4 | Bayou | BY-S10-02 | Trouble - no power | P2 same day | 2026-06-02 | 2026-06-03 | 2026-06-03 | Internal line |  | 321.62 | Completed | No
WO-26-005891 | 4.2 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 313.01 | Completed | No
WO-26-005892 | 2.3 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Internal line |  | 314.13 | Completed | No
WO-26-005893 | 2 | Bayou | BY-S16-06 | Trouble - partial or voltage | P3 within 10 days | 2026-06-02 | 2026-06-07 | 2026-06-08 | Troubleman |  | 85.82 | Completed | No
WO-26-005894 | 5.6 | Crossroads | CR-S25-05 | Corrective maintenance | P4 planned | 2026-06-02 | 2026-07-10 | 2026-07-12 | Internal line |  | 170.18 | Completed | No
WO-26-005895 | 10.5 | Crossroads | CR-S26-06 | Corrective maintenance | P3 within 10 days | 2026-06-02 | 2026-06-08 | 2026-06-08 | Underground crew |  | 877.68 | Completed | No
WO-26-005896 | 3.3 | Crossroads | CR-S30-03 | Corrective maintenance | P3 within 10 days | 2026-06-02 | 2026-06-04 | 2026-06-04 | Internal line |  | 424.57 | Completed | No
WO-26-005897 | 11.9 | Crossroads | CR-S09-02 | Corrective maintenance | P4 planned | 2026-06-02 | 2026-06-19 | 2026-06-20 | Underground crew |  | 2377.45 | Completed | No
WO-26-005898 | 9.3 | Crossroads | CR-S18-06 | Corrective maintenance | P3 within 10 days | 2026-06-02 | 2026-06-04 | 2026-06-05 | Contract line | CT-02 | 2060.11 | Completed | No
WO-26-005899 | 1.4 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-06-02 | 2026-06-08 | 2026-06-08 | Meter technician |  | 65.37 | Completed | No
WO-26-005900 | 1.5 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-06-02 | 2026-06-08 | 2026-06-08 | Meter technician |  | 126.51 | Completed | No
WO-26-005901 | 13.4 | Crossroads | CR-S03-01 | Pole replacement | P3 within 10 days | 2026-06-02 | 2026-06-12 | 2026-06-16 | Internal line |  | 2586.65 | Completed | No
WO-26-005902 | 8 | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-07-17 | 2026-07-21 | Internal line |  | 157.36 | Completed | No
WO-26-005903 | 7.8 | Crossroads | CR-S28-04 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-06-16 | 2026-06-18 | Underground crew |  | 154.8 | Completed | No
WO-26-005904 | 4.2 | Crossroads | CR-S07-03 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-07-21 | 2026-07-21 | Underground crew |  | 60.69 | Completed | No
WO-26-005905 | 4.9 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-07-15 | 2026-07-15 | Internal line |  | 71.34 | Completed | No
WO-26-005906 | 6 | Crossroads | CR-S27-02 | Preventive maintenance | P4 planned | 2026-06-02 | 2026-07-16 | 2026-07-20 | Contract line | CT-02 | 468.5 | Completed | No
WO-26-005907 | 0.6 | Crossroads | CR-S13-06 | Service order - field | P3 within 10 days | 2026-06-02 | 2026-06-05 | 2026-06-06 | Meter technician |  | 11.67 | Completed | No
WO-26-005908 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-02 | 2026-06-10 | 2026-06-10 | Contract line | CT-01 | 104.01 | Completed | No
WO-26-005909 | 12.5 | Crossroads | CR-S04-06 | Transformer replacement | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Internal line |  | 5015.96 | Completed | No
WO-26-005910 | 5.4 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 224.95 | Completed | No
WO-26-005911 | 5.3 | Crossroads | CR-S05-02 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 300.92 | Completed | No
WO-26-005912 | 3.9 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 32.27 | Completed | No
WO-26-005913 | 4.3 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-06-02 | 2026-06-02 | 2026-06-02 | Troubleman |  | 118.07 | Completed | No
WO-26-005914 | 4.3 | Crossroads | CR-S05-06 | Trouble - no power | P2 same day | 2026-06-02 | 2026-06-03 | 2026-06-03 | Troubleman |  | 278.58 | Completed | No
WO-26-005915 | 1.8 | Crossroads | CR-S02-01 | Trouble - partial or voltage | P3 within 10 days | 2026-06-02 | 2026-06-12 | 2026-06-13 | Troubleman |  | 89.8 | Completed | No
WO-26-005916 | 3.5 | Crossroads | CR-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-02 | 2026-06-10 | 2026-06-11 | Troubleman |  | 136.33 | Completed | No
WO-26-005917 | 4.6 | Crossroads | CR-S13-05 | Trouble - partial or voltage | P2 same day | 2026-06-02 | 2026-06-03 | 2026-06-03 | Troubleman |  | 68.09 | Completed | No
WO-26-005918 |  | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-06-03 | 2026-06-08 |  | Underground crew |  |  | Cancelled | No
WO-26-005919 | 4.5 | Bayou | BY-S26-02 | Corrective maintenance | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Internal line |  | 490.12 | Completed | No
WO-26-005920 | 1.4 | Bayou | BY-S21-02 | Meter exchange | P4 planned | 2026-06-03 | 2026-08-02 | 2026-08-02 | Meter technician |  | 80.72 | Completed | No
WO-26-005921 | 1.2 | Bayou | BY-S29-02 | Meter exchange | P3 within 10 days | 2026-06-03 | 2026-06-13 | 2026-06-13 | Meter technician |  | 100.88 | Completed | No
WO-26-005922 | 12 | Bayou | BY-S21-01 | New service - small | P4 planned | 2026-06-03 | 2026-07-27 | 2026-07-28 | Internal line |  | 3838.2 | Completed | No
WO-26-005923 | 9.4 | Bayou | BY-S13-05 | New service - small | P4 planned | 2026-06-03 | 2026-07-10 | 2026-07-10 | Internal line |  | 1794.2 | Completed | No
WO-26-005924 | 10.7 | Bayou | BY-S16-01 | Pole replacement | P3 within 10 days | 2026-06-03 | 2026-06-12 | 2026-06-12 | Internal line |  | 2461.24 | Completed | No
WO-26-005925 | 6.8 | Bayou | BY-S18-05 | Preventive maintenance | P4 planned | 2026-06-03 | 2026-07-03 | 2026-07-11 | Internal line |  | 442.98 | Completed | No
WO-26-005926 | 2.6 | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-06-03 | 2026-06-23 | 2026-07-01 | Internal line |  | 580.19 | Completed | No
WO-26-005927 | 1.5 | Bayou | BY-S30-01 | Service order - field | P3 within 10 days | 2026-06-03 | 2026-06-05 | 2026-06-06 | Meter technician |  | 16 | Completed | No
WO-26-005928 | 13.9 | Bayou | BY-S14-01 | Transformer replacement | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Internal line |  | 7341.27 | Completed | No
WO-26-005929 | 8.8 | Bayou | BY-S15-01 | Transformer replacement | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Contract line | CT-04 | 11370.01 | Completed | No
WO-26-005930 | 10.6 | Bayou | BY-S14-01 | Transformer replacement | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Internal line |  | 5933 | Completed | No
WO-26-005931 | 2.4 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 121.84 | Completed | No
WO-26-005932 | 5.9 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 330.86 | Completed | No
WO-26-005933 | 3.7 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 187.7 | Completed | No
WO-26-005934 | 5 | Bayou | BY-S22-04 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 47.24 | Completed | No
WO-26-005935 | 5.4 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 69.05 | Completed | No
WO-26-005936 | 1.6 | Bayou | BY-S21-01 | Trouble - partial or voltage | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 176.65 | Completed | No
WO-26-005937 | 3 | Bayou | BY-S16-02 | Trouble - partial or voltage | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Internal line |  | 206.77 | Completed | No
WO-26-005938 | 4.2 | Bayou | BY-S02-02 | Trouble - partial or voltage | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 229.3 | Completed | No
WO-26-005939 | 2 | Bayou | BY-S21-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-03 | 2026-06-13 | 2026-06-21 | Troubleman |  | 247.82 | Completed | No
WO-26-005940 | 3.6 | Bayou | BY-S15-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-03 | 2026-06-07 | 2026-06-07 | Troubleman |  | 191.47 | Completed | No
WO-26-005941 | 7.8 | Crossroads | CR-S28-04 | Corrective maintenance | P3 within 10 days | 2026-06-03 | 2026-06-09 | 2026-06-09 | Underground crew |  | 306.67 | Completed | No
WO-26-005942 | 1 | Crossroads | CR-S28-02 | Meter exchange | P3 within 10 days | 2026-06-03 | 2026-06-11 | 2026-06-11 | Meter technician |  | 139.59 | Completed | No
WO-26-005943 | 1.5 | Crossroads | CR-S07-04 | Meter exchange | P3 within 10 days | 2026-06-03 | 2026-06-07 | 2026-06-07 | Meter technician |  | 171.57 | Completed | No
WO-26-005944 | 20.9 | Crossroads | CR-S30-07 | Pole replacement | P3 within 10 days | 2026-06-03 | 2026-06-11 | 2026-06-11 | Internal line |  | 1485.71 | Completed | No
WO-26-005945 | 14.5 | Crossroads | CR-S19-03 | Pole replacement | P4 planned | 2026-06-03 | 2026-07-02 | 2026-07-02 | Internal line |  | 2595.79 | Completed | No
WO-26-005946 | 7 | Crossroads | CR-S05-02 | Preventive maintenance | P4 planned | 2026-06-03 | 2026-06-15 | 2026-06-15 | Internal line |  | 571.11 | Completed | No
WO-26-005947 | 5.6 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-06-03 | 2026-07-04 | 2026-07-04 | Underground crew |  | 144.02 | Completed | No
WO-26-005948 | 4.3 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-06-03 | 2026-07-28 | 2026-07-28 | Underground crew |  | 156.93 | Completed | No
WO-26-005949 | 6.3 | Crossroads | CR-S30-03 | Preventive maintenance | P4 planned | 2026-06-03 | 2026-07-18 | 2026-07-19 | Contract line | CT-01 | 580.25 | Completed | No
WO-26-005950 | 1.5 | Crossroads | CR-S16-03 | Service order - field | P2 same day | 2026-06-03 | 2026-06-04 | 2026-06-04 | Meter technician |  | 31.84 | Completed | No
WO-26-005951 | 1.6 | Crossroads | CR-S06-02 | Service order - field | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Meter technician |  | 4.17 | Completed | No
WO-26-005952 | 1.5 | Crossroads | CR-S04-06 | Service order - field | P3 within 10 days | 2026-06-03 | 2026-06-09 | 2026-06-09 | Meter technician |  | 23.47 | Completed | No
WO-26-005953 | 1.7 | Crossroads | CR-S05-01 | Service order - field | P2 same day | 2026-06-03 | 2026-06-03 | 2026-06-03 | Meter technician |  | 36.23 | Completed | No
WO-26-005954 | 0.9 | Crossroads | CR-S20-01 | Service order - field | P3 within 10 days | 2026-06-03 | 2026-06-05 | 2026-06-05 | Meter technician |  | 39.56 | Completed | No
WO-26-005955 | 1 | Crossroads | CR-S02-02 | Service order - field | P3 within 10 days | 2026-06-03 | 2026-06-10 | 2026-06-14 | Meter technician |  | 25.55 | Completed | No
WO-26-005956 | 2.6 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-03 | 2026-06-08 | 2026-06-09 | Contract line | CT-01 | 84.87 | Completed | No
WO-26-005957 | 1.4 | Crossroads |  | Streetlight | P4 planned | 2026-06-03 | 2026-06-18 | 2026-06-22 | Contract line | CT-01 | 241.38 | Completed | No
WO-26-005958 | 1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-03 | 2026-06-05 | 2026-06-06 | Contract line | CT-01 | 231.54 | Completed | No
WO-26-005959 | 4.3 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 316.24 | Completed | No
WO-26-005960 | 5.8 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 183.43 | Completed | No
WO-26-005961 | 2.3 | Crossroads | CR-S05-01 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Troubleman |  | 203.26 | Completed | No
WO-26-005962 | 3.3 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-06-03 | 2026-06-03 | 2026-06-03 | Internal line |  | 100.16 | Completed | No
WO-26-005963 | 2.3 | Crossroads | CR-S28-02 | Trouble - partial or voltage | P2 same day | 2026-06-03 | 2026-06-04 | 2026-06-04 | Internal line |  | 220.26 | Completed | No
WO-26-005964 | 10.2 | Bayou | BY-S04-02 | Corrective maintenance | P4 planned | 2026-06-04 | 2026-07-22 | 2026-07-22 | Internal line |  | 1207.41 | Completed | No
WO-26-005965 | 0.6 | Bayou | BY-S19-02 | Meter exchange | P4 planned | 2026-06-04 | 2026-06-19 | 2026-06-19 | Meter technician |  | 166.42 | Completed | No
WO-26-005966 | 5.2 | Bayou | BY-S07-06 | New service - small | P4 planned | 2026-06-04 | 2026-06-23 | 2026-07-01 | Underground crew |  | 2441.61 | Completed | No
WO-26-005967 | 5.5 | Bayou | BY-S20-03 | Preventive maintenance | P4 planned | 2026-06-04 | 2026-06-28 | 2026-06-28 | Contract line | CT-04 | 357.67 | Completed | No
WO-26-005968 | 4 | Bayou | BY-S03-01 | Preventive maintenance | P4 planned | 2026-06-04 | 2026-06-30 | 2026-07-04 | Internal line |  | 82.28 | Completed | No
WO-26-005969 | 0.6 | Bayou | BY-S08-02 | Service order - field | P2 same day | 2026-06-04 | 2026-06-04 | 2026-06-04 | Meter technician |  | 9.31 | Completed | No
WO-26-005970 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-04 | 2026-06-07 | 2026-06-08 | Contract line | CT-03 | 99.27 | Completed | No
WO-26-005971 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-04 | 2026-06-05 | 2026-06-05 | Contract line | CT-04 | 409.48 | Completed | No
WO-26-005972 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-04 | 2026-06-05 | 2026-06-06 | Contract line | CT-03 | 162.2 | Completed | No
WO-26-005973 | 4.5 | Bayou | BY-S08-01 | Trouble - no power | P2 same day | 2026-06-04 | 2026-06-04 | 2026-06-04 | Troubleman |  | 182.41 | Completed | No
WO-26-005974 | 2.8 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-06-04 | 2026-06-04 | 2026-06-04 | Internal line |  | 184.53 | Completed | No
WO-26-005975 | 3.8 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-06-04 | 2026-06-04 | 2026-06-04 | Troubleman |  | 85.4 | Completed | No
WO-26-005976 |  | Bayou | BY-S29-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-04 | 2026-06-11 |  | Troubleman |  |  | Cancelled | No
WO-26-005977 |  | Bayou | BY-S21-02 | Trouble - partial or voltage | P2 same day | 2026-06-04 | 2026-06-04 |  | Troubleman |  |  | Cancelled | No
WO-26-005978 | 6.4 | Crossroads | CR-S25-05 | Corrective maintenance | P4 planned | 2026-06-04 | 2026-07-06 | 2026-07-14 | Internal line |  | 983.9 | Completed | No
WO-26-005979 | 8.7 | Crossroads | CR-S29-02 | Corrective maintenance | P2 same day | 2026-06-04 | 2026-06-04 | 2026-06-04 | Contract line | CT-01 | 1704.28 | Completed | No
WO-26-005980 | 3.8 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-06-04 | 2026-06-13 | 2026-06-13 | Contract line | CT-02 | 2169.92 | Completed | No
WO-26-005981 | 8.4 | Crossroads | CR-S29-03 | Corrective maintenance | P4 planned | 2026-06-04 | 2026-06-19 | 2026-06-20 | Underground crew |  | 438.71 | Completed | No
WO-26-005982 | 8.5 | Crossroads | CR-S10-02 | Corrective maintenance | P3 within 10 days | 2026-06-04 | 2026-06-10 | 2026-06-10 | Underground crew |  | 97.4 | Completed | No
WO-26-005983 | 6.1 | Crossroads | CR-S16-04 | Corrective maintenance | P3 within 10 days | 2026-06-04 | 2026-06-09 | 2026-06-13 | Underground crew |  | 1250.33 | Completed | No
WO-26-005984 | 6.2 | Crossroads | CR-S13-05 | Corrective maintenance | P3 within 10 days | 2026-06-04 | 2026-06-11 | 2026-06-11 | Underground crew |  | 1359.73 | Completed | No
WO-26-005985 |  | Crossroads | CR-S18-06 | Corrective maintenance | P3 within 10 days | 2026-06-04 | 2026-06-06 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-005986 | 0.7 | Crossroads | CR-S13-06 | Meter exchange | P3 within 10 days | 2026-06-04 | 2026-06-07 | 2026-06-07 | Meter technician |  | 60.5 | Completed | No
WO-26-005987 | 0.9 | Crossroads | CR-S10-03 | Meter exchange | P4 planned | 2026-06-04 | 2026-07-01 | 2026-07-05 | Meter technician |  | 167.7 | Completed | No
WO-26-005988 | 21 | Crossroads | CR-S16-02 | Pole replacement | P4 planned | 2026-06-04 | 2026-07-06 | 2026-07-07 | Contract line | CT-01 | 2640.3 | Completed | No
WO-26-005989 | 5.5 | Crossroads | CR-S30-04 | Preventive maintenance | P4 planned | 2026-06-04 | 2026-07-25 | 2026-07-25 | Underground crew |  | 152.15 | Completed | No
WO-26-005990 | 0.6 | Crossroads | CR-S05-05 | Service order - field | P2 same day | 2026-06-04 | 2026-06-05 | 2026-06-05 | Meter technician |  | 19.7 | Completed | No
WO-26-005991 | 1.8 | Crossroads | CR-S25-05 | Service order - field | P2 same day | 2026-06-04 | 2026-06-05 | 2026-06-05 | Meter technician |  | 26.47 | Completed | No
WO-26-005992 | 1.6 | Crossroads | CR-S18-05 | Service order - field | P2 same day | 2026-06-04 | 2026-06-05 | 2026-06-05 | Meter technician |  | 4.53 | Completed | No
WO-26-005993 | 1.6 | Crossroads | CR-S30-03 | Service order - field | P3 within 10 days | 2026-06-04 | 2026-06-10 | 2026-06-10 | Meter technician |  | 17.93 | Completed | No
WO-26-005994 | 0.9 | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-06-04 | 2026-06-04 | 2026-06-04 | Meter technician |  | 26.56 | Completed | No
WO-26-005995 | 11.7 | Crossroads | CR-S01-01 | Transformer replacement | P2 same day | 2026-06-04 | 2026-06-05 | 2026-06-05 | Internal line |  | 9649.68 | Completed | No
WO-26-005996 | 4.6 | Crossroads | CR-S25-05 | Trouble - no power | P1 emergency | 2026-06-04 | 2026-06-04 | 2026-06-04 | Troubleman |  | 303.77 | Completed | No
WO-26-005997 | 2.9 | Crossroads | CR-S28-04 | Trouble - no power | P1 emergency | 2026-06-04 | 2026-06-04 | 2026-06-04 | Troubleman |  | 155.81 | Completed | No
WO-26-005998 | 4.8 | Crossroads | CR-S23-02 | Trouble - partial or voltage | P2 same day | 2026-06-04 | 2026-06-05 | 2026-06-05 | Troubleman |  | 7.43 | Completed | No
WO-26-005999 | 3.9 | Crossroads | CR-S23-05 | Trouble - partial or voltage | P3 within 10 days | 2026-06-04 | 2026-06-06 | 2026-06-06 | Troubleman |  | 107.17 | Completed | No
WO-26-006000 | 8.7 | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-06-05 | 2026-06-07 | 2026-06-07 | Internal line |  | 770.32 | Completed | No
WO-26-006001 | 6.6 | Bayou | BY-S01-02 | Corrective maintenance | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Underground crew |  | 1824.85 | Completed | No
WO-26-006002 | 0.7 | Bayou | BY-S15-02 | Meter exchange | P3 within 10 days | 2026-06-05 | 2026-06-07 | 2026-06-07 | Meter technician |  | 141.2 | Completed | No
WO-26-006003 | 0.7 | Bayou | BY-S22-04 | Meter exchange | P3 within 10 days | 2026-06-05 | 2026-06-13 | 2026-06-14 | Meter technician |  | 175.92 | Completed | No
WO-26-006004 | 1.5 | Bayou | BY-S21-01 | Meter exchange | P4 planned | 2026-06-05 | 2026-08-02 | 2026-08-10 | Meter technician |  | 141.37 | Completed | No
WO-26-006005 | 1.5 | Bayou | BY-S08-03 | Meter exchange | P3 within 10 days | 2026-06-05 | 2026-06-06 | 2026-06-06 | Meter technician |  | 93.56 | Completed | No
WO-26-006006 | 0.8 | Bayou | BY-S16-04 | Meter exchange | P3 within 10 days | 2026-06-05 | 2026-06-15 | 2026-06-15 | Meter technician |  | 157.55 | Completed | No
WO-26-006007 | 15.3 | Bayou | BY-S27-06 | New service - small | P4 planned | 2026-06-05 | 2026-07-16 | 2026-07-17 | Contract line | CT-04 | 3507.26 | Completed | No
WO-26-006008 |  | Bayou | BY-S15-01 | New service - small | P4 planned | 2026-06-05 | 2026-07-17 |  | Underground crew |  |  | Cancelled | No
WO-26-006009 | 6.2 | Bayou | BY-S22-01 | Preventive maintenance | P4 planned | 2026-06-05 | 2026-07-11 | 2026-07-12 | Contract line | CT-03 | 214.53 | Completed | No
WO-26-006010 | 4.9 | Bayou | BY-S20-02 | Preventive maintenance | P4 planned | 2026-06-05 | 2026-06-26 | 2026-06-30 | Internal line |  | 129.2 | Completed | No
WO-26-006011 | 0.9 | Bayou | BY-S01-01 | Service order - field | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Meter technician |  | 27.32 | Completed | No
WO-26-006012 | 0.7 | Bayou | BY-S22-04 | Service order - field | P3 within 10 days | 2026-06-05 | 2026-06-12 | 2026-06-12 | Meter technician |  | 35.3 | Completed | No
WO-26-006013 | 0.7 | Bayou | BY-S25-01 | Service order - field | P2 same day | 2026-06-05 | 2026-06-05 | 2026-06-05 | Meter technician |  | 17.52 | Completed | No
WO-26-006014 | 0.7 | Bayou | BY-S15-05 | Service order - field | P3 within 10 days | 2026-06-05 | 2026-06-08 | 2026-06-12 | Meter technician |  | 31.28 | Completed | No
WO-26-006015 | 1.2 | Bayou |  | Streetlight | P4 planned | 2026-06-05 | 2026-07-20 | 2026-07-21 | Contract line | CT-04 | 428.73 | Completed | No
WO-26-006016 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-05 | 2026-06-06 | 2026-06-08 | Contract line | CT-04 | 387.25 | Completed | No
WO-26-006017 | 6.7 | Bayou | BY-S22-03 | Transformer replacement | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Internal line |  | 6980.61 | Completed | No
WO-26-006018 | 13 | Bayou | BY-S26-06 | Transformer replacement | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Contract line | CT-04 | 6167.56 | Completed | No
WO-26-006019 | 2.7 | Bayou | BY-S12-02 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Internal line |  | 325.34 | Completed | No
WO-26-006020 | 2.7 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Troubleman |  | 336.33 | Completed | No
WO-26-006021 | 2.1 | Bayou | BY-S16-02 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Troubleman |  | 258.65 | Completed | No
WO-26-006022 | 3 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Troubleman |  | 109.28 | Completed | No
WO-26-006023 | 4.9 | Bayou | BY-S25-02 | Trouble - no power | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Troubleman |  | 248.12 | Completed | No
WO-26-006024 | 3.5 | Bayou | BY-S16-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-05 | 2026-06-15 | 2026-06-15 | Troubleman |  | 49.46 | Completed | No
WO-26-006025 | 1.6 | Bayou | BY-S15-06 | Trouble - partial or voltage | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Troubleman |  | 155.33 | Completed | No
WO-26-006026 | 5 | Bayou | BY-S17-04 | Trouble - partial or voltage | P3 within 10 days | 2026-06-05 | 2026-06-15 | 2026-06-15 | Troubleman |  | 31.67 | Completed | No
WO-26-006027 | 2.7 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Troubleman |  | 204.11 | Completed | No
WO-26-006028 | 1.6 | Bayou | BY-S10-01 | Trouble - partial or voltage | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Troubleman |  | 210.08 | Completed | No
WO-26-006029 | 6.5 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-06-05 | 2026-06-05 | 2026-06-05 | Contract line | CT-02 | 1919.71 | Completed | No
WO-26-006030 | 11.6 | Crossroads | CR-S18-01 | Corrective maintenance | P3 within 10 days | 2026-06-05 | 2026-06-10 | 2026-06-14 | Internal line |  | 2187.81 | Completed | No
WO-26-006031 | 9.2 | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-06-05 | 2026-06-11 | 2026-06-12 | Internal line |  | 880.17 | Completed | No
WO-26-006032 | 0.9 | Crossroads | CR-S30-06 | Meter exchange | P3 within 10 days | 2026-06-05 | 2026-06-14 | 2026-06-18 | Meter technician |  | 135.17 | Completed | No
WO-26-006033 | 0.6 | Crossroads | CR-S20-04 | Meter exchange | P4 planned | 2026-06-05 | 2026-07-10 | 2026-07-10 | Meter technician |  | 161.07 | Completed | No
WO-26-006034 | 1.1 | Crossroads | CR-S04-05 | Meter exchange | P3 within 10 days | 2026-06-05 | 2026-06-06 | 2026-06-08 | Meter technician |  | 81.12 | Completed | No
WO-26-006035 | 6.8 | Crossroads | CR-S09-03 | New service - small | P4 planned | 2026-06-05 | 2026-06-23 | 2026-07-01 | Contract line | CT-02 | 2516.71 | Completed | No
WO-26-006036 | 10.9 | Crossroads | CR-S07-07 | New service - small | P3 within 10 days | 2026-06-05 | 2026-06-07 | 2026-06-09 | Underground crew |  | 3806.56 | Completed | No
WO-26-006037 | 20.3 | Crossroads | CR-S11-01 | Pole replacement | P3 within 10 days | 2026-06-05 | 2026-06-13 | 2026-06-13 | Contract line | CT-01 | 2441.21 | Completed | No
WO-26-006038 | 6.9 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-06-05 | 2026-06-27 | 2026-06-28 | Underground crew |  | 214.11 | Completed | No
WO-26-006039 | 0.8 | Crossroads | CR-S09-03 | Service order - field | P3 within 10 days | 2026-06-05 | 2026-06-09 | 2026-06-13 | Meter technician |  | 25.48 | Completed | No
WO-26-006040 | 1.8 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-06-05 | 2026-06-06 | 2026-06-06 | Meter technician |  | 7.13 | Completed | No
WO-26-006041 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-05 | 2026-06-15 | 2026-06-15 | Contract line | CT-01 | 298.91 | Completed | No
WO-26-006042 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-05 | 2026-06-10 | 2026-06-14 | Contract line | CT-02 | 390.85 | Completed | No
WO-26-006043 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-05 | 2026-06-13 | 2026-06-13 | Contract line | CT-01 | 180.39 | Completed | No
WO-26-006044 | 2.2 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Internal line |  | 304.41 | Completed | No
WO-26-006045 | 5.5 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Troubleman |  | 142.22 | Completed | No
WO-26-006046 | 3.9 | Crossroads | CR-S32-02 | Trouble - no power | P2 same day | 2026-06-05 | 2026-06-05 | 2026-06-05 | Troubleman |  | 234.54 | Completed | No
WO-26-006047 | 2.7 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Troubleman |  | 315.61 | Completed | No
WO-26-006048 | 3.9 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-06-05 | 2026-06-05 | 2026-06-05 | Internal line |  | 315.64 | Completed | No
WO-26-006049 | 1.8 | Bayou | BY-S16-02 | Service order - field | P2 same day | 2026-06-06 | 2026-06-07 | 2026-06-07 | Meter technician |  | 23.63 | Completed | No
WO-26-006050 | 1.8 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Meter technician |  | 16.2 | Completed | No
WO-26-006051 | 1.3 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Meter technician |  | 25.23 | Completed | No
WO-26-006052 | 4.1 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 291.98 | Completed | No
WO-26-006053 | 3.7 | Bayou | BY-S10-03 | Trouble - partial or voltage | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 174.71 | Completed | No
WO-26-006054 | 4.3 | Bayou | BY-S09-01 | Trouble - partial or voltage | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 19.24 | Completed | No
WO-26-006055 | 3.6 | Bayou | BY-S19-02 | Trouble - partial or voltage | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 87.45 | Completed | No
WO-26-006056 | 1.6 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Meter technician |  | 27.63 | Completed | No
WO-26-006057 | 6.3 | Crossroads | CR-S28-04 | Transformer replacement | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Internal line |  | 11489.01 | Completed | No
WO-26-006058 | 13.1 | Crossroads | CR-S30-04 | Transformer replacement | P1 emergency | 2026-06-06 | 2026-06-06 | 2026-06-06 | Internal line |  | 11860.27 | Completed | No
WO-26-006059 | 2.7 | Crossroads | CR-S14-01 | Trouble - no power | P2 same day | 2026-06-06 | 2026-06-07 | 2026-06-07 | Troubleman |  | 9.82 | Completed | No
WO-26-006060 | 3 | Crossroads | CR-S21-01 | Trouble - no power | P2 same day | 2026-06-06 | 2026-06-07 | 2026-06-07 | Troubleman |  | 230.29 | Completed | No
WO-26-006061 | 4.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 228.78 | Completed | No
WO-26-006062 | 5.2 | Crossroads | CR-S08-06 | Trouble - no power | P2 same day | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 78.53 | Completed | No
WO-26-006063 | 3.3 | Crossroads | CR-S07-02 | Trouble - no power | P1 emergency | 2026-06-06 | 2026-06-06 | 2026-06-06 | Internal line |  | 15.62 | Completed | No
WO-26-006064 | 3.7 | Crossroads | CR-S26-03 | Trouble - no power | P1 emergency | 2026-06-06 | 2026-06-06 | 2026-06-06 | Troubleman |  | 125.92 | Completed | No
WO-26-006065 | 4.8 | Crossroads | CR-S20-03 | Trouble - partial or voltage | P2 same day | 2026-06-06 | 2026-06-07 | 2026-06-07 | Troubleman |  | 19.6 | Completed | No
WO-26-006066 | 1 | Bayou | BY-S15-04 | Service order - field | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Meter technician |  | 14.59 | Completed | No
WO-26-006067 | 1.9 | Bayou | BY-S15-06 | Service order - field | P2 same day | 2026-06-07 | 2026-06-07 | 2026-06-07 | Meter technician |  | 1.06 | Completed | No
WO-26-006068 | 0.8 | Bayou | BY-S27-06 | Service order - field | P2 same day | 2026-06-07 | 2026-06-07 | 2026-06-07 | Meter technician |  | 24.72 | Completed | No
WO-26-006069 | 8.2 | Bayou | BY-S12-02 | Transformer replacement | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Internal line |  | 6203.49 | Completed | No
WO-26-006070 | 7.2 | Bayou | BY-S16-01 | Transformer replacement | P2 same day | 2026-06-07 | 2026-06-07 | 2026-06-07 | Internal line |  | 8809.66 | Completed | No
WO-26-006071 | 9.3 | Bayou | BY-S23-01 | Transformer replacement | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Internal line |  | 3437.58 | Completed | No
WO-26-006072 | 5.3 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Internal line |  | 278.33 | Completed | No
WO-26-006073 | 5.9 | Bayou | BY-S15-05 | Trouble - no power | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Troubleman |  | 64.24 | Completed | No
WO-26-006074 | 3.4 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Troubleman |  | 148.59 | Completed | No
WO-26-006075 | 1.9 | Bayou | BY-S19-04 | Trouble - partial or voltage | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Internal line |  | 232.5 | Completed | No
WO-26-006076 | 4.9 | Bayou | BY-S12-02 | Trouble - partial or voltage | P2 same day | 2026-06-07 | 2026-06-07 | 2026-06-07 | Troubleman |  | 25.56 | Completed | No
WO-26-006077 | 1.2 | Crossroads | CR-S14-01 | Service order - field | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Meter technician |  | 5.37 | Completed | No
WO-26-006078 | 0.6 | Crossroads | CR-S32-03 | Service order - field | P2 same day | 2026-06-07 | 2026-06-08 | 2026-06-08 | Meter technician |  | 39.47 | Completed | No
WO-26-006079 | 8.6 | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Internal line |  | 4774.3 | Completed | No
WO-26-006080 | 3.1 | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Troubleman |  | 331.12 | Completed | No
WO-26-006081 | 2.3 | Crossroads | CR-S30-02 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Troubleman |  | 84.28 | Completed | No
WO-26-006082 | 2.2 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Internal line |  | 233.94 | Completed | No
WO-26-006083 | 2.5 | Crossroads | CR-S07-01 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Internal line |  | 349.79 | Completed | No
WO-26-006084 | 2.6 | Crossroads | CR-S16-01 | Trouble - no power | P1 emergency | 2026-06-07 | 2026-06-07 | 2026-06-07 | Internal line |  | 346.67 | Completed | No
WO-26-006085 | 6.2 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-06-08 | 2026-06-16 | 2026-06-16 | Internal line |  | 873.89 | Completed | No
WO-26-006086 | 5.1 | Bayou | BY-S24-01 | Corrective maintenance | P4 planned | 2026-06-08 | 2026-07-07 | 2026-07-11 | Internal line |  | 310.46 | Completed | No
WO-26-006087 | 7.7 | Bayou | BY-S16-04 | Corrective maintenance | P2 same day | 2026-06-08 | 2026-06-08 | 2026-06-08 | Contract line | CT-04 | 1211.63 | Completed | No
WO-26-006088 | 1.4 | Bayou | BY-S10-05 | Meter exchange | P4 planned | 2026-06-08 | 2026-07-27 | 2026-07-27 | Meter technician |  | 110.8 | Completed | No
WO-26-006089 | 1.4 | Bayou | BY-S29-02 | Meter exchange | P4 planned | 2026-06-08 | 2026-06-19 | 2026-06-19 | Meter technician |  | 134.72 | Completed | No
WO-26-006090 | 1.2 | Bayou | BY-S04-02 | Meter exchange | P3 within 10 days | 2026-06-08 | 2026-06-12 | 2026-06-12 | Meter technician |  | 121.23 | Completed | No
WO-26-006091 | 1.3 | Bayou | BY-S06-02 | Meter exchange | P3 within 10 days | 2026-06-08 | 2026-06-13 | 2026-06-13 | Meter technician |  | 127.38 | Completed | No
WO-26-006092 | 1.5 | Bayou | BY-S26-02 | Meter exchange | P4 planned | 2026-06-08 | 2026-06-28 | 2026-06-29 | Meter technician |  | 143.65 | Completed | No
WO-26-006093 | 0.6 | Bayou | BY-S15-06 | Meter exchange | P4 planned | 2026-06-08 | 2026-06-23 | 2026-06-25 | Meter technician |  | 135.55 | Completed | No
WO-26-006094 | 9.3 | Bayou | BY-S03-01 | New service - small | P4 planned | 2026-06-08 | 2026-07-05 | 2026-07-13 | Contract line | CT-03 | 2823.96 | Completed | No
WO-26-006095 | 4.8 | Bayou | BY-S11-03 | New service - small | P4 planned | 2026-06-08 | 2026-06-29 | 2026-06-29 | Contract line | CT-04 | 2094.38 | Completed | No
WO-26-006096 | 13.8 | Bayou | BY-S15-01 | New service - small | P4 planned | 2026-06-08 | 2026-07-27 | 2026-07-27 | Contract line | CT-04 | 2384.03 | Completed | No
WO-26-006097 |  | Bayou | BY-S07-01 | Pole replacement | P4 planned | 2026-06-08 | 2026-06-30 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-006098 | 3.8 | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-02 | 2026-07-06 | Underground crew |  | 38.31 | Completed | No
WO-26-006099 | 3 | Bayou | BY-S23-04 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-19 | 2026-07-21 | Internal line |  | 526.01 | Completed | No
WO-26-006100 | 6.1 | Bayou | BY-S25-03 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-20 | 2026-07-20 | Internal line |  | 108.07 | Completed | No
WO-26-006101 | 7 | Bayou | BY-S06-01 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-31 | 2026-08-01 | Contract line | CT-04 | 171.98 | Completed | No
WO-26-006102 | 1 | Bayou | BY-S17-02 | Service order - field | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Meter technician |  | 5.11 | Completed | No
WO-26-006103 | 1.7 | Bayou | BY-S14-01 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-16 | 2026-06-24 | Meter technician |  | 25.38 | Completed | No
WO-26-006104 | 0.6 | Bayou | BY-S13-06 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-11 | 2026-06-11 | Meter technician |  | 19.6 | Completed | No
WO-26-006105 | 1 | Bayou | BY-S29-03 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-12 | 2026-06-20 | Meter technician |  | 22.42 | Completed | No
WO-26-006106 | 1.3 | Bayou |  | Streetlight | P4 planned | 2026-06-08 | 2026-07-13 | 2026-07-13 | Contract line | CT-04 | 45.51 | Completed | No
WO-26-006107 | 10.8 | Bayou | BY-S26-01 | Transformer replacement | P2 same day | 2026-06-08 | 2026-06-08 | 2026-06-08 | Internal line |  | 6497.64 | Completed | No
WO-26-006108 | 5.6 | Bayou | BY-S15-06 | Trouble - no power | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Troubleman |  | 63.81 | Completed | No
WO-26-006109 | 5.4 | Bayou | BY-S29-02 | Trouble - no power | P2 same day | 2026-06-08 | 2026-06-08 | 2026-06-08 | Internal line |  | 193.21 | Completed | No
WO-26-006110 | 4.5 | Bayou | BY-S25-04 | Trouble - no power | P1 emergency | 2026-06-08 | 2026-06-08 | 2026-06-08 | Internal line |  | 152.7 | Completed | No
WO-26-006111 | 4.8 | Bayou | BY-S20-02 | Trouble - no power | P1 emergency | 2026-06-08 | 2026-06-08 | 2026-06-08 | Troubleman |  | 231.95 | Completed | No
WO-26-006112 | 4.1 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-06-08 | 2026-06-08 | 2026-06-08 | Troubleman |  | 300.92 | Completed | No
WO-26-006113 | 3 | Bayou | BY-S15-04 | Trouble - partial or voltage | P3 within 10 days | 2026-06-08 | 2026-06-12 | 2026-06-20 | Troubleman |  | 220.79 | Completed | No
WO-26-006114 | 2.9 | Bayou | BY-S29-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-08 | 2026-06-16 | 2026-06-16 | Troubleman |  | 238.92 | Completed | No
WO-26-006115 | 1.6 | Bayou | BY-S15-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-08 | 2026-06-16 | 2026-06-18 | Troubleman |  | 186.17 | Completed | No
WO-26-006116 | 2.2 | Bayou | BY-S21-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-08 | 2026-06-18 | 2026-06-19 | Troubleman |  | 106.2 | Completed | No
WO-26-006117 | 3.4 | Bayou | BY-S12-03 | Trouble - partial or voltage | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Internal line |  | 158.87 | Completed | No
WO-26-006118 | 2 | Bayou | BY-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-06-08 | 2026-06-09 | 2026-06-11 | Troubleman |  | 177.17 | Completed | No
WO-26-006119 | 9.8 | Crossroads | CR-S01-03 | Corrective maintenance | P2 same day | 2026-06-08 | 2026-06-08 | 2026-06-08 | Internal line |  | 1320.4 | Completed | No
WO-26-006120 | 9 | Crossroads | CR-S05-06 | Corrective maintenance | P3 within 10 days | 2026-06-08 | 2026-06-12 | 2026-06-20 | Underground crew |  | 384.63 | Completed | No
WO-26-006121 | 6.7 | Crossroads | CR-S32-01 | Corrective maintenance | P2 same day | 2026-06-08 | 2026-06-08 | 2026-06-08 | Contract line | CT-01 | 1460.58 | Completed | No
WO-26-006122 | 1.2 | Crossroads | CR-S25-01 | Meter exchange | P4 planned | 2026-06-08 | 2026-07-01 | 2026-07-05 | Meter technician |  | 93.65 | Completed | No
WO-26-006123 | 1.2 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-06-08 | 2026-06-18 | 2026-06-19 | Meter technician |  | 93.57 | Completed | No
WO-26-006124 | 4.4 | Crossroads | CR-S03-02 | New service - small | P3 within 10 days | 2026-06-08 | 2026-06-16 | 2026-06-17 | Underground crew |  | 3991.99 | Completed | No
WO-26-006125 | 15.7 | Crossroads | CR-S18-01 | New service - small | P4 planned | 2026-06-08 | 2026-07-29 | 2026-07-29 | Contract line | CT-02 | 3924.89 | Completed | No
WO-26-006126 | 11.1 | Crossroads | CR-S26-02 | Pole replacement | P3 within 10 days | 2026-06-08 | 2026-06-09 | 2026-06-09 | Internal line |  | 1459.24 | Completed | No
WO-26-006127 | 4.3 | Crossroads | CR-S17-03 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-31 | 2026-07-31 | Underground crew |  | 289.43 | Completed | No
WO-26-006128 | 6.3 | Crossroads | CR-S06-03 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-08 | 2026-07-10 | Internal line |  | 99.84 | Completed | No
WO-26-006129 | 7.8 | Crossroads | CR-S05-02 | Preventive maintenance | P4 planned | 2026-06-08 | 2026-07-08 | 2026-07-08 | Internal line |  | 545.05 | Completed | No
WO-26-006130 | 1.8 | Crossroads | CR-S22-01 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-13 | 2026-06-13 | Meter technician |  | 12.36 | Completed | No
WO-26-006131 | 1.4 | Crossroads | CR-S23-05 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-12 | 2026-06-12 | Meter technician |  | 3.73 | Completed | No
WO-26-006132 | 0.5 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-11 | 2026-06-15 | Meter technician |  | 30.56 | Completed | No
WO-26-006133 | 1.5 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Meter technician |  | 6.43 | Completed | No
WO-26-006134 | 1.5 | Crossroads | CR-S03-02 | Service order - field | P3 within 10 days | 2026-06-08 | 2026-06-12 | 2026-06-12 | Meter technician |  | 39.93 | Completed | No
WO-26-006135 | 1.8 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-06-08 | 2026-06-08 | 2026-06-08 | Meter technician |  | 12.33 | Completed | No
WO-26-006136 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-08 | 2026-06-15 | 2026-06-16 | Internal line |  | 197.86 | Completed | No
WO-26-006137 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-08 | 2026-06-14 | 2026-06-22 | Internal line |  | 259.98 | Completed | No
WO-26-006138 | 11.3 | Crossroads | CR-S07-07 | Transformer replacement | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Contract line | CT-02 | 3345.1 | Completed | No
WO-26-006139 | 12.5 | Crossroads | CR-S25-02 | Transformer replacement | P1 emergency | 2026-06-08 | 2026-06-08 | 2026-06-08 | Internal line |  | 10869.95 | Completed | No
WO-26-006140 | 2.8 | Crossroads | CR-S30-02 | Trouble - no power | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Troubleman |  | 46.75 | Completed | No
WO-26-006141 | 2.5 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-06-08 | 2026-06-08 | 2026-06-08 | Troubleman |  | 313.5 | Completed | No
WO-26-006142 | 4 | Crossroads | CR-S23-02 | Trouble - partial or voltage | P2 same day | 2026-06-08 | 2026-06-09 | 2026-06-09 | Troubleman |  | 182.12 | Completed | No
WO-26-006143 | 5.2 | Bayou | BY-S26-06 | Corrective maintenance | P4 planned | 2026-06-09 | 2026-07-27 | 2026-07-28 | Contract line | CT-03 | 201.01 | Completed | No
WO-26-006144 | 0.6 | Bayou | BY-S03-03 | Meter exchange | P3 within 10 days | 2026-06-09 | 2026-06-16 | 2026-06-16 | Meter technician |  | 135.59 | Completed | No
WO-26-006145 | 1.3 | Bayou | BY-S26-02 | Meter exchange | P4 planned | 2026-06-09 | 2026-07-11 | 2026-07-11 | Meter technician |  | 135.61 | Completed | No
WO-26-006146 | 0.7 | Bayou | BY-S30-02 | Meter exchange | P3 within 10 days | 2026-06-09 | 2026-06-13 | 2026-06-15 | Meter technician |  | 173.76 | Completed | No
WO-26-006147 | 1 | Bayou | BY-S18-05 | Meter exchange | P3 within 10 days | 2026-06-09 | 2026-06-16 | 2026-06-18 | Meter technician |  | 91.7 | Completed | No
WO-26-006148 | 0.9 | Bayou | BY-S30-01 | Meter exchange | P4 planned | 2026-06-09 | 2026-07-24 | 2026-08-01 | Meter technician |  | 156.68 | Completed | No
WO-26-006149 | 5.7 | Bayou | BY-S29-04 | New service - small | P4 planned | 2026-06-09 | 2026-07-28 | 2026-08-01 | Internal line |  | 4076.62 | Completed | No
WO-26-006150 | 16.1 | Bayou | BY-S10-05 | Pole replacement | P3 within 10 days | 2026-06-09 | 2026-06-14 | 2026-06-14 | Internal line |  | 2424.2 | Completed | No
WO-26-006151 | 3.4 | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-06-09 | 2026-06-18 | 2026-06-19 | Internal line |  | 153.13 | Completed | No
WO-26-006152 | 7.9 | Bayou | BY-S29-04 | Preventive maintenance | P4 planned | 2026-06-09 | 2026-07-16 | 2026-07-16 | Contract line | CT-04 | 354.77 | Completed | No
WO-26-006153 | 0.8 | Bayou | BY-S22-03 | Service order - field | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Meter technician |  | 14.55 | Completed | No
WO-26-006154 | 1.3 | Bayou | BY-S06-03 | Service order - field | P2 same day | 2026-06-09 | 2026-06-10 | 2026-06-10 | Meter technician |  | 23.21 | Completed | No
WO-26-006155 | 0.6 | Bayou | BY-S29-04 | Service order - field | P3 within 10 days | 2026-06-09 | 2026-06-17 | 2026-06-19 | Meter technician |  | 26.45 | Completed | No
WO-26-006156 | 1.6 | Bayou | BY-S19-04 | Service order - field | P3 within 10 days | 2026-06-09 | 2026-06-17 | 2026-06-17 | Meter technician |  | 3.25 | Completed | No
WO-26-006157 | 1.3 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Meter technician |  | 36.91 | Completed | No
WO-26-006158 | 1.5 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-06-09 | 2026-06-10 | 2026-06-10 | Meter technician |  | 10.86 | Completed | No
WO-26-006159 | 1.9 | Bayou | BY-S25-04 | Service order - field | P3 within 10 days | 2026-06-09 | 2026-06-10 | 2026-06-12 | Meter technician |  | 9.21 | Completed | No
WO-26-006160 | 12.1 | Bayou | BY-S24-03 | Transformer replacement | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Contract line | CT-04 | 9032.59 | Completed | No
WO-26-006161 | 3.3 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 45.89 | Completed | No
WO-26-006162 | 3.1 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-06-09 | 2026-06-10 | 2026-06-10 | Troubleman |  | 187.16 | Completed | No
WO-26-006163 | 4.1 | Bayou | BY-S19-01 | Trouble - no power | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 61.91 | Completed | No
WO-26-006164 | 4.4 | Bayou | BY-S18-07 | Trouble - no power | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 71.66 | Completed | No
WO-26-006165 | 4 | Bayou | BY-S29-03 | Trouble - no power | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 22.36 | Completed | No
WO-26-006166 | 2.3 | Bayou | BY-S04-03 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 153.35 | Completed | No
WO-26-006167 | 3.9 | Bayou | BY-S09-02 | Trouble - partial or voltage | P2 same day | 2026-06-09 | 2026-06-10 | 2026-06-10 | Troubleman |  | 187.15 | Completed | No
WO-26-006168 | 4 | Crossroads | CR-S20-02 | Corrective maintenance | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Underground crew |  | 755.66 | Completed | No
WO-26-006169 | 11.8 | Crossroads | CR-S10-03 | Corrective maintenance | P3 within 10 days | 2026-06-09 | 2026-06-18 | 2026-06-18 | Internal line |  | 2369.47 | Completed | No
WO-26-006170 | 0.6 | Crossroads | CR-S30-07 | Meter exchange | P4 planned | 2026-06-09 | 2026-06-23 | 2026-06-23 | Meter technician |  | 77.9 | Completed | No
WO-26-006171 | 0.9 | Crossroads | CR-S10-03 | Meter exchange | P4 planned | 2026-06-09 | 2026-06-20 | 2026-06-20 | Meter technician |  | 136.94 | Completed | No
WO-26-006172 | 1.2 | Crossroads | CR-S14-01 | Meter exchange | P3 within 10 days | 2026-06-09 | 2026-06-16 | 2026-06-16 | Meter technician |  | 95.16 | Completed | No
WO-26-006173 | 1.1 | Crossroads | CR-S02-04 | Meter exchange | P3 within 10 days | 2026-06-09 | 2026-06-19 | 2026-06-23 | Meter technician |  | 127.33 | Completed | No
WO-26-006174 | 15.2 | Crossroads | CR-S30-01 | Pole replacement | P4 planned | 2026-06-09 | 2026-07-01 | 2026-07-02 | Internal line |  | 1410.18 | Completed | No
WO-26-006175 | 6.2 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-06-09 | 2026-07-02 | 2026-07-04 | Internal line |  | 215.74 | Completed | No
WO-26-006176 | 0.5 | Crossroads | CR-S30-05 | Service order - field | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Meter technician |  | 27.01 | Completed | No
WO-26-006177 | 1.1 | Crossroads | CR-S02-01 | Service order - field | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Meter technician |  | 24.3 | Completed | No
WO-26-006178 | 2 | Crossroads | CR-S19-02 | Service order - field | P3 within 10 days | 2026-06-09 | 2026-06-19 | 2026-06-19 | Meter technician |  | 11.88 | Completed | No
WO-26-006179 | 1.5 | Crossroads | CR-S23-05 | Service order - field | P3 within 10 days | 2026-06-09 | 2026-06-19 | 2026-06-19 | Meter technician |  | 21.05 | Completed | No
WO-26-006180 | 0.9 | Crossroads | CR-S02-02 | Service order - field | P2 same day | 2026-06-09 | 2026-06-09 | 2026-06-09 | Meter technician |  | 37.47 | Completed | No
WO-26-006181 | 1 | Crossroads |  | Streetlight | P4 planned | 2026-06-09 | 2026-06-27 | 2026-06-29 | Contract line | CT-02 | 145.22 | Completed | No
WO-26-006182 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-09 | 2026-06-12 | 2026-06-12 | Contract line | CT-01 | 376.23 | Completed | No
WO-26-006183 | 2.2 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 303.09 | Completed | No
WO-26-006184 | 5.5 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 307.81 | Completed | No
WO-26-006185 |  | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 |  | Troubleman |  |  | Cancelled | No
WO-26-006186 | 3.9 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 88.35 | Completed | No
WO-26-006187 | 3.8 | Crossroads | CR-S02-05 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 154.51 | Completed | No
WO-26-006188 | 3.6 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 11.54 | Completed | No
WO-26-006189 | 2.7 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-06-09 | 2026-06-09 | 2026-06-09 | Troubleman |  | 137.63 | Completed | No
WO-26-006190 | 2.4 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-09 | 2026-06-18 | 2026-06-18 | Troubleman |  | 1.88 | Completed | No
WO-26-006191 | 3.5 | Crossroads | CR-S19-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-09 | 2026-06-13 | 2026-06-14 | Internal line |  | 97.25 | Completed | No
WO-26-006192 | 5.4 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-06-10 | 2026-06-17 | 2026-06-17 | Internal line |  | 882.35 | Completed | No
WO-26-006193 | 5.2 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-06-10 | 2026-06-20 | 2026-06-21 | Contract line | CT-03 | 1491.69 | Completed | No
WO-26-006194 | 10.8 | Bayou | BY-S26-01 | Corrective maintenance | P3 within 10 days | 2026-06-10 | 2026-06-18 | 2026-06-22 | Contract line | CT-03 | 1401.92 | Completed | No
WO-26-006195 | 1.2 | Bayou | BY-S29-05 | Meter exchange | P3 within 10 days | 2026-06-10 | 2026-06-18 | 2026-06-19 | Meter technician |  | 67.23 | Completed | No
WO-26-006196 | 0.9 | Bayou | BY-S29-02 | Meter exchange | P3 within 10 days | 2026-06-10 | 2026-06-14 | 2026-06-15 | Meter technician |  | 148.14 | Completed | No
WO-26-006197 | 1.5 | Bayou | BY-S18-06 | Meter exchange | P4 planned | 2026-06-10 | 2026-07-23 | 2026-07-23 | Meter technician |  | 142.25 | Completed | No
WO-26-006198 | 7.3 | Bayou | BY-S07-03 | New service - small | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-15 | Contract line | CT-04 | 4128.93 | Completed | No
WO-26-006199 | 2.8 | Bayou | BY-S28-03 | Preventive maintenance | P4 planned | 2026-06-10 | 2026-07-25 | 2026-08-02 | Internal line |  | 435.4 | Completed | No
WO-26-006200 | 1.7 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Meter technician |  | 11.78 | Completed | No
WO-26-006201 | 0.9 | Bayou | BY-S26-02 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-15 | Meter technician |  | 17.15 | Completed | No
WO-26-006202 | 1.7 | Bayou | BY-S21-03 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-15 | Meter technician |  | 16.67 | Completed | No
WO-26-006203 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-15 | Contract line | CT-04 | 364.23 | Completed | No
WO-26-006204 | 1.5 | Bayou |  | Streetlight | P4 planned | 2026-06-10 | 2026-08-04 | 2026-08-04 | Contract line | CT-03 | 366.19 | Completed | No
WO-26-006205 | 6.7 | Bayou | BY-S20-03 | Transformer replacement | P2 same day | 2026-06-10 | 2026-06-10 | 2026-06-10 | Internal line |  | 9549.76 | Completed | No
WO-26-006206 | 2.2 | Bayou | BY-S17-01 | Trouble - no power | P2 same day | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 62.58 | Completed | No
WO-26-006207 | 5.4 | Bayou | BY-S28-02 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 14.18 | Completed | No
WO-26-006208 | 4.3 | Bayou | BY-S13-02 | Trouble - no power | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Troubleman |  | 14.81 | Completed | No
WO-26-006209 | 3.6 | Bayou | BY-S25-03 | Trouble - no power | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Troubleman |  | 165.93 | Completed | No
WO-26-006210 | 5.7 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Troubleman |  | 314.11 | Completed | No
WO-26-006211 | 2.7 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 318.95 | Completed | No
WO-26-006212 | 5.4 | Bayou | BY-S20-02 | Trouble - no power | P2 same day | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 66.39 | Completed | No
WO-26-006213 | 5.7 | Bayou | BY-S06-03 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 155.38 | Completed | No
WO-26-006214 | 5.6 | Bayou | BY-S12-02 | Trouble - no power | P2 same day | 2026-06-10 | 2026-06-10 | 2026-06-10 | Internal line |  | 51.49 | Completed | No
WO-26-006215 | 5.6 | Bayou | BY-S19-04 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 278.86 | Completed | No
WO-26-006216 | 3.4 | Bayou | BY-S03-03 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 236.33 | Completed | No
WO-26-006217 | 2.1 | Bayou | BY-S15-04 | Trouble - partial or voltage | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Internal line |  | 38.29 | Completed | No
WO-26-006218 | 8.4 | Crossroads | CR-S13-04 | Corrective maintenance | P3 within 10 days | 2026-06-10 | 2026-06-18 | 2026-06-18 | Contract line | CT-01 | 1975.48 | Completed | No
WO-26-006219 | 11.6 | Crossroads | CR-S13-05 | Corrective maintenance | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-15 | Contract line | CT-02 | 1397.21 | Completed | No
WO-26-006220 |  | Crossroads | CR-S25-01 | Corrective maintenance | P2 same day | 2026-06-10 | 2026-06-10 |  | Internal line |  |  | Cancelled | No
WO-26-006221 | 4.9 | Crossroads | CR-S19-02 | Corrective maintenance | P3 within 10 days | 2026-06-10 | 2026-06-19 | 2026-06-19 | Underground crew |  | 951.12 | Completed | No
WO-26-006222 | 1 | Crossroads | CR-S17-01 | Meter exchange | P4 planned | 2026-06-10 | 2026-08-09 | 2026-08-11 | Meter technician |  | 172.61 | Completed | No
WO-26-006223 | 1 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-06-10 | 2026-06-19 | 2026-06-20 | Meter technician |  | 124.24 | Completed | No
WO-26-006224 | 13.3 | Crossroads | CR-S10-02 | New service - small | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-15 | Contract line | CT-02 | 3460.36 | Completed | No
WO-26-006225 | 12 | Crossroads | CR-S30-02 | Pole replacement | P4 planned | 2026-06-10 | 2026-06-30 | 2026-07-02 | Contract line | CT-02 | 2278.46 | Completed | No
WO-26-006226 | 3 | Crossroads | CR-S03-02 | Preventive maintenance | P4 planned | 2026-06-10 | 2026-07-03 | 2026-07-05 | Internal line |  | 526.67 | Completed | No
WO-26-006227 | 0.5 | Crossroads | CR-S17-03 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-13 | 2026-06-15 | Meter technician |  | 25.12 | Completed | No
WO-26-006228 | 1.2 | Crossroads | CR-S26-06 | Service order - field | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Meter technician |  | 15.57 | Completed | No
WO-26-006229 | 1.4 | Crossroads | CR-S16-03 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-14 | 2026-06-18 | Meter technician |  | 3.56 | Completed | No
WO-26-006230 | 1 | Crossroads | CR-S23-01 | Service order - field | P2 same day | 2026-06-10 | 2026-06-10 | 2026-06-10 | Meter technician |  | 31.74 | Completed | No
WO-26-006231 | 1.6 | Crossroads | CR-S05-02 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-20 | 2026-06-21 | Meter technician |  | 37.81 | Completed | No
WO-26-006232 | 1.8 | Crossroads | CR-S19-02 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-17 | 2026-06-19 | Meter technician |  | 9.3 | Completed | No
WO-26-006233 | 1.4 | Crossroads | CR-S14-01 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-20 | 2026-06-20 | Meter technician |  | 14.84 | Completed | No
WO-26-006234 | 1 | Crossroads | CR-S07-05 | Service order - field | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Meter technician |  | 15.25 | Completed | No
WO-26-006235 | 0.6 | Crossroads | CR-S08-06 | Service order - field | P3 within 10 days | 2026-06-10 | 2026-06-19 | 2026-06-19 | Meter technician |  | 18.05 | Completed | No
WO-26-006236 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-10 | 2026-06-20 | 2026-06-20 | Internal line |  | 47.07 | Completed | No
WO-26-006237 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-10 | 2026-06-15 | 2026-06-23 | Internal line |  | 65.51 | Completed | No
WO-26-006238 | 13 | Crossroads | CR-S21-01 | Transformer replacement | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Contract line | CT-02 | 10236.32 | Completed | No
WO-26-006239 | 3.5 | Crossroads | CR-S32-01 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Internal line |  | 152.99 | Completed | No
WO-26-006240 | 5.1 | Crossroads | CR-S03-02 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 162.73 | Completed | No
WO-26-006241 | 2.7 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 44.19 | Completed | No
WO-26-006242 | 3.5 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-06-10 | 2026-06-10 | 2026-06-10 | Troubleman |  | 97.63 | Completed | No
WO-26-006243 | 2.7 | Crossroads | CR-S07-07 | Trouble - partial or voltage | P2 same day | 2026-06-10 | 2026-06-11 | 2026-06-11 | Troubleman |  | 216.99 | Completed | No
WO-26-006244 | 9.9 | Bayou | BY-S23-01 | Corrective maintenance | P3 within 10 days | 2026-06-11 | 2026-06-14 | 2026-06-18 | Internal line |  | 565.83 | Completed | No
WO-26-006245 | 0.8 | Bayou | BY-S11-03 | Meter exchange | P3 within 10 days | 2026-06-11 | 2026-06-12 | 2026-06-12 | Meter technician |  | 143.77 | Completed | No
WO-26-006246 | 1.2 | Bayou | BY-S09-03 | Meter exchange | P4 planned | 2026-06-11 | 2026-07-06 | 2026-07-10 | Meter technician |  | 61.3 | Completed | No
WO-26-006247 | 1.3 | Bayou | BY-S07-02 | Meter exchange | P4 planned | 2026-06-11 | 2026-06-24 | 2026-06-25 | Meter technician |  | 74.33 | Completed | No
WO-26-006248 | 13 | Bayou | BY-S07-02 | New service - small | P4 planned | 2026-06-11 | 2026-06-25 | 2026-06-25 | Underground crew |  | 2934.65 | Completed | No
WO-26-006249 | 2.9 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-06-11 | 2026-06-27 | 2026-06-27 | Internal line |  | 3.37 | Completed | No
WO-26-006250 |  | Bayou | BY-S21-05 | Service order - field | P2 same day | 2026-06-11 | 2026-06-12 |  | Meter technician |  |  | Cancelled | No
WO-26-006251 | 1 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-11 | 2026-06-19 | 2026-06-19 | Contract line | CT-04 | 380.43 | Completed | No
WO-26-006252 | 5.6 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Internal line |  | 258.34 | Completed | No
WO-26-006253 | 4.2 | Bayou | BY-S27-03 | Trouble - no power | P2 same day | 2026-06-11 | 2026-06-12 | 2026-06-12 | Troubleman |  | 114.29 | Completed | No
WO-26-006254 | 5.9 | Bayou | BY-S17-03 | Trouble - no power | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Troubleman |  | 85.13 | Completed | No
WO-26-006255 | 2.1 | Bayou | BY-S14-02 | Trouble - partial or voltage | P2 same day | 2026-06-11 | 2026-06-11 | 2026-06-11 | Troubleman |  | 57.96 | Completed | No
WO-26-006256 | 3.6 | Bayou | BY-S13-05 | Trouble - partial or voltage | P2 same day | 2026-06-11 | 2026-06-12 | 2026-06-12 | Troubleman |  | 162.14 | Completed | No
WO-26-006257 | 1.5 | Bayou | BY-S09-04 | Trouble - partial or voltage | P3 within 10 days | 2026-06-11 | 2026-06-19 | 2026-06-20 | Internal line |  | 10.13 | Completed | No
WO-26-006258 | 3.9 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-06-11 | 2026-06-12 | 2026-06-12 | Troubleman |  | 62.06 | Completed | No
WO-26-006259 | 7.1 | Crossroads | CR-S20-02 | Corrective maintenance | P4 planned | 2026-06-11 | 2026-08-02 | 2026-08-03 | Underground crew |  | 946.19 | Completed | No
WO-26-006260 | 3.5 | Crossroads | CR-S04-05 | Corrective maintenance | P3 within 10 days | 2026-06-11 | 2026-06-19 | 2026-06-19 | Underground crew |  | 897.66 | Completed | No
WO-26-006261 | 7.7 | Crossroads | CR-S25-04 | Corrective maintenance | P2 same day | 2026-06-11 | 2026-06-11 | 2026-06-11 | Underground crew |  | 1278.86 | Completed | No
WO-26-006262 | 1 | Crossroads | CR-S02-02 | Meter exchange | P4 planned | 2026-06-11 | 2026-08-04 | 2026-08-08 | Meter technician |  | 83.63 | Completed | No
WO-26-006263 | 0.7 | Crossroads | CR-S24-01 | Meter exchange | P3 within 10 days | 2026-06-11 | 2026-06-18 | 2026-06-22 | Meter technician |  | 151.66 | Completed | No
WO-26-006264 | 0.8 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-06-11 | 2026-06-15 | 2026-06-16 | Meter technician |  | 63.66 | Completed | No
WO-26-006265 | 11.8 | Crossroads | CR-S11-01 | New service - small | P4 planned | 2026-06-11 | 2026-08-03 | 2026-08-07 | Underground crew |  | 3383.03 | Completed | No
WO-26-006266 | 1 | Crossroads | CR-S07-05 | Service order - field | P3 within 10 days | 2026-06-11 | 2026-06-15 | 2026-06-15 | Meter technician |  | 21.18 | Completed | No
WO-26-006267 | 1.2 | Crossroads | CR-S21-02 | Service order - field | P3 within 10 days | 2026-06-11 | 2026-06-15 | 2026-06-16 | Meter technician |  | 22.03 | Completed | No
WO-26-006268 | 1.4 | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-06-11 | 2026-06-12 | 2026-06-12 | Meter technician |  | 29.84 | Completed | No
WO-26-006269 | 1.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-11 | 2026-06-15 | 2026-06-15 | Contract line | CT-01 | 225.51 | Completed | No
WO-26-006270 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-11 | 2026-06-15 | 2026-06-15 | Internal line |  | 356.58 | Completed | No
WO-26-006271 | 7.8 | Crossroads | CR-S28-02 | Transformer replacement | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Internal line |  | 8280.82 | Completed | No
WO-26-006272 | 12.6 | Crossroads | CR-S28-03 | Transformer replacement | P2 same day | 2026-06-11 | 2026-06-12 | 2026-06-12 | Contract line | CT-01 | 5851.27 | Completed | No
WO-26-006273 | 6.4 | Crossroads | CR-S17-01 | Transformer replacement | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Internal line |  | 6745.4 | Completed | No
WO-26-006274 | 3.5 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Troubleman |  | 170.24 | Completed | No
WO-26-006275 | 3.6 | Crossroads | CR-S30-04 | Trouble - no power | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Troubleman |  | 83.15 | Completed | No
WO-26-006276 | 5.9 | Crossroads | CR-S12-03 | Trouble - no power | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Troubleman |  | 167.08 | Completed | No
WO-26-006277 | 2.3 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-06-11 | 2026-06-11 | 2026-06-11 | Troubleman |  | 326.29 | Completed | No
WO-26-006278 | 2.9 | Crossroads | CR-S16-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-11 | 2026-06-20 | 2026-06-20 | Troubleman |  | 240.49 | Completed | No
WO-26-006279 | 3.1 | Crossroads | CR-S32-04 | Trouble - partial or voltage | P3 within 10 days | 2026-06-11 | 2026-06-20 | 2026-06-20 | Troubleman |  | 194.13 | Completed | No
WO-26-006280 | 2.6 | Crossroads | CR-S28-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-11 | 2026-06-21 | 2026-06-21 | Troubleman |  | 65.3 | Completed | No
WO-26-006281 | 10.1 | Bayou | BY-S23-02 | Corrective maintenance | P4 planned | 2026-06-12 | 2026-07-06 | 2026-07-07 | Underground crew |  | 380.44 | Completed | No
WO-26-006282 | 5.5 | Bayou | BY-S30-03 | Corrective maintenance | P3 within 10 days | 2026-06-12 | 2026-06-13 | 2026-06-21 | Internal line |  | 2158.92 | Completed | No
WO-26-006283 | 3.7 | Bayou | BY-S26-01 | Corrective maintenance | P4 planned | 2026-06-12 | 2026-08-04 | 2026-08-04 | Internal line |  | 592.79 | Completed | No
WO-26-006284 | 6.5 | Bayou | BY-S25-04 | Corrective maintenance | P2 same day | 2026-06-12 | 2026-06-13 | 2026-06-13 | Internal line |  | 1049.02 | Completed | No
WO-26-006285 | 5.8 | Bayou | BY-S10-03 | Corrective maintenance | P3 within 10 days | 2026-06-12 | 2026-06-13 | 2026-06-13 | Contract line | CT-04 | 1428.24 | Completed | No
WO-26-006286 | 9.7 | Bayou | BY-S09-03 | Corrective maintenance | P2 same day | 2026-06-12 | 2026-06-12 | 2026-06-12 | Contract line | CT-03 | 1247.82 | Completed | No
WO-26-006287 | 1.3 | Bayou | BY-S11-03 | Meter exchange | P3 within 10 days | 2026-06-12 | 2026-06-18 | 2026-06-22 | Meter technician |  | 117.51 | Completed | No
WO-26-006288 | 1.2 | Bayou | BY-S27-06 | Meter exchange | P4 planned | 2026-06-12 | 2026-07-10 | 2026-07-12 | Meter technician |  | 115.26 | Completed | No
WO-26-006289 | 1.3 | Bayou | BY-S11-03 | Meter exchange | P4 planned | 2026-06-12 | 2026-07-03 | 2026-07-07 | Meter technician |  | 145.93 | Completed | No
WO-26-006290 | 7.1 | Bayou | BY-S27-02 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-06-21 | 2026-06-25 | Underground crew |  | 11.64 | Completed | No
WO-26-006291 | 6.4 | Bayou | BY-S12-02 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-07-23 | 2026-07-23 | Internal line |  | 65.61 | Completed | No
WO-26-006292 | 7.6 | Bayou | BY-S09-05 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-07-18 | 2026-07-18 | Contract line | CT-03 | 299.25 | Completed | No
WO-26-006293 | 7.9 | Bayou | BY-S07-04 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-07-03 | 2026-07-07 | Internal line |  | 76.18 | Completed | No
WO-26-006294 | 1.2 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-06-12 | 2026-06-13 | 2026-06-13 | Meter technician |  | 38.94 | Completed | No
WO-26-006295 | 1.4 | Bayou | BY-S08-03 | Service order - field | P3 within 10 days | 2026-06-12 | 2026-06-19 | 2026-06-19 | Meter technician |  | 34.79 | Completed | No
WO-26-006296 | 1.6 | Bayou | BY-S18-07 | Service order - field | P2 same day | 2026-06-12 | 2026-06-12 | 2026-06-12 | Meter technician |  | 34.29 | Completed | No
WO-26-006297 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-12 | 2026-06-19 | 2026-06-19 | Internal line |  | 298.53 | Completed | No
WO-26-006298 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-12 | 2026-06-22 | 2026-06-22 | Contract line | CT-04 | 430.55 | Completed | No
WO-26-006299 |  | Bayou |  | Streetlight | P4 planned | 2026-06-12 | 2026-06-26 |  | Internal line |  |  | Cancelled | No
WO-26-006300 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-12 | 2026-06-19 | 2026-06-20 | Internal line |  | 90.6 | Completed | No
WO-26-006301 | 7.9 | Bayou | BY-S09-01 | Transformer replacement | P2 same day | 2026-06-12 | 2026-06-13 | 2026-06-13 | Internal line |  | 12064.28 | Completed | No
WO-26-006302 | 3.8 | Bayou | BY-S13-02 | Trouble - no power | P2 same day | 2026-06-12 | 2026-06-12 | 2026-06-12 | Troubleman |  | 306.68 | Completed | No
WO-26-006303 | 5.1 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-06-12 | 2026-06-12 | 2026-06-12 | Internal line |  | 208.6 | Completed | No
WO-26-006304 | 3.3 | Bayou | BY-S21-02 | Trouble - no power | P2 same day | 2026-06-12 | 2026-06-12 | 2026-06-12 | Troubleman |  | 194.25 | Completed | No
WO-26-006305 | 2.4 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-06-12 | 2026-06-12 | 2026-06-12 | Troubleman |  | 273.69 | Completed | No
WO-26-006306 | 1.9 | Bayou | BY-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-06-12 | 2026-06-22 | 2026-06-22 | Internal line |  | 46.84 | Completed | No
WO-26-006307 | 3.9 | Bayou | BY-S07-02 | Trouble - partial or voltage | P2 same day | 2026-06-12 | 2026-06-13 | 2026-06-13 | Troubleman |  | 229.96 | Completed | No
WO-26-006308 | 1.2 | Crossroads | CR-S02-03 | Meter exchange | P4 planned | 2026-06-12 | 2026-06-22 | 2026-06-22 | Meter technician |  | 141.87 | Completed | No
WO-26-006309 | 0.8 | Crossroads | CR-S02-01 | Meter exchange | P3 within 10 days | 2026-06-12 | 2026-06-17 | 2026-06-17 | Meter technician |  | 126.56 | Completed | No
WO-26-006310 | 10.2 | Crossroads | CR-S19-04 | Pole replacement | P3 within 10 days | 2026-06-12 | 2026-06-21 | 2026-06-21 | Contract line | CT-01 | 2809.51 | Completed | No
WO-26-006311 | 3 | Crossroads | CR-S04-06 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-07-31 | 2026-08-01 | Internal line |  | 237.22 | Completed | No
WO-26-006312 | 4.6 | Crossroads | CR-S30-07 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-08-09 | 2026-08-09 | Underground crew |  | 242.86 | Completed | No
WO-26-006313 | 7.3 | Crossroads | CR-S05-01 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-08-05 | 2026-08-07 | Internal line |  | 334.12 | Completed | No
WO-26-006314 | 4.1 | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-08-03 | 2026-08-05 | Internal line |  | 397.61 | Completed | No
WO-26-006315 | 3.7 | Crossroads | CR-S03-01 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-07-29 | 2026-08-02 | Internal line |  | 521.25 | Completed | No
WO-26-006316 | 6.2 | Crossroads | CR-S17-01 | Preventive maintenance | P4 planned | 2026-06-12 | 2026-07-29 | 2026-07-29 | Internal line |  | 156.22 | Completed | No
WO-26-006317 | 0.7 | Crossroads | CR-S18-02 | Service order - field | P2 same day | 2026-06-12 | 2026-06-12 | 2026-06-12 | Meter technician |  | 13.51 | Completed | No
WO-26-006318 | 1.4 | Crossroads | CR-S08-02 | Service order - field | P2 same day | 2026-06-12 | 2026-06-12 | 2026-06-12 | Meter technician |  | 38.76 | Completed | No
WO-26-006319 |  | Crossroads | CR-S32-02 | Transformer replacement | P1 emergency | 2026-06-12 | 2026-06-12 |  | Internal line |  |  | Cancelled | No
WO-26-006320 | 5.2 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-06-12 | 2026-06-12 | 2026-06-12 | Troubleman |  | 9.16 | Completed | No
WO-26-006321 | 5.8 | Crossroads | CR-S24-04 | Trouble - no power | P1 emergency | 2026-06-12 | 2026-06-12 | 2026-06-12 | Internal line |  | 313.96 | Completed | No
WO-26-006322 | 6 | Crossroads | CR-S28-04 | Trouble - no power | P1 emergency | 2026-06-12 | 2026-06-12 | 2026-06-12 | Troubleman |  | 124.99 | Completed | No
WO-26-006323 | 5.2 | Crossroads | CR-S05-01 | Trouble - no power | P1 emergency | 2026-06-12 | 2026-06-12 | 2026-06-12 | Troubleman |  | 347.94 | Completed | No
WO-26-006324 | 3.4 | Crossroads | CR-S28-01 | Trouble - no power | P2 same day | 2026-06-12 | 2026-06-13 | 2026-06-13 | Internal line |  | 207.06 | Completed | No
WO-26-006325 | 1.9 | Crossroads | CR-S06-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-12 | 2026-06-16 | 2026-06-16 | Troubleman |  | 121.06 | Completed | No
WO-26-006326 | 8.5 | Bayou | BY-S16-06 | Transformer replacement | P2 same day | 2026-06-13 | 2026-06-13 | 2026-06-13 | Internal line |  | 10561.9 | Completed | No
WO-26-006327 |  | Bayou | BY-S04-01 | Trouble - no power | P1 emergency | 2026-06-13 | 2026-06-13 |  | Troubleman |  |  | Cancelled | No
WO-26-006328 | 4.5 | Bayou | BY-S28-01 | Trouble - no power | P2 same day | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 158.69 | Completed | No
WO-26-006329 | 2.1 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 308.08 | Completed | No
WO-26-006330 | 4.7 | Crossroads | CR-S10-03 | Corrective maintenance | P2 same day | 2026-06-13 | 2026-06-14 | 2026-06-14 | Internal line |  | 1158.12 | Completed | No
WO-26-006331 | 13.4 | Crossroads | CR-S19-03 | Transformer replacement | P1 emergency | 2026-06-13 | 2026-06-13 | 2026-06-13 | Internal line |  | 10028.17 | Completed | No
WO-26-006332 | 4.5 | Crossroads | CR-S10-01 | Trouble - no power | P1 emergency | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 175.48 | Completed | No
WO-26-006333 | 2.2 | Crossroads | CR-S15-03 | Trouble - no power | P1 emergency | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 176.91 | Completed | No
WO-26-006334 | 2.2 | Crossroads | CR-S24-02 | Trouble - no power | P2 same day | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 134.98 | Completed | No
WO-26-006335 | 4 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 90.2 | Completed | No
WO-26-006336 | 2.8 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 342.23 | Completed | No
WO-26-006337 | 1.9 | Crossroads | CR-S22-01 | Trouble - partial or voltage | P2 same day | 2026-06-13 | 2026-06-13 | 2026-06-13 | Troubleman |  | 123.19 | Completed | No
WO-26-006338 | 1.4 | Bayou | BY-S16-03 | Service order - field | P2 same day | 2026-06-14 | 2026-06-14 | 2026-06-14 | Meter technician |  | 25.9 | Completed | No
WO-26-006339 | 1.8 | Bayou | BY-S26-01 | Service order - field | P2 same day | 2026-06-14 | 2026-06-15 | 2026-06-15 | Meter technician |  | 1.41 | Completed | No
WO-26-006340 | 10.8 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-06-14 | 2026-06-14 | 2026-06-14 | Underground crew |  | 818.85 | Completed | No
WO-26-006341 | 1.1 | Crossroads | CR-S08-03 | Service order - field | P2 same day | 2026-06-14 | 2026-06-14 | 2026-06-14 | Meter technician |  | 27.68 | Completed | No
WO-26-006342 | 1.2 | Crossroads | CR-S20-05 | Service order - field | P2 same day | 2026-06-14 | 2026-06-14 | 2026-06-14 | Meter technician |  | 33.52 | Completed | No
WO-26-006343 | 4.3 | Crossroads | CR-S18-06 | Trouble - no power | P1 emergency | 2026-06-14 | 2026-06-14 | 2026-06-14 | Troubleman |  | 6.79 | Completed | No
WO-26-006344 | 3.7 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-06-14 | 2026-06-14 | 2026-06-14 | Troubleman |  | 335.33 | Completed | No
WO-26-006345 | 3.1 | Crossroads | CR-S30-05 | Trouble - partial or voltage | P2 same day | 2026-06-14 | 2026-06-14 | 2026-06-14 | Troubleman |  | 230.55 | Completed | No
WO-26-006346 | 11.3 | Bayou | BY-S21-05 | Corrective maintenance | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-22 | Underground crew |  | 947.16 | Completed | No
WO-26-006347 | 8.2 | Bayou | BY-S16-05 | Corrective maintenance | P3 within 10 days | 2026-06-15 | 2026-06-23 | 2026-06-25 | Contract line | CT-03 | 2032.12 | Completed | No
WO-26-006348 | 0.7 | Bayou | BY-S10-05 | Meter exchange | P3 within 10 days | 2026-06-15 | 2026-06-18 | 2026-06-20 | Meter technician |  | 166.99 | Completed | No
WO-26-006349 | 0.7 | Bayou | BY-S04-02 | Meter exchange | P3 within 10 days | 2026-06-15 | 2026-06-17 | 2026-06-19 | Meter technician |  | 61.39 | Completed | No
WO-26-006350 | 0.9 | Bayou | BY-S13-06 | Meter exchange | P3 within 10 days | 2026-06-15 | 2026-06-22 | 2026-06-22 | Meter technician |  | 64.79 | Completed | No
WO-26-006351 | 1.2 | Bayou | BY-S23-05 | Meter exchange | P4 planned | 2026-06-15 | 2026-07-24 | 2026-07-28 | Meter technician |  | 72.19 | Completed | No
WO-26-006352 | 0.5 | Bayou | BY-S10-04 | Meter exchange | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-21 | Meter technician |  | 172.11 | Completed | No
WO-26-006353 | 4.7 | Bayou | BY-S18-07 | Preventive maintenance | P4 planned | 2026-06-15 | 2026-07-13 | 2026-07-13 | Contract line | CT-03 | 517.57 | Completed | No
WO-26-006354 | 2.3 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-06-15 | 2026-07-28 | 2026-07-28 | Internal line |  | 132.83 | Completed | No
WO-26-006355 | 7 | Bayou | BY-S06-01 | Preventive maintenance | P4 planned | 2026-06-15 | 2026-08-09 | 2026-08-10 | Internal line |  | 416.79 | Completed | No
WO-26-006356 | 1.1 | Bayou | BY-S29-02 | Service order - field | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-21 | Meter technician |  | 18 | Completed | No
WO-26-006357 | 0.7 | Bayou | BY-S14-01 | Service order - field | P3 within 10 days | 2026-06-15 | 2026-06-24 | 2026-06-24 | Meter technician |  | 25.64 | Completed | No
WO-26-006358 | 1.2 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-06-15 | 2026-06-15 | 2026-06-15 | Meter technician |  | 27.46 | Completed | No
WO-26-006359 | 1.5 | Bayou | BY-S24-02 | Service order - field | P2 same day | 2026-06-15 | 2026-06-15 | 2026-06-15 | Meter technician |  | 25.48 | Completed | No
WO-26-006360 | 1.7 | Bayou | BY-S17-03 | Service order - field | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-21 | Meter technician |  | 19.3 | Completed | No
WO-26-006361 | 1.9 | Bayou | BY-S23-01 | Service order - field | P3 within 10 days | 2026-06-15 | 2026-06-23 | 2026-06-23 | Meter technician |  | 25.37 | Completed | No
WO-26-006362 | 1.7 | Bayou |  | Streetlight | P4 planned | 2026-06-15 | 2026-07-10 | 2026-07-18 | Contract line | CT-04 | 387.35 | Completed | No
WO-26-006363 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-15 | 2026-06-23 | 2026-06-24 | Contract line | CT-04 | 90.1 | Completed | No
WO-26-006364 | 1.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-15 | 2026-06-25 | 2026-06-25 | Contract line | CT-03 | 312.81 | Completed | No
WO-26-006365 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-15 | 2026-06-22 | 2026-06-26 | Internal line |  | 63.8 | Completed | No
WO-26-006366 | 1.7 | Bayou |  | Streetlight | P4 planned | 2026-06-15 | 2026-07-17 | 2026-07-21 | Internal line |  | 248.23 | Completed | No
WO-26-006367 | 8.6 | Bayou | BY-S24-05 | Transformer replacement | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Contract line | CT-03 | 4715.85 | Completed | No
WO-26-006368 | 2.7 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 331.78 | Completed | No
WO-26-006369 | 2.9 | Bayou | BY-S21-03 | Trouble - no power | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Troubleman |  | 133.71 | Completed | No
WO-26-006370 | 5.2 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 181.55 | Completed | No
WO-26-006371 | 3 | Bayou | BY-S21-03 | Trouble - no power | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 165.79 | Completed | No
WO-26-006372 | 4.6 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 96.26 | Completed | No
WO-26-006373 | 3.8 | Bayou | BY-S10-05 | Trouble - partial or voltage | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Troubleman |  | 148.84 | Completed | No
WO-26-006374 | 2.3 | Bayou | BY-S17-01 | Trouble - partial or voltage | P2 same day | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 216.64 | Completed | No
WO-26-006375 | 10.9 | Crossroads | CR-S08-03 | Corrective maintenance | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-25 | Internal line |  | 1152.66 | Completed | No
WO-26-006376 | 3.1 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-06-15 | 2026-06-17 | 2026-06-18 | Contract line | CT-01 | 1872.86 | Completed | No
WO-26-006377 | 5.3 | Crossroads | CR-S22-02 | Corrective maintenance | P4 planned | 2026-06-15 | 2026-07-15 | 2026-07-15 | Contract line | CT-01 | 1845.09 | Completed | No
WO-26-006378 | 7.4 | Crossroads | CR-S16-04 | Corrective maintenance | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Internal line |  | 2057.23 | Completed | No
WO-26-006379 | 7.1 | Crossroads | CR-S05-05 | Corrective maintenance | P3 within 10 days | 2026-06-15 | 2026-06-19 | 2026-06-21 | Internal line |  | 1909.24 | Completed | No
WO-26-006380 | 9 | Crossroads | CR-S25-03 | Corrective maintenance | P3 within 10 days | 2026-06-15 | 2026-06-25 | 2026-06-25 | Internal line |  | 705.02 | Completed | No
WO-26-006381 | 0.5 | Crossroads | CR-S29-02 | Meter exchange | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-22 | Meter technician |  | 77.93 | Completed | No
WO-26-006382 | 12.9 | Crossroads | CR-S19-03 | New service - small | P4 planned | 2026-06-15 | 2026-08-02 | 2026-08-02 | Internal line |  | 3915 | Completed | No
WO-26-006383 | 7.3 | Crossroads | CR-S09-04 | Preventive maintenance | P4 planned | 2026-06-15 | 2026-08-04 | 2026-08-05 | Internal line |  | 441.8 | Completed | No
WO-26-006384 | 6.2 | Crossroads | CR-S32-05 | Preventive maintenance | P4 planned | 2026-06-15 | 2026-06-27 | 2026-06-29 | Underground crew |  | 478.88 | Completed | No
WO-26-006385 | 1.9 | Crossroads | CR-S26-06 | Service order - field | P3 within 10 days | 2026-06-15 | 2026-06-17 | 2026-06-21 | Meter technician |  | 26.99 | Completed | No
WO-26-006386 | 0.8 | Crossroads | CR-S12-02 | Service order - field | P3 within 10 days | 2026-06-15 | 2026-06-24 | 2026-06-26 | Meter technician |  | 12.13 | Completed | No
WO-26-006387 | 1.8 | Crossroads | CR-S28-03 | Service order - field | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Meter technician |  | 24.58 | Completed | No
WO-26-006388 | 1.8 | Crossroads | CR-S03-03 | Service order - field | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Meter technician |  | 24.11 | Completed | No
WO-26-006389 | 0.5 | Crossroads | CR-S12-02 | Service order - field | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Meter technician |  | 0.89 | Completed | No
WO-26-006390 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-15 | 2026-06-16 | 2026-06-20 | Contract line | CT-02 | 413.71 | Completed | No
WO-26-006391 | 7.9 | Crossroads | CR-S21-03 | Transformer replacement | P3 within 10 days | 2026-06-15 | 2026-06-24 | 2026-06-24 | Internal line |  | 2827.03 | Completed | No
WO-26-006392 | 7.5 | Crossroads | CR-S20-02 | Transformer replacement | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Internal line |  | 7948.65 | Completed | No
WO-26-006393 | 9.6 | Crossroads | CR-S06-02 | Transformer replacement | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Internal line |  | 7849.25 | Completed | No
WO-26-006394 | 10.8 | Crossroads | CR-S29-03 | Transformer replacement | P2 same day | 2026-06-15 | 2026-06-15 | 2026-06-15 | Internal line |  | 5175.74 | Completed | No
WO-26-006395 | 6.9 | Crossroads | CR-S01-03 | Transformer replacement | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Internal line |  | 10557.13 | Completed | No
WO-26-006396 | 13.4 | Crossroads | CR-S25-02 | Transformer replacement | P3 within 10 days | 2026-06-15 | 2026-06-21 | 2026-06-23 | Internal line |  | 8855.32 | Completed | No
WO-26-006397 | 2.8 | Crossroads | CR-S29-01 | Trouble - no power | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 72.09 | Completed | No
WO-26-006398 | 2.2 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-06-15 | 2026-06-16 | 2026-06-16 | Troubleman |  | 339.44 | Completed | No
WO-26-006399 | 3.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-06-15 | 2026-06-15 | 2026-06-15 | Troubleman |  | 200.55 | Completed | No
WO-26-006400 | 2.3 | Crossroads | CR-S23-04 | Trouble - partial or voltage | P3 within 10 days | 2026-06-15 | 2026-06-16 | 2026-06-16 | Troubleman |  | 139.54 | Completed | No
WO-26-006401 | 6.9 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-06-16 | 2026-06-19 | 2026-06-23 | Internal line |  | 2210 | Completed | No
WO-26-006402 | 0.9 | Bayou | BY-S23-01 | Meter exchange | P3 within 10 days | 2026-06-16 | 2026-06-25 | 2026-06-26 | Meter technician |  | 67.54 | Completed | No
WO-26-006403 | 1.5 | Bayou | BY-S29-01 | Meter exchange | P4 planned | 2026-06-16 | 2026-07-02 | 2026-07-02 | Meter technician |  | 60.33 | Completed | No
WO-26-006404 | 1.3 | Bayou | BY-S01-01 | Meter exchange | P4 planned | 2026-06-16 | 2026-07-14 | 2026-07-22 | Meter technician |  | 105.68 | Completed | No
WO-26-006405 | 0.7 | Bayou | BY-S17-01 | Meter exchange | P3 within 10 days | 2026-06-16 | 2026-06-26 | 2026-06-26 | Meter technician |  | 155.85 | Completed | No
WO-26-006406 | 13.2 | Bayou | BY-S15-06 | Pole replacement | P3 within 10 days | 2026-06-16 | 2026-06-17 | 2026-06-25 | Internal line |  | 3388.22 | Completed | No
WO-26-006407 | 2.3 | Bayou | BY-S30-03 | Preventive maintenance | P4 planned | 2026-06-16 | 2026-07-09 | 2026-07-13 | Underground crew |  | 159.28 | Completed | No
WO-26-006408 | 6.5 | Bayou | BY-S27-06 | Preventive maintenance | P4 planned | 2026-06-16 | 2026-06-26 | 2026-06-26 | Contract line | CT-03 | 335.64 | Completed | No
WO-26-006409 | 5.6 | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-06-16 | 2026-07-23 | 2026-07-27 | Internal line |  | 234.67 | Completed | No
WO-26-006410 | 0.7 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-06-16 | 2026-06-16 | 2026-06-16 | Meter technician |  | 10.82 | Completed | No
WO-26-006411 | 1 | Bayou | BY-S10-02 | Service order - field | P3 within 10 days | 2026-06-16 | 2026-06-25 | 2026-06-25 | Meter technician |  | 18.89 | Completed | No
WO-26-006412 | 1.2 | Bayou | BY-S10-01 | Service order - field | P2 same day | 2026-06-16 | 2026-06-16 | 2026-06-16 | Meter technician |  | 2.22 | Completed | No
WO-26-006413 | 0.6 | Bayou | BY-S26-03 | Service order - field | P3 within 10 days | 2026-06-16 | 2026-06-23 | 2026-06-23 | Meter technician |  | 19.31 | Completed | No
WO-26-006414 | 11 | Bayou | BY-S13-03 | Transformer replacement | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Internal line |  | 11350.42 | Completed | No
WO-26-006415 | 2.4 | Bayou | BY-S16-01 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Troubleman |  | 82.1 | Completed | No
WO-26-006416 | 3.1 | Bayou | BY-S18-02 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Internal line |  | 33.95 | Completed | No
WO-26-006417 | 3.9 | Bayou | BY-S23-04 | Trouble - no power | P2 same day | 2026-06-16 | 2026-06-17 | 2026-06-17 | Troubleman |  | 189.34 | Completed | No
WO-26-006418 | 2.1 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Internal line |  | 171.08 | Completed | No
WO-26-006419 | 4.4 | Bayou | BY-S19-01 | Trouble - no power | P2 same day | 2026-06-16 | 2026-06-17 | 2026-06-17 | Troubleman |  | 126.75 | Completed | No
WO-26-006420 | 3 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Troubleman |  | 60.9 | Completed | No
WO-26-006421 | 5.5 | Crossroads | CR-S02-02 | Corrective maintenance | P4 planned | 2026-06-16 | 2026-07-27 | 2026-07-27 | Underground crew |  | 1032.8 | Completed | No
WO-26-006422 | 9.9 | Crossroads | CR-S28-03 | Corrective maintenance | P2 same day | 2026-06-16 | 2026-06-16 | 2026-06-16 | Internal line |  | 405.43 | Completed | No
WO-26-006423 | 11.1 | Crossroads | CR-S16-02 | Corrective maintenance | P2 same day | 2026-06-16 | 2026-06-16 | 2026-06-16 | Contract line | CT-01 | 330.95 | Completed | No
WO-26-006424 | 6.7 | Crossroads | CR-S14-02 | Corrective maintenance | P3 within 10 days | 2026-06-16 | 2026-06-24 | 2026-06-24 | Underground crew |  | 107.36 | Completed | No
WO-26-006425 | 0.8 | Crossroads | CR-S04-02 | Meter exchange | P3 within 10 days | 2026-06-16 | 2026-06-25 | 2026-06-25 | Meter technician |  | 171.74 | Completed | No
WO-26-006426 | 1.4 | Crossroads | CR-S30-01 | Meter exchange | P3 within 10 days | 2026-06-16 | 2026-06-20 | 2026-06-20 | Meter technician |  | 173.47 | Completed | No
WO-26-006427 | 16 | Crossroads | CR-S31-02 | New service - small | P4 planned | 2026-06-16 | 2026-07-04 | 2026-07-04 | Contract line | CT-02 | 1115.34 | Completed | No
WO-26-006428 | 6.5 | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-06-16 | 2026-08-01 | 2026-08-01 | Internal line |  | 100.04 | Completed | No
WO-26-006429 | 4.8 | Crossroads | CR-S06-03 | Preventive maintenance | P4 planned | 2026-06-16 | 2026-07-12 | 2026-07-20 | Contract line | CT-02 | 260.4 | Completed | No
WO-26-006430 | 2.7 | Crossroads | CR-S01-02 | Preventive maintenance | P4 planned | 2026-06-16 | 2026-07-07 | 2026-07-07 | Underground crew |  | 17.77 | Completed | No
WO-26-006431 | 0.6 | Crossroads | CR-S03-01 | Service order - field | P3 within 10 days | 2026-06-16 | 2026-06-21 | 2026-06-23 | Meter technician |  | 12.07 | Completed | No
WO-26-006432 | 1.7 | Crossroads | CR-S18-04 | Service order - field | P3 within 10 days | 2026-06-16 | 2026-06-24 | 2026-06-26 | Meter technician |  | 33.81 | Completed | No
WO-26-006433 | 1.3 | Crossroads | CR-S32-02 | Service order - field | P3 within 10 days | 2026-06-16 | 2026-06-23 | 2026-06-25 | Meter technician |  | 6.16 | Completed | No
WO-26-006434 | 0.9 | Crossroads | CR-S32-03 | Service order - field | P3 within 10 days | 2026-06-16 | 2026-06-19 | 2026-06-19 | Meter technician |  | 18.53 | Completed | No
WO-26-006435 | 8.8 | Crossroads | CR-S29-02 | Transformer replacement | P3 within 10 days | 2026-06-16 | 2026-06-18 | 2026-06-18 | Internal line |  | 7908.11 | Completed | No
WO-26-006436 | 13.8 | Crossroads | CR-S22-01 | Transformer replacement | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Contract line | CT-01 | 3710.07 | Completed | No
WO-26-006437 | 3.7 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Troubleman |  | 340.13 | Completed | No
WO-26-006438 | 5.5 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Troubleman |  | 183.08 | Completed | No
WO-26-006439 | 2.4 | Crossroads | CR-S02-05 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Troubleman |  | 255.83 | Completed | No
WO-26-006440 | 4.3 | Crossroads | CR-S17-02 | Trouble - no power | P1 emergency | 2026-06-16 | 2026-06-16 | 2026-06-16 | Troubleman |  | 284.51 | Completed | No
WO-26-006441 | 4.8 | Crossroads | CR-S23-02 | Trouble - partial or voltage | P2 same day | 2026-06-16 | 2026-06-17 | 2026-06-17 | Internal line |  | 135.49 | Completed | No
WO-26-006442 | 3.7 | Crossroads | CR-S23-03 | Trouble - partial or voltage | P2 same day | 2026-06-16 | 2026-06-17 | 2026-06-17 | Troubleman |  | 193.17 | Completed | No
WO-26-006443 | 4.4 | Bayou | BY-S12-04 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-20 | 2026-06-20 | Contract line | CT-03 | 1331.59 | Completed | No
WO-26-006444 | 5.1 | Bayou | BY-S23-05 | Corrective maintenance | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Underground crew |  | 986.23 | Completed | No
WO-26-006445 | 10.2 | Bayou | BY-S13-02 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-20 | 2026-06-22 | Internal line |  | 2106.28 | Completed | No
WO-26-006446 | 9 | Bayou | BY-S12-04 | Corrective maintenance | P4 planned | 2026-06-17 | 2026-07-20 | 2026-07-21 | Underground crew |  | 467 | Completed | No
WO-26-006447 | 10.4 | Bayou | BY-S18-06 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-25 | 2026-06-27 | Underground crew |  | 92.18 | Completed | No
WO-26-006448 | 5.1 | Bayou | BY-S07-02 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-18 | 2026-06-26 | Underground crew |  | 238.18 | Completed | No
WO-26-006449 | 11.5 | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-27 | 2026-06-27 | Contract line | CT-04 | 324.15 | Completed | No
WO-26-006450 | 9.6 | Bayou | BY-S10-05 | Corrective maintenance | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Underground crew |  | 2206.23 | Completed | No
WO-26-006451 | 4.3 | Bayou | BY-S21-02 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-22 | 2026-06-22 | Contract line | CT-04 | 666.27 | Completed | No
WO-26-006452 | 1.3 | Bayou | BY-S16-02 | Meter exchange | P4 planned | 2026-06-17 | 2026-07-05 | 2026-07-05 | Meter technician |  | 71.75 | Completed | No
WO-26-006453 | 0.8 | Bayou | BY-S08-02 | Meter exchange | P3 within 10 days | 2026-06-17 | 2026-06-20 | 2026-06-20 | Meter technician |  | 67.62 | Completed | No
WO-26-006454 | 12.8 | Bayou | BY-S16-02 | New service - small | P4 planned | 2026-06-17 | 2026-07-23 | 2026-07-23 | Contract line | CT-04 | 3731.65 | Completed | No
WO-26-006455 | 17.6 | Bayou | BY-S19-02 | Pole replacement | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Internal line |  | 1326.57 | Completed | No
WO-26-006456 | 1.6 | Bayou | BY-S16-01 | Service order - field | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Meter technician |  | 26.29 | Completed | No
WO-26-006457 | 1.7 | Bayou | BY-S11-03 | Service order - field | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Meter technician |  | 39.46 | Completed | No
WO-26-006458 | 1.2 | Bayou | BY-S10-04 | Service order - field | P3 within 10 days | 2026-06-17 | 2026-06-19 | 2026-06-23 | Meter technician |  | 32.37 | Completed | No
WO-26-006459 | 0.8 | Bayou | BY-S27-03 | Service order - field | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Meter technician |  | 34.26 | Completed | No
WO-26-006460 | 1.6 | Bayou | BY-S25-02 | Service order - field | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Meter technician |  | 1.19 | Completed | No
WO-26-006461 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-17 | 2026-06-18 | 2026-06-19 | Contract line | CT-03 | 337.96 | Completed | No
WO-26-006462 | 8.8 | Bayou | BY-S11-02 | Transformer replacement | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Internal line |  | 12424.44 | Completed | No
WO-26-006463 | 12.5 | Bayou | BY-S16-01 | Transformer replacement | P1 emergency | 2026-06-17 | 2026-06-17 | 2026-06-17 | Internal line |  | 7823.62 | Completed | No
WO-26-006464 | 6.8 | Bayou | BY-S13-02 | Transformer replacement | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Contract line | CT-03 | 8301.87 | Completed | No
WO-26-006465 | 5.3 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-06-17 | 2026-06-17 | 2026-06-17 | Troubleman |  | 312.29 | Completed | No
WO-26-006466 | 4.4 | Bayou | BY-S25-02 | Trouble - no power | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Troubleman |  | 289.09 | Completed | No
WO-26-006467 | 3.3 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-06-17 | 2026-06-17 | 2026-06-17 | Internal line |  | 50.39 | Completed | No
WO-26-006468 | 4.7 | Bayou | BY-S19-01 | Trouble - no power | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Troubleman |  | 136.95 | Completed | No
WO-26-006469 | 3.7 | Bayou | BY-S18-03 | Trouble - no power | P1 emergency | 2026-06-17 | 2026-06-17 | 2026-06-17 | Troubleman |  | 219.51 | Completed | No
WO-26-006470 | 2.6 | Bayou | BY-S12-03 | Trouble - no power | P1 emergency | 2026-06-17 | 2026-06-17 | 2026-06-17 | Troubleman |  | 195.79 | Completed | No
WO-26-006471 |  | Crossroads | CR-S21-01 | Corrective maintenance | P2 same day | 2026-06-17 | 2026-06-18 |  | Internal line |  |  | Cancelled | No
WO-26-006472 | 4.1 | Crossroads | CR-S07-07 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-18 | 2026-06-18 | Internal line |  | 1416.65 | Completed | No
WO-26-006473 | 5.7 | Crossroads | CR-S15-03 | Corrective maintenance | P4 planned | 2026-06-17 | 2026-07-07 | 2026-07-09 | Internal line |  | 1799.03 | Completed | No
WO-26-006474 | 11.8 | Crossroads | CR-S12-01 | Corrective maintenance | P3 within 10 days | 2026-06-17 | 2026-06-27 | 2026-06-27 | Internal line |  | 766.84 | Completed | No
WO-26-006475 | 1.1 | Crossroads | CR-S05-03 | Meter exchange | P3 within 10 days | 2026-06-17 | 2026-06-23 | 2026-06-23 | Meter technician |  | 102.32 | Completed | No
WO-26-006476 | 0.8 | Crossroads | CR-S13-02 | Meter exchange | P3 within 10 days | 2026-06-17 | 2026-06-20 | 2026-06-20 | Meter technician |  | 122.92 | Completed | No
WO-26-006477 | 7 | Crossroads | CR-S03-02 | New service - small | P4 planned | 2026-06-17 | 2026-07-23 | 2026-07-24 | Underground crew |  | 585.87 | Completed | No
WO-26-006478 | 18.5 | Crossroads | CR-S07-02 | Pole replacement | P4 planned | 2026-06-17 | 2026-07-13 | 2026-07-14 | Internal line |  | 1485.06 | Completed | No
WO-26-006479 | 5.2 | Crossroads | CR-S24-01 | Preventive maintenance | P4 planned | 2026-06-17 | 2026-07-09 | 2026-07-09 | Internal line |  | 371.79 | Completed | No
WO-26-006480 | 4.7 | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-06-17 | 2026-08-08 | 2026-08-10 | Underground crew |  | 408.24 | Completed | No
WO-26-006481 | 6.6 | Crossroads | CR-S29-02 | Preventive maintenance | P4 planned | 2026-06-17 | 2026-07-26 | 2026-07-28 | Internal line |  | 67.34 | Completed | No
WO-26-006482 | 7.1 | Crossroads | CR-S03-01 | Preventive maintenance | P4 planned | 2026-06-17 | 2026-08-15 | 2026-08-15 | Internal line |  | 485.06 | Completed | No
WO-26-006483 | 1.9 | Crossroads | CR-S20-05 | Service order - field | P3 within 10 days | 2026-06-17 | 2026-06-23 | 2026-06-23 | Meter technician |  | 24.34 | Completed | No
WO-26-006484 | 0.7 | Crossroads | CR-S01-01 | Service order - field | P3 within 10 days | 2026-06-17 | 2026-06-22 | 2026-06-22 | Meter technician |  | 0.54 | Completed | No
WO-26-006485 | 1.1 | Crossroads |  | Streetlight | P4 planned | 2026-06-17 | 2026-07-05 | 2026-07-05 | Contract line | CT-01 | 255.64 | Completed | No
WO-26-006486 | 3.4 | Crossroads | CR-S24-01 | Trouble - no power | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Troubleman |  | 212.54 | Completed | No
WO-26-006487 | 3.9 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Troubleman |  | 72.65 | Completed | No
WO-26-006488 | 5.5 | Crossroads | CR-S16-03 | Trouble - no power | P2 same day | 2026-06-17 | 2026-06-18 | 2026-06-18 | Troubleman |  | 120.55 | Completed | No
WO-26-006489 | 2.3 | Crossroads | CR-S07-07 | Trouble - partial or voltage | P2 same day | 2026-06-17 | 2026-06-17 | 2026-06-17 | Troubleman |  | 30.53 | Completed | No
WO-26-006490 | 4.3 | Crossroads | CR-S14-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-17 | 2026-06-21 | 2026-06-23 | Troubleman |  | 154.39 | Completed | No
WO-26-006491 | 7.2 | Bayou | BY-S15-06 | Corrective maintenance | P4 planned | 2026-06-18 | 2026-06-27 | 2026-06-27 | Internal line |  | 461.8 | Completed | No
WO-26-006492 | 5.8 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-06-18 | 2026-06-21 | 2026-06-21 | Contract line | CT-04 | 1341.24 | Completed | No
WO-26-006493 | 7.8 | Bayou | BY-S30-01 | Corrective maintenance | P4 planned | 2026-06-18 | 2026-08-15 | 2026-08-16 | Internal line |  | 984.96 | Completed | No
WO-26-006494 | 8.6 | Bayou | BY-S27-02 | Corrective maintenance | P3 within 10 days | 2026-06-18 | 2026-06-21 | 2026-06-21 | Contract line | CT-03 | 144.31 | Completed | No
WO-26-006495 | 0.8 | Bayou | BY-S29-03 | Meter exchange | P3 within 10 days | 2026-06-18 | 2026-06-28 | 2026-06-28 | Meter technician |  | 76.84 | Completed | No
WO-26-006496 | 1.1 | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-06-18 | 2026-06-24 | 2026-07-02 | Meter technician |  | 130.8 | Completed | No
WO-26-006497 |  | Bayou | BY-S19-02 | Meter exchange | P3 within 10 days | 2026-06-18 | 2026-06-25 |  | Meter technician |  |  | Cancelled | No
WO-26-006498 | 6.8 | Bayou | BY-S14-01 | New service - small | P4 planned | 2026-06-18 | 2026-08-05 | 2026-08-05 | Contract line | CT-03 | 3587.93 | Completed | No
WO-26-006499 | 3.4 | Bayou | BY-S20-02 | Preventive maintenance | P4 planned | 2026-06-18 | 2026-07-17 | 2026-07-18 | Internal line |  | 145.69 | Completed | No
WO-26-006500 | 6.3 | Bayou | BY-S24-05 | Preventive maintenance | P4 planned | 2026-06-18 | 2026-07-29 | 2026-07-29 | Internal line |  | 69.58 | Completed | No
WO-26-006501 | 2.8 | Bayou | BY-S22-02 | Preventive maintenance | P4 planned | 2026-06-18 | 2026-06-29 | 2026-07-03 | Internal line |  | 25.44 | Completed | No
WO-26-006502 | 1.3 | Bayou | BY-S15-05 | Service order - field | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Meter technician |  | 36.19 | Completed | No
WO-26-006503 | 2.1 | Bayou |  | Streetlight | P4 planned | 2026-06-18 | 2026-07-31 | 2026-07-31 | Internal line |  | 285.74 | Completed | No
WO-26-006504 | 11.9 | Bayou | BY-S27-06 | Transformer replacement | P3 within 10 days | 2026-06-18 | 2026-06-19 | 2026-06-23 | Internal line |  | 5281.75 | Completed | No
WO-26-006505 | 4.6 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 303.12 | Completed | No
WO-26-006506 | 4.1 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Internal line |  | 288.8 | Completed | No
WO-26-006507 | 2.4 | Bayou | BY-S27-03 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 30.44 | Completed | No
WO-26-006508 | 4.2 | Bayou | BY-S29-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-18 | 2026-06-23 | 2026-07-01 | Troubleman |  | 179.68 | Completed | No
WO-26-006509 | 3.8 | Bayou | BY-S10-05 | Trouble - partial or voltage | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 164.4 | Completed | No
WO-26-006510 | 5 | Bayou | BY-S07-01 | Trouble - partial or voltage | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Internal line |  | 38.75 | Completed | No
WO-26-006511 | 2.1 | Bayou | BY-S24-01 | Trouble - partial or voltage | P3 within 10 days | 2026-06-18 | 2026-06-19 | 2026-06-19 | Troubleman |  | 119.54 | Completed | No
WO-26-006512 | 2.7 | Bayou | BY-S24-02 | Trouble - partial or voltage | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Troubleman |  | 230.29 | Completed | No
WO-26-006513 | 2.3 | Bayou | BY-S23-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-18 | 2026-06-27 | 2026-07-05 | Internal line |  | 93.09 | Completed | No
WO-26-006514 | 7 | Crossroads | CR-S28-04 | Corrective maintenance | P4 planned | 2026-06-18 | 2026-06-27 | 2026-06-27 | Underground crew |  | 1032.14 | Completed | No
WO-26-006515 | 9.5 | Crossroads | CR-S31-02 | Corrective maintenance | P4 planned | 2026-06-18 | 2026-07-04 | 2026-07-06 | Internal line |  | 466.04 | Completed | No
WO-26-006516 | 11.7 | Crossroads | CR-S12-02 | Corrective maintenance | P3 within 10 days | 2026-06-18 | 2026-06-26 | 2026-06-26 | Underground crew |  | 1374.52 | Completed | No
WO-26-006517 | 3.2 | Crossroads | CR-S05-04 | Corrective maintenance | P3 within 10 days | 2026-06-18 | 2026-06-27 | 2026-06-27 | Internal line |  | 1628.04 | Completed | No
WO-26-006518 | 3.2 | Crossroads | CR-S07-03 | Corrective maintenance | P3 within 10 days | 2026-06-18 | 2026-06-26 | 2026-06-26 | Internal line |  | 2371.43 | Completed | No
WO-26-006519 | 1.1 | Crossroads | CR-S27-03 | Meter exchange | P3 within 10 days | 2026-06-18 | 2026-06-28 | 2026-06-29 | Meter technician |  | 115.19 | Completed | No
WO-26-006520 | 1.1 | Crossroads | CR-S29-01 | Meter exchange | P3 within 10 days | 2026-06-18 | 2026-06-22 | 2026-06-22 | Meter technician |  | 158.9 | Completed | No
WO-26-006521 | 4.4 | Crossroads | CR-S14-02 | New service - small | P4 planned | 2026-06-18 | 2026-08-01 | 2026-08-02 | Internal line |  | 516.76 | Completed | No
WO-26-006522 | 22.8 | Crossroads | CR-S07-02 | Pole replacement | P4 planned | 2026-06-18 | 2026-08-12 | 2026-08-14 | Contract line | CT-02 | 2106.09 | Completed | No
WO-26-006523 | 18 | Crossroads | CR-S27-01 | Pole replacement | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Contract line | CT-02 | 2187.58 | Completed | No
WO-26-006524 | 5.2 | Crossroads | CR-S02-03 | Preventive maintenance | P4 planned | 2026-06-18 | 2026-08-03 | 2026-08-03 | Contract line | CT-01 | 297.76 | Completed | No
WO-26-006525 | 6 | Crossroads | CR-S08-01 | Preventive maintenance | P4 planned | 2026-06-18 | 2026-07-19 | 2026-07-19 | Contract line | CT-02 | 543.03 | Completed | No
WO-26-006526 | 4.1 | Crossroads | CR-S14-03 | Preventive maintenance | P4 planned | 2026-06-18 | 2026-07-19 | 2026-07-20 | Internal line |  | 109.63 | Completed | No
WO-26-006527 | 2 | Crossroads | CR-S32-03 | Service order - field | P3 within 10 days | 2026-06-18 | 2026-06-27 | 2026-07-05 | Meter technician |  | 30.25 | Completed | No
WO-26-006528 | 1.9 | Crossroads | CR-S14-05 | Service order - field | P3 within 10 days | 2026-06-18 | 2026-06-27 | 2026-07-05 | Meter technician |  | 3.01 | Completed | No
WO-26-006529 | 1.7 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Meter technician |  | 22.26 | Completed | No
WO-26-006530 | 0.7 | Crossroads | CR-S26-04 | Service order - field | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Meter technician |  | 23.69 | Completed | No
WO-26-006531 | 1 | Crossroads | CR-S26-06 | Service order - field | P3 within 10 days | 2026-06-18 | 2026-06-19 | 2026-06-19 | Meter technician |  | 8.36 | Completed | No
WO-26-006532 | 1.3 | Crossroads | CR-S32-03 | Service order - field | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Meter technician |  | 18.06 | Completed | No
WO-26-006533 | 1.3 | Crossroads | CR-S31-01 | Service order - field | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Meter technician |  | 34.53 | Completed | No
WO-26-006534 | 1.4 | Crossroads | CR-S17-03 | Service order - field | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Meter technician |  | 25.9 | Completed | No
WO-26-006535 | 0.9 | Crossroads | CR-S23-04 | Service order - field | P3 within 10 days | 2026-06-18 | 2026-06-27 | 2026-06-27 | Meter technician |  | 35.72 | Completed | No
WO-26-006536 | 1.5 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Meter technician |  | 11.49 | Completed | No
WO-26-006537 | 1.4 | Crossroads | CR-S18-01 | Service order - field | P3 within 10 days | 2026-06-18 | 2026-06-27 | 2026-06-29 | Meter technician |  | 26.33 | Completed | No
WO-26-006538 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-18 | 2026-06-27 |  | Internal line |  |  | Cancelled | No
WO-26-006539 | 2.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-18 | 2026-06-28 | 2026-06-29 | Contract line | CT-02 | 301.57 | Completed | No
WO-26-006540 | 2.1 | Crossroads |  | Streetlight | P4 planned | 2026-06-18 | 2026-07-20 | 2026-07-22 | Contract line | CT-01 | 94.48 | Completed | No
WO-26-006541 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-18 | 2026-06-24 | 2026-06-25 | Contract line | CT-02 | 125.28 | Completed | No
WO-26-006542 | 11.1 | Crossroads | CR-S11-01 | Transformer replacement | P3 within 10 days | 2026-06-18 | 2026-06-22 | 2026-06-22 | Internal line |  | 4392.65 | Completed | No
WO-26-006543 | 9.2 | Crossroads | CR-S23-02 | Transformer replacement | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Internal line |  | 6300.61 | Completed | No
WO-26-006544 | 4.7 | Crossroads | CR-S30-07 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Internal line |  | 203.51 | Completed | No
WO-26-006545 | 4.5 | Crossroads | CR-S26-04 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Internal line |  | 259.64 | Completed | No
WO-26-006546 | 2 | Crossroads | CR-S01-02 | Trouble - no power | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Troubleman |  | 126.37 | Completed | No
WO-26-006547 | 3.5 | Crossroads | CR-S32-04 | Trouble - no power | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Internal line |  | 84.43 | Completed | No
WO-26-006548 | 2.3 | Crossroads | CR-S16-01 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 238.96 | Completed | No
WO-26-006549 | 3.5 | Crossroads | CR-S22-02 | Trouble - no power | P2 same day | 2026-06-18 | 2026-06-19 | 2026-06-19 | Troubleman |  | 120.59 | Completed | No
WO-26-006550 | 2.5 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Internal line |  | 340.95 | Completed | No
WO-26-006551 | 3.6 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 280.13 | Completed | No
WO-26-006552 | 3.9 | Crossroads | CR-S29-03 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 253.76 | Completed | No
WO-26-006553 | 4.1 | Crossroads | CR-S06-01 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Internal line |  | 337.35 | Completed | No
WO-26-006554 | 5.2 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 178.87 | Completed | No
WO-26-006555 | 5.5 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 316.12 | Completed | No
WO-26-006556 | 4.1 | Crossroads | CR-S32-02 | Trouble - partial or voltage | P2 same day | 2026-06-18 | 2026-06-18 | 2026-06-18 | Troubleman |  | 148.19 | Completed | No
WO-26-006557 | 3.2 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-06-19 | 2026-06-20 | 2026-06-21 | Internal line |  | 563.47 | Completed | No
WO-26-006558 | 6.5 | Bayou | BY-S12-02 | Corrective maintenance | P4 planned | 2026-06-19 | 2026-08-10 | 2026-08-10 | Contract line | CT-03 | 913.15 | Completed | No
WO-26-006559 | 6.9 | Bayou | BY-S13-02 | Corrective maintenance | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Underground crew |  | 1598.26 | Completed | No
WO-26-006560 | 4.4 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-06-19 | 2026-06-21 | 2026-06-29 | Internal line |  | 1189.21 | Completed | No
WO-26-006561 | 1.2 | Bayou | BY-S15-04 | Meter exchange | P4 planned | 2026-06-19 | 2026-07-18 | 2026-07-18 | Meter technician |  | 67.68 | Completed | No
WO-26-006562 | 12 | Bayou | BY-S07-02 | Pole replacement | P3 within 10 days | 2026-06-19 | 2026-06-28 | 2026-06-29 | Internal line |  | 1794.81 | Completed | No
WO-26-006563 | 2.9 | Bayou | BY-S10-02 | Preventive maintenance | P4 planned | 2026-06-19 | 2026-07-07 | 2026-07-07 | Internal line |  | 204.2 | Completed | No
WO-26-006564 | 5 | Bayou | BY-S04-02 | Preventive maintenance | P4 planned | 2026-06-19 | 2026-06-30 | 2026-07-02 | Internal line |  | 284 | Completed | No
WO-26-006565 | 2 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-06-19 | 2026-06-22 | 2026-06-22 | Meter technician |  | 10.36 | Completed | No
WO-26-006566 | 1.2 | Bayou | BY-S13-01 | Service order - field | P3 within 10 days | 2026-06-19 | 2026-06-25 | 2026-06-25 | Meter technician |  | 34.34 | Completed | No
WO-26-006567 | 0.9 | Bayou | BY-S16-02 | Service order - field | P3 within 10 days | 2026-06-19 | 2026-06-21 | 2026-06-22 | Meter technician |  | 9.88 | Completed | No
WO-26-006568 | 1.9 | Bayou | BY-S06-01 | Service order - field | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Meter technician |  | 29.24 | Completed | No
WO-26-006569 | 9.9 | Bayou | BY-S25-02 | Transformer replacement | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Internal line |  | 10699.47 | Completed | No
WO-26-006570 | 13.5 | Bayou | BY-S11-01 | Transformer replacement | P3 within 10 days | 2026-06-19 | 2026-06-20 | 2026-06-24 | Internal line |  | 10456.49 | Completed | No
WO-26-006571 | 4 | Bayou | BY-S10-05 | Trouble - no power | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Troubleman |  | 218.87 | Completed | No
WO-26-006572 | 4.2 | Bayou | BY-S19-01 | Trouble - no power | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Troubleman |  | 52.88 | Completed | No
WO-26-006573 | 1.7 | Bayou | BY-S12-03 | Trouble - partial or voltage | P2 same day | 2026-06-19 | 2026-06-20 | 2026-06-20 | Troubleman |  | 115.04 | Completed | No
WO-26-006574 | 5.8 | Crossroads | CR-S22-03 | Corrective maintenance | P3 within 10 days | 2026-06-19 | 2026-06-26 | 2026-06-26 | Underground crew |  | 2332.18 | Completed | No
WO-26-006575 | 4.2 | Crossroads | CR-S23-02 | Corrective maintenance | P3 within 10 days | 2026-06-19 | 2026-06-23 | 2026-06-23 | Internal line |  | 1514.7 | Completed | No
WO-26-006576 | 8.8 | Crossroads | CR-S05-02 | Corrective maintenance | P4 planned | 2026-06-19 | 2026-07-30 | 2026-07-31 | Contract line | CT-02 | 398.33 | Completed | No
WO-26-006577 | 10.3 | Crossroads | CR-S07-03 | Corrective maintenance | P3 within 10 days | 2026-06-19 | 2026-06-28 | 2026-06-29 | Underground crew |  | 361.45 | Completed | No
WO-26-006578 | 4.7 | Crossroads | CR-S25-06 | Corrective maintenance | P3 within 10 days | 2026-06-19 | 2026-06-21 | 2026-06-22 | Underground crew |  | 381.64 | Completed | No
WO-26-006579 | 10.6 | Crossroads | CR-S06-02 | Pole replacement | P4 planned | 2026-06-19 | 2026-07-23 | 2026-07-25 | Internal line |  | 2703.19 | Completed | No
WO-26-006580 | 7.6 | Crossroads | CR-S14-01 | Preventive maintenance | P4 planned | 2026-06-19 | 2026-08-17 | 2026-08-21 | Contract line | CT-01 | 518.45 | Completed | No
WO-26-006581 | 6.1 | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-06-19 | 2026-07-20 | 2026-07-21 | Internal line |  | 485.91 | Completed | No
WO-26-006582 | 6.3 | Crossroads | CR-S22-02 | Preventive maintenance | P4 planned | 2026-06-19 | 2026-07-05 | 2026-07-06 | Contract line | CT-01 | 185.67 | Completed | No
WO-26-006583 | 1.8 | Crossroads | CR-S07-02 | Service order - field | P3 within 10 days | 2026-06-19 | 2026-06-28 | 2026-07-02 | Meter technician |  | 25.63 | Completed | No
WO-26-006584 | 1.1 | Crossroads | CR-S18-03 | Service order - field | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Meter technician |  | 8.15 | Completed | No
WO-26-006585 | 1.5 | Crossroads | CR-S04-05 | Service order - field | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Meter technician |  | 13.18 | Completed | No
WO-26-006586 | 0.6 | Crossroads | CR-S02-01 | Service order - field | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Meter technician |  | 37.51 | Completed | No
WO-26-006587 | 1.8 | Crossroads | CR-S25-06 | Service order - field | P3 within 10 days | 2026-06-19 | 2026-06-21 | 2026-06-23 | Meter technician |  | 5.49 | Completed | No
WO-26-006588 | 0.8 | Crossroads | CR-S09-03 | Service order - field | P3 within 10 days | 2026-06-19 | 2026-06-21 | 2026-06-29 | Meter technician |  | 32.21 | Completed | No
WO-26-006589 | 1.4 | Crossroads |  | Streetlight | P4 planned | 2026-06-19 | 2026-08-10 | 2026-08-11 | Contract line | CT-02 | 432.91 | Completed | No
WO-26-006590 | 9.8 | Crossroads | CR-S24-01 | Transformer replacement | P2 same day | 2026-06-19 | 2026-06-20 | 2026-06-20 | Internal line |  | 9493.83 | Completed | No
WO-26-006591 | 6.1 | Crossroads | CR-S16-02 | Transformer replacement | P1 emergency | 2026-06-19 | 2026-06-19 | 2026-06-19 | Internal line |  | 11468.23 | Completed | No
WO-26-006592 | 2.5 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-06-19 | 2026-06-19 | 2026-06-19 | Internal line |  | 12.79 | Completed | No
WO-26-006593 | 4.1 | Crossroads | CR-S30-05 | Trouble - partial or voltage | P2 same day | 2026-06-19 | 2026-06-19 | 2026-06-19 | Troubleman |  | 105.42 | Completed | No
WO-26-006594 | 3.4 | Bayou | BY-S04-02 | Corrective maintenance | P2 same day | 2026-06-20 | 2026-06-21 | 2026-06-21 | Underground crew |  | 1350.54 | Completed | No
WO-26-006595 | 6.6 | Bayou | BY-S16-05 | Corrective maintenance | P2 same day | 2026-06-20 | 2026-06-21 | 2026-06-21 | Internal line |  | 1883.77 | Completed | No
WO-26-006596 | 1.3 | Bayou | BY-S23-04 | Service order - field | P2 same day | 2026-06-20 | 2026-06-20 | 2026-06-20 | Meter technician |  | 5.46 | Completed | No
WO-26-006597 | 9.9 | Bayou | BY-S29-04 | Transformer replacement | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Contract line | CT-04 | 8167.3 | Completed | No
WO-26-006598 | 7.4 | Bayou | BY-S07-02 | Transformer replacement | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 7622.34 | Completed | No
WO-26-006599 | 2.2 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 334.26 | Completed | No
WO-26-006600 | 2.3 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 122.18 | Completed | No
WO-26-006601 | 5.7 | Bayou | BY-S17-02 | Trouble - no power | P2 same day | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 213.56 | Completed | No
WO-26-006602 | 3.6 | Bayou | BY-S09-05 | Trouble - no power | P2 same day | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 137.74 | Completed | No
WO-26-006603 | 4.9 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 75.54 | Completed | No
WO-26-006604 | 5.4 | Bayou | BY-S14-03 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 46.45 | Completed | No
WO-26-006605 | 2.5 | Bayou | BY-S23-03 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 164.72 | Completed | No
WO-26-006606 | 5.3 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 328.55 | Completed | No
WO-26-006607 | 2.8 | Bayou | BY-S22-04 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 105.69 | Completed | No
WO-26-006608 | 2 | Crossroads | CR-S03-01 | Service order - field | P2 same day | 2026-06-20 | 2026-06-21 | 2026-06-21 | Meter technician |  | 13.9 | Completed | No
WO-26-006609 | 12.8 | Crossroads | CR-S06-02 | Transformer replacement | P2 same day | 2026-06-20 | 2026-06-21 | 2026-06-21 | Internal line |  | 12327.65 | Completed | No
WO-26-006610 | 12.7 | Crossroads | CR-S30-02 | Transformer replacement | P2 same day | 2026-06-20 | 2026-06-21 | 2026-06-21 | Internal line |  | 8598.23 | Completed | No
WO-26-006611 | 3.2 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 74.08 | Completed | No
WO-26-006612 | 4.3 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 205.69 | Completed | No
WO-26-006613 | 5 | Crossroads | CR-S24-01 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 329.34 | Completed | No
WO-26-006614 | 5.6 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 142.75 | Completed | No
WO-26-006615 | 4.5 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 251.6 | Completed | No
WO-26-006616 | 4.3 | Crossroads | CR-S10-02 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 60.84 | Completed | No
WO-26-006617 | 5.3 | Crossroads | CR-S24-02 | Trouble - no power | P1 emergency | 2026-06-20 | 2026-06-20 | 2026-06-20 | Troubleman |  | 306.37 | Completed | No
WO-26-006618 | 4.2 | Crossroads | CR-S07-04 | Trouble - partial or voltage | P2 same day | 2026-06-20 | 2026-06-20 | 2026-06-20 | Internal line |  | 66.49 | Completed | No
WO-26-006619 | 8.8 | Bayou | BY-S04-03 | Corrective maintenance | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Contract line | CT-04 | 1131.69 | Completed | No
WO-26-006620 | 1 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Meter technician |  | 35.29 | Completed | No
WO-26-006621 | 2.7 | Bayou | BY-S17-04 | Trouble - no power | P1 emergency | 2026-06-21 | 2026-06-21 | 2026-06-21 | Troubleman |  | 311.39 | Completed | No
WO-26-006622 | 4.7 | Bayou | BY-S28-02 | Trouble - no power | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Troubleman |  | 36.77 | Completed | No
WO-26-006623 | 3.1 | Bayou | BY-S23-01 | Trouble - no power | P2 same day | 2026-06-21 | 2026-06-22 | 2026-06-22 | Troubleman |  | 110.22 | Completed | No
WO-26-006624 | 4.3 | Bayou | BY-S21-03 | Trouble - no power | P1 emergency | 2026-06-21 | 2026-06-21 | 2026-06-21 | Internal line |  | 257.03 | Completed | No
WO-26-006625 | 2.3 | Bayou | BY-S27-04 | Trouble - partial or voltage | P2 same day | 2026-06-21 | 2026-06-22 | 2026-06-22 | Internal line |  | 14.67 | Completed | No
WO-26-006626 | 21.6 | Crossroads | CR-S21-03 | Pole replacement | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Contract line | CT-01 | 1408.18 | Completed | No
WO-26-006627 | 0.9 | Crossroads | CR-S13-03 | Service order - field | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Meter technician |  | 18.88 | Completed | No
WO-26-006628 | 1.8 | Crossroads | CR-S15-03 | Service order - field | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Meter technician |  | 15.21 | Completed | No
WO-26-006629 | 1.2 | Crossroads | CR-S30-07 | Service order - field | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Meter technician |  | 26.73 | Completed | No
WO-26-006630 | 9.1 | Crossroads | CR-S08-03 | Transformer replacement | P2 same day | 2026-06-21 | 2026-06-21 | 2026-06-21 | Contract line | CT-01 | 2853.12 | Completed | No
WO-26-006631 | 4.6 | Crossroads | CR-S20-01 | Trouble - no power | P1 emergency | 2026-06-21 | 2026-06-21 | 2026-06-21 | Troubleman |  | 89.87 | Completed | No
WO-26-006632 | 3.6 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-06-21 | 2026-06-21 | 2026-06-21 | Troubleman |  | 265.05 | Completed | No
WO-26-006633 | 5.2 | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-06-21 | 2026-06-21 | 2026-06-21 | Troubleman |  | 2.85 | Completed | No
WO-26-006634 | 4.8 | Crossroads | CR-S09-04 | Trouble - no power | P2 same day | 2026-06-21 | 2026-06-22 | 2026-06-22 | Troubleman |  | 97.29 | Completed | No
WO-26-006635 | 5 | Bayou | BY-S16-02 | Corrective maintenance | P4 planned | 2026-06-22 | 2026-08-12 | 2026-08-20 | Internal line |  | 849.53 | Completed | No
WO-26-006636 | 4.1 | Bayou | BY-S13-05 | Corrective maintenance | P4 planned | 2026-06-22 | 2026-08-16 | 2026-08-16 | Contract line | CT-04 | 1131.48 | Completed | No
WO-26-006637 | 9.1 | Bayou | BY-S29-02 | Corrective maintenance | P3 within 10 days | 2026-06-22 | 2026-06-24 | 2026-06-25 | Internal line |  | 1087.16 | Completed | No
WO-26-006638 | 5.2 | Bayou | BY-S06-01 | Corrective maintenance | P3 within 10 days | 2026-06-22 | 2026-06-25 | 2026-06-29 | Internal line |  | 1693.9 | Completed | No
WO-26-006639 | 1.3 | Bayou | BY-S08-01 | Meter exchange | P3 within 10 days | 2026-06-22 | 2026-06-24 | 2026-06-25 | Meter technician |  | 165.76 | Completed | No
WO-26-006640 | 1.4 | Bayou | BY-S08-01 | Meter exchange | P4 planned | 2026-06-22 | 2026-06-30 | 2026-07-01 | Meter technician |  | 151.46 | Completed | No
WO-26-006641 | 1.1 | Bayou | BY-S06-02 | Meter exchange | P4 planned | 2026-06-22 | 2026-07-03 | 2026-07-04 | Meter technician |  | 119.59 | Completed | No
WO-26-006642 | 7 | Bayou | BY-S16-02 | Preventive maintenance | P4 planned | 2026-06-22 | 2026-08-14 | 2026-08-16 | Internal line |  | 27.44 | Completed | No
WO-26-006643 | 3 | Bayou | BY-S15-02 | Preventive maintenance | P4 planned | 2026-06-22 | 2026-07-28 | 2026-07-28 | Underground crew |  | 545.34 | Completed | No
WO-26-006644 | 1.2 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-06-22 | 2026-06-23 | 2026-06-23 | Meter technician |  | 26.96 | Completed | No
WO-26-006645 | 0.6 | Bayou | BY-S06-02 | Service order - field | P3 within 10 days | 2026-06-22 | 2026-06-28 | 2026-06-29 | Meter technician |  | 14.52 | Completed | No
WO-26-006646 | 1.8 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-06-22 | 2026-06-23 | 2026-06-23 | Meter technician |  | 10.64 | Completed | No
WO-26-006647 | 0.9 | Bayou | BY-S13-02 | Service order - field | P3 within 10 days | 2026-06-22 | 2026-06-29 | 2026-07-01 | Meter technician |  | 16.78 | Completed | No
WO-26-006648 | 1.7 | Bayou | BY-S15-05 | Service order - field | P2 same day | 2026-06-22 | 2026-06-23 | 2026-06-23 | Meter technician |  | 1.38 | Completed | No
WO-26-006649 | 1 | Bayou | BY-S12-03 | Service order - field | P3 within 10 days | 2026-06-22 | 2026-06-29 | 2026-06-29 | Meter technician |  | 37.61 | Completed | No
WO-26-006650 | 2.9 | Bayou |  | Streetlight | P4 planned | 2026-06-22 | 2026-08-06 | 2026-08-06 | Contract line | CT-04 | 430.83 | Completed | No
WO-26-006651 | 3.2 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 325.9 | Completed | No
WO-26-006652 | 4.1 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 42.39 | Completed | No
WO-26-006653 | 5.5 | Bayou | BY-S26-02 | Trouble - no power | P2 same day | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 308.85 | Completed | No
WO-26-006654 | 2.7 | Bayou | BY-S21-01 | Trouble - partial or voltage | P2 same day | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 82.84 | Completed | No
WO-26-006655 | 5.4 | Crossroads | CR-S14-01 | Corrective maintenance | P3 within 10 days | 2026-06-22 | 2026-06-23 | 2026-06-27 | Contract line | CT-02 | 324.94 | Completed | No
WO-26-006656 | 8.5 | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-06-22 | 2026-06-24 | 2026-06-24 | Contract line | CT-02 | 1352.11 | Completed | No
WO-26-006657 | 11.5 | Crossroads | CR-S19-02 | Corrective maintenance | P4 planned | 2026-06-22 | 2026-06-29 | 2026-06-29 | Contract line | CT-01 | 1367.31 | Completed | No
WO-26-006658 | 0.6 | Crossroads | CR-S14-02 | Meter exchange | P3 within 10 days | 2026-06-22 | 2026-06-26 | 2026-06-28 | Meter technician |  | 88.14 | Completed | No
WO-26-006659 | 1.4 | Crossroads | CR-S03-01 | Meter exchange | P4 planned | 2026-06-22 | 2026-07-29 | 2026-07-29 | Meter technician |  | 137.92 | Completed | No
WO-26-006660 | 13.6 | Crossroads | CR-S13-01 | New service - small | P4 planned | 2026-06-22 | 2026-07-30 | 2026-07-30 | Underground crew |  | 2219.26 | Completed | No
WO-26-006661 | 4.3 | Crossroads | CR-S15-01 | Preventive maintenance | P4 planned | 2026-06-22 | 2026-07-13 | 2026-07-13 | Underground crew |  | 11.35 | Completed | No
WO-26-006662 | 7.7 | Crossroads | CR-S08-04 | Preventive maintenance | P4 planned | 2026-06-22 | 2026-08-08 | 2026-08-08 | Contract line | CT-02 | 54.43 | Completed | No
WO-26-006663 | 8 | Crossroads | CR-S30-07 | Preventive maintenance | P4 planned | 2026-06-22 | 2026-07-25 | 2026-07-25 | Internal line |  | 387.03 | Completed | No
WO-26-006664 | 6.1 | Crossroads | CR-S23-04 | Preventive maintenance | P4 planned | 2026-06-22 | 2026-07-12 | 2026-07-16 | Contract line | CT-02 | 301.4 | Completed | No
WO-26-006665 | 1.3 | Crossroads | CR-S02-02 | Service order - field | P3 within 10 days | 2026-06-22 | 2026-06-24 | 2026-06-28 | Meter technician |  | 14.72 | Completed | No
WO-26-006666 | 1.9 | Crossroads |  | Streetlight | P4 planned | 2026-06-22 | 2026-07-07 | 2026-07-08 | Internal line |  | 290.12 | Completed | No
WO-26-006667 | 1.7 | Crossroads |  | Streetlight | P4 planned | 2026-06-22 | 2026-07-12 | 2026-07-16 | Internal line |  | 116.71 | Completed | No
WO-26-006668 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-22 | 2026-06-27 | 2026-07-01 | Internal line |  | 180.55 | Completed | No
WO-26-006669 | 2 | Crossroads |  | Streetlight | P4 planned | 2026-06-22 | 2026-07-23 | 2026-07-23 | Contract line | CT-01 | 148.82 | Completed | No
WO-26-006670 | 4.3 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 312.35 | Completed | No
WO-26-006671 | 4.7 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 82.87 | Completed | No
WO-26-006672 | 5.3 | Crossroads | CR-S04-02 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 312.93 | Completed | No
WO-26-006673 | 2.5 | Crossroads | CR-S30-02 | Trouble - no power | P2 same day | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 149.41 | Completed | No
WO-26-006674 |  | Crossroads | CR-S06-03 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 |  | Troubleman |  |  | Cancelled | No
WO-26-006675 | 4.4 | Crossroads | CR-S05-03 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 168.37 | Completed | No
WO-26-006676 | 3.9 | Crossroads | CR-S01-03 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 337.32 | Completed | No
WO-26-006677 | 3.3 | Crossroads | CR-S28-02 | Trouble - no power | P1 emergency | 2026-06-22 | 2026-06-22 | 2026-06-22 | Troubleman |  | 325.68 | Completed | No
WO-26-006678 | 3.9 | Crossroads | CR-S27-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-22 | 2026-06-23 | 2026-06-23 | Troubleman |  | 86.83 | Completed | No
WO-26-006679 | 9.3 | Bayou | BY-S25-01 | Corrective maintenance | P3 within 10 days | 2026-06-23 | 2026-06-24 | 2026-06-24 | Internal line |  | 1689.08 | Completed | No
WO-26-006680 | 4.4 | Bayou | BY-S11-02 | Corrective maintenance | P4 planned | 2026-06-23 | 2026-07-26 | 2026-07-27 | Internal line |  | 2093.89 | Completed | No
WO-26-006681 | 8.3 | Bayou | BY-S28-01 | Corrective maintenance | P3 within 10 days | 2026-06-23 | 2026-06-24 | 2026-06-24 | Underground crew |  | 114.18 | Completed | No
WO-26-006682 | 6.8 | Bayou | BY-S21-02 | Corrective maintenance | P3 within 10 days | 2026-06-23 | 2026-06-29 | 2026-06-29 | Underground crew |  | 920.45 | Completed | No
WO-26-006683 | 9.3 | Bayou | BY-S02-02 | Corrective maintenance | P3 within 10 days | 2026-06-23 | 2026-07-02 | 2026-07-06 | Underground crew |  | 1681.88 | Completed | No
WO-26-006684 | 8.4 | Bayou | BY-S10-03 | Corrective maintenance | P3 within 10 days | 2026-06-23 | 2026-06-26 | 2026-06-26 | Contract line | CT-03 | 158.69 | Completed | No
WO-26-006685 | 1 | Bayou | BY-S29-04 | Meter exchange | P4 planned | 2026-06-23 | 2026-07-22 | 2026-07-22 | Meter technician |  | 135.6 | Completed | No
WO-26-006686 | 1.5 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-06-23 | 2026-06-26 | 2026-06-26 | Meter technician |  | 68.46 | Completed | No
WO-26-006687 | 0.7 | Bayou | BY-S18-06 | Meter exchange | P3 within 10 days | 2026-06-23 | 2026-06-25 | 2026-07-03 | Meter technician |  | 82.02 | Completed | No
WO-26-006688 | 13.2 | Bayou | BY-S16-06 | Pole replacement | P4 planned | 2026-06-23 | 2026-08-04 | 2026-08-05 | Contract line | CT-04 | 1522.18 | Completed | No
WO-26-006689 | 7.7 | Bayou | BY-S30-02 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-07-28 | 2026-07-28 | Contract line | CT-03 | 246.14 | Completed | No
WO-26-006690 | 2.3 | Bayou | BY-S22-04 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-08-01 | 2026-08-03 | Underground crew |  | 109.37 | Completed | No
WO-26-006691 | 2.3 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-08-06 | 2026-08-08 | Internal line |  | 441.15 | Completed | No
WO-26-006692 | 6.3 | Bayou | BY-S05-02 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-07-24 | 2026-07-24 | Contract line | CT-04 | 403.76 | Completed | No
WO-26-006693 | 1.7 | Bayou | BY-S28-01 | Service order - field | P3 within 10 days | 2026-06-23 | 2026-06-26 | 2026-06-30 | Meter technician |  | 8.69 | Completed | No
WO-26-006694 | 1 | Bayou | BY-S27-03 | Service order - field | P3 within 10 days | 2026-06-23 | 2026-06-27 | 2026-06-27 | Meter technician |  | 6.7 | Completed | No
WO-26-006695 | 1 | Bayou | BY-S27-05 | Service order - field | P2 same day | 2026-06-23 | 2026-06-23 | 2026-06-23 | Meter technician |  | 9.3 | Completed | No
WO-26-006696 | 1.1 | Bayou | BY-S24-05 | Service order - field | P2 same day | 2026-06-23 | 2026-06-23 | 2026-06-23 | Meter technician |  | 28.36 | Completed | No
WO-26-006697 | 0.9 | Bayou | BY-S06-01 | Service order - field | P3 within 10 days | 2026-06-23 | 2026-06-24 | 2026-06-25 | Meter technician |  | 36.15 | Completed | No
WO-26-006698 | 13.7 | Bayou | BY-S25-05 | Transformer replacement | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Internal line |  | 8425.38 | Completed | No
WO-26-006699 | 5 | Bayou | BY-S12-01 | Trouble - no power | P2 same day | 2026-06-23 | 2026-06-24 | 2026-06-24 | Internal line |  | 129.36 | Completed | No
WO-26-006700 | 5.9 | Bayou | BY-S13-04 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Troubleman |  | 143.28 | Completed | No
WO-26-006701 | 2.4 | Bayou | BY-S16-04 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Internal line |  | 253.57 | Completed | No
WO-26-006702 |  | Bayou | BY-S12-01 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 |  | Troubleman |  |  | Cancelled | No
WO-26-006703 | 4.2 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Troubleman |  | 65.86 | Completed | No
WO-26-006704 | 3.5 | Bayou | BY-S09-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-23 | 2026-06-26 | 2026-06-26 | Troubleman |  | 102.99 | Completed | No
WO-26-006705 | 1.9 | Bayou | BY-S14-03 | Trouble - partial or voltage | P2 same day | 2026-06-23 | 2026-06-23 | 2026-06-23 | Troubleman |  | 59.43 | Completed | No
WO-26-006706 | 8.3 | Crossroads | CR-S06-01 | Corrective maintenance | P4 planned | 2026-06-23 | 2026-07-25 | 2026-07-25 | Underground crew |  | 125.17 | Completed | No
WO-26-006707 | 7.5 | Crossroads | CR-S17-01 | Corrective maintenance | P4 planned | 2026-06-23 | 2026-07-31 | 2026-07-31 | Internal line |  | 1815.52 | Completed | No
WO-26-006708 | 10.7 | Crossroads | CR-S08-03 | Corrective maintenance | P2 same day | 2026-06-23 | 2026-06-23 | 2026-06-23 | Underground crew |  | 796.95 | Completed | No
WO-26-006709 | 5.1 | Crossroads | CR-S29-01 | Corrective maintenance | P3 within 10 days | 2026-06-23 | 2026-06-24 | 2026-06-28 | Contract line | CT-02 | 1011.16 | Completed | No
WO-26-006710 | 9.6 | Crossroads | CR-S14-04 | Corrective maintenance | P4 planned | 2026-06-23 | 2026-08-22 | 2026-08-23 | Internal line |  | 621.46 | Completed | No
WO-26-006711 | 1.2 | Crossroads | CR-S23-05 | Meter exchange | P3 within 10 days | 2026-06-23 | 2026-07-01 | 2026-07-02 | Meter technician |  | 134.38 | Completed | No
WO-26-006712 | 0.7 | Crossroads | CR-S10-02 | Meter exchange | P3 within 10 days | 2026-06-23 | 2026-06-26 | 2026-06-26 | Meter technician |  | 122.75 | Completed | No
WO-26-006713 |  | Crossroads | CR-S16-03 | Meter exchange | P4 planned | 2026-06-23 | 2026-07-06 |  | Meter technician |  |  | Cancelled | No
WO-26-006714 | 21.3 | Crossroads | CR-S26-06 | Pole replacement | P3 within 10 days | 2026-06-23 | 2026-06-25 | 2026-06-25 | Internal line |  | 2327.57 | Completed | No
WO-26-006715 | 16.5 | Crossroads | CR-S25-03 | Pole replacement | P3 within 10 days | 2026-06-23 | 2026-06-24 | 2026-07-02 | Internal line |  | 1721.03 | Completed | No
WO-26-006716 | 4.9 | Crossroads | CR-S08-06 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-07-29 | 2026-07-29 | Underground crew |  | 364.59 | Completed | No
WO-26-006717 | 7.7 | Crossroads | CR-S15-01 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-08-06 | 2026-08-06 | Internal line |  | 531.02 | Completed | No
WO-26-006718 | 3.9 | Crossroads | CR-S26-02 | Preventive maintenance | P4 planned | 2026-06-23 | 2026-07-22 | 2026-07-23 | Underground crew |  | 71.43 | Completed | No
WO-26-006719 | 1.8 | Crossroads | CR-S07-06 | Service order - field | P2 same day | 2026-06-23 | 2026-06-24 | 2026-06-24 | Meter technician |  | 29.4 | Completed | No
WO-26-006720 | 1.7 | Crossroads | CR-S04-03 | Service order - field | P3 within 10 days | 2026-06-23 | 2026-07-01 | 2026-07-01 | Meter technician |  | 32.96 | Completed | No
WO-26-006721 | 0.6 | Crossroads | CR-S16-05 | Service order - field | P2 same day | 2026-06-23 | 2026-06-23 | 2026-06-23 | Meter technician |  | 22.02 | Completed | No
WO-26-006722 | 1.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-23 | 2026-06-27 | 2026-06-27 | Contract line | CT-02 | 280.68 | Completed | No
WO-26-006723 | 1.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-23 | 2026-06-28 | 2026-06-28 | Internal line |  | 331.16 | Completed | No
WO-26-006724 | 1.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-23 | 2026-06-29 | 2026-06-29 | Contract line | CT-02 | 330.54 | Completed | No
WO-26-006725 | 1.8 | Crossroads |  | Streetlight | P4 planned | 2026-06-23 | 2026-07-30 | 2026-07-31 | Contract line | CT-01 | 62.62 | Completed | No
WO-26-006726 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-23 | 2026-06-24 | 2026-06-26 | Contract line | CT-01 | 346.39 | Completed | No
WO-26-006727 | 9.2 | Crossroads | CR-S08-03 | Transformer replacement | P2 same day | 2026-06-23 | 2026-06-24 | 2026-06-24 | Internal line |  | 3734.09 | Completed | No
WO-26-006728 | 5 | Crossroads | CR-S07-01 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Troubleman |  | 198.28 | Completed | No
WO-26-006729 | 5 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Troubleman |  | 342.88 | Completed | No
WO-26-006730 | 4.7 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-06-23 | 2026-06-23 | 2026-06-23 | Troubleman |  | 159.8 | Completed | No
WO-26-006731 | 2 | Crossroads | CR-S31-02 | Trouble - no power | P2 same day | 2026-06-23 | 2026-06-24 | 2026-06-24 | Troubleman |  | 341.64 | Completed | No
WO-26-006732 | 2.3 | Crossroads | CR-S16-05 | Trouble - partial or voltage | P2 same day | 2026-06-23 | 2026-06-24 | 2026-06-24 | Troubleman |  | 21.48 | Completed | No
WO-26-006733 | 7.1 | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-06-24 | 2026-08-11 | 2026-08-11 | Underground crew |  | 2089.02 | Completed | No
WO-26-006734 | 7.4 | Bayou | BY-S24-01 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-07-02 | 2026-07-06 | Contract line | CT-03 | 1157.32 | Completed | No
WO-26-006735 | 3.7 | Bayou | BY-S21-02 | Corrective maintenance | P2 same day | 2026-06-24 | 2026-06-24 | 2026-06-24 | Contract line | CT-03 | 575.61 | Completed | No
WO-26-006736 | 6.6 | Bayou | BY-S22-03 | Corrective maintenance | P4 planned | 2026-06-24 | 2026-07-28 | 2026-07-28 | Contract line | CT-03 | 890.02 | Completed | No
WO-26-006737 | 3.9 | Bayou | BY-S09-01 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-07-01 | 2026-07-01 | Internal line |  | 988.38 | Completed | No
WO-26-006738 | 9.4 | Bayou | BY-S16-01 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-06-29 | 2026-07-03 | Underground crew |  | 1818.94 | Completed | No
WO-26-006739 | 5.4 | Bayou | BY-S10-04 | Corrective maintenance | P4 planned | 2026-06-24 | 2026-07-03 | 2026-07-03 | Underground crew |  | 1478.59 | Completed | No
WO-26-006740 | 6.4 | Bayou | BY-S28-02 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-06-30 | 2026-07-02 | Contract line | CT-04 | 1955.24 | Completed | No
WO-26-006741 | 8.2 | Bayou | BY-S18-05 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-06-27 | 2026-06-27 | Internal line |  | 2245.98 | Completed | No
WO-26-006742 | 5.6 | Bayou | BY-S15-02 | Corrective maintenance | P4 planned | 2026-06-24 | 2026-08-08 | 2026-08-09 | Internal line |  | 1165.62 | Completed | No
WO-26-006743 | 0.7 | Bayou | BY-S06-02 | Meter exchange | P3 within 10 days | 2026-06-24 | 2026-06-25 | 2026-06-27 | Meter technician |  | 172.95 | Completed | No
WO-26-006744 | 1 | Bayou | BY-S13-04 | Meter exchange | P4 planned | 2026-06-24 | 2026-08-21 | 2026-08-25 | Meter technician |  | 67.53 | Completed | No
WO-26-006745 | 0.7 | Bayou | BY-S23-02 | Meter exchange | P3 within 10 days | 2026-06-24 | 2026-06-27 | 2026-07-01 | Meter technician |  | 104.08 | Completed | No
WO-26-006746 | 1.3 | Bayou | BY-S10-04 | Meter exchange | P3 within 10 days | 2026-06-24 | 2026-06-28 | 2026-06-28 | Meter technician |  | 73 | Completed | No
WO-26-006747 | 1.2 | Bayou | BY-S23-02 | Meter exchange | P3 within 10 days | 2026-06-24 | 2026-06-27 | 2026-06-27 | Meter technician |  | 80.15 | Completed | No
WO-26-006748 | 1.3 | Bayou | BY-S17-03 | Meter exchange | P3 within 10 days | 2026-06-24 | 2026-07-01 | 2026-07-05 | Meter technician |  | 146.41 | Completed | No
WO-26-006749 | 7.3 | Bayou | BY-S06-02 | New service - small | P3 within 10 days | 2026-06-24 | 2026-06-28 | 2026-06-28 | Internal line |  | 1842.81 | Completed | No
WO-26-006750 | 4 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-06-24 | 2026-07-29 | 2026-07-31 | Internal line |  | 208.33 | Completed | No
WO-26-006751 | 3.7 | Bayou | BY-S20-02 | Preventive maintenance | P4 planned | 2026-06-24 | 2026-07-17 | 2026-07-17 | Internal line |  | 395.13 | Completed | No
WO-26-006752 | 5.7 | Bayou | BY-S04-03 | Preventive maintenance | P4 planned | 2026-06-24 | 2026-07-13 | 2026-07-13 | Internal line |  | 311.07 | Completed | No
WO-26-006753 | 1.7 | Bayou | BY-S29-02 | Service order - field | P2 same day | 2026-06-24 | 2026-06-24 | 2026-06-24 | Meter technician |  | 8.64 | Completed | No
WO-26-006754 | 0.6 | Bayou | BY-S16-06 | Service order - field | P3 within 10 days | 2026-06-24 | 2026-07-01 | 2026-07-01 | Meter technician |  | 7.3 | Completed | No
WO-26-006755 | 1.3 | Bayou | BY-S23-04 | Service order - field | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Meter technician |  | 16.54 | Completed | No
WO-26-006756 | 1.4 | Bayou | BY-S13-05 | Service order - field | P3 within 10 days | 2026-06-24 | 2026-07-01 | 2026-07-09 | Meter technician |  | 27.53 | Completed | No
WO-26-006757 | 1.3 | Bayou | BY-S23-03 | Service order - field | P3 within 10 days | 2026-06-24 | 2026-06-29 | 2026-06-29 | Meter technician |  | 29.5 | Completed | No
WO-26-006758 | 6.2 | Bayou | BY-S23-03 | Transformer replacement | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Internal line |  | 10750.16 | Completed | No
WO-26-006759 | 3.4 | Bayou | BY-S16-02 | Trouble - no power | P2 same day | 2026-06-24 | 2026-06-24 | 2026-06-24 | Troubleman |  | 347.66 | Completed | No
WO-26-006760 | 3.1 | Bayou | BY-S16-04 | Trouble - no power | P2 same day | 2026-06-24 | 2026-06-24 | 2026-06-24 | Internal line |  | 120.31 | Completed | No
WO-26-006761 | 3.8 | Crossroads | CR-S13-01 | Corrective maintenance | P4 planned | 2026-06-24 | 2026-07-30 | 2026-08-03 | Internal line |  | 1219.67 | Completed | No
WO-26-006762 | 10 | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-07-01 | 2026-07-03 | Contract line | CT-02 | 796.96 | Completed | No
WO-26-006763 | 3.9 | Crossroads | CR-S03-02 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-06-29 | 2026-06-30 | Contract line | CT-01 | 1739.89 | Completed | No
WO-26-006764 | 3.1 | Crossroads | CR-S18-02 | Corrective maintenance | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Contract line | CT-02 | 1834.27 | Completed | No
WO-26-006765 | 11.1 | Crossroads | CR-S32-04 | Corrective maintenance | P3 within 10 days | 2026-06-24 | 2026-06-30 | 2026-07-04 | Contract line | CT-01 | 900.46 | Completed | No
WO-26-006766 | 0.6 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-06-24 | 2026-06-29 | 2026-06-29 | Meter technician |  | 160.38 | Completed | No
WO-26-006767 | 0.8 | Crossroads | CR-S23-02 | Meter exchange | P4 planned | 2026-06-24 | 2026-07-31 | 2026-07-31 | Meter technician |  | 82.11 | Completed | No
WO-26-006768 | 17.8 | Crossroads | CR-S18-04 | Pole replacement | P3 within 10 days | 2026-06-24 | 2026-07-03 | 2026-07-07 | Contract line | CT-02 | 1729.46 | Completed | No
WO-26-006769 | 4.4 | Crossroads | CR-S09-01 | Preventive maintenance | P4 planned | 2026-06-24 | 2026-08-19 | 2026-08-23 | Underground crew |  | 210 | Completed | No
WO-26-006770 | 2.5 | Crossroads | CR-S13-02 | Preventive maintenance | P4 planned | 2026-06-24 | 2026-07-22 | 2026-07-22 | Internal line |  | 449.91 | Completed | No
WO-26-006771 |  | Crossroads | CR-S24-01 | Preventive maintenance | P4 planned | 2026-06-24 | 2026-08-10 |  | Contract line | CT-01 |  | Cancelled | No
WO-26-006772 | 1.2 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Meter technician |  | 1.32 | Completed | No
WO-26-006773 | 1.9 | Crossroads | CR-S23-04 | Service order - field | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Meter technician |  | 35.93 | Completed | No
WO-26-006774 | 2.8 | Crossroads |  | Streetlight | P4 planned | 2026-06-24 | 2026-07-03 | 2026-07-11 | Contract line | CT-02 | 81.14 | Completed | No
WO-26-006775 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-24 | 2026-06-25 | 2026-06-27 | Contract line | CT-02 | 379.86 | Completed | No
WO-26-006776 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-24 | 2026-06-30 | 2026-07-04 | Contract line | CT-01 | 222.99 | Completed | No
WO-26-006777 | 10.2 | Crossroads | CR-S26-02 | Transformer replacement | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Internal line |  | 3612.3 | Completed | No
WO-26-006778 | 2.4 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 | 2026-06-24 | Internal line |  | 48.3 | Completed | No
WO-26-006779 | 4.4 | Crossroads | CR-S07-07 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 | 2026-06-24 | Internal line |  | 200.83 | Completed | No
WO-26-006780 | 3.4 | Crossroads | CR-S03-01 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 | 2026-06-24 | Troubleman |  | 259.56 | Completed | No
WO-26-006781 | 4.7 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 | 2026-06-24 | Troubleman |  | 150.5 | Completed | No
WO-26-006782 | 2.7 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 | 2026-06-24 | Troubleman |  | 312.58 | Completed | No
WO-26-006783 | 2.7 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 | 2026-06-24 | Troubleman |  | 145.6 | Completed | No
WO-26-006784 | 4.3 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Troubleman |  | 49.74 | Completed | No
WO-26-006785 |  | Crossroads | CR-S28-01 | Trouble - no power | P1 emergency | 2026-06-24 | 2026-06-24 |  | Internal line |  |  | Cancelled | No
WO-26-006786 | 5.4 | Crossroads | CR-S18-04 | Trouble - no power | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Troubleman |  | 337.25 | Completed | No
WO-26-006787 | 4.7 | Crossroads | CR-S08-01 | Trouble - no power | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Internal line |  | 228.69 | Completed | No
WO-26-006788 | 1.9 | Crossroads | CR-S26-03 | Trouble - partial or voltage | P2 same day | 2026-06-24 | 2026-06-25 | 2026-06-25 | Troubleman |  | 150.17 | Completed | No
WO-26-006789 | 8.1 | Bayou | BY-S29-02 | Corrective maintenance | P3 within 10 days | 2026-06-25 | 2026-06-26 | 2026-06-26 | Internal line |  | 380.91 | Completed | No
WO-26-006790 | 5.8 | Bayou | BY-S06-01 | Corrective maintenance | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Contract line | CT-03 | 307.03 | Completed | No
WO-26-006791 | 1 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-06-25 | 2026-07-05 | 2026-07-09 | Meter technician |  | 87.02 | Completed | No
WO-26-006792 | 9.4 | Bayou | BY-S08-02 | New service - small | P4 planned | 2026-06-25 | 2026-07-30 | 2026-08-03 | Contract line | CT-04 | 1803.17 | Completed | No
WO-26-006793 | 17.4 | Bayou | BY-S09-01 | Pole replacement | P3 within 10 days | 2026-06-25 | 2026-07-02 | 2026-07-02 | Internal line |  | 2431.63 | Completed | No
WO-26-006794 | 3.9 | Bayou | BY-S07-02 | Preventive maintenance | P4 planned | 2026-06-25 | 2026-08-15 | 2026-08-15 | Underground crew |  | 281.64 | Completed | No
WO-26-006795 | 4.4 | Bayou | BY-S06-02 | Preventive maintenance | P4 planned | 2026-06-25 | 2026-07-30 | 2026-07-31 | Internal line |  | 211.1 | Completed | No
WO-26-006796 | 0.7 | Bayou | BY-S26-05 | Service order - field | P3 within 10 days | 2026-06-25 | 2026-06-28 | 2026-06-30 | Meter technician |  | 28.09 | Completed | No
WO-26-006797 | 1.2 | Bayou | BY-S14-03 | Service order - field | P3 within 10 days | 2026-06-25 | 2026-06-28 | 2026-06-29 | Meter technician |  | 33.9 | Completed | No
WO-26-006798 | 1.5 | Bayou | BY-S16-01 | Service order - field | P3 within 10 days | 2026-06-25 | 2026-06-28 | 2026-06-29 | Meter technician |  | 6.43 | Completed | No
WO-26-006799 | 1.7 | Bayou | BY-S17-01 | Service order - field | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Meter technician |  | 31.76 | Completed | No
WO-26-006800 | 0.8 | Bayou | BY-S02-01 | Service order - field | P2 same day | 2026-06-25 | 2026-06-25 | 2026-06-25 | Meter technician |  | 34.98 | Completed | No
WO-26-006801 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-25 | 2026-07-05 | 2026-07-09 | Contract line | CT-04 | 96.12 | Completed | No
WO-26-006802 | 11.4 | Bayou | BY-S29-04 | Transformer replacement | P3 within 10 days | 2026-06-25 | 2026-06-26 | 2026-06-27 | Internal line |  | 3858.95 | Completed | No
WO-26-006803 | 7.8 | Bayou | BY-S24-04 | Transformer replacement | P2 same day | 2026-06-25 | 2026-06-25 | 2026-06-25 | Contract line | CT-03 | 11835.88 | Completed | No
WO-26-006804 | 4.4 | Bayou | BY-S24-04 | Trouble - no power | P2 same day | 2026-06-25 | 2026-06-25 | 2026-06-25 | Internal line |  | 91.86 | Completed | No
WO-26-006805 | 3.1 | Bayou | BY-S10-01 | Trouble - no power | P1 emergency | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 243.82 | Completed | No
WO-26-006806 | 4.7 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 148.21 | Completed | No
WO-26-006807 | 2.2 | Bayou | BY-S29-04 | Trouble - partial or voltage | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Troubleman |  | 5.59 | Completed | No
WO-26-006808 | 4.6 | Bayou | BY-S19-04 | Trouble - partial or voltage | P3 within 10 days | 2026-06-25 | 2026-06-26 | 2026-06-26 | Troubleman |  | 84.33 | Completed | No
WO-26-006809 | 3.6 | Bayou | BY-S27-06 | Trouble - partial or voltage | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Troubleman |  | 142.83 | Completed | No
WO-26-006810 | 4.2 | Bayou | BY-S18-05 | Trouble - partial or voltage | P2 same day | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 85.44 | Completed | No
WO-26-006811 | 9.6 | Crossroads | CR-S08-02 | Corrective maintenance | P3 within 10 days | 2026-06-25 | 2026-06-26 | 2026-06-27 | Underground crew |  | 166.07 | Completed | No
WO-26-006812 | 0.9 | Crossroads | CR-S16-04 | Meter exchange | P4 planned | 2026-06-25 | 2026-07-07 | 2026-07-07 | Meter technician |  | 108.02 | Completed | No
WO-26-006813 | 0.8 | Crossroads | CR-S32-01 | Meter exchange | P3 within 10 days | 2026-06-25 | 2026-07-02 | 2026-07-06 | Meter technician |  | 150.58 | Completed | No
WO-26-006814 | 0.8 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-06-25 | 2026-06-28 | 2026-07-06 | Meter technician |  | 105.86 | Completed | No
WO-26-006815 | 0.9 | Crossroads | CR-S05-02 | Meter exchange | P4 planned | 2026-06-25 | 2026-08-02 | 2026-08-03 | Meter technician |  | 146.35 | Completed | No
WO-26-006816 |  | Crossroads | CR-S08-04 | Meter exchange | P3 within 10 days | 2026-06-25 | 2026-06-26 |  | Meter technician |  |  | Cancelled | No
WO-26-006817 | 0.8 | Crossroads | CR-S05-02 | Meter exchange | P4 planned | 2026-06-25 | 2026-07-07 | 2026-07-15 | Meter technician |  | 147.07 | Completed | No
WO-26-006818 | 1.4 | Crossroads | CR-S12-01 | Meter exchange | P3 within 10 days | 2026-06-25 | 2026-06-27 | 2026-07-01 | Meter technician |  | 82.13 | Completed | No
WO-26-006819 | 9 | Crossroads | CR-S20-03 | New service - small | P4 planned | 2026-06-25 | 2026-08-18 | 2026-08-18 | Contract line | CT-02 | 1609.28 | Completed | No
WO-26-006820 | 12.6 | Crossroads | CR-S26-02 | Pole replacement | P3 within 10 days | 2026-06-25 | 2026-07-04 | 2026-07-04 | Internal line |  | 2855.47 | Completed | No
WO-26-006821 | 19.7 | Crossroads | CR-S17-01 | Pole replacement | P3 within 10 days | 2026-06-25 | 2026-06-28 | 2026-06-30 | Contract line | CT-01 | 3096.98 | Completed | No
WO-26-006822 | 7.3 | Crossroads | CR-S13-06 | Preventive maintenance | P4 planned | 2026-06-25 | 2026-08-23 | 2026-08-23 | Contract line | CT-01 | 205.74 | Completed | No
WO-26-006823 | 2.7 | Crossroads | CR-S14-03 | Preventive maintenance | P4 planned | 2026-06-25 | 2026-08-05 | 2026-08-06 | Underground crew |  | 159.51 | Completed | No
WO-26-006824 | 2.8 | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-06-25 | 2026-07-29 | 2026-07-30 | Underground crew |  | 213.96 | Completed | No
WO-26-006825 | 0.9 | Crossroads | CR-S08-06 | Service order - field | P3 within 10 days | 2026-06-25 | 2026-06-27 | 2026-06-28 | Meter technician |  | 20.87 | Completed | No
WO-26-006826 | 1.6 | Crossroads | CR-S17-03 | Service order - field | P3 within 10 days | 2026-06-25 | 2026-06-29 | 2026-07-03 | Meter technician |  | 18.37 | Completed | No
WO-26-006827 | 2 | Crossroads | CR-S16-06 | Service order - field | P2 same day | 2026-06-25 | 2026-06-25 | 2026-06-25 | Meter technician |  | 3.91 | Completed | No
WO-26-006828 | 1.3 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Meter technician |  | 33.62 | Completed | No
WO-26-006829 | 1.7 | Crossroads | CR-S10-01 | Service order - field | P3 within 10 days | 2026-06-25 | 2026-06-28 | 2026-06-28 | Meter technician |  | 32.88 | Completed | No
WO-26-006830 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-25 | 2026-07-02 | 2026-07-02 | Contract line | CT-01 | 52.6 | Completed | No
WO-26-006831 | 8.7 | Crossroads | CR-S18-02 | Transformer replacement | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Contract line | CT-01 | 7118.68 | Completed | No
WO-26-006832 | 4.4 | Crossroads | CR-S23-02 | Trouble - no power | P1 emergency | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 329.37 | Completed | No
WO-26-006833 | 4.6 | Crossroads | CR-S23-05 | Trouble - no power | P1 emergency | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 125.01 | Completed | No
WO-26-006834 | 5.2 | Crossroads | CR-S06-03 | Trouble - no power | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Troubleman |  | 251.64 | Completed | No
WO-26-006835 | 5.5 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 252.34 | Completed | No
WO-26-006836 | 4.2 | Crossroads | CR-S23-05 | Trouble - partial or voltage | P2 same day | 2026-06-25 | 2026-06-26 | 2026-06-26 | Troubleman |  | 106.19 | Completed | No
WO-26-006837 | 2.6 | Crossroads | CR-S23-04 | Trouble - partial or voltage | P2 same day | 2026-06-25 | 2026-06-25 | 2026-06-25 | Troubleman |  | 138.66 | Completed | No
WO-26-006838 | 11.2 | Bayou | BY-S15-04 | Corrective maintenance | P3 within 10 days | 2026-06-26 | 2026-06-27 | 2026-06-27 | Internal line |  | 1860.81 | Completed | No
WO-26-006839 | 5.8 | Bayou | BY-S01-01 | Corrective maintenance | P3 within 10 days | 2026-06-26 | 2026-07-06 | 2026-07-07 | Underground crew |  | 1411.74 | Completed | No
WO-26-006840 | 6.3 | Bayou | BY-S04-03 | Corrective maintenance | P3 within 10 days | 2026-06-26 | 2026-06-30 | 2026-06-30 | Internal line |  | 95.31 | Completed | No
WO-26-006841 | 11.8 | Bayou | BY-S28-03 | Corrective maintenance | P3 within 10 days | 2026-06-26 | 2026-06-29 | 2026-06-30 | Contract line | CT-04 | 1739.19 | Completed | No
WO-26-006842 | 7.5 | Bayou | BY-S23-05 | Corrective maintenance | P2 same day | 2026-06-26 | 2026-06-27 | 2026-06-27 | Contract line | CT-03 | 587 | Completed | No
WO-26-006843 | 0.9 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-06-26 | 2026-06-27 | 2026-07-01 | Meter technician |  | 147.92 | Completed | No
WO-26-006844 | 0.9 | Bayou | BY-S09-05 | Meter exchange | P4 planned | 2026-06-26 | 2026-07-10 | 2026-07-12 | Meter technician |  | 106.88 | Completed | No
WO-26-006845 | 1 | Bayou | BY-S23-03 | Meter exchange | P4 planned | 2026-06-26 | 2026-07-29 | 2026-07-29 | Meter technician |  | 97.77 | Completed | No
WO-26-006846 | 5 | Bayou | BY-S07-06 | New service - small | P3 within 10 days | 2026-06-26 | 2026-06-28 | 2026-06-28 | Internal line |  | 2563.94 | Completed | No
WO-26-006847 | 17.6 | Bayou | BY-S22-04 | Pole replacement | P4 planned | 2026-06-26 | 2026-07-09 | 2026-07-11 | Internal line |  | 1762.64 | Completed | No
WO-26-006848 | 16.7 | Bayou | BY-S09-03 | Pole replacement | P2 same day | 2026-06-26 | 2026-06-27 | 2026-06-27 | Internal line |  | 2091.25 | Completed | No
WO-26-006849 | 2.5 | Bayou | BY-S15-01 | Preventive maintenance | P4 planned | 2026-06-26 | 2026-07-31 | 2026-08-01 | Internal line |  | 322.96 | Completed | No
WO-26-006850 | 1 | Bayou | BY-S18-02 | Service order - field | P3 within 10 days | 2026-06-26 | 2026-06-30 | 2026-06-30 | Meter technician |  | 4.92 | Completed | No
WO-26-006851 | 0.8 | Bayou | BY-S13-01 | Service order - field | P3 within 10 days | 2026-06-26 | 2026-06-28 | 2026-06-28 | Meter technician |  | 22.52 | Completed | No
WO-26-006852 | 1.9 | Bayou | BY-S06-01 | Service order - field | P2 same day | 2026-06-26 | 2026-06-26 | 2026-06-26 | Meter technician |  | 35.66 | Completed | No
WO-26-006853 | 1.7 | Bayou | BY-S02-01 | Service order - field | P2 same day | 2026-06-26 | 2026-06-26 | 2026-06-26 | Meter technician |  | 14.48 | Completed | No
WO-26-006854 | 1.1 | Bayou | BY-S13-06 | Service order - field | P3 within 10 days | 2026-06-26 | 2026-06-30 | 2026-07-01 | Meter technician |  | 21.44 | Completed | No
WO-26-006855 | 1.7 | Bayou | BY-S26-05 | Service order - field | P2 same day | 2026-06-26 | 2026-06-27 | 2026-06-27 | Meter technician |  | 29.75 | Completed | No
WO-26-006856 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-26 | 2026-07-03 | 2026-07-03 | Contract line | CT-04 | 441.1 | Completed | No
WO-26-006857 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-26 | 2026-07-05 | 2026-07-05 | Contract line | CT-04 | 134.54 | Completed | No
WO-26-006858 | 7.4 | Bayou | BY-S12-02 | Transformer replacement | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 10235.01 | Completed | No
WO-26-006859 | 4.1 | Bayou | BY-S29-02 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 155.69 | Completed | No
WO-26-006860 | 2 | Bayou | BY-S18-06 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 283.89 | Completed | No
WO-26-006861 | 5.2 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 267.45 | Completed | No
WO-26-006862 | 6 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 206.73 | Completed | No
WO-26-006863 | 5.1 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 257.97 | Completed | No
WO-26-006864 | 5.8 | Bayou | BY-S18-05 | Trouble - no power | P2 same day | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 24.49 | Completed | No
WO-26-006865 | 1.7 | Bayou | BY-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-06-26 | 2026-07-06 | 2026-07-06 | Troubleman |  | 161.5 | Completed | No
WO-26-006866 | 2 | Bayou | BY-S27-06 | Trouble - partial or voltage | P3 within 10 days | 2026-06-26 | 2026-07-02 | 2026-07-02 | Troubleman |  | 209.01 | Completed | No
WO-26-006867 | 6.1 | Crossroads | CR-S23-04 | Corrective maintenance | P3 within 10 days | 2026-06-26 | 2026-06-29 | 2026-07-03 | Internal line |  | 1184.35 | Completed | No
WO-26-006868 | 7.4 | Crossroads | CR-S06-03 | Corrective maintenance | P3 within 10 days | 2026-06-26 | 2026-07-06 | 2026-07-06 | Internal line |  | 2298.08 | Completed | No
WO-26-006869 | 0.7 | Crossroads | CR-S11-01 | Meter exchange | P4 planned | 2026-06-26 | 2026-08-15 | 2026-08-15 | Meter technician |  | 113.49 | Completed | No
WO-26-006870 | 0.7 | Crossroads | CR-S14-03 | Meter exchange | P3 within 10 days | 2026-06-26 | 2026-07-04 | 2026-07-05 | Meter technician |  | 162.81 | Completed | No
WO-26-006871 | 0.7 | Crossroads | CR-S15-03 | Meter exchange | P4 planned | 2026-06-26 | 2026-08-04 | 2026-08-04 | Meter technician |  | 104.34 | Completed | No
WO-26-006872 | 1.1 | Crossroads | CR-S02-05 | Meter exchange | P3 within 10 days | 2026-06-26 | 2026-06-27 | 2026-06-28 | Meter technician |  | 63.78 | Completed | No
WO-26-006873 | 1.2 | Crossroads | CR-S14-06 | Meter exchange | P3 within 10 days | 2026-06-26 | 2026-07-01 | 2026-07-01 | Meter technician |  | 78.41 | Completed | No
WO-26-006874 | 9.8 | Crossroads | CR-S03-01 | New service - small | P4 planned | 2026-06-26 | 2026-08-01 | 2026-08-03 | Contract line | CT-01 | 798.11 | Completed | No
WO-26-006875 | 11.3 | Crossroads | CR-S08-01 | Pole replacement | P3 within 10 days | 2026-06-26 | 2026-07-02 | 2026-07-03 | Contract line | CT-02 | 3283.01 | Completed | No
WO-26-006876 | 2.2 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-06-26 | 2026-08-15 | 2026-08-17 | Contract line | CT-01 | 399.78 | Completed | No
WO-26-006877 | 3.8 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-06-26 | 2026-07-15 | 2026-07-17 | Internal line |  | 134.54 | Completed | No
WO-26-006878 | 7.1 | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-06-26 | 2026-08-11 | 2026-08-15 | Underground crew |  | 53.85 | Completed | No
WO-26-006879 | 7.6 | Crossroads | CR-S32-04 | Preventive maintenance | P4 planned | 2026-06-26 | 2026-08-02 | 2026-08-02 | Internal line |  | 16.41 | Completed | No
WO-26-006880 | 3.7 | Crossroads | CR-S07-05 | Preventive maintenance | P4 planned | 2026-06-26 | 2026-07-18 | 2026-07-22 | Contract line | CT-02 | 44.92 | Completed | No
WO-26-006881 | 1.2 | Crossroads | CR-S18-02 | Service order - field | P2 same day | 2026-06-26 | 2026-06-27 | 2026-06-27 | Meter technician |  | 15.89 | Completed | No
WO-26-006882 | 1.4 | Crossroads | CR-S01-01 | Service order - field | P3 within 10 days | 2026-06-26 | 2026-07-02 | 2026-07-02 | Meter technician |  | 11.49 | Completed | No
WO-26-006883 | 0.8 | Crossroads | CR-S16-04 | Service order - field | P2 same day | 2026-06-26 | 2026-06-26 | 2026-06-26 | Meter technician |  | 32.12 | Completed | No
WO-26-006884 | 1 | Crossroads | CR-S32-04 | Service order - field | P3 within 10 days | 2026-06-26 | 2026-07-02 | 2026-07-02 | Meter technician |  | 32.61 | Completed | No
WO-26-006885 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-26 | 2026-07-02 |  | Contract line | CT-01 |  | Cancelled | No
WO-26-006886 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-26 | 2026-07-02 | 2026-07-02 | Contract line | CT-02 | 342.97 | Completed | No
WO-26-006887 | 7.2 | Crossroads | CR-S14-04 | Transformer replacement | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 4660.4 | Completed | No
WO-26-006888 | 2.4 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 6.9 | Completed | No
WO-26-006889 | 5.1 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 1.03 | Completed | No
WO-26-006890 | 5.9 | Crossroads | CR-S30-03 | Trouble - no power | P2 same day | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 46.51 | Completed | No
WO-26-006891 | 3.8 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 305.67 | Completed | No
WO-26-006892 | 5.5 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Troubleman |  | 206.28 | Completed | No
WO-26-006893 | 4.2 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 125.24 | Completed | No
WO-26-006894 | 1.7 | Crossroads | CR-S08-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-26 | 2026-06-28 | 2026-06-28 | Troubleman |  | 93.37 | Completed | No
WO-26-006895 | 3 | Crossroads | CR-S19-04 | Trouble - partial or voltage | P2 same day | 2026-06-26 | 2026-06-26 | 2026-06-26 | Internal line |  | 5.74 | Completed | No
WO-26-006896 | 16.2 | Bayou | BY-S17-04 | Pole replacement | P2 same day | 2026-06-27 | 2026-06-27 | 2026-06-27 | Contract line | CT-03 | 3499.13 | Completed | No
WO-26-006897 | 1.3 | Bayou | BY-S08-03 | Service order - field | P2 same day | 2026-06-27 | 2026-06-27 | 2026-06-27 | Meter technician |  | 5.78 | Completed | No
WO-26-006898 | 2 | Bayou | BY-S04-01 | Service order - field | P2 same day | 2026-06-27 | 2026-06-28 | 2026-06-28 | Meter technician |  | 34.25 | Completed | No
WO-26-006899 | 0.6 | Bayou | BY-S07-03 | Service order - field | P2 same day | 2026-06-27 | 2026-06-28 | 2026-06-28 | Meter technician |  | 17.61 | Completed | No
WO-26-006900 | 0.6 | Bayou | BY-S09-04 | Service order - field | P2 same day | 2026-06-27 | 2026-06-28 | 2026-06-28 | Meter technician |  | 35.54 | Completed | No
WO-26-006901 | 9.7 | Bayou | BY-S06-02 | Transformer replacement | P2 same day | 2026-06-27 | 2026-06-27 | 2026-06-27 | Internal line |  | 8234.53 | Completed | No
WO-26-006902 | 4.1 | Bayou | BY-S13-05 | Trouble - no power | P2 same day | 2026-06-27 | 2026-06-28 | 2026-06-28 | Troubleman |  | 134.3 | Completed | No
WO-26-006903 | 4.6 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-06-27 | 2026-06-27 | 2026-06-27 | Troubleman |  | 313.68 | Completed | No
WO-26-006904 |  | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-06-27 | 2026-06-27 |  | Troubleman |  |  | Cancelled | No
WO-26-006905 | 3.4 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-06-27 | 2026-06-27 | 2026-06-27 | Troubleman |  | 71.6 | Completed | No
WO-26-006906 | 1.3 | Crossroads | CR-S27-03 | Service order - field | P2 same day | 2026-06-27 | 2026-06-27 | 2026-06-27 | Meter technician |  | 35.89 | Completed | No
WO-26-006907 | 6.8 | Crossroads | CR-S19-02 | Transformer replacement | P1 emergency | 2026-06-27 | 2026-06-27 | 2026-06-27 | Internal line |  | 8916.33 | Completed | No
WO-26-006908 | 5 | Crossroads | CR-S07-02 | Trouble - no power | P2 same day | 2026-06-27 | 2026-06-27 | 2026-06-27 | Troubleman |  | 234.34 | Completed | No
WO-26-006909 | 4.7 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-06-27 | 2026-06-27 | 2026-06-27 | Troubleman |  | 74.67 | Completed | No
WO-26-006910 | 4.7 | Crossroads | CR-S18-06 | Trouble - no power | P1 emergency | 2026-06-27 | 2026-06-27 | 2026-06-27 | Troubleman |  | 118 | Completed | No
WO-26-006911 | 3.5 | Crossroads | CR-S18-03 | Trouble - no power | P2 same day | 2026-06-27 | 2026-06-28 | 2026-06-28 | Troubleman |  | 62.83 | Completed | No
WO-26-006912 | 3.3 | Crossroads | CR-S02-03 | Trouble - no power | P1 emergency | 2026-06-27 | 2026-06-27 | 2026-06-27 | Troubleman |  | 112.2 | Completed | No
WO-26-006913 | 6 | Crossroads | CR-S06-03 | Trouble - no power | P2 same day | 2026-06-27 | 2026-06-28 | 2026-06-28 | Troubleman |  | 222.41 | Completed | No
WO-26-006914 | 4.2 | Crossroads | CR-S20-03 | Trouble - partial or voltage | P2 same day | 2026-06-27 | 2026-06-27 | 2026-06-27 | Internal line |  | 102.36 | Completed | No
WO-26-006915 | 0.9 | Bayou | BY-S13-06 | Service order - field | P2 same day | 2026-06-28 | 2026-06-29 | 2026-06-29 | Meter technician |  | 25.09 | Completed | No
WO-26-006916 | 3.2 | Bayou | BY-S18-02 | Trouble - no power | P2 same day | 2026-06-28 | 2026-06-28 | 2026-06-28 | Internal line |  | 116.13 | Completed | No
WO-26-006917 | 3 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 290.68 | Completed | No
WO-26-006918 | 4.8 | Bayou | BY-S21-02 | Trouble - no power | P2 same day | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 177.39 | Completed | No
WO-26-006919 | 4.5 | Bayou | BY-S18-07 | Trouble - no power | P2 same day | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 229.78 | Completed | No
WO-26-006920 | 2.2 | Bayou | BY-S13-03 | Trouble - no power | P2 same day | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 165.95 | Completed | No
WO-26-006921 | 2.4 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 5.79 | Completed | No
WO-26-006922 | 3.1 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 234.36 | Completed | No
WO-26-006923 | 1.9 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-06-28 | 2026-06-29 | 2026-06-29 | Meter technician |  | 34.89 | Completed | No
WO-26-006924 | 1.6 | Crossroads | CR-S13-06 | Service order - field | P2 same day | 2026-06-28 | 2026-06-29 | 2026-06-29 | Meter technician |  | 16.71 | Completed | No
WO-26-006925 | 10.6 | Crossroads | CR-S04-01 | Transformer replacement | P2 same day | 2026-06-28 | 2026-06-29 | 2026-06-29 | Internal line |  | 8167.93 | Completed | No
WO-26-006926 | 4.7 | Crossroads | CR-S25-01 | Trouble - no power | P2 same day | 2026-06-28 | 2026-06-28 | 2026-06-28 | Internal line |  | 234.44 | Completed | No
WO-26-006927 | 3.9 | Crossroads | CR-S05-03 | Trouble - no power | P1 emergency | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 116.75 | Completed | No
WO-26-006928 | 4.2 | Crossroads | CR-S14-06 | Trouble - no power | P1 emergency | 2026-06-28 | 2026-06-28 | 2026-06-28 | Troubleman |  | 184.81 | Completed | No
WO-26-006929 | 8.6 | Bayou | BY-S06-03 | Corrective maintenance | P4 planned | 2026-06-29 | 2026-08-02 | 2026-08-02 | Internal line |  | 1895.38 | Completed | No
WO-26-006930 | 6.6 | Bayou | BY-S26-04 | Corrective maintenance | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Contract line | CT-04 | 2178.64 | Completed | No
WO-26-006931 | 7.5 | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-07-03 | 2026-07-04 | Internal line |  | 916.18 | Completed | No
WO-26-006932 | 9.2 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-07-01 | 2026-07-02 | Internal line |  | 2309.02 | Completed | No
WO-26-006933 | 5.1 | Bayou | BY-S30-01 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-07-01 | 2026-07-01 | Underground crew |  | 1844.25 | Completed | No
WO-26-006934 | 11.8 | Bayou | BY-S18-01 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-06-30 | 2026-07-01 | Contract line | CT-03 | 929.6 | Completed | No
WO-26-006935 | 0.7 | Bayou | BY-S12-02 | Meter exchange | P3 within 10 days | 2026-06-29 | 2026-07-04 | 2026-07-04 | Meter technician |  | 134.43 | Completed | No
WO-26-006936 | 0.7 | Bayou | BY-S27-06 | Meter exchange | P4 planned | 2026-06-29 | 2026-08-28 | 2026-08-28 | Meter technician |  | 64.67 | Completed | No
WO-26-006937 | 4.4 | Bayou | BY-S24-03 | Preventive maintenance | P4 planned | 2026-06-29 | 2026-07-10 | 2026-07-10 | Contract line | CT-03 | 368.49 | Completed | No
WO-26-006938 | 3.2 | Bayou | BY-S17-02 | Preventive maintenance | P4 planned | 2026-06-29 | 2026-07-28 | 2026-07-30 | Contract line | CT-03 | 466.96 | Completed | No
WO-26-006939 | 3.8 | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-06-29 | 2026-07-08 | 2026-07-09 | Contract line | CT-04 | 418.67 | Completed | No
WO-26-006940 | 0.6 | Bayou | BY-S19-03 | Service order - field | P2 same day | 2026-06-29 | 2026-06-29 | 2026-06-29 | Meter technician |  | 3.1 | Completed | No
WO-26-006941 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-29 | 2026-06-30 | 2026-06-30 | Contract line | CT-04 | 222.72 | Completed | No
WO-26-006942 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-29 | 2026-07-01 | 2026-07-05 | Internal line |  | 242.5 | Completed | No
WO-26-006943 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-29 | 2026-07-08 | 2026-07-08 | Contract line | CT-04 | 284.56 | Completed | No
WO-26-006944 | 11.1 | Bayou | BY-S17-02 | Transformer replacement | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Contract line | CT-03 | 2849.46 | Completed | No
WO-26-006945 | 7.4 | Bayou | BY-S10-01 | Transformer replacement | P3 within 10 days | 2026-06-29 | 2026-07-05 | 2026-07-05 | Contract line | CT-04 | 6275.62 | Completed | No
WO-26-006946 | 5.8 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 62.04 | Completed | No
WO-26-006947 | 2.6 | Bayou | BY-S16-03 | Trouble - no power | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Internal line |  | 228.91 | Completed | No
WO-26-006948 | 4 | Bayou | BY-S24-04 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 80.24 | Completed | No
WO-26-006949 | 4.5 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Internal line |  | 157.53 | Completed | No
WO-26-006950 | 2.8 | Bayou | BY-S06-02 | Trouble - partial or voltage | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Internal line |  | 22.16 | Completed | No
WO-26-006951 | 4.3 | Bayou | BY-S21-02 | Trouble - partial or voltage | P2 same day | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 185.73 | Completed | No
WO-26-006952 | 2.4 | Bayou | BY-S22-03 | Trouble - partial or voltage | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Troubleman |  | 179.6 | Completed | No
WO-26-006953 | 4.8 | Crossroads | CR-S25-06 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-07-07 | 2026-07-07 | Contract line | CT-01 | 1127.42 | Completed | No
WO-26-006954 | 5.5 | Crossroads | CR-S27-04 | Corrective maintenance | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Internal line |  | 1919.81 | Completed | No
WO-26-006955 | 4 | Crossroads | CR-S10-02 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-07-04 | 2026-07-06 | Internal line |  | 181.59 | Completed | No
WO-26-006956 | 6.8 | Crossroads | CR-S24-03 | Corrective maintenance | P3 within 10 days | 2026-06-29 | 2026-07-05 | 2026-07-05 | Internal line |  | 396.4 | Completed | No
WO-26-006957 | 0.7 | Crossroads | CR-S04-01 | Meter exchange | P3 within 10 days | 2026-06-29 | 2026-07-05 | 2026-07-05 | Meter technician |  | 160.99 | Completed | No
WO-26-006958 | 1.3 | Crossroads | CR-S04-03 | Meter exchange | P3 within 10 days | 2026-06-29 | 2026-07-08 | 2026-07-09 | Meter technician |  | 178 | Completed | No
WO-26-006959 | 0.7 | Crossroads | CR-S09-01 | Meter exchange | P3 within 10 days | 2026-06-29 | 2026-07-05 | 2026-07-05 | Meter technician |  | 101.31 | Completed | No
WO-26-006960 | 4.6 | Crossroads | CR-S19-04 | New service - small | P3 within 10 days | 2026-06-29 | 2026-07-06 | 2026-07-07 | Internal line |  | 3335.15 | Completed | No
WO-26-006961 | 23.5 | Crossroads | CR-S32-02 | Pole replacement | P4 planned | 2026-06-29 | 2026-08-17 | 2026-08-21 | Internal line |  | 1263.3 | Completed | No
WO-26-006962 | 14.5 | Crossroads | CR-S28-03 | Pole replacement | P2 same day | 2026-06-29 | 2026-06-29 | 2026-06-29 | Internal line |  | 1867.02 | Completed | No
WO-26-006963 | 18.6 | Crossroads | CR-S16-02 | Pole replacement | P2 same day | 2026-06-29 | 2026-06-29 | 2026-06-29 | Contract line | CT-01 | 2106.48 | Completed | No
WO-26-006964 | 15.5 | Crossroads | CR-S25-03 | Pole replacement | P3 within 10 days | 2026-06-29 | 2026-07-06 | 2026-07-10 | Contract line | CT-01 | 1644.62 | Completed | No
WO-26-006965 | 5.8 | Crossroads | CR-S25-06 | Preventive maintenance | P4 planned | 2026-06-29 | 2026-07-10 | 2026-07-10 | Internal line |  | 82.17 | Completed | No
WO-26-006966 | 2.3 | Crossroads | CR-S20-02 | Preventive maintenance | P4 planned | 2026-06-29 | 2026-08-14 | 2026-08-14 | Underground crew |  | 177.19 | Completed | No
WO-26-006967 | 1.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-06-29 | 2026-07-08 | 2026-07-09 | Contract line | CT-02 | 204.86 | Completed | No
WO-26-006968 | 6.2 | Crossroads | CR-S01-03 | Transformer replacement | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Internal line |  | 11155.22 | Completed | No
WO-26-006969 | 2.8 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Internal line |  | 183.11 | Completed | No
WO-26-006970 | 2.8 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 205.62 | Completed | No
WO-26-006971 | 2.9 | Crossroads | CR-S14-04 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 293.69 | Completed | No
WO-26-006972 | 5.4 | Crossroads | CR-S11-01 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 262.94 | Completed | No
WO-26-006973 | 5.6 | Crossroads | CR-S20-03 | Trouble - no power | P1 emergency | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 23.99 | Completed | No
WO-26-006974 | 2.4 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P2 same day | 2026-06-29 | 2026-06-29 | 2026-06-29 | Troubleman |  | 197.07 | Completed | No
WO-26-006975 | 4.6 | Crossroads | CR-S28-03 | Trouble - partial or voltage | P2 same day | 2026-06-29 | 2026-06-30 | 2026-06-30 | Troubleman |  | 145.24 | Completed | No
WO-26-006976 | 4.7 | Crossroads | CR-S16-03 | Trouble - partial or voltage | P3 within 10 days | 2026-06-29 | 2026-07-08 | 2026-07-08 | Troubleman |  | 147.98 | Completed | No
WO-26-006977 | 10.8 | Bayou | BY-S09-01 | Corrective maintenance | P3 within 10 days | 2026-06-30 | 2026-07-08 | 2026-07-08 | Underground crew |  | 1944.22 | Completed | No
WO-26-006978 | 3.9 | Bayou | BY-S21-04 | Corrective maintenance | P4 planned | 2026-06-30 | 2026-08-26 | 2026-08-26 | Internal line |  | 1831.35 | Completed | No
WO-26-006979 | 7.5 | Bayou | BY-S06-02 | Corrective maintenance | P3 within 10 days | 2026-06-30 | 2026-07-01 | 2026-07-02 | Underground crew |  | 886.87 | Completed | No
WO-26-006980 | 7.9 | Bayou | BY-S23-05 | Corrective maintenance | P3 within 10 days | 2026-06-30 | 2026-07-04 | 2026-07-06 | Contract line | CT-04 | 1694.69 | Completed | No
WO-26-006981 | 0.9 | Bayou | BY-S19-03 | Meter exchange | P3 within 10 days | 2026-06-30 | 2026-07-04 | 2026-07-08 | Meter technician |  | 114.6 | Completed | No
WO-26-006982 | 0.7 | Bayou | BY-S13-03 | Meter exchange | P3 within 10 days | 2026-06-30 | 2026-07-02 | 2026-07-02 | Meter technician |  | 175.09 | Completed | No
WO-26-006983 | 1.3 | Bayou | BY-S18-07 | Meter exchange | P3 within 10 days | 2026-06-30 | 2026-07-02 | 2026-07-06 | Meter technician |  | 158.39 | Completed | No
WO-26-006984 | 13 | Bayou | BY-S27-05 | Pole replacement | P4 planned | 2026-06-30 | 2026-08-22 | 2026-08-22 | Contract line | CT-03 | 1473.22 | Completed | No
WO-26-006985 | 18.1 | Bayou | BY-S17-03 | Pole replacement | P4 planned | 2026-06-30 | 2026-07-15 | 2026-07-15 | Contract line | CT-03 | 1553.3 | Completed | No
WO-26-006986 | 3.4 | Bayou | BY-S19-01 | Preventive maintenance | P4 planned | 2026-06-30 | 2026-08-21 | 2026-08-25 | Underground crew |  | 502.56 | Completed | No
WO-26-006987 | 7.5 | Bayou | BY-S28-01 | Preventive maintenance | P4 planned | 2026-06-30 | 2026-08-16 | 2026-08-16 | Underground crew |  | 150.07 | Completed | No
WO-26-006988 | 4.4 | Bayou | BY-S14-01 | Preventive maintenance | P4 planned | 2026-06-30 | 2026-07-30 | 2026-08-07 | Underground crew |  | 178.45 | Completed | No
WO-26-006989 | 1.7 | Bayou | BY-S29-02 | Service order - field | P3 within 10 days | 2026-06-30 | 2026-07-01 | 2026-07-01 | Meter technician |  | 8.39 | Completed | No
WO-26-006990 | 0.7 | Bayou | BY-S07-02 | Service order - field | P3 within 10 days | 2026-06-30 | 2026-07-02 | 2026-07-04 | Meter technician |  | 36.37 | Completed | No
WO-26-006991 | 1.7 | Bayou | BY-S16-04 | Service order - field | P2 same day | 2026-06-30 | 2026-07-01 | 2026-07-01 | Meter technician |  | 38.26 | Completed | No
WO-26-006992 | 1.7 | Bayou | BY-S29-05 | Service order - field | P3 within 10 days | 2026-06-30 | 2026-07-03 | 2026-07-05 | Meter technician |  | 31.9 | Completed | No
WO-26-006993 | 1.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-30 | 2026-07-10 | 2026-07-11 | Contract line | CT-03 | 401.34 | Completed | No
WO-26-006994 | 1.2 | Bayou |  | Streetlight | P4 planned | 2026-06-30 | 2026-08-03 | 2026-08-03 | Internal line |  | 147.27 | Completed | No
WO-26-006995 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-30 | 2026-07-02 | 2026-07-03 | Internal line |  | 430.21 | Completed | No
WO-26-006996 | 1.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-06-30 | 2026-07-09 | 2026-07-09 | Contract line | CT-03 | 265.05 | Completed | No
WO-26-006997 | 2.2 | Bayou | BY-S06-03 | Trouble - no power | P1 emergency | 2026-06-30 | 2026-06-30 | 2026-06-30 | Troubleman |  | 179.75 | Completed | No
WO-26-006998 | 4.3 | Bayou | BY-S28-03 | Trouble - no power | P1 emergency | 2026-06-30 | 2026-06-30 | 2026-06-30 | Troubleman |  | 253.62 | Completed | No
WO-26-006999 | 2.9 | Bayou | BY-S14-01 | Trouble - partial or voltage | P2 same day | 2026-06-30 | 2026-06-30 | 2026-06-30 | Internal line |  | 127.29 | Completed | No
WO-26-007000 | 10.9 | Crossroads | CR-S08-06 | Corrective maintenance | P3 within 10 days | 2026-06-30 | 2026-07-04 | 2026-07-04 | Internal line |  | 1100.08 | Completed | No
WO-26-007001 | 5.7 | Crossroads | CR-S18-06 | Corrective maintenance | P3 within 10 days | 2026-06-30 | 2026-07-02 | 2026-07-04 | Internal line |  | 1955.8 | Completed | No
WO-26-007002 | 3.6 | Crossroads | CR-S14-04 | Corrective maintenance | P4 planned | 2026-06-30 | 2026-08-11 | 2026-08-15 | Underground crew |  | 1713.93 | Completed | No
WO-26-007003 | 11.3 | Crossroads | CR-S27-04 | Corrective maintenance | P2 same day | 2026-06-30 | 2026-07-01 | 2026-07-01 | Internal line |  | 1505.1 | Completed | No
WO-26-007004 | 6 | Crossroads | CR-S09-05 | Corrective maintenance | P3 within 10 days | 2026-06-30 | 2026-07-08 | 2026-07-12 | Internal line |  | 1897.74 | Completed | No
WO-26-007005 | 1.3 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-06-30 | 2026-07-08 | 2026-07-09 | Meter technician |  | 119.26 | Completed | No
WO-26-007006 | 0.7 | Crossroads | CR-S29-02 | Meter exchange | P3 within 10 days | 2026-06-30 | 2026-07-09 | 2026-07-09 | Meter technician |  | 84.48 | Completed | No
WO-26-007007 | 11.4 | Crossroads | CR-S28-03 | New service - small | P4 planned | 2026-06-30 | 2026-08-02 | 2026-08-04 | Contract line | CT-01 | 3738.01 | Completed | No
WO-26-007008 | 21.5 | Crossroads | CR-S13-01 | Pole replacement | P4 planned | 2026-06-30 | 2026-08-21 | 2026-08-22 | Contract line | CT-02 | 3463.37 | Completed | No
WO-26-007009 | 0.6 | Crossroads | CR-S18-03 | Service order - field | P2 same day | 2026-06-30 | 2026-06-30 | 2026-06-30 | Meter technician |  | 35.5 | Completed | No
WO-26-007010 | 1.5 | Crossroads | CR-S09-02 | Service order - field | P3 within 10 days | 2026-06-30 | 2026-07-05 | 2026-07-05 | Meter technician |  | 38.75 | Completed | No
WO-26-007011 | 1.9 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-06-30 | 2026-06-30 | 2026-06-30 | Meter technician |  | 19.89 | Completed | No
WO-26-007012 | 2 | Crossroads | CR-S15-02 | Service order - field | P3 within 10 days | 2026-06-30 | 2026-07-09 | 2026-07-09 | Meter technician |  | 20.79 | Completed | No
WO-26-007013 | 1.2 | Crossroads | CR-S21-01 | Service order - field | P3 within 10 days | 2026-06-30 | 2026-07-10 | 2026-07-10 | Meter technician |  | 14.95 | Completed | No
WO-26-007014 | 8.6 | Crossroads | CR-S07-01 | Transformer replacement | P3 within 10 days | 2026-06-30 | 2026-07-07 | 2026-07-11 | Contract line | CT-02 | 6524.68 | Completed | No
WO-26-007015 | 4 | Crossroads | CR-S01-02 | Trouble - no power | P1 emergency | 2026-06-30 | 2026-06-30 | 2026-06-30 | Troubleman |  | 64.5 | Completed | No
WO-26-007016 | 3.7 | Crossroads | CR-S01-01 | Trouble - no power | P2 same day | 2026-06-30 | 2026-07-01 | 2026-07-01 | Troubleman |  | 114.2 | Completed | No
WO-26-007017 | 4.9 | Crossroads | CR-S10-03 | Trouble - no power | P1 emergency | 2026-06-30 | 2026-06-30 | 2026-06-30 | Troubleman |  | 208.92 | Completed | No
WO-26-007018 | 4.6 | Crossroads | CR-S02-05 | Trouble - no power | P2 same day | 2026-06-30 | 2026-06-30 | 2026-06-30 | Troubleman |  | 287.11 | Completed | No
WO-26-007019 | 5 | Crossroads | CR-S02-01 | Trouble - no power | P1 emergency | 2026-06-30 | 2026-06-30 | 2026-06-30 | Troubleman |  | 3.68 | Completed | No
WO-26-007020 | 5.7 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-06-30 | 2026-06-30 | 2026-06-30 | Internal line |  | 326.35 | Completed | No
WO-26-007021 | 4.1 | Crossroads | CR-S14-02 | Trouble - partial or voltage | P2 same day | 2026-06-30 | 2026-06-30 | 2026-06-30 | Internal line |  | 203.02 | Completed | No
WO-26-007022 | 11.8 | Bayou | BY-S07-04 | Corrective maintenance | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Internal line |  | 515.43 | Completed | No
WO-26-007023 | 7.7 | Bayou | BY-S08-02 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-06 | 2026-07-06 | Internal line |  | 945.75 | Completed | No
WO-26-007024 | 8 | Bayou | BY-S30-03 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-05 | 2026-07-07 | Contract line | CT-04 | 671.53 | Completed | No
WO-26-007025 | 9.2 | Bayou | BY-S19-04 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-07 | 2026-07-08 | Internal line |  | 2042.83 | Completed | No
WO-26-007026 | 4.4 | Bayou | BY-S08-01 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-11 | 2026-07-11 | Contract line | CT-03 | 1535.55 | Completed | No
WO-26-007027 | 10.9 | Bayou | BY-S18-06 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-10 | 2026-07-10 | Underground crew |  | 274.22 | Completed | No
WO-26-007028 | 1.4 | Bayou | BY-S13-05 | Meter exchange | P4 planned | 2026-07-01 | 2026-08-03 | 2026-08-03 | Meter technician |  | 87.25 | Completed | No
WO-26-007029 | 1.5 | Bayou | BY-S06-01 | Meter exchange | P3 within 10 days | 2026-07-01 | 2026-07-08 | 2026-07-08 | Meter technician |  | 122 | Completed | No
WO-26-007030 | 1.2 | Bayou | BY-S30-03 | Meter exchange | P3 within 10 days | 2026-07-01 | 2026-07-03 | 2026-07-03 | Meter technician |  | 126.64 | Completed | No
WO-26-007031 | 16.6 | Bayou | BY-S26-04 | Pole replacement | P3 within 10 days | 2026-07-01 | 2026-07-06 | 2026-07-10 | Contract line | CT-03 | 3215.86 | Completed | No
WO-26-007032 | 16.6 | Bayou | BY-S10-04 | Pole replacement | P3 within 10 days | 2026-07-01 | 2026-07-09 | 2026-07-13 | Contract line | CT-04 | 2373.16 | Completed | No
WO-26-007033 | 6.5 | Bayou | BY-S16-06 | Preventive maintenance | P4 planned | 2026-07-01 | 2026-07-28 | 2026-07-29 | Internal line |  | 76.57 | Completed | No
WO-26-007034 | 3 | Bayou | BY-S18-05 | Preventive maintenance | P4 planned | 2026-07-01 | 2026-08-07 | 2026-08-07 | Internal line |  | 132.13 | Completed | No
WO-26-007035 | 1 | Bayou | BY-S16-02 | Service order - field | P3 within 10 days | 2026-07-01 | 2026-07-10 | 2026-07-10 | Meter technician |  | 30.06 | Completed | No
WO-26-007036 | 1.6 | Bayou | BY-S11-02 | Service order - field | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Meter technician |  | 28.37 | Completed | No
WO-26-007037 | 1.6 | Bayou |  | Streetlight | P4 planned | 2026-07-01 | 2026-08-24 | 2026-08-24 | Internal line |  | 352.22 | Completed | No
WO-26-007038 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-01 | 2026-07-04 | 2026-07-04 | Contract line | CT-04 | 203.22 | Completed | No
WO-26-007039 | 2.6 | Bayou |  | Streetlight | P4 planned | 2026-07-01 | 2026-08-28 | 2026-08-29 | Contract line | CT-04 | 397.5 | Completed | No
WO-26-007040 | 10.3 | Bayou | BY-S04-01 | Transformer replacement | P2 same day | 2026-07-01 | 2026-07-01 | 2026-07-01 | Internal line |  | 12251.78 | Completed | No
WO-26-007041 | 3.5 | Bayou | BY-S06-03 | Trouble - no power | P1 emergency | 2026-07-01 | 2026-07-01 | 2026-07-01 | Troubleman |  | 292.51 | Completed | No
WO-26-007042 | 5.5 | Bayou | BY-S16-02 | Trouble - no power | P1 emergency | 2026-07-01 | 2026-07-01 | 2026-07-01 | Internal line |  | 259.29 | Completed | No
WO-26-007043 | 5.3 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-07-01 | 2026-07-01 | 2026-07-01 | Troubleman |  | 81.16 | Completed | No
WO-26-007044 | 3.7 | Bayou | BY-S13-04 | Trouble - no power | P1 emergency | 2026-07-01 | 2026-07-01 | 2026-07-01 | Troubleman |  | 287.61 | Completed | No
WO-26-007045 | 2.2 | Bayou | BY-S09-05 | Trouble - partial or voltage | P2 same day | 2026-07-01 | 2026-07-01 | 2026-07-01 | Troubleman |  | 171.18 | Completed | No
WO-26-007046 | 4.1 | Bayou | BY-S08-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-01 | 2026-07-10 | 2026-07-10 | Troubleman |  | 144.32 | Completed | No
WO-26-007047 | 1.9 | Bayou | BY-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-01 | 2026-07-08 | 2026-07-09 | Troubleman |  | 223.49 | Completed | No
WO-26-007048 | 11.6 | Crossroads | CR-S04-04 | Corrective maintenance | P4 planned | 2026-07-01 | 2026-07-09 | 2026-07-09 | Underground crew |  | 91.65 | Completed | No
WO-26-007049 | 7.2 | Crossroads | CR-S18-04 | Corrective maintenance | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Contract line | CT-01 | 766.15 | Completed | No
WO-26-007050 | 10.1 | Crossroads | CR-S24-02 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-06 | 2026-07-10 | Internal line |  | 1107.26 | Completed | No
WO-26-007051 | 8.6 | Crossroads | CR-S27-02 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-11 | 2026-07-11 | Internal line |  | 1198.39 | Completed | No
WO-26-007052 | 6.9 | Crossroads | CR-S16-05 | Corrective maintenance | P3 within 10 days | 2026-07-01 | 2026-07-09 | 2026-07-10 | Internal line |  | 1822.59 | Completed | No
WO-26-007053 | 6.6 | Crossroads | CR-S24-03 | Corrective maintenance | P4 planned | 2026-07-01 | 2026-07-28 | 2026-07-29 | Internal line |  | 1739.56 | Completed | No
WO-26-007054 | 1.4 | Crossroads | CR-S23-02 | Meter exchange | P4 planned | 2026-07-01 | 2026-08-12 | 2026-08-13 | Meter technician |  | 146.36 | Completed | No
WO-26-007055 | 1.2 | Crossroads | CR-S09-04 | Meter exchange | P3 within 10 days | 2026-07-01 | 2026-07-10 | 2026-07-12 | Meter technician |  | 179.3 | Completed | No
WO-26-007056 | 12.7 | Crossroads | CR-S05-03 | New service - small | P4 planned | 2026-07-01 | 2026-08-03 | 2026-08-03 | Underground crew |  | 2512.77 | Completed | No
WO-26-007057 | 13.4 | Crossroads | CR-S11-02 | New service - small | P4 planned | 2026-07-01 | 2026-08-10 | 2026-08-10 | Underground crew |  | 3489.42 | Completed | No
WO-26-007058 | 2.1 | Crossroads | CR-S02-05 | Preventive maintenance | P4 planned | 2026-07-01 | 2026-08-30 | 2026-08-30 | Underground crew |  | 60.56 | Completed | No
WO-26-007059 | 2.3 | Crossroads | CR-S29-02 | Preventive maintenance | P4 planned | 2026-07-01 | 2026-08-13 | 2026-08-13 | Underground crew |  | 69.89 | Completed | No
WO-26-007060 | 5.3 | Crossroads | CR-S29-02 | Preventive maintenance | P4 planned | 2026-07-01 | 2026-07-10 | 2026-07-10 | Internal line |  | 282.47 | Completed | No
WO-26-007061 | 0.7 | Crossroads | CR-S30-03 | Service order - field | P3 within 10 days | 2026-07-01 | 2026-07-03 | 2026-07-03 | Meter technician |  | 27.48 | Completed | No
WO-26-007062 | 0.6 | Crossroads | CR-S31-02 | Service order - field | P3 within 10 days | 2026-07-01 | 2026-07-04 | 2026-07-04 | Meter technician |  | 6.29 | Completed | No
WO-26-007063 | 0.6 | Crossroads | CR-S14-01 | Service order - field | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Meter technician |  | 0.99 | Completed | No
WO-26-007064 | 2.6 | Crossroads |  | Streetlight | P4 planned | 2026-07-01 | 2026-08-09 | 2026-08-09 | Internal line |  | 67.76 | Completed | No
WO-26-007065 | 10 | Crossroads | CR-S22-03 | Transformer replacement | P3 within 10 days | 2026-07-01 | 2026-07-03 | 2026-07-03 | Internal line |  | 4182.03 | Completed | No
WO-26-007066 | 10.1 | Crossroads | CR-S07-03 | Transformer replacement | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Internal line |  | 4383.57 | Completed | No
WO-26-007067 | 7.6 | Crossroads | CR-S26-03 | Transformer replacement | P2 same day | 2026-07-01 | 2026-07-01 | 2026-07-01 | Contract line | CT-02 | 11048.49 | Completed | No
WO-26-007068 | 3 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-07-01 | 2026-07-01 | 2026-07-01 | Troubleman |  | 242.32 | Completed | No
WO-26-007069 | 4.3 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-07-01 | 2026-07-01 | 2026-07-01 | Internal line |  | 244.29 | Completed | No
WO-26-007070 | 3 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Internal line |  | 57.08 | Completed | No
WO-26-007071 | 2.5 | Crossroads | CR-S14-01 | Trouble - partial or voltage | P2 same day | 2026-07-01 | 2026-07-01 | 2026-07-01 | Troubleman |  | 78.92 | Completed | No
WO-26-007072 | 2.5 | Crossroads | CR-S32-05 | Trouble - partial or voltage | P2 same day | 2026-07-01 | 2026-07-02 | 2026-07-02 | Troubleman |  | 168.65 | Completed | No
WO-26-007073 | 5 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-06 | 2026-07-07 | Contract line | CT-04 | 290.9 | Completed | No
WO-26-007074 | 12 | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-07 | 2026-07-07 | Internal line |  | 82.96 | Completed | No
WO-26-007075 | 4 | Bayou | BY-S09-05 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-05 | 2026-07-05 | Contract line | CT-03 | 704.64 | Completed | No
WO-26-007076 | 9 | Bayou | BY-S30-03 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-07 | 2026-07-11 | Underground crew |  | 306.06 | Completed | No
WO-26-007077 | 3.6 | Bayou | BY-S15-04 | Corrective maintenance | P4 planned | 2026-07-02 | 2026-08-10 | 2026-08-10 | Underground crew |  | 1347.35 | Completed | No
WO-26-007078 | 7.2 | Bayou | BY-S23-01 | New service - small | P4 planned | 2026-07-02 | 2026-08-07 | 2026-08-07 | Underground crew |  | 3766.01 | Completed | No
WO-26-007079 | 5.4 | Bayou | BY-S10-04 | New service - small | P4 planned | 2026-07-02 | 2026-08-09 | 2026-08-09 | Contract line | CT-04 | 956.74 | Completed | No
WO-26-007080 | 22.8 | Bayou | BY-S16-04 | Pole replacement | P3 within 10 days | 2026-07-02 | 2026-07-04 | 2026-07-04 | Internal line |  | 2956.32 | Completed | No
WO-26-007081 | 22.7 | Bayou | BY-S21-04 | Pole replacement | P3 within 10 days | 2026-07-02 | 2026-07-07 | 2026-07-09 | Contract line | CT-03 | 3467.2 | Completed | No
WO-26-007082 | 2.7 | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-07-02 | 2026-08-06 | 2026-08-06 | Contract line | CT-03 | 285.19 | Completed | No
WO-26-007083 | 6.5 | Bayou | BY-S17-01 | Preventive maintenance | P4 planned | 2026-07-02 | 2026-08-26 | 2026-08-28 | Internal line |  | 469.36 | Completed | No
WO-26-007084 | 3.4 | Bayou | BY-S19-01 | Preventive maintenance | P4 planned | 2026-07-02 | 2026-07-29 | 2026-07-29 | Underground crew |  | 163.93 | Completed | No
WO-26-007085 | 0.5 | Bayou | BY-S20-03 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-03 | 2026-07-03 | Meter technician |  | 34.5 | Completed | No
WO-26-007086 | 1.5 | Bayou | BY-S09-01 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-06 | 2026-07-06 | Meter technician |  | 6.43 | Completed | No
WO-26-007087 | 1.1 | Bayou |  | Streetlight | P4 planned | 2026-07-02 | 2026-08-27 | 2026-08-27 | Contract line | CT-03 | 155.57 | Completed | No
WO-26-007088 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-02 | 2026-07-07 | 2026-07-11 | Contract line | CT-04 | 445.27 | Completed | No
WO-26-007089 | 7.8 | Bayou | BY-S16-03 | Transformer replacement | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Internal line |  | 4850.54 | Completed | No
WO-26-007090 | 3 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 11.52 | Completed | No
WO-26-007091 | 4.4 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 218.81 | Completed | No
WO-26-007092 | 4.2 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 198 | Completed | No
WO-26-007093 | 5.5 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 341.79 | Completed | No
WO-26-007094 | 3.5 | Bayou | BY-S15-04 | Trouble - no power | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 292.78 | Completed | No
WO-26-007095 | 5.2 | Bayou | BY-S09-03 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 265.74 | Completed | No
WO-26-007096 | 3.6 | Bayou | BY-S11-01 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Internal line |  | 326.82 | Completed | No
WO-26-007097 | 4.5 | Bayou | BY-S16-05 | Trouble - no power | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 283.03 | Completed | No
WO-26-007098 | 4.4 | Bayou | BY-S29-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-02 | 2026-07-10 | 2026-07-14 | Troubleman |  | 37.65 | Completed | No
WO-26-007099 | 1.6 | Bayou | BY-S21-03 | Trouble - partial or voltage | P2 same day | 2026-07-02 | 2026-07-03 | 2026-07-03 | Troubleman |  | 2.17 | Completed | No
WO-26-007100 | 3.1 | Bayou | BY-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-07-02 | 2026-07-10 | 2026-07-10 | Troubleman |  | 45.47 | Completed | No
WO-26-007101 | 2.6 | Bayou | BY-S14-01 | Trouble - partial or voltage | P2 same day | 2026-07-02 | 2026-07-03 | 2026-07-03 | Troubleman |  | 203.38 | Completed | No
WO-26-007102 | 6.1 | Crossroads | CR-S32-01 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-12 | 2026-07-12 | Contract line | CT-02 | 2304.58 | Completed | No
WO-26-007103 | 7.8 | Crossroads | CR-S26-02 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-10 | 2026-07-11 | Contract line | CT-01 | 2330.8 | Completed | No
WO-26-007104 | 7.4 | Crossroads | CR-S28-01 | Corrective maintenance | P4 planned | 2026-07-02 | 2026-07-21 | 2026-07-21 | Internal line |  | 1953.84 | Completed | No
WO-26-007105 | 10.2 | Crossroads | CR-S01-03 | Corrective maintenance | P3 within 10 days | 2026-07-02 | 2026-07-07 | 2026-07-07 | Internal line |  | 1452.91 | Completed | No
WO-26-007106 | 1.3 | Crossroads | CR-S20-04 | Meter exchange | P3 within 10 days | 2026-07-02 | 2026-07-05 | 2026-07-06 | Meter technician |  | 143.88 | Completed | No
WO-26-007107 | 1.1 | Crossroads | CR-S19-04 | Meter exchange | P3 within 10 days | 2026-07-02 | 2026-07-12 | 2026-07-16 | Meter technician |  | 88.02 | Completed | No
WO-26-007108 | 0.9 | Crossroads | CR-S07-03 | Meter exchange | P4 planned | 2026-07-02 | 2026-07-21 | 2026-07-21 | Meter technician |  | 78.3 | Completed | No
WO-26-007109 | 1.2 | Crossroads | CR-S04-06 | Meter exchange | P3 within 10 days | 2026-07-02 | 2026-07-12 | 2026-07-12 | Meter technician |  | 166.13 | Completed | No
WO-26-007110 | 4.1 | Crossroads | CR-S28-03 | Preventive maintenance | P4 planned | 2026-07-02 | 2026-08-11 | 2026-08-11 | Internal line |  | 16.27 | Completed | No
WO-26-007111 | 1.5 | Crossroads | CR-S24-03 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-03 | 2026-07-05 | Meter technician |  | 26.87 | Completed | No
WO-26-007112 | 1 | Crossroads | CR-S04-03 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-12 | 2026-07-12 | Meter technician |  | 1.96 | Completed | No
WO-26-007113 |  | Crossroads | CR-S04-02 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-06 |  | Meter technician |  |  | Cancelled | No
WO-26-007114 | 1.6 | Crossroads | CR-S13-01 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-04 | 2026-07-04 | Meter technician |  | 14.67 | Completed | No
WO-26-007115 | 1.8 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-07-02 | 2026-07-08 | 2026-07-08 | Meter technician |  | 36.95 | Completed | No
WO-26-007116 | 1.7 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Meter technician |  | 31.95 | Completed | No
WO-26-007117 | 1.6 | Crossroads | CR-S18-04 | Service order - field | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Meter technician |  | 5.26 | Completed | No
WO-26-007118 | 1.8 | Crossroads | CR-S09-04 | Service order - field | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Meter technician |  | 17.79 | Completed | No
WO-26-007119 | 1.2 | Crossroads |  | Streetlight | P4 planned | 2026-07-02 | 2026-07-21 | 2026-07-21 | Contract line | CT-01 | 427.98 | Completed | No
WO-26-007120 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-02 | 2026-07-09 | 2026-07-09 | Contract line | CT-02 | 72.63 | Completed | No
WO-26-007121 |  | Crossroads |  | Streetlight | P4 planned | 2026-07-02 | 2026-08-29 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-007122 | 12.2 | Crossroads | CR-S32-03 | Transformer replacement | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Contract line | CT-02 | 3686.66 | Completed | No
WO-26-007123 | 3.3 | Crossroads | CR-S10-01 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 331.72 | Completed | No
WO-26-007124 | 3.5 | Crossroads | CR-S08-05 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 99.71 | Completed | No
WO-26-007125 | 4 | Crossroads | CR-S25-01 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Internal line |  | 228.41 | Completed | No
WO-26-007126 | 2.2 | Crossroads | CR-S26-03 | Trouble - no power | P2 same day | 2026-07-02 | 2026-07-03 | 2026-07-03 | Troubleman |  | 84.68 | Completed | No
WO-26-007127 | 5.6 | Crossroads | CR-S31-01 | Trouble - no power | P1 emergency | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 236.34 | Completed | No
WO-26-007128 | 2.7 | Crossroads | CR-S31-01 | Trouble - partial or voltage | P2 same day | 2026-07-02 | 2026-07-02 | 2026-07-02 | Troubleman |  | 141.18 | Completed | No
WO-26-007129 | 10.1 | Bayou | BY-S07-02 | Corrective maintenance | P3 within 10 days | 2026-07-03 | 2026-07-11 | 2026-07-11 | Contract line | CT-04 | 1572.52 | Completed | No
WO-26-007130 | 4.6 | Bayou | BY-S06-03 | Corrective maintenance | P3 within 10 days | 2026-07-03 | 2026-07-08 | 2026-07-10 | Contract line | CT-04 | 546.32 | Completed | No
WO-26-007131 | 7.2 | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-07-03 | 2026-07-07 | 2026-07-07 | Internal line |  | 2240.77 | Completed | No
WO-26-007132 | 1.1 | Bayou | BY-S22-03 | Meter exchange | P3 within 10 days | 2026-07-03 | 2026-07-11 | 2026-07-13 | Meter technician |  | 93.43 | Completed | No
WO-26-007133 | 0.9 | Bayou | BY-S21-03 | Meter exchange | P4 planned | 2026-07-03 | 2026-08-13 | 2026-08-13 | Meter technician |  | 108.31 | Completed | No
WO-26-007134 | 0.5 | Bayou | BY-S18-04 | Meter exchange | P4 planned | 2026-07-03 | 2026-08-08 | 2026-08-10 | Meter technician |  | 99.42 | Completed | No
WO-26-007135 | 18.2 | Bayou | BY-S29-04 | Pole replacement | P3 within 10 days | 2026-07-03 | 2026-07-10 | 2026-07-12 | Internal line |  | 1426.31 | Completed | No
WO-26-007136 | 13.6 | Bayou | BY-S21-01 | Pole replacement | P3 within 10 days | 2026-07-03 | 2026-07-05 | 2026-07-05 | Contract line | CT-04 | 3331.13 | Completed | No
WO-26-007137 | 10.2 | Bayou | BY-S07-03 | Pole replacement | P4 planned | 2026-07-03 | 2026-08-20 | 2026-08-20 | Contract line | CT-03 | 2378.67 | Completed | No
WO-26-007138 | 3.9 | Bayou | BY-S14-02 | Preventive maintenance | P4 planned | 2026-07-03 | 2026-07-10 | 2026-07-10 | Internal line |  | 481.77 | Completed | No
WO-26-007139 | 7.8 | Bayou | BY-S07-01 | Preventive maintenance | P4 planned | 2026-07-03 | 2026-08-03 | 2026-08-07 | Internal line |  | 180.56 | Completed | No
WO-26-007140 | 2.3 | Bayou | BY-S17-03 | Preventive maintenance | P4 planned | 2026-07-03 | 2026-08-26 | 2026-08-26 | Internal line |  | 537.54 | Completed | No
WO-26-007141 | 1.5 | Bayou | BY-S10-01 | Service order - field | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Meter technician |  | 15.58 | Completed | No
WO-26-007142 | 1 | Bayou | BY-S29-02 | Service order - field | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Meter technician |  | 8.3 | Completed | No
WO-26-007143 | 1.3 | Bayou | BY-S18-05 | Service order - field | P3 within 10 days | 2026-07-03 | 2026-07-11 | 2026-07-11 | Meter technician |  | 34.93 | Completed | No
WO-26-007144 | 2.5 | Bayou | BY-S14-02 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 154.88 | Completed | No
WO-26-007145 | 4.1 | Bayou | BY-S15-01 | Trouble - no power | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Internal line |  | 2.68 | Completed | No
WO-26-007146 | 5.9 | Bayou | BY-S16-02 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 73.17 | Completed | No
WO-26-007147 |  | Bayou | BY-S06-02 | Trouble - no power | P2 same day | 2026-07-03 | 2026-07-04 |  | Troubleman |  |  | Cancelled | No
WO-26-007148 | 2.3 | Bayou | BY-S12-04 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Internal line |  | 205.5 | Completed | No
WO-26-007149 | 3.2 | Bayou | BY-S07-05 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 73.07 | Completed | No
WO-26-007150 | 3.4 | Bayou | BY-S17-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-03 | 2026-07-12 | 2026-07-20 | Troubleman |  | 153.12 | Completed | No
WO-26-007151 | 4.2 | Crossroads | CR-S08-05 | Corrective maintenance | P4 planned | 2026-07-03 | 2026-07-18 | 2026-07-18 | Underground crew |  | 159.54 | Completed | No
WO-26-007152 | 11.5 | Crossroads | CR-S31-01 | Corrective maintenance | P3 within 10 days | 2026-07-03 | 2026-07-09 | 2026-07-10 | Internal line |  | 1415.15 | Completed | No
WO-26-007153 | 0.9 | Crossroads | CR-S07-05 | Meter exchange | P3 within 10 days | 2026-07-03 | 2026-07-11 | 2026-07-11 | Meter technician |  | 148.24 | Completed | No
WO-26-007154 | 1.5 | Crossroads | CR-S01-02 | Meter exchange | P3 within 10 days | 2026-07-03 | 2026-07-05 | 2026-07-06 | Meter technician |  | 125.21 | Completed | No
WO-26-007155 | 15.7 | Crossroads | CR-S06-03 | New service - small | P4 planned | 2026-07-03 | 2026-07-15 | 2026-07-16 | Contract line | CT-01 | 2657.07 | Completed | No
WO-26-007156 | 5.1 | Crossroads | CR-S15-01 | New service - small | P4 planned | 2026-07-03 | 2026-08-08 | 2026-08-09 | Underground crew |  | 2540.64 | Completed | No
WO-26-007157 |  | Crossroads | CR-S21-03 | Pole replacement | P4 planned | 2026-07-03 | 2026-07-13 |  | Contract line | CT-01 |  | Cancelled | No
WO-26-007158 | 13.6 | Crossroads | CR-S17-03 | Pole replacement | P4 planned | 2026-07-03 | 2026-08-26 | 2026-08-26 | Contract line | CT-01 | 1552.54 | Completed | No
WO-26-007159 | 15.2 | Crossroads | CR-S21-03 | Pole replacement | P4 planned | 2026-07-03 | 2026-07-22 | 2026-07-22 | Contract line | CT-01 | 1226.76 | Completed | No
WO-26-007160 | 4.7 | Crossroads | CR-S30-01 | Preventive maintenance | P4 planned | 2026-07-03 | 2026-08-13 | 2026-08-13 | Internal line |  | 363.97 | Completed | No
WO-26-007161 | 1.8 | Crossroads | CR-S19-04 | Service order - field | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Meter technician |  | 38.2 | Completed | No
WO-26-007162 | 1.7 | Crossroads | CR-S29-02 | Service order - field | P3 within 10 days | 2026-07-03 | 2026-07-08 | 2026-07-08 | Meter technician |  | 19.63 | Completed | No
WO-26-007163 | 0.9 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-07-03 | 2026-07-07 | 2026-07-09 | Meter technician |  | 8.26 | Completed | No
WO-26-007164 | 0.7 | Crossroads | CR-S23-04 | Service order - field | P3 within 10 days | 2026-07-03 | 2026-07-13 | 2026-07-21 | Meter technician |  | 26.47 | Completed | No
WO-26-007165 | 8.9 | Crossroads | CR-S14-06 | Transformer replacement | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Contract line | CT-01 | 7344.14 | Completed | No
WO-26-007166 | 6.7 | Crossroads | CR-S12-01 | Transformer replacement | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Internal line |  | 8628.89 | Completed | No
WO-26-007167 | 10.2 | Crossroads | CR-S16-04 | Transformer replacement | P3 within 10 days | 2026-07-03 | 2026-07-07 | 2026-07-07 | Internal line |  | 5360.52 | Completed | No
WO-26-007168 | 8.7 | Crossroads | CR-S07-01 | Transformer replacement | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Contract line | CT-01 | 4244.25 | Completed | No
WO-26-007169 | 8.8 | Crossroads | CR-S24-04 | Transformer replacement | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Internal line |  | 10721.22 | Completed | No
WO-26-007170 | 12.7 | Crossroads | CR-S04-05 | Transformer replacement | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Contract line | CT-01 | 10667.08 | Completed | No
WO-26-007171 | 2.4 | Crossroads | CR-S09-02 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 214.25 | Completed | No
WO-26-007172 | 5.4 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 253.48 | Completed | No
WO-26-007173 | 2.4 | Crossroads | CR-S16-05 | Trouble - no power | P2 same day | 2026-07-03 | 2026-07-04 | 2026-07-04 | Troubleman |  | 238.46 | Completed | No
WO-26-007174 | 2.8 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 165.72 | Completed | No
WO-26-007175 | 2 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Internal line |  | 85.24 | Completed | No
WO-26-007176 | 3.5 | Crossroads | CR-S04-05 | Trouble - no power | P2 same day | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 124.73 | Completed | No
WO-26-007177 | 3 | Crossroads | CR-S28-02 | Trouble - no power | P1 emergency | 2026-07-03 | 2026-07-03 | 2026-07-03 | Troubleman |  | 24.02 | Completed | No
WO-26-007178 | 3.3 | Crossroads | CR-S17-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-03 | 2026-07-08 | 2026-07-08 | Troubleman |  | 187.25 | Completed | No
WO-26-007179 | 4.3 | Bayou | BY-S16-06 | Corrective maintenance | P2 same day | 2026-07-04 | 2026-07-04 | 2026-07-04 | Internal line |  | 2363.16 | Completed | No
WO-26-007180 | 1.6 | Bayou | BY-S08-03 | Service order - field | P2 same day | 2026-07-04 | 2026-07-04 | 2026-07-04 | Meter technician |  | 23.42 | Completed | No
WO-26-007181 | 1.4 | Bayou | BY-S18-06 | Service order - field | P2 same day | 2026-07-04 | 2026-07-05 | 2026-07-05 | Meter technician |  | 36.16 | Completed | No
WO-26-007182 | 2 | Bayou | BY-S09-04 | Service order - field | P2 same day | 2026-07-04 | 2026-07-05 | 2026-07-05 | Meter technician |  | 6.2 | Completed | No
WO-26-007183 | 1.5 | Bayou | BY-S13-05 | Service order - field | P2 same day | 2026-07-04 | 2026-07-04 | 2026-07-04 | Meter technician |  | 0.03 | Completed | No
WO-26-007184 | 3 | Bayou | BY-S29-01 | Trouble - no power | P2 same day | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 69.34 | Completed | No
WO-26-007185 | 2.5 | Bayou | BY-S24-04 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Internal line |  | 348.17 | Completed | No
WO-26-007186 | 4.6 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 240.67 | Completed | No
WO-26-007187 | 3.8 | Bayou | BY-S29-02 | Trouble - no power | P2 same day | 2026-07-04 | 2026-07-04 | 2026-07-04 | Internal line |  | 134.13 | Completed | No
WO-26-007188 | 2.2 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 164.59 | Completed | No
WO-26-007189 | 4.8 | Bayou | BY-S17-01 | Trouble - no power | P2 same day | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 41.95 | Completed | No
WO-26-007190 | 5.9 | Bayou | BY-S23-04 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 328.84 | Completed | No
WO-26-007191 | 4.6 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 229.13 | Completed | No
WO-26-007192 | 12.7 | Crossroads | CR-S16-02 | Transformer replacement | P2 same day | 2026-07-04 | 2026-07-05 | 2026-07-05 | Internal line |  | 8828.99 | Completed | No
WO-26-007193 | 3.4 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 275.1 | Completed | No
WO-26-007194 | 4.5 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Internal line |  | 29.02 | Completed | No
WO-26-007195 | 4.9 | Crossroads | CR-S17-03 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 220.31 | Completed | No
WO-26-007196 | 4.2 | Crossroads | CR-S14-05 | Trouble - no power | P1 emergency | 2026-07-04 | 2026-07-04 | 2026-07-04 | Troubleman |  | 276.95 | Completed | No
WO-26-007197 |  | Bayou | BY-S15-02 | Corrective maintenance | P2 same day | 2026-07-05 | 2026-07-06 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-007198 | 9.6 | Bayou | BY-S10-01 | Corrective maintenance | P2 same day | 2026-07-05 | 2026-07-05 | 2026-07-05 | Internal line |  | 2194.22 | Completed | No
WO-26-007199 | 1.1 | Bayou | BY-S11-01 | Service order - field | P2 same day | 2026-07-05 | 2026-07-06 | 2026-07-06 | Meter technician |  | 39 | Completed | No
WO-26-007200 | 1.5 | Bayou | BY-S06-03 | Service order - field | P2 same day | 2026-07-05 | 2026-07-05 | 2026-07-05 | Meter technician |  | 3.25 | Completed | No
WO-26-007201 | 6.4 | Bayou | BY-S19-03 | Transformer replacement | P2 same day | 2026-07-05 | 2026-07-06 | 2026-07-06 | Contract line | CT-03 | 4083.65 | Completed | No
WO-26-007202 | 6.1 | Bayou | BY-S09-03 | Transformer replacement | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Internal line |  | 7892.48 | Completed | No
WO-26-007203 | 11.2 | Bayou | BY-S22-03 | Transformer replacement | P2 same day | 2026-07-05 | 2026-07-05 | 2026-07-05 | Internal line |  | 5812.5 | Completed | No
WO-26-007204 | 2.9 | Bayou | BY-S10-01 | Trouble - no power | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Troubleman |  | 340.68 | Completed | No
WO-26-007205 | 2.6 | Bayou | BY-S18-03 | Trouble - partial or voltage | P2 same day | 2026-07-05 | 2026-07-06 | 2026-07-06 | Troubleman |  | 195.13 | Completed | No
WO-26-007206 | 7.7 | Crossroads | CR-S14-05 | Transformer replacement | P2 same day | 2026-07-05 | 2026-07-05 | 2026-07-05 | Contract line | CT-02 | 9861.53 | Completed | No
WO-26-007207 | 4.9 | Crossroads | CR-S25-02 | Trouble - no power | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Internal line |  | 219.93 | Completed | No
WO-26-007208 | 2.1 | Crossroads | CR-S28-02 | Trouble - no power | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Troubleman |  | 272.55 | Completed | No
WO-26-007209 | 2.6 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-07-05 | 2026-07-05 | 2026-07-05 | Troubleman |  | 150.23 | Completed | No
WO-26-007210 | 3.6 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Troubleman |  | 187.12 | Completed | No
WO-26-007211 | 3 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Troubleman |  | 138.51 | Completed | No
WO-26-007212 | 4.5 | Crossroads | CR-S01-01 | Trouble - no power | P1 emergency | 2026-07-05 | 2026-07-05 | 2026-07-05 | Troubleman |  | 291.87 | Completed | No
WO-26-007213 | 4 | Crossroads | CR-S22-04 | Trouble - partial or voltage | P2 same day | 2026-07-05 | 2026-07-06 | 2026-07-06 | Troubleman |  | 114.05 | Completed | No
WO-26-007214 | 11.4 | Bayou | BY-S05-02 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-07 | 2026-07-08 | Internal line |  | 906.03 | Completed | No
WO-26-007215 | 3.9 | Bayou | BY-S21-03 | Corrective maintenance | P4 planned | 2026-07-06 | 2026-07-18 | 2026-07-22 | Internal line |  | 2266.16 | Completed | No
WO-26-007216 | 6.9 | Bayou | BY-S28-02 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-14 | 2026-07-15 | Internal line |  | 1686.47 | Completed | No
WO-26-007217 | 0.6 | Bayou | BY-S23-04 | Meter exchange | P4 planned | 2026-07-06 | 2026-08-17 | 2026-08-19 | Meter technician |  | 178.36 | Completed | No
WO-26-007218 | 0.6 | Bayou | BY-S23-04 | Meter exchange | P3 within 10 days | 2026-07-06 | 2026-07-15 | 2026-07-16 | Meter technician |  | 100.67 | Completed | No
WO-26-007219 | 0.9 | Bayou | BY-S11-03 | Meter exchange | P3 within 10 days | 2026-07-06 | 2026-07-08 | 2026-07-08 | Meter technician |  | 156.57 | Completed | No
WO-26-007220 | 15.6 | Bayou | BY-S12-04 | New service - small | P3 within 10 days | 2026-07-06 | 2026-07-16 | 2026-07-17 | Contract line | CT-03 | 1277.06 | Completed | No
WO-26-007221 | 13.3 | Bayou | BY-S16-06 | Pole replacement | P3 within 10 days | 2026-07-06 | 2026-07-11 | 2026-07-15 | Contract line | CT-03 | 1202.83 | Completed | No
WO-26-007222 | 5.6 | Bayou | BY-S21-01 | Preventive maintenance | P4 planned | 2026-07-06 | 2026-07-16 | 2026-07-16 | Internal line |  | 201 | Completed | No
WO-26-007223 | 1.3 | Bayou | BY-S16-01 | Service order - field | P3 within 10 days | 2026-07-06 | 2026-07-12 | 2026-07-16 | Meter technician |  | 29.04 | Completed | No
WO-26-007224 | 0.6 | Bayou | BY-S21-04 | Service order - field | P3 within 10 days | 2026-07-06 | 2026-07-16 | 2026-07-20 | Meter technician |  | 24.44 | Completed | No
WO-26-007225 | 11.7 | Bayou | BY-S17-01 | Transformer replacement | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Contract line | CT-04 | 9750.59 | Completed | No
WO-26-007226 | 11 | Bayou | BY-S16-03 | Transformer replacement | P2 same day | 2026-07-06 | 2026-07-06 | 2026-07-06 | Internal line |  | 10572.92 | Completed | No
WO-26-007227 | 10.8 | Bayou | BY-S16-05 | Transformer replacement | P2 same day | 2026-07-06 | 2026-07-07 | 2026-07-07 | Contract line | CT-04 | 12412.02 | Completed | No
WO-26-007228 | 4.4 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 11.51 | Completed | No
WO-26-007229 | 3.1 | Bayou | BY-S29-03 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 348.22 | Completed | No
WO-26-007230 | 3.2 | Bayou | BY-S09-04 | Trouble - no power | P2 same day | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 345.62 | Completed | No
WO-26-007231 | 3.7 | Bayou | BY-S23-04 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 135.65 | Completed | No
WO-26-007232 | 9.2 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-11 | 2026-07-19 | Underground crew |  | 821.62 | Completed | No
WO-26-007233 | 7.2 | Crossroads | CR-S02-01 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-09 | 2026-07-09 | Internal line |  | 764.62 | Completed | No
WO-26-007234 | 4.3 | Crossroads | CR-S27-02 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-10 | 2026-07-10 | Underground crew |  | 1900.08 | Completed | No
WO-26-007235 | 5.2 | Crossroads | CR-S19-04 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-07 | 2026-07-11 | Underground crew |  | 1589.9 | Completed | No
WO-26-007236 | 6.4 | Crossroads | CR-S32-03 | Corrective maintenance | P3 within 10 days | 2026-07-06 | 2026-07-16 | 2026-07-16 | Underground crew |  | 1179.69 | Completed | No
WO-26-007237 | 1.4 | Crossroads | CR-S24-03 | Meter exchange | P3 within 10 days | 2026-07-06 | 2026-07-14 | 2026-07-22 | Meter technician |  | 78.59 | Completed | No
WO-26-007238 | 1.1 | Crossroads | CR-S14-01 | Meter exchange | P3 within 10 days | 2026-07-06 | 2026-07-08 | 2026-07-09 | Meter technician |  | 86.62 | Completed | No
WO-26-007239 | 22.3 | Crossroads | CR-S10-03 | Pole replacement | P4 planned | 2026-07-06 | 2026-07-31 | 2026-07-31 | Internal line |  | 3269.72 | Completed | No
WO-26-007240 | 20.2 | Crossroads | CR-S24-04 | Pole replacement | P4 planned | 2026-07-06 | 2026-07-24 | 2026-08-01 | Internal line |  | 2093 | Completed | No
WO-26-007241 | 3.6 | Crossroads | CR-S28-03 | Preventive maintenance | P4 planned | 2026-07-06 | 2026-08-25 | 2026-08-27 | Internal line |  | 428.98 | Completed | No
WO-26-007242 | 0.9 | Crossroads | CR-S08-02 | Service order - field | P3 within 10 days | 2026-07-06 | 2026-07-13 | 2026-07-13 | Meter technician |  | 18.01 | Completed | No
WO-26-007243 | 1.7 | Crossroads | CR-S08-04 | Service order - field | P3 within 10 days | 2026-07-06 | 2026-07-13 | 2026-07-13 | Meter technician |  | 35.53 | Completed | No
WO-26-007244 | 1.8 | Crossroads | CR-S25-02 | Service order - field | P2 same day | 2026-07-06 | 2026-07-07 | 2026-07-07 | Meter technician |  | 5.02 | Completed | No
WO-26-007245 | 0.8 | Crossroads | CR-S28-01 | Service order - field | P3 within 10 days | 2026-07-06 | 2026-07-13 | 2026-07-13 | Meter technician |  | 26.13 | Completed | No
WO-26-007246 | 2.7 | Crossroads |  | Streetlight | P4 planned | 2026-07-06 | 2026-08-17 | 2026-08-17 | Contract line | CT-01 | 418.52 | Completed | No
WO-26-007247 | 13.8 | Crossroads | CR-S32-01 | Transformer replacement | P2 same day | 2026-07-06 | 2026-07-07 | 2026-07-07 | Internal line |  | 10678.43 | Completed | No
WO-26-007248 | 13.8 | Crossroads | CR-S29-02 | Transformer replacement | P3 within 10 days | 2026-07-06 | 2026-07-08 | 2026-07-08 | Contract line | CT-01 | 11804.25 | Completed | No
WO-26-007249 | 6.3 | Crossroads | CR-S07-07 | Transformer replacement | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Internal line |  | 11442.97 | Completed | No
WO-26-007250 |  | Crossroads | CR-S06-01 | Transformer replacement | P2 same day | 2026-07-06 | 2026-07-07 |  | Internal line |  |  | Cancelled | No
WO-26-007251 | 2.7 | Crossroads | CR-S16-05 | Trouble - no power | P2 same day | 2026-07-06 | 2026-07-06 | 2026-07-06 | Internal line |  | 335.55 | Completed | No
WO-26-007252 | 2.5 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 243 | Completed | No
WO-26-007253 | 3.3 | Crossroads | CR-S21-03 | Trouble - no power | P2 same day | 2026-07-06 | 2026-07-07 | 2026-07-07 | Troubleman |  | 245.91 | Completed | No
WO-26-007254 | 4 | Crossroads | CR-S26-01 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 146.21 | Completed | No
WO-26-007255 | 2.2 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 173.89 | Completed | No
WO-26-007256 | 4.3 | Crossroads | CR-S05-02 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 77.17 | Completed | No
WO-26-007257 | 2.8 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-07-06 | 2026-07-06 | 2026-07-06 | Troubleman |  | 129 | Completed | No
WO-26-007258 | 4.8 | Crossroads | CR-S20-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-06 | 2026-07-10 | 2026-07-10 | Troubleman |  | 60.57 | Completed | No
WO-26-007259 | 3.6 | Crossroads | CR-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-06 | 2026-07-15 | 2026-07-17 | Troubleman |  | 120.84 | Completed | No
WO-26-007260 | 2.6 | Crossroads | CR-S20-02 | Trouble - partial or voltage | P2 same day | 2026-07-06 | 2026-07-07 | 2026-07-07 | Troubleman |  | 10.15 | Completed | No
WO-26-007261 | 9.2 | Bayou | BY-S18-06 | Corrective maintenance | P3 within 10 days | 2026-07-07 | 2026-07-14 | 2026-07-14 | Internal line |  | 165.39 | Completed | No
WO-26-007262 | 3.8 | Bayou | BY-S30-01 | Corrective maintenance | P3 within 10 days | 2026-07-07 | 2026-07-17 | 2026-07-17 | Internal line |  | 1101.85 | Completed | No
WO-26-007263 | 5.9 | Bayou | BY-S01-02 | Corrective maintenance | P2 same day | 2026-07-07 | 2026-07-08 | 2026-07-08 | Contract line | CT-03 | 1383.1 | Completed | No
WO-26-007264 | 0.7 | Bayou | BY-S10-02 | Meter exchange | P3 within 10 days | 2026-07-07 | 2026-07-14 | 2026-07-15 | Meter technician |  | 60.65 | Completed | No
WO-26-007265 | 1.4 | Bayou | BY-S19-04 | Meter exchange | P3 within 10 days | 2026-07-07 | 2026-07-08 | 2026-07-08 | Meter technician |  | 73.5 | Completed | No
WO-26-007266 | 1.1 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-07-07 | 2026-07-13 | 2026-07-15 | Meter technician |  | 64.01 | Completed | No
WO-26-007267 | 0.9 | Bayou | BY-S13-01 | Meter exchange | P4 planned | 2026-07-07 | 2026-07-16 | 2026-07-17 | Meter technician |  | 78.49 | Completed | No
WO-26-007268 | 1.4 | Bayou | BY-S07-06 | Meter exchange | P3 within 10 days | 2026-07-07 | 2026-07-14 | 2026-07-18 | Meter technician |  | 69.04 | Completed | No
WO-26-007269 | 12.6 | Bayou | BY-S18-03 | Pole replacement | P4 planned | 2026-07-07 | 2026-08-08 | 2026-08-12 | Contract line | CT-03 | 1558.25 | Completed | No
WO-26-007270 | 1.5 | Bayou | BY-S09-04 | Service order - field | P3 within 10 days | 2026-07-07 | 2026-07-11 | 2026-07-15 | Meter technician |  | 9.38 | Completed | No
WO-26-007271 |  | Bayou | BY-S20-02 | Service order - field | P2 same day | 2026-07-07 | 2026-07-08 |  | Meter technician |  |  | Cancelled | No
WO-26-007272 | 0.9 | Bayou | BY-S23-03 | Service order - field | P3 within 10 days | 2026-07-07 | 2026-07-09 | 2026-07-09 | Meter technician |  | 14.83 | Completed | No
WO-26-007273 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-07-07 | 2026-07-15 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-007274 | 1.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-07 | 2026-07-12 | 2026-07-12 | Contract line | CT-03 | 312.36 | Completed | No
WO-26-007275 | 3.4 | Bayou | BY-S21-05 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 322.55 | Completed | No
WO-26-007276 | 5.5 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 209.33 | Completed | No
WO-26-007277 | 5.1 | Bayou | BY-S23-04 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 27.83 | Completed | No
WO-26-007278 | 2.6 | Bayou | BY-S08-01 | Trouble - no power | P2 same day | 2026-07-07 | 2026-07-08 | 2026-07-08 | Troubleman |  | 45.61 | Completed | No
WO-26-007279 | 3.8 | Bayou | BY-S08-03 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 230.69 | Completed | No
WO-26-007280 | 3.2 | Bayou | BY-S29-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-07 | 2026-07-08 | 2026-07-08 | Internal line |  | 234.95 | Completed | No
WO-26-007281 | 5.9 | Crossroads | CR-S22-04 | Corrective maintenance | P3 within 10 days | 2026-07-07 | 2026-07-09 | 2026-07-10 | Underground crew |  | 1999.47 | Completed | No
WO-26-007282 |  | Crossroads | CR-S07-06 | Corrective maintenance | P4 planned | 2026-07-07 | 2026-09-01 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-007283 | 9.3 | Crossroads | CR-S25-03 | Corrective maintenance | P3 within 10 days | 2026-07-07 | 2026-07-13 | 2026-07-13 | Internal line |  | 1566.79 | Completed | No
WO-26-007284 | 0.6 | Crossroads | CR-S15-02 | Meter exchange | P3 within 10 days | 2026-07-07 | 2026-07-17 | 2026-07-17 | Meter technician |  | 97.39 | Completed | No
WO-26-007285 | 0.9 | Crossroads | CR-S02-05 | Meter exchange | P4 planned | 2026-07-07 | 2026-08-02 | 2026-08-03 | Meter technician |  | 135.45 | Completed | No
WO-26-007286 | 12.6 | Crossroads | CR-S21-02 | Pole replacement | P4 planned | 2026-07-07 | 2026-08-11 | 2026-08-11 | Internal line |  | 2617.84 | Completed | No
WO-26-007287 |  | Crossroads | CR-S10-01 | Preventive maintenance | P4 planned | 2026-07-07 | 2026-09-02 |  | Internal line |  |  | Scheduled | No
WO-26-007288 | 5.9 | Crossroads | CR-S15-02 | Preventive maintenance | P4 planned | 2026-07-07 | 2026-08-29 | 2026-08-30 | Internal line |  | 493.52 | Completed | No
WO-26-007289 | 4.9 | Crossroads | CR-S16-06 | Preventive maintenance | P4 planned | 2026-07-07 | 2026-07-18 | 2026-07-19 | Contract line | CT-01 | 484.65 | Completed | No
WO-26-007290 | 4.2 | Crossroads | CR-S04-01 | Preventive maintenance | P4 planned | 2026-07-07 | 2026-07-16 | 2026-07-16 | Internal line |  | 457.78 | Completed | No
WO-26-007291 | 1.6 | Crossroads | CR-S16-03 | Service order - field | P3 within 10 days | 2026-07-07 | 2026-07-08 | 2026-07-16 | Meter technician |  | 34.23 | Completed | No
WO-26-007292 | 1.6 | Crossroads | CR-S27-04 | Service order - field | P2 same day | 2026-07-07 | 2026-07-08 | 2026-07-08 | Meter technician |  | 34.28 | Completed | No
WO-26-007293 | 0.7 | Crossroads | CR-S30-05 | Service order - field | P2 same day | 2026-07-07 | 2026-07-08 | 2026-07-08 | Meter technician |  | 12.32 | Completed | No
WO-26-007294 | 1 | Crossroads | CR-S23-02 | Service order - field | P3 within 10 days | 2026-07-07 | 2026-07-16 | 2026-07-18 | Meter technician |  | 31.53 | Completed | No
WO-26-007295 | 0.7 | Crossroads | CR-S21-02 | Service order - field | P2 same day | 2026-07-07 | 2026-07-08 | 2026-07-08 | Meter technician |  | 11.53 | Completed | No
WO-26-007296 | 1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-07 | 2026-07-14 | 2026-07-15 | Internal line |  | 191.81 | Completed | No
WO-26-007297 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-07 | 2026-07-11 | 2026-07-13 | Internal line |  | 164.39 | Completed | No
WO-26-007298 | 12.9 | Crossroads | CR-S19-03 | Transformer replacement | P3 within 10 days | 2026-07-07 | 2026-07-11 | 2026-07-12 | Internal line |  | 10124.44 | Completed | No
WO-26-007299 | 6.9 | Crossroads | CR-S20-02 | Transformer replacement | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Internal line |  | 9615.46 | Completed | No
WO-26-007300 | 7.6 | Crossroads | CR-S12-02 | Transformer replacement | P2 same day | 2026-07-07 | 2026-07-07 | 2026-07-07 | Internal line |  | 6116.85 | Completed | No
WO-26-007301 | 3.4 | Crossroads | CR-S28-02 | Trouble - no power | P2 same day | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 90.22 | Completed | No
WO-26-007302 | 4.1 | Crossroads | CR-S30-05 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 210.73 | Completed | No
WO-26-007303 | 5.5 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 28.85 | Completed | No
WO-26-007304 |  | Crossroads | CR-S13-03 | Trouble - no power | P2 same day | 2026-07-07 | 2026-07-08 |  | Troubleman |  |  | Cancelled | No
WO-26-007305 | 5.9 | Crossroads | CR-S32-02 | Trouble - no power | P1 emergency | 2026-07-07 | 2026-07-07 | 2026-07-07 | Troubleman |  | 281.7 | Completed | No
WO-26-007306 |  | Bayou | BY-S16-06 | Corrective maintenance | P4 planned | 2026-07-08 | 2026-09-03 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-007307 | 4 | Bayou | BY-S15-03 | Corrective maintenance | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-13 | Contract line | CT-03 | 2289.45 | Completed | No
WO-26-007308 | 0.7 | Bayou | BY-S28-02 | Meter exchange | P4 planned | 2026-07-08 | 2026-08-21 | 2026-08-21 | Meter technician |  | 129.96 | Completed | No
WO-26-007309 | 0.7 | Bayou | BY-S02-01 | Meter exchange | P3 within 10 days | 2026-07-08 | 2026-07-10 | 2026-07-10 | Meter technician |  | 60.19 | Completed | No
WO-26-007310 |  | Bayou | BY-S25-05 | New service - small | P4 planned | 2026-07-08 | 2026-09-05 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-007311 | 17.6 | Bayou | BY-S30-01 | Pole replacement | P4 planned | 2026-07-08 | 2026-07-18 | 2026-07-20 | Internal line |  | 2988.71 | Completed | No
WO-26-007312 | 12.6 | Bayou | BY-S09-01 | Pole replacement | P3 within 10 days | 2026-07-08 | 2026-07-11 | 2026-07-11 | Internal line |  | 1805.9 | Completed | No
WO-26-007313 | 3.8 | Bayou | BY-S29-04 | Preventive maintenance | P4 planned | 2026-07-08 | 2026-08-05 | 2026-08-07 | Underground crew |  | 239.57 | Completed | No
WO-26-007314 | 0.9 | Bayou | BY-S21-03 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-18 | 2026-07-22 | Meter technician |  | 9.88 | Completed | No
WO-26-007315 | 1.4 | Bayou | BY-S25-01 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-14 | Meter technician |  | 18.3 | Completed | No
WO-26-007316 | 1.6 | Bayou | BY-S16-05 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-13 | Meter technician |  | 5.13 | Completed | No
WO-26-007317 | 1.4 | Bayou | BY-S06-03 | Service order - field | P2 same day | 2026-07-08 | 2026-07-09 | 2026-07-09 | Meter technician |  | 33.22 | Completed | No
WO-26-007318 | 1.5 | Bayou | BY-S22-02 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-12 | 2026-07-16 | Meter technician |  | 38.95 | Completed | No
WO-26-007319 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-08 | 2026-07-17 | 2026-07-17 | Contract line | CT-03 | 137.9 | Completed | No
WO-26-007320 | 2.6 | Bayou |  | Streetlight | P4 planned | 2026-07-08 | 2026-08-06 | 2026-08-06 | Contract line | CT-04 | 380.09 | Completed | No
WO-26-007321 | 6.8 | Bayou | BY-S19-02 | Transformer replacement | P1 emergency | 2026-07-08 | 2026-07-08 | 2026-07-08 | Internal line |  | 2812.15 | Completed | No
WO-26-007322 | 4.7 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-07-08 | 2026-07-08 | 2026-07-08 | Troubleman |  | 30.26 | Completed | No
WO-26-007323 | 3 | Bayou | BY-S05-03 | Trouble - no power | P2 same day | 2026-07-08 | 2026-07-08 | 2026-07-08 | Troubleman |  | 97.1 | Completed | No
WO-26-007324 | 3.2 | Bayou | BY-S06-02 | Trouble - no power | P2 same day | 2026-07-08 | 2026-07-08 | 2026-07-08 | Troubleman |  | 227.77 | Completed | No
WO-26-007325 | 2.7 | Bayou | BY-S13-04 | Trouble - partial or voltage | P2 same day | 2026-07-08 | 2026-07-09 | 2026-07-09 | Troubleman |  | 223.93 | Completed | No
WO-26-007326 | 4 | Bayou | BY-S07-05 | Trouble - partial or voltage | P2 same day | 2026-07-08 | 2026-07-08 | 2026-07-08 | Troubleman |  | 119.39 | Completed | No
WO-26-007327 | 4 | Bayou | BY-S17-02 | Trouble - partial or voltage | P2 same day | 2026-07-08 | 2026-07-08 | 2026-07-08 | Internal line |  | 46.72 | Completed | No
WO-26-007328 | 8.6 | Crossroads | CR-S30-06 | Corrective maintenance | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-14 | Underground crew |  | 100.43 | Completed | No
WO-26-007329 | 4.8 | Crossroads | CR-S24-04 | Corrective maintenance | P3 within 10 days | 2026-07-08 | 2026-07-09 | 2026-07-10 | Internal line |  | 2194.3 | Completed | No
WO-26-007330 | 9.2 | Crossroads | CR-S04-05 | Corrective maintenance | P3 within 10 days | 2026-07-08 | 2026-07-16 | 2026-07-20 | Contract line | CT-01 | 2020.3 | Completed | No
WO-26-007331 | 0.7 | Crossroads | CR-S27-02 | Meter exchange | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-13 | Meter technician |  | 127.52 | Completed | No
WO-26-007332 | 0.9 | Crossroads | CR-S04-05 | Meter exchange | P3 within 10 days | 2026-07-08 | 2026-07-14 | 2026-07-15 | Meter technician |  | 87.35 | Completed | No
WO-26-007333 | 11.1 | Crossroads | CR-S14-05 | New service - small | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-13 | Underground crew |  | 3349.4 | Completed | No
WO-26-007334 | 14.2 | Crossroads | CR-S21-03 | New service - small | P4 planned | 2026-07-08 | 2026-08-07 | 2026-08-15 | Underground crew |  | 2769.13 | Completed | No
WO-26-007335 | 1.9 | Crossroads | CR-S20-05 | Service order - field | P2 same day | 2026-07-08 | 2026-07-08 | 2026-07-08 | Meter technician |  | 4.7 | Completed | No
WO-26-007336 | 1.5 | Crossroads | CR-S24-03 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-14 | 2026-07-14 | Meter technician |  | 2.14 | Completed | No
WO-26-007337 | 1.3 | Crossroads | CR-S27-02 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-12 | 2026-07-14 | Meter technician |  | 30.81 | Completed | No
WO-26-007338 | 0.6 | Crossroads | CR-S13-05 | Service order - field | P3 within 10 days | 2026-07-08 | 2026-07-13 | 2026-07-13 | Meter technician |  | 2.98 | Completed | No
WO-26-007339 | 1.1 | Crossroads |  | Streetlight | P4 planned | 2026-07-08 | 2026-07-31 | 2026-08-02 | Contract line | CT-02 | 84.49 | Completed | No
WO-26-007340 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-08 | 2026-07-12 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-007341 | 2.7 | Crossroads |  | Streetlight | P4 planned | 2026-07-08 | 2026-07-27 | 2026-07-28 | Contract line | CT-01 | 193.24 | Completed | No
WO-26-007342 | 1.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-08 | 2026-07-11 | 2026-07-12 | Contract line | CT-01 | 356.38 | Completed | No
WO-26-007343 | 7.9 | Crossroads | CR-S26-01 | Transformer replacement | P3 within 10 days | 2026-07-08 | 2026-07-18 | 2026-07-18 | Contract line | CT-02 | 8229.93 | Completed | No
WO-26-007344 | 12 | Crossroads | CR-S16-04 | Transformer replacement | P2 same day | 2026-07-08 | 2026-07-08 | 2026-07-08 | Internal line |  | 9961.32 | Completed | No
WO-26-007345 | 3.6 | Crossroads | CR-S23-01 | Trouble - no power | P1 emergency | 2026-07-08 | 2026-07-08 | 2026-07-08 | Troubleman |  | 135 | Completed | No
WO-26-007346 | 4.9 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-07-08 | 2026-07-08 | 2026-07-08 | Internal line |  | 138.82 | Completed | No
WO-26-007347 | 3.9 | Crossroads | CR-S27-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-08 | 2026-07-11 | 2026-07-11 | Internal line |  | 174.41 | Completed | No
WO-26-007348 | 5.7 | Bayou | BY-S17-01 | Corrective maintenance | P4 planned | 2026-07-09 | 2026-08-15 | 2026-08-17 | Internal line |  | 1792.09 | Completed | No
WO-26-007349 |  | Bayou | BY-S13-02 | Corrective maintenance | P3 within 10 days | 2026-07-09 | 2026-07-10 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-007350 | 8.2 | Bayou | BY-S23-03 | Corrective maintenance | P4 planned | 2026-07-09 | 2026-08-07 | 2026-08-15 | Contract line | CT-03 | 1205.52 | Completed | No
WO-26-007351 | 0.7 | Bayou | BY-S22-04 | Meter exchange | P4 planned | 2026-07-09 | 2026-08-01 | 2026-08-03 | Meter technician |  | 148.82 | Completed | No
WO-26-007352 | 0.6 | Bayou | BY-S12-01 | Meter exchange | P4 planned | 2026-07-09 | 2026-08-28 | 2026-08-28 | Meter technician |  | 179.21 | Completed | No
WO-26-007353 | 0.9 | Bayou | BY-S21-01 | Meter exchange | P3 within 10 days | 2026-07-09 | 2026-07-18 | 2026-07-26 | Meter technician |  | 170.21 | Completed | No
WO-26-007354 | 14.4 | Bayou | BY-S18-04 | Pole replacement | P2 same day | 2026-07-09 | 2026-07-09 | 2026-07-09 | Internal line |  | 3192.52 | Completed | No
WO-26-007355 | 0.8 | Bayou | BY-S22-01 | Service order - field | P3 within 10 days | 2026-07-09 | 2026-07-12 | 2026-07-12 | Meter technician |  | 32.67 | Completed | No
WO-26-007356 | 1.7 | Bayou | BY-S12-04 | Service order - field | P2 same day | 2026-07-09 | 2026-07-09 | 2026-07-09 | Meter technician |  | 5.32 | Completed | No
WO-26-007357 | 7.7 | Bayou | BY-S15-02 | Transformer replacement | P2 same day | 2026-07-09 | 2026-07-09 | 2026-07-09 | Contract line | CT-04 | 3123.29 | Completed | No
WO-26-007358 | 11.4 | Bayou | BY-S24-02 | Transformer replacement | P2 same day | 2026-07-09 | 2026-07-09 | 2026-07-09 | Internal line |  | 10541.85 | Completed | No
WO-26-007359 | 3.6 | Bayou | BY-S12-03 | Trouble - no power | P2 same day | 2026-07-09 | 2026-07-10 | 2026-07-10 | Troubleman |  | 27.9 | Completed | No
WO-26-007360 | 2.3 | Bayou | BY-S11-02 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 239.34 | Completed | No
WO-26-007361 | 5.7 | Bayou | BY-S20-02 | Trouble - no power | P2 same day | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 241.52 | Completed | No
WO-26-007362 | 4.3 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 306.44 | Completed | No
WO-26-007363 | 2.6 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 335.14 | Completed | No
WO-26-007364 | 6 | Bayou | BY-S15-05 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 270.77 | Completed | No
WO-26-007365 | 2.7 | Bayou | BY-S16-04 | Trouble - partial or voltage | P2 same day | 2026-07-09 | 2026-07-10 | 2026-07-10 | Troubleman |  | 196.58 | Completed | No
WO-26-007366 | 4.2 | Bayou | BY-S07-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-09 | 2026-07-10 | 2026-07-14 | Troubleman |  | 35.38 | Completed | No
WO-26-007367 | 9.9 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-07-09 | 2026-07-13 | 2026-07-13 | Contract line | CT-02 | 1204.9 | Completed | No
WO-26-007368 |  | Crossroads | CR-S32-03 | Corrective maintenance | P4 planned | 2026-07-09 | 2026-09-03 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-007369 | 1.5 | Crossroads | CR-S12-02 | Meter exchange | P3 within 10 days | 2026-07-09 | 2026-07-16 | 2026-07-17 | Meter technician |  | 96.85 | Completed | No
WO-26-007370 | 1.3 | Crossroads | CR-S05-06 | Meter exchange | P3 within 10 days | 2026-07-09 | 2026-07-14 | 2026-07-14 | Meter technician |  | 133.93 | Completed | No
WO-26-007371 | 14.6 | Crossroads | CR-S18-03 | New service - small | P4 planned | 2026-07-09 | 2026-07-19 | 2026-07-21 | Contract line | CT-02 | 2056.45 | Completed | No
WO-26-007372 | 21.9 | Crossroads | CR-S16-04 | Pole replacement | P4 planned | 2026-07-09 | 2026-07-21 | 2026-07-22 | Contract line | CT-01 | 1795.79 | Completed | No
WO-26-007373 | 5.1 | Crossroads | CR-S20-02 | Preventive maintenance | P4 planned | 2026-07-09 | 2026-08-08 | 2026-08-09 | Contract line | CT-01 | 7.07 | Completed | No
WO-26-007374 | 6.4 | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-07-09 | 2026-07-30 | 2026-08-07 | Contract line | CT-01 | 121.71 | Completed | No
WO-26-007375 | 7.6 | Crossroads | CR-S27-04 | Preventive maintenance | P4 planned | 2026-07-09 | 2026-08-03 | 2026-08-11 | Underground crew |  | 251.34 | Completed | No
WO-26-007376 | 1.7 | Crossroads | CR-S28-03 | Service order - field | P2 same day | 2026-07-09 | 2026-07-10 | 2026-07-10 | Meter technician |  | 25.98 | Completed | No
WO-26-007377 | 0.6 | Crossroads | CR-S13-04 | Service order - field | P2 same day | 2026-07-09 | 2026-07-10 | 2026-07-10 | Meter technician |  | 15.85 | Completed | No
WO-26-007378 | 1.2 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-07-09 | 2026-07-11 | 2026-07-12 | Meter technician |  | 3.42 | Completed | No
WO-26-007379 |  | Crossroads |  | Streetlight | P4 planned | 2026-07-09 | 2026-09-07 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-007380 | 2.8 | Crossroads |  | Streetlight | P4 planned | 2026-07-09 | 2026-08-19 | 2026-08-19 | Contract line | CT-01 | 146.11 | Completed | No
WO-26-007381 | 1.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-09 | 2026-07-14 | 2026-07-14 | Internal line |  | 272.07 | Completed | No
WO-26-007382 | 12.1 | Crossroads | CR-S26-02 | Transformer replacement | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Contract line | CT-02 | 6965.59 | Completed | No
WO-26-007383 | 7.9 | Crossroads | CR-S21-01 | Transformer replacement | P3 within 10 days | 2026-07-09 | 2026-07-18 | 2026-07-19 | Internal line |  | 4601.17 | Completed | No
WO-26-007384 | 7.8 | Crossroads | CR-S17-02 | Transformer replacement | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Internal line |  | 5379.09 | Completed | No
WO-26-007385 | 4.3 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 23.08 | Completed | No
WO-26-007386 | 3.1 | Crossroads | CR-S29-03 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 348.88 | Completed | No
WO-26-007387 | 3.4 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 182.26 | Completed | No
WO-26-007388 | 4.5 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Troubleman |  | 224.71 | Completed | No
WO-26-007389 | 3.4 | Crossroads | CR-S07-04 | Trouble - no power | P1 emergency | 2026-07-09 | 2026-07-09 | 2026-07-09 | Internal line |  | 193.78 | Completed | No
WO-26-007390 | 4.2 | Crossroads | CR-S13-01 | Trouble - partial or voltage | P3 within 10 days | 2026-07-09 | 2026-07-11 | 2026-07-15 | Troubleman |  | 14.89 | Completed | No
WO-26-007391 | 4.7 | Bayou | BY-S13-03 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-20 | 2026-07-20 | Internal line |  | 1496.86 | Completed | No
WO-26-007392 | 7.1 | Bayou | BY-S28-02 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-17 | 2026-07-17 | Internal line |  | 297.41 | Completed | No
WO-26-007393 | 6.3 | Bayou | BY-S30-01 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-17 | 2026-07-17 | Internal line |  | 1387.66 | Completed | No
WO-26-007394 | 0.8 | Bayou | BY-S19-01 | Meter exchange | P3 within 10 days | 2026-07-10 | 2026-07-18 | 2026-07-18 | Meter technician |  | 158.38 | Completed | No
WO-26-007395 | 20.4 | Bayou | BY-S19-02 | Pole replacement | P3 within 10 days | 2026-07-10 | 2026-07-16 | 2026-07-16 | Contract line | CT-03 | 1492.04 | Completed | No
WO-26-007396 | 5.2 | Bayou | BY-S19-03 | Preventive maintenance | P4 planned | 2026-07-10 | 2026-08-05 | 2026-08-09 | Underground crew |  | 241.3 | Completed | No
WO-26-007397 | 0.8 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-07-10 | 2026-07-20 | 2026-07-21 | Meter technician |  | 3.38 | Completed | No
WO-26-007398 | 1.6 | Bayou | BY-S21-04 | Service order - field | P2 same day | 2026-07-10 | 2026-07-11 | 2026-07-11 | Meter technician |  | 14.38 | Completed | No
WO-26-007399 | 0.6 | Bayou | BY-S04-02 | Service order - field | P2 same day | 2026-07-10 | 2026-07-11 | 2026-07-11 | Meter technician |  | 21.9 | Completed | No
WO-26-007400 | 2 | Bayou | BY-S26-04 | Service order - field | P2 same day | 2026-07-10 | 2026-07-11 | 2026-07-11 | Meter technician |  | 6.04 | Completed | No
WO-26-007401 | 1.9 | Bayou | BY-S18-07 | Service order - field | P2 same day | 2026-07-10 | 2026-07-11 | 2026-07-11 | Meter technician |  | 11.62 | Completed | No
WO-26-007402 | 2.5 | Bayou |  | Streetlight | P4 planned | 2026-07-10 | 2026-07-24 | 2026-07-24 | Internal line |  | 250.37 | Completed | No
WO-26-007403 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-10 | 2026-07-12 | 2026-07-12 | Internal line |  | 448.65 | Completed | No
WO-26-007404 | 10.2 | Bayou | BY-S22-03 | Transformer replacement | P3 within 10 days | 2026-07-10 | 2026-07-17 | 2026-07-17 | Internal line |  | 9004.63 | Completed | No
WO-26-007405 | 3.1 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-07-10 | 2026-07-10 | 2026-07-10 | Troubleman |  | 155.55 | Completed | No
WO-26-007406 | 2.1 | Bayou | BY-S16-05 | Trouble - no power | P1 emergency | 2026-07-10 | 2026-07-10 | 2026-07-10 | Troubleman |  | 208.5 | Completed | No
WO-26-007407 | 4.7 | Bayou | BY-S27-05 | Trouble - no power | P1 emergency | 2026-07-10 | 2026-07-10 | 2026-07-10 | Troubleman |  | 255.38 | Completed | No
WO-26-007408 | 3.6 | Bayou | BY-S11-03 | Trouble - no power | P1 emergency | 2026-07-10 | 2026-07-10 | 2026-07-10 | Internal line |  | 192.48 | Completed | No
WO-26-007409 | 3.1 | Bayou | BY-S04-01 | Trouble - no power | P1 emergency | 2026-07-10 | 2026-07-10 | 2026-07-10 | Troubleman |  | 232.64 | Completed | No
WO-26-007410 |  | Bayou | BY-S15-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-10 | 2026-07-17 |  | Troubleman |  |  | Cancelled | No
WO-26-007411 | 4.9 | Bayou | BY-S02-02 | Trouble - partial or voltage | P2 same day | 2026-07-10 | 2026-07-10 | 2026-07-10 | Troubleman |  | 35.49 | Completed | No
WO-26-007412 | 3.6 | Bayou | BY-S09-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-10 | 2026-07-18 | 2026-07-18 | Troubleman |  | 132.59 | Completed | No
WO-26-007413 | 3.2 | Bayou | BY-S23-03 | Trouble - partial or voltage | P2 same day | 2026-07-10 | 2026-07-10 | 2026-07-10 | Troubleman |  | 226.36 | Completed | No
WO-26-007414 | 4.6 | Bayou | BY-S17-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-10 | 2026-07-13 | 2026-07-13 | Troubleman |  | 16.77 | Completed | No
WO-26-007415 | 9 | Crossroads | CR-S29-03 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-18 | 2026-07-18 | Underground crew |  | 968.84 | Completed | No
WO-26-007416 | 3.9 | Crossroads | CR-S11-02 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-19 | 2026-07-19 | Internal line |  | 1429.67 | Completed | No
WO-26-007417 | 11 | Crossroads | CR-S14-03 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-14 | 2026-07-16 | Contract line | CT-02 | 1801.25 | Completed | No
WO-26-007418 | 3.7 | Crossroads | CR-S15-03 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-12 | 2026-07-14 | Contract line | CT-01 | 1611.26 | Completed | No
WO-26-007419 | 10.1 | Crossroads | CR-S23-04 | Corrective maintenance | P3 within 10 days | 2026-07-10 | 2026-07-18 | 2026-07-18 | Internal line |  | 361.9 | Completed | No
WO-26-007420 | 1.4 | Crossroads | CR-S18-05 | Meter exchange | P4 planned | 2026-07-10 | 2026-08-18 | 2026-08-19 | Meter technician |  | 70.26 | Completed | No
WO-26-007421 |  | Crossroads | CR-S18-02 | Meter exchange | P4 planned | 2026-07-10 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-007422 | 1.2 | Crossroads | CR-S04-06 | Meter exchange | P3 within 10 days | 2026-07-10 | 2026-07-20 | 2026-07-21 | Meter technician |  | 123.35 | Completed | No
WO-26-007423 | 0.8 | Crossroads | CR-S27-02 | Meter exchange | P4 planned | 2026-07-10 | 2026-08-27 | 2026-08-29 | Meter technician |  | 76.57 | Completed | No
WO-26-007424 | 13.1 | Crossroads | CR-S22-03 | New service - small | P4 planned | 2026-07-10 | 2026-07-28 | 2026-07-28 | Contract line | CT-02 | 2931.59 | Completed | No
WO-26-007425 | 4.3 | Crossroads | CR-S09-03 | Preventive maintenance | P4 planned | 2026-07-10 | 2026-07-18 | 2026-07-20 | Contract line | CT-02 | 11.9 | Completed | No
WO-26-007426 | 7.3 | Crossroads | CR-S21-03 | Preventive maintenance | P4 planned | 2026-07-10 | 2026-08-11 | 2026-08-13 | Internal line |  | 512.36 | Completed | No
WO-26-007427 | 2 | Crossroads | CR-S16-06 | Preventive maintenance | P4 planned | 2026-07-10 | 2026-07-25 | 2026-07-25 | Underground crew |  | 51.63 | Completed | No
WO-26-007428 | 1.6 | Crossroads | CR-S16-04 | Service order - field | P3 within 10 days | 2026-07-10 | 2026-07-14 | 2026-07-14 | Meter technician |  | 30.05 | Completed | No
WO-26-007429 | 1.1 | Crossroads | CR-S23-04 | Service order - field | P3 within 10 days | 2026-07-10 | 2026-07-19 | 2026-07-19 | Meter technician |  | 35.89 | Completed | No
WO-26-007430 | 1.5 | Crossroads | CR-S29-03 | Service order - field | P3 within 10 days | 2026-07-10 | 2026-07-20 | 2026-07-20 | Meter technician |  | 0.85 | Completed | No
WO-26-007431 | 2.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-10 | 2026-07-16 | 2026-07-20 | Contract line | CT-01 | 441.81 | Completed | No
WO-26-007432 | 6.3 | Crossroads | CR-S04-04 | Transformer replacement | P3 within 10 days | 2026-07-10 | 2026-07-12 | 2026-07-12 | Internal line |  | 4864.98 | Completed | No
WO-26-007433 | 3.6 | Crossroads | CR-S11-02 | Trouble - no power | P2 same day | 2026-07-10 | 2026-07-11 | 2026-07-11 | Internal line |  | 36.13 | Completed | No
WO-26-007434 | 4.9 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-10 | 2026-07-19 | 2026-07-19 | Troubleman |  | 205.66 | Completed | No
WO-26-007435 | 1.6 | Bayou | BY-S27-01 | Service order - field | P2 same day | 2026-07-11 | 2026-07-12 | 2026-07-12 | Meter technician |  | 3.59 | Completed | No
WO-26-007436 | 1.1 | Bayou | BY-S09-01 | Service order - field | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Meter technician |  | 14.8 | Completed | No
WO-26-007437 | 13 | Bayou | BY-S29-01 | Transformer replacement | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Internal line |  | 9472.75 | Completed | No
WO-26-007438 | 12.2 | Bayou | BY-S26-02 | Transformer replacement | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Internal line |  | 8399.53 | Completed | No
WO-26-007439 | 3.5 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 300.27 | Completed | No
WO-26-007440 | 3.6 | Bayou | BY-S01-01 | Trouble - no power | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 38.49 | Completed | No
WO-26-007441 | 5 | Bayou | BY-S13-06 | Trouble - no power | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 340.79 | Completed | No
WO-26-007442 | 2.9 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 285.94 | Completed | No
WO-26-007443 | 4.4 | Bayou | BY-S27-01 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 101.6 | Completed | No
WO-26-007444 | 12.3 | Crossroads | CR-S05-04 | Pole replacement | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Contract line | CT-02 | 2080.21 | Completed | No
WO-26-007445 | 0.9 | Crossroads | CR-S06-03 | Service order - field | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Meter technician |  | 0.7 | Completed | No
WO-26-007446 | 13.4 | Crossroads | CR-S27-04 | Transformer replacement | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Internal line |  | 10536.28 | Completed | No
WO-26-007447 | 6.4 | Crossroads | CR-S26-06 | Transformer replacement | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Internal line |  | 7633.07 | Completed | No
WO-26-007448 | 3.5 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 191.79 | Completed | No
WO-26-007449 | 3.3 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Internal line |  | 75.75 | Completed | No
WO-26-007450 | 3.1 | Crossroads | CR-S32-03 | Trouble - no power | P2 same day | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 112.06 | Completed | No
WO-26-007451 | 6 | Crossroads | CR-S25-04 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 143.8 | Completed | No
WO-26-007452 | 3.1 | Crossroads | CR-S24-01 | Trouble - no power | P2 same day | 2026-07-11 | 2026-07-12 | 2026-07-12 | Troubleman |  | 26.08 | Completed | No
WO-26-007453 | 2.8 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 212.62 | Completed | No
WO-26-007454 |  | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 |  | Internal line |  |  | Cancelled | No
WO-26-007455 | 3.7 | Crossroads | CR-S14-01 | Trouble - no power | P2 same day | 2026-07-11 | 2026-07-12 | 2026-07-12 | Troubleman |  | 74.91 | Completed | No
WO-26-007456 | 2.6 | Crossroads | CR-S22-03 | Trouble - no power | P1 emergency | 2026-07-11 | 2026-07-11 | 2026-07-11 | Troubleman |  | 337.06 | Completed | No
WO-26-007457 | 3.9 | Bayou | BY-S07-04 | Corrective maintenance | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Contract line | CT-03 | 1161.01 | Completed | No
WO-26-007458 | 22.9 | Bayou | BY-S19-01 | Pole replacement | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Contract line | CT-03 | 2898.06 | Completed | No
WO-26-007459 | 1.6 | Bayou | BY-S17-01 | Service order - field | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Meter technician |  | 36.86 | Completed | No
WO-26-007460 | 1.8 | Bayou | BY-S02-01 | Service order - field | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Meter technician |  | 22.77 | Completed | No
WO-26-007461 | 7.5 | Bayou | BY-S21-02 | Transformer replacement | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Contract line | CT-03 | 3456.01 | Completed | No
WO-26-007462 | 4.2 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 183.4 | Completed | No
WO-26-007463 | 3.5 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 214.25 | Completed | No
WO-26-007464 | 4.5 | Bayou | BY-S25-05 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Internal line |  | 79.71 | Completed | No
WO-26-007465 | 5.2 | Bayou | BY-S25-05 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 103.23 | Completed | No
WO-26-007466 | 2.5 | Bayou | BY-S21-05 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 208.63 | Completed | No
WO-26-007467 | 3.1 | Bayou | BY-S17-04 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Troubleman |  | 127.01 | Completed | No
WO-26-007468 | 3.8 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 19.67 | Completed | No
WO-26-007469 | 2.9 | Bayou | BY-S26-03 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 52.11 | Completed | No
WO-26-007470 | 4 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Internal line |  | 34.67 | Completed | No
WO-26-007471 | 4.7 | Bayou | BY-S08-01 | Trouble - partial or voltage | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Troubleman |  | 44.36 | Completed | No
WO-26-007472 | 8.7 | Crossroads | CR-S07-07 | Corrective maintenance | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Underground crew |  | 1550.65 | Completed | No
WO-26-007473 | 1.6 | Crossroads | CR-S19-02 | Service order - field | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Meter technician |  | 20.52 | Completed | No
WO-26-007474 | 9.8 | Crossroads | CR-S30-01 | Transformer replacement | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Internal line |  | 3061.76 | Completed | No
WO-26-007475 | 4.7 | Crossroads | CR-S05-03 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 308.99 | Completed | No
WO-26-007476 | 2.5 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Internal line |  | 304.44 | Completed | No
WO-26-007477 | 3.3 | Crossroads | CR-S32-04 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 58.99 | Completed | No
WO-26-007478 | 3.5 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 301.99 | Completed | No
WO-26-007479 | 5.3 | Crossroads | CR-S31-03 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Troubleman |  | 336.4 | Completed | No
WO-26-007480 | 4.1 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 48.36 | Completed | No
WO-26-007481 | 4.5 | Crossroads | CR-S29-01 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-12 | 2026-07-12 | Troubleman |  | 272.09 | Completed | No
WO-26-007482 | 3.4 | Crossroads | CR-S04-01 | Trouble - no power | P2 same day | 2026-07-12 | 2026-07-13 | 2026-07-13 | Troubleman |  | 167.34 | Completed | No
WO-26-007483 | 10.2 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-07-13 | 2026-07-19 | 2026-07-27 | Contract line | CT-03 | 1934.33 | Completed | No
WO-26-007484 | 4.9 | Bayou | BY-S12-03 | Corrective maintenance | P3 within 10 days | 2026-07-13 | 2026-07-17 | 2026-07-17 | Contract line | CT-03 | 1374.74 | Completed | No
WO-26-007485 | 10.1 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-07-13 | 2026-07-21 | 2026-07-23 | Internal line |  | 2295.25 | Completed | No
WO-26-007486 | 1 | Bayou | BY-S29-05 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-21 | 2026-07-23 | Meter technician |  | 61.56 | Completed | No
WO-26-007487 |  | Bayou | BY-S14-01 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-15 |  | Meter technician |  |  | Cancelled | No
WO-26-007488 | 0.8 | Bayou | BY-S23-03 | Meter exchange | P4 planned | 2026-07-13 | 2026-08-16 | 2026-08-16 | Meter technician |  | 151.9 | Completed | No
WO-26-007489 | 1.1 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-14 | 2026-07-15 | Meter technician |  | 154.32 | Completed | No
WO-26-007490 | 0.9 | Bayou | BY-S27-03 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-17 | 2026-07-21 | Meter technician |  | 64.51 | Completed | No
WO-26-007491 | 7 | Bayou | BY-S09-03 | New service - small | P4 planned | 2026-07-13 | 2026-08-19 | 2026-08-19 | Contract line | CT-03 | 4007.62 | Completed | No
WO-26-007492 | 0.9 | Bayou | BY-S11-02 | Service order - field | P3 within 10 days | 2026-07-13 | 2026-07-15 | 2026-07-16 | Meter technician |  | 4.36 | Completed | No
WO-26-007493 | 1.7 | Bayou | BY-S15-03 | Service order - field | P3 within 10 days | 2026-07-13 | 2026-07-21 | 2026-07-22 | Meter technician |  | 19.57 | Completed | No
WO-26-007494 | 2.6 | Bayou |  | Streetlight | P4 planned | 2026-07-13 | 2026-08-06 | 2026-08-10 | Contract line | CT-03 | 365.31 | Completed | No
WO-26-007495 |  | Bayou |  | Streetlight | P4 planned | 2026-07-13 | 2026-09-09 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-007496 | 12.3 | Bayou | BY-S04-01 | Transformer replacement | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Internal line |  | 11261.29 | Completed | No
WO-26-007497 | 8.2 | Bayou | BY-S23-05 | Transformer replacement | P3 within 10 days | 2026-07-13 | 2026-07-15 | 2026-07-17 | Internal line |  | 9792.15 | Completed | No
WO-26-007498 | 3.1 | Bayou | BY-S23-01 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 325.41 | Completed | No
WO-26-007499 | 4.7 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 47.87 | Completed | No
WO-26-007500 | 3.7 | Bayou | BY-S22-04 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 207.08 | Completed | No
WO-26-007501 | 4.7 | Bayou | BY-S12-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-13 | 2026-07-14 | 2026-07-15 | Troubleman |  | 97.56 | Completed | No
WO-26-007502 | 4.3 | Crossroads | CR-S31-03 | Corrective maintenance | P3 within 10 days | 2026-07-13 | 2026-07-20 | 2026-07-20 | Underground crew |  | 2000.79 | Completed | No
WO-26-007503 | 4.2 | Crossroads | CR-S13-06 | Corrective maintenance | P3 within 10 days | 2026-07-13 | 2026-07-17 | 2026-07-21 | Internal line |  | 613.34 | Completed | No
WO-26-007504 | 11.3 | Crossroads | CR-S03-03 | Corrective maintenance | P3 within 10 days | 2026-07-13 | 2026-07-17 | 2026-07-19 | Internal line |  | 1313.53 | Completed | No
WO-26-007505 | 1.4 | Crossroads | CR-S19-03 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-20 | 2026-07-20 | Meter technician |  | 105.2 | Completed | No
WO-26-007506 | 1.3 | Crossroads | CR-S20-02 | Meter exchange | P4 planned | 2026-07-13 | 2026-07-23 | 2026-07-23 | Meter technician |  | 144.73 | Completed | No
WO-26-007507 | 0.7 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-15 | 2026-07-15 | Meter technician |  | 179.68 | Completed | No
WO-26-007508 | 0.9 | Crossroads | CR-S27-03 | Meter exchange | P3 within 10 days | 2026-07-13 | 2026-07-14 | 2026-07-14 | Meter technician |  | 142.31 | Completed | No
WO-26-007509 |  | Crossroads | CR-S13-05 | New service - small | P4 planned | 2026-07-13 | 2026-09-04 |  | Internal line |  |  | Scheduled | No
WO-26-007510 | 6.2 | Crossroads | CR-S27-04 | New service - small | P4 planned | 2026-07-13 | 2026-08-29 | 2026-08-31 | Contract line | CT-01 | 590.42 | Completed | No
WO-26-007511 | 21.1 | Crossroads | CR-S31-01 | Pole replacement | P2 same day | 2026-07-13 | 2026-07-13 | 2026-07-13 | Contract line | CT-01 | 2253.9 | Completed | No
WO-26-007512 | 10.8 | Crossroads | CR-S26-02 | Pole replacement | P4 planned | 2026-07-13 | 2026-08-29 | 2026-08-29 | Contract line | CT-01 | 3376.95 | Completed | No
WO-26-007513 | 6.7 | Crossroads | CR-S04-06 | Preventive maintenance | P4 planned | 2026-07-13 | 2026-08-16 | 2026-08-18 | Underground crew |  | 68.52 | Completed | No
WO-26-007514 | 1.4 | Crossroads | CR-S01-03 | Service order - field | P3 within 10 days | 2026-07-13 | 2026-07-20 | 2026-07-22 | Meter technician |  | 17.1 | Completed | No
WO-26-007515 | 1.4 | Crossroads | CR-S04-02 | Service order - field | P3 within 10 days | 2026-07-13 | 2026-07-20 | 2026-07-20 | Meter technician |  | 4.1 | Completed | No
WO-26-007516 | 0.8 | Crossroads | CR-S09-05 | Service order - field | P3 within 10 days | 2026-07-13 | 2026-07-20 | 2026-07-21 | Meter technician |  | 26.61 | Completed | No
WO-26-007517 | 0.9 | Crossroads | CR-S18-06 | Service order - field | P3 within 10 days | 2026-07-13 | 2026-07-16 | 2026-07-17 | Meter technician |  | 2.66 | Completed | No
WO-26-007518 | 3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-13 | 2026-07-15 | 2026-07-19 | Internal line |  | 209.98 | Completed | No
WO-26-007519 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-13 | 2026-07-17 | 2026-07-18 | Contract line | CT-02 | 234.48 | Completed | No
WO-26-007520 | 1.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-13 | 2026-07-23 | 2026-07-24 | Contract line | CT-01 | 385.41 | Completed | No
WO-26-007521 |  | Crossroads |  | Streetlight | P4 planned | 2026-07-13 | 2026-09-04 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-007522 | 13.5 | Crossroads | CR-S05-01 | Transformer replacement | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Internal line |  | 10385.47 | Completed | No
WO-26-007523 | 2.2 | Crossroads | CR-S25-03 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 315.69 | Completed | No
WO-26-007524 | 2.1 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 80.09 | Completed | No
WO-26-007525 | 4.5 | Crossroads | CR-S27-03 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 86.15 | Completed | No
WO-26-007526 | 5.6 | Crossroads | CR-S19-04 | Trouble - no power | P2 same day | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 260.68 | Completed | No
WO-26-007527 | 4.5 | Crossroads | CR-S05-06 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 47.2 | Completed | No
WO-26-007528 | 3.2 | Crossroads | CR-S05-01 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Internal line |  | 181.76 | Completed | No
WO-26-007529 | 5.2 | Crossroads | CR-S25-01 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 348.37 | Completed | No
WO-26-007530 | 4.2 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 330.48 | Completed | No
WO-26-007531 | 5.7 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 119.82 | Completed | No
WO-26-007532 | 2.4 | Crossroads | CR-S07-02 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 112.83 | Completed | No
WO-26-007533 | 5.7 | Crossroads | CR-S14-06 | Trouble - no power | P1 emergency | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 284.41 | Completed | No
WO-26-007534 | 4.6 | Crossroads | CR-S20-01 | Trouble - partial or voltage | P2 same day | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 175.94 | Completed | No
WO-26-007535 | 2.5 | Crossroads | CR-S13-04 | Trouble - partial or voltage | P2 same day | 2026-07-13 | 2026-07-13 | 2026-07-13 | Troubleman |  | 226.98 | Completed | No
WO-26-007536 | 2.1 | Crossroads | CR-S08-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-13 | 2026-07-23 | 2026-07-24 | Troubleman |  | 17.99 | Completed | No
WO-26-007537 | 4.7 | Bayou | BY-S23-01 | Corrective maintenance | P3 within 10 days | 2026-07-14 | 2026-07-22 | 2026-07-23 | Underground crew |  | 2173.78 | Completed | No
WO-26-007538 | 4 | Bayou | BY-S25-03 | Corrective maintenance | P3 within 10 days | 2026-07-14 | 2026-07-15 | 2026-07-15 | Contract line | CT-04 | 1246.91 | Completed | No
WO-26-007539 | 9.5 | Bayou | BY-S25-02 | Corrective maintenance | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Underground crew |  | 1781.96 | Completed | No
WO-26-007540 | 3.5 | Bayou | BY-S18-05 | Corrective maintenance | P3 within 10 days | 2026-07-14 | 2026-07-19 | 2026-07-19 | Underground crew |  | 143.23 | Completed | No
WO-26-007541 |  | Bayou | BY-S26-04 | Meter exchange | P4 planned | 2026-07-14 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-007542 | 0.6 | Bayou | BY-S22-03 | Meter exchange | P4 planned | 2026-07-14 | 2026-07-27 | 2026-07-31 | Meter technician |  | 90.21 | Completed | No
WO-26-007543 | 1.4 | Bayou | BY-S27-06 | Meter exchange | P4 planned | 2026-07-14 | 2026-08-15 | 2026-08-16 | Meter technician |  | 138.45 | Completed | No
WO-26-007544 | 1 | Bayou | BY-S13-05 | Meter exchange | P3 within 10 days | 2026-07-14 | 2026-07-22 | 2026-07-22 | Meter technician |  | 116.26 | Completed | No
WO-26-007545 | 1.3 | Bayou | BY-S13-04 | Meter exchange | P3 within 10 days | 2026-07-14 | 2026-07-19 | 2026-07-19 | Meter technician |  | 169.5 | Completed | No
WO-26-007546 | 0.5 | Bayou | BY-S20-03 | Meter exchange | P3 within 10 days | 2026-07-14 | 2026-07-22 | 2026-07-23 | Meter technician |  | 172.89 | Completed | No
WO-26-007547 | 14.3 | Bayou | BY-S15-02 | Pole replacement | P3 within 10 days | 2026-07-14 | 2026-07-18 | 2026-07-18 | Contract line | CT-04 | 2197.78 | Completed | No
WO-26-007548 |  | Bayou | BY-S01-01 | Pole replacement | P4 planned | 2026-07-14 | 2026-09-10 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-007549 | 17 | Bayou | BY-S17-02 | Pole replacement | P3 within 10 days | 2026-07-14 | 2026-07-16 | 2026-07-16 | Contract line | CT-04 | 2467.55 | Completed | No
WO-26-007550 | 7.2 | Bayou | BY-S23-01 | Preventive maintenance | P4 planned | 2026-07-14 | 2026-08-13 | 2026-08-13 | Internal line |  | 495.34 | Completed | No
WO-26-007551 | 4.1 | Bayou | BY-S13-01 | Preventive maintenance | P4 planned | 2026-07-14 | 2026-08-27 | 2026-08-29 | Underground crew |  | 582.9 | Completed | No
WO-26-007552 | 1.5 | Bayou | BY-S14-01 | Service order - field | P3 within 10 days | 2026-07-14 | 2026-07-21 | 2026-07-29 | Meter technician |  | 39.46 | Completed | No
WO-26-007553 | 1.7 | Bayou | BY-S11-01 | Service order - field | P3 within 10 days | 2026-07-14 | 2026-07-21 | 2026-07-21 | Meter technician |  | 9.19 | Completed | No
WO-26-007554 | 1.5 | Bayou | BY-S03-02 | Service order - field | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Meter technician |  | 33.6 | Completed | No
WO-26-007555 | 2 | Bayou | BY-S07-04 | Service order - field | P3 within 10 days | 2026-07-14 | 2026-07-20 | 2026-07-24 | Meter technician |  | 1.95 | Completed | No
WO-26-007556 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-14 | 2026-07-17 | 2026-07-21 | Internal line |  | 115.25 | Completed | No
WO-26-007557 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-14 | 2026-07-24 | 2026-08-01 | Contract line | CT-03 | 275.74 | Completed | No
WO-26-007558 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-14 | 2026-07-24 | 2026-08-01 | Contract line | CT-03 | 367.26 | Completed | No
WO-26-007559 | 9.4 | Bayou | BY-S09-04 | Transformer replacement | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 4259.19 | Completed | No
WO-26-007560 | 7.8 | Bayou | BY-S29-05 | Transformer replacement | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Contract line | CT-03 | 7800.91 | Completed | No
WO-26-007561 | 5.2 | Bayou | BY-S17-04 | Trouble - no power | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 309.61 | Completed | No
WO-26-007562 | 3.1 | Bayou | BY-S16-06 | Trouble - no power | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Troubleman |  | 267.52 | Completed | No
WO-26-007563 | 2.7 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 321.41 | Completed | No
WO-26-007564 |  | Bayou | BY-S17-02 | Trouble - partial or voltage | P2 same day | 2026-07-14 | 2026-07-14 |  | Troubleman |  |  | Cancelled | No
WO-26-007565 | 2.8 | Bayou | BY-S07-04 | Trouble - partial or voltage | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Troubleman |  | 93.42 | Completed | No
WO-26-007566 | 4.7 | Bayou | BY-S21-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-14 | 2026-07-17 | 2026-07-17 | Troubleman |  | 96.42 | Completed | No
WO-26-007567 | 11.7 | Crossroads | CR-S08-05 | Corrective maintenance | P3 within 10 days | 2026-07-14 | 2026-07-16 | 2026-07-16 | Underground crew |  | 2103.71 | Completed | No
WO-26-007568 | 6.4 | Crossroads | CR-S03-02 | Corrective maintenance | P3 within 10 days | 2026-07-14 | 2026-07-17 | 2026-07-17 | Underground crew |  | 1320.11 | Completed | No
WO-26-007569 | 4 | Crossroads | CR-S09-02 | Corrective maintenance | P3 within 10 days | 2026-07-14 | 2026-07-18 | 2026-07-18 | Internal line |  | 437.32 | Completed | No
WO-26-007570 |  | Crossroads | CR-S28-03 | Corrective maintenance | P4 planned | 2026-07-14 | 2026-09-01 |  | Internal line |  |  | Scheduled | No
WO-26-007571 | 4.9 | Crossroads | CR-S20-02 | Corrective maintenance | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 928.58 | Completed | No
WO-26-007572 | 4.4 | Crossroads | CR-S04-06 | Corrective maintenance | P4 planned | 2026-07-14 | 2026-08-10 | 2026-08-10 | Underground crew |  | 2229.2 | Completed | No
WO-26-007573 | 0.8 | Crossroads | CR-S28-03 | Meter exchange | P4 planned | 2026-07-14 | 2026-08-27 | 2026-08-28 | Meter technician |  | 66.51 | Completed | No
WO-26-007574 | 0.6 | Crossroads | CR-S27-04 | Meter exchange | P4 planned | 2026-07-14 | 2026-08-28 | 2026-08-28 | Meter technician |  | 135.29 | Completed | No
WO-26-007575 |  | Crossroads | CR-S17-02 | Meter exchange | P4 planned | 2026-07-14 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-007576 | 1 | Crossroads | CR-S08-02 | Meter exchange | P3 within 10 days | 2026-07-14 | 2026-07-15 | 2026-07-16 | Meter technician |  | 169.81 | Completed | No
WO-26-007577 | 14.5 | Crossroads | CR-S30-03 | New service - small | P4 planned | 2026-07-14 | 2026-08-15 | 2026-08-17 | Internal line |  | 1270.98 | Completed | No
WO-26-007578 | 4.1 | Crossroads | CR-S18-04 | New service - small | P4 planned | 2026-07-14 | 2026-07-27 | 2026-07-27 | Contract line | CT-01 | 505.45 | Completed | No
WO-26-007579 | 12.1 | Crossroads | CR-S09-01 | New service - small | P4 planned | 2026-07-14 | 2026-07-21 | 2026-07-29 | Underground crew |  | 3817.58 | Completed | No
WO-26-007580 | 10.4 | Crossroads | CR-S15-03 | Pole replacement | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Contract line | CT-02 | 3124.61 | Completed | No
WO-26-007581 | 4.1 | Crossroads | CR-S02-01 | Preventive maintenance | P4 planned | 2026-07-14 | 2026-07-22 | 2026-07-23 | Internal line |  | 273.06 | Completed | No
WO-26-007582 | 7.5 | Crossroads | CR-S23-04 | Preventive maintenance | P4 planned | 2026-07-14 | 2026-08-13 | 2026-08-15 | Underground crew |  | 45.01 | Completed | No
WO-26-007583 | 2.4 | Crossroads | CR-S03-03 | Preventive maintenance | P4 planned | 2026-07-14 | 2026-08-26 | 2026-08-27 | Contract line | CT-02 | 295.8 | Completed | No
WO-26-007584 |  | Crossroads | CR-S07-07 | Preventive maintenance | P4 planned | 2026-07-14 | 2026-09-04 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-007585 | 1 | Crossroads | CR-S19-03 | Service order - field | P3 within 10 days | 2026-07-14 | 2026-07-24 | 2026-07-24 | Meter technician |  | 31.84 | Completed | No
WO-26-007586 | 1 | Crossroads | CR-S28-02 | Service order - field | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Meter technician |  | 31.51 | Completed | No
WO-26-007587 | 0.6 | Crossroads | CR-S20-04 | Service order - field | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Meter technician |  | 30.81 | Completed | No
WO-26-007588 | 1 | Crossroads | CR-S09-04 | Service order - field | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Meter technician |  | 11.7 | Completed | No
WO-26-007589 | 1.2 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-07-14 | 2026-07-20 | 2026-07-20 | Meter technician |  | 24.92 | Completed | No
WO-26-007590 | 1.3 | Crossroads | CR-S20-05 | Service order - field | P2 same day | 2026-07-14 | 2026-07-15 | 2026-07-15 | Meter technician |  | 19 | Completed | No
WO-26-007591 | 1.8 | Crossroads |  | Streetlight | P4 planned | 2026-07-14 | 2026-08-09 | 2026-08-17 | Contract line | CT-01 | 280.05 | Completed | No
WO-26-007592 |  | Crossroads |  | Streetlight | P4 planned | 2026-07-14 | 2026-09-01 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-007593 | 9.7 | Crossroads | CR-S28-04 | Transformer replacement | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 5932.25 | Completed | No
WO-26-007594 | 8 | Crossroads | CR-S03-01 | Transformer replacement | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 11174.16 | Completed | No
WO-26-007595 | 8.3 | Crossroads | CR-S11-01 | Transformer replacement | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 11749.76 | Completed | No
WO-26-007596 | 3.2 | Crossroads | CR-S16-03 | Trouble - no power | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 38.19 | Completed | No
WO-26-007597 | 4.5 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 42.18 | Completed | No
WO-26-007598 | 3.3 | Crossroads | CR-S26-03 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 162.62 | Completed | No
WO-26-007599 | 3 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 286.75 | Completed | No
WO-26-007600 | 2.6 | Crossroads | CR-S25-06 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 322.14 | Completed | No
WO-26-007601 | 3.2 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 97.21 | Completed | No
WO-26-007602 | 5.6 | Crossroads | CR-S23-04 | Trouble - no power | P1 emergency | 2026-07-14 | 2026-07-14 | 2026-07-14 | Internal line |  | 332.3 | Completed | No
WO-26-007603 | 1.8 | Crossroads | CR-S06-01 | Trouble - partial or voltage | P3 within 10 days | 2026-07-14 | 2026-07-16 | 2026-07-16 | Troubleman |  | 130.35 | Completed | No
WO-26-007604 | 4.3 | Crossroads | CR-S27-04 | Trouble - partial or voltage | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 142.27 | Completed | No
WO-26-007605 | 2.2 | Crossroads | CR-S09-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-14 | 2026-07-17 | 2026-07-19 | Troubleman |  | 88.97 | Completed | No
WO-26-007606 | 2.8 | Crossroads | CR-S16-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-14 | 2026-07-18 | 2026-07-19 | Troubleman |  | 227.92 | Completed | No
WO-26-007607 | 4.3 | Crossroads | CR-S32-01 | Trouble - partial or voltage | P2 same day | 2026-07-14 | 2026-07-14 | 2026-07-14 | Troubleman |  | 108.71 | Completed | No
WO-26-007608 | 5.7 | Bayou | BY-S15-01 | Corrective maintenance | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Internal line |  | 887.17 | Completed | No
WO-26-007609 | 9.8 | Bayou | BY-S23-04 | Corrective maintenance | P3 within 10 days | 2026-07-15 | 2026-07-22 | 2026-07-22 | Internal line |  | 2085.49 | Completed | No
WO-26-007610 | 1.4 | Bayou | BY-S25-02 | Meter exchange | P4 planned | 2026-07-15 | 2026-08-23 | 2026-08-23 | Meter technician |  | 148.25 | Completed | No
WO-26-007611 | 1.1 | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-07-15 | 2026-07-19 | 2026-07-20 | Meter technician |  | 127.14 | Completed | No
WO-26-007612 | 15.6 | Bayou | BY-S24-05 | Pole replacement | P2 same day | 2026-07-15 | 2026-07-16 | 2026-07-16 | Contract line | CT-03 | 1249.35 | Completed | No
WO-26-007613 | 2.7 | Bayou | BY-S02-02 | Preventive maintenance | P4 planned | 2026-07-15 | 2026-08-01 | 2026-08-03 | Internal line |  | 546.24 | Completed | No
WO-26-007614 | 1.9 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-07-15 | 2026-07-16 | 2026-07-20 | Meter technician |  | 20.24 | Completed | No
WO-26-007615 | 1.9 | Bayou | BY-S10-04 | Service order - field | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Meter technician |  | 9.53 | Completed | No
WO-26-007616 | 0.8 | Bayou | BY-S19-04 | Service order - field | P2 same day | 2026-07-15 | 2026-07-16 | 2026-07-16 | Meter technician |  | 23.61 | Completed | No
WO-26-007617 | 1.7 | Bayou | BY-S15-02 | Service order - field | P2 same day | 2026-07-15 | 2026-07-16 | 2026-07-16 | Meter technician |  | 26.92 | Completed | No
WO-26-007618 | 1.6 | Bayou | BY-S30-01 | Service order - field | P3 within 10 days | 2026-07-15 | 2026-07-17 | 2026-07-19 | Meter technician |  | 2.37 | Completed | No
WO-26-007619 | 1.6 | Bayou | BY-S27-06 | Service order - field | P3 within 10 days | 2026-07-15 | 2026-07-22 | 2026-07-22 | Meter technician |  | 39.19 | Completed | No
WO-26-007620 | 2 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-07-15 | 2026-07-16 | 2026-07-16 | Meter technician |  | 15.26 | Completed | No
WO-26-007621 | 0.6 | Bayou | BY-S07-02 | Service order - field | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Meter technician |  | 30.35 | Completed | No
WO-26-007622 | 1.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-15 | 2026-07-19 | 2026-07-27 | Contract line | CT-04 | 330.13 | Completed | No
WO-26-007623 | 2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-15 | 2026-07-16 | 2026-07-18 | Contract line | CT-04 | 431.26 | Completed | No
WO-26-007624 | 5.3 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Internal line |  | 211.65 | Completed | No
WO-26-007625 | 3.6 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 5.24 | Completed | No
WO-26-007626 | 2.9 | Bayou | BY-S15-03 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 282.98 | Completed | No
WO-26-007627 | 4.8 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 282.24 | Completed | No
WO-26-007628 | 4.1 | Bayou | BY-S02-01 | Trouble - partial or voltage | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 90.89 | Completed | No
WO-26-007629 | 2.8 | Bayou | BY-S25-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-15 | 2026-07-23 | 2026-07-23 | Troubleman |  | 41.14 | Completed | No
WO-26-007630 | 10.3 | Crossroads | CR-S13-01 | Corrective maintenance | P3 within 10 days | 2026-07-15 | 2026-07-16 | 2026-07-20 | Underground crew |  | 1556.53 | Completed | No
WO-26-007631 | 1.5 | Crossroads | CR-S07-03 | Meter exchange | P3 within 10 days | 2026-07-15 | 2026-07-24 | 2026-07-24 | Meter technician |  | 124.62 | Completed | No
WO-26-007632 | 22.7 | Crossroads | CR-S15-01 | Pole replacement | P3 within 10 days | 2026-07-15 | 2026-07-16 | 2026-07-16 | Contract line | CT-02 | 1686.53 | Completed | No
WO-26-007633 | 18.6 | Crossroads | CR-S14-02 | Pole replacement | P3 within 10 days | 2026-07-15 | 2026-07-24 | 2026-07-24 | Contract line | CT-01 | 1594.72 | Completed | No
WO-26-007634 |  | Crossroads | CR-S03-02 | Pole replacement | P4 planned | 2026-07-15 | 2026-09-13 |  | Internal line |  |  | Scheduled | No
WO-26-007635 | 17 | Crossroads | CR-S30-03 | Pole replacement | P3 within 10 days | 2026-07-15 | 2026-07-25 | 2026-07-25 | Contract line | CT-02 | 2568.27 | Completed | No
WO-26-007636 | 22.6 | Crossroads | CR-S11-01 | Pole replacement | P3 within 10 days | 2026-07-15 | 2026-07-21 | 2026-07-21 | Internal line |  | 3220.81 | Completed | No
WO-26-007637 | 1.2 | Crossroads | CR-S04-01 | Service order - field | P2 same day | 2026-07-15 | 2026-07-16 | 2026-07-16 | Meter technician |  | 17.45 | Completed | No
WO-26-007638 | 1 | Crossroads | CR-S16-05 | Service order - field | P3 within 10 days | 2026-07-15 | 2026-07-25 | 2026-07-25 | Meter technician |  | 22.03 | Completed | No
WO-26-007639 | 1.5 | Crossroads | CR-S07-07 | Service order - field | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Meter technician |  | 35.01 | Completed | No
WO-26-007640 | 2 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Meter technician |  | 32.87 | Completed | No
WO-26-007641 | 0.7 | Crossroads | CR-S25-04 | Service order - field | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Meter technician |  | 16.22 | Completed | No
WO-26-007642 | 1.2 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-07-15 | 2026-07-16 | 2026-07-16 | Meter technician |  | 7.68 | Completed | No
WO-26-007643 | 4.7 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Internal line |  | 95.88 | Completed | No
WO-26-007644 | 2.1 | Crossroads | CR-S22-01 | Trouble - no power | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 49.52 | Completed | No
WO-26-007645 | 4.4 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 183.61 | Completed | No
WO-26-007646 | 4.1 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 317.7 | Completed | No
WO-26-007647 | 4.3 | Crossroads | CR-S30-03 | Trouble - no power | P1 emergency | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 343.43 | Completed | No
WO-26-007648 | 4.4 | Crossroads | CR-S25-01 | Trouble - partial or voltage | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 244.95 | Completed | No
WO-26-007649 | 4.3 | Crossroads | CR-S05-03 | Trouble - partial or voltage | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 144.21 | Completed | No
WO-26-007650 | 4.3 | Crossroads | CR-S12-01 | Trouble - partial or voltage | P3 within 10 days | 2026-07-15 | 2026-07-21 | 2026-07-21 | Troubleman |  | 221.86 | Completed | No
WO-26-007651 | 2.3 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P2 same day | 2026-07-15 | 2026-07-15 | 2026-07-15 | Troubleman |  | 192.31 | Completed | No
WO-26-007652 | 11.6 | Bayou | BY-S23-02 | Corrective maintenance | P3 within 10 days | 2026-07-16 | 2026-07-21 | 2026-07-21 | Underground crew |  | 835.23 | Completed | No
WO-26-007653 | 10.7 | Bayou | BY-S12-03 | Corrective maintenance | P3 within 10 days | 2026-07-16 | 2026-07-24 | 2026-07-24 | Internal line |  | 1887.7 | Completed | No
WO-26-007654 | 7.4 | Bayou | BY-S16-03 | Corrective maintenance | P3 within 10 days | 2026-07-16 | 2026-07-20 | 2026-07-22 | Internal line |  | 680.32 | Completed | No
WO-26-007655 | 1.3 | Bayou | BY-S16-05 | Meter exchange | P3 within 10 days | 2026-07-16 | 2026-07-24 | 2026-07-24 | Meter technician |  | 75.84 | Completed | No
WO-26-007656 | 0.8 | Bayou | BY-S07-02 | Meter exchange | P3 within 10 days | 2026-07-16 | 2026-07-18 | 2026-07-19 | Meter technician |  | 156.91 | Completed | No
WO-26-007657 |  | Bayou | BY-S29-03 | Meter exchange | P4 planned | 2026-07-16 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-007658 | 7.6 | Bayou | BY-S16-02 | New service - small | P4 planned | 2026-07-16 | 2026-08-15 | 2026-08-15 | Underground crew |  | 1301.15 | Completed | No
WO-26-007659 | 17.3 | Bayou | BY-S09-05 | Pole replacement | P4 planned | 2026-07-16 | 2026-08-21 | 2026-08-21 | Contract line | CT-04 | 2323.83 | Completed | No
WO-26-007660 | 7.4 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-07-16 | 2026-08-08 | 2026-08-08 | Underground crew |  | 26.46 | Completed | No
WO-26-007661 | 7 | Bayou | BY-S17-04 | Preventive maintenance | P4 planned | 2026-07-16 | 2026-07-23 | 2026-07-23 | Contract line | CT-03 | 421.81 | Completed | No
WO-26-007662 | 8 | Bayou | BY-S05-02 | Preventive maintenance | P4 planned | 2026-07-16 | 2026-08-11 | 2026-08-15 | Underground crew |  | 71.62 | Completed | No
WO-26-007663 | 1.7 | Bayou | BY-S19-01 | Service order - field | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Meter technician |  | 9.52 | Completed | No
WO-26-007664 | 1.4 | Bayou | BY-S06-01 | Service order - field | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Meter technician |  | 19.03 | Completed | No
WO-26-007665 | 1.2 | Bayou | BY-S05-03 | Service order - field | P3 within 10 days | 2026-07-16 | 2026-07-21 | 2026-07-29 | Meter technician |  | 14.83 | Completed | No
WO-26-007666 | 1.9 | Bayou | BY-S25-03 | Service order - field | P3 within 10 days | 2026-07-16 | 2026-07-17 | 2026-07-17 | Meter technician |  | 4.09 | Completed | No
WO-26-007667 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-16 | 2026-07-24 | 2026-07-24 | Contract line | CT-04 | 124.17 | Completed | No
WO-26-007668 | 8.5 | Bayou | BY-S23-05 | Transformer replacement | P1 emergency | 2026-07-16 | 2026-07-16 | 2026-07-16 | Contract line | CT-03 | 9517.52 | Completed | No
WO-26-007669 | 10.7 | Bayou | BY-S22-03 | Transformer replacement | P2 same day | 2026-07-16 | 2026-07-17 | 2026-07-17 | Internal line |  | 6397.04 | Completed | No
WO-26-007670 | 10.9 | Bayou | BY-S03-03 | Transformer replacement | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Internal line |  | 4444.83 | Completed | No
WO-26-007671 | 13.6 | Bayou | BY-S21-05 | Transformer replacement | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Internal line |  | 9001.08 | Completed | No
WO-26-007672 | 7.6 | Bayou | BY-S12-01 | Transformer replacement | P1 emergency | 2026-07-16 | 2026-07-16 | 2026-07-16 | Internal line |  | 7479.03 | Completed | No
WO-26-007673 | 2.6 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-07-16 | 2026-07-16 | 2026-07-16 | Internal line |  | 310.66 | Completed | No
WO-26-007674 | 2.4 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-07-16 | 2026-07-16 | 2026-07-16 | Troubleman |  | 197.6 | Completed | No
WO-26-007675 | 2.8 | Bayou | BY-S27-01 | Trouble - no power | P2 same day | 2026-07-16 | 2026-07-17 | 2026-07-17 | Troubleman |  | 232.16 | Completed | No
WO-26-007676 | 2.1 | Bayou | BY-S23-02 | Trouble - partial or voltage | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Troubleman |  | 26.77 | Completed | No
WO-26-007677 | 1.5 | Bayou | BY-S09-04 | Trouble - partial or voltage | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Troubleman |  | 238.99 | Completed | No
WO-26-007678 | 4.6 | Bayou | BY-S25-01 | Trouble - partial or voltage | P2 same day | 2026-07-16 | 2026-07-17 | 2026-07-17 | Troubleman |  | 197.85 | Completed | No
WO-26-007679 | 4.5 | Bayou | BY-S22-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-16 | 2026-07-24 | 2026-07-28 | Troubleman |  | 102.95 | Completed | No
WO-26-007680 | 4.7 | Crossroads | CR-S11-01 | Corrective maintenance | P3 within 10 days | 2026-07-16 | 2026-07-21 | 2026-07-21 | Contract line | CT-01 | 1182.36 | Completed | No
WO-26-007681 | 4.3 | Crossroads | CR-S26-02 | Corrective maintenance | P3 within 10 days | 2026-07-16 | 2026-07-21 | 2026-07-21 | Contract line | CT-02 | 1681.39 | Completed | No
WO-26-007682 | 11.6 | Crossroads | CR-S01-03 | Corrective maintenance | P3 within 10 days | 2026-07-16 | 2026-07-22 | 2026-07-23 | Internal line |  | 1094.08 | Completed | No
WO-26-007683 |  | Crossroads | CR-S20-05 | Corrective maintenance | P4 planned | 2026-07-16 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-007684 | 0.9 | Crossroads | CR-S15-03 | Meter exchange | P3 within 10 days | 2026-07-16 | 2026-07-26 | 2026-07-26 | Meter technician |  | 161.98 | Completed | No
WO-26-007685 | 1.4 | Crossroads | CR-S14-02 | Meter exchange | P3 within 10 days | 2026-07-16 | 2026-07-24 | 2026-07-24 | Meter technician |  | 92.78 | Completed | No
WO-26-007686 | 1 | Crossroads | CR-S15-02 | Meter exchange | P3 within 10 days | 2026-07-16 | 2026-07-21 | 2026-07-21 | Meter technician |  | 158.37 | Completed | No
WO-26-007687 |  | Crossroads | CR-S14-03 | Meter exchange | P4 planned | 2026-07-16 | 2026-09-12 |  | Meter technician |  |  | Scheduled | No
WO-26-007688 | 7.6 | Crossroads | CR-S14-02 | Preventive maintenance | P4 planned | 2026-07-16 | 2026-08-03 | 2026-08-03 | Internal line |  | 325.87 | Completed | No
WO-26-007689 | 1.6 | Crossroads | CR-S01-01 | Service order - field | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Meter technician |  | 33.07 | Completed | No
WO-26-007690 | 1.5 | Crossroads | CR-S07-05 | Service order - field | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Meter technician |  | 35.95 | Completed | No
WO-26-007691 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-16 | 2026-07-20 | 2026-07-28 | Contract line | CT-02 | 389.65 | Completed | No
WO-26-007692 | 3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-16 | 2026-07-20 | 2026-07-22 | Internal line |  | 328.1 | Completed | No
WO-26-007693 | 1.4 | Crossroads |  | Streetlight | P4 planned | 2026-07-16 | 2026-08-23 | 2026-08-24 | Internal line |  | 131.66 | Completed | No
WO-26-007694 | 12.9 | Crossroads | CR-S12-02 | Transformer replacement | P1 emergency | 2026-07-16 | 2026-07-16 | 2026-07-16 | Internal line |  | 4217.08 | Completed | No
WO-26-007695 | 12.2 | Crossroads | CR-S21-01 | Transformer replacement | P3 within 10 days | 2026-07-16 | 2026-07-23 | 2026-07-23 | Internal line |  | 5811.67 | Completed | No
WO-26-007696 | 3.4 | Crossroads | CR-S27-04 | Trouble - partial or voltage | P2 same day | 2026-07-16 | 2026-07-16 | 2026-07-16 | Troubleman |  | 220.98 | Completed | No
WO-26-007697 | 11.3 | Bayou | BY-S29-02 | Corrective maintenance | P3 within 10 days | 2026-07-17 | 2026-07-18 | 2026-07-19 | Underground crew |  | 1737.47 | Completed | No
WO-26-007698 | 10.3 | Bayou | BY-S19-04 | Corrective maintenance | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Underground crew |  | 2378.47 | Completed | No
WO-26-007699 | 9.6 | Bayou | BY-S15-02 | Corrective maintenance | P4 planned | 2026-07-17 | 2026-08-01 | 2026-08-01 | Internal line |  | 1154.2 | Completed | No
WO-26-007700 | 4.1 | Bayou | BY-S27-02 | Corrective maintenance | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Contract line | CT-03 | 367.91 | Completed | No
WO-26-007701 | 0.8 | Bayou | BY-S05-02 | Meter exchange | P3 within 10 days | 2026-07-17 | 2026-07-25 | 2026-07-27 | Meter technician |  | 79.3 | Completed | No
WO-26-007702 | 1.1 | Bayou | BY-S23-03 | Meter exchange | P4 planned | 2026-07-17 | 2026-07-28 | 2026-07-28 | Meter technician |  | 138.48 | Completed | No
WO-26-007703 |  | Bayou | BY-S25-05 | Pole replacement | P3 within 10 days | 2026-07-17 | 2026-07-27 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-007704 | 2.1 | Bayou | BY-S28-01 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-08-22 | 2026-08-24 | Internal line |  | 14.71 | Completed | No
WO-26-007705 | 6.9 | Bayou | BY-S29-02 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-08-14 | 2026-08-16 | Internal line |  | 114.62 | Completed | No
WO-26-007706 | 7.3 | Bayou | BY-S19-01 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-07-26 | 2026-08-03 | Internal line |  | 161.95 | Completed | No
WO-26-007707 | 0.9 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Meter technician |  | 1.26 | Completed | No
WO-26-007708 | 7.7 | Bayou | BY-S03-01 | Transformer replacement | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Internal line |  | 10786.26 | Completed | No
WO-26-007709 | 6.3 | Bayou | BY-S07-04 | Transformer replacement | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Contract line | CT-04 | 8417.15 | Completed | No
WO-26-007710 | 10.9 | Bayou | BY-S22-02 | Transformer replacement | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Internal line |  | 11483.95 | Completed | No
WO-26-007711 | 9.5 | Bayou | BY-S26-03 | Transformer replacement | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Internal line |  | 6379.89 | Completed | No
WO-26-007712 | 2.2 | Bayou | BY-S18-03 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 3.07 | Completed | No
WO-26-007713 | 3.4 | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 31.05 | Completed | No
WO-26-007714 | 3.1 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 21.98 | Completed | No
WO-26-007715 | 2.8 | Bayou | BY-S16-05 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 340.97 | Completed | No
WO-26-007716 | 3 | Bayou | BY-S26-02 | Trouble - no power | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Troubleman |  | 208.75 | Completed | No
WO-26-007717 | 3.3 | Bayou | BY-S10-04 | Trouble - partial or voltage | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Internal line |  | 36.82 | Completed | No
WO-26-007718 | 3.9 | Bayou | BY-S27-06 | Trouble - partial or voltage | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Troubleman |  | 151.24 | Completed | No
WO-26-007719 | 4.6 | Bayou | BY-S15-06 | Trouble - partial or voltage | P2 same day | 2026-07-17 | 2026-07-18 | 2026-07-18 | Internal line |  | 241.56 | Completed | No
WO-26-007720 | 4.1 | Crossroads | CR-S16-02 | Corrective maintenance | P3 within 10 days | 2026-07-17 | 2026-07-27 | 2026-07-31 | Internal line |  | 597.34 | Completed | No
WO-26-007721 | 7.3 | Crossroads | CR-S04-03 | Corrective maintenance | P3 within 10 days | 2026-07-17 | 2026-07-20 | 2026-07-20 | Contract line | CT-01 | 1095.28 | Completed | No
WO-26-007722 | 8.3 | Crossroads | CR-S08-03 | Corrective maintenance | P3 within 10 days | 2026-07-17 | 2026-07-24 | 2026-07-25 | Underground crew |  | 2190.43 | Completed | No
WO-26-007723 | 4.1 | Crossroads | CR-S16-03 | Corrective maintenance | P3 within 10 days | 2026-07-17 | 2026-07-19 | 2026-07-20 | Contract line | CT-02 | 2164.48 | Completed | No
WO-26-007724 | 0.8 | Crossroads | CR-S23-02 | Meter exchange | P3 within 10 days | 2026-07-17 | 2026-07-18 | 2026-07-18 | Meter technician |  | 83.79 | Completed | No
WO-26-007725 | 1.4 | Crossroads | CR-S27-02 | Meter exchange | P3 within 10 days | 2026-07-17 | 2026-07-24 | 2026-07-24 | Meter technician |  | 160.94 | Completed | No
WO-26-007726 | 11.9 | Crossroads | CR-S10-01 | Pole replacement | P3 within 10 days | 2026-07-17 | 2026-07-20 | 2026-07-24 | Internal line |  | 2934.35 | Completed | No
WO-26-007727 | 7.4 | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-08-28 | 2026-08-28 | Internal line |  | 97.7 | Completed | No
WO-26-007728 |  | Crossroads | CR-S26-04 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-09-02 |  | Internal line |  |  | Scheduled | No
WO-26-007729 |  | Crossroads | CR-S06-02 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-09-11 |  | Internal line |  |  | Scheduled | No
WO-26-007730 |  | Crossroads | CR-S24-03 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-09-12 |  | Internal line |  |  | Scheduled | No
WO-26-007731 |  | Crossroads | CR-S03-03 | Preventive maintenance | P4 planned | 2026-07-17 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-007732 | 1.2 | Crossroads | CR-S19-04 | Service order - field | P3 within 10 days | 2026-07-17 | 2026-07-22 | 2026-07-23 | Meter technician |  | 37.29 | Completed | No
WO-26-007733 | 1.9 | Crossroads | CR-S06-01 | Service order - field | P3 within 10 days | 2026-07-17 | 2026-07-26 | 2026-07-26 | Meter technician |  | 18.37 | Completed | No
WO-26-007734 | 1.7 | Crossroads | CR-S16-05 | Service order - field | P3 within 10 days | 2026-07-17 | 2026-07-21 | 2026-07-21 | Meter technician |  | 21.5 | Completed | No
WO-26-007735 | 1.1 | Crossroads | CR-S05-04 | Service order - field | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Meter technician |  | 28.09 | Completed | No
WO-26-007736 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-17 | 2026-07-18 | 2026-07-18 | Internal line |  | 417.16 | Completed | No
WO-26-007737 | 2.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-17 | 2026-07-19 | 2026-07-21 | Internal line |  | 224.53 | Completed | No
WO-26-007738 | 10 | Crossroads | CR-S14-02 | Transformer replacement | P3 within 10 days | 2026-07-17 | 2026-07-27 | 2026-07-27 | Internal line |  | 7539.48 | Completed | No
WO-26-007739 | 6 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Internal line |  | 237 | Completed | No
WO-26-007740 | 3.9 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Internal line |  | 293.68 | Completed | No
WO-26-007741 | 2.8 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Internal line |  | 6.56 | Completed | No
WO-26-007742 | 5 | Crossroads | CR-S16-06 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 57.03 | Completed | No
WO-26-007743 | 2.4 | Crossroads | CR-S23-04 | Trouble - no power | P1 emergency | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 342.35 | Completed | No
WO-26-007744 | 3.4 | Crossroads | CR-S09-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-17 | 2026-07-24 | 2026-07-24 | Internal line |  | 130.46 | Completed | No
WO-26-007745 | 4.5 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 114.54 | Completed | No
WO-26-007746 | 3.6 | Crossroads | CR-S13-04 | Trouble - partial or voltage | P2 same day | 2026-07-17 | 2026-07-17 | 2026-07-17 | Troubleman |  | 147.69 | Completed | No
WO-26-007747 | 6 | Bayou | BY-S16-04 | Corrective maintenance | P2 same day | 2026-07-18 | 2026-07-18 | 2026-07-18 | Contract line | CT-03 | 286.28 | Completed | No
WO-26-007748 |  | Bayou | BY-S07-02 | Service order - field | P2 same day | 2026-07-18 | 2026-07-19 |  | Meter technician |  |  | Cancelled | No
WO-26-007749 | 1.9 | Bayou | BY-S02-01 | Service order - field | P2 same day | 2026-07-18 | 2026-07-19 | 2026-07-19 | Meter technician |  | 11.56 | Completed | No
WO-26-007750 | 0.8 | Bayou | BY-S05-01 | Service order - field | P2 same day | 2026-07-18 | 2026-07-18 | 2026-07-18 | Meter technician |  | 22.19 | Completed | No
WO-26-007751 | 9.7 | Bayou | BY-S17-01 | Transformer replacement | P2 same day | 2026-07-18 | 2026-07-19 | 2026-07-19 | Contract line | CT-03 | 7539.27 | Completed | No
WO-26-007752 | 12.8 | Bayou | BY-S06-03 | Transformer replacement | P2 same day | 2026-07-18 | 2026-07-19 | 2026-07-19 | Internal line |  | 4374.94 | Completed | No
WO-26-007753 | 5.6 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 264.27 | Completed | No
WO-26-007754 | 2.8 | Bayou | BY-S23-04 | Trouble - no power | P1 emergency | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 69.35 | Completed | No
WO-26-007755 | 5 | Bayou | BY-S15-01 | Trouble - no power | P1 emergency | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 73.37 | Completed | No
WO-26-007756 | 4.9 | Bayou | BY-S17-04 | Trouble - no power | P2 same day | 2026-07-18 | 2026-07-19 | 2026-07-19 | Troubleman |  | 133.83 | Completed | No
WO-26-007757 | 2.9 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 285.81 | Completed | No
WO-26-007758 | 5.3 | Bayou | BY-S28-01 | Trouble - no power | P2 same day | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 158.9 | Completed | No
WO-26-007759 | 5.2 | Crossroads | CR-S02-02 | Trouble - no power | P2 same day | 2026-07-18 | 2026-07-19 | 2026-07-19 | Troubleman |  | 256.48 | Completed | No
WO-26-007760 | 4.7 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 322.69 | Completed | No
WO-26-007761 | 4 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-07-18 | 2026-07-18 | 2026-07-18 | Troubleman |  | 306.91 | Completed | No
WO-26-007762 | 3.4 | Crossroads | CR-S22-02 | Trouble - partial or voltage | P2 same day | 2026-07-18 | 2026-07-19 | 2026-07-19 | Troubleman |  | 230.79 | Completed | No
WO-26-007763 | 10.4 | Bayou | BY-S09-04 | Corrective maintenance | P2 same day | 2026-07-19 | 2026-07-20 | 2026-07-20 | Contract line | CT-03 | 543.16 | Completed | No
WO-26-007764 |  | Bayou | BY-S24-04 | Service order - field | P2 same day | 2026-07-19 | 2026-07-19 |  | Meter technician |  |  | Cancelled | No
WO-26-007765 |  | Bayou | BY-S16-01 | Transformer replacement | P2 same day | 2026-07-19 | 2026-07-20 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-007766 | 9 | Bayou | BY-S19-02 | Transformer replacement | P2 same day | 2026-07-19 | 2026-07-19 | 2026-07-19 | Contract line | CT-04 | 5918.57 | Completed | No
WO-26-007767 | 2 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 128.96 | Completed | No
WO-26-007768 | 2.8 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 18.59 | Completed | No
WO-26-007769 | 4.3 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 104.18 | Completed | No
WO-26-007770 | 4.4 | Bayou | BY-S05-03 | Trouble - no power | P1 emergency | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 212.92 | Completed | No
WO-26-007771 | 3.2 | Bayou | BY-S03-02 | Trouble - partial or voltage | P2 same day | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 166.01 | Completed | No
WO-26-007772 | 5.5 | Crossroads | CR-S04-03 | Corrective maintenance | P2 same day | 2026-07-19 | 2026-07-20 | 2026-07-20 | Underground crew |  | 668.69 | Completed | No
WO-26-007773 | 2 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-07-19 | 2026-07-19 | 2026-07-19 | Meter technician |  | 19.22 | Completed | No
WO-26-007774 | 0.8 | Crossroads | CR-S17-03 | Service order - field | P2 same day | 2026-07-19 | 2026-07-20 | 2026-07-20 | Meter technician |  | 4.09 | Completed | No
WO-26-007775 | 3.4 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 193.83 | Completed | No
WO-26-007776 | 3.6 | Crossroads | CR-S07-05 | Trouble - no power | P1 emergency | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 4.15 | Completed | No
WO-26-007777 | 2 | Crossroads | CR-S23-05 | Trouble - partial or voltage | P2 same day | 2026-07-19 | 2026-07-19 | 2026-07-19 | Troubleman |  | 67.87 | Completed | No
WO-26-007778 | 4.8 | Bayou | BY-S12-01 | Corrective maintenance | P4 planned | 2026-07-20 | 2026-08-14 | 2026-08-18 | Contract line | CT-04 | 470.63 | Completed | No
WO-26-007779 | 5.8 | Bayou | BY-S27-05 | Corrective maintenance | P4 planned | 2026-07-20 | 2026-07-29 | 2026-08-02 | Underground crew |  | 1075.41 | Completed | No
WO-26-007780 | 10.7 | Bayou | BY-S28-03 | Corrective maintenance | P3 within 10 days | 2026-07-20 | 2026-07-22 | 2026-07-24 | Internal line |  | 1753.75 | Completed | No
WO-26-007781 | 11.1 | Bayou | BY-S29-04 | Corrective maintenance | P2 same day | 2026-07-20 | 2026-07-20 | 2026-07-20 | Underground crew |  | 1778.44 | Completed | No
WO-26-007782 | 1.1 | Bayou | BY-S10-01 | Meter exchange | P3 within 10 days | 2026-07-20 | 2026-07-25 | 2026-07-25 | Meter technician |  | 75.42 | Completed | No
WO-26-007783 | 23.6 | Bayou | BY-S14-01 | Pole replacement | P2 same day | 2026-07-20 | 2026-07-20 | 2026-07-20 | Contract line | CT-04 | 1869.53 | Completed | No
WO-26-007784 |  | Bayou | BY-S25-01 | Preventive maintenance | P4 planned | 2026-07-20 | 2026-09-03 |  | Underground crew |  |  | Scheduled | No
WO-26-007785 | 7.6 | Bayou | BY-S12-04 | Preventive maintenance | P4 planned | 2026-07-20 | 2026-08-08 | 2026-08-08 | Internal line |  | 147.63 | Completed | No
WO-26-007786 | 1.9 | Bayou | BY-S06-01 | Service order - field | P3 within 10 days | 2026-07-20 | 2026-07-23 | 2026-07-23 | Meter technician |  | 31.52 | Completed | No
WO-26-007787 | 1.2 | Bayou | BY-S05-02 | Service order - field | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Meter technician |  | 12.57 | Completed | No
WO-26-007788 | 0.8 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Meter technician |  | 18.93 | Completed | No
WO-26-007789 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-20 | 2026-07-29 | 2026-07-30 | Contract line | CT-03 | 329.18 | Completed | No
WO-26-007790 | 1 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-20 | 2026-07-29 | 2026-07-29 | Internal line |  | 298.2 | Completed | No
WO-26-007791 | 6.4 | Bayou | BY-S29-05 | Transformer replacement | P2 same day | 2026-07-20 | 2026-07-20 | 2026-07-20 | Internal line |  | 7372.97 | Completed | No
WO-26-007792 | 3.4 | Bayou | BY-S19-04 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 333.53 | Completed | No
WO-26-007793 | 3.8 | Bayou | BY-S16-04 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 303.17 | Completed | No
WO-26-007794 | 3.7 | Bayou | BY-S02-02 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 9.36 | Completed | No
WO-26-007795 | 4.8 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 306.22 | Completed | No
WO-26-007796 | 4.6 | Bayou | BY-S24-03 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 22.41 | Completed | No
WO-26-007797 | 2.1 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 238.04 | Completed | No
WO-26-007798 | 4.5 | Bayou | BY-S30-01 | Trouble - partial or voltage | P2 same day | 2026-07-20 | 2026-07-20 | 2026-07-20 | Internal line |  | 20.55 | Completed | No
WO-26-007799 |  | Crossroads | CR-S31-02 | Corrective maintenance | P3 within 10 days | 2026-07-20 | 2026-07-28 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-007800 |  | Crossroads | CR-S04-03 | Corrective maintenance | P4 planned | 2026-07-20 | 2026-09-16 |  | Internal line |  |  | Scheduled | No
WO-26-007801 | 4 | Crossroads | CR-S03-02 | Corrective maintenance | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Contract line | CT-01 | 843.15 | Completed | No
WO-26-007802 | 6.1 | Crossroads | CR-S04-02 | Corrective maintenance | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Internal line |  | 1478.61 | Completed | No
WO-26-007803 | 5.9 | Crossroads | CR-S23-04 | Corrective maintenance | P3 within 10 days | 2026-07-20 | 2026-07-21 | 2026-07-22 | Contract line | CT-02 | 1093.88 | Completed | No
WO-26-007804 | 1.2 | Crossroads | CR-S06-01 | Meter exchange | P3 within 10 days | 2026-07-20 | 2026-07-21 | 2026-07-21 | Meter technician |  | 104.44 | Completed | No
WO-26-007805 | 1.1 | Crossroads | CR-S19-02 | Meter exchange | P3 within 10 days | 2026-07-20 | 2026-07-22 | 2026-07-26 | Meter technician |  | 172.48 | Completed | No
WO-26-007806 |  | Crossroads | CR-S23-04 | Preventive maintenance | P4 planned | 2026-07-20 | 2026-09-01 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-007807 |  | Crossroads | CR-S12-01 | Preventive maintenance | P4 planned | 2026-07-20 | 2026-08-11 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-007808 | 0.7 | Crossroads | CR-S32-03 | Service order - field | P3 within 10 days | 2026-07-20 | 2026-07-30 | 2026-08-07 | Meter technician |  | 11.4 | Completed | No
WO-26-007809 | 1.5 | Crossroads | CR-S10-02 | Service order - field | P3 within 10 days | 2026-07-20 | 2026-07-26 | 2026-07-26 | Meter technician |  | 24.85 | Completed | No
WO-26-007810 | 2 | Crossroads | CR-S10-01 | Service order - field | P3 within 10 days | 2026-07-20 | 2026-07-22 | 2026-07-23 | Meter technician |  | 0.7 | Completed | No
WO-26-007811 | 0.7 | Crossroads | CR-S08-06 | Service order - field | P3 within 10 days | 2026-07-20 | 2026-07-29 | 2026-08-02 | Meter technician |  | 20.07 | Completed | No
WO-26-007812 | 1.4 | Crossroads | CR-S27-02 | Service order - field | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Meter technician |  | 0.94 | Completed | No
WO-26-007813 | 1.6 | Crossroads | CR-S14-04 | Service order - field | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Meter technician |  | 7.57 | Completed | No
WO-26-007814 | 1 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-20 | 2026-07-30 | 2026-07-31 | Contract line | CT-01 | 68.98 | Completed | No
WO-26-007815 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-20 | 2026-07-25 | 2026-07-25 | Contract line | CT-01 | 393.36 | Completed | No
WO-26-007816 | 7.2 | Crossroads | CR-S04-01 | Transformer replacement | P2 same day | 2026-07-20 | 2026-07-21 | 2026-07-21 | Contract line | CT-02 | 9383.12 | Completed | No
WO-26-007817 | 3.9 | Crossroads | CR-S12-03 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Internal line |  | 256.07 | Completed | No
WO-26-007818 | 3 | Crossroads | CR-S01-04 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Internal line |  | 105.53 | Completed | No
WO-26-007819 | 5.2 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 331.28 | Completed | No
WO-26-007820 | 5.4 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-07-20 | 2026-07-20 | 2026-07-20 | Troubleman |  | 286.9 | Completed | No
WO-26-007821 | 4.9 | Crossroads | CR-S13-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-20 | 2026-07-30 | 2026-07-31 | Troubleman |  | 230.53 | Completed | No
WO-26-007822 | 1.8 | Crossroads | CR-S24-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-20 | 2026-07-21 | 2026-07-21 | Troubleman |  | 84.62 | Completed | No
WO-26-007823 | 7.1 | Bayou | BY-S07-03 | Corrective maintenance | P4 planned | 2026-07-21 | 2026-08-07 | 2026-08-07 | Internal line |  | 995.23 | Completed | No
WO-26-007824 | 0.7 | Bayou | BY-S23-01 | Meter exchange | P4 planned | 2026-07-21 | 2026-08-13 | 2026-08-13 | Meter technician |  | 159.78 | Completed | No
WO-26-007825 | 0.8 | Bayou | BY-S26-02 | Meter exchange | P4 planned | 2026-07-21 | 2026-08-26 | 2026-08-28 | Meter technician |  | 142.08 | Completed | No
WO-26-007826 | 0.8 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-07-21 | 2026-07-31 | 2026-08-01 | Meter technician |  | 148.81 | Completed | No
WO-26-007827 |  | Bayou | BY-S05-02 | New service - small | P4 planned | 2026-07-21 | 2026-09-17 |  | Underground crew |  |  | Open - awaiting material | No
WO-26-007828 | 6.7 | Bayou | BY-S04-03 | Preventive maintenance | P4 planned | 2026-07-21 | 2026-08-02 | 2026-08-02 | Underground crew |  | 530.12 | Completed | No
WO-26-007829 | 1.8 | Bayou | BY-S21-03 | Service order - field | P2 same day | 2026-07-21 | 2026-07-22 | 2026-07-22 | Meter technician |  | 1.08 | Completed | No
WO-26-007830 | 1.8 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-07-21 | 2026-07-24 | 2026-07-25 | Meter technician |  | 35.79 | Completed | No
WO-26-007831 | 1.7 | Bayou | BY-S24-03 | Service order - field | P3 within 10 days | 2026-07-21 | 2026-07-23 | 2026-07-23 | Meter technician |  | 33.27 | Completed | No
WO-26-007832 | 1.6 | Bayou | BY-S24-04 | Service order - field | P3 within 10 days | 2026-07-21 | 2026-07-29 | 2026-07-30 | Meter technician |  | 10.97 | Completed | No
WO-26-007833 | 1.3 | Bayou | BY-S19-03 | Service order - field | P3 within 10 days | 2026-07-21 | 2026-07-29 | 2026-07-30 | Meter technician |  | 11.67 | Completed | No
WO-26-007834 | 2.5 | Bayou |  | Streetlight | P4 planned | 2026-07-21 | 2026-08-22 | 2026-08-23 | Contract line | CT-04 | 278.9 | Completed | No
WO-26-007835 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-21 | 2026-07-25 | 2026-07-26 | Contract line | CT-04 | 409.75 | Completed | No
WO-26-007836 | 2.1 | Bayou |  | Streetlight | P4 planned | 2026-07-21 | 2026-08-09 | 2026-08-10 | Contract line | CT-04 | 179.5 | Completed | No
WO-26-007837 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-21 | 2026-07-22 | 2026-07-30 | Internal line |  | 202.91 | Completed | No
WO-26-007838 | 5 | Bayou | BY-S30-01 | Trouble - no power | P2 same day | 2026-07-21 | 2026-07-22 | 2026-07-22 | Troubleman |  | 57.81 | Completed | No
WO-26-007839 | 5.7 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-07-21 | 2026-07-21 | 2026-07-21 | Troubleman |  | 286.71 | Completed | No
WO-26-007840 | 11.7 | Crossroads | CR-S30-06 | Corrective maintenance | P3 within 10 days | 2026-07-21 | 2026-07-28 | 2026-07-30 | Internal line |  | 1649.03 | Completed | No
WO-26-007841 | 7.3 | Crossroads | CR-S26-06 | Corrective maintenance | P3 within 10 days | 2026-07-21 | 2026-07-29 | 2026-07-29 | Underground crew |  | 2041.56 | Completed | No
WO-26-007842 | 10.1 | Crossroads | CR-S08-05 | Corrective maintenance | P4 planned | 2026-07-21 | 2026-08-30 | 2026-08-30 | Internal line |  | 1247.66 | Completed | No
WO-26-007843 | 9.7 | Crossroads | CR-S19-04 | Corrective maintenance | P2 same day | 2026-07-21 | 2026-07-21 | 2026-07-21 | Contract line | CT-01 | 2203.63 | Completed | No
WO-26-007844 | 5.2 | Crossroads | CR-S25-05 | Corrective maintenance | P4 planned | 2026-07-21 | 2026-08-17 | 2026-08-17 | Underground crew |  | 2204.58 | Completed | No
WO-26-007845 | 0.6 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-07-21 | 2026-07-26 | 2026-07-26 | Meter technician |  | 110.17 | Completed | No
WO-26-007846 | 1.5 | Crossroads | CR-S08-02 | Meter exchange | P3 within 10 days | 2026-07-21 | 2026-07-27 | 2026-07-27 | Meter technician |  | 72.42 | Completed | No
WO-26-007847 | 4.1 | Crossroads | CR-S24-01 | New service - small | P3 within 10 days | 2026-07-21 | 2026-07-25 | 2026-07-26 | Contract line | CT-02 | 2923.5 | Completed | No
WO-26-007848 | 1.2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-21 | 2026-07-28 | 2026-07-28 | Internal line |  | 333.64 | Completed | No
WO-26-007849 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-21 | 2026-07-26 | 2026-07-26 | Contract line | CT-01 | 117.98 | Completed | No
WO-26-007850 |  | Crossroads |  | Streetlight | P4 planned | 2026-07-21 | 2026-09-03 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-007851 |  | Crossroads | CR-S21-01 | Transformer replacement | P2 same day | 2026-07-21 | 2026-07-21 |  | Internal line |  |  | Open - awaiting material | No
WO-26-007852 |  | Crossroads | CR-S23-01 | Transformer replacement | P1 emergency | 2026-07-21 | 2026-07-21 |  | Contract line | CT-01 |  | Open - awaiting material | No
WO-26-007853 | 3.1 | Bayou | BY-S10-05 | Corrective maintenance | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Contract line | CT-03 | 1841.1 | Completed | No
WO-26-007854 | 7.1 | Bayou | BY-S16-05 | Corrective maintenance | P3 within 10 days | 2026-07-22 | 2026-07-26 | 2026-07-26 | Internal line |  | 1118.63 | Completed | No
WO-26-007855 | 7.9 | Bayou | BY-S29-05 | Corrective maintenance | P3 within 10 days | 2026-07-22 | 2026-07-26 | 2026-07-26 | Internal line |  | 1261.72 | Completed | No
WO-26-007856 | 10.3 | Bayou | BY-S09-02 | Corrective maintenance | P3 within 10 days | 2026-07-22 | 2026-07-25 | 2026-07-25 | Underground crew |  | 1032.32 | Completed | No
WO-26-007857 | 0.9 | Bayou | BY-S07-02 | Meter exchange | P3 within 10 days | 2026-07-22 | 2026-08-01 | 2026-08-03 | Meter technician |  | 100.03 | Completed | No
WO-26-007858 |  | Bayou | BY-S25-01 | Meter exchange | P3 within 10 days | 2026-07-22 | 2026-07-26 |  | Meter technician |  |  | Cancelled | No
WO-26-007859 | 1.1 | Bayou | BY-S23-05 | Meter exchange | P3 within 10 days | 2026-07-22 | 2026-08-01 | 2026-08-09 | Meter technician |  | 92.11 | Completed | No
WO-26-007860 | 1.2 | Bayou | BY-S21-01 | Meter exchange | P4 planned | 2026-07-22 | 2026-08-26 | 2026-08-26 | Meter technician |  | 165.6 | Completed | No
WO-26-007861 |  | Bayou | BY-S10-05 | Pole replacement | P3 within 10 days | 2026-07-22 | 2026-07-28 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-007862 |  | Bayou | BY-S02-01 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-007863 | 2.1 | Bayou | BY-S04-01 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-08-19 | 2026-08-21 | Underground crew |  | 410.9 | Completed | No
WO-26-007864 | 3.3 | Bayou | BY-S25-01 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-08-01 | 2026-08-01 | Internal line |  | 593.47 | Completed | No
WO-26-007865 | 5.1 | Bayou | BY-S30-01 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-08-14 | 2026-08-14 | Underground crew |  | 107.49 | Completed | No
WO-26-007866 |  | Bayou | BY-S13-01 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-08-17 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-007867 | 0.5 | Bayou | BY-S15-06 | Service order - field | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Meter technician |  | 30.02 | Completed | No
WO-26-007868 | 0.5 | Bayou | BY-S24-02 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-07-28 | 2026-07-28 | Meter technician |  | 13.86 | Completed | No
WO-26-007869 | 0.6 | Bayou | BY-S09-04 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-07-24 | 2026-07-26 | Meter technician |  | 27.21 | Completed | No
WO-26-007870 | 0.7 | Bayou | BY-S15-03 | Service order - field | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Meter technician |  | 18.91 | Completed | No
WO-26-007871 | 1.4 | Bayou | BY-S03-01 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-08-01 | 2026-08-02 | Meter technician |  | 3.11 | Completed | No
WO-26-007872 | 0.9 | Bayou | BY-S21-01 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-07-30 | 2026-07-30 | Meter technician |  | 25.25 | Completed | No
WO-26-007873 | 0.7 | Bayou | BY-S29-02 | Service order - field | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Meter technician |  | 33.87 | Completed | No
WO-26-007874 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-22 | 2026-07-27 | 2026-07-27 | Contract line | CT-03 | 119.89 | Completed | No
WO-26-007875 | 8.9 | Bayou | BY-S18-05 | Transformer replacement | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Internal line |  | 2837.81 | Completed | No
WO-26-007876 |  | Bayou | BY-S11-01 | Transformer replacement | P1 emergency | 2026-07-22 | 2026-07-22 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-007877 | 9.4 | Bayou | BY-S18-07 | Transformer replacement | P3 within 10 days | 2026-07-22 | 2026-07-29 | 2026-07-29 | Internal line |  | 2810.4 | Completed | No
WO-26-007878 | 12.4 | Bayou | BY-S07-02 | Transformer replacement | P2 same day | 2026-07-22 | 2026-07-22 | 2026-07-22 | Contract line | CT-03 | 7612.32 | Completed | No
WO-26-007879 | 5.3 | Bayou | BY-S21-04 | Trouble - no power | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Troubleman |  | 82.08 | Completed | No
WO-26-007880 | 3.7 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-07-22 | 2026-07-22 | 2026-07-22 | Internal line |  | 20.82 | Completed | No
WO-26-007881 | 4.2 | Bayou | BY-S01-02 | Trouble - no power | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Troubleman |  | 335.3 | Completed | No
WO-26-007882 | 2.3 | Bayou | BY-S15-01 | Trouble - no power | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Troubleman |  | 14.06 | Completed | No
WO-26-007883 | 5.9 | Bayou | BY-S25-03 | Trouble - no power | P1 emergency | 2026-07-22 | 2026-07-22 | 2026-07-22 | Troubleman |  | 193.02 | Completed | No
WO-26-007884 | 2.5 | Bayou | BY-S09-02 | Trouble - no power | P2 same day | 2026-07-22 | 2026-07-23 | 2026-07-23 | Troubleman |  | 255.56 | Completed | No
WO-26-007885 | 5.7 | Crossroads | CR-S27-03 | Corrective maintenance | P3 within 10 days | 2026-07-22 | 2026-07-31 | 2026-07-31 | Internal line |  | 817.95 | Completed | No
WO-26-007886 | 4.4 | Crossroads | CR-S12-01 | Corrective maintenance | P3 within 10 days | 2026-07-22 | 2026-07-30 | 2026-07-30 | Internal line |  | 1267.59 | Completed | No
WO-26-007887 | 0.8 | Crossroads | CR-S10-02 | Meter exchange | P4 planned | 2026-07-22 | 2026-08-27 | 2026-08-27 | Meter technician |  | 159.05 | Completed | No
WO-26-007888 | 0.8 | Crossroads | CR-S16-04 | Meter exchange | P3 within 10 days | 2026-07-22 | 2026-07-27 | 2026-07-28 | Meter technician |  | 92.47 | Completed | No
WO-26-007889 |  | Crossroads | CR-S25-02 | Meter exchange | P4 planned | 2026-07-22 | 2026-09-07 |  | Meter technician |  |  | Scheduled | No
WO-26-007890 | 1.4 | Crossroads | CR-S17-03 | Meter exchange | P3 within 10 days | 2026-07-22 | 2026-07-23 | 2026-07-31 | Meter technician |  | 109.29 | Completed | No
WO-26-007891 | 15.3 | Crossroads | CR-S17-03 | New service - small | P4 planned | 2026-07-22 | 2026-08-16 | 2026-08-16 | Contract line | CT-01 | 2770.06 | Completed | No
WO-26-007892 | 11.2 | Crossroads | CR-S27-03 | New service - small | P3 within 10 days | 2026-07-22 | 2026-07-27 | 2026-07-28 | Internal line |  | 1070.57 | Completed | No
WO-26-007893 | 22.1 | Crossroads | CR-S05-02 | Pole replacement | P3 within 10 days | 2026-07-22 | 2026-07-29 | 2026-07-29 | Internal line |  | 2175.18 | Completed | No
WO-26-007894 |  | Crossroads | CR-S08-06 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-09-01 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-007895 | 2.5 | Crossroads | CR-S08-02 | Preventive maintenance | P4 planned | 2026-07-22 | 2026-08-01 | 2026-08-03 | Underground crew |  | 224.42 | Completed | No
WO-26-007896 | 1.8 | Crossroads | CR-S07-02 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-07-30 | 2026-07-30 | Meter technician |  | 27.46 | Completed | No
WO-26-007897 | 1.7 | Crossroads | CR-S15-01 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-07-29 | 2026-08-02 | Meter technician |  | 8.58 | Completed | No
WO-26-007898 |  | Crossroads | CR-S11-02 | Service order - field | P3 within 10 days | 2026-07-22 | 2026-07-28 |  | Meter technician |  |  | Cancelled | No
WO-26-007899 | 2.3 | Crossroads |  | Streetlight | P4 planned | 2026-07-22 | 2026-08-14 | 2026-08-15 | Internal line |  | 449.46 | Completed | No
WO-26-007900 | 8.3 | Crossroads | CR-S07-02 | Transformer replacement | P1 emergency | 2026-07-22 | 2026-07-22 | 2026-07-22 | Contract line | CT-01 | 5188.77 | Completed | No
WO-26-007901 |  | Crossroads | CR-S20-02 | Transformer replacement | P2 same day | 2026-07-22 | 2026-07-22 |  | Internal line |  |  | Open - awaiting material | No
WO-26-007902 | 4 | Crossroads | CR-S27-04 | Trouble - no power | P2 same day | 2026-07-22 | 2026-07-22 | 2026-07-22 | Troubleman |  | 12.65 | Completed | No
WO-26-007903 | 3.3 | Crossroads | CR-S04-03 | Trouble - no power | P2 same day | 2026-07-22 | 2026-07-22 | 2026-07-22 | Troubleman |  | 216.43 | Completed | No
WO-26-007904 | 4.7 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-07-22 | 2026-07-22 | 2026-07-22 | Troubleman |  | 237.03 | Completed | No
WO-26-007905 | 1.8 | Crossroads | CR-S20-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-22 | 2026-07-31 | 2026-07-31 | Internal line |  | 211.55 | Completed | No
WO-26-007906 | 11.1 | Bayou | BY-S21-05 | Corrective maintenance | P3 within 10 days | 2026-07-23 | 2026-08-01 | 2026-08-03 | Internal line |  | 633.84 | Completed | No
WO-26-007907 | 8.6 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-07-23 | 2026-07-31 | 2026-07-31 | Contract line | CT-03 | 1995.76 | Completed | No
WO-26-007908 | 9.5 | Bayou | BY-S09-03 | Corrective maintenance | P3 within 10 days | 2026-07-23 | 2026-07-29 | 2026-07-29 | Underground crew |  | 1584.23 | Completed | No
WO-26-007909 | 1.1 | Bayou | BY-S23-04 | Meter exchange | P3 within 10 days | 2026-07-23 | 2026-08-01 | 2026-08-02 | Meter technician |  | 101.82 | Completed | No
WO-26-007910 |  | Bayou | BY-S02-01 | Preventive maintenance | P4 planned | 2026-07-23 | 2026-09-09 |  | Internal line |  |  | Scheduled | No
WO-26-007911 | 1.3 | Bayou | BY-S30-01 | Service order - field | P3 within 10 days | 2026-07-23 | 2026-07-27 | 2026-07-31 | Meter technician |  | 26.36 | Completed | No
WO-26-007912 | 0.6 | Bayou | BY-S23-01 | Service order - field | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Meter technician |  | 37.95 | Completed | No
WO-26-007913 | 1.7 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-07-23 | 2026-07-24 | 2026-07-24 | Meter technician |  | 6.64 | Completed | No
WO-26-007914 | 1.3 | Bayou | BY-S29-01 | Service order - field | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Meter technician |  | 5.09 | Completed | No
WO-26-007915 | 1.6 | Bayou | BY-S04-02 | Service order - field | P3 within 10 days | 2026-07-23 | 2026-08-01 | 2026-08-02 | Meter technician |  | 1.44 | Completed | No
WO-26-007916 | 0.8 | Bayou | BY-S23-03 | Service order - field | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Meter technician |  | 32.32 | Completed | No
WO-26-007917 | 9.7 | Bayou | BY-S01-01 | Transformer replacement | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Internal line |  | 4161.96 | Completed | No
WO-26-007918 | 10.3 | Bayou | BY-S04-02 | Transformer replacement | P3 within 10 days | 2026-07-23 | 2026-08-02 | 2026-08-02 | Internal line |  | 7296.59 | Completed | No
WO-26-007919 | 5.5 | Bayou | BY-S23-05 | Trouble - no power | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 133.1 | Completed | No
WO-26-007920 | 4.1 | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 34.19 | Completed | No
WO-26-007921 | 3.8 | Bayou | BY-S15-03 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 48.74 | Completed | No
WO-26-007922 | 4.7 | Bayou | BY-S03-02 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Internal line |  | 270.13 | Completed | No
WO-26-007923 | 5.2 | Bayou | BY-S17-03 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Internal line |  | 229.91 | Completed | No
WO-26-007924 | 4.8 | Bayou | BY-S21-02 | Trouble - partial or voltage | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 115.81 | Completed | No
WO-26-007925 | 3.5 | Bayou | BY-S06-01 | Trouble - partial or voltage | P2 same day | 2026-07-23 | 2026-07-24 | 2026-07-24 | Troubleman |  | 218.93 | Completed | No
WO-26-007926 | 7.2 | Crossroads | CR-S20-05 | Corrective maintenance | P3 within 10 days | 2026-07-23 | 2026-07-30 | 2026-08-01 | Internal line |  | 2238.54 | Completed | No
WO-26-007927 | 7.9 | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-07-23 | 2026-07-27 | 2026-07-27 | Internal line |  | 2049.81 | Completed | No
WO-26-007928 |  | Crossroads | CR-S30-03 | Meter exchange | P4 planned | 2026-07-23 | 2026-09-20 |  | Meter technician |  |  | Scheduled | No
WO-26-007929 | 0.9 | Crossroads | CR-S23-05 | Meter exchange | P3 within 10 days | 2026-07-23 | 2026-07-26 | 2026-07-26 | Meter technician |  | 157.28 | Completed | No
WO-26-007930 | 1.3 | Crossroads | CR-S08-05 | Meter exchange | P3 within 10 days | 2026-07-23 | 2026-07-30 | 2026-07-31 | Meter technician |  | 164.51 | Completed | No
WO-26-007931 | 1.2 | Crossroads | CR-S02-02 | Meter exchange | P3 within 10 days | 2026-07-23 | 2026-07-27 | 2026-07-27 | Meter technician |  | 164.98 | Completed | No
WO-26-007932 | 1.4 | Crossroads | CR-S20-01 | Meter exchange | P4 planned | 2026-07-23 | 2026-08-15 | 2026-08-23 | Meter technician |  | 165.97 | Completed | No
WO-26-007933 | 6.2 | Crossroads | CR-S18-01 | New service - small | P4 planned | 2026-07-23 | 2026-08-17 | 2026-08-17 | Underground crew |  | 2707.7 | Completed | No
WO-26-007934 | 2.1 | Crossroads | CR-S13-04 | Preventive maintenance | P4 planned | 2026-07-23 | 2026-08-14 | 2026-08-14 | Contract line | CT-02 | 74.69 | Completed | No
WO-26-007935 |  | Crossroads | CR-S20-05 | Preventive maintenance | P4 planned | 2026-07-23 | 2026-09-14 |  | Underground crew |  |  | Scheduled | No
WO-26-007936 | 5.9 | Crossroads | CR-S21-01 | Preventive maintenance | P4 planned | 2026-07-23 | 2026-08-08 | 2026-08-16 | Underground crew |  | 161.48 | Completed | No
WO-26-007937 | 1.5 | Crossroads | CR-S30-07 | Service order - field | P3 within 10 days | 2026-07-23 | 2026-08-01 | 2026-08-05 | Meter technician |  | 35.29 | Completed | No
WO-26-007938 | 0.5 | Crossroads | CR-S05-01 | Service order - field | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Meter technician |  | 4.64 | Completed | No
WO-26-007939 | 1.3 | Crossroads | CR-S09-01 | Service order - field | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Meter technician |  | 5.56 | Completed | No
WO-26-007940 | 1.2 | Crossroads | CR-S16-01 | Service order - field | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Meter technician |  | 7.23 | Completed | No
WO-26-007941 | 1 | Crossroads | CR-S05-03 | Service order - field | P2 same day | 2026-07-23 | 2026-07-24 | 2026-07-24 | Meter technician |  | 6.11 | Completed | No
WO-26-007942 | 1.4 | Crossroads |  | Streetlight | P4 planned | 2026-07-23 | 2026-08-15 | 2026-08-15 | Contract line | CT-02 | 101.65 | Completed | No
WO-26-007943 | 1.8 | Crossroads |  | Streetlight | P4 planned | 2026-07-23 | 2026-08-10 | 2026-08-10 | Internal line |  | 120.72 | Completed | No
WO-26-007944 | 9.5 | Crossroads | CR-S23-01 | Transformer replacement | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Internal line |  | 9021.35 | Completed | No
WO-26-007945 | 4.7 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 325.33 | Completed | No
WO-26-007946 | 4.7 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Internal line |  | 333.28 | Completed | No
WO-26-007947 | 2.8 | Crossroads | CR-S23-05 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 222.52 | Completed | No
WO-26-007948 | 2.8 | Crossroads | CR-S20-05 | Trouble - no power | P2 same day | 2026-07-23 | 2026-07-24 | 2026-07-24 | Troubleman |  | 189.27 | Completed | No
WO-26-007949 | 4.6 | Crossroads | CR-S18-02 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 74.7 | Completed | No
WO-26-007950 | 2.1 | Crossroads | CR-S19-04 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 99.91 | Completed | No
WO-26-007951 | 4.2 | Crossroads | CR-S19-02 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 137 | Completed | No
WO-26-007952 | 2.3 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-07-23 | 2026-07-23 | 2026-07-23 | Internal line |  | 319.39 | Completed | No
WO-26-007953 | 2.2 | Crossroads | CR-S05-04 | Trouble - no power | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 214.45 | Completed | No
WO-26-007954 | 2.5 | Crossroads | CR-S23-05 | Trouble - partial or voltage | P2 same day | 2026-07-23 | 2026-07-24 | 2026-07-24 | Internal line |  | 98.6 | Completed | No
WO-26-007955 | 3.3 | Crossroads | CR-S32-04 | Trouble - partial or voltage | P2 same day | 2026-07-23 | 2026-07-23 | 2026-07-23 | Troubleman |  | 159.19 | Completed | No
WO-26-007956 | 10.5 | Bayou | BY-S13-02 | Corrective maintenance | P3 within 10 days | 2026-07-24 | 2026-07-29 | 2026-07-30 | Underground crew |  | 2059.54 | Completed | No
WO-26-007957 |  | Bayou | BY-S22-04 | Corrective maintenance | P2 same day | 2026-07-24 | 2026-07-24 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-007958 | 1.4 | Bayou | BY-S27-04 | Meter exchange | P3 within 10 days | 2026-07-24 | 2026-07-26 | 2026-07-26 | Meter technician |  | 64.48 | Completed | No
WO-26-007959 | 0.5 | Bayou | BY-S07-06 | Meter exchange | P3 within 10 days | 2026-07-24 | 2026-08-02 | 2026-08-04 | Meter technician |  | 118.96 | Completed | No
WO-26-007960 | 0.7 | Bayou | BY-S23-02 | Meter exchange | P3 within 10 days | 2026-07-24 | 2026-07-25 | 2026-07-25 | Meter technician |  | 126.47 | Completed | No
WO-26-007961 | 1.3 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-07-24 | 2026-07-29 | 2026-07-30 | Meter technician |  | 98.88 | Completed | No
WO-26-007962 | 0.7 | Bayou | BY-S16-06 | Meter exchange | P3 within 10 days | 2026-07-24 | 2026-07-25 | 2026-07-29 | Meter technician |  | 166.99 | Completed | No
WO-26-007963 | 13.3 | Bayou | BY-S10-04 | New service - small | P3 within 10 days | 2026-07-24 | 2026-08-03 | 2026-08-07 | Internal line |  | 2534.27 | Completed | No
WO-26-007964 | 11.5 | Bayou | BY-S29-04 | New service - small | P4 planned | 2026-07-24 | 2026-08-12 | 2026-08-14 | Internal line |  | 2826.35 | Completed | No
WO-26-007965 |  | Bayou | BY-S13-01 | Pole replacement | P4 planned | 2026-07-24 | 2026-08-16 |  | Internal line |  |  | Open - awaiting material | No
WO-26-007966 | 7.9 | Bayou | BY-S27-05 | Preventive maintenance | P4 planned | 2026-07-24 | 2026-08-17 | 2026-08-18 | Contract line | CT-04 | 26.95 | Completed | No
WO-26-007967 | 5.7 | Bayou | BY-S29-02 | Preventive maintenance | P4 planned | 2026-07-24 | 2026-08-29 | 2026-08-30 | Contract line | CT-04 | 376.14 | Completed | No
WO-26-007968 | 1.4 | Bayou | BY-S29-04 | Service order - field | P3 within 10 days | 2026-07-24 | 2026-08-02 | 2026-08-02 | Meter technician |  | 3.69 | Completed | No
WO-26-007969 | 0.7 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Meter technician |  | 37.47 | Completed | No
WO-26-007970 | 1.3 | Bayou | BY-S10-04 | Service order - field | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Meter technician |  | 31.52 | Completed | No
WO-26-007971 | 0.5 | Bayou | BY-S22-03 | Service order - field | P2 same day | 2026-07-24 | 2026-07-25 | 2026-07-25 | Meter technician |  | 35.22 | Completed | No
WO-26-007972 | 1.1 | Bayou | BY-S25-01 | Service order - field | P3 within 10 days | 2026-07-24 | 2026-08-01 | 2026-08-01 | Meter technician |  | 11.29 | Completed | No
WO-26-007973 | 2 | Bayou | BY-S20-01 | Service order - field | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Meter technician |  | 4.64 | Completed | No
WO-26-007974 | 0.8 | Bayou | BY-S05-01 | Service order - field | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Meter technician |  | 39.57 | Completed | No
WO-26-007975 |  | Bayou |  | Streetlight | P4 planned | 2026-07-24 | 2026-08-07 |  | Contract line | CT-03 |  | Cancelled | No
WO-26-007976 | 13.2 | Bayou | BY-S04-02 | Transformer replacement | P1 emergency | 2026-07-24 | 2026-07-24 | 2026-07-24 | Internal line |  | 4978.29 | Completed | No
WO-26-007977 | 3.3 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-07-24 | 2026-07-24 | 2026-07-24 | Troubleman |  | 197.22 | Completed | No
WO-26-007978 | 3.8 | Bayou | BY-S12-01 | Trouble - no power | P1 emergency | 2026-07-24 | 2026-07-24 | 2026-07-24 | Troubleman |  | 136.15 | Completed | No
WO-26-007979 | 3.7 | Bayou | BY-S22-04 | Trouble - no power | P2 same day | 2026-07-24 | 2026-07-25 | 2026-07-25 | Troubleman |  | 64.64 | Completed | No
WO-26-007980 | 4.2 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-07-24 | 2026-07-24 | 2026-07-24 | Troubleman |  | 124.97 | Completed | No
WO-26-007981 | 2.3 | Bayou | BY-S08-03 | Trouble - partial or voltage | P2 same day | 2026-07-24 | 2026-07-25 | 2026-07-25 | Troubleman |  | 191.84 | Completed | No
WO-26-007982 | 11.3 | Crossroads | CR-S15-02 | Corrective maintenance | P3 within 10 days | 2026-07-24 | 2026-08-03 | 2026-08-05 | Internal line |  | 1596.33 | Completed | No
WO-26-007983 |  | Crossroads | CR-S09-04 | Corrective maintenance | P4 planned | 2026-07-24 | 2026-09-13 |  | Underground crew |  |  | Scheduled | No
WO-26-007984 | 4.5 | Crossroads | CR-S16-05 | Corrective maintenance | P2 same day | 2026-07-24 | 2026-07-25 | 2026-07-25 | Contract line | CT-02 | 574.38 | Completed | No
WO-26-007985 | 0.5 | Crossroads | CR-S15-02 | Meter exchange | P4 planned | 2026-07-24 | 2026-08-12 | 2026-08-14 | Meter technician |  | 145.56 | Completed | No
WO-26-007986 | 1.2 | Crossroads | CR-S02-02 | Meter exchange | P4 planned | 2026-07-24 | 2026-08-06 | 2026-08-06 | Meter technician |  | 175.81 | Completed | No
WO-26-007987 | 0.9 | Crossroads | CR-S20-03 | Meter exchange | P4 planned | 2026-07-24 | 2026-08-11 | 2026-08-15 | Meter technician |  | 101.54 | Completed | No
WO-26-007988 |  | Crossroads | CR-S02-05 | Pole replacement | P4 planned | 2026-07-24 | 2026-09-05 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-007989 | 15.1 | Crossroads | CR-S32-02 | Pole replacement | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Internal line |  | 3133.41 | Completed | No
WO-26-007990 | 7.8 | Crossroads | CR-S29-03 | Preventive maintenance | P4 planned | 2026-07-24 | 2026-07-31 | 2026-07-31 | Contract line | CT-01 | 7.23 | Completed | No
WO-26-007991 | 2.8 | Crossroads | CR-S09-01 | Preventive maintenance | P4 planned | 2026-07-24 | 2026-07-31 | 2026-08-01 | Underground crew |  | 303.8 | Completed | No
WO-26-007992 |  | Crossroads | CR-S15-01 | Preventive maintenance | P4 planned | 2026-07-24 | 2026-09-11 |  | Underground crew |  |  | Scheduled | No
WO-26-007993 | 1 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-07-24 | 2026-07-28 | 2026-07-29 | Meter technician |  | 6.15 | Completed | No
WO-26-007994 | 1.4 | Crossroads | CR-S07-02 | Service order - field | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Meter technician |  | 28.24 | Completed | No
WO-26-007995 | 12.9 | Crossroads | CR-S07-02 | Transformer replacement | P2 same day | 2026-07-24 | 2026-07-25 | 2026-07-25 | Contract line | CT-01 | 10719.83 | Completed | No
WO-26-007996 | 2.6 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-07-24 | 2026-07-25 | 2026-07-25 | Internal line |  | 113.4 | Completed | No
WO-26-007997 | 2.8 | Crossroads | CR-S07-04 | Trouble - no power | P1 emergency | 2026-07-24 | 2026-07-24 | 2026-07-24 | Troubleman |  | 190.35 | Completed | No
WO-26-007998 | 4.9 | Crossroads | CR-S13-03 | Trouble - no power | P1 emergency | 2026-07-24 | 2026-07-24 | 2026-07-24 | Troubleman |  | 28.48 | Completed | No
WO-26-007999 | 3.5 | Crossroads | CR-S07-02 | Trouble - no power | P2 same day | 2026-07-24 | 2026-07-24 | 2026-07-24 | Internal line |  | 233.99 | Completed | No
WO-26-008000 | 3.3 | Crossroads | CR-S04-04 | Trouble - partial or voltage | P3 within 10 days | 2026-07-24 | 2026-07-28 | 2026-07-28 | Troubleman |  | 39.74 | Completed | No
WO-26-008001 | 18.8 | Bayou | BY-S19-01 | Pole replacement | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Contract line | CT-03 | 1611.6 | Completed | No
WO-26-008002 | 1.8 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-07-25 | 2026-07-25 | 2026-07-25 | Meter technician |  | 21.11 | Completed | No
WO-26-008003 | 1.9 | Bayou | BY-S16-04 | Service order - field | P2 same day | 2026-07-25 | 2026-07-25 | 2026-07-25 | Meter technician |  | 37.86 | Completed | No
WO-26-008004 | 2 | Bayou | BY-S11-03 | Service order - field | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Meter technician |  | 30.33 | Completed | No
WO-26-008005 | 8.2 | Bayou | BY-S12-04 | Transformer replacement | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Internal line |  | 9395.85 | Completed | No
WO-26-008006 | 3.7 | Bayou | BY-S08-03 | Trouble - no power | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Internal line |  | 64.17 | Completed | No
WO-26-008007 | 5 | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 115.17 | Completed | No
WO-26-008008 | 5.5 | Bayou | BY-S27-04 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Internal line |  | 167.94 | Completed | No
WO-26-008009 |  | Bayou | BY-S19-02 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 |  | Internal line |  |  | Cancelled | No
WO-26-008010 | 5.9 | Bayou | BY-S24-04 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 180.91 | Completed | No
WO-26-008011 | 2.3 | Bayou | BY-S06-03 | Trouble - no power | P2 same day | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 321.9 | Completed | No
WO-26-008012 | 4.1 | Bayou | BY-S24-04 | Trouble - partial or voltage | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Troubleman |  | 178.53 | Completed | No
WO-26-008013 | 3.2 | Bayou | BY-S27-06 | Trouble - partial or voltage | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Troubleman |  | 164.35 | Completed | No
WO-26-008014 | 1.7 | Bayou | BY-S16-01 | Trouble - partial or voltage | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Troubleman |  | 246.02 | Completed | No
WO-26-008015 | 1.7 | Crossroads | CR-S11-01 | Service order - field | P2 same day | 2026-07-25 | 2026-07-25 | 2026-07-25 | Meter technician |  | 17.82 | Completed | No
WO-26-008016 | 1.9 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Meter technician |  | 38.97 | Completed | No
WO-26-008017 |  | Crossroads | CR-S23-04 | Transformer replacement | P2 same day | 2026-07-25 | 2026-07-26 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-008018 | 8.6 | Crossroads | CR-S17-01 | Transformer replacement | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Contract line | CT-02 | 4651.53 | Completed | No
WO-26-008019 | 4.8 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 29.75 | Completed | No
WO-26-008020 | 4.3 | Crossroads | CR-S26-03 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 281.46 | Completed | No
WO-26-008021 | 5.1 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 40.1 | Completed | No
WO-26-008022 | 3.1 | Crossroads | CR-S28-01 | Trouble - no power | P1 emergency | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 90.86 | Completed | No
WO-26-008023 | 2.9 | Crossroads | CR-S16-02 | Trouble - partial or voltage | P2 same day | 2026-07-25 | 2026-07-25 | 2026-07-25 | Troubleman |  | 135.66 | Completed | No
WO-26-008024 | 3.8 | Crossroads | CR-S30-07 | Trouble - partial or voltage | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Troubleman |  | 153.79 | Completed | No
WO-26-008025 | 3 | Crossroads | CR-S03-01 | Trouble - partial or voltage | P2 same day | 2026-07-25 | 2026-07-26 | 2026-07-26 | Troubleman |  | 101.21 | Completed | No
WO-26-008026 | 10.5 | Bayou | BY-S06-01 | Corrective maintenance | P2 same day | 2026-07-26 | 2026-07-26 | 2026-07-26 | Contract line | CT-03 | 2187.9 | Completed | No
WO-26-008027 | 12.8 | Bayou | BY-S18-05 | Pole replacement | P2 same day | 2026-07-26 | 2026-07-26 | 2026-07-26 | Contract line | CT-03 | 2939.78 | Completed | No
WO-26-008028 | 7.8 | Bayou | BY-S15-02 | Transformer replacement | P2 same day | 2026-07-26 | 2026-07-26 | 2026-07-26 | Contract line | CT-04 | 5348.56 | Completed | No
WO-26-008029 |  | Bayou | BY-S18-04 | Transformer replacement | P2 same day | 2026-07-26 | 2026-07-26 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008030 | 7.3 | Bayou | BY-S06-01 | Transformer replacement | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Internal line |  | 3307.27 | Completed | No
WO-26-008031 | 4.8 | Bayou | BY-S18-02 | Trouble - no power | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Troubleman |  | 237.18 | Completed | No
WO-26-008032 | 2.9 | Bayou | BY-S21-05 | Trouble - no power | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Internal line |  | 233.4 | Completed | No
WO-26-008033 | 3.1 | Bayou | BY-S23-04 | Trouble - no power | P1 emergency | 2026-07-26 | 2026-07-26 | 2026-07-26 | Troubleman |  | 149.13 | Completed | No
WO-26-008034 | 5.8 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Troubleman |  | 100.59 | Completed | No
WO-26-008035 | 1.8 | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Meter technician |  | 11.24 | Completed | No
WO-26-008036 | 1.8 | Crossroads | CR-S29-01 | Service order - field | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Meter technician |  | 4.74 | Completed | No
WO-26-008037 | 0.8 | Crossroads | CR-S08-02 | Service order - field | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Meter technician |  | 30.66 | Completed | No
WO-26-008038 | 1.9 | Crossroads | CR-S32-01 | Service order - field | P2 same day | 2026-07-26 | 2026-07-26 | 2026-07-26 | Meter technician |  | 26.24 | Completed | No
WO-26-008039 | 7.1 | Crossroads | CR-S21-01 | Transformer replacement | P2 same day | 2026-07-26 | 2026-07-27 | 2026-07-27 | Contract line | CT-01 | 11781.06 | Completed | No
WO-26-008040 |  | Crossroads | CR-S08-03 | Transformer replacement | P2 same day | 2026-07-26 | 2026-07-26 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008041 | 3.1 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-07-26 | 2026-07-26 | 2026-07-26 | Troubleman |  | 121.69 | Completed | No
WO-26-008042 | 4.2 | Crossroads | CR-S04-04 | Trouble - no power | P2 same day | 2026-07-26 | 2026-07-26 | 2026-07-26 | Troubleman |  | 174.32 | Completed | No
WO-26-008043 | 2.7 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-07-26 | 2026-07-26 | 2026-07-26 | Troubleman |  | 196.63 | Completed | No
WO-26-008044 | 2.5 | Crossroads | CR-S29-03 | Trouble - no power | P2 same day | 2026-07-26 | 2026-07-26 | 2026-07-26 | Troubleman |  | 321.97 | Completed | No
WO-26-008045 | 4.7 | Bayou | BY-S18-03 | Corrective maintenance | P3 within 10 days | 2026-07-27 | 2026-08-01 | 2026-08-05 | Contract line | CT-03 | 257.29 | Completed | No
WO-26-008046 | 11.3 | Bayou | BY-S15-02 | Corrective maintenance | P3 within 10 days | 2026-07-27 | 2026-07-29 | 2026-08-02 | Contract line | CT-04 | 669.51 | Completed | No
WO-26-008047 | 1.2 | Bayou | BY-S17-01 | Meter exchange | P3 within 10 days | 2026-07-27 | 2026-07-28 | 2026-07-28 | Meter technician |  | 167.41 | Completed | No
WO-26-008048 | 6.4 | Bayou | BY-S19-02 | New service - small | P4 planned | 2026-07-27 | 2026-08-22 | 2026-08-22 | Internal line |  | 2710.44 | Completed | No
WO-26-008049 | 10.2 | Bayou | BY-S02-01 | New service - small | P4 planned | 2026-07-27 | 2026-08-04 | 2026-08-05 | Contract line | CT-03 | 3677.14 | Completed | No
WO-26-008050 | 19.4 | Bayou | BY-S16-03 | Pole replacement | P4 planned | 2026-07-27 | 2026-08-24 | 2026-08-26 | Contract line | CT-04 | 3378.86 | Completed | No
WO-26-008051 | 4.8 | Bayou | BY-S07-03 | Preventive maintenance | P4 planned | 2026-07-27 | 2026-08-12 | 2026-08-13 | Internal line |  | 272.53 | Completed | No
WO-26-008052 |  | Bayou | BY-S24-03 | Preventive maintenance | P4 planned | 2026-07-27 | 2026-09-08 |  | Internal line |  |  | Scheduled | No
WO-26-008053 |  | Bayou | BY-S06-01 | Preventive maintenance | P4 planned | 2026-07-27 | 2026-09-24 |  | Underground crew |  |  | Scheduled | No
WO-26-008054 | 0.8 | Bayou | BY-S21-04 | Service order - field | P3 within 10 days | 2026-07-27 | 2026-08-01 | 2026-08-05 | Meter technician |  | 13.73 | Completed | No
WO-26-008055 | 0.9 | Bayou | BY-S03-02 | Service order - field | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Meter technician |  | 39 | Completed | No
WO-26-008056 | 1.2 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-07-27 | 2026-08-03 | 2026-08-03 | Meter technician |  | 26.68 | Completed | No
WO-26-008057 | 1.1 | Bayou | BY-S23-01 | Service order - field | P3 within 10 days | 2026-07-27 | 2026-07-28 | 2026-07-30 | Meter technician |  | 12.92 | Completed | No
WO-26-008058 | 1.4 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-07-27 | 2026-08-02 | 2026-08-06 | Meter technician |  | 35.7 | Completed | No
WO-26-008059 | 1.8 | Bayou | BY-S23-01 | Service order - field | P2 same day | 2026-07-27 | 2026-07-28 | 2026-07-28 | Meter technician |  | 5.13 | Completed | No
WO-26-008060 |  | Bayou |  | Streetlight | P4 planned | 2026-07-27 | 2026-09-19 |  | Internal line |  |  | Scheduled | No
WO-26-008061 |  | Bayou |  | Streetlight | P4 planned | 2026-07-27 | 2026-09-25 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008062 | 3 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-27 | 2026-07-30 | 2026-07-30 | Contract line | CT-03 | 183.34 | Completed | No
WO-26-008063 | 12.4 | Bayou | BY-S18-07 | Transformer replacement | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Internal line |  | 6780.93 | Completed | No
WO-26-008064 | 3.2 | Bayou | BY-S15-02 | Trouble - no power | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 42.74 | Completed | No
WO-26-008065 | 1.6 | Bayou | BY-S30-01 | Trouble - partial or voltage | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 201.28 | Completed | No
WO-26-008066 | 4.7 | Crossroads | CR-S31-01 | Corrective maintenance | P3 within 10 days | 2026-07-27 | 2026-08-02 | 2026-08-10 | Contract line | CT-01 | 1282.47 | Completed | No
WO-26-008067 | 7.5 | Crossroads | CR-S28-02 | Corrective maintenance | P4 planned | 2026-07-27 | 2026-08-20 | 2026-08-20 | Internal line |  | 2030.89 | Completed | No
WO-26-008068 |  | Crossroads | CR-S23-05 | Corrective maintenance | P3 within 10 days | 2026-07-27 | 2026-08-05 |  | Internal line |  |  | Cancelled | No
WO-26-008069 | 3.9 | Crossroads | CR-S07-07 | Corrective maintenance | P3 within 10 days | 2026-07-27 | 2026-07-29 | 2026-08-02 | Internal line |  | 1217.1 | Completed | No
WO-26-008070 | 1.4 | Crossroads | CR-S15-03 | Meter exchange | P3 within 10 days | 2026-07-27 | 2026-07-29 | 2026-07-30 | Meter technician |  | 174.57 | Completed | No
WO-26-008071 | 1.7 | Crossroads | CR-S25-03 | Service order - field | P3 within 10 days | 2026-07-27 | 2026-08-02 | 2026-08-03 | Meter technician |  | 17.9 | Completed | No
WO-26-008072 | 0.6 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-07-27 | 2026-07-28 | 2026-07-28 | Meter technician |  | 5.8 | Completed | No
WO-26-008073 | 1.6 | Crossroads | CR-S30-05 | Service order - field | P2 same day | 2026-07-27 | 2026-07-28 | 2026-07-28 | Meter technician |  | 18.3 | Completed | No
WO-26-008074 | 1.7 | Crossroads | CR-S23-04 | Service order - field | P2 same day | 2026-07-27 | 2026-07-28 | 2026-07-28 | Meter technician |  | 34.04 | Completed | No
WO-26-008075 | 0.9 | Crossroads | CR-S29-03 | Service order - field | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Meter technician |  | 31.9 | Completed | No
WO-26-008076 | 1.5 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-27 | 2026-08-02 | 2026-08-02 | Contract line | CT-02 | 125.18 | Completed | No
WO-26-008077 |  | Crossroads | CR-S32-05 | Transformer replacement | P2 same day | 2026-07-27 | 2026-07-28 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008078 |  | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-07-27 | 2026-07-27 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008079 |  | Crossroads | CR-S20-01 | Transformer replacement | P1 emergency | 2026-07-27 | 2026-07-27 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008080 | 5.7 | Crossroads | CR-S23-03 | Trouble - no power | P2 same day | 2026-07-27 | 2026-07-28 | 2026-07-28 | Troubleman |  | 134.82 | Completed | No
WO-26-008081 | 4.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 159.99 | Completed | No
WO-26-008082 | 5.5 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 65.92 | Completed | No
WO-26-008083 | 4.2 | Crossroads | CR-S05-03 | Trouble - no power | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Internal line |  | 204.89 | Completed | No
WO-26-008084 | 4.6 | Crossroads | CR-S30-05 | Trouble - no power | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 94.58 | Completed | No
WO-26-008085 | 4.9 | Crossroads | CR-S02-03 | Trouble - no power | P1 emergency | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 217.18 | Completed | No
WO-26-008086 | 2.1 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 40.21 | Completed | No
WO-26-008087 | 5.1 | Crossroads | CR-S26-01 | Trouble - no power | P1 emergency | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 266.69 | Completed | No
WO-26-008088 | 2.2 | Crossroads | CR-S14-03 | Trouble - no power | P2 same day | 2026-07-27 | 2026-07-28 | 2026-07-28 | Troubleman |  | 58.03 | Completed | No
WO-26-008089 | 3.6 | Crossroads | CR-S21-03 | Trouble - partial or voltage | P2 same day | 2026-07-27 | 2026-07-27 | 2026-07-27 | Troubleman |  | 142.5 | Completed | No
WO-26-008090 | 4.9 | Bayou | BY-S03-02 | Corrective maintenance | P4 planned | 2026-07-28 | 2026-08-29 | 2026-08-29 | Internal line |  | 1309.68 | Completed | No
WO-26-008091 | 7.6 | Bayou | BY-S07-02 | Corrective maintenance | P3 within 10 days | 2026-07-28 | 2026-08-06 | 2026-08-10 | Contract line | CT-03 | 323.31 | Completed | No
WO-26-008092 | 10.8 | Bayou | BY-S14-01 | Corrective maintenance | P3 within 10 days | 2026-07-28 | 2026-07-30 | 2026-07-30 | Contract line | CT-03 | 1949.95 | Completed | No
WO-26-008093 | 8.1 | Bayou | BY-S02-01 | Corrective maintenance | P3 within 10 days | 2026-07-28 | 2026-08-03 | 2026-08-03 | Internal line |  | 1773.63 | Completed | No
WO-26-008094 | 1.5 | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-07-28 | 2026-08-02 | 2026-08-02 | Meter technician |  | 63.22 | Completed | No
WO-26-008095 | 1.4 | Bayou | BY-S16-02 | Meter exchange | P3 within 10 days | 2026-07-28 | 2026-07-31 | 2026-07-31 | Meter technician |  | 102.34 | Completed | No
WO-26-008096 | 19.9 | Bayou | BY-S14-01 | Pole replacement | P2 same day | 2026-07-28 | 2026-07-28 | 2026-07-28 | Contract line | CT-04 | 3495.9 | Completed | No
WO-26-008097 | 4.3 | Bayou | BY-S12-01 | Preventive maintenance | P4 planned | 2026-07-28 | 2026-08-06 | 2026-08-06 | Internal line |  | 501.47 | Completed | No
WO-26-008098 | 1 | Bayou | BY-S06-02 | Service order - field | P3 within 10 days | 2026-07-28 | 2026-08-01 | 2026-08-09 | Meter technician |  | 10.47 | Completed | No
WO-26-008099 | 1.1 | Bayou | BY-S13-06 | Service order - field | P3 within 10 days | 2026-07-28 | 2026-07-29 | 2026-07-30 | Meter technician |  | 3.37 | Completed | No
WO-26-008100 | 0.8 | Bayou | BY-S26-03 | Service order - field | P2 same day | 2026-07-28 | 2026-07-28 | 2026-07-28 | Meter technician |  | 13.8 | Completed | No
WO-26-008101 | 0.5 | Bayou | BY-S07-03 | Service order - field | P3 within 10 days | 2026-07-28 | 2026-08-06 | 2026-08-06 | Meter technician |  | 19.47 | Completed | No
WO-26-008102 | 1.4 | Bayou | BY-S15-04 | Service order - field | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Meter technician |  | 33.37 | Completed | No
WO-26-008103 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-28 | 2026-08-03 | 2026-08-04 | Internal line |  | 61.55 | Completed | No
WO-26-008104 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-28 | 2026-08-07 | 2026-08-07 | Internal line |  | 431.99 | Completed | No
WO-26-008105 | 13 | Bayou | BY-S01-01 | Transformer replacement | P3 within 10 days | 2026-07-28 | 2026-08-03 | 2026-08-11 | Contract line | CT-04 | 6902.51 | Completed | No
WO-26-008106 | 10.2 | Bayou | BY-S29-02 | Transformer replacement | P3 within 10 days | 2026-07-28 | 2026-08-07 | 2026-08-07 | Internal line |  | 8537.16 | Completed | No
WO-26-008107 | 3.7 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-07-28 | 2026-07-28 | 2026-07-28 | Internal line |  | 247.17 | Completed | No
WO-26-008108 | 3.3 | Bayou | BY-S22-04 | Trouble - no power | P1 emergency | 2026-07-28 | 2026-07-28 | 2026-07-28 | Troubleman |  | 41.58 | Completed | No
WO-26-008109 | 4 | Bayou | BY-S01-01 | Trouble - partial or voltage | P3 within 10 days | 2026-07-28 | 2026-08-07 | 2026-08-08 | Troubleman |  | 76.22 | Completed | No
WO-26-008110 | 5.2 | Crossroads | CR-S17-03 | Corrective maintenance | P3 within 10 days | 2026-07-28 | 2026-08-07 | 2026-08-07 | Underground crew |  | 2090.64 | Completed | No
WO-26-008111 |  | Crossroads | CR-S06-02 | Meter exchange | P4 planned | 2026-07-28 | 2026-09-19 |  | Meter technician |  |  | Scheduled | No
WO-26-008112 | 1 | Crossroads | CR-S04-06 | Meter exchange | P3 within 10 days | 2026-07-28 | 2026-08-02 | 2026-08-02 | Meter technician |  | 158.17 | Completed | No
WO-26-008113 |  | Crossroads | CR-S30-04 | Meter exchange | P4 planned | 2026-07-28 | 2026-09-16 |  | Meter technician |  |  | Scheduled | No
WO-26-008114 | 18.3 | Crossroads | CR-S20-03 | Pole replacement | P3 within 10 days | 2026-07-28 | 2026-07-29 | 2026-07-29 | Contract line | CT-01 | 2667.13 | Completed | No
WO-26-008115 | 2.8 | Crossroads | CR-S29-03 | Preventive maintenance | P4 planned | 2026-07-28 | 2026-08-17 | 2026-08-17 | Underground crew |  | 356.06 | Completed | No
WO-26-008116 | 1.3 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Meter technician |  | 31.78 | Completed | No
WO-26-008117 | 0.6 | Crossroads | CR-S23-02 | Service order - field | P2 same day | 2026-07-28 | 2026-07-28 | 2026-07-28 | Meter technician |  | 8.28 | Completed | No
WO-26-008118 | 0.9 | Crossroads | CR-S15-02 | Service order - field | P2 same day | 2026-07-28 | 2026-07-28 | 2026-07-28 | Meter technician |  | 22.03 | Completed | No
WO-26-008119 | 1.1 | Crossroads | CR-S28-04 | Service order - field | P3 within 10 days | 2026-07-28 | 2026-08-02 | 2026-08-03 | Meter technician |  | 38.3 | Completed | No
WO-26-008120 | 1.1 | Crossroads | CR-S04-06 | Service order - field | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Meter technician |  | 16.52 | Completed | No
WO-26-008121 | 1.7 | Crossroads | CR-S06-03 | Service order - field | P3 within 10 days | 2026-07-28 | 2026-08-07 | 2026-08-09 | Meter technician |  | 31.2 | Completed | No
WO-26-008122 | 6.5 | Crossroads | CR-S12-01 | Transformer replacement | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Internal line |  | 8847.4 | Completed | No
WO-26-008123 | 12.4 | Crossroads | CR-S23-02 | Transformer replacement | P1 emergency | 2026-07-28 | 2026-07-28 | 2026-07-28 | Internal line |  | 8826.01 | Completed | No
WO-26-008124 | 13.3 | Crossroads | CR-S04-02 | Transformer replacement | P1 emergency | 2026-07-28 | 2026-07-28 | 2026-07-28 | Internal line |  | 4211.18 | Completed | No
WO-26-008125 | 3.6 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Internal line |  | 167.08 | Completed | No
WO-26-008126 | 3.1 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-07-28 | 2026-07-28 | 2026-07-28 | Troubleman |  | 50.66 | Completed | No
WO-26-008127 | 2.1 | Crossroads | CR-S05-06 | Trouble - no power | P2 same day | 2026-07-28 | 2026-07-28 | 2026-07-28 | Internal line |  | 143.03 | Completed | No
WO-26-008128 | 5.2 | Crossroads | CR-S15-02 | Trouble - no power | P1 emergency | 2026-07-28 | 2026-07-28 | 2026-07-28 | Internal line |  | 192.02 | Completed | No
WO-26-008129 | 4.6 | Crossroads | CR-S21-01 | Trouble - partial or voltage | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Troubleman |  | 1.15 | Completed | No
WO-26-008130 | 4.4 | Crossroads | CR-S23-05 | Trouble - partial or voltage | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Internal line |  | 162.86 | Completed | No
WO-26-008131 | 4.7 | Crossroads | CR-S08-06 | Trouble - partial or voltage | P2 same day | 2026-07-28 | 2026-07-28 | 2026-07-28 | Troubleman |  | 147.23 | Completed | No
WO-26-008132 | 2.4 | Crossroads | CR-S25-03 | Trouble - partial or voltage | P2 same day | 2026-07-28 | 2026-07-29 | 2026-07-29 | Troubleman |  | 156.3 | Completed | No
WO-26-008133 | 8 | Bayou | BY-S01-01 | Corrective maintenance | P3 within 10 days | 2026-07-29 | 2026-08-05 | 2026-08-05 | Underground crew |  | 606.89 | Completed | No
WO-26-008134 | 11.3 | Bayou | BY-S07-03 | Corrective maintenance | P3 within 10 days | 2026-07-29 | 2026-08-08 | 2026-08-08 | Underground crew |  | 1194.33 | Completed | No
WO-26-008135 | 11.3 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-07-29 | 2026-08-01 | 2026-08-09 | Contract line | CT-04 | 2201.3 | Completed | No
WO-26-008136 | 11.7 | Bayou | BY-S29-04 | Corrective maintenance | P3 within 10 days | 2026-07-29 | 2026-08-05 | 2026-08-06 | Internal line |  | 1380.37 | Completed | No
WO-26-008137 | 1 | Bayou | BY-S10-04 | Meter exchange | P3 within 10 days | 2026-07-29 | 2026-08-08 | 2026-08-09 | Meter technician |  | 83.56 | Completed | No
WO-26-008138 | 0.6 | Bayou | BY-S18-05 | Meter exchange | P3 within 10 days | 2026-07-29 | 2026-07-31 | 2026-07-31 | Meter technician |  | 109.76 | Completed | No
WO-26-008139 | 0.7 | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-07-29 | 2026-08-03 | 2026-08-07 | Meter technician |  | 89.14 | Completed | No
WO-26-008140 |  | Bayou | BY-S29-01 | Pole replacement | P4 planned | 2026-07-29 | 2026-09-03 |  | Internal line |  |  | Scheduled | No
WO-26-008141 |  | Bayou | BY-S07-05 | Pole replacement | P3 within 10 days | 2026-07-29 | 2026-08-08 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008142 | 6.9 | Bayou | BY-S19-01 | Preventive maintenance | P4 planned | 2026-07-29 | 2026-08-20 | 2026-08-20 | Internal line |  | 509.27 | Completed | No
WO-26-008143 | 1.5 | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-07-29 | 2026-08-08 | 2026-08-08 | Meter technician |  | 18.03 | Completed | No
WO-26-008144 | 1.1 | Bayou | BY-S12-04 | Service order - field | P2 same day | 2026-07-29 | 2026-07-30 | 2026-07-30 | Meter technician |  | 11.66 | Completed | No
WO-26-008145 |  | Bayou | BY-S24-01 | Service order - field | P3 within 10 days | 2026-07-29 | 2026-08-08 |  | Meter technician |  |  | Cancelled | No
WO-26-008146 | 1.4 | Bayou |  | Streetlight | P4 planned | 2026-07-29 | 2026-08-23 | 2026-08-23 | Contract line | CT-03 | 340.81 | Completed | No
WO-26-008147 | 1.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-29 | 2026-08-06 | 2026-08-06 | Contract line | CT-03 | 55.97 | Completed | No
WO-26-008148 |  | Bayou |  | Streetlight | P4 planned | 2026-07-29 | 2026-09-09 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008149 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-29 | 2026-08-07 | 2026-08-08 | Contract line | CT-03 | 233.71 | Completed | No
WO-26-008150 | 1.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-29 | 2026-08-02 | 2026-08-10 | Internal line |  | 193.81 | Completed | No
WO-26-008151 | 10 | Bayou | BY-S16-01 | Transformer replacement | P3 within 10 days | 2026-07-29 | 2026-08-05 | 2026-08-09 | Internal line |  | 4640.53 | Completed | No
WO-26-008152 | 6.2 | Bayou | BY-S15-03 | Transformer replacement | P3 within 10 days | 2026-07-29 | 2026-08-04 | 2026-08-05 | Contract line | CT-03 | 10014.02 | Completed | No
WO-26-008153 | 4.7 | Bayou | BY-S09-02 | Trouble - no power | P1 emergency | 2026-07-29 | 2026-07-29 | 2026-07-29 | Troubleman |  | 148.61 | Completed | No
WO-26-008154 | 2.1 | Bayou | BY-S28-02 | Trouble - partial or voltage | P2 same day | 2026-07-29 | 2026-07-29 | 2026-07-29 | Internal line |  | 205.38 | Completed | No
WO-26-008155 |  | Crossroads | CR-S17-01 | Corrective maintenance | P4 planned | 2026-07-29 | 2026-09-26 |  | Underground crew |  |  | Scheduled | No
WO-26-008156 | 11.4 | Crossroads | CR-S09-03 | Corrective maintenance | P4 planned | 2026-07-29 | 2026-08-21 | 2026-08-22 | Internal line |  | 2081.77 | Completed | No
WO-26-008157 | 9.6 | Crossroads | CR-S07-07 | Corrective maintenance | P3 within 10 days | 2026-07-29 | 2026-08-02 | 2026-08-02 | Internal line |  | 92.3 | Completed | No
WO-26-008158 | 0.8 | Crossroads | CR-S04-04 | Meter exchange | P3 within 10 days | 2026-07-29 | 2026-08-02 | 2026-08-04 | Meter technician |  | 134.68 | Completed | No
WO-26-008159 | 1.2 | Crossroads | CR-S30-07 | Meter exchange | P4 planned | 2026-07-29 | 2026-08-23 | 2026-08-31 | Meter technician |  | 138.46 | Completed | No
WO-26-008160 | 0.7 | Crossroads | CR-S13-06 | Meter exchange | P4 planned | 2026-07-29 | 2026-08-28 | 2026-08-28 | Meter technician |  | 67.54 | Completed | No
WO-26-008161 | 0.8 | Crossroads | CR-S06-02 | Meter exchange | P4 planned | 2026-07-29 | 2026-08-11 | 2026-08-15 | Meter technician |  | 171.37 | Completed | No
WO-26-008162 | 1.2 | Crossroads | CR-S27-02 | Meter exchange | P3 within 10 days | 2026-07-29 | 2026-08-05 | 2026-08-09 | Meter technician |  | 160.6 | Completed | No
WO-26-008163 | 10.7 | Crossroads | CR-S30-01 | New service - small | P4 planned | 2026-07-29 | 2026-08-16 | 2026-08-16 | Contract line | CT-02 | 3274.95 | Completed | No
WO-26-008164 | 3.3 | Crossroads | CR-S24-03 | Preventive maintenance | P4 planned | 2026-07-29 | 2026-08-28 | 2026-08-28 | Underground crew |  | 346.94 | Completed | No
WO-26-008165 |  | Crossroads | CR-S06-03 | Preventive maintenance | P4 planned | 2026-07-29 | 2026-09-12 |  | Internal line |  |  | Scheduled | No
WO-26-008166 |  | Crossroads | CR-S19-03 | Preventive maintenance | P4 planned | 2026-07-29 | 2026-08-06 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008167 |  | Crossroads | CR-S12-01 | Preventive maintenance | P4 planned | 2026-07-29 | 2026-09-25 |  | Underground crew |  |  | Scheduled | No
WO-26-008168 | 7.2 | Crossroads | CR-S04-02 | Preventive maintenance | P4 planned | 2026-07-29 | 2026-08-15 | 2026-08-15 | Underground crew |  | 381.49 | Completed | No
WO-26-008169 | 1 | Crossroads | CR-S04-04 | Service order - field | P2 same day | 2026-07-29 | 2026-07-29 | 2026-07-29 | Meter technician |  | 36.51 | Completed | No
WO-26-008170 | 0.7 | Crossroads | CR-S30-02 | Service order - field | P3 within 10 days | 2026-07-29 | 2026-08-07 | 2026-08-08 | Meter technician |  | 23.18 | Completed | No
WO-26-008171 | 1.6 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-07-29 | 2026-08-03 | 2026-08-03 | Meter technician |  | 2.28 | Completed | No
WO-26-008172 | 2 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-07-29 | 2026-07-29 | 2026-07-29 | Meter technician |  | 25.87 | Completed | No
WO-26-008173 | 1.9 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-07-29 | 2026-08-01 | 2026-08-02 | Meter technician |  | 33.59 | Completed | No
WO-26-008174 | 1.8 | Crossroads | CR-S10-02 | Service order - field | P2 same day | 2026-07-29 | 2026-07-30 | 2026-07-30 | Meter technician |  | 30.64 | Completed | No
WO-26-008175 | 2.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-29 | 2026-08-08 | 2026-08-09 | Contract line | CT-02 | 248.21 | Completed | No
WO-26-008176 | 3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-29 | 2026-08-08 | 2026-08-08 | Contract line | CT-02 | 413.21 | Completed | No
WO-26-008177 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-29 | 2026-08-02 | 2026-08-02 | Internal line |  | 166.07 | Completed | No
WO-26-008178 | 12.2 | Crossroads | CR-S22-02 | Transformer replacement | P2 same day | 2026-07-29 | 2026-07-30 | 2026-07-30 | Internal line |  | 12206.66 | Completed | No
WO-26-008179 | 11.2 | Crossroads | CR-S14-03 | Transformer replacement | P2 same day | 2026-07-29 | 2026-07-29 | 2026-07-29 | Internal line |  | 11266.29 | Completed | No
WO-26-008180 | 11.7 | Crossroads | CR-S28-03 | Transformer replacement | P3 within 10 days | 2026-07-29 | 2026-08-02 | 2026-08-02 | Internal line |  | 3256.97 | Completed | No
WO-26-008181 | 7.2 | Crossroads | CR-S20-04 | Transformer replacement | P2 same day | 2026-07-29 | 2026-07-29 | 2026-07-29 | Contract line | CT-01 | 4022.64 | Completed | No
WO-26-008182 | 8 | Crossroads | CR-S30-03 | Transformer replacement | P2 same day | 2026-07-29 | 2026-07-30 | 2026-07-30 | Internal line |  | 7492.23 | Completed | No
WO-26-008183 | 5.8 | Crossroads | CR-S24-01 | Trouble - no power | P2 same day | 2026-07-29 | 2026-07-29 | 2026-07-29 | Troubleman |  | 9.07 | Completed | No
WO-26-008184 | 5.2 | Crossroads | CR-S26-04 | Trouble - no power | P1 emergency | 2026-07-29 | 2026-07-29 | 2026-07-29 | Troubleman |  | 100.92 | Completed | No
WO-26-008185 | 4.7 | Crossroads | CR-S29-01 | Trouble - partial or voltage | P2 same day | 2026-07-29 | 2026-07-30 | 2026-07-30 | Internal line |  | 79.75 | Completed | No
WO-26-008186 | 2.6 | Crossroads | CR-S31-02 | Trouble - partial or voltage | P3 within 10 days | 2026-07-29 | 2026-08-02 | 2026-08-03 | Internal line |  | 13.47 | Completed | No
WO-26-008187 |  | Bayou | BY-S17-02 | Corrective maintenance | P3 within 10 days | 2026-07-30 | 2026-08-03 |  | Contract line | CT-03 |  | Open - awaiting outage | No
WO-26-008188 | 10.4 | Bayou | BY-S09-04 | Corrective maintenance | P4 planned | 2026-07-30 | 2026-08-14 | 2026-08-18 | Contract line | CT-04 | 2245.15 | Completed | No
WO-26-008189 |  | Bayou | BY-S16-01 | Meter exchange | P4 planned | 2026-07-30 | 2026-09-26 |  | Meter technician |  |  | Scheduled | No
WO-26-008190 | 1.4 | Bayou | BY-S13-03 | Meter exchange | P3 within 10 days | 2026-07-30 | 2026-08-02 | 2026-08-02 | Meter technician |  | 154.91 | Completed | No
WO-26-008191 | 0.7 | Bayou | BY-S21-02 | Meter exchange | P3 within 10 days | 2026-07-30 | 2026-08-05 | 2026-08-05 | Meter technician |  | 61.15 | Completed | No
WO-26-008192 | 5.5 | Bayou | BY-S10-01 | New service - small | P4 planned | 2026-07-30 | 2026-08-17 | 2026-08-19 | Contract line | CT-03 | 2322.78 | Completed | No
WO-26-008193 |  | Bayou | BY-S15-01 | New service - small | P4 planned | 2026-07-30 | 2026-09-05 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-008194 | 1.2 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-07-30 | 2026-07-31 | 2026-07-31 | Meter technician |  | 22.22 | Completed | No
WO-26-008195 | 1.5 | Bayou | BY-S09-04 | Service order - field | P3 within 10 days | 2026-07-30 | 2026-08-08 | 2026-08-10 | Meter technician |  | 1.21 | Completed | No
WO-26-008196 | 0.6 | Bayou | BY-S23-02 | Service order - field | P3 within 10 days | 2026-07-30 | 2026-08-07 | 2026-08-07 | Meter technician |  | 24.36 | Completed | No
WO-26-008197 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-30 | 2026-07-31 | 2026-07-31 | Contract line | CT-03 | 295.52 | Completed | No
WO-26-008198 | 2.5 | Bayou | BY-S02-01 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 298.62 | Completed | No
WO-26-008199 | 4.9 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 0.05 | Completed | No
WO-26-008200 | 4.5 | Bayou | BY-S21-01 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 328.52 | Completed | No
WO-26-008201 | 2.9 | Bayou | BY-S23-02 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 207.06 | Completed | No
WO-26-008202 | 3.4 | Bayou | BY-S29-05 | Trouble - no power | P2 same day | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 228.15 | Completed | No
WO-26-008203 | 2.8 | Bayou | BY-S07-05 | Trouble - no power | P2 same day | 2026-07-30 | 2026-07-31 | 2026-07-31 | Troubleman |  | 339.18 | Completed | No
WO-26-008204 | 4.2 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 251.05 | Completed | No
WO-26-008205 | 4.9 | Bayou | BY-S22-01 | Trouble - partial or voltage | P2 same day | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 173.93 | Completed | No
WO-26-008206 | 0.7 | Crossroads | CR-S13-03 | Meter exchange | P3 within 10 days | 2026-07-30 | 2026-08-09 | 2026-08-09 | Meter technician |  | 119.71 | Completed | No
WO-26-008207 | 1.4 | Crossroads | CR-S09-01 | Meter exchange | P3 within 10 days | 2026-07-30 | 2026-07-31 | 2026-08-01 | Meter technician |  | 83.59 | Completed | No
WO-26-008208 | 22.4 | Crossroads | CR-S11-01 | Pole replacement | P2 same day | 2026-07-30 | 2026-07-30 | 2026-07-30 | Internal line |  | 1212.28 | Completed | No
WO-26-008209 |  | Crossroads | CR-S13-03 | Preventive maintenance | P4 planned | 2026-07-30 | 2026-09-24 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008210 |  | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-07-30 | 2026-09-28 |  | Internal line |  |  | Scheduled | No
WO-26-008211 | 7.2 | Crossroads | CR-S05-01 | Preventive maintenance | P4 planned | 2026-07-30 | 2026-08-06 | 2026-08-07 | Internal line |  | 206.18 | Completed | No
WO-26-008212 |  | Crossroads | CR-S28-04 | Preventive maintenance | P4 planned | 2026-07-30 | 2026-09-11 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008213 | 5.9 | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-07-30 | 2026-08-25 | 2026-08-25 | Underground crew |  | 591.16 | Completed | No
WO-26-008214 | 1.7 | Crossroads | CR-S09-03 | Service order - field | P2 same day | 2026-07-30 | 2026-07-31 | 2026-07-31 | Meter technician |  | 28.37 | Completed | No
WO-26-008215 | 1.1 | Crossroads | CR-S26-02 | Service order - field | P2 same day | 2026-07-30 | 2026-07-30 | 2026-07-30 | Meter technician |  | 2.49 | Completed | No
WO-26-008216 | 0.6 | Crossroads | CR-S24-04 | Service order - field | P3 within 10 days | 2026-07-30 | 2026-08-01 | 2026-08-03 | Meter technician |  | 14.07 | Completed | No
WO-26-008217 | 1.6 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-07-30 | 2026-07-31 | 2026-07-31 | Meter technician |  | 6.66 | Completed | No
WO-26-008218 | 0.7 | Crossroads | CR-S30-02 | Service order - field | P3 within 10 days | 2026-07-30 | 2026-08-08 | 2026-08-08 | Meter technician |  | 12.93 | Completed | No
WO-26-008219 | 1 | Crossroads | CR-S09-02 | Service order - field | P3 within 10 days | 2026-07-30 | 2026-08-05 | 2026-08-05 | Meter technician |  | 18.54 | Completed | No
WO-26-008220 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-30 | 2026-08-07 | 2026-08-09 | Contract line | CT-02 | 402.96 | Completed | No
WO-26-008221 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-30 | 2026-08-06 | 2026-08-10 | Internal line |  | 159.13 | Completed | No
WO-26-008222 |  | Crossroads |  | Streetlight | P4 planned | 2026-07-30 | 2026-09-15 |  | Internal line |  |  | Scheduled | No
WO-26-008223 | 8.6 | Crossroads | CR-S22-04 | Transformer replacement | P3 within 10 days | 2026-07-30 | 2026-08-02 | 2026-08-02 | Internal line |  | 4567.41 | Completed | No
WO-26-008224 |  | Crossroads | CR-S07-03 | Transformer replacement | P2 same day | 2026-07-30 | 2026-07-31 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008225 | 7.4 | Crossroads | CR-S26-02 | Transformer replacement | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Internal line |  | 11452.32 | Completed | No
WO-26-008226 | 5.5 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 238.4 | Completed | No
WO-26-008227 | 4 | Crossroads | CR-S04-01 | Trouble - no power | P2 same day | 2026-07-30 | 2026-07-31 | 2026-07-31 | Troubleman |  | 314.34 | Completed | No
WO-26-008228 | 4.9 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Internal line |  | 130.55 | Completed | No
WO-26-008229 | 5.1 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Troubleman |  | 6.3 | Completed | No
WO-26-008230 | 3 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-07-30 | 2026-07-30 | 2026-07-30 | Internal line |  | 94.35 | Completed | No
WO-26-008231 | 4.7 | Crossroads | CR-S08-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-30 | 2026-08-01 | 2026-08-03 | Troubleman |  | 104.69 | Completed | No
WO-26-008232 |  | Bayou | BY-S23-01 | Corrective maintenance | P3 within 10 days | 2026-07-31 | 2026-08-06 |  | Underground crew |  |  | Cancelled | No
WO-26-008233 | 3.5 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-07-31 | 2026-08-05 | 2026-08-07 | Internal line |  | 1313.66 | Completed | No
WO-26-008234 |  | Bayou | BY-S14-01 | Meter exchange | P4 planned | 2026-07-31 | 2026-09-16 |  | Meter technician |  |  | Scheduled | No
WO-26-008235 | 1 | Bayou | BY-S30-01 | Meter exchange | P3 within 10 days | 2026-07-31 | 2026-08-06 | 2026-08-10 | Meter technician |  | 158.28 | Completed | No
WO-26-008236 |  | Bayou | BY-S10-02 | Meter exchange | P4 planned | 2026-07-31 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-008237 | 0.5 | Bayou | BY-S02-01 | Meter exchange | P4 planned | 2026-07-31 | 2026-08-08 | 2026-08-08 | Meter technician |  | 176.85 | Completed | No
WO-26-008238 | 6.7 | Bayou | BY-S25-03 | Preventive maintenance | P4 planned | 2026-07-31 | 2026-08-09 | 2026-08-10 | Internal line |  | 100.62 | Completed | No
WO-26-008239 | 4.4 | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-07-31 | 2026-08-10 | 2026-08-10 | Internal line |  | 485.83 | Completed | No
WO-26-008240 | 0.6 | Bayou | BY-S29-02 | Service order - field | P2 same day | 2026-07-31 | 2026-08-01 | 2026-08-01 | Meter technician |  | 27.96 | Completed | No
WO-26-008241 | 1.5 | Bayou | BY-S10-04 | Service order - field | P2 same day | 2026-07-31 | 2026-08-01 | 2026-08-01 | Meter technician |  | 16.7 | Completed | No
WO-26-008242 | 3 | Bayou |  | Streetlight | P3 within 10 days | 2026-07-31 | 2026-08-07 | 2026-08-07 | Internal line |  | 253.37 | Completed | No
WO-26-008243 |  | Bayou | BY-S29-04 | Transformer replacement | P2 same day | 2026-07-31 | 2026-08-01 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008244 | 12.9 | Bayou | BY-S12-02 | Transformer replacement | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Internal line |  | 4910.91 | Completed | No
WO-26-008245 | 9.8 | Bayou | BY-S05-02 | Transformer replacement | P3 within 10 days | 2026-07-31 | 2026-08-03 | 2026-08-03 | Contract line | CT-03 | 11086.18 | Completed | No
WO-26-008246 | 6.4 | Bayou | BY-S29-01 | Transformer replacement | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Internal line |  | 6882.16 | Completed | No
WO-26-008247 | 2.9 | Bayou | BY-S18-07 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 200.47 | Completed | No
WO-26-008248 | 4.9 | Bayou | BY-S20-01 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 107.71 | Completed | No
WO-26-008249 | 4.4 | Bayou | BY-S17-01 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 202.89 | Completed | No
WO-26-008250 | 4.1 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Internal line |  | 307.77 | Completed | No
WO-26-008251 | 3.3 | Bayou | BY-S06-01 | Trouble - partial or voltage | P3 within 10 days | 2026-07-31 | 2026-08-07 | 2026-08-07 | Troubleman |  | 11.8 | Completed | No
WO-26-008252 | 2.8 | Bayou | BY-S07-05 | Trouble - partial or voltage | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 222.34 | Completed | No
WO-26-008253 | 4.5 | Bayou | BY-S19-02 | Trouble - partial or voltage | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 244 | Completed | No
WO-26-008254 | 7.4 | Crossroads | CR-S01-01 | Corrective maintenance | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Contract line | CT-02 | 345.23 | Completed | No
WO-26-008255 |  | Crossroads | CR-S27-04 | Corrective maintenance | P4 planned | 2026-07-31 | 2026-09-15 |  | Underground crew |  |  | Scheduled | No
WO-26-008256 | 3.9 | Crossroads | CR-S22-02 | Corrective maintenance | P4 planned | 2026-07-31 | 2026-08-22 | 2026-08-23 | Internal line |  | 2167.51 | Completed | No
WO-26-008257 | 7.6 | Crossroads | CR-S20-03 | Corrective maintenance | P3 within 10 days | 2026-07-31 | 2026-08-02 | 2026-08-06 | Internal line |  | 1397.1 | Completed | No
WO-26-008258 |  | Crossroads | CR-S24-04 | New service - small | P4 planned | 2026-07-31 | 2026-09-18 |  | Internal line |  |  | Scheduled | No
WO-26-008259 |  | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-07-31 | 2026-09-09 |  | Internal line |  |  | Scheduled | No
WO-26-008260 |  | Crossroads | CR-S04-03 | Preventive maintenance | P4 planned | 2026-07-31 | 2026-08-11 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008261 | 2.8 | Crossroads | CR-S06-03 | Preventive maintenance | P4 planned | 2026-07-31 | 2026-08-08 | 2026-08-10 | Internal line |  | 323.77 | Completed | No
WO-26-008262 | 1.6 | Crossroads | CR-S14-01 | Service order - field | P3 within 10 days | 2026-07-31 | 2026-08-07 | 2026-08-08 | Meter technician |  | 18.3 | Completed | No
WO-26-008263 | 1.5 | Crossroads | CR-S29-03 | Service order - field | P3 within 10 days | 2026-07-31 | 2026-08-07 | 2026-08-09 | Meter technician |  | 2.08 | Completed | No
WO-26-008264 | 0.5 | Crossroads | CR-S08-05 | Service order - field | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Meter technician |  | 16.13 | Completed | No
WO-26-008265 | 0.7 | Crossroads | CR-S24-04 | Service order - field | P2 same day | 2026-07-31 | 2026-08-01 | 2026-08-01 | Meter technician |  | 23.63 | Completed | No
WO-26-008266 | 1.7 | Crossroads | CR-S17-01 | Service order - field | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Meter technician |  | 8.53 | Completed | No
WO-26-008267 | 2.8 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-31 | 2026-08-09 | 2026-08-13 | Contract line | CT-01 | 276.58 | Completed | No
WO-26-008268 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-07-31 | 2026-08-01 | 2026-08-01 | Contract line | CT-01 | 413.71 | Completed | No
WO-26-008269 | 8.1 | Crossroads | CR-S10-03 | Transformer replacement | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Internal line |  | 4581.15 | Completed | No
WO-26-008270 | 12 | Crossroads | CR-S04-03 | Transformer replacement | P3 within 10 days | 2026-07-31 | 2026-08-04 | 2026-08-04 | Internal line |  | 5612.1 | Completed | No
WO-26-008271 | 10 | Crossroads | CR-S09-03 | Transformer replacement | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Contract line | CT-01 | 3971.53 | Completed | No
WO-26-008272 | 4.3 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Internal line |  | 215.57 | Completed | No
WO-26-008273 | 3.7 | Crossroads | CR-S20-05 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 119.29 | Completed | No
WO-26-008274 | 4.2 | Crossroads | CR-S16-02 | Trouble - no power | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 301.92 | Completed | No
WO-26-008275 | 2.7 | Crossroads | CR-S21-01 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Internal line |  | 166.75 | Completed | No
WO-26-008276 | 4.6 | Crossroads | CR-S12-02 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 135.71 | Completed | No
WO-26-008277 | 3.9 | Crossroads | CR-S05-06 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 235.18 | Completed | No
WO-26-008278 | 4.8 | Crossroads | CR-S13-01 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 106.9 | Completed | No
WO-26-008279 | 3.9 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 110.03 | Completed | No
WO-26-008280 | 4.9 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 283.32 | Completed | No
WO-26-008281 | 3.3 | Crossroads | CR-S28-03 | Trouble - no power | P1 emergency | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 126.02 | Completed | No
WO-26-008282 | 2.8 | Crossroads | CR-S27-03 | Trouble - partial or voltage | P3 within 10 days | 2026-07-31 | 2026-08-05 | 2026-08-05 | Troubleman |  | 80.05 | Completed | No
WO-26-008283 | 4.5 | Crossroads | CR-S24-03 | Trouble - partial or voltage | P2 same day | 2026-07-31 | 2026-07-31 | 2026-07-31 | Troubleman |  | 116.35 | Completed | No
WO-26-008284 | 1 | Bayou | BY-S17-03 | Service order - field | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Meter technician |  | 5.94 | Completed | No
WO-26-008285 | 1.8 | Bayou | BY-S04-02 | Service order - field | P2 same day | 2026-08-01 | 2026-08-01 | 2026-08-01 | Meter technician |  | 4.64 | Completed | No
WO-26-008286 | 9.3 | Bayou | BY-S27-01 | Transformer replacement | P1 emergency | 2026-08-01 | 2026-08-01 | 2026-08-01 | Contract line | CT-04 | 7816.35 | Completed | No
WO-26-008287 | 13.2 | Bayou | BY-S14-02 | Transformer replacement | P2 same day | 2026-08-01 | 2026-08-01 | 2026-08-01 | Internal line |  | 5315.61 | Completed | No
WO-26-008288 | 3.2 | Bayou | BY-S24-03 | Trouble - no power | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Troubleman |  | 273.71 | Completed | No
WO-26-008289 | 3.5 | Bayou | BY-S26-04 | Trouble - no power | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Internal line |  | 9.32 | Completed | No
WO-26-008290 |  | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-08-01 | 2026-08-01 |  | Troubleman |  |  | Cancelled | No
WO-26-008291 | 4.8 | Bayou | BY-S21-03 | Trouble - no power | P1 emergency | 2026-08-01 | 2026-08-01 | 2026-08-01 | Troubleman |  | 188.14 | Completed | No
WO-26-008292 | 4.6 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-08-01 | 2026-08-01 | 2026-08-01 | Troubleman |  | 347.26 | Completed | No
WO-26-008293 | 3.9 | Bayou | BY-S25-01 | Trouble - no power | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Troubleman |  | 194.62 | Completed | No
WO-26-008294 | 2 | Bayou | BY-S19-02 | Trouble - partial or voltage | P2 same day | 2026-08-01 | 2026-08-01 | 2026-08-01 | Troubleman |  | 17.39 | Completed | No
WO-26-008295 | 5.9 | Crossroads | CR-S15-02 | Trouble - no power | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Troubleman |  | 203.26 | Completed | No
WO-26-008296 | 4.8 | Crossroads | CR-S16-04 | Trouble - no power | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Troubleman |  | 26.89 | Completed | No
WO-26-008297 | 5.3 | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-08-01 | 2026-08-01 | 2026-08-01 | Troubleman |  | 213.39 | Completed | No
WO-26-008298 | 5.3 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-08-01 | 2026-08-01 | 2026-08-01 | Troubleman |  | 268.38 | Completed | No
WO-26-008299 | 4.3 | Crossroads | CR-S04-06 | Trouble - no power | P2 same day | 2026-08-01 | 2026-08-01 | 2026-08-01 | Troubleman |  | 153.06 | Completed | No
WO-26-008300 | 5.8 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-08-01 | 2026-08-01 | 2026-08-01 | Internal line |  | 321.05 | Completed | No
WO-26-008301 | 2.7 | Crossroads | CR-S24-03 | Trouble - partial or voltage | P2 same day | 2026-08-01 | 2026-08-02 | 2026-08-02 | Troubleman |  | 21.8 | Completed | No
WO-26-008302 | 0.6 | Bayou | BY-S26-06 | Service order - field | P2 same day | 2026-08-02 | 2026-08-03 | 2026-08-03 | Meter technician |  | 29.18 | Completed | No
WO-26-008303 |  | Bayou | BY-S01-01 | Transformer replacement | P1 emergency | 2026-08-02 | 2026-08-02 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008304 | 5.5 | Bayou | BY-S14-02 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 248.19 | Completed | No
WO-26-008305 | 4.4 | Bayou | BY-S04-01 | Trouble - no power | P2 same day | 2026-08-02 | 2026-08-03 | 2026-08-03 | Internal line |  | 77.81 | Completed | No
WO-26-008306 | 3.4 | Bayou | BY-S28-02 | Trouble - no power | P2 same day | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 280.28 | Completed | No
WO-26-008307 | 2.7 | Bayou | BY-S26-05 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 344.38 | Completed | No
WO-26-008308 | 0.8 | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-08-02 | 2026-08-03 | 2026-08-03 | Meter technician |  | 27.85 | Completed | No
WO-26-008309 |  | Crossroads | CR-S12-01 | Transformer replacement | P1 emergency | 2026-08-02 | 2026-08-02 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-008310 | 11.3 | Crossroads | CR-S27-02 | Transformer replacement | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Internal line |  | 5377.71 | Completed | No
WO-26-008311 | 2.2 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 21.3 | Completed | No
WO-26-008312 | 4.2 | Crossroads | CR-S04-05 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 307.28 | Completed | No
WO-26-008313 | 5.2 | Crossroads | CR-S08-03 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Internal line |  | 45.39 | Completed | No
WO-26-008314 | 3.6 | Crossroads | CR-S04-03 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 166.25 | Completed | No
WO-26-008315 | 3.5 | Crossroads | CR-S32-05 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 144.55 | Completed | No
WO-26-008316 | 2.6 | Crossroads | CR-S16-05 | Trouble - no power | P2 same day | 2026-08-02 | 2026-08-03 | 2026-08-03 | Troubleman |  | 349.96 | Completed | No
WO-26-008317 | 5.4 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 76.75 | Completed | No
WO-26-008318 | 3.9 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 16.81 | Completed | No
WO-26-008319 | 3.4 | Crossroads | CR-S24-01 | Trouble - partial or voltage | P2 same day | 2026-08-02 | 2026-08-03 | 2026-08-03 | Troubleman |  | 99.36 | Completed | No
WO-26-008320 | 1.9 | Crossroads | CR-S08-02 | Trouble - partial or voltage | P2 same day | 2026-08-02 | 2026-08-02 | 2026-08-02 | Troubleman |  | 133.18 | Completed | No
WO-26-008321 |  | Bayou | BY-S21-03 | Corrective maintenance | P4 planned | 2026-08-03 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-008322 | 6.3 | Bayou | BY-S29-04 | Corrective maintenance | P3 within 10 days | 2026-08-03 | 2026-08-05 | 2026-08-05 | Internal line |  | 1754.79 | Completed | No
WO-26-008323 | 10 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-08-03 | 2026-08-12 | 2026-08-12 | Internal line |  | 466.47 | Completed | No
WO-26-008324 | 4.7 | Bayou | BY-S19-01 | Corrective maintenance | P2 same day | 2026-08-03 | 2026-08-03 | 2026-08-03 | Internal line |  | 1863.57 | Completed | No
WO-26-008325 | 1.2 | Bayou | BY-S03-02 | Meter exchange | P4 planned | 2026-08-03 | 2026-08-10 | 2026-08-14 | Meter technician |  | 92.97 | Completed | No
WO-26-008326 | 0.9 | Bayou | BY-S09-04 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-08 | 2026-08-09 | Meter technician |  | 168.57 | Completed | No
WO-26-008327 | 1.5 | Bayou | BY-S16-01 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-10 | 2026-08-14 | Meter technician |  | 139.28 | Completed | No
WO-26-008328 | 0.7 | Bayou | BY-S23-01 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-13 | 2026-08-13 | Meter technician |  | 116.72 | Completed | No
WO-26-008329 | 1.2 | Bayou | BY-S08-01 | Meter exchange | P4 planned | 2026-08-03 | 2026-08-20 | 2026-08-22 | Meter technician |  | 101.99 | Completed | No
WO-26-008330 | 1.2 | Bayou | BY-S13-04 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-06 | 2026-08-10 | Meter technician |  | 161.96 | Completed | No
WO-26-008331 | 0.8 | Bayou | BY-S19-02 | Meter exchange | P4 planned | 2026-08-03 | 2026-08-14 | 2026-08-16 | Meter technician |  | 153.71 | Completed | No
WO-26-008332 | 1.4 | Bayou | BY-S23-01 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-06 | 2026-08-06 | Meter technician |  | 172.74 | Completed | No
WO-26-008333 | 1.1 | Bayou | BY-S04-02 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-10 | 2026-08-10 | Meter technician |  | 112.64 | Completed | No
WO-26-008334 | 12 | Bayou | BY-S22-02 | Pole replacement | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Contract line | CT-04 | 2043.42 | Completed | No
WO-26-008335 | 5.3 | Bayou | BY-S17-01 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-08-21 | 2026-08-21 | Contract line | CT-04 | 306.35 | Completed | No
WO-26-008336 |  | Bayou | BY-S26-03 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-10-02 |  | Internal line |  |  | Scheduled | No
WO-26-008337 |  | Bayou | BY-S23-05 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-09-20 |  | Internal line |  |  | Scheduled | No
WO-26-008338 | 7 | Bayou | BY-S20-02 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-08-15 | 2026-08-15 | Underground crew |  | 281.76 | Completed | No
WO-26-008339 |  | Bayou | BY-S21-03 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-09-15 |  | Internal line |  |  | Scheduled | No
WO-26-008340 | 1.8 | Bayou | BY-S18-05 | Service order - field | P2 same day | 2026-08-03 | 2026-08-03 | 2026-08-03 | Meter technician |  | 39.94 | Completed | No
WO-26-008341 |  | Bayou |  | Streetlight | P4 planned | 2026-08-03 | 2026-09-16 |  | Internal line |  |  | Scheduled | No
WO-26-008342 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-03 | 2026-08-05 | 2026-08-05 | Internal line |  | 206.41 | Completed | No
WO-26-008343 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-03 | 2026-08-10 | 2026-08-11 | Contract line | CT-04 | 286.46 | Completed | No
WO-26-008344 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-08-03 | 2026-08-12 |  | Internal line |  |  | Cancelled | No
WO-26-008345 | 2.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-03 | 2026-08-04 | 2026-08-04 | Contract line | CT-04 | 379.3 | Completed | No
WO-26-008346 |  | Bayou | BY-S26-02 | Transformer replacement | P2 same day | 2026-08-03 | 2026-08-04 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008347 | 9.9 | Bayou | BY-S06-01 | Transformer replacement | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Internal line |  | 3804.98 | Completed | No
WO-26-008348 | 13.7 | Bayou | BY-S09-03 | Transformer replacement | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Contract line | CT-04 | 6031.84 | Completed | No
WO-26-008349 |  | Bayou | BY-S30-01 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 |  | Troubleman |  |  | Cancelled | No
WO-26-008350 | 5.3 | Bayou | BY-S16-04 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 208.73 | Completed | No
WO-26-008351 | 3.2 | Bayou | BY-S27-06 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 346.12 | Completed | No
WO-26-008352 | 3.9 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Troubleman |  | 306.46 | Completed | No
WO-26-008353 | 5 | Bayou | BY-S13-06 | Trouble - no power | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Troubleman |  | 174.79 | Completed | No
WO-26-008354 | 2.4 | Bayou | BY-S13-02 | Trouble - partial or voltage | P2 same day | 2026-08-03 | 2026-08-03 | 2026-08-03 | Internal line |  | 27.85 | Completed | No
WO-26-008355 | 3.8 | Bayou | BY-S24-03 | Trouble - partial or voltage | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Troubleman |  | 41.39 | Completed | No
WO-26-008356 | 3.1 | Crossroads | CR-S32-03 | Corrective maintenance | P3 within 10 days | 2026-08-03 | 2026-08-13 | 2026-08-14 | Underground crew |  | 238.96 | Completed | No
WO-26-008357 | 9.6 | Crossroads | CR-S08-05 | Corrective maintenance | P3 within 10 days | 2026-08-03 | 2026-08-06 | 2026-08-07 | Underground crew |  | 441.39 | Completed | No
WO-26-008358 | 7.8 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-08-03 | 2026-08-12 | 2026-08-13 | Contract line | CT-01 | 790.52 | Completed | No
WO-26-008359 | 9 | Crossroads | CR-S18-04 | Corrective maintenance | P3 within 10 days | 2026-08-03 | 2026-08-05 | 2026-08-07 | Underground crew |  | 1492.23 | Completed | No
WO-26-008360 |  | Crossroads | CR-S20-05 | Meter exchange | P4 planned | 2026-08-03 | 2026-10-02 |  | Meter technician |  |  | Scheduled | No
WO-26-008361 |  | Crossroads | CR-S09-01 | Meter exchange | P4 planned | 2026-08-03 | 2026-09-15 |  | Meter technician |  |  | Scheduled | No
WO-26-008362 | 1.2 | Crossroads | CR-S05-01 | Meter exchange | P3 within 10 days | 2026-08-03 | 2026-08-09 | 2026-08-10 | Meter technician |  | 141.56 | Completed | No
WO-26-008363 |  | Crossroads | CR-S13-01 | Pole replacement | P3 within 10 days | 2026-08-03 | 2026-08-10 |  | Contract line | CT-01 |  | Open - awaiting material | No
WO-26-008364 |  | Crossroads | CR-S31-02 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-09-02 |  | Underground crew |  |  | Scheduled | No
WO-26-008365 | 6.9 | Crossroads | CR-S31-01 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-08-18 | 2026-08-18 | Underground crew |  | 394.61 | Completed | No
WO-26-008366 |  | Crossroads | CR-S32-02 | Preventive maintenance | P4 planned | 2026-08-03 | 2026-09-29 |  | Underground crew |  |  | Scheduled | No
WO-26-008367 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-03 | 2026-10-02 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008368 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-03 | 2026-09-10 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008369 |  | Crossroads | CR-S21-03 | Transformer replacement | P3 within 10 days | 2026-08-03 | 2026-08-04 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008370 |  | Crossroads | CR-S08-04 | Transformer replacement | P1 emergency | 2026-08-03 | 2026-08-03 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008371 | 3.5 | Crossroads | CR-S27-01 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 323.7 | Completed | No
WO-26-008372 | 5.8 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 69.1 | Completed | No
WO-26-008373 | 3.4 | Crossroads | CR-S31-02 | Trouble - no power | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Internal line |  | 131.46 | Completed | No
WO-26-008374 | 5.2 | Crossroads | CR-S31-02 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 91.14 | Completed | No
WO-26-008375 | 5.2 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 251.48 | Completed | No
WO-26-008376 | 5.4 | Crossroads | CR-S22-02 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 307.58 | Completed | No
WO-26-008377 | 4.7 | Crossroads | CR-S25-01 | Trouble - no power | P1 emergency | 2026-08-03 | 2026-08-03 | 2026-08-03 | Troubleman |  | 53.88 | Completed | No
WO-26-008378 | 3.1 | Crossroads | CR-S27-02 | Trouble - no power | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Internal line |  | 95.63 | Completed | No
WO-26-008379 | 3.3 | Crossroads | CR-S18-06 | Trouble - partial or voltage | P2 same day | 2026-08-03 | 2026-08-04 | 2026-08-04 | Troubleman |  | 215.73 | Completed | No
WO-26-008380 | 5.4 | Bayou | BY-S29-04 | Corrective maintenance | P3 within 10 days | 2026-08-04 | 2026-08-13 | 2026-08-17 | Internal line |  | 351.01 | Completed | No
WO-26-008381 | 4.5 | Bayou | BY-S16-04 | Corrective maintenance | P3 within 10 days | 2026-08-04 | 2026-08-12 | 2026-08-12 | Contract line | CT-03 | 1305.87 | Completed | No
WO-26-008382 | 4 | Bayou | BY-S13-01 | Corrective maintenance | P3 within 10 days | 2026-08-04 | 2026-08-07 | 2026-08-08 | Internal line |  | 1780.06 | Completed | No
WO-26-008383 |  | Bayou | BY-S26-06 | Corrective maintenance | P4 planned | 2026-08-04 | 2026-09-27 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-008384 |  | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-08-04 | 2026-09-16 |  | Underground crew |  |  | Scheduled | No
WO-26-008385 | 3.3 | Bayou | BY-S30-03 | Corrective maintenance | P3 within 10 days | 2026-08-04 | 2026-08-13 | 2026-08-21 | Internal line |  | 1877.65 | Completed | No
WO-26-008386 |  | Bayou | BY-S30-01 | Meter exchange | P4 planned | 2026-08-04 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-008387 | 1 | Bayou | BY-S25-05 | Meter exchange | P4 planned | 2026-08-04 | 2026-08-24 | 2026-08-24 | Meter technician |  | 177.53 | Completed | No
WO-26-008388 |  | Bayou | BY-S06-01 | Meter exchange | P4 planned | 2026-08-04 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-008389 | 0.5 | Bayou | BY-S13-01 | Meter exchange | P3 within 10 days | 2026-08-04 | 2026-08-07 | 2026-08-08 | Meter technician |  | 78.17 | Completed | No
WO-26-008390 | 1.3 | Bayou | BY-S06-03 | Meter exchange | P3 within 10 days | 2026-08-04 | 2026-08-12 | 2026-08-12 | Meter technician |  | 108.75 | Completed | No
WO-26-008391 |  | Bayou | BY-S24-05 | New service - small | P4 planned | 2026-08-04 | 2026-09-02 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-008392 |  | Bayou | BY-S08-01 | Preventive maintenance | P4 planned | 2026-08-04 | 2026-09-14 |  | Underground crew |  |  | Scheduled | No
WO-26-008393 |  | Bayou | BY-S07-04 | Preventive maintenance | P4 planned | 2026-08-04 | 2026-09-28 |  | Internal line |  |  | Scheduled | No
WO-26-008394 | 1.2 | Bayou | BY-S18-05 | Service order - field | P3 within 10 days | 2026-08-04 | 2026-08-10 | 2026-08-11 | Meter technician |  | 0.64 | Completed | No
WO-26-008395 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-04 | 2026-08-11 | 2026-08-12 | Contract line | CT-04 | 228.25 | Completed | No
WO-26-008396 | 7 | Bayou | BY-S10-04 | Transformer replacement | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Internal line |  | 4444.72 | Completed | No
WO-26-008397 |  | Bayou | BY-S16-06 | Transformer replacement | P2 same day | 2026-08-04 | 2026-08-04 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008398 |  | Bayou | BY-S07-03 | Transformer replacement | P1 emergency | 2026-08-04 | 2026-08-04 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008399 | 6.7 | Bayou | BY-S06-01 | Transformer replacement | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Internal line |  | 5631.25 | Completed | No
WO-26-008400 | 12.4 | Bayou | BY-S21-04 | Transformer replacement | P3 within 10 days | 2026-08-04 | 2026-08-08 | 2026-08-10 | Contract line | CT-04 | 5533.59 | Completed | No
WO-26-008401 | 13 | Bayou | BY-S18-04 | Transformer replacement | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Internal line |  | 10772.2 | Completed | No
WO-26-008402 | 11.7 | Bayou | BY-S19-01 | Transformer replacement | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Internal line |  | 4909.36 | Completed | No
WO-26-008403 | 2.1 | Bayou | BY-S17-04 | Trouble - no power | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Troubleman |  | 131.31 | Completed | No
WO-26-008404 | 5.6 | Bayou | BY-S09-04 | Trouble - no power | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Troubleman |  | 236.66 | Completed | No
WO-26-008405 | 4.8 | Bayou | BY-S23-01 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 190.18 | Completed | No
WO-26-008406 | 5.5 | Bayou | BY-S19-01 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 238.85 | Completed | No
WO-26-008407 | 5.5 | Bayou | BY-S07-06 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 153.27 | Completed | No
WO-26-008408 | 2.3 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 198.69 | Completed | No
WO-26-008409 | 5.6 | Bayou | BY-S14-03 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 232.05 | Completed | No
WO-26-008410 | 6 | Bayou | BY-S18-02 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Internal line |  | 53.27 | Completed | No
WO-26-008411 | 4.4 | Bayou | BY-S07-01 | Trouble - partial or voltage | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Internal line |  | 220.83 | Completed | No
WO-26-008412 | 4 | Bayou | BY-S23-01 | Trouble - partial or voltage | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Internal line |  | 145.02 | Completed | No
WO-26-008413 |  | Crossroads | CR-S09-05 | Corrective maintenance | P4 planned | 2026-08-04 | 2026-09-30 |  | Internal line |  |  | Scheduled | No
WO-26-008414 | 7.7 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-08-04 | 2026-08-07 | 2026-08-15 | Contract line | CT-02 | 928.2 | Completed | No
WO-26-008415 | 10.7 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-08-04 | 2026-08-11 | 2026-08-15 | Internal line |  | 1724.13 | Completed | No
WO-26-008416 |  | Crossroads | CR-S22-03 | Meter exchange | P4 planned | 2026-08-04 | 2026-09-14 |  | Meter technician |  |  | Scheduled | No
WO-26-008417 | 0.5 | Crossroads | CR-S05-04 | Meter exchange | P3 within 10 days | 2026-08-04 | 2026-08-09 | 2026-08-09 | Meter technician |  | 71.41 | Completed | No
WO-26-008418 | 7.7 | Crossroads | CR-S30-02 | New service - small | P3 within 10 days | 2026-08-04 | 2026-08-13 | 2026-08-14 | Contract line | CT-01 | 322.34 | Completed | No
WO-26-008419 | 15.5 | Crossroads | CR-S21-03 | Pole replacement | P3 within 10 days | 2026-08-04 | 2026-08-12 | 2026-08-13 | Internal line |  | 2621.38 | Completed | No
WO-26-008420 |  | Crossroads | CR-S22-01 | Preventive maintenance | P4 planned | 2026-08-04 | 2026-10-02 |  | Underground crew |  |  | Scheduled | No
WO-26-008421 | 1.2 | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-08-04 | 2026-08-05 | 2026-08-05 | Meter technician |  | 21.81 | Completed | No
WO-26-008422 | 1.1 | Crossroads | CR-S14-03 | Service order - field | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Meter technician |  | 23.67 | Completed | No
WO-26-008423 | 0.9 | Crossroads | CR-S23-03 | Service order - field | P2 same day | 2026-08-04 | 2026-08-05 | 2026-08-05 | Meter technician |  | 36.05 | Completed | No
WO-26-008424 | 0.9 | Crossroads | CR-S10-03 | Service order - field | P3 within 10 days | 2026-08-04 | 2026-08-06 | 2026-08-10 | Meter technician |  | 12.26 | Completed | No
WO-26-008425 | 2 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-04 | 2026-08-05 | 2026-08-06 | Contract line | CT-02 | 228.77 | Completed | No
WO-26-008426 | 1.4 | Crossroads |  | Streetlight | P4 planned | 2026-08-04 | 2026-08-22 | 2026-08-24 | Contract line | CT-02 | 124.57 | Completed | No
WO-26-008427 |  | Crossroads | CR-S05-02 | Transformer replacement | P1 emergency | 2026-08-04 | 2026-08-04 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-008428 | 12.9 | Crossroads | CR-S25-06 | Transformer replacement | P3 within 10 days | 2026-08-04 | 2026-08-09 | 2026-08-09 | Internal line |  | 3658.21 | Completed | No
WO-26-008429 | 6 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 313.91 | Completed | No
WO-26-008430 | 2.5 | Crossroads | CR-S28-04 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Internal line |  | 12.9 | Completed | No
WO-26-008431 | 3.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Internal line |  | 138.29 | Completed | No
WO-26-008432 | 2.6 | Crossroads | CR-S08-06 | Trouble - no power | P1 emergency | 2026-08-04 | 2026-08-04 | 2026-08-04 | Internal line |  | 228.56 | Completed | No
WO-26-008433 | 3.4 | Crossroads | CR-S17-01 | Trouble - partial or voltage | P2 same day | 2026-08-04 | 2026-08-04 | 2026-08-04 | Troubleman |  | 12.28 | Completed | No
WO-26-008434 |  | Bayou | BY-S02-01 | Corrective maintenance | P4 planned | 2026-08-05 | 2026-09-26 |  | Internal line |  |  | Scheduled | No
WO-26-008435 | 1.5 | Bayou | BY-S28-03 | Meter exchange | P3 within 10 days | 2026-08-05 | 2026-08-11 | 2026-08-11 | Meter technician |  | 83.38 | Completed | No
WO-26-008436 | 0.7 | Bayou | BY-S29-05 | Meter exchange | P3 within 10 days | 2026-08-05 | 2026-08-08 | 2026-08-08 | Meter technician |  | 136.34 | Completed | No
WO-26-008437 |  | Bayou | BY-S10-01 | New service - small | P4 planned | 2026-08-05 | 2026-09-26 |  | Underground crew |  |  | Scheduled | No
WO-26-008438 | 15.1 | Bayou | BY-S23-01 | Pole replacement | P4 planned | 2026-08-05 | 2026-08-27 | 2026-08-27 | Contract line | CT-04 | 1401.78 | Completed | No
WO-26-008439 |  | Bayou | BY-S29-05 | Pole replacement | P3 within 10 days | 2026-08-05 | 2026-08-15 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008440 | 15.4 | Bayou | BY-S27-03 | Pole replacement | P3 within 10 days | 2026-08-05 | 2026-08-06 | 2026-08-14 | Contract line | CT-03 | 2370.51 | Completed | No
WO-26-008441 | 12.5 | Bayou | BY-S07-03 | Pole replacement | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Contract line | CT-04 | 1464.42 | Completed | No
WO-26-008442 |  | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-08-05 | 2026-09-04 |  | Internal line |  |  | Scheduled | No
WO-26-008443 |  | Bayou | BY-S25-05 | Preventive maintenance | P4 planned | 2026-08-05 | 2026-09-27 |  | Internal line |  |  | Scheduled | No
WO-26-008444 |  | Bayou | BY-S24-04 | Preventive maintenance | P4 planned | 2026-08-05 | 2026-09-06 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008445 | 1.1 | Bayou | BY-S10-01 | Service order - field | P3 within 10 days | 2026-08-05 | 2026-08-11 | 2026-08-11 | Meter technician |  | 24.41 | Completed | No
WO-26-008446 | 0.7 | Bayou | BY-S30-01 | Service order - field | P3 within 10 days | 2026-08-05 | 2026-08-08 | 2026-08-08 | Meter technician |  | 16.8 | Completed | No
WO-26-008447 |  | Bayou |  | Streetlight | P4 planned | 2026-08-05 | 2026-10-01 |  | Internal line |  |  | Scheduled | No
WO-26-008448 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-05 | 2026-08-06 | 2026-08-08 | Contract line | CT-04 | 368.56 | Completed | No
WO-26-008449 | 11.8 | Bayou | BY-S09-02 | Transformer replacement | P1 emergency | 2026-08-05 | 2026-08-05 | 2026-08-05 | Internal line |  | 10005.18 | Completed | No
WO-26-008450 |  | Bayou | BY-S15-06 | Transformer replacement | P3 within 10 days | 2026-08-05 | 2026-08-07 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008451 | 3.7 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-08-05 | 2026-08-05 | 2026-08-05 | Troubleman |  | 79.62 | Completed | No
WO-26-008452 | 2.5 | Bayou | BY-S18-04 | Trouble - no power | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Troubleman |  | 7.01 | Completed | No
WO-26-008453 |  | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-08-05 | 2026-08-05 |  | Troubleman |  |  | Cancelled | No
WO-26-008454 | 3.5 | Bayou | BY-S26-03 | Trouble - no power | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Internal line |  | 208.06 | Completed | No
WO-26-008455 | 2.7 | Bayou | BY-S23-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-05 | 2026-08-07 | 2026-08-09 | Internal line |  | 247.36 | Completed | No
WO-26-008456 | 3.7 | Bayou | BY-S15-04 | Trouble - partial or voltage | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Troubleman |  | 71.46 | Completed | No
WO-26-008457 | 3.7 | Bayou | BY-S30-03 | Trouble - partial or voltage | P2 same day | 2026-08-05 | 2026-08-05 | 2026-08-05 | Troubleman |  | 68.1 | Completed | No
WO-26-008458 | 9.4 | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-08-05 | 2026-08-08 | 2026-08-08 | Underground crew |  | 1425.57 | Completed | No
WO-26-008459 | 3.6 | Crossroads | CR-S09-01 | Corrective maintenance | P3 within 10 days | 2026-08-05 | 2026-08-10 | 2026-08-12 | Underground crew |  | 123.71 | Completed | No
WO-26-008460 | 1 | Crossroads | CR-S15-01 | Meter exchange | P3 within 10 days | 2026-08-05 | 2026-08-13 | 2026-08-14 | Meter technician |  | 152.78 | Completed | No
WO-26-008461 | 13.5 | Crossroads | CR-S08-06 | New service - small | P3 within 10 days | 2026-08-05 | 2026-08-13 | 2026-08-17 | Contract line | CT-01 | 783.71 | Completed | No
WO-26-008462 |  | Crossroads | CR-S14-01 | Preventive maintenance | P4 planned | 2026-08-05 | 2026-10-02 |  | Internal line |  |  | Scheduled | No
WO-26-008463 | 4.5 | Crossroads | CR-S30-02 | Preventive maintenance | P4 planned | 2026-08-05 | 2026-08-30 | 2026-08-30 | Underground crew |  | 61.97 | Completed | No
WO-26-008464 | 0.8 | Crossroads | CR-S05-02 | Service order - field | P3 within 10 days | 2026-08-05 | 2026-08-08 | 2026-08-10 | Meter technician |  | 31.29 | Completed | No
WO-26-008465 | 1.5 | Crossroads | CR-S07-01 | Service order - field | P3 within 10 days | 2026-08-05 | 2026-08-13 | 2026-08-13 | Meter technician |  | 22.77 | Completed | No
WO-26-008466 | 1.3 | Crossroads | CR-S04-06 | Service order - field | P3 within 10 days | 2026-08-05 | 2026-08-15 | 2026-08-15 | Meter technician |  | 36.12 | Completed | No
WO-26-008467 | 1.7 | Crossroads | CR-S12-01 | Service order - field | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Meter technician |  | 23.54 | Completed | No
WO-26-008468 | 1.7 | Crossroads | CR-S25-03 | Service order - field | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Meter technician |  | 8.44 | Completed | No
WO-26-008469 | 8.2 | Crossroads | CR-S30-06 | Transformer replacement | P3 within 10 days | 2026-08-05 | 2026-08-11 | 2026-08-11 | Internal line |  | 4606.97 | Completed | No
WO-26-008470 | 11.5 | Crossroads | CR-S28-04 | Transformer replacement | P1 emergency | 2026-08-05 | 2026-08-05 | 2026-08-05 | Internal line |  | 4229.19 | Completed | No
WO-26-008471 | 2.2 | Crossroads | CR-S20-04 | Trouble - no power | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Internal line |  | 230.29 | Completed | No
WO-26-008472 | 3.9 | Crossroads | CR-S10-03 | Trouble - no power | P1 emergency | 2026-08-05 | 2026-08-05 | 2026-08-05 | Troubleman |  | 295.85 | Completed | No
WO-26-008473 | 5.9 | Crossroads | CR-S23-03 | Trouble - no power | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Troubleman |  | 1.69 | Completed | No
WO-26-008474 | 4.1 | Crossroads | CR-S26-04 | Trouble - no power | P2 same day | 2026-08-05 | 2026-08-05 | 2026-08-05 | Troubleman |  | 167.16 | Completed | No
WO-26-008475 | 5.3 | Crossroads | CR-S17-03 | Trouble - no power | P2 same day | 2026-08-05 | 2026-08-06 | 2026-08-06 | Troubleman |  | 225.11 | Completed | No
WO-26-008476 | 3.5 | Crossroads | CR-S01-02 | Trouble - no power | P1 emergency | 2026-08-05 | 2026-08-05 | 2026-08-05 | Troubleman |  | 260.5 | Completed | No
WO-26-008477 | 3.5 | Crossroads | CR-S28-03 | Trouble - partial or voltage | P2 same day | 2026-08-05 | 2026-08-05 | 2026-08-05 | Troubleman |  | 30.86 | Completed | No
WO-26-008478 | 10.2 | Bayou | BY-S25-03 | Corrective maintenance | P3 within 10 days | 2026-08-06 | 2026-08-15 | 2026-08-16 | Internal line |  | 181.9 | Completed | No
WO-26-008479 | 8.3 | Bayou | BY-S21-02 | Corrective maintenance | P3 within 10 days | 2026-08-06 | 2026-08-13 | 2026-08-13 | Contract line | CT-04 | 1881.47 | Completed | No
WO-26-008480 | 1.1 | Bayou | BY-S02-01 | Meter exchange | P3 within 10 days | 2026-08-06 | 2026-08-07 | 2026-08-11 | Meter technician |  | 132.79 | Completed | No
WO-26-008481 |  | Bayou | BY-S27-06 | Meter exchange | P4 planned | 2026-08-06 | 2026-09-25 |  | Meter technician |  |  | Scheduled | No
WO-26-008482 | 1.3 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-08-06 | 2026-08-09 | 2026-08-09 | Meter technician |  | 101.2 | Completed | No
WO-26-008483 |  | Bayou | BY-S26-04 | New service - small | P4 planned | 2026-08-06 | 2026-09-12 |  | Underground crew |  |  | Scheduled | No
WO-26-008484 | 5.2 | Bayou | BY-S22-03 | New service - small | P4 planned | 2026-08-06 | 2026-08-22 | 2026-08-24 | Internal line |  | 2922.44 | Completed | No
WO-26-008485 | 12.3 | Bayou | BY-S06-02 | New service - small | P3 within 10 days | 2026-08-06 | 2026-08-09 | 2026-08-10 | Internal line |  | 3678.86 | Completed | No
WO-26-008486 |  | Bayou | BY-S23-02 | Preventive maintenance | P4 planned | 2026-08-06 | 2026-09-13 |  | Internal line |  |  | Scheduled | No
WO-26-008487 | 1 | Bayou | BY-S07-03 | Service order - field | P3 within 10 days | 2026-08-06 | 2026-08-12 | 2026-08-16 | Meter technician |  | 6.37 | Completed | No
WO-26-008488 | 0.6 | Bayou | BY-S21-01 | Service order - field | P3 within 10 days | 2026-08-06 | 2026-08-11 | 2026-08-11 | Meter technician |  | 12.9 | Completed | No
WO-26-008489 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-06 | 2026-08-15 | 2026-08-15 | Internal line |  | 60.69 | Completed | No
WO-26-008490 |  | Bayou | BY-S01-02 | Transformer replacement | P1 emergency | 2026-08-06 | 2026-08-06 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008491 | 9.7 | Bayou | BY-S21-04 | Transformer replacement | P1 emergency | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 8287.23 | Completed | No
WO-26-008492 | 7.7 | Bayou | BY-S22-03 | Transformer replacement | P2 same day | 2026-08-06 | 2026-08-07 | 2026-08-07 | Internal line |  | 3924.34 | Completed | No
WO-26-008493 | 10.6 | Bayou | BY-S25-01 | Transformer replacement | P2 same day | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 4290.44 | Completed | No
WO-26-008494 |  | Bayou | BY-S23-02 | Transformer replacement | P1 emergency | 2026-08-06 | 2026-08-06 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008495 | 6.8 | Bayou | BY-S25-01 | Transformer replacement | P2 same day | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 9409.98 | Completed | No
WO-26-008496 | 5.4 | Bayou | BY-S16-02 | Trouble - no power | P1 emergency | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 287.8 | Completed | No
WO-26-008497 | 3.5 | Bayou | BY-S18-05 | Trouble - no power | P1 emergency | 2026-08-06 | 2026-08-06 | 2026-08-06 | Troubleman |  | 245.99 | Completed | No
WO-26-008498 | 3.8 | Bayou | BY-S08-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-06 | 2026-08-13 | 2026-08-13 | Troubleman |  | 75.33 | Completed | No
WO-26-008499 | 3.7 | Bayou | BY-S26-02 | Trouble - partial or voltage | P2 same day | 2026-08-06 | 2026-08-07 | 2026-08-07 | Troubleman |  | 20.81 | Completed | No
WO-26-008500 | 3.4 | Bayou | BY-S19-04 | Trouble - partial or voltage | P3 within 10 days | 2026-08-06 | 2026-08-15 | 2026-08-16 | Troubleman |  | 70.49 | Completed | No
WO-26-008501 | 1 | Crossroads | CR-S24-04 | Meter exchange | P3 within 10 days | 2026-08-06 | 2026-08-09 | 2026-08-09 | Meter technician |  | 119.38 | Completed | No
WO-26-008502 | 0.5 | Crossroads | CR-S24-03 | Meter exchange | P3 within 10 days | 2026-08-06 | 2026-08-07 | 2026-08-07 | Meter technician |  | 92.67 | Completed | No
WO-26-008503 | 13.8 | Crossroads | CR-S12-01 | New service - small | P3 within 10 days | 2026-08-06 | 2026-08-13 | 2026-08-13 | Contract line | CT-02 | 2733.62 | Completed | No
WO-26-008504 | 19.1 | Crossroads | CR-S20-02 | Pole replacement | P2 same day | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 2287.83 | Completed | No
WO-26-008505 | 20.4 | Crossroads | CR-S20-01 | Pole replacement | P3 within 10 days | 2026-08-06 | 2026-08-07 | 2026-08-07 | Contract line | CT-01 | 1799.48 | Completed | No
WO-26-008506 |  | Crossroads | CR-S21-01 | Preventive maintenance | P4 planned | 2026-08-06 | 2026-09-20 |  | Internal line |  |  | Scheduled | No
WO-26-008507 | 6 | Crossroads | CR-S25-03 | Preventive maintenance | P4 planned | 2026-08-06 | 2026-08-18 | 2026-08-18 | Underground crew |  | 226.94 | Completed | No
WO-26-008508 | 6.3 | Crossroads | CR-S22-04 | Preventive maintenance | P4 planned | 2026-08-06 | 2026-08-30 | 2026-08-30 | Internal line |  | 111.57 | Completed | No
WO-26-008509 | 1.3 | Crossroads | CR-S21-03 | Service order - field | P2 same day | 2026-08-06 | 2026-08-07 | 2026-08-07 | Meter technician |  | 31.57 | Completed | No
WO-26-008510 | 1.4 | Crossroads | CR-S12-03 | Service order - field | P2 same day | 2026-08-06 | 2026-08-07 | 2026-08-07 | Meter technician |  | 14.5 | Completed | No
WO-26-008511 | 1.3 | Crossroads | CR-S30-04 | Service order - field | P3 within 10 days | 2026-08-06 | 2026-08-07 | 2026-08-07 | Meter technician |  | 19.27 | Completed | No
WO-26-008512 | 2.3 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-06 | 2026-08-12 | 2026-08-12 | Internal line |  | 175.08 | Completed | No
WO-26-008513 | 8.2 | Crossroads | CR-S13-02 | Transformer replacement | P1 emergency | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 10337.69 | Completed | No
WO-26-008514 | 7.9 | Crossroads | CR-S15-02 | Transformer replacement | P1 emergency | 2026-08-06 | 2026-08-06 | 2026-08-06 | Internal line |  | 7358.08 | Completed | No
WO-26-008515 | 2.5 | Crossroads | CR-S01-01 | Trouble - no power | P1 emergency | 2026-08-06 | 2026-08-06 | 2026-08-06 | Troubleman |  | 216.14 | Completed | No
WO-26-008516 | 4.1 | Crossroads | CR-S19-03 | Trouble - no power | P2 same day | 2026-08-06 | 2026-08-06 | 2026-08-06 | Troubleman |  | 267.93 | Completed | No
WO-26-008517 | 3.1 | Crossroads | CR-S20-02 | Trouble - no power | P2 same day | 2026-08-06 | 2026-08-07 | 2026-08-07 | Troubleman |  | 130.34 | Completed | No
WO-26-008518 | 4.9 | Crossroads | CR-S16-06 | Trouble - partial or voltage | P3 within 10 days | 2026-08-06 | 2026-08-08 | 2026-08-09 | Internal line |  | 240.11 | Completed | No
WO-26-008519 | 2.8 | Crossroads | CR-S21-03 | Trouble - partial or voltage | P3 within 10 days | 2026-08-06 | 2026-08-08 | 2026-08-09 | Internal line |  | 217.22 | Completed | No
WO-26-008520 | 5.8 | Bayou | BY-S24-04 | Corrective maintenance | P3 within 10 days | 2026-08-07 | 2026-08-15 | 2026-08-15 | Underground crew |  | 495.1 | Completed | No
WO-26-008521 | 8 | Bayou | BY-S25-05 | Corrective maintenance | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Internal line |  | 2109.73 | Completed | No
WO-26-008522 | 4.5 | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-08-07 | 2026-08-12 | 2026-08-20 | Underground crew |  | 485.71 | Completed | No
WO-26-008523 | 1 | Bayou | BY-S01-01 | Meter exchange | P4 planned | 2026-08-07 | 2026-08-26 | 2026-08-28 | Meter technician |  | 149.64 | Completed | No
WO-26-008524 |  | Bayou | BY-S08-03 | Meter exchange | P4 planned | 2026-08-07 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-008525 | 14.3 | Bayou | BY-S09-02 | New service - small | P3 within 10 days | 2026-08-07 | 2026-08-13 | 2026-08-13 | Underground crew |  | 2567.8 | Completed | No
WO-26-008526 |  | Bayou | BY-S06-02 | New service - small | P4 planned | 2026-08-07 | 2026-08-31 |  | Underground crew |  |  | Scheduled | No
WO-26-008527 |  | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-08-07 | 2026-09-14 |  | Internal line |  |  | Scheduled | No
WO-26-008528 |  | Bayou | BY-S04-01 | Preventive maintenance | P4 planned | 2026-08-07 | 2026-09-11 |  | Internal line |  |  | Scheduled | No
WO-26-008529 |  | Bayou | BY-S26-02 | Preventive maintenance | P4 planned | 2026-08-07 | 2026-09-20 |  | Underground crew |  |  | Scheduled | No
WO-26-008530 |  | Bayou | BY-S21-02 | Preventive maintenance | P4 planned | 2026-08-07 | 2026-08-31 |  | Contract line | CT-03 |  | Open - awaiting outage | No
WO-26-008531 | 1.4 | Bayou | BY-S15-01 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-08 | 2026-08-08 | Meter technician |  | 7.49 | Completed | No
WO-26-008532 | 0.7 | Bayou | BY-S03-01 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-11 | 2026-08-11 | Meter technician |  | 8.9 | Completed | No
WO-26-008533 | 1.5 | Bayou | BY-S25-02 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-12 | 2026-08-14 | Meter technician |  | 17.21 | Completed | No
WO-26-008534 | 1.1 | Bayou | BY-S18-04 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-15 | 2026-08-19 | Meter technician |  | 20.37 | Completed | No
WO-26-008535 | 1.8 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-08-07 | 2026-08-08 | 2026-08-08 | Meter technician |  | 34.94 | Completed | No
WO-26-008536 | 1 | Bayou | BY-S26-04 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-14 | 2026-08-14 | Meter technician |  | 35.24 | Completed | No
WO-26-008537 | 1.2 | Bayou | BY-S26-03 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-08 | 2026-08-09 | Meter technician |  | 17.46 | Completed | No
WO-26-008538 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-07 | 2026-08-08 | 2026-08-08 | Contract line | CT-04 | 449.66 | Completed | No
WO-26-008539 |  | Bayou |  | Streetlight | P4 planned | 2026-08-07 | 2026-09-21 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-008540 | 1.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-07 | 2026-08-15 | 2026-08-15 | Internal line |  | 280.49 | Completed | No
WO-26-008541 | 10 | Bayou | BY-S12-02 | Transformer replacement | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Contract line | CT-04 | 7170.54 | Completed | No
WO-26-008542 | 2.5 | Bayou | BY-S11-01 | Trouble - no power | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 30.03 | Completed | No
WO-26-008543 | 5.4 | Bayou | BY-S03-02 | Trouble - no power | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Internal line |  | 245.2 | Completed | No
WO-26-008544 | 3.4 | Bayou | BY-S23-02 | Trouble - no power | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 160.71 | Completed | No
WO-26-008545 | 2.1 | Bayou | BY-S25-05 | Trouble - no power | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 90.76 | Completed | No
WO-26-008546 | 2.3 | Bayou | BY-S13-03 | Trouble - no power | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 74.93 | Completed | No
WO-26-008547 | 4.7 | Bayou | BY-S29-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-07 | 2026-08-16 | 2026-08-20 | Troubleman |  | 183.26 | Completed | No
WO-26-008548 | 4.3 | Bayou | BY-S19-04 | Trouble - partial or voltage | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 187.13 | Completed | No
WO-26-008549 | 3.2 | Bayou | BY-S13-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-07 | 2026-08-10 | 2026-08-12 | Troubleman |  | 92.52 | Completed | No
WO-26-008550 | 3.2 | Bayou | BY-S20-01 | Trouble - partial or voltage | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 42.91 | Completed | No
WO-26-008551 | 6.3 | Crossroads | CR-S20-02 | Corrective maintenance | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Internal line |  | 332.51 | Completed | No
WO-26-008552 |  | Crossroads | CR-S19-03 | Corrective maintenance | P3 within 10 days | 2026-08-07 | 2026-08-14 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-008553 | 9.9 | Crossroads | CR-S30-05 | Corrective maintenance | P3 within 10 days | 2026-08-07 | 2026-08-12 | 2026-08-12 | Internal line |  | 1853.79 | Completed | No
WO-26-008554 | 6.5 | Crossroads | CR-S08-06 | Corrective maintenance | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Contract line | CT-01 | 1381 | Completed | No
WO-26-008555 |  | Crossroads | CR-S05-01 | Corrective maintenance | P4 planned | 2026-08-07 | 2026-09-05 |  | Internal line |  |  | Scheduled | No
WO-26-008556 | 10.8 | Crossroads | CR-S07-05 | Corrective maintenance | P3 within 10 days | 2026-08-07 | 2026-08-12 | 2026-08-12 | Internal line |  | 1069.45 | Completed | No
WO-26-008557 | 5.8 | Crossroads | CR-S21-03 | Corrective maintenance | P3 within 10 days | 2026-08-07 | 2026-08-08 | 2026-08-12 | Internal line |  | 1668.52 | Completed | No
WO-26-008558 | 1.1 | Crossroads | CR-S01-02 | Meter exchange | P3 within 10 days | 2026-08-07 | 2026-08-08 | 2026-08-09 | Meter technician |  | 61.21 | Completed | No
WO-26-008559 | 1.1 | Crossroads | CR-S04-03 | Meter exchange | P3 within 10 days | 2026-08-07 | 2026-08-09 | 2026-08-10 | Meter technician |  | 168.68 | Completed | No
WO-26-008560 |  | Crossroads | CR-S32-04 | New service - small | P4 planned | 2026-08-07 | 2026-10-01 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008561 |  | Crossroads | CR-S19-03 | New service - small | P4 planned | 2026-08-07 | 2026-09-05 |  | Underground crew |  |  | Open - awaiting material | No
WO-26-008562 |  | Crossroads | CR-S16-04 | Preventive maintenance | P4 planned | 2026-08-07 | 2026-09-17 |  | Internal line |  |  | Scheduled | No
WO-26-008563 |  | Crossroads | CR-S30-06 | Preventive maintenance | P4 planned | 2026-08-07 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-008564 | 1.1 | Crossroads | CR-S22-01 | Service order - field | P3 within 10 days | 2026-08-07 | 2026-08-11 | 2026-08-11 | Meter technician |  | 22.37 | Completed | No
WO-26-008565 | 6.6 | Crossroads | CR-S20-01 | Transformer replacement | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Internal line |  | 9863.91 | Completed | No
WO-26-008566 |  | Crossroads | CR-S08-01 | Transformer replacement | P3 within 10 days | 2026-08-07 | 2026-08-14 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008567 |  | Crossroads | CR-S03-02 | Transformer replacement | P1 emergency | 2026-08-07 | 2026-08-07 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008568 | 12.4 | Crossroads | CR-S25-03 | Transformer replacement | P2 same day | 2026-08-07 | 2026-08-07 | 2026-08-07 | Internal line |  | 4463.93 | Completed | No
WO-26-008569 | 5.6 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 187.4 | Completed | No
WO-26-008570 | 2.3 | Crossroads | CR-S14-05 | Trouble - no power | P2 same day | 2026-08-07 | 2026-08-08 | 2026-08-08 | Troubleman |  | 220.18 | Completed | No
WO-26-008571 | 2.1 | Crossroads | CR-S24-01 | Trouble - no power | P2 same day | 2026-08-07 | 2026-08-08 | 2026-08-08 | Troubleman |  | 119.43 | Completed | No
WO-26-008572 | 3.8 | Crossroads | CR-S29-02 | Trouble - no power | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 62.59 | Completed | No
WO-26-008573 | 3.8 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-08-07 | 2026-08-07 | 2026-08-07 | Troubleman |  | 229.55 | Completed | No
WO-26-008574 | 3.6 | Bayou | BY-S20-03 | Corrective maintenance | P2 same day | 2026-08-08 | 2026-08-08 | 2026-08-08 | Contract line | CT-04 | 2158.99 | Completed | No
WO-26-008575 | 11.2 | Bayou | BY-S11-03 | Corrective maintenance | P2 same day | 2026-08-08 | 2026-08-09 | 2026-08-09 | Internal line |  | 1818.41 | Completed | No
WO-26-008576 | 9.4 | Bayou | BY-S25-01 | Transformer replacement | P2 same day | 2026-08-08 | 2026-08-09 | 2026-08-09 | Contract line | CT-03 | 7467.26 | Completed | No
WO-26-008577 |  | Bayou | BY-S23-04 | Transformer replacement | P2 same day | 2026-08-08 | 2026-08-08 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008578 |  | Bayou | BY-S19-03 | Transformer replacement | P2 same day | 2026-08-08 | 2026-08-09 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008579 | 2.1 | Bayou | BY-S19-04 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 179.7 | Completed | No
WO-26-008580 | 2 | Bayou | BY-S26-01 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 322.17 | Completed | No
WO-26-008581 | 4.1 | Bayou | BY-S25-05 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 46.16 | Completed | No
WO-26-008582 | 2.9 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 228.47 | Completed | No
WO-26-008583 | 5.8 | Bayou | BY-S14-01 | Trouble - no power | P2 same day | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 259.66 | Completed | No
WO-26-008584 | 4 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Internal line |  | 191.67 | Completed | No
WO-26-008585 | 2.4 | Bayou | BY-S24-05 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 154.15 | Completed | No
WO-26-008586 | 0.9 | Crossroads | CR-S25-02 | Service order - field | P2 same day | 2026-08-08 | 2026-08-09 | 2026-08-09 | Meter technician |  | 16.83 | Completed | No
WO-26-008587 | 8.9 | Crossroads | CR-S18-04 | Transformer replacement | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Internal line |  | 6711.05 | Completed | No
WO-26-008588 | 5.2 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Internal line |  | 41.06 | Completed | No
WO-26-008589 | 2.4 | Crossroads | CR-S09-05 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 187.5 | Completed | No
WO-26-008590 | 5.7 | Crossroads | CR-S13-01 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 104.26 | Completed | No
WO-26-008591 | 2.6 | Crossroads | CR-S04-02 | Trouble - no power | P1 emergency | 2026-08-08 | 2026-08-08 | 2026-08-08 | Internal line |  | 239.03 | Completed | No
WO-26-008592 | 5.8 | Crossroads | CR-S03-03 | Trouble - no power | P2 same day | 2026-08-08 | 2026-08-09 | 2026-08-09 | Internal line |  | 117.86 | Completed | No
WO-26-008593 | 5.1 | Crossroads | CR-S29-02 | Trouble - no power | P2 same day | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 346.88 | Completed | No
WO-26-008594 | 5.3 | Crossroads | CR-S25-01 | Trouble - no power | P2 same day | 2026-08-08 | 2026-08-08 | 2026-08-08 | Troubleman |  | 234.83 | Completed | No
WO-26-008595 | 0.9 | Bayou | BY-S25-04 | Service order - field | P2 same day | 2026-08-09 | 2026-08-10 | 2026-08-10 | Meter technician |  | 20.96 | Completed | No
WO-26-008596 |  | Bayou | BY-S05-02 | Transformer replacement | P2 same day | 2026-08-09 | 2026-08-09 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008597 | 12.7 | Bayou | BY-S15-03 | Transformer replacement | P2 same day | 2026-08-09 | 2026-08-10 | 2026-08-10 | Contract line | CT-03 | 6627.55 | Completed | No
WO-26-008598 | 9.1 | Bayou | BY-S19-03 | Transformer replacement | P1 emergency | 2026-08-09 | 2026-08-09 | 2026-08-09 | Contract line | CT-04 | 7697.06 | Completed | No
WO-26-008599 | 10.9 | Bayou | BY-S18-01 | Transformer replacement | P2 same day | 2026-08-09 | 2026-08-09 | 2026-08-09 | Contract line | CT-03 | 5372.86 | Completed | No
WO-26-008600 | 3.3 | Bayou | BY-S22-03 | Trouble - partial or voltage | P2 same day | 2026-08-09 | 2026-08-09 | 2026-08-09 | Troubleman |  | 14.25 | Completed | No
WO-26-008601 | 2.4 | Bayou | BY-S19-02 | Trouble - partial or voltage | P2 same day | 2026-08-09 | 2026-08-09 | 2026-08-09 | Troubleman |  | 146.13 | Completed | No
WO-26-008602 | 1 | Crossroads | CR-S18-04 | Service order - field | P2 same day | 2026-08-09 | 2026-08-09 | 2026-08-09 | Meter technician |  | 31.99 | Completed | No
WO-26-008603 | 0.8 | Crossroads | CR-S28-03 | Service order - field | P2 same day | 2026-08-09 | 2026-08-10 | 2026-08-10 | Meter technician |  | 12.99 | Completed | No
WO-26-008604 | 1.8 | Crossroads | CR-S11-02 | Service order - field | P2 same day | 2026-08-09 | 2026-08-10 | 2026-08-10 | Meter technician |  | 10.82 | Completed | No
WO-26-008605 | 1.9 | Crossroads | CR-S04-02 | Service order - field | P2 same day | 2026-08-09 | 2026-08-10 | 2026-08-10 | Meter technician |  | 36.08 | Completed | No
WO-26-008606 | 12.9 | Crossroads | CR-S22-03 | Transformer replacement | P1 emergency | 2026-08-09 | 2026-08-09 | 2026-08-09 | Internal line |  | 6482.33 | Completed | No
WO-26-008607 | 13.3 | Crossroads | CR-S07-03 | Transformer replacement | P1 emergency | 2026-08-09 | 2026-08-09 | 2026-08-09 | Internal line |  | 5202.62 | Completed | No
WO-26-008608 |  | Crossroads | CR-S16-04 | Transformer replacement | P2 same day | 2026-08-09 | 2026-08-10 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-008609 |  | Crossroads | CR-S25-01 | Trouble - no power | P1 emergency | 2026-08-09 | 2026-08-09 |  | Troubleman |  |  | Cancelled | No
WO-26-008610 | 3.2 | Crossroads | CR-S16-03 | Trouble - no power | P1 emergency | 2026-08-09 | 2026-08-09 | 2026-08-09 | Troubleman |  | 10.75 | Completed | No
WO-26-008611 | 2.9 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-08-09 | 2026-08-09 | 2026-08-09 | Troubleman |  | 313.98 | Completed | No
WO-26-008612 | 3.7 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-09 | 2026-08-09 | 2026-08-09 | Troubleman |  | 269.96 | Completed | No
WO-26-008613 | 9.8 | Bayou | BY-S21-03 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-17 | Underground crew |  | 2094.71 | Completed | No
WO-26-008614 |  | Bayou | BY-S16-06 | Corrective maintenance | P4 planned | 2026-08-10 | 2026-09-20 |  | Underground crew |  |  | Scheduled | No
WO-26-008615 | 11.9 | Bayou | BY-S19-03 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-17 | 2026-08-25 | Internal line |  | 493.6 | Completed | No
WO-26-008616 | 11.6 | Bayou | BY-S21-03 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-12 | 2026-08-13 | Contract line | CT-04 | 2314.57 | Completed | No
WO-26-008617 | 0.7 | Bayou | BY-S05-01 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-16 | 2026-08-16 | Meter technician |  | 153.3 | Completed | No
WO-26-008618 | 0.6 | Bayou | BY-S18-06 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-17 | Meter technician |  | 169.81 | Completed | No
WO-26-008619 | 1.4 | Bayou | BY-S10-01 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-20 | 2026-08-20 | Meter technician |  | 154.59 | Completed | No
WO-26-008620 |  | Bayou | BY-S13-06 | Meter exchange | P4 planned | 2026-08-10 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-008621 | 1.5 | Bayou | BY-S27-06 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-15 | Meter technician |  | 109.19 | Completed | No
WO-26-008622 | 1.2 | Bayou | BY-S04-01 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-11 | 2026-08-12 | Meter technician |  | 121.87 | Completed | No
WO-26-008623 | 15.6 | Bayou | BY-S03-02 | Pole replacement | P4 planned | 2026-08-10 | 2026-08-22 | 2026-08-24 | Contract line | CT-04 | 3454.66 | Completed | No
WO-26-008624 |  | Bayou | BY-S07-05 | Pole replacement | P2 same day | 2026-08-10 | 2026-08-11 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008625 |  | Bayou | BY-S14-02 | Pole replacement | P4 planned | 2026-08-10 | 2026-09-10 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008626 |  | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-08-10 | 2026-10-07 |  | Internal line |  |  | Scheduled | No
WO-26-008627 |  | Bayou | BY-S29-04 | Preventive maintenance | P4 planned | 2026-08-10 | 2026-09-17 |  | Internal line |  |  | Scheduled | No
WO-26-008628 | 1.2 | Bayou | BY-S10-02 | Service order - field | P3 within 10 days | 2026-08-10 | 2026-08-18 | 2026-08-22 | Meter technician |  | 1.17 | Completed | No
WO-26-008629 | 1.8 | Bayou | BY-S18-04 | Service order - field | P3 within 10 days | 2026-08-10 | 2026-08-14 | 2026-08-14 | Meter technician |  | 10.1 | Completed | No
WO-26-008630 | 0.8 | Bayou | BY-S18-03 | Service order - field | P2 same day | 2026-08-10 | 2026-08-11 | 2026-08-11 | Meter technician |  | 31.51 | Completed | No
WO-26-008631 | 1.2 | Bayou | BY-S17-02 | Service order - field | P3 within 10 days | 2026-08-10 | 2026-08-17 | 2026-08-19 | Meter technician |  | 26.03 | Completed | No
WO-26-008632 | 1.3 | Bayou | BY-S13-03 | Service order - field | P3 within 10 days | 2026-08-10 | 2026-08-20 | 2026-08-24 | Meter technician |  | 17.88 | Completed | No
WO-26-008633 |  | Bayou |  | Streetlight | P4 planned | 2026-08-10 | 2026-09-03 |  | Internal line |  |  | Scheduled | No
WO-26-008634 | 2.2 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-10 | 2026-08-14 | 2026-08-14 | Contract line | CT-04 | 366.82 | Completed | No
WO-26-008635 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-16 | Contract line | CT-04 | 332.26 | Completed | No
WO-26-008636 |  | Bayou |  | Streetlight | P4 planned | 2026-08-10 | 2026-10-03 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-008637 | 11.8 | Bayou | BY-S13-05 | Transformer replacement | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-19 | Internal line |  | 8784.4 | Completed | No
WO-26-008638 |  | Bayou | BY-S14-02 | Transformer replacement | P2 same day | 2026-08-10 | 2026-08-10 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008639 | 3.5 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-08-10 | 2026-08-10 | 2026-08-10 | Troubleman |  | 308.28 | Completed | No
WO-26-008640 | 2.1 | Bayou | BY-S16-06 | Trouble - no power | P2 same day | 2026-08-10 | 2026-08-11 | 2026-08-11 | Internal line |  | 272.33 | Completed | No
WO-26-008641 | 3.1 | Bayou | BY-S04-02 | Trouble - no power | P2 same day | 2026-08-10 | 2026-08-11 | 2026-08-11 | Troubleman |  | 197.96 | Completed | No
WO-26-008642 | 10.4 | Crossroads | CR-S08-02 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-19 | 2026-08-19 | Internal line |  | 990.73 | Completed | No
WO-26-008643 |  | Crossroads | CR-S29-02 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-20 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008644 | 4.5 | Crossroads | CR-S30-07 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-18 | 2026-08-18 | Underground crew |  | 361.99 | Completed | No
WO-26-008645 | 6.3 | Crossroads | CR-S32-02 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-12 | 2026-08-13 | Underground crew |  | 1339.39 | Completed | No
WO-26-008646 | 6.7 | Crossroads | CR-S22-01 | Corrective maintenance | P2 same day | 2026-08-10 | 2026-08-11 | 2026-08-11 | Contract line | CT-01 | 691.43 | Completed | No
WO-26-008647 | 7.9 | Crossroads | CR-S20-03 | Corrective maintenance | P3 within 10 days | 2026-08-10 | 2026-08-20 | 2026-08-20 | Internal line |  | 711.68 | Completed | No
WO-26-008648 |  | Crossroads | CR-S32-01 | Meter exchange | P4 planned | 2026-08-10 | 2026-09-25 |  | Meter technician |  |  | Scheduled | No
WO-26-008649 | 1.2 | Crossroads | CR-S07-03 | Meter exchange | P4 planned | 2026-08-10 | 2026-08-27 | 2026-08-27 | Meter technician |  | 87.12 | Completed | No
WO-26-008650 |  | Crossroads | CR-S03-02 | Meter exchange | P4 planned | 2026-08-10 | 2026-08-30 |  | Meter technician |  |  | Scheduled | No
WO-26-008651 |  | Crossroads | CR-S16-02 | Meter exchange | P4 planned | 2026-08-10 | 2026-10-05 |  | Meter technician |  |  | Scheduled | No
WO-26-008652 |  | Crossroads | CR-S30-01 | Meter exchange | P4 planned | 2026-08-10 | 2026-09-21 |  | Meter technician |  |  | Scheduled | No
WO-26-008653 | 0.5 | Crossroads | CR-S18-04 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-14 | 2026-08-14 | Meter technician |  | 85.59 | Completed | No
WO-26-008654 | 1.1 | Crossroads | CR-S22-02 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-18 | 2026-08-19 | Meter technician |  | 86.33 | Completed | No
WO-26-008655 | 1.3 | Crossroads | CR-S17-01 | Meter exchange | P3 within 10 days | 2026-08-10 | 2026-08-19 | 2026-08-19 | Meter technician |  | 168.31 | Completed | No
WO-26-008656 | 12.5 | Crossroads | CR-S30-02 | New service - small | P3 within 10 days | 2026-08-10 | 2026-08-13 | 2026-08-13 | Underground crew |  | 2234.09 | Completed | No
WO-26-008657 |  | Crossroads | CR-S25-04 | Preventive maintenance | P4 planned | 2026-08-10 | 2026-09-05 |  | Internal line |  |  | Scheduled | No
WO-26-008658 |  | Crossroads | CR-S32-04 | Preventive maintenance | P4 planned | 2026-08-10 | 2026-09-16 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-008659 |  | Crossroads | CR-S15-01 | Preventive maintenance | P4 planned | 2026-08-10 | 2026-09-13 |  | Underground crew |  |  | Scheduled | No
WO-26-008660 |  | Crossroads | CR-S09-04 | Preventive maintenance | P4 planned | 2026-08-10 | 2026-09-14 |  | Underground crew |  |  | Scheduled | No
WO-26-008661 | 0.9 | Crossroads | CR-S16-03 | Service order - field | P2 same day | 2026-08-10 | 2026-08-10 | 2026-08-10 | Meter technician |  | 1.06 | Completed | No
WO-26-008662 | 0.9 | Crossroads | CR-S18-02 | Service order - field | P3 within 10 days | 2026-08-10 | 2026-08-11 | 2026-08-11 | Meter technician |  | 5.67 | Completed | No
WO-26-008663 | 1.4 | Crossroads | CR-S30-05 | Service order - field | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-15 | Meter technician |  | 13.56 | Completed | No
WO-26-008664 | 1.3 | Crossroads | CR-S30-07 | Service order - field | P2 same day | 2026-08-10 | 2026-08-11 | 2026-08-11 | Meter technician |  | 1.81 | Completed | No
WO-26-008665 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-10 | 2026-08-15 | 2026-08-15 | Contract line | CT-01 | 246.21 | Completed | No
WO-26-008666 |  | Crossroads | CR-S08-05 | Transformer replacement | P2 same day | 2026-08-10 | 2026-08-11 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-008667 | 5.3 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-08-10 | 2026-08-10 | 2026-08-10 | Troubleman |  | 0.26 | Completed | No
WO-26-008668 | 2.6 | Crossroads | CR-S02-02 | Trouble - no power | P1 emergency | 2026-08-10 | 2026-08-10 | 2026-08-10 | Troubleman |  | 270.16 | Completed | No
WO-26-008669 | 3.2 | Crossroads | CR-S07-02 | Trouble - no power | P2 same day | 2026-08-10 | 2026-08-10 | 2026-08-10 | Troubleman |  | 239.39 | Completed | No
WO-26-008670 | 3.2 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-08-10 | 2026-08-11 | 2026-08-11 | Troubleman |  | 318.22 | Completed | No
WO-26-008671 | 1.9 | Crossroads | CR-S07-05 | Trouble - partial or voltage | P2 same day | 2026-08-10 | 2026-08-10 | 2026-08-10 | Troubleman |  | 201.32 | Completed | No
WO-26-008672 | 4.8 | Bayou | BY-S17-01 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-15 | 2026-08-17 | Underground crew |  | 2207.13 | Completed | No
WO-26-008673 |  | Bayou | BY-S23-03 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-21 |  | Contract line | CT-04 |  | Open - awaiting outage | No
WO-26-008674 | 8.4 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-17 | 2026-08-17 | Contract line | CT-04 | 820.47 | Completed | No
WO-26-008675 | 1.4 | Bayou | BY-S28-03 | Meter exchange | P3 within 10 days | 2026-08-11 | 2026-08-13 | 2026-08-13 | Meter technician |  | 121.62 | Completed | No
WO-26-008676 |  | Bayou | BY-S29-02 | Meter exchange | P4 planned | 2026-08-11 | 2026-09-27 |  | Meter technician |  |  | Scheduled | No
WO-26-008677 |  | Bayou | BY-S23-02 | Meter exchange | P4 planned | 2026-08-11 | 2026-09-20 |  | Meter technician |  |  | Scheduled | No
WO-26-008678 |  | Bayou | BY-S06-02 | Meter exchange | P4 planned | 2026-08-11 | 2026-09-14 |  | Meter technician |  |  | Scheduled | No
WO-26-008679 | 1.4 | Bayou | BY-S01-01 | Meter exchange | P3 within 10 days | 2026-08-11 | 2026-08-15 | 2026-08-16 | Meter technician |  | 100.48 | Completed | No
WO-26-008680 |  | Bayou | BY-S18-02 | Meter exchange | P4 planned | 2026-08-11 | 2026-09-13 |  | Meter technician |  |  | Scheduled | No
WO-26-008681 | 1 | Bayou | BY-S15-06 | Meter exchange | P3 within 10 days | 2026-08-11 | 2026-08-14 | 2026-08-14 | Meter technician |  | 70.59 | Completed | No
WO-26-008682 |  | Bayou | BY-S10-05 | Meter exchange | P4 planned | 2026-08-11 | 2026-10-10 |  | Meter technician |  |  | Scheduled | No
WO-26-008683 |  | Bayou | BY-S24-04 | Pole replacement | P4 planned | 2026-08-11 | 2026-09-08 |  | Internal line |  |  | Scheduled | No
WO-26-008684 |  | Bayou | BY-S30-01 | Pole replacement | P4 planned | 2026-08-11 | 2026-08-30 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-008685 |  | Bayou |  | Streetlight | P4 planned | 2026-08-11 | 2026-09-02 |  | Internal line |  |  | Scheduled | No
WO-26-008686 | 4.4 | Bayou | BY-S26-02 | Trouble - no power | P1 emergency | 2026-08-11 | 2026-08-11 | 2026-08-11 | Internal line |  | 66.76 | Completed | No
WO-26-008687 | 5.9 | Bayou | BY-S21-04 | Trouble - no power | P1 emergency | 2026-08-11 | 2026-08-11 | 2026-08-11 | Internal line |  | 201.04 | Completed | No
WO-26-008688 | 4.2 | Bayou | BY-S28-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-11 | 2026-08-19 | 2026-08-19 | Troubleman |  | 106.1 | Completed | No
WO-26-008689 | 9.4 | Crossroads | CR-S04-03 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-12 | 2026-08-12 | Underground crew |  | 1986.7 | Completed | No
WO-26-008690 |  | Crossroads | CR-S15-01 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-14 |  | Contract line | CT-02 |  | Cancelled | No
WO-26-008691 | 10.8 | Crossroads | CR-S27-01 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-19 | 2026-08-19 | Underground crew |  | 2355.55 | Completed | No
WO-26-008692 |  | Crossroads | CR-S15-01 | Corrective maintenance | P3 within 10 days | 2026-08-11 | 2026-08-15 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-008693 | 1.5 | Crossroads | CR-S29-03 | Meter exchange | P3 within 10 days | 2026-08-11 | 2026-08-21 | 2026-08-21 | Meter technician |  | 100.26 | Completed | No
WO-26-008694 |  | Crossroads | CR-S17-01 | New service - small | P3 within 10 days | 2026-08-11 | 2026-08-19 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-008695 | 11.8 | Crossroads | CR-S24-04 | Pole replacement | P2 same day | 2026-08-11 | 2026-08-11 | 2026-08-11 | Contract line | CT-01 | 2221.88 | Completed | No
WO-26-008696 |  | Crossroads | CR-S20-05 | Pole replacement | P2 same day | 2026-08-11 | 2026-08-11 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008697 |  | Crossroads | CR-S04-03 | Preventive maintenance | P4 planned | 2026-08-11 | 2026-09-29 |  | Internal line |  |  | Scheduled | No
WO-26-008698 |  | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-08-11 | 2026-10-07 |  | Underground crew |  |  | Scheduled | No
WO-26-008699 | 0.9 | Crossroads | CR-S32-01 | Service order - field | P2 same day | 2026-08-11 | 2026-08-12 | 2026-08-12 | Meter technician |  | 3.12 | Completed | No
WO-26-008700 | 1.8 | Crossroads | CR-S20-02 | Service order - field | P2 same day | 2026-08-11 | 2026-08-12 | 2026-08-12 | Meter technician |  | 35.03 | Completed | No
WO-26-008701 | 0.7 | Crossroads | CR-S21-02 | Service order - field | P2 same day | 2026-08-11 | 2026-08-12 | 2026-08-12 | Meter technician |  | 19.83 | Completed | No
WO-26-008702 | 1.5 | Crossroads | CR-S07-02 | Service order - field | P3 within 10 days | 2026-08-11 | 2026-08-18 | 2026-08-22 | Meter technician |  | 33.17 | Completed | No
WO-26-008703 | 1.9 | Crossroads | CR-S19-02 | Service order - field | P2 same day | 2026-08-11 | 2026-08-11 | 2026-08-11 | Meter technician |  | 29.34 | Completed | No
WO-26-008704 | 1.9 | Crossroads | CR-S24-03 | Service order - field | P2 same day | 2026-08-11 | 2026-08-12 | 2026-08-12 | Meter technician |  | 27.99 | Completed | No
WO-26-008705 | 0.9 | Crossroads | CR-S27-03 | Service order - field | P2 same day | 2026-08-11 | 2026-08-11 | 2026-08-11 | Meter technician |  | 16.77 | Completed | No
WO-26-008706 | 1.6 | Crossroads | CR-S02-03 | Service order - field | P3 within 10 days | 2026-08-11 | 2026-08-19 | 2026-08-19 | Meter technician |  | 10.47 | Completed | No
WO-26-008707 | 1.4 | Crossroads | CR-S25-04 | Service order - field | P2 same day | 2026-08-11 | 2026-08-11 | 2026-08-11 | Meter technician |  | 6.94 | Completed | No
WO-26-008708 | 1.7 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-08-11 | 2026-08-14 | 2026-08-14 | Meter technician |  | 14.74 | Completed | No
WO-26-008709 | 13.3 | Crossroads | CR-S13-05 | Transformer replacement | P2 same day | 2026-08-11 | 2026-08-12 | 2026-08-12 | Internal line |  | 9959.26 | Completed | No
WO-26-008710 | 6.9 | Crossroads | CR-S05-02 | Transformer replacement | P1 emergency | 2026-08-11 | 2026-08-11 | 2026-08-11 | Internal line |  | 11966.25 | Completed | No
WO-26-008711 | 5.2 | Crossroads | CR-S23-04 | Trouble - no power | P1 emergency | 2026-08-11 | 2026-08-11 | 2026-08-11 | Troubleman |  | 139.07 | Completed | No
WO-26-008712 | 2.2 | Crossroads | CR-S18-01 | Trouble - no power | P2 same day | 2026-08-11 | 2026-08-11 | 2026-08-11 | Troubleman |  | 217.36 | Completed | No
WO-26-008713 | 4 | Crossroads | CR-S05-04 | Trouble - no power | P1 emergency | 2026-08-11 | 2026-08-11 | 2026-08-11 | Troubleman |  | 296.92 | Completed | No
WO-26-008714 | 2.4 | Crossroads | CR-S05-02 | Trouble - partial or voltage | P2 same day | 2026-08-11 | 2026-08-11 | 2026-08-11 | Troubleman |  | 146.6 | Completed | No
WO-26-008715 | 3.5 | Crossroads | CR-S24-04 | Trouble - partial or voltage | P2 same day | 2026-08-11 | 2026-08-12 | 2026-08-12 | Troubleman |  | 125.66 | Completed | No
WO-26-008716 | 4.2 | Bayou | BY-S13-03 | Corrective maintenance | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Internal line |  | 1349.24 | Completed | No
WO-26-008717 | 4.4 | Bayou | BY-S16-02 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-21 | 2026-08-21 | Internal line |  | 2237.31 | Completed | No
WO-26-008718 | 10.6 | Bayou | BY-S17-02 | Corrective maintenance | P4 planned | 2026-08-12 | 2026-08-19 | 2026-08-19 | Internal line |  | 1287.1 | Completed | No
WO-26-008719 | 11.6 | Bayou | BY-S07-04 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-15 | 2026-08-19 | Contract line | CT-04 | 1368.57 | Completed | No
WO-26-008720 | 9.9 | Bayou | BY-S30-01 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-15 | 2026-08-16 | Internal line |  | 1026.98 | Completed | No
WO-26-008721 |  | Bayou | BY-S16-06 | Meter exchange | P4 planned | 2026-08-12 | 2026-09-24 |  | Meter technician |  |  | Scheduled | No
WO-26-008722 | 0.6 | Bayou | BY-S17-02 | Meter exchange | P3 within 10 days | 2026-08-12 | 2026-08-15 | 2026-08-16 | Meter technician |  | 165.34 | Completed | No
WO-26-008723 | 1.5 | Bayou | BY-S08-01 | Meter exchange | P3 within 10 days | 2026-08-12 | 2026-08-22 | 2026-08-24 | Meter technician |  | 151.52 | Completed | No
WO-26-008724 | 1.3 | Bayou | BY-S05-02 | Meter exchange | P3 within 10 days | 2026-08-12 | 2026-08-16 | 2026-08-16 | Meter technician |  | 164.77 | Completed | No
WO-26-008725 |  | Bayou | BY-S03-02 | Meter exchange | P4 planned | 2026-08-12 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-008726 |  | Bayou | BY-S23-01 | Meter exchange | P4 planned | 2026-08-12 | 2026-09-18 |  | Meter technician |  |  | Scheduled | No
WO-26-008727 |  | Bayou | BY-S10-02 | Pole replacement | P4 planned | 2026-08-12 | 2026-10-03 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008728 | 13.1 | Bayou | BY-S18-04 | Pole replacement | P3 within 10 days | 2026-08-12 | 2026-08-22 | 2026-08-22 | Contract line | CT-04 | 3428.42 | Completed | No
WO-26-008729 |  | Bayou | BY-S29-03 | Preventive maintenance | P4 planned | 2026-08-12 | 2026-09-11 |  | Internal line |  |  | Scheduled | No
WO-26-008730 |  | Bayou | BY-S25-05 | Preventive maintenance | P4 planned | 2026-08-12 | 2026-09-12 |  | Internal line |  |  | Scheduled | No
WO-26-008731 | 0.8 | Bayou | BY-S17-02 | Service order - field | P3 within 10 days | 2026-08-12 | 2026-08-20 | 2026-08-20 | Meter technician |  | 28.68 | Completed | No
WO-26-008732 | 1.8 | Bayou | BY-S23-03 | Service order - field | P3 within 10 days | 2026-08-12 | 2026-08-17 | 2026-08-17 | Meter technician |  | 24.02 | Completed | No
WO-26-008733 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-12 | 2026-08-13 | 2026-08-13 | Contract line | CT-03 | 313.55 | Completed | No
WO-26-008734 |  | Bayou | BY-S18-01 | Transformer replacement | P1 emergency | 2026-08-12 | 2026-08-12 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008735 | 3.6 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Internal line |  | 290.55 | Completed | No
WO-26-008736 | 5.8 | Bayou | BY-S21-02 | Trouble - no power | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 108.68 | Completed | No
WO-26-008737 | 4.7 | Bayou | BY-S06-01 | Trouble - no power | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 241.42 | Completed | No
WO-26-008738 | 5.3 | Bayou | BY-S08-02 | Trouble - no power | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 281.02 | Completed | No
WO-26-008739 | 4.1 | Bayou | BY-S14-01 | Trouble - no power | P2 same day | 2026-08-12 | 2026-08-13 | 2026-08-13 | Troubleman |  | 32.16 | Completed | No
WO-26-008740 | 4 | Bayou | BY-S24-05 | Trouble - partial or voltage | P3 within 10 days | 2026-08-12 | 2026-08-14 | 2026-08-15 | Troubleman |  | 1.49 | Completed | No
WO-26-008741 | 11.3 | Crossroads | CR-S30-07 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-18 | 2026-08-18 | Internal line |  | 1646.87 | Completed | No
WO-26-008742 | 9.6 | Crossroads | CR-S02-02 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-13 | 2026-08-17 | Contract line | CT-02 | 1944.09 | Completed | No
WO-26-008743 | 7.3 | Crossroads | CR-S08-04 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-18 | 2026-08-18 | Internal line |  | 91.76 | Completed | No
WO-26-008744 | 11.4 | Crossroads | CR-S26-05 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-18 | 2026-08-18 | Underground crew |  | 2026.77 | Completed | No
WO-26-008745 | 5.2 | Crossroads | CR-S21-02 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-18 | 2026-08-18 | Contract line | CT-01 | 478.78 | Completed | No
WO-26-008746 | 10.7 | Crossroads | CR-S17-01 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-22 | 2026-08-26 | Contract line | CT-01 | 254.9 | Completed | No
WO-26-008747 | 3.6 | Crossroads | CR-S24-01 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-19 | 2026-08-19 | Underground crew |  | 816.65 | Completed | No
WO-26-008748 | 4 | Crossroads | CR-S30-07 | Corrective maintenance | P3 within 10 days | 2026-08-12 | 2026-08-19 | 2026-08-20 | Internal line |  | 1909.76 | Completed | No
WO-26-008749 |  | Crossroads | CR-S09-02 | Meter exchange | P4 planned | 2026-08-12 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-008750 | 1.1 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-08-12 | 2026-08-14 | 2026-08-15 | Meter technician |  | 110.36 | Completed | No
WO-26-008751 | 1.5 | Crossroads | CR-S16-02 | Meter exchange | P3 within 10 days | 2026-08-12 | 2026-08-19 | 2026-08-23 | Meter technician |  | 109.24 | Completed | No
WO-26-008752 |  | Crossroads | CR-S14-03 | New service - small | P4 planned | 2026-08-12 | 2026-09-18 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008753 | 15.2 | Crossroads | CR-S26-06 | Pole replacement | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Contract line | CT-02 | 3224.18 | Completed | No
WO-26-008754 | 14.2 | Crossroads | CR-S24-04 | Pole replacement | P3 within 10 days | 2026-08-12 | 2026-08-17 | 2026-08-17 | Internal line |  | 3272.08 | Completed | No
WO-26-008755 |  | Crossroads | CR-S13-06 | Preventive maintenance | P4 planned | 2026-08-12 | 2026-09-26 |  | Internal line |  |  | Scheduled | No
WO-26-008756 | 1 | Crossroads | CR-S15-01 | Service order - field | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Meter technician |  | 30.89 | Completed | No
WO-26-008757 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-12 | 2026-10-01 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008758 | 8 | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Internal line |  | 2919.65 | Completed | No
WO-26-008759 | 6.3 | Crossroads | CR-S07-07 | Transformer replacement | P2 same day | 2026-08-12 | 2026-08-13 | 2026-08-13 | Contract line | CT-02 | 3655.51 | Completed | No
WO-26-008760 | 11.1 | Crossroads | CR-S19-02 | Transformer replacement | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Internal line |  | 11693.25 | Completed | No
WO-26-008761 |  | Crossroads | CR-S03-02 | Transformer replacement | P1 emergency | 2026-08-12 | 2026-08-12 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008762 | 11.4 | Crossroads | CR-S23-02 | Transformer replacement | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Contract line | CT-01 | 4626.56 | Completed | No
WO-26-008763 | 5.6 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 318.94 | Completed | No
WO-26-008764 | 4.9 | Crossroads | CR-S06-01 | Trouble - no power | P1 emergency | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 232.43 | Completed | No
WO-26-008765 | 5.1 | Crossroads | CR-S26-03 | Trouble - no power | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 134.59 | Completed | No
WO-26-008766 | 3 | Crossroads | CR-S15-01 | Trouble - no power | P2 same day | 2026-08-12 | 2026-08-12 | 2026-08-12 | Troubleman |  | 238.4 | Completed | No
WO-26-008767 | 5 | Crossroads | CR-S32-02 | Trouble - no power | P2 same day | 2026-08-12 | 2026-08-13 | 2026-08-13 | Internal line |  | 14.04 | Completed | No
WO-26-008768 | 3 | Crossroads | CR-S10-01 | Trouble - partial or voltage | P2 same day | 2026-08-12 | 2026-08-13 | 2026-08-13 | Troubleman |  | 215.11 | Completed | No
WO-26-008769 | 3.6 | Crossroads | CR-S24-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-12 | 2026-08-19 | 2026-08-19 | Internal line |  | 0.68 | Completed | No
WO-26-008770 | 5 | Bayou | BY-S18-04 | Corrective maintenance | P3 within 10 days | 2026-08-13 | 2026-08-20 | 2026-08-28 | Internal line |  | 158.41 | Completed | No
WO-26-008771 |  | Bayou | BY-S15-04 | Corrective maintenance | P4 planned | 2026-08-13 | 2026-09-04 |  | Internal line |  |  | Scheduled | No
WO-26-008772 | 7.1 | Bayou | BY-S11-01 | Corrective maintenance | P3 within 10 days | 2026-08-13 | 2026-08-19 | 2026-08-21 | Internal line |  | 1179.91 | Completed | No
WO-26-008773 |  | Bayou | BY-S20-02 | Corrective maintenance | P4 planned | 2026-08-13 | 2026-10-10 |  | Internal line |  |  | Scheduled | No
WO-26-008774 |  | Bayou | BY-S26-03 | Corrective maintenance | P3 within 10 days | 2026-08-13 | 2026-08-19 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008775 | 1 | Bayou | BY-S08-03 | Meter exchange | P3 within 10 days | 2026-08-13 | 2026-08-16 | 2026-08-17 | Meter technician |  | 113.01 | Completed | No
WO-26-008776 | 1.2 | Bayou | BY-S28-02 | Meter exchange | P3 within 10 days | 2026-08-13 | 2026-08-22 | 2026-08-26 | Meter technician |  | 120.31 | Completed | No
WO-26-008777 | 8.1 | Bayou | BY-S29-02 | New service - small | P3 within 10 days | 2026-08-13 | 2026-08-21 | 2026-08-21 | Underground crew |  | 1378.01 | Completed | No
WO-26-008778 | 1.1 | Bayou | BY-S16-02 | Service order - field | P3 within 10 days | 2026-08-13 | 2026-08-17 | 2026-08-17 | Meter technician |  | 34.97 | Completed | No
WO-26-008779 | 1.2 | Bayou | BY-S27-01 | Service order - field | P2 same day | 2026-08-13 | 2026-08-13 | 2026-08-13 | Meter technician |  | 12.33 | Completed | No
WO-26-008780 | 0.9 | Bayou | BY-S21-01 | Service order - field | P2 same day | 2026-08-13 | 2026-08-13 | 2026-08-13 | Meter technician |  | 20.65 | Completed | No
WO-26-008781 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-13 | 2026-08-23 | 2026-08-23 | Contract line | CT-04 | 433.54 | Completed | No
WO-26-008782 | 1.9 | Bayou |  | Streetlight | P4 planned | 2026-08-13 | 2026-08-20 | 2026-08-21 | Contract line | CT-03 | 128.63 | Completed | No
WO-26-008783 |  | Bayou | BY-S19-03 | Transformer replacement | P3 within 10 days | 2026-08-13 | 2026-08-17 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008784 |  | Bayou | BY-S03-01 | Transformer replacement | P1 emergency | 2026-08-13 | 2026-08-13 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008785 | 9.9 | Bayou | BY-S11-01 | Transformer replacement | P1 emergency | 2026-08-13 | 2026-08-13 | 2026-08-13 | Internal line |  | 5144.14 | Completed | No
WO-26-008786 |  | Bayou | BY-S07-03 | Transformer replacement | P2 same day | 2026-08-13 | 2026-08-13 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008787 | 6.1 | Bayou | BY-S03-03 | Transformer replacement | P3 within 10 days | 2026-08-13 | 2026-08-22 | 2026-08-30 | Internal line |  | 8545.7 | Completed | No
WO-26-008788 | 8.7 | Bayou | BY-S26-06 | Transformer replacement | P2 same day | 2026-08-13 | 2026-08-13 | 2026-08-13 | Internal line |  | 5770.92 | Completed | No
WO-26-008789 | 9.2 | Bayou | BY-S06-02 | Transformer replacement | P2 same day | 2026-08-13 | 2026-08-14 | 2026-08-14 | Internal line |  | 4846.79 | Completed | No
WO-26-008790 | 2.4 | Bayou | BY-S22-03 | Trouble - no power | P2 same day | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 172.12 | Completed | No
WO-26-008791 | 4 | Bayou | BY-S29-01 | Trouble - no power | P2 same day | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 36.06 | Completed | No
WO-26-008792 | 3.6 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-08-13 | 2026-08-13 | 2026-08-13 | Internal line |  | 224.48 | Completed | No
WO-26-008793 | 1.8 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 67.84 | Completed | No
WO-26-008794 | 3.4 | Crossroads | CR-S14-03 | Corrective maintenance | P3 within 10 days | 2026-08-13 | 2026-08-14 | 2026-08-14 | Underground crew |  | 1445.51 | Completed | No
WO-26-008795 |  | Crossroads | CR-S13-04 | Corrective maintenance | P4 planned | 2026-08-13 | 2026-10-02 |  | Internal line |  |  | Scheduled | No
WO-26-008796 | 8.9 | Crossroads | CR-S04-02 | Corrective maintenance | P3 within 10 days | 2026-08-13 | 2026-08-23 | 2026-08-23 | Internal line |  | 1168.92 | Completed | No
WO-26-008797 | 0.8 | Crossroads | CR-S02-04 | Meter exchange | P3 within 10 days | 2026-08-13 | 2026-08-21 | 2026-08-22 | Meter technician |  | 170.14 | Completed | No
WO-26-008798 |  | Crossroads | CR-S02-05 | Meter exchange | P4 planned | 2026-08-13 | 2026-09-16 |  | Meter technician |  |  | Scheduled | No
WO-26-008799 | 1.1 | Crossroads | CR-S22-03 | Meter exchange | P3 within 10 days | 2026-08-13 | 2026-08-22 | 2026-08-22 | Meter technician |  | 152.79 | Completed | No
WO-26-008800 |  | Crossroads | CR-S15-02 | Meter exchange | P4 planned | 2026-08-13 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-008801 | 6.3 | Crossroads | CR-S17-01 | Preventive maintenance | P4 planned | 2026-08-13 | 2026-08-27 | 2026-08-27 | Underground crew |  | 395.69 | Completed | No
WO-26-008802 |  | Crossroads | CR-S28-02 | Preventive maintenance | P4 planned | 2026-08-13 | 2026-08-31 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008803 | 1.9 | Crossroads | CR-S24-02 | Service order - field | P3 within 10 days | 2026-08-13 | 2026-08-20 | 2026-08-22 | Meter technician |  | 38.61 | Completed | No
WO-26-008804 | 1.6 | Crossroads | CR-S32-03 | Service order - field | P3 within 10 days | 2026-08-13 | 2026-08-19 | 2026-08-19 | Meter technician |  | 2.78 | Completed | No
WO-26-008805 | 1.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-13 | 2026-08-19 | 2026-08-23 | Internal line |  | 423.23 | Completed | No
WO-26-008806 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-13 | 2026-08-20 |  | Internal line |  |  | Cancelled | No
WO-26-008807 | 13.1 | Crossroads | CR-S22-04 | Transformer replacement | P3 within 10 days | 2026-08-13 | 2026-08-18 | 2026-08-19 | Internal line |  | 9137.14 | Completed | No
WO-26-008808 |  | Crossroads | CR-S25-05 | Transformer replacement | P2 same day | 2026-08-13 | 2026-08-13 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008809 | 2.2 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 44.02 | Completed | No
WO-26-008810 |  | Crossroads | CR-S01-04 | Trouble - no power | P1 emergency | 2026-08-13 | 2026-08-13 |  | Troubleman |  |  | Cancelled | No
WO-26-008811 | 2.8 | Crossroads | CR-S12-02 | Trouble - no power | P1 emergency | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 188.01 | Completed | No
WO-26-008812 | 3.7 | Crossroads | CR-S20-02 | Trouble - no power | P1 emergency | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 290.56 | Completed | No
WO-26-008813 | 4.7 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-08-13 | 2026-08-13 | 2026-08-13 | Troubleman |  | 287.93 | Completed | No
WO-26-008814 | 2.8 | Crossroads | CR-S21-03 | Trouble - partial or voltage | P2 same day | 2026-08-13 | 2026-08-14 | 2026-08-14 | Internal line |  | 215.22 | Completed | No
WO-26-008815 | 1.6 | Crossroads | CR-S20-05 | Trouble - partial or voltage | P3 within 10 days | 2026-08-13 | 2026-08-19 | 2026-08-27 | Troubleman |  | 217.73 | Completed | No
WO-26-008816 | 4.8 | Crossroads | CR-S19-03 | Trouble - partial or voltage | P3 within 10 days | 2026-08-13 | 2026-08-16 | 2026-08-16 | Troubleman |  | 22.26 | Completed | No
WO-26-008817 | 2.1 | Crossroads | CR-S10-03 | Trouble - partial or voltage | P3 within 10 days | 2026-08-13 | 2026-08-20 | 2026-08-28 | Troubleman |  | 179.31 | Completed | No
WO-26-008818 | 7.4 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-08-14 | 2026-08-22 | 2026-08-22 | Internal line |  | 1240.45 | Completed | No
WO-26-008819 |  | Bayou | BY-S15-02 | Corrective maintenance | P2 same day | 2026-08-14 | 2026-08-14 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008820 |  | Bayou | BY-S29-01 | Corrective maintenance | P2 same day | 2026-08-14 | 2026-08-14 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-008821 |  | Bayou | BY-S11-02 | Corrective maintenance | P4 planned | 2026-08-14 | 2026-10-03 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008822 | 5.1 | Bayou | BY-S14-03 | Corrective maintenance | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Internal line |  | 681.87 | Completed | No
WO-26-008823 | 4.4 | Bayou | BY-S25-02 | Corrective maintenance | P3 within 10 days | 2026-08-14 | 2026-08-18 | 2026-08-18 | Internal line |  | 414.28 | Completed | No
WO-26-008824 | 8.9 | Bayou | BY-S13-06 | Corrective maintenance | P3 within 10 days | 2026-08-14 | 2026-08-15 | 2026-08-17 | Internal line |  | 1283 | Completed | No
WO-26-008825 |  | Bayou | BY-S26-02 | Meter exchange | P4 planned | 2026-08-14 | 2026-10-07 |  | Meter technician |  |  | Scheduled | No
WO-26-008826 | 0.5 | Bayou | BY-S01-01 | Meter exchange | P3 within 10 days | 2026-08-14 | 2026-08-17 | 2026-08-19 | Meter technician |  | 94.94 | Completed | No
WO-26-008827 | 0.9 | Bayou | BY-S09-01 | Meter exchange | P3 within 10 days | 2026-08-14 | 2026-08-16 | 2026-08-17 | Meter technician |  | 63.32 | Completed | No
WO-26-008828 |  | Bayou | BY-S12-03 | New service - small | P4 planned | 2026-08-14 | 2026-09-09 |  | Underground crew |  |  | Scheduled | No
WO-26-008829 |  | Bayou | BY-S24-04 | Preventive maintenance | P4 planned | 2026-08-14 | 2026-09-14 |  | Internal line |  |  | Scheduled | No
WO-26-008830 | 2 | Bayou | BY-S24-03 | Preventive maintenance | P4 planned | 2026-08-14 | 2026-08-21 | 2026-08-29 | Underground crew |  | 297.17 | Completed | No
WO-26-008831 | 1.8 | Bayou | BY-S26-05 | Service order - field | P3 within 10 days | 2026-08-14 | 2026-08-20 | 2026-08-20 | Meter technician |  | 12.95 | Completed | No
WO-26-008832 | 0.6 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Meter technician |  | 15.56 | Completed | No
WO-26-008833 | 0.8 | Bayou | BY-S15-06 | Service order - field | P3 within 10 days | 2026-08-14 | 2026-08-24 | 2026-08-24 | Meter technician |  | 3.22 | Completed | No
WO-26-008834 | 1.6 | Bayou | BY-S16-03 | Service order - field | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Meter technician |  | 16.93 | Completed | No
WO-26-008835 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-14 | 2026-08-15 | 2026-08-15 | Contract line | CT-04 | 279.1 | Completed | No
WO-26-008836 | 1.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-14 | 2026-08-21 | 2026-08-21 | Internal line |  | 406.12 | Completed | No
WO-26-008837 | 2.7 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-14 | 2026-08-18 | 2026-08-18 | Contract line | CT-04 | 248.99 | Completed | No
WO-26-008838 | 1.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-14 | 2026-08-22 | 2026-08-22 | Contract line | CT-04 | 355.49 | Completed | No
WO-26-008839 |  | Bayou |  | Streetlight | P4 planned | 2026-08-14 | 2026-09-30 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-008840 | 13.9 | Bayou | BY-S18-04 | Transformer replacement | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Internal line |  | 6020.39 | Completed | No
WO-26-008841 | 12.3 | Bayou | BY-S01-01 | Transformer replacement | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Internal line |  | 3479.38 | Completed | No
WO-26-008842 | 2 | Bayou | BY-S21-05 | Trouble - no power | P2 same day | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 90.74 | Completed | No
WO-26-008843 | 2.1 | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 28.35 | Completed | No
WO-26-008844 | 2.7 | Bayou | BY-S28-02 | Trouble - no power | P2 same day | 2026-08-14 | 2026-08-14 | 2026-08-14 | Internal line |  | 83.69 | Completed | No
WO-26-008845 | 4.2 | Bayou | BY-S01-01 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 310.62 | Completed | No
WO-26-008846 | 4.7 | Bayou | BY-S27-03 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 37.53 | Completed | No
WO-26-008847 | 2 | Bayou | BY-S17-02 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 279.83 | Completed | No
WO-26-008848 | 4.7 | Bayou | BY-S29-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-14 | 2026-08-17 | 2026-08-17 | Troubleman |  | 217.86 | Completed | No
WO-26-008849 | 9.4 | Crossroads | CR-S15-02 | Corrective maintenance | P3 within 10 days | 2026-08-14 | 2026-08-15 | 2026-08-17 | Underground crew |  | 1025.24 | Completed | No
WO-26-008850 | 8.2 | Crossroads | CR-S24-03 | Corrective maintenance | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Contract line | CT-01 | 1075.92 | Completed | No
WO-26-008851 | 3.5 | Crossroads | CR-S15-01 | Corrective maintenance | P3 within 10 days | 2026-08-14 | 2026-08-19 | 2026-08-23 | Contract line | CT-02 | 1017.47 | Completed | No
WO-26-008852 | 3.8 | Crossroads | CR-S23-04 | Corrective maintenance | P3 within 10 days | 2026-08-14 | 2026-08-18 | 2026-08-22 | Internal line |  | 204.14 | Completed | No
WO-26-008853 | 0.9 | Crossroads | CR-S15-03 | Meter exchange | P3 within 10 days | 2026-08-14 | 2026-08-20 | 2026-08-20 | Meter technician |  | 132.21 | Completed | No
WO-26-008854 | 6.5 | Crossroads | CR-S01-03 | Preventive maintenance | P4 planned | 2026-08-14 | 2026-08-24 | 2026-08-24 | Internal line |  | 66.45 | Completed | No
WO-26-008855 |  | Crossroads | CR-S25-02 | Preventive maintenance | P4 planned | 2026-08-14 | 2026-09-17 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008856 |  | Crossroads | CR-S16-04 | Preventive maintenance | P4 planned | 2026-08-14 | 2026-09-13 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-008857 | 1.2 | Crossroads | CR-S22-03 | Service order - field | P3 within 10 days | 2026-08-14 | 2026-08-21 | 2026-08-25 | Meter technician |  | 28.81 | Completed | No
WO-26-008858 | 1.6 | Crossroads | CR-S25-03 | Service order - field | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Meter technician |  | 37.36 | Completed | No
WO-26-008859 | 1.2 | Crossroads | CR-S32-01 | Service order - field | P3 within 10 days | 2026-08-14 | 2026-08-23 | 2026-08-23 | Meter technician |  | 10.45 | Completed | No
WO-26-008860 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-14 | 2026-08-17 | 2026-08-21 | Contract line | CT-01 | 266.13 | Completed | No
WO-26-008861 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-14 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-008862 |  | Crossroads | CR-S32-04 | Transformer replacement | P1 emergency | 2026-08-14 | 2026-08-14 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008863 | 13.9 | Crossroads | CR-S02-03 | Transformer replacement | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Internal line |  | 7837.09 | Completed | No
WO-26-008864 |  | Crossroads | CR-S32-01 | Transformer replacement | P1 emergency | 2026-08-14 | 2026-08-14 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008865 |  | Crossroads | CR-S03-02 | Transformer replacement | P2 same day | 2026-08-14 | 2026-08-14 |  | Contract line | CT-01 |  | Open - awaiting material | No
WO-26-008866 | 5.7 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 259.32 | Completed | No
WO-26-008867 | 4 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 207.01 | Completed | No
WO-26-008868 | 5.6 | Crossroads | CR-S15-03 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 34.54 | Completed | No
WO-26-008869 | 3.8 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 32.05 | Completed | No
WO-26-008870 | 4 | Crossroads | CR-S08-02 | Trouble - no power | P2 same day | 2026-08-14 | 2026-08-15 | 2026-08-15 | Troubleman |  | 246.17 | Completed | No
WO-26-008871 | 2.9 | Crossroads | CR-S17-01 | Trouble - no power | P2 same day | 2026-08-14 | 2026-08-14 | 2026-08-14 | Internal line |  | 335.58 | Completed | No
WO-26-008872 | 2.1 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-08-14 | 2026-08-14 | 2026-08-14 | Troubleman |  | 344.21 | Completed | No
WO-26-008873 | 3.9 | Crossroads | CR-S13-05 | Trouble - partial or voltage | P3 within 10 days | 2026-08-14 | 2026-08-20 | 2026-08-20 | Troubleman |  | 226.76 | Completed | No
WO-26-008874 | 2.9 | Crossroads | CR-S04-03 | Trouble - partial or voltage | P3 within 10 days | 2026-08-14 | 2026-08-17 | 2026-08-17 | Troubleman |  | 21.03 | Completed | No
WO-26-008875 | 19.8 | Bayou | BY-S13-05 | Pole replacement | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Internal line |  | 1748.13 | Completed | No
WO-26-008876 | 0.9 | Bayou | BY-S16-06 | Service order - field | P2 same day | 2026-08-15 | 2026-08-15 | 2026-08-15 | Meter technician |  | 36.17 | Completed | No
WO-26-008877 | 1.4 | Bayou | BY-S22-04 | Service order - field | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Meter technician |  | 35.96 | Completed | No
WO-26-008878 | 1.7 | Bayou | BY-S27-01 | Service order - field | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Meter technician |  | 19.72 | Completed | No
WO-26-008879 | 0.7 | Bayou | BY-S04-03 | Service order - field | P2 same day | 2026-08-15 | 2026-08-15 | 2026-08-15 | Meter technician |  | 29.07 | Completed | No
WO-26-008880 | 7 | Bayou | BY-S16-05 | Transformer replacement | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Internal line |  | 10224.2 | Completed | No
WO-26-008881 | 4.3 | Bayou | BY-S07-01 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 71.81 | Completed | No
WO-26-008882 | 2.7 | Bayou | BY-S02-01 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Internal line |  | 249.92 | Completed | No
WO-26-008883 | 2.1 | Bayou | BY-S16-06 | Trouble - no power | P2 same day | 2026-08-15 | 2026-08-15 | 2026-08-15 | Internal line |  | 163.25 | Completed | No
WO-26-008884 | 2.7 | Bayou | BY-S02-02 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 191.64 | Completed | No
WO-26-008885 | 4.1 | Bayou | BY-S25-02 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 153.06 | Completed | No
WO-26-008886 | 4.8 | Bayou | BY-S19-03 | Trouble - partial or voltage | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Troubleman |  | 77.84 | Completed | No
WO-26-008887 | 11.4 | Crossroads | CR-S20-02 | Corrective maintenance | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Contract line | CT-02 | 219.07 | Completed | No
WO-26-008888 | 1.5 | Crossroads | CR-S17-03 | Service order - field | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Meter technician |  | 19.14 | Completed | No
WO-26-008889 | 0.6 | Crossroads | CR-S14-05 | Service order - field | P2 same day | 2026-08-15 | 2026-08-15 | 2026-08-15 | Meter technician |  | 34 | Completed | No
WO-26-008890 |  | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-08-15 | 2026-08-16 |  | Meter technician |  |  | Cancelled | No
WO-26-008891 | 12.2 | Crossroads | CR-S07-07 | Transformer replacement | P2 same day | 2026-08-15 | 2026-08-16 | 2026-08-16 | Contract line | CT-02 | 9417.28 | Completed | No
WO-26-008892 | 12.2 | Crossroads | CR-S06-03 | Transformer replacement | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Internal line |  | 6690.33 | Completed | No
WO-26-008893 | 11.3 | Crossroads | CR-S03-02 | Transformer replacement | P2 same day | 2026-08-15 | 2026-08-15 | 2026-08-15 | Internal line |  | 6842.71 | Completed | No
WO-26-008894 | 2.5 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 87.7 | Completed | No
WO-26-008895 | 3.2 | Crossroads | CR-S30-01 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 189.35 | Completed | No
WO-26-008896 | 5.7 | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 316.48 | Completed | No
WO-26-008897 | 2.6 | Crossroads | CR-S15-03 | Trouble - no power | P2 same day | 2026-08-15 | 2026-08-15 | 2026-08-15 | Troubleman |  | 139.02 | Completed | No
WO-26-008898 | 0.7 | Bayou | BY-S09-02 | Service order - field | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Meter technician |  | 31.63 | Completed | No
WO-26-008899 | 1.8 | Bayou | BY-S22-03 | Service order - field | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Meter technician |  | 30.4 | Completed | No
WO-26-008900 |  | Bayou | BY-S05-03 | Transformer replacement | P1 emergency | 2026-08-16 | 2026-08-16 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-008901 | 3.7 | Bayou | BY-S02-02 | Trouble - no power | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Internal line |  | 56 | Completed | No
WO-26-008902 | 5 | Bayou | BY-S13-06 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 249.06 | Completed | No
WO-26-008903 |  | Bayou | BY-S21-03 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 |  | Troubleman |  |  | Cancelled | No
WO-26-008904 | 3.3 | Bayou | BY-S12-02 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 342.91 | Completed | No
WO-26-008905 | 3.9 | Bayou | BY-S13-03 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 228.97 | Completed | No
WO-26-008906 | 3.5 | Bayou | BY-S19-02 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Troubleman |  | 192.61 | Completed | No
WO-26-008907 | 3.1 | Bayou | BY-S23-02 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Internal line |  | 14.94 | Completed | No
WO-26-008908 | 1.8 | Bayou | BY-S23-02 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 235.8 | Completed | No
WO-26-008909 | 4.1 | Crossroads | CR-S30-02 | Corrective maintenance | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Internal line |  | 324.14 | Completed | No
WO-26-008910 | 1.2 | Crossroads | CR-S19-03 | Service order - field | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Meter technician |  | 13.61 | Completed | No
WO-26-008911 | 0.8 | Crossroads | CR-S18-05 | Service order - field | P2 same day | 2026-08-16 | 2026-08-16 | 2026-08-16 | Meter technician |  | 14.74 | Completed | No
WO-26-008912 |  | Crossroads | CR-S13-01 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 |  | Troubleman |  |  | Cancelled | No
WO-26-008913 | 5.5 | Crossroads | CR-S25-03 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 115.04 | Completed | No
WO-26-008914 | 4.6 | Crossroads | CR-S04-05 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 9.16 | Completed | No
WO-26-008915 | 3.2 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 89.9 | Completed | No
WO-26-008916 | 2.3 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-16 | 2026-08-16 | Troubleman |  | 138.07 | Completed | No
WO-26-008917 | 3.1 | Crossroads | CR-S26-02 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Troubleman |  | 44.41 | Completed | No
WO-26-008918 | 4.8 | Crossroads | CR-S15-03 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-17 | 2026-08-17 | Troubleman |  | 106.42 | Completed | No
WO-26-008919 |  | Crossroads | CR-S22-01 | Trouble - partial or voltage | P2 same day | 2026-08-16 | 2026-08-17 |  | Troubleman |  |  | Cancelled | No
WO-26-008920 | 5.9 | Bayou | BY-S09-02 | Corrective maintenance | P3 within 10 days | 2026-08-17 | 2026-08-20 | 2026-08-22 | Underground crew |  | 1065.61 | Completed | No
WO-26-008921 |  | Bayou | BY-S18-03 | New service - small | P4 planned | 2026-08-17 | 2026-09-23 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008922 | 2.3 | Bayou | BY-S20-03 | Preventive maintenance | P4 planned | 2026-08-17 | 2026-08-27 | 2026-08-28 | Internal line |  | 104.87 | Completed | No
WO-26-008923 |  | Bayou | BY-S13-06 | Preventive maintenance | P4 planned | 2026-08-17 | 2026-10-15 |  | Underground crew |  |  | Scheduled | No
WO-26-008924 | 4.7 | Bayou | BY-S26-06 | Preventive maintenance | P4 planned | 2026-08-17 | 2026-08-26 | 2026-08-26 | Underground crew |  | 427.8 | Completed | No
WO-26-008925 | 0.7 | Bayou | BY-S24-03 | Service order - field | P3 within 10 days | 2026-08-17 | 2026-08-26 | 2026-08-30 | Meter technician |  | 22.85 | Completed | No
WO-26-008926 | 1.2 | Bayou | BY-S23-01 | Service order - field | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Meter technician |  | 28 | Completed | No
WO-26-008927 | 1.5 | Bayou | BY-S29-03 | Service order - field | P2 same day | 2026-08-17 | 2026-08-18 | 2026-08-18 | Meter technician |  | 5.55 | Completed | No
WO-26-008928 | 1.3 | Bayou | BY-S23-03 | Service order - field | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Meter technician |  | 13.8 | Completed | No
WO-26-008929 | 2.1 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-17 | 2026-08-24 | 2026-08-24 | Contract line | CT-03 | 211.96 | Completed | No
WO-26-008930 |  | Bayou | BY-S15-01 | Transformer replacement | P1 emergency | 2026-08-17 | 2026-08-17 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008931 | 12.8 | Bayou | BY-S25-02 | Transformer replacement | P3 within 10 days | 2026-08-17 | 2026-08-22 | 2026-08-24 | Internal line |  | 9258.94 | Completed | No
WO-26-008932 | 11.2 | Bayou | BY-S28-03 | Transformer replacement | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Internal line |  | 10956.59 | Completed | No
WO-26-008933 | 7.5 | Bayou | BY-S25-03 | Transformer replacement | P2 same day | 2026-08-17 | 2026-08-18 | 2026-08-18 | Contract line | CT-04 | 5381.09 | Completed | No
WO-26-008934 | 6.1 | Bayou | BY-S16-01 | Transformer replacement | P1 emergency | 2026-08-17 | 2026-08-17 | 2026-08-17 | Internal line |  | 3879.29 | Completed | No
WO-26-008935 |  | Bayou | BY-S09-04 | Transformer replacement | P3 within 10 days | 2026-08-17 | 2026-08-25 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008936 | 3.8 | Bayou | BY-S13-02 | Trouble - no power | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Troubleman |  | 159.55 | Completed | No
WO-26-008937 | 4.9 | Bayou | BY-S18-03 | Trouble - no power | P2 same day | 2026-08-17 | 2026-08-18 | 2026-08-18 | Internal line |  | 90.48 | Completed | No
WO-26-008938 | 3.6 | Bayou | BY-S25-01 | Trouble - no power | P1 emergency | 2026-08-17 | 2026-08-17 | 2026-08-17 | Troubleman |  | 189.84 | Completed | No
WO-26-008939 | 4.9 | Bayou | BY-S26-03 | Trouble - no power | P1 emergency | 2026-08-17 | 2026-08-17 | 2026-08-17 | Troubleman |  | 172.76 | Completed | No
WO-26-008940 | 3.9 | Crossroads | CR-S02-05 | Corrective maintenance | P3 within 10 days | 2026-08-17 | 2026-08-24 | 2026-08-24 | Underground crew |  | 227.2 | Completed | No
WO-26-008941 |  | Crossroads | CR-S05-06 | Corrective maintenance | P3 within 10 days | 2026-08-17 | 2026-08-25 |  | Contract line | CT-01 |  | Open - awaiting outage | No
WO-26-008942 | 5.7 | Crossroads | CR-S18-03 | Corrective maintenance | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Internal line |  | 569.17 | Completed | No
WO-26-008943 | 10.5 | Crossroads | CR-S08-06 | Corrective maintenance | P4 planned | 2026-08-17 | 2026-08-27 | 2026-08-27 | Internal line |  | 1883.17 | Completed | No
WO-26-008944 | 10.4 | Crossroads | CR-S21-02 | Corrective maintenance | P3 within 10 days | 2026-08-17 | 2026-08-22 | 2026-08-22 | Contract line | CT-02 | 598.97 | Completed | No
WO-26-008945 | 1.4 | Crossroads | CR-S14-02 | Meter exchange | P3 within 10 days | 2026-08-17 | 2026-08-27 | 2026-08-27 | Meter technician |  | 116.29 | Completed | No
WO-26-008946 |  | Crossroads | CR-S04-05 | Meter exchange | P4 planned | 2026-08-17 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-008947 | 0.7 | Crossroads | CR-S26-03 | Meter exchange | P3 within 10 days | 2026-08-17 | 2026-08-24 | 2026-08-24 | Meter technician |  | 129.81 | Completed | No
WO-26-008948 |  | Crossroads | CR-S13-02 | New service - small | P4 planned | 2026-08-17 | 2026-09-09 |  | Internal line |  |  | Scheduled | No
WO-26-008949 |  | Crossroads | CR-S17-01 | Pole replacement | P4 planned | 2026-08-17 | 2026-10-15 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-008950 | 0.7 | Crossroads | CR-S27-03 | Service order - field | P3 within 10 days | 2026-08-17 | 2026-08-21 | 2026-08-21 | Meter technician |  | 6.65 | Completed | No
WO-26-008951 | 0.9 | Crossroads | CR-S17-01 | Service order - field | P3 within 10 days | 2026-08-17 | 2026-08-25 | 2026-08-27 | Meter technician |  | 20.86 | Completed | No
WO-26-008952 | 1.6 | Crossroads | CR-S18-06 | Service order - field | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Meter technician |  | 0.56 | Completed | No
WO-26-008953 | 1.9 | Crossroads | CR-S28-03 | Service order - field | P3 within 10 days | 2026-08-17 | 2026-08-26 | 2026-08-26 | Meter technician |  | 17.32 | Completed | No
WO-26-008954 | 0.9 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-08-17 | 2026-08-18 | 2026-08-18 | Meter technician |  | 39.99 | Completed | No
WO-26-008955 | 1.2 | Crossroads | CR-S04-04 | Service order - field | P3 within 10 days | 2026-08-17 | 2026-08-21 | 2026-08-21 | Meter technician |  | 38.66 | Completed | No
WO-26-008956 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-17 | 2026-10-07 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-008957 |  | Crossroads | CR-S11-02 | Transformer replacement | P2 same day | 2026-08-17 | 2026-08-17 |  | Internal line |  |  | Open - awaiting material | No
WO-26-008958 | 7.8 | Crossroads | CR-S23-02 | Transformer replacement | P2 same day | 2026-08-17 | 2026-08-18 | 2026-08-18 | Internal line |  | 4632.7 | Completed | No
WO-26-008959 | 10.2 | Crossroads | CR-S18-05 | Transformer replacement | P1 emergency | 2026-08-17 | 2026-08-17 | 2026-08-17 | Internal line |  | 6284.27 | Completed | No
WO-26-008960 | 2.9 | Crossroads | CR-S09-02 | Trouble - no power | P1 emergency | 2026-08-17 | 2026-08-17 | 2026-08-17 | Troubleman |  | 61.68 | Completed | No
WO-26-008961 | 4.7 | Crossroads | CR-S13-02 | Trouble - no power | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Troubleman |  | 164.95 | Completed | No
WO-26-008962 | 4.8 | Crossroads | CR-S14-03 | Trouble - no power | P1 emergency | 2026-08-17 | 2026-08-17 | 2026-08-17 | Troubleman |  | 90.34 | Completed | No
WO-26-008963 | 4.4 | Crossroads | CR-S25-02 | Trouble - partial or voltage | P2 same day | 2026-08-17 | 2026-08-17 | 2026-08-17 | Internal line |  | 45.86 | Completed | No
WO-26-008964 | 1.9 | Crossroads | CR-S30-06 | Trouble - partial or voltage | P3 within 10 days | 2026-08-17 | 2026-08-21 | 2026-08-29 | Troubleman |  | 205.63 | Completed | No
WO-26-008965 | 5.8 | Bayou | BY-S07-02 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-26 | 2026-08-26 | Underground crew |  | 1816.35 | Completed | No
WO-26-008966 |  | Bayou | BY-S11-03 | Corrective maintenance | P4 planned | 2026-08-18 | 2026-08-28 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-008967 | 8.8 | Bayou | BY-S26-02 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-23 | 2026-08-25 | Contract line | CT-04 | 1844.58 | Completed | No
WO-26-008968 |  | Bayou | BY-S27-05 | Corrective maintenance | P4 planned | 2026-08-18 | 2026-10-14 |  | Internal line |  |  | Scheduled | No
WO-26-008969 | 11.1 | Bayou | BY-S15-02 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-21 | 2026-08-21 | Internal line |  | 1874.94 | Completed | No
WO-26-008970 | 9.4 | Bayou | BY-S27-02 | Corrective maintenance | P2 same day | 2026-08-18 | 2026-08-19 | 2026-08-19 | Internal line |  | 2110.02 | Completed | No
WO-26-008971 |  | Bayou | BY-S26-05 | Meter exchange | P4 planned | 2026-08-18 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-008972 |  | Bayou | BY-S16-01 | Meter exchange | P4 planned | 2026-08-18 | 2026-10-07 |  | Meter technician |  |  | Scheduled | No
WO-26-008973 |  | Bayou | BY-S06-02 | Pole replacement | P4 planned | 2026-08-18 | 2026-10-01 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008974 | 0.9 | Bayou | BY-S28-02 | Service order - field | P3 within 10 days | 2026-08-18 | 2026-08-23 | 2026-08-24 | Meter technician |  | 32.93 | Completed | No
WO-26-008975 | 0.8 | Bayou | BY-S23-03 | Service order - field | P2 same day | 2026-08-18 | 2026-08-18 | 2026-08-18 | Meter technician |  | 29.45 | Completed | No
WO-26-008976 | 0.7 | Bayou | BY-S16-03 | Service order - field | P2 same day | 2026-08-18 | 2026-08-19 | 2026-08-19 | Meter technician |  | 10.98 | Completed | No
WO-26-008977 |  | Bayou |  | Streetlight | P4 planned | 2026-08-18 | 2026-10-12 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-008978 | 2.6 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-18 | 2026-08-23 | 2026-08-23 | Contract line | CT-03 | 425.99 | Completed | No
WO-26-008979 |  | Bayou | BY-S07-06 | Transformer replacement | P2 same day | 2026-08-18 | 2026-08-18 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-008980 | 10.4 | Bayou | BY-S15-06 | Transformer replacement | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Internal line |  | 12377.5 | Completed | No
WO-26-008981 | 10.7 | Bayou | BY-S13-05 | Transformer replacement | P2 same day | 2026-08-18 | 2026-08-18 | 2026-08-18 | Contract line | CT-03 | 5315.35 | Completed | No
WO-26-008982 | 2 | Bayou | BY-S12-03 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Internal line |  | 107.86 | Completed | No
WO-26-008983 | 4.1 | Bayou | BY-S19-03 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 297.46 | Completed | No
WO-26-008984 | 5.1 | Bayou | BY-S09-05 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Internal line |  | 273.03 | Completed | No
WO-26-008985 | 4.3 | Bayou | BY-S12-01 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Internal line |  | 315.95 | Completed | No
WO-26-008986 | 3.5 | Bayou | BY-S23-04 | Trouble - partial or voltage | P2 same day | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 122.15 | Completed | No
WO-26-008987 | 10 | Crossroads | CR-S04-01 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-19 | 2026-08-20 | Contract line | CT-01 | 301.31 | Completed | No
WO-26-008988 |  | Crossroads | CR-S09-03 | Corrective maintenance | P4 planned | 2026-08-18 | 2026-09-25 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-008989 | 4.6 | Crossroads | CR-S05-05 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-22 | 2026-08-30 | Internal line |  | 1690.77 | Completed | No
WO-26-008990 |  | Crossroads | CR-S10-03 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-27 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-008991 | 10 | Crossroads | CR-S02-03 | Corrective maintenance | P3 within 10 days | 2026-08-18 | 2026-08-26 | 2026-08-26 | Underground crew |  | 1755.64 | Completed | No
WO-26-008992 | 1 | Crossroads | CR-S27-04 | Meter exchange | P3 within 10 days | 2026-08-18 | 2026-08-23 | 2026-08-23 | Meter technician |  | 178.41 | Completed | No
WO-26-008993 | 0.8 | Crossroads | CR-S23-05 | Meter exchange | P4 planned | 2026-08-18 | 2026-08-27 | 2026-08-27 | Meter technician |  | 71.49 | Completed | No
WO-26-008994 | 0.9 | Crossroads | CR-S02-04 | Meter exchange | P3 within 10 days | 2026-08-18 | 2026-08-24 | 2026-08-24 | Meter technician |  | 144.03 | Completed | No
WO-26-008995 | 0.8 | Crossroads | CR-S25-01 | Meter exchange | P3 within 10 days | 2026-08-18 | 2026-08-22 | 2026-08-23 | Meter technician |  | 82.38 | Completed | No
WO-26-008996 | 1 | Crossroads | CR-S20-02 | Meter exchange | P3 within 10 days | 2026-08-18 | 2026-08-21 | 2026-08-21 | Meter technician |  | 100.75 | Completed | No
WO-26-008997 | 1.5 | Crossroads | CR-S05-04 | Meter exchange | P3 within 10 days | 2026-08-18 | 2026-08-24 | 2026-08-28 | Meter technician |  | 179.93 | Completed | No
WO-26-008998 | 21 | Crossroads | CR-S15-02 | Pole replacement | P2 same day | 2026-08-18 | 2026-08-18 | 2026-08-18 | Contract line | CT-01 | 2401.07 | Completed | No
WO-26-008999 | 18 | Crossroads | CR-S26-03 | Pole replacement | P2 same day | 2026-08-18 | 2026-08-18 | 2026-08-18 | Contract line | CT-01 | 2864.37 | Completed | No
WO-26-009000 | 21.5 | Crossroads | CR-S22-04 | Pole replacement | P3 within 10 days | 2026-08-18 | 2026-08-22 | 2026-08-22 | Contract line | CT-01 | 1587.41 | Completed | No
WO-26-009001 |  | Crossroads | CR-S12-03 | Preventive maintenance | P4 planned | 2026-08-18 | 2026-09-15 |  | Internal line |  |  | Scheduled | No
WO-26-009002 |  | Crossroads | CR-S32-03 | Preventive maintenance | P4 planned | 2026-08-18 | 2026-10-15 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009003 |  | Crossroads | CR-S25-04 | Preventive maintenance | P4 planned | 2026-08-18 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-009004 |  | Crossroads | CR-S04-06 | Preventive maintenance | P4 planned | 2026-08-18 | 2026-10-04 |  | Internal line |  |  | Scheduled | No
WO-26-009005 | 1.4 | Crossroads | CR-S14-01 | Service order - field | P3 within 10 days | 2026-08-18 | 2026-08-25 | 2026-08-26 | Meter technician |  | 20.71 | Completed | No
WO-26-009006 | 2 | Crossroads | CR-S23-02 | Service order - field | P3 within 10 days | 2026-08-18 | 2026-08-23 | 2026-08-23 | Meter technician |  | 31.75 | Completed | No
WO-26-009007 | 1.7 | Crossroads | CR-S22-03 | Service order - field | P2 same day | 2026-08-18 | 2026-08-19 | 2026-08-19 | Meter technician |  | 29.27 | Completed | No
WO-26-009008 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-18 | 2026-08-19 | 2026-08-19 | Contract line | CT-02 | 442.75 | Completed | No
WO-26-009009 |  | Crossroads | CR-S21-03 | Transformer replacement | P2 same day | 2026-08-18 | 2026-08-18 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009010 | 5 | Crossroads | CR-S07-04 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 201.84 | Completed | No
WO-26-009011 | 2.2 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 52.82 | Completed | No
WO-26-009012 | 2.1 | Crossroads | CR-S15-02 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 189.22 | Completed | No
WO-26-009013 | 5.9 | Crossroads | CR-S13-05 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 292.92 | Completed | No
WO-26-009014 | 5.1 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 31.83 | Completed | No
WO-26-009015 | 4.8 | Crossroads | CR-S07-03 | Trouble - no power | P1 emergency | 2026-08-18 | 2026-08-18 | 2026-08-18 | Troubleman |  | 317.85 | Completed | No
WO-26-009016 | 2.5 | Crossroads | CR-S09-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-18 | 2026-08-26 | 2026-08-27 | Troubleman |  | 71.16 | Completed | No
WO-26-009017 | 2.5 | Crossroads | CR-S14-05 | Trouble - partial or voltage | P2 same day | 2026-08-18 | 2026-08-19 | 2026-08-19 | Troubleman |  | 243.25 | Completed | No
WO-26-009018 | 8.1 | Bayou | BY-S29-05 | Corrective maintenance | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Underground crew |  | 1831.71 | Completed | No
WO-26-009019 |  | Bayou | BY-S29-01 | Corrective maintenance | P4 planned | 2026-08-19 | 2026-09-16 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009020 | 3.2 | Bayou | BY-S03-03 | Corrective maintenance | P2 same day | 2026-08-19 | 2026-08-19 | 2026-08-19 | Internal line |  | 817.5 | Completed | No
WO-26-009021 | 3.4 | Bayou | BY-S29-01 | Corrective maintenance | P3 within 10 days | 2026-08-19 | 2026-08-26 | 2026-08-26 | Contract line | CT-03 | 1231.45 | Completed | No
WO-26-009022 | 0.7 | Bayou | BY-S13-05 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-29 | 2026-08-29 | Meter technician |  | 158.52 | Completed | No
WO-26-009023 | 1 | Bayou | BY-S17-04 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-28 | 2026-08-30 | Meter technician |  | 88.18 | Completed | No
WO-26-009024 | 1.2 | Bayou | BY-S27-02 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-20 | 2026-08-20 | Meter technician |  | 158.81 | Completed | No
WO-26-009025 |  | Bayou | BY-S27-04 | New service - small | P4 planned | 2026-08-19 | 2026-09-15 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-009026 | 15.6 | Bayou | BY-S20-02 | Pole replacement | P3 within 10 days | 2026-08-19 | 2026-08-24 | 2026-08-24 | Contract line | CT-03 | 2215.47 | Completed | No
WO-26-009027 | 20.3 | Bayou | BY-S13-03 | Pole replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Contract line | CT-04 | 1622.76 | Completed | No
WO-26-009028 | 22.3 | Bayou | BY-S03-01 | Pole replacement | P4 planned | 2026-08-19 | 2026-08-27 | 2026-08-28 | Contract line | CT-04 | 1845.68 | Completed | No
WO-26-009029 | 11.6 | Bayou | BY-S27-04 | Pole replacement | P3 within 10 days | 2026-08-19 | 2026-08-22 | 2026-08-22 | Contract line | CT-03 | 2104.75 | Completed | No
WO-26-009030 |  | Bayou | BY-S28-02 | Preventive maintenance | P4 planned | 2026-08-19 | 2026-09-13 |  | Underground crew |  |  | Scheduled | No
WO-26-009031 |  | Bayou | BY-S25-02 | Preventive maintenance | P4 planned | 2026-08-19 | 2026-10-07 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009032 |  | Bayou | BY-S15-03 | Preventive maintenance | P4 planned | 2026-08-19 | 2026-09-28 |  | Underground crew |  |  | Scheduled | No
WO-26-009033 |  | Bayou | BY-S18-04 | Preventive maintenance | P4 planned | 2026-08-19 | 2026-10-14 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009034 | 2 | Bayou | BY-S08-01 | Service order - field | P3 within 10 days | 2026-08-19 | 2026-08-28 | 2026-08-28 | Meter technician |  | 27.1 | Completed | No
WO-26-009035 | 1.7 | Bayou | BY-S26-02 | Service order - field | P2 same day | 2026-08-19 | 2026-08-19 | 2026-08-19 | Meter technician |  | 33.7 | Completed | No
WO-26-009036 | 0.7 | Bayou | BY-S25-02 | Service order - field | P3 within 10 days | 2026-08-19 | 2026-08-24 | 2026-08-25 | Meter technician |  | 23.71 | Completed | No
WO-26-009037 | 0.5 | Bayou | BY-S18-06 | Service order - field | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Meter technician |  | 26.55 | Completed | No
WO-26-009038 |  | Bayou |  | Streetlight | P4 planned | 2026-08-19 | 2026-09-15 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009039 | 13.2 | Bayou | BY-S27-05 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Internal line |  | 6610.57 | Completed | No
WO-26-009040 |  | Bayou | BY-S26-02 | Transformer replacement | P3 within 10 days | 2026-08-19 | 2026-08-28 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-009041 |  | Bayou | BY-S14-01 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-19 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009042 |  | Bayou | BY-S21-02 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-19 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-009043 | 9.2 | Bayou | BY-S09-04 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Contract line | CT-04 | 8830.52 | Completed | No
WO-26-009044 | 7.2 | Bayou | BY-S27-03 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Contract line | CT-04 | 8093.04 | Completed | No
WO-26-009045 |  | Bayou | BY-S03-02 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-19 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009046 | 12.9 | Bayou | BY-S07-05 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Internal line |  | 6596.17 | Completed | No
WO-26-009047 | 2.8 | Bayou | BY-S14-01 | Trouble - no power | P1 emergency | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 107.73 | Completed | No
WO-26-009048 | 2.7 | Bayou | BY-S16-06 | Trouble - no power | P1 emergency | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 346.81 | Completed | No
WO-26-009049 | 2.6 | Bayou | BY-S29-04 | Trouble - no power | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Troubleman |  | 219.5 | Completed | No
WO-26-009050 | 4.4 | Bayou | BY-S22-03 | Trouble - no power | P1 emergency | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 290.18 | Completed | No
WO-26-009051 | 4.1 | Bayou | BY-S07-06 | Trouble - no power | P1 emergency | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 222.44 | Completed | No
WO-26-009052 | 5.7 | Crossroads | CR-S15-03 | Corrective maintenance | P4 planned | 2026-08-19 | 2026-08-29 | 2026-08-29 | Contract line | CT-01 | 1473.33 | Completed | No
WO-26-009053 | 1.2 | Crossroads | CR-S05-03 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-21 | 2026-08-23 | Meter technician |  | 96.29 | Completed | No
WO-26-009054 |  | Crossroads | CR-S08-06 | Meter exchange | P4 planned | 2026-08-19 | 2026-10-01 |  | Meter technician |  |  | Scheduled | No
WO-26-009055 | 1.2 | Crossroads | CR-S26-02 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-21 | 2026-08-21 | Meter technician |  | 160.46 | Completed | No
WO-26-009056 |  | Crossroads | CR-S17-02 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-29 |  | Meter technician |  |  | Scheduled | No
WO-26-009057 |  | Crossroads | CR-S28-01 | Meter exchange | P4 planned | 2026-08-19 | 2026-10-17 |  | Meter technician |  |  | Scheduled | No
WO-26-009058 | 1.5 | Crossroads | CR-S08-02 | Meter exchange | P3 within 10 days | 2026-08-19 | 2026-08-25 | 2026-08-26 | Meter technician |  | 119.68 | Completed | No
WO-26-009059 |  | Crossroads | CR-S13-06 | Pole replacement | P4 planned | 2026-08-19 | 2026-10-01 |  | Internal line |  |  | Scheduled | No
WO-26-009060 |  | Crossroads | CR-S19-01 | Preventive maintenance | P4 planned | 2026-08-19 | 2026-10-16 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009061 | 1.2 | Crossroads | CR-S04-04 | Service order - field | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Meter technician |  | 18.04 | Completed | No
WO-26-009062 | 0.5 | Crossroads | CR-S13-01 | Service order - field | P3 within 10 days | 2026-08-19 | 2026-08-23 | 2026-08-23 | Meter technician |  | 36.78 | Completed | No
WO-26-009063 | 1.9 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-19 | 2026-08-22 | 2026-08-22 | Contract line | CT-02 | 352.67 | Completed | No
WO-26-009064 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-19 | 2026-09-29 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009065 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-19 | 2026-09-11 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009066 | 11.7 | Crossroads | CR-S17-01 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Internal line |  | 3016.37 | Completed | No
WO-26-009067 | 13.1 | Crossroads | CR-S07-01 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-19 | 2026-08-19 | Internal line |  | 3434.32 | Completed | No
WO-26-009068 | 12.9 | Crossroads | CR-S15-01 | Transformer replacement | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Internal line |  | 8592.66 | Completed | No
WO-26-009069 | 3.4 | Crossroads | CR-S09-04 | Trouble - no power | P1 emergency | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 225.55 | Completed | No
WO-26-009070 | 2.4 | Crossroads | CR-S23-05 | Trouble - no power | P2 same day | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 157.8 | Completed | No
WO-26-009071 | 3.3 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-08-19 | 2026-08-19 | 2026-08-19 | Internal line |  | 208.67 | Completed | No
WO-26-009072 | 3.5 | Crossroads | CR-S13-01 | Trouble - no power | P2 same day | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 182.24 | Completed | No
WO-26-009073 | 4 | Crossroads | CR-S29-01 | Trouble - partial or voltage | P2 same day | 2026-08-19 | 2026-08-20 | 2026-08-20 | Troubleman |  | 135.34 | Completed | No
WO-26-009074 | 3.2 | Crossroads | CR-S28-01 | Trouble - partial or voltage | P2 same day | 2026-08-19 | 2026-08-19 | 2026-08-19 | Troubleman |  | 26.06 | Completed | No
WO-26-009075 | 3.4 | Crossroads | CR-S20-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-19 | 2026-08-26 | 2026-08-26 | Troubleman |  | 96.65 | Completed | No
WO-26-009076 | 3.9 | Crossroads | CR-S22-04 | Trouble - partial or voltage | P3 within 10 days | 2026-08-19 | 2026-08-27 | 2026-08-27 | Troubleman |  | 60.22 | Completed | No
WO-26-009077 | 9.6 | Bayou | BY-S06-02 | Corrective maintenance | P3 within 10 days | 2026-08-20 | 2026-08-24 | 2026-08-24 | Underground crew |  | 1155.27 | Completed | No
WO-26-009078 | 11.3 | Bayou | BY-S29-04 | Corrective maintenance | P2 same day | 2026-08-20 | 2026-08-21 | 2026-08-21 | Contract line | CT-04 | 1463.07 | Completed | No
WO-26-009079 | 1.1 | Bayou | BY-S16-06 | Meter exchange | P3 within 10 days | 2026-08-20 | 2026-08-22 | 2026-08-30 | Meter technician |  | 79.78 | Completed | No
WO-26-009080 | 0.5 | Bayou | BY-S15-02 | Meter exchange | P3 within 10 days | 2026-08-20 | 2026-08-28 | 2026-08-29 | Meter technician |  | 114.79 | Completed | No
WO-26-009081 | 0.5 | Bayou | BY-S26-02 | Meter exchange | P3 within 10 days | 2026-08-20 | 2026-08-22 | 2026-08-22 | Meter technician |  | 99.4 | Completed | No
WO-26-009082 |  | Bayou | BY-S15-06 | New service - small | P4 planned | 2026-08-20 | 2026-10-17 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009083 |  | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-08-20 | 2026-09-21 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009084 |  | Bayou | BY-S19-02 | Preventive maintenance | P4 planned | 2026-08-20 | 2026-10-06 |  | Underground crew |  |  | Scheduled | No
WO-26-009085 | 3.3 | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-08-20 | 2026-08-28 | 2026-08-28 | Internal line |  | 419.6 | Completed | No
WO-26-009086 | 1.8 | Bayou | BY-S03-02 | Service order - field | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Meter technician |  | 14.52 | Completed | No
WO-26-009087 | 1.9 | Bayou | BY-S24-05 | Service order - field | P3 within 10 days | 2026-08-20 | 2026-08-24 | 2026-08-24 | Meter technician |  | 17.36 | Completed | No
WO-26-009088 | 0.7 | Bayou | BY-S09-04 | Service order - field | P3 within 10 days | 2026-08-20 | 2026-08-23 | 2026-08-31 | Meter technician |  | 15.77 | Completed | No
WO-26-009089 |  | Bayou |  | Streetlight | P4 planned | 2026-08-20 | 2026-10-08 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009090 | 13.5 | Bayou | BY-S01-01 | Transformer replacement | P3 within 10 days | 2026-08-20 | 2026-08-27 | 2026-08-27 | Internal line |  | 12478.55 | Completed | No
WO-26-009091 | 10.3 | Bayou | BY-S20-02 | Transformer replacement | P2 same day | 2026-08-20 | 2026-08-21 | 2026-08-21 | Internal line |  | 2994.3 | Completed | No
WO-26-009092 |  | Bayou | BY-S08-02 | Transformer replacement | P3 within 10 days | 2026-08-20 | 2026-08-29 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009093 | 9.3 | Bayou | BY-S30-01 | Transformer replacement | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Internal line |  | 10908.78 | Completed | No
WO-26-009094 | 12.1 | Bayou | BY-S04-02 | Transformer replacement | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Internal line |  | 3427.27 | Completed | No
WO-26-009095 | 2.1 | Bayou | BY-S04-02 | Trouble - no power | P2 same day | 2026-08-20 | 2026-08-21 | 2026-08-21 | Troubleman |  | 96.14 | Completed | No
WO-26-009096 | 5.7 | Bayou | BY-S05-03 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 43.24 | Completed | No
WO-26-009097 | 2.9 | Bayou | BY-S18-01 | Trouble - partial or voltage | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 122.49 | Completed | No
WO-26-009098 | 3.9 | Bayou | BY-S16-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-20 | 2026-08-26 | 2026-08-26 | Troubleman |  | 229.33 | Completed | No
WO-26-009099 | 2.5 | Bayou | BY-S19-01 | Trouble - partial or voltage | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 204.02 | Completed | No
WO-26-009100 |  | Crossroads | CR-S32-04 | Corrective maintenance | P3 within 10 days | 2026-08-20 | 2026-08-24 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-009101 |  | Crossroads | CR-S30-06 | Meter exchange | P4 planned | 2026-08-20 | 2026-10-19 |  | Meter technician |  |  | Scheduled | No
WO-26-009102 | 0.8 | Crossroads | CR-S07-01 | Meter exchange | P3 within 10 days | 2026-08-20 | 2026-08-23 | 2026-08-23 | Meter technician |  | 171.94 | Completed | No
WO-26-009103 |  | Crossroads | CR-S14-02 | Meter exchange | P4 planned | 2026-08-20 | 2026-09-08 |  | Meter technician |  |  | Scheduled | No
WO-26-009104 | 16 | Crossroads | CR-S24-03 | Pole replacement | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Contract line | CT-02 | 1623.91 | Completed | No
WO-26-009105 |  | Crossroads | CR-S17-03 | Pole replacement | P4 planned | 2026-08-20 | 2026-10-03 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-009106 |  | Crossroads | CR-S26-03 | Pole replacement | P4 planned | 2026-08-20 | 2026-10-07 |  | Internal line |  |  | Scheduled | No
WO-26-009107 | 1.3 | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-08-20 | 2026-08-27 | 2026-08-27 | Meter technician |  | 13.89 | Completed | No
WO-26-009108 | 1.3 | Crossroads | CR-S08-03 | Service order - field | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Meter technician |  | 34.08 | Completed | No
WO-26-009109 | 0.6 | Crossroads | CR-S19-03 | Service order - field | P3 within 10 days | 2026-08-20 | 2026-08-22 | 2026-08-26 | Meter technician |  | 18.68 | Completed | No
WO-26-009110 | 1.5 | Crossroads | CR-S12-03 | Service order - field | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Meter technician |  | 32.62 | Completed | No
WO-26-009111 | 1.2 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-08-20 | 2026-08-20 | 2026-08-20 | Meter technician |  | 22.32 | Completed | No
WO-26-009112 | 0.9 | Crossroads | CR-S24-04 | Service order - field | P3 within 10 days | 2026-08-20 | 2026-08-27 | 2026-08-31 | Meter technician |  | 17.45 | Completed | No
WO-26-009113 | 0.5 | Crossroads | CR-S04-05 | Service order - field | P3 within 10 days | 2026-08-20 | 2026-08-25 | 2026-08-26 | Meter technician |  | 11.87 | Completed | No
WO-26-009114 | 2.4 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-20 | 2026-08-21 | 2026-08-21 | Internal line |  | 162.6 | Completed | No
WO-26-009115 | 2.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-20 | 2026-08-25 | 2026-08-27 | Contract line | CT-01 | 226.73 | Completed | No
WO-26-009116 |  | Crossroads | CR-S21-01 | Transformer replacement | P3 within 10 days | 2026-08-20 | 2026-08-22 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009117 | 4 | Crossroads | CR-S11-02 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Internal line |  | 143.41 | Completed | No
WO-26-009118 | 5.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 226.27 | Completed | No
WO-26-009119 | 3.7 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 293.85 | Completed | No
WO-26-009120 | 4.1 | Crossroads | CR-S17-01 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 345.79 | Completed | No
WO-26-009121 | 2.7 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Internal line |  | 334.29 | Completed | No
WO-26-009122 | 3.6 | Crossroads | CR-S18-05 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 335.83 | Completed | No
WO-26-009123 | 5.7 | Crossroads | CR-S08-02 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 229.69 | Completed | No
WO-26-009124 | 4.2 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 179.28 | Completed | No
WO-26-009125 | 4.1 | Crossroads | CR-S11-01 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Internal line |  | 23.92 | Completed | No
WO-26-009126 | 4.4 | Crossroads | CR-S13-06 | Trouble - no power | P1 emergency | 2026-08-20 | 2026-08-20 | 2026-08-20 | Troubleman |  | 95.87 | Completed | No
WO-26-009127 | 1.8 | Crossroads | CR-S04-06 | Trouble - partial or voltage | P3 within 10 days | 2026-08-20 | 2026-08-25 | 2026-08-26 | Troubleman |  | 238.69 | Completed | No
WO-26-009128 | 3.7 | Crossroads | CR-S13-02 | Trouble - partial or voltage | P2 same day | 2026-08-20 | 2026-08-21 | 2026-08-21 | Troubleman |  | 199.6 | Completed | No
WO-26-009129 |  | Bayou | BY-S06-01 | Corrective maintenance | P4 planned | 2026-08-21 | 2026-10-04 |  | Underground crew |  |  | Scheduled | No
WO-26-009130 | 10.1 | Bayou | BY-S29-04 | Corrective maintenance | P4 planned | 2026-08-21 | 2026-08-29 | 2026-08-29 | Contract line | CT-04 | 1725.78 | Completed | No
WO-26-009131 | 4 | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-26 | 2026-08-26 | Internal line |  | 2065.75 | Completed | No
WO-26-009132 |  | Bayou | BY-S19-01 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-31 |  | Contract line | CT-04 |  | Open - awaiting outage | No
WO-26-009133 |  | Bayou | BY-S20-02 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-26 |  | Meter technician |  |  | Scheduled | No
WO-26-009134 | 0.6 | Bayou | BY-S26-03 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-29 | 2026-08-31 | Meter technician |  | 141.5 | Completed | No
WO-26-009135 | 1.4 | Bayou | BY-S24-01 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-25 | 2026-08-25 | Meter technician |  | 112.17 | Completed | No
WO-26-009136 | 0.5 | Bayou | BY-S06-02 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-26 | 2026-08-26 | Meter technician |  | 176.65 | Completed | No
WO-26-009137 | 1.5 | Bayou | BY-S12-02 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-29 | 2026-08-29 | Meter technician |  | 113.22 | Completed | No
WO-26-009138 |  | Bayou | BY-S25-01 | Pole replacement | P4 planned | 2026-08-21 | 2026-09-28 |  | Internal line |  |  | Scheduled | No
WO-26-009139 |  | Bayou | BY-S11-01 | Pole replacement | P4 planned | 2026-08-21 | 2026-09-10 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009140 |  | Bayou | BY-S04-01 | Preventive maintenance | P4 planned | 2026-08-21 | 2026-10-17 |  | Internal line |  |  | Scheduled | No
WO-26-009141 | 1.4 | Bayou | BY-S25-05 | Service order - field | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Meter technician |  | 20.64 | Completed | No
WO-26-009142 |  | Bayou | BY-S10-05 | Service order - field | P3 within 10 days | 2026-08-21 | 2026-08-28 |  | Meter technician |  |  | Scheduled | No
WO-26-009143 |  | Bayou |  | Streetlight | P4 planned | 2026-08-21 | 2026-10-02 |  | Internal line |  |  | Scheduled | No
WO-26-009144 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-21 | 2026-08-28 | 2026-08-28 | Internal line |  | 409.83 | Completed | No
WO-26-009145 |  | Bayou |  | Streetlight | P4 planned | 2026-08-21 | 2026-10-13 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009146 | 2.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-21 | 2026-08-22 | 2026-08-22 | Internal line |  | 383.41 | Completed | No
WO-26-009147 | 1.8 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-21 | 2026-08-28 | 2026-08-30 | Contract line | CT-04 | 291.2 | Completed | No
WO-26-009148 |  | Bayou |  | Streetlight | P4 planned | 2026-08-21 | 2026-10-03 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009149 |  | Bayou | BY-S19-01 | Transformer replacement | P1 emergency | 2026-08-21 | 2026-08-21 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009150 |  | Bayou | BY-S30-01 | Transformer replacement | P2 same day | 2026-08-21 | 2026-08-22 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-009151 | 4.7 | Bayou | BY-S14-03 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Internal line |  | 241.23 | Completed | No
WO-26-009152 | 5.3 | Bayou | BY-S27-03 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 114.18 | Completed | No
WO-26-009153 | 5.9 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 301.61 | Completed | No
WO-26-009154 | 2.7 | Bayou | BY-S20-02 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 34.25 | Completed | No
WO-26-009155 | 4.9 | Bayou | BY-S15-02 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 16.6 | Completed | No
WO-26-009156 | 3.2 | Bayou | BY-S28-03 | Trouble - partial or voltage | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 185.25 | Completed | No
WO-26-009157 | 2.3 | Bayou | BY-S27-04 | Trouble - partial or voltage | P2 same day | 2026-08-21 | 2026-08-22 | 2026-08-22 | Troubleman |  | 134.83 | Completed | No
WO-26-009158 | 2.9 | Bayou | BY-S19-03 | Trouble - partial or voltage | P2 same day | 2026-08-21 | 2026-08-22 | 2026-08-22 | Troubleman |  | 107.89 | Completed | No
WO-26-009159 | 10.7 | Crossroads | CR-S28-01 | Corrective maintenance | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Contract line | CT-01 | 2029.61 | Completed | No
WO-26-009160 |  | Crossroads | CR-S30-03 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-31 |  | Internal line |  |  | Scheduled | No
WO-26-009161 | 5.6 | Crossroads | CR-S12-02 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-30 | 2026-08-30 | Underground crew |  | 1929.34 | Completed | No
WO-26-009162 | 6 | Crossroads | CR-S01-02 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-29 | 2026-08-29 | Underground crew |  | 2223.36 | Completed | No
WO-26-009163 | 6.8 | Crossroads | CR-S05-02 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-23 | 2026-08-27 | Contract line | CT-02 | 399.1 | Completed | No
WO-26-009164 | 8.1 | Crossroads | CR-S25-06 | Corrective maintenance | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Underground crew |  | 861.31 | Completed | No
WO-26-009165 | 11.7 | Crossroads | CR-S15-02 | Corrective maintenance | P3 within 10 days | 2026-08-21 | 2026-08-27 | 2026-08-28 | Internal line |  | 1084.57 | Completed | No
WO-26-009166 |  | Crossroads | CR-S31-03 | Meter exchange | P4 planned | 2026-08-21 | 2026-09-21 |  | Meter technician |  |  | Scheduled | No
WO-26-009167 | 1.2 | Crossroads | CR-S27-03 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-25 | 2026-08-26 | Meter technician |  | 165.85 | Completed | No
WO-26-009168 |  | Crossroads | CR-S21-03 | Meter exchange | P4 planned | 2026-08-21 | 2026-09-29 |  | Meter technician |  |  | Cancelled | No
WO-26-009169 | 0.6 | Crossroads | CR-S21-03 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-28 | 2026-08-29 | Meter technician |  | 105.96 | Completed | No
WO-26-009170 |  | Crossroads | CR-S28-01 | Meter exchange | P4 planned | 2026-08-21 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009171 | 0.8 | Crossroads | CR-S03-01 | Meter exchange | P3 within 10 days | 2026-08-21 | 2026-08-25 | 2026-08-27 | Meter technician |  | 160.41 | Completed | No
WO-26-009172 |  | Crossroads | CR-S30-05 | New service - small | P4 planned | 2026-08-21 | 2026-10-08 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009173 |  | Crossroads | CR-S05-03 | New service - small | P4 planned | 2026-08-21 | 2026-10-12 |  | Underground crew |  |  | Scheduled | No
WO-26-009174 | 13.4 | Crossroads | CR-S02-05 | New service - small | P4 planned | 2026-08-21 | 2026-08-31 | 2026-08-31 | Underground crew |  | 435.9 | Completed | No
WO-26-009175 | 9 | Crossroads | CR-S20-02 | New service - small | P3 within 10 days | 2026-08-21 | 2026-08-23 | 2026-08-31 | Contract line | CT-02 | 625.86 | Completed | No
WO-26-009176 |  | Crossroads | CR-S24-03 | Pole replacement | P4 planned | 2026-08-21 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-009177 |  | Crossroads | CR-S22-04 | Preventive maintenance | P4 planned | 2026-08-21 | 2026-10-13 |  | Internal line |  |  | Scheduled | No
WO-26-009178 |  | Crossroads | CR-S14-03 | Preventive maintenance | P4 planned | 2026-08-21 | 2026-09-26 |  | Contract line | CT-02 |  | Open - awaiting outage | No
WO-26-009179 |  | Crossroads | CR-S22-03 | Preventive maintenance | P4 planned | 2026-08-21 | 2026-09-12 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009180 | 1.4 | Crossroads | CR-S28-01 | Service order - field | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Meter technician |  | 9.85 | Completed | No
WO-26-009181 | 0.7 | Crossroads | CR-S01-03 | Service order - field | P2 same day | 2026-08-21 | 2026-08-22 | 2026-08-22 | Meter technician |  | 23.96 | Completed | No
WO-26-009182 | 1.6 | Crossroads | CR-S29-02 | Service order - field | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Meter technician |  | 23.83 | Completed | No
WO-26-009183 | 1.7 | Crossroads | CR-S05-01 | Service order - field | P3 within 10 days | 2026-08-21 | 2026-08-25 | 2026-08-25 | Meter technician |  | 12.95 | Completed | No
WO-26-009184 | 1.7 | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-21 | 2026-08-26 | 2026-08-27 | Contract line | CT-02 | 244.85 | Completed | No
WO-26-009185 | 6.3 | Crossroads | CR-S12-01 | Transformer replacement | P2 same day | 2026-08-21 | 2026-08-22 | 2026-08-22 | Internal line |  | 7857.75 | Completed | No
WO-26-009186 | 3.8 | Crossroads | CR-S15-01 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 179.18 | Completed | No
WO-26-009187 | 2.6 | Crossroads | CR-S02-04 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 91.7 | Completed | No
WO-26-009188 | 5.9 | Crossroads | CR-S32-01 | Trouble - no power | P1 emergency | 2026-08-21 | 2026-08-21 | 2026-08-21 | Troubleman |  | 22.99 | Completed | No
WO-26-009189 | 2.5 | Crossroads | CR-S29-03 | Trouble - partial or voltage | P2 same day | 2026-08-21 | 2026-08-21 | 2026-08-21 | Internal line |  | 25.87 | Completed | No
WO-26-009190 | 5 | Crossroads | CR-S07-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-21 | 2026-08-27 | 2026-08-28 | Troubleman |  | 204.37 | Completed | No
WO-26-009191 | 2 | Crossroads | CR-S22-03 | Trouble - partial or voltage | P2 same day | 2026-08-21 | 2026-08-22 | 2026-08-22 | Troubleman |  | 95.23 | Completed | No
WO-26-009192 | 1.4 | Bayou | BY-S18-05 | Service order - field | P2 same day | 2026-08-22 | 2026-08-23 | 2026-08-23 | Meter technician |  | 24.34 | Completed | No
WO-26-009193 | 1.2 | Bayou | BY-S27-04 | Service order - field | P2 same day | 2026-08-22 | 2026-08-22 | 2026-08-22 | Meter technician |  | 5.54 | Completed | No
WO-26-009194 | 0.9 | Bayou | BY-S18-04 | Service order - field | P2 same day | 2026-08-22 | 2026-08-22 | 2026-08-22 | Meter technician |  | 28.85 | Completed | No
WO-26-009195 |  | Bayou | BY-S25-02 | Transformer replacement | P2 same day | 2026-08-22 | 2026-08-23 |  | Internal line |  |  | Cancelled | No
WO-26-009196 | 7.3 | Bayou | BY-S16-06 | Transformer replacement | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Internal line |  | 10117.12 | Completed | No
WO-26-009197 |  | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 |  | Troubleman |  |  | Cancelled | No
WO-26-009198 | 4 | Bayou | BY-S07-04 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Internal line |  | 60.16 | Completed | No
WO-26-009199 | 4.9 | Bayou | BY-S24-03 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Internal line |  | 315.31 | Completed | No
WO-26-009200 | 4.9 | Bayou | BY-S22-03 | Trouble - no power | P2 same day | 2026-08-22 | 2026-08-22 | 2026-08-22 | Troubleman |  | 187.61 | Completed | No
WO-26-009201 | 5.9 | Crossroads | CR-S15-01 | Corrective maintenance | P2 same day | 2026-08-22 | 2026-08-23 | 2026-08-23 | Internal line |  | 688.27 | Completed | No
WO-26-009202 | 1.2 | Crossroads | CR-S16-06 | Service order - field | P2 same day | 2026-08-22 | 2026-08-22 | 2026-08-22 | Meter technician |  | 11.4 | Completed | No
WO-26-009203 | 13.1 | Crossroads | CR-S14-01 | Transformer replacement | P2 same day | 2026-08-22 | 2026-08-22 | 2026-08-22 | Internal line |  | 6201.45 | Completed | No
WO-26-009204 | 2.9 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Troubleman |  | 23.83 | Completed | No
WO-26-009205 | 2.5 | Crossroads | CR-S14-01 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Troubleman |  | 211.14 | Completed | No
WO-26-009206 | 5.8 | Crossroads | CR-S18-03 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Internal line |  | 245.84 | Completed | No
WO-26-009207 | 2.6 | Crossroads | CR-S26-01 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Troubleman |  | 171.34 | Completed | No
WO-26-009208 | 5.2 | Crossroads | CR-S04-01 | Trouble - no power | P2 same day | 2026-08-22 | 2026-08-22 | 2026-08-22 | Troubleman |  | 223.47 | Completed | No
WO-26-009209 | 5.4 | Crossroads | CR-S10-03 | Trouble - no power | P2 same day | 2026-08-22 | 2026-08-23 | 2026-08-23 | Troubleman |  | 315.8 | Completed | No
WO-26-009210 | 5.5 | Crossroads | CR-S16-01 | Trouble - no power | P1 emergency | 2026-08-22 | 2026-08-22 | 2026-08-22 | Troubleman |  | 72.95 | Completed | No
WO-26-009211 | 1.9 | Crossroads | CR-S13-06 | Trouble - partial or voltage | P2 same day | 2026-08-22 | 2026-08-23 | 2026-08-23 | Troubleman |  | 113.98 | Completed | No
WO-26-009212 | 0.9 | Bayou | BY-S29-04 | Service order - field | P2 same day | 2026-08-23 | 2026-08-24 | 2026-08-24 | Meter technician |  | 18.9 | Completed | No
WO-26-009213 | 2.3 | Bayou | BY-S02-02 | Trouble - no power | P1 emergency | 2026-08-23 | 2026-08-23 | 2026-08-23 | Troubleman |  | 321.8 | Completed | No
WO-26-009214 | 5.2 | Bayou | BY-S09-01 | Trouble - no power | P1 emergency | 2026-08-23 | 2026-08-23 | 2026-08-23 | Internal line |  | 331.38 | Completed | No
WO-26-009215 | 2.6 | Bayou | BY-S13-01 | Trouble - no power | P1 emergency | 2026-08-23 | 2026-08-23 | 2026-08-23 | Troubleman |  | 242.23 | Completed | No
WO-26-009216 | 4 | Bayou | BY-S14-01 | Trouble - no power | P2 same day | 2026-08-23 | 2026-08-24 | 2026-08-24 | Troubleman |  | 100.68 | Completed | No
WO-26-009217 | 3.4 | Bayou | BY-S25-02 | Trouble - partial or voltage | P2 same day | 2026-08-23 | 2026-08-23 | 2026-08-23 | Internal line |  | 194.25 | Completed | No
WO-26-009218 | 2.8 | Bayou | BY-S29-01 | Trouble - partial or voltage | P2 same day | 2026-08-23 | 2026-08-23 | 2026-08-23 | Troubleman |  | 60.24 | Completed | No
WO-26-009219 | 2 | Bayou | BY-S23-03 | Trouble - partial or voltage | P2 same day | 2026-08-23 | 2026-08-23 | 2026-08-23 | Troubleman |  | 181.27 | Completed | No
WO-26-009220 | 3.2 | Crossroads | CR-S30-06 | Trouble - no power | P2 same day | 2026-08-23 | 2026-08-24 | 2026-08-24 | Troubleman |  | 102.58 | Completed | No
WO-26-009221 | 3.3 | Crossroads | CR-S23-03 | Trouble - no power | P1 emergency | 2026-08-23 | 2026-08-23 | 2026-08-23 | Troubleman |  | 189.19 | Completed | No
WO-26-009222 |  | Bayou | BY-S21-02 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-09-01 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009223 |  | Bayou | BY-S08-03 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-08-28 |  | Internal line |  |  | Scheduled | No
WO-26-009224 |  | Bayou | BY-S15-02 | Corrective maintenance | P2 same day | 2026-08-24 | 2026-08-25 |  | Underground crew |  |  | Cancelled | No
WO-26-009225 | 10 | Bayou | BY-S13-01 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-08-26 | 2026-08-30 | Internal line |  | 1163.54 | Completed | No
WO-26-009226 |  | Bayou | BY-S14-01 | Meter exchange | P4 planned | 2026-08-24 | 2026-09-26 |  | Meter technician |  |  | Scheduled | No
WO-26-009227 |  | Bayou | BY-S25-05 | Meter exchange | P4 planned | 2026-08-24 | 2026-10-12 |  | Meter technician |  |  | Scheduled | No
WO-26-009228 |  | Bayou | BY-S21-05 | Meter exchange | P3 within 10 days | 2026-08-24 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-009229 |  | Bayou | BY-S10-05 | Meter exchange | P3 within 10 days | 2026-08-24 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-009230 | 0.5 | Bayou | BY-S22-03 | Meter exchange | P3 within 10 days | 2026-08-24 | 2026-08-28 | 2026-08-30 | Meter technician |  | 65.25 | Completed | No
WO-26-009231 |  | Bayou | BY-S05-02 | Meter exchange | P4 planned | 2026-08-24 | 2026-09-10 |  | Meter technician |  |  | Scheduled | No
WO-26-009232 | 0.9 | Bayou | BY-S29-04 | Meter exchange | P3 within 10 days | 2026-08-24 | 2026-08-25 | 2026-08-26 | Meter technician |  | 76.61 | Completed | No
WO-26-009233 |  | Bayou | BY-S03-02 | Meter exchange | P4 planned | 2026-08-24 | 2026-10-17 |  | Meter technician |  |  | Scheduled | No
WO-26-009234 | 6.3 | Bayou | BY-S02-02 | New service - small | P3 within 10 days | 2026-08-24 | 2026-08-28 | 2026-08-28 | Contract line | CT-04 | 2871.08 | Completed | No
WO-26-009235 |  | Bayou | BY-S06-01 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-10-17 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009236 |  | Bayou | BY-S27-02 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-09-21 |  | Underground crew |  |  | Scheduled | No
WO-26-009237 |  | Bayou | BY-S08-01 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-09-09 |  | Underground crew |  |  | Scheduled | No
WO-26-009238 | 1.4 | Bayou | BY-S27-05 | Service order - field | P2 same day | 2026-08-24 | 2026-08-24 | 2026-08-24 | Meter technician |  | 25.29 | Completed | No
WO-26-009239 | 0.9 | Bayou | BY-S09-05 | Service order - field | P2 same day | 2026-08-24 | 2026-08-24 | 2026-08-24 | Meter technician |  | 23.45 | Completed | No
WO-26-009240 | 1.2 | Bayou | BY-S23-04 | Service order - field | P2 same day | 2026-08-24 | 2026-08-25 | 2026-08-25 | Meter technician |  | 28.5 | Completed | No
WO-26-009241 |  | Bayou | BY-S18-04 | Service order - field | P3 within 10 days | 2026-08-24 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-009242 |  | Bayou | BY-S29-01 | Service order - field | P3 within 10 days | 2026-08-24 | 2026-08-29 |  | Meter technician |  |  | Scheduled | No
WO-26-009243 | 1.3 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-24 | 2026-08-29 | 2026-08-29 | Internal line |  | 55.75 | Completed | No
WO-26-009244 |  | Bayou |  | Streetlight | P4 planned | 2026-08-24 | 2026-10-07 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009245 |  | Bayou | BY-S29-03 | Transformer replacement | P3 within 10 days | 2026-08-24 | 2026-09-02 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009246 | 5.5 | Bayou | BY-S07-03 | Trouble - no power | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Internal line |  | 322.99 | Completed | No
WO-26-009247 | 5.7 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Troubleman |  | 302.82 | Completed | No
WO-26-009248 | 5.3 | Bayou | BY-S06-02 | Trouble - no power | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Internal line |  | 175.85 | Completed | No
WO-26-009249 | 4 | Bayou | BY-S22-02 | Trouble - no power | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Troubleman |  | 311.89 | Completed | No
WO-26-009250 |  | Bayou | BY-S27-05 | Trouble - partial or voltage | P3 within 10 days | 2026-08-24 | 2026-09-02 |  | Troubleman |  |  | Scheduled | No
WO-26-009251 |  | Crossroads | CR-S29-03 | Corrective maintenance | P4 planned | 2026-08-24 | 2026-09-01 |  | Underground crew |  |  | Scheduled | No
WO-26-009252 |  | Crossroads | CR-S04-06 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-09-03 |  | Underground crew |  |  | Scheduled | No
WO-26-009253 | 10.2 | Crossroads | CR-S25-03 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-08-25 | 2026-08-27 | Contract line | CT-02 | 1519.14 | Completed | No
WO-26-009254 | 5.5 | Crossroads | CR-S30-04 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-08-27 | 2026-08-27 | Underground crew |  | 2272.8 | Completed | No
WO-26-009255 |  | Crossroads | CR-S14-03 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-09-01 |  | Internal line |  |  | Scheduled | No
WO-26-009256 | 10.7 | Crossroads | CR-S13-05 | Corrective maintenance | P3 within 10 days | 2026-08-24 | 2026-08-28 | 2026-08-28 | Internal line |  | 84.23 | Completed | No
WO-26-009257 |  | Crossroads | CR-S07-02 | Meter exchange | P4 planned | 2026-08-24 | 2026-09-19 |  | Meter technician |  |  | Scheduled | No
WO-26-009258 |  | Crossroads | CR-S21-03 | New service - small | P4 planned | 2026-08-24 | 2026-10-13 |  | Underground crew |  |  | Scheduled | No
WO-26-009259 |  | Crossroads | CR-S20-05 | New service - small | P3 within 10 days | 2026-08-24 | 2026-09-02 |  | Contract line | CT-01 |  | Open - awaiting material | No
WO-26-009260 | 7.4 | Crossroads | CR-S07-03 | New service - small | P4 planned | 2026-08-24 | 2026-08-31 | 2026-08-31 | Contract line | CT-02 | 3546.98 | Completed | No
WO-26-009261 |  | Crossroads | CR-S19-04 | Pole replacement | P4 planned | 2026-08-24 | 2026-09-15 |  | Internal line |  |  | Scheduled | No
WO-26-009262 |  | Crossroads | CR-S07-05 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-09-09 |  | Internal line |  |  | Scheduled | No
WO-26-009263 |  | Crossroads | CR-S23-05 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-09-14 |  | Internal line |  |  | Scheduled | No
WO-26-009264 |  | Crossroads | CR-S04-03 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-10-07 |  | Underground crew |  |  | Scheduled | No
WO-26-009265 |  | Crossroads | CR-S26-03 | Preventive maintenance | P4 planned | 2026-08-24 | 2026-09-16 |  | Internal line |  |  | Scheduled | No
WO-26-009266 | 0.5 | Crossroads | CR-S25-01 | Service order - field | P2 same day | 2026-08-24 | 2026-08-25 | 2026-08-25 | Meter technician |  | 20.94 | Completed | No
WO-26-009267 |  | Crossroads | CR-S31-02 | Service order - field | P3 within 10 days | 2026-08-24 | 2026-08-31 |  | Meter technician |  |  | Scheduled | No
WO-26-009268 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-24 | 2026-09-06 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009269 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-24 | 2026-09-11 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009270 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-24 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-009271 |  | Crossroads | CR-S21-01 | Transformer replacement | P2 same day | 2026-08-24 | 2026-08-25 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009272 | 6.5 | Crossroads | CR-S16-02 | Transformer replacement | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Contract line | CT-02 | 7970.67 | Completed | No
WO-26-009273 |  | Crossroads | CR-S18-03 | Transformer replacement | P1 emergency | 2026-08-24 | 2026-08-24 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-009274 | 3.3 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Troubleman |  | 306.38 | Completed | No
WO-26-009275 | 3.5 | Crossroads | CR-S01-02 | Trouble - no power | P2 same day | 2026-08-24 | 2026-08-25 | 2026-08-25 | Troubleman |  | 218.85 | Completed | No
WO-26-009276 | 4.8 | Crossroads | CR-S18-01 | Trouble - no power | P1 emergency | 2026-08-24 | 2026-08-24 | 2026-08-24 | Troubleman |  | 134.62 | Completed | No
WO-26-009277 | 3.7 | Crossroads | CR-S14-02 | Trouble - partial or voltage | P2 same day | 2026-08-24 | 2026-08-24 | 2026-08-24 | Troubleman |  | 88.7 | Completed | No
WO-26-009278 | 5.5 | Bayou | BY-S09-02 | Corrective maintenance | P2 same day | 2026-08-25 | 2026-08-26 | 2026-08-26 | Contract line | CT-04 | 744.4 | Completed | No
WO-26-009279 | 3.5 | Bayou | BY-S07-05 | Corrective maintenance | P3 within 10 days | 2026-08-25 | 2026-08-30 | 2026-08-30 | Internal line |  | 854.94 | Completed | No
WO-26-009280 | 1.4 | Bayou | BY-S04-03 | Meter exchange | P3 within 10 days | 2026-08-25 | 2026-08-26 | 2026-08-27 | Meter technician |  | 138.98 | Completed | No
WO-26-009281 |  | Bayou | BY-S18-01 | Meter exchange | P3 within 10 days | 2026-08-25 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009282 |  | Bayou | BY-S26-04 | Meter exchange | P4 planned | 2026-08-25 | 2026-09-17 |  | Meter technician |  |  | Scheduled | No
WO-26-009283 | 0.7 | Bayou | BY-S27-02 | Meter exchange | P3 within 10 days | 2026-08-25 | 2026-08-30 | 2026-08-30 | Meter technician |  | 147.74 | Completed | No
WO-26-009284 |  | Bayou | BY-S08-02 | New service - small | P4 planned | 2026-08-25 | 2026-09-13 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-009285 |  | Bayou | BY-S20-02 | New service - small | P4 planned | 2026-08-25 | 2026-09-01 |  | Internal line |  |  | Scheduled | No
WO-26-009286 |  | Bayou | BY-S16-01 | Preventive maintenance | P4 planned | 2026-08-25 | 2026-09-12 |  | Underground crew |  |  | Scheduled | No
WO-26-009287 | 1.7 | Bayou | BY-S29-02 | Service order - field | P2 same day | 2026-08-25 | 2026-08-26 | 2026-08-26 | Meter technician |  | 11.45 | Completed | No
WO-26-009288 |  | Bayou | BY-S05-02 | Service order - field | P3 within 10 days | 2026-08-25 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009289 |  | Bayou | BY-S15-06 | Service order - field | P3 within 10 days | 2026-08-25 | 2026-08-31 |  | Meter technician |  |  | Scheduled | No
WO-26-009290 | 1.4 | Bayou | BY-S17-04 | Service order - field | P2 same day | 2026-08-25 | 2026-08-26 | 2026-08-26 | Meter technician |  | 31.56 | Completed | No
WO-26-009291 |  | Bayou |  | Streetlight | P4 planned | 2026-08-25 | 2026-10-11 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009292 |  | Bayou |  | Streetlight | P4 planned | 2026-08-25 | 2026-09-05 |  | Internal line |  |  | Scheduled | No
WO-26-009293 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-25 | 2026-08-31 | 2026-08-31 | Contract line | CT-04 | 416.17 | Completed | No
WO-26-009294 | 13.6 | Bayou | BY-S14-02 | Transformer replacement | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Internal line |  | 11310.69 | Completed | No
WO-26-009295 |  | Bayou | BY-S21-03 | Transformer replacement | P1 emergency | 2026-08-25 | 2026-08-25 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009296 | 4.8 | Bayou | BY-S18-03 | Trouble - no power | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Troubleman |  | 84.5 | Completed | No
WO-26-009297 | 1.8 | Bayou | BY-S10-01 | Trouble - partial or voltage | P2 same day | 2026-08-25 | 2026-08-25 | 2026-08-25 | Troubleman |  | 152.21 | Completed | No
WO-26-009298 | 2.4 | Bayou | BY-S26-01 | Trouble - partial or voltage | P2 same day | 2026-08-25 | 2026-08-26 | 2026-08-26 | Troubleman |  | 168.21 | Completed | No
WO-26-009299 | 8.1 | Crossroads | CR-S14-02 | Corrective maintenance | P3 within 10 days | 2026-08-25 | 2026-08-28 | 2026-08-28 | Internal line |  | 1540.19 | Completed | No
WO-26-009300 |  | Crossroads | CR-S23-05 | Corrective maintenance | P4 planned | 2026-08-25 | 2026-10-09 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009301 |  | Crossroads | CR-S04-06 | Meter exchange | P4 planned | 2026-08-25 | 2026-10-06 |  | Meter technician |  |  | Scheduled | No
WO-26-009302 | 1.1 | Crossroads | CR-S06-03 | Meter exchange | P3 within 10 days | 2026-08-25 | 2026-08-28 | 2026-08-28 | Meter technician |  | 82.5 | Completed | No
WO-26-009303 | 0.7 | Crossroads | CR-S01-03 | Meter exchange | P3 within 10 days | 2026-08-25 | 2026-08-28 | 2026-08-28 | Meter technician |  | 168.08 | Completed | No
WO-26-009304 |  | Crossroads | CR-S29-02 | Meter exchange | P3 within 10 days | 2026-08-25 | 2026-08-29 |  | Meter technician |  |  | Scheduled | No
WO-26-009305 |  | Crossroads | CR-S08-06 | New service - small | P4 planned | 2026-08-25 | 2026-09-07 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009306 | 16.6 | Crossroads | CR-S11-01 | Pole replacement | P3 within 10 days | 2026-08-25 | 2026-08-27 | 2026-08-28 | Contract line | CT-02 | 2481.18 | Completed | No
WO-26-009307 | 14.3 | Crossroads | CR-S23-02 | Pole replacement | P2 same day | 2026-08-25 | 2026-08-25 | 2026-08-25 | Internal line |  | 2442.37 | Completed | No
WO-26-009308 |  | Crossroads | CR-S02-03 | Pole replacement | P3 within 10 days | 2026-08-25 | 2026-08-31 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009309 |  | Crossroads | CR-S19-02 | Preventive maintenance | P4 planned | 2026-08-25 | 2026-10-07 |  | Internal line |  |  | Scheduled | No
WO-26-009310 | 0.5 | Crossroads | CR-S24-01 | Service order - field | P2 same day | 2026-08-25 | 2026-08-25 | 2026-08-25 | Meter technician |  | 5.71 | Completed | No
WO-26-009311 | 1 | Crossroads | CR-S28-02 | Service order - field | P2 same day | 2026-08-25 | 2026-08-26 | 2026-08-26 | Meter technician |  | 36.8 | Completed | No
WO-26-009312 | 1 | Crossroads | CR-S21-02 | Service order - field | P2 same day | 2026-08-25 | 2026-08-25 | 2026-08-25 | Meter technician |  | 23.6 | Completed | No
WO-26-009313 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-25 | 2026-08-30 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009314 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-25 | 2026-09-01 |  | Internal line |  |  | Scheduled | No
WO-26-009315 | 12 | Crossroads | CR-S24-02 | Transformer replacement | P3 within 10 days | 2026-08-25 | 2026-08-27 | 2026-08-28 | Internal line |  | 10316.64 | Completed | No
WO-26-009316 |  | Crossroads | CR-S27-04 | Transformer replacement | P3 within 10 days | 2026-08-25 | 2026-09-01 |  | Internal line |  |  | Scheduled | No
WO-26-009317 | 3.5 | Crossroads | CR-S29-02 | Trouble - no power | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Internal line |  | 79.79 | Completed | No
WO-26-009318 | 3.6 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Troubleman |  | 177.48 | Completed | No
WO-26-009319 | 5.2 | Crossroads | CR-S11-01 | Trouble - no power | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Troubleman |  | 247.22 | Completed | No
WO-26-009320 | 4.5 | Crossroads | CR-S18-04 | Trouble - no power | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Internal line |  | 322.89 | Completed | No
WO-26-009321 | 5.9 | Crossroads | CR-S31-03 | Trouble - no power | P1 emergency | 2026-08-25 | 2026-08-25 | 2026-08-25 | Troubleman |  | 253.66 | Completed | No
WO-26-009322 |  | Crossroads | CR-S16-03 | Trouble - partial or voltage | P3 within 10 days | 2026-08-25 | 2026-09-02 |  | Troubleman |  |  | Scheduled | No
WO-26-009323 |  | Crossroads | CR-S18-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-25 | 2026-08-29 |  | Troubleman |  |  | Cancelled | No
WO-26-009324 | 7.6 | Bayou | BY-S30-01 | Corrective maintenance | P3 within 10 days | 2026-08-26 | 2026-08-27 | 2026-08-27 | Contract line | CT-03 | 773.17 | Completed | No
WO-26-009325 |  | Bayou | BY-S22-04 | Meter exchange | P4 planned | 2026-08-26 | 2026-09-09 |  | Meter technician |  |  | Scheduled | No
WO-26-009326 |  | Bayou | BY-S03-02 | Meter exchange | P3 within 10 days | 2026-08-26 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-009327 |  | Bayou | BY-S04-02 | Pole replacement | P4 planned | 2026-08-26 | 2026-09-25 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-009328 |  | Bayou | BY-S29-04 | Preventive maintenance | P4 planned | 2026-08-26 | 2026-09-20 |  | Internal line |  |  | Scheduled | No
WO-26-009329 |  | Bayou | BY-S21-04 | Preventive maintenance | P4 planned | 2026-08-26 | 2026-09-30 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009330 | 1 | Bayou | BY-S21-03 | Service order - field | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Meter technician |  | 1.73 | Completed | No
WO-26-009331 |  | Bayou | BY-S15-02 | Service order - field | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009332 |  | Bayou | BY-S21-02 | Service order - field | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Meter technician |  |  | Cancelled | No
WO-26-009333 |  | Bayou |  | Streetlight | P4 planned | 2026-08-26 | 2026-09-02 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009334 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009335 | 2.9 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-26 | 2026-08-28 | 2026-08-30 | Internal line |  | 196.27 | Completed | No
WO-26-009336 |  | Bayou | BY-S24-04 | Transformer replacement | P2 same day | 2026-08-26 | 2026-08-27 |  | Contract line | CT-04 |  | Open - awaiting material | No
WO-26-009337 |  | Bayou | BY-S15-04 | Transformer replacement | P1 emergency | 2026-08-26 | 2026-08-26 |  | Internal line |  |  | Cancelled | No
WO-26-009338 |  | Bayou | BY-S22-02 | Transformer replacement | P2 same day | 2026-08-26 | 2026-08-27 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009339 | 13 | Bayou | BY-S01-02 | Transformer replacement | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Internal line |  | 11870.48 | Completed | No
WO-26-009340 | 3.8 | Bayou | BY-S21-05 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 230.42 | Completed | No
WO-26-009341 | 3.6 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 105.57 | Completed | No
WO-26-009342 | 3.4 | Bayou | BY-S03-01 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 156.42 | Completed | No
WO-26-009343 |  | Bayou | BY-S17-01 | Trouble - no power | P2 same day | 2026-08-26 | 2026-08-27 |  | Troubleman |  |  | Cancelled | No
WO-26-009344 | 3.4 | Bayou | BY-S16-05 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 215.6 | Completed | No
WO-26-009345 | 4.4 | Bayou | BY-S01-02 | Trouble - no power | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Troubleman |  | 116.59 | Completed | No
WO-26-009346 | 3.4 | Bayou | BY-S13-03 | Trouble - no power | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Troubleman |  | 285.52 | Completed | No
WO-26-009347 |  | Bayou | BY-S29-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Troubleman |  |  | Scheduled | No
WO-26-009348 | 2.8 | Bayou | BY-S15-02 | Trouble - partial or voltage | P2 same day | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 200.58 | Completed | No
WO-26-009349 | 9.9 | Crossroads | CR-S24-04 | Corrective maintenance | P3 within 10 days | 2026-08-26 | 2026-08-27 | 2026-08-31 | Underground crew |  | 1066.04 | Completed | No
WO-26-009350 |  | Crossroads | CR-S06-02 | Corrective maintenance | P3 within 10 days | 2026-08-26 | 2026-09-01 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009351 |  | Crossroads | CR-S14-02 | Corrective maintenance | P3 within 10 days | 2026-08-26 | 2026-09-04 |  | Internal line |  |  | Scheduled | No
WO-26-009352 |  | Crossroads | CR-S21-03 | Corrective maintenance | P4 planned | 2026-08-26 | 2026-10-09 |  | Underground crew |  |  | Scheduled | No
WO-26-009353 |  | Crossroads | CR-S04-02 | Corrective maintenance | P4 planned | 2026-08-26 | 2026-09-03 |  | Underground crew |  |  | Scheduled | No
WO-26-009354 | 8.1 | Crossroads | CR-S08-06 | Corrective maintenance | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Underground crew |  | 1320.26 | Completed | No
WO-26-009355 | 8.8 | Crossroads | CR-S18-06 | Corrective maintenance | P2 same day | 2026-08-26 | 2026-08-26 | 2026-08-26 | Contract line | CT-02 | 1674.96 | Completed | No
WO-26-009356 |  | Crossroads | CR-S24-02 | Meter exchange | P3 within 10 days | 2026-08-26 | 2026-08-31 |  | Meter technician |  |  | Scheduled | No
WO-26-009357 |  | Crossroads | CR-S02-01 | Meter exchange | P4 planned | 2026-08-26 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-009358 |  | Crossroads | CR-S22-02 | Meter exchange | P3 within 10 days | 2026-08-26 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-009359 |  | Crossroads | CR-S25-03 | Meter exchange | P3 within 10 days | 2026-08-26 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-009360 |  | Crossroads | CR-S14-03 | Meter exchange | P4 planned | 2026-08-26 | 2026-10-17 |  | Meter technician |  |  | Scheduled | No
WO-26-009361 |  | Crossroads | CR-S06-03 | New service - small | P4 planned | 2026-08-26 | 2026-09-22 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009362 | 1.1 | Crossroads | CR-S28-01 | Service order - field | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Meter technician |  | 8.56 | Completed | No
WO-26-009363 | 0.5 | Crossroads | CR-S07-01 | Service order - field | P3 within 10 days | 2026-08-26 | 2026-08-29 | 2026-08-29 | Meter technician |  | 5.85 | Completed | No
WO-26-009364 | 0.8 | Crossroads | CR-S31-02 | Service order - field | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Meter technician |  | 21.83 | Completed | No
WO-26-009365 | 0.5 | Crossroads | CR-S19-03 | Service order - field | P3 within 10 days | 2026-08-26 | 2026-08-28 | 2026-08-28 | Meter technician |  | 12.02 | Completed | No
WO-26-009366 |  | Crossroads | CR-S21-03 | Service order - field | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009367 |  | Crossroads | CR-S27-04 | Service order - field | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009368 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-26 | 2026-09-02 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009369 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-26 | 2026-09-05 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009370 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-26 | 2026-09-07 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009371 |  | Crossroads | CR-S27-02 | Transformer replacement | P1 emergency | 2026-08-26 | 2026-08-26 |  | Contract line | CT-01 |  | Open - awaiting material | No
WO-26-009372 | 10.5 | Crossroads | CR-S19-04 | Transformer replacement | P2 same day | 2026-08-26 | 2026-08-26 | 2026-08-26 | Contract line | CT-02 | 7983.29 | Completed | No
WO-26-009373 |  | Crossroads | CR-S28-03 | Transformer replacement | P1 emergency | 2026-08-26 | 2026-08-26 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009374 | 6.8 | Crossroads | CR-S24-02 | Transformer replacement | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Internal line |  | 8078.54 | Completed | No
WO-26-009375 | 6 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 339.81 | Completed | No
WO-26-009376 | 5.5 | Crossroads | CR-S02-05 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Internal line |  | 174.38 | Completed | No
WO-26-009377 | 5 | Crossroads | CR-S32-03 | Trouble - no power | P1 emergency | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 78.16 | Completed | No
WO-26-009378 | 3 | Crossroads | CR-S25-03 | Trouble - partial or voltage | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Troubleman |  | 17.56 | Completed | No
WO-26-009379 | 3.7 | Crossroads | CR-S23-04 | Trouble - partial or voltage | P2 same day | 2026-08-26 | 2026-08-27 | 2026-08-27 | Internal line |  | 27.28 | Completed | No
WO-26-009380 | 2.4 | Crossroads | CR-S14-03 | Trouble - partial or voltage | P2 same day | 2026-08-26 | 2026-08-26 | 2026-08-26 | Troubleman |  | 9.41 | Completed | No
WO-26-009381 | 10.7 | Bayou | BY-S16-06 | Corrective maintenance | P3 within 10 days | 2026-08-27 | 2026-08-29 | 2026-08-29 | Contract line | CT-04 | 266.12 | Completed | No
WO-26-009382 | 10.7 | Bayou | BY-S18-07 | Corrective maintenance | P2 same day | 2026-08-27 | 2026-08-28 | 2026-08-28 | Underground crew |  | 670.68 | Completed | No
WO-26-009383 |  | Bayou | BY-S09-04 | Corrective maintenance | P3 within 10 days | 2026-08-27 | 2026-09-06 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009384 |  | Bayou | BY-S11-01 | Corrective maintenance | P4 planned | 2026-08-27 | 2026-09-18 |  | Internal line |  |  | Scheduled | No
WO-26-009385 |  | Bayou | BY-S21-01 | Corrective maintenance | P3 within 10 days | 2026-08-27 | 2026-09-05 |  | Internal line |  |  | Scheduled | No
WO-26-009386 | 3.7 | Bayou | BY-S07-03 | Corrective maintenance | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Contract line | CT-04 | 2212.55 | Completed | No
WO-26-009387 |  | Bayou | BY-S30-02 | Meter exchange | P3 within 10 days | 2026-08-27 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-009388 |  | Bayou | BY-S26-06 | Meter exchange | P3 within 10 days | 2026-08-27 | 2026-08-31 |  | Meter technician |  |  | Scheduled | No
WO-26-009389 |  | Bayou | BY-S25-04 | Meter exchange | P3 within 10 days | 2026-08-27 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009390 |  | Bayou | BY-S12-03 | Preventive maintenance | P4 planned | 2026-08-27 | 2026-10-18 |  | Underground crew |  |  | Scheduled | No
WO-26-009391 |  | Bayou | BY-S13-01 | Preventive maintenance | P4 planned | 2026-08-27 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-009392 |  | Bayou | BY-S03-03 | Preventive maintenance | P4 planned | 2026-08-27 | 2026-09-08 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009393 | 0.8 | Bayou | BY-S24-05 | Service order - field | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Meter technician |  | 14.71 | Completed | No
WO-26-009394 | 2.4 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-27 | 2026-08-30 | 2026-08-31 | Internal line |  | 305.46 | Completed | No
WO-26-009395 | 7.3 | Bayou | BY-S24-03 | Transformer replacement | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Internal line |  | 3818.51 | Completed | No
WO-26-009396 | 9.3 | Bayou | BY-S23-02 | Transformer replacement | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Contract line | CT-03 | 8739.28 | Completed | No
WO-26-009397 | 3.2 | Bayou | BY-S16-01 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 296.5 | Completed | No
WO-26-009398 | 4 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 340.59 | Completed | No
WO-26-009399 | 5.7 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 63.61 | Completed | No
WO-26-009400 | 3.5 | Bayou | BY-S16-03 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 180.27 | Completed | No
WO-26-009401 | 4.8 | Bayou | BY-S18-03 | Trouble - no power | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 335.02 | Completed | No
WO-26-009402 | 2.4 | Bayou | BY-S27-04 | Trouble - no power | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 14.74 | Completed | No
WO-26-009403 | 4.7 | Bayou | BY-S02-02 | Trouble - no power | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 33.49 | Completed | No
WO-26-009404 | 2.3 | Bayou | BY-S12-03 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 152.76 | Completed | No
WO-26-009405 | 5.4 | Bayou | BY-S19-02 | Trouble - no power | P2 same day | 2026-08-27 | 2026-08-28 | 2026-08-28 | Troubleman |  | 56.56 | Completed | No
WO-26-009406 |  | Bayou | BY-S27-01 | Trouble - partial or voltage | P2 same day | 2026-08-27 | 2026-08-27 |  | Troubleman |  |  | Cancelled | No
WO-26-009407 | 1.8 | Bayou | BY-S24-04 | Trouble - partial or voltage | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 186.89 | Completed | No
WO-26-009408 | 2.9 | Bayou | BY-S07-06 | Trouble - partial or voltage | P2 same day | 2026-08-27 | 2026-08-28 | 2026-08-28 | Troubleman |  | 242.14 | Completed | No
WO-26-009409 |  | Bayou | BY-S06-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-27 | 2026-09-05 |  | Troubleman |  |  | Scheduled | No
WO-26-009410 |  | Bayou | BY-S16-06 | Trouble - partial or voltage | P3 within 10 days | 2026-08-27 | 2026-09-02 |  | Troubleman |  |  | Scheduled | No
WO-26-009411 |  | Crossroads | CR-S09-05 | Corrective maintenance | P3 within 10 days | 2026-08-27 | 2026-09-06 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009412 |  | Crossroads | CR-S01-03 | Corrective maintenance | P4 planned | 2026-08-27 | 2026-10-25 |  | Underground crew |  |  | Scheduled | No
WO-26-009413 |  | Crossroads | CR-S14-03 | Corrective maintenance | P3 within 10 days | 2026-08-27 | 2026-09-06 |  | Internal line |  |  | Scheduled | No
WO-26-009414 |  | Crossroads | CR-S08-02 | Corrective maintenance | P2 same day | 2026-08-27 | 2026-08-28 |  | Internal line |  |  | Cancelled | No
WO-26-009415 |  | Crossroads | CR-S28-03 | Corrective maintenance | P3 within 10 days | 2026-08-27 | 2026-09-01 |  | Underground crew |  |  | Scheduled | No
WO-26-009416 |  | Crossroads | CR-S16-01 | Meter exchange | P3 within 10 days | 2026-08-27 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-009417 |  | Crossroads | CR-S12-03 | New service - small | P3 within 10 days | 2026-08-27 | 2026-09-03 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009418 |  | Crossroads | CR-S02-03 | Preventive maintenance | P4 planned | 2026-08-27 | 2026-10-26 |  | Underground crew |  |  | Scheduled | No
WO-26-009419 |  | Crossroads | CR-S19-04 | Preventive maintenance | P4 planned | 2026-08-27 | 2026-10-26 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009420 |  | Crossroads | CR-S32-01 | Preventive maintenance | P4 planned | 2026-08-27 | 2026-10-07 |  | Internal line |  |  | Scheduled | No
WO-26-009421 |  | Crossroads | CR-S19-03 | Service order - field | P3 within 10 days | 2026-08-27 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-009422 |  | Crossroads | CR-S03-01 | Service order - field | P3 within 10 days | 2026-08-27 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-009423 | 1.8 | Crossroads | CR-S02-05 | Service order - field | P2 same day | 2026-08-27 | 2026-08-28 | 2026-08-28 | Meter technician |  | 1.25 | Completed | No
WO-26-009424 |  | Crossroads | CR-S22-04 | Service order - field | P3 within 10 days | 2026-08-27 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-009425 |  | Crossroads | CR-S27-03 | Service order - field | P3 within 10 days | 2026-08-27 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009426 |  | Crossroads | CR-S06-02 | Service order - field | P3 within 10 days | 2026-08-27 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009427 | 1.8 | Crossroads | CR-S30-06 | Service order - field | P2 same day | 2026-08-27 | 2026-08-27 | 2026-08-27 | Meter technician |  | 3.01 | Completed | No
WO-26-009428 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-27 | 2026-09-27 |  | Internal line |  |  | Scheduled | No
WO-26-009429 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-27 | 2026-08-28 |  | Internal line |  |  | Scheduled | No
WO-26-009430 |  | Crossroads | CR-S14-02 | Transformer replacement | P2 same day | 2026-08-27 | 2026-08-27 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009431 |  | Crossroads | CR-S19-03 | Transformer replacement | P2 same day | 2026-08-27 | 2026-08-28 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009432 |  | Crossroads | CR-S14-02 | Transformer replacement | P3 within 10 days | 2026-08-27 | 2026-08-30 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-009433 | 2.6 | Crossroads | CR-S14-01 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 266.2 | Completed | No
WO-26-009434 | 2.5 | Crossroads | CR-S16-02 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 76.04 | Completed | No
WO-26-009435 | 4.1 | Crossroads | CR-S21-02 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 150.52 | Completed | No
WO-26-009436 | 5.7 | Crossroads | CR-S15-02 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 256.65 | Completed | No
WO-26-009437 | 4.7 | Crossroads | CR-S27-04 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Internal line |  | 111.16 | Completed | No
WO-26-009438 | 3.1 | Crossroads | CR-S03-02 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Troubleman |  | 291.4 | Completed | No
WO-26-009439 | 3.8 | Crossroads | CR-S04-06 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Internal line |  | 210.8 | Completed | No
WO-26-009440 | 5.4 | Crossroads | CR-S19-03 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Internal line |  | 169.76 | Completed | No
WO-26-009441 | 2.5 | Crossroads | CR-S14-02 | Trouble - no power | P1 emergency | 2026-08-27 | 2026-08-27 | 2026-08-27 | Internal line |  | 155.35 | Completed | No
WO-26-009442 | 2.1 | Crossroads | CR-S19-03 | Trouble - partial or voltage | P2 same day | 2026-08-27 | 2026-08-28 | 2026-08-28 | Troubleman |  | 106.87 | Completed | No
WO-26-009443 |  | Bayou | BY-S18-05 | Corrective maintenance | P3 within 10 days | 2026-08-28 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-009444 | 5.2 | Bayou | BY-S30-02 | Corrective maintenance | P3 within 10 days | 2026-08-28 | 2026-08-30 | 2026-08-30 | Internal line |  | 360.83 | Completed | No
WO-26-009445 |  | Bayou | BY-S19-02 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-09-07 |  | Meter technician |  |  | Scheduled | No
WO-26-009446 |  | Bayou | BY-S14-02 | Meter exchange | P4 planned | 2026-08-28 | 2026-09-15 |  | Meter technician |  |  | Scheduled | No
WO-26-009447 |  | Bayou | BY-S22-04 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-009448 |  | Bayou | BY-S23-02 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-009449 |  | Bayou | BY-S06-02 | New service - small | P3 within 10 days | 2026-08-28 | 2026-09-02 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009450 |  | Bayou | BY-S12-02 | Pole replacement | P4 planned | 2026-08-28 | 2026-09-06 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009451 |  | Bayou | BY-S24-01 | Pole replacement | P3 within 10 days | 2026-08-28 | 2026-09-04 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009452 |  | Bayou | BY-S19-01 | Pole replacement | P3 within 10 days | 2026-08-28 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-009453 |  | Bayou | BY-S19-01 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-09-27 |  | Internal line |  |  | Scheduled | No
WO-26-009454 |  | Bayou | BY-S11-02 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-10-02 |  | Underground crew |  |  | Scheduled | No
WO-26-009455 | 1.7 | Bayou | BY-S15-06 | Service order - field | P2 same day | 2026-08-28 | 2026-08-28 | 2026-08-28 | Meter technician |  | 4.89 | Completed | No
WO-26-009456 | 0.7 | Bayou | BY-S19-02 | Service order - field | P3 within 10 days | 2026-08-28 | 2026-08-29 | 2026-08-29 | Meter technician |  | 14.54 | Completed | No
WO-26-009457 | 1.2 | Bayou | BY-S19-02 | Service order - field | P2 same day | 2026-08-28 | 2026-08-28 | 2026-08-28 | Meter technician |  | 29.55 | Completed | No
WO-26-009458 | 2.5 | Bayou |  | Streetlight | P3 within 10 days | 2026-08-28 | 2026-08-29 | 2026-08-30 | Internal line |  | 41.27 | Completed | No
WO-26-009459 | 12.6 | Bayou | BY-S12-01 | Transformer replacement | P1 emergency | 2026-08-28 | 2026-08-28 | 2026-08-28 | Internal line |  | 10660.57 | Completed | No
WO-26-009460 |  | Bayou | BY-S24-05 | Transformer replacement | P3 within 10 days | 2026-08-28 | 2026-09-01 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009461 | 4.9 | Bayou | BY-S09-03 | Trouble - no power | P1 emergency | 2026-08-28 | 2026-08-28 | 2026-08-28 | Troubleman |  | 233.67 | Completed | No
WO-26-009462 | 3 | Bayou | BY-S15-06 | Trouble - no power | P2 same day | 2026-08-28 | 2026-08-29 | 2026-08-29 | Internal line |  | 223.23 | Completed | No
WO-26-009463 |  | Crossroads | CR-S13-04 | Corrective maintenance | P3 within 10 days | 2026-08-28 | 2026-09-02 |  | Underground crew |  |  | Scheduled | No
WO-26-009464 |  | Crossroads | CR-S12-01 | Corrective maintenance | P4 planned | 2026-08-28 | 2026-10-27 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009465 |  | Crossroads | CR-S14-05 | Corrective maintenance | P3 within 10 days | 2026-08-28 | 2026-09-02 |  | Underground crew |  |  | Scheduled | No
WO-26-009466 | 1.1 | Crossroads | CR-S08-01 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-08-29 | 2026-08-30 | Meter technician |  | 103.95 | Completed | No
WO-26-009467 |  | Crossroads | CR-S24-01 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-09-07 |  | Meter technician |  |  | Scheduled | No
WO-26-009468 | 0.6 | Crossroads | CR-S26-06 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-08-31 | 2026-08-31 | Meter technician |  | 140.93 | Completed | No
WO-26-009469 | 1.3 | Crossroads | CR-S02-04 | Meter exchange | P3 within 10 days | 2026-08-28 | 2026-08-29 | 2026-08-31 | Meter technician |  | 167.65 | Completed | No
WO-26-009470 |  | Crossroads | CR-S15-02 | Meter exchange | P4 planned | 2026-08-28 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009471 |  | Crossroads | CR-S13-06 | New service - small | P4 planned | 2026-08-28 | 2026-09-18 |  | Internal line |  |  | Scheduled | No
WO-26-009472 |  | Crossroads | CR-S27-04 | Pole replacement | P3 within 10 days | 2026-08-28 | 2026-09-04 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009473 |  | Crossroads | CR-S10-03 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-10-16 |  | Underground crew |  |  | Scheduled | No
WO-26-009474 |  | Crossroads | CR-S19-04 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-10-19 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-009475 |  | Crossroads | CR-S05-01 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-09-16 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-009476 |  | Crossroads | CR-S16-02 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-09-10 |  | Internal line |  |  | Scheduled | No
WO-26-009477 |  | Crossroads | CR-S10-01 | Preventive maintenance | P4 planned | 2026-08-28 | 2026-10-05 |  | Internal line |  |  | Scheduled | No
WO-26-009478 | 0.8 | Crossroads | CR-S01-01 | Service order - field | P2 same day | 2026-08-28 | 2026-08-29 | 2026-08-29 | Meter technician |  | 26.43 | Completed | No
WO-26-009479 | 0.8 | Crossroads | CR-S20-03 | Service order - field | P2 same day | 2026-08-28 | 2026-08-29 | 2026-08-29 | Meter technician |  | 15.22 | Completed | No
WO-26-009480 |  | Crossroads | CR-S03-02 | Service order - field | P3 within 10 days | 2026-08-28 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-009481 |  | Crossroads | CR-S27-02 | Service order - field | P3 within 10 days | 2026-08-28 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-009482 | 0.7 | Crossroads | CR-S17-02 | Service order - field | P2 same day | 2026-08-28 | 2026-08-28 | 2026-08-28 | Meter technician |  | 11.06 | Completed | No
WO-26-009483 | 1.5 | Crossroads | CR-S20-04 | Service order - field | P2 same day | 2026-08-28 | 2026-08-29 | 2026-08-29 | Meter technician |  | 21.22 | Completed | No
WO-26-009484 |  | Crossroads | CR-S02-01 | Service order - field | P3 within 10 days | 2026-08-28 | 2026-08-30 |  | Meter technician |  |  | Scheduled | No
WO-26-009485 |  | Crossroads | CR-S25-03 | Service order - field | P3 within 10 days | 2026-08-28 | 2026-09-03 |  | Meter technician |  |  | Scheduled | No
WO-26-009486 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-28 | 2026-09-21 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009487 |  | Crossroads | CR-S02-01 | Transformer replacement | P3 within 10 days | 2026-08-28 | 2026-09-05 |  | Internal line |  |  | Scheduled | No
WO-26-009488 |  | Crossroads | CR-S28-02 | Transformer replacement | P3 within 10 days | 2026-08-28 | 2026-09-03 |  | Internal line |  |  | Scheduled | No
WO-26-009489 |  | Crossroads | CR-S12-02 | Transformer replacement | P2 same day | 2026-08-28 | 2026-08-29 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009490 | 11.3 | Crossroads | CR-S24-03 | Transformer replacement | P2 same day | 2026-08-28 | 2026-08-29 | 2026-08-29 | Contract line | CT-02 | 7240.9 | Completed | No
WO-26-009491 | 4 | Crossroads | CR-S22-01 | Trouble - no power | P1 emergency | 2026-08-28 | 2026-08-28 | 2026-08-28 | Troubleman |  | 218.96 | Completed | No
WO-26-009492 | 3.6 | Crossroads | CR-S18-03 | Trouble - no power | P1 emergency | 2026-08-28 | 2026-08-28 | 2026-08-28 | Internal line |  | 39.46 | Completed | No
WO-26-009493 | 3.5 | Crossroads | CR-S27-02 | Trouble - no power | P1 emergency | 2026-08-28 | 2026-08-28 | 2026-08-28 | Troubleman |  | 254.5 | Completed | No
WO-26-009494 | 1.9 | Crossroads | CR-S23-02 | Trouble - partial or voltage | P3 within 10 days | 2026-08-28 | 2026-08-30 | 2026-08-30 | Troubleman |  | 199.49 | Completed | No
WO-26-009495 |  | Crossroads | CR-S06-02 | Trouble - partial or voltage | P2 same day | 2026-08-28 | 2026-08-29 |  | Troubleman |  |  | Cancelled | No
WO-26-009496 | 10.3 | Bayou | BY-S15-01 | Corrective maintenance | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Contract line | CT-04 | 2394.64 | Completed | No
WO-26-009497 | 19.5 | Bayou | BY-S13-05 | Pole replacement | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Contract line | CT-03 | 1544.48 | Completed | No
WO-26-009498 | 1.3 | Bayou | BY-S26-03 | Service order - field | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Meter technician |  | 27.62 | Completed | No
WO-26-009499 | 0.5 | Bayou | BY-S04-02 | Service order - field | P2 same day | 2026-08-29 | 2026-08-30 | 2026-08-30 | Meter technician |  | 7.92 | Completed | No
WO-26-009500 | 5.3 | Bayou | BY-S07-01 | Trouble - no power | P2 same day | 2026-08-29 | 2026-08-30 | 2026-08-30 | Troubleman |  | 132.69 | Completed | No
WO-26-009501 | 3.4 | Bayou | BY-S08-01 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 11.03 | Completed | No
WO-26-009502 | 4.1 | Bayou | BY-S29-01 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 176.43 | Completed | No
WO-26-009503 | 4.2 | Bayou | BY-S29-02 | Trouble - partial or voltage | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 19.04 | Completed | No
WO-26-009504 | 2.1 | Bayou | BY-S11-03 | Trouble - partial or voltage | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 219.01 | Completed | No
WO-26-009505 | 9.6 | Crossroads | CR-S18-03 | Corrective maintenance | P2 same day | 2026-08-29 | 2026-08-30 | 2026-08-30 | Internal line |  | 629.15 | Completed | No
WO-26-009506 | 5.5 | Crossroads | CR-S07-03 | Corrective maintenance | P2 same day | 2026-08-29 | 2026-08-30 | 2026-08-30 | Contract line | CT-02 | 2296.48 | Completed | No
WO-26-009507 | 22.4 | Crossroads | CR-S08-02 | Pole replacement | P2 same day | 2026-08-29 | 2026-08-30 | 2026-08-30 | Contract line | CT-02 | 1292.74 | Completed | No
WO-26-009508 | 11.2 | Crossroads | CR-S27-02 | Pole replacement | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Contract line | CT-01 | 1813.95 | Completed | No
WO-26-009509 | 1.9 | Crossroads | CR-S14-05 | Service order - field | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Meter technician |  | 16.95 | Completed | No
WO-26-009510 |  | Crossroads | CR-S07-05 | Transformer replacement | P2 same day | 2026-08-29 | 2026-08-30 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009511 | 11.6 | Crossroads | CR-S04-05 | Transformer replacement | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Internal line |  | 11898.48 | Completed | No
WO-26-009512 | 2.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 60.62 | Completed | No
WO-26-009513 | 5.6 | Crossroads | CR-S08-05 | Trouble - no power | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Internal line |  | 25.59 | Completed | No
WO-26-009514 | 3.3 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 259.83 | Completed | No
WO-26-009515 | 2.3 | Crossroads | CR-S03-02 | Trouble - no power | P2 same day | 2026-08-29 | 2026-08-30 | 2026-08-30 | Troubleman |  | 296.32 | Completed | No
WO-26-009516 | 5.3 | Crossroads | CR-S16-04 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 144.08 | Completed | No
WO-26-009517 | 4 | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Internal line |  | 213.18 | Completed | No
WO-26-009518 | 3.9 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 27.11 | Completed | No
WO-26-009519 | 3.2 | Crossroads | CR-S06-02 | Trouble - partial or voltage | P2 same day | 2026-08-29 | 2026-08-29 | 2026-08-29 | Troubleman |  | 16.94 | Completed | No
WO-26-009520 | 4.1 | Bayou | BY-S04-01 | Corrective maintenance | P2 same day | 2026-08-30 | 2026-08-31 | 2026-08-31 | Internal line |  | 834.04 | Completed | No
WO-26-009521 | 0.8 | Bayou | BY-S23-02 | Service order - field | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Meter technician |  | 26.85 | Completed | No
WO-26-009522 |  | Bayou | BY-S29-03 | Transformer replacement | P2 same day | 2026-08-30 | 2026-08-31 |  | Contract line | CT-03 |  | Open - awaiting material | No
WO-26-009523 | 3 | Bayou | BY-S04-01 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 53.88 | Completed | No
WO-26-009524 | 3.7 | Bayou | BY-S18-04 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Internal line |  | 275.57 | Completed | No
WO-26-009525 | 2.2 | Bayou | BY-S21-02 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 169.85 | Completed | No
WO-26-009526 | 2.7 | Bayou | BY-S10-02 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 99.75 | Completed | No
WO-26-009527 | 5.6 | Bayou | BY-S16-06 | Trouble - no power | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 110.38 | Completed | No
WO-26-009528 | 5.5 | Bayou | BY-S20-02 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Internal line |  | 232.67 | Completed | No
WO-26-009529 | 4.4 | Bayou | BY-S13-05 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 12.79 | Completed | No
WO-26-009530 | 5.3 | Bayou | BY-S16-04 | Trouble - no power | P2 same day | 2026-08-30 | 2026-08-31 | 2026-08-31 | Troubleman |  | 173.43 | Completed | No
WO-26-009531 | 4.6 | Bayou | BY-S08-02 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 6.16 | Completed | No
WO-26-009532 | 2.3 | Bayou | BY-S05-02 | Trouble - partial or voltage | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 39.57 | Completed | No
WO-26-009533 |  | Crossroads | CR-S28-01 | Service order - field | P2 same day | 2026-08-30 | 2026-08-31 |  | Meter technician |  |  | Cancelled | No
WO-26-009534 | 1.1 | Crossroads | CR-S07-03 | Service order - field | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Meter technician |  | 8.16 | Completed | No
WO-26-009535 | 0.7 | Crossroads | CR-S07-05 | Service order - field | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Meter technician |  | 11.79 | Completed | No
WO-26-009536 |  | Crossroads | CR-S11-01 | Transformer replacement | P2 same day | 2026-08-30 | 2026-08-31 |  | Contract line | CT-01 |  | Open - awaiting material | No
WO-26-009537 |  | Crossroads | CR-S32-05 | Transformer replacement | P1 emergency | 2026-08-30 | 2026-08-30 |  | Contract line | CT-02 |  | Open - awaiting material | No
WO-26-009538 |  | Crossroads | CR-S02-02 | Transformer replacement | P2 same day | 2026-08-30 | 2026-08-31 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009539 |  | Crossroads | CR-S19-01 | Transformer replacement | P1 emergency | 2026-08-30 | 2026-08-30 |  | Internal line |  |  | Open - awaiting material | No
WO-26-009540 | 3.1 | Crossroads | CR-S15-03 | Trouble - no power | P2 same day | 2026-08-30 | 2026-08-31 | 2026-08-31 | Troubleman |  | 1.35 | Completed | No
WO-26-009541 | 5.1 | Crossroads | CR-S12-01 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 110.5 | Completed | No
WO-26-009542 | 5.9 | Crossroads | CR-S29-01 | Trouble - no power | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 71.63 | Completed | No
WO-26-009543 | 5.6 | Crossroads | CR-S20-01 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 248.78 | Completed | No
WO-26-009544 | 2.9 | Crossroads | CR-S30-03 | Trouble - no power | P2 same day | 2026-08-30 | 2026-08-30 | 2026-08-30 | Troubleman |  | 334.19 | Completed | No
WO-26-009545 | 5.3 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-30 | 2026-08-30 | 2026-08-30 | Internal line |  | 254.02 | Completed | No
WO-26-009546 | 2.1 | Crossroads | CR-S03-03 | Trouble - partial or voltage | P2 same day | 2026-08-30 | 2026-08-31 | 2026-08-31 | Troubleman |  | 68.46 | Completed | No
WO-26-009547 |  | Bayou | BY-S25-01 | Corrective maintenance | P4 planned | 2026-08-31 | 2026-10-14 |  | Underground crew |  |  | Scheduled | No
WO-26-009548 |  | Bayou | BY-S08-03 | Corrective maintenance | P4 planned | 2026-08-31 | 2026-09-10 |  | Internal line |  |  | Scheduled | No
WO-26-009549 |  | Bayou | BY-S17-02 | Corrective maintenance | P2 same day | 2026-08-31 | 2026-09-01 |  | Internal line |  |  | Open - awaiting outage | No
WO-26-009550 |  | Bayou | BY-S12-03 | Meter exchange | P4 planned | 2026-08-31 | 2026-09-25 |  | Meter technician |  |  | Scheduled | No
WO-26-009551 |  | Bayou | BY-S14-02 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-06 |  | Meter technician |  |  | Scheduled | No
WO-26-009552 |  | Bayou | BY-S30-03 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009553 |  | Bayou | BY-S25-04 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-09 |  | Meter technician |  |  | Scheduled | No
WO-26-009554 |  | Bayou | BY-S24-02 | Meter exchange | P4 planned | 2026-08-31 | 2026-10-10 |  | Meter technician |  |  | Scheduled | No
WO-26-009555 |  | Bayou | BY-S10-01 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-10 |  | Meter technician |  |  | Scheduled | No
WO-26-009556 |  | Bayou | BY-S22-01 | New service - small | P4 planned | 2026-08-31 | 2026-10-18 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009557 |  | Bayou | BY-S30-01 | Pole replacement | P3 within 10 days | 2026-08-31 | 2026-09-06 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009558 |  | Bayou | BY-S23-01 | Pole replacement | P3 within 10 days | 2026-08-31 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-009559 |  | Bayou | BY-S21-02 | Preventive maintenance | P4 planned | 2026-08-31 | 2026-10-01 |  | Internal line |  |  | Scheduled | No
WO-26-009560 |  | Bayou | BY-S09-04 | Preventive maintenance | P4 planned | 2026-08-31 | 2026-09-26 |  | Contract line | CT-04 |  | Cancelled | No
WO-26-009561 |  | Bayou | BY-S29-01 | Preventive maintenance | P4 planned | 2026-08-31 | 2026-09-16 |  | Internal line |  |  | Scheduled | No
WO-26-009562 |  | Bayou | BY-S07-05 | Service order - field | P3 within 10 days | 2026-08-31 | 2026-09-05 |  | Meter technician |  |  | Scheduled | No
WO-26-009563 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-08-31 | 2026-09-03 |  | Contract line | CT-04 |  | Scheduled | No
WO-26-009564 |  | Bayou |  | Streetlight | P4 planned | 2026-08-31 | 2026-09-10 |  | Contract line | CT-03 |  | Scheduled | No
WO-26-009565 |  | Bayou |  | Streetlight | P3 within 10 days | 2026-08-31 | 2026-09-07 |  | Internal line |  |  | Scheduled | No
WO-26-009566 | 11.6 | Bayou | BY-S18-06 | Transformer replacement | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Internal line |  | 12032.18 | Completed | No
WO-26-009567 |  | Bayou | BY-S14-03 | Transformer replacement | P2 same day | 2026-08-31 | 2026-09-01 |  | Internal line |  |  | Cancelled | No
WO-26-009568 | 4.1 | Bayou | BY-S26-01 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Internal line |  | 240.69 | Completed | No
WO-26-009569 | 5.7 | Bayou | BY-S09-04 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 204.92 | Completed | No
WO-26-009570 | 4.8 | Bayou | BY-S23-04 | Trouble - no power | P2 same day | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 33.08 | Completed | No
WO-26-009571 | 2.1 | Bayou | BY-S26-04 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 184.39 | Completed | No
WO-26-009572 | 3 | Bayou | BY-S29-04 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 42.11 | Completed | No
WO-26-009573 |  | Bayou | BY-S25-01 | Trouble - no power | P2 same day | 2026-08-31 | 2026-09-01 |  | Troubleman |  |  | Scheduled | No
WO-26-009574 |  | Bayou | BY-S19-01 | Trouble - partial or voltage | P3 within 10 days | 2026-08-31 | 2026-09-08 |  | Troubleman |  |  | Scheduled | No
WO-26-009575 |  | Crossroads | CR-S18-02 | Corrective maintenance | P3 within 10 days | 2026-08-31 | 2026-09-05 |  | Underground crew |  |  | Open - awaiting outage | No
WO-26-009576 |  | Crossroads | CR-S20-04 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-02 |  | Meter technician |  |  | Scheduled | No
WO-26-009577 |  | Crossroads | CR-S20-02 | Meter exchange | P4 planned | 2026-08-31 | 2026-10-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009578 |  | Crossroads | CR-S04-04 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-04 |  | Meter technician |  |  | Scheduled | No
WO-26-009579 |  | Crossroads | CR-S10-01 | Meter exchange | P3 within 10 days | 2026-08-31 | 2026-09-08 |  | Meter technician |  |  | Scheduled | No
WO-26-009580 |  | Crossroads | CR-S20-01 | Preventive maintenance | P4 planned | 2026-08-31 | 2026-10-09 |  | Internal line |  |  | Scheduled | No
WO-26-009581 |  | Crossroads | CR-S18-04 | Preventive maintenance | P4 planned | 2026-08-31 | 2026-09-28 |  | Internal line |  |  | Scheduled | No
WO-26-009582 |  | Crossroads | CR-S24-02 | Preventive maintenance | P4 planned | 2026-08-31 | 2026-09-07 |  | Contract line | CT-02 |  | Scheduled | No
WO-26-009583 | 1 | Crossroads | CR-S07-03 | Service order - field | P2 same day | 2026-08-31 | 2026-08-31 | 2026-08-31 | Meter technician |  | 39.99 | Completed | No
WO-26-009584 |  | Crossroads | CR-S29-01 | Service order - field | P2 same day | 2026-08-31 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-009585 |  | Crossroads | CR-S07-07 | Service order - field | P2 same day | 2026-08-31 | 2026-09-01 |  | Meter technician |  |  | Scheduled | No
WO-26-009586 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-31 | 2026-09-09 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009587 |  | Crossroads |  | Streetlight | P3 within 10 days | 2026-08-31 | 2026-09-04 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009588 |  | Crossroads |  | Streetlight | P4 planned | 2026-08-31 | 2026-09-09 |  | Internal line |  |  | Scheduled | No
WO-26-009589 |  | Crossroads | CR-S15-03 | Transformer replacement | P3 within 10 days | 2026-08-31 | 2026-09-08 |  | Contract line | CT-01 |  | Scheduled | No
WO-26-009590 | 8.8 | Crossroads | CR-S14-01 | Transformer replacement | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Internal line |  | 3784.55 | Completed | No
WO-26-009591 | 8.2 | Crossroads | CR-S04-06 | Transformer replacement | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Internal line |  | 8261.29 | Completed | No
WO-26-009592 |  | Crossroads | CR-S22-03 | Transformer replacement | P3 within 10 days | 2026-08-31 | 2026-09-02 |  | Internal line |  |  | Scheduled | No
WO-26-009593 | 2.3 | Crossroads | CR-S08-01 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Internal line |  | 164.21 | Completed | No
WO-26-009594 | 4.1 | Crossroads | CR-S18-03 | Trouble - no power | P2 same day | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 172.17 | Completed | No
WO-26-009595 |  | Crossroads | CR-S09-01 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 |  | Troubleman |  |  | Cancelled | No
WO-26-009596 | 4.2 | Crossroads | CR-S11-02 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 214.67 | Completed | No
WO-26-009597 | 3.7 | Crossroads | CR-S06-02 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 22.3 | Completed | No
WO-26-009598 | 5.4 | Crossroads | CR-S28-01 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 254.43 | Completed | No
WO-26-009599 | 2.6 | Crossroads | CR-S21-03 | Trouble - no power | P1 emergency | 2026-08-31 | 2026-08-31 | 2026-08-31 | Troubleman |  | 318.56 | Completed | No
WO-26-009600 |  | Crossroads | CR-S09-03 | Trouble - partial or voltage | P3 within 10 days | 2026-08-31 | 2026-09-07 |  | Troubleman |  |  | Scheduled | No

## Data 2
record_id | available_hours | district | crew_type | week_start | regular_hours | overtime_hours | storm_hours
CC-000001 | 2004.6 | Harbor | Internal line | 2026-01-05 | 1889.8 | 146.9 | 22
CC-000002 | 2031.8 | Harbor | Internal line | 2026-01-12 | 1987.4 | 166.4 | 17.7
CC-000003 | 1713.1 | Harbor | Internal line | 2026-01-19 | 1648.9 | 151.1 | 21.7
CC-000004 | 2023.4 | Harbor | Internal line | 2026-01-26 | 1963.1 | 170.6 | 2
CC-000005 | 1997.5 | Harbor | Internal line | 2026-02-02 | 1887.5 | 179.3 | 6.7
CC-000006 | 2027.7 | Harbor | Internal line | 2026-02-09 | 1927.2 | 218.3 | 48.6
CC-000007 | 1960.3 | Harbor | Internal line | 2026-02-16 | 1781.3 | 158.6 | 10.5
CC-000008 | 2051.6 | Harbor | Internal line | 2026-02-23 | 1945.2 | 197.5 | 5
CC-000009 | 1944.8 | Harbor | Internal line | 2026-03-02 | 1782.6 | 138.9 | 8.6
CC-000010 | 1970.5 | Harbor | Internal line | 2026-03-09 | 1795.8 | 143.6 | 3.5
CC-000011 | 2058.7 | Harbor | Internal line | 2026-03-16 | 1997.1 | 201.1 | 23.4
CC-000012 | 1951.5 | Harbor | Internal line | 2026-03-23 | 1862.7 | 121.5 | 26.1
CC-000013 | 2010.1 | Harbor | Internal line | 2026-03-30 | 1913.8 | 220.2 | 3.9
CC-000014 | 1971.5 | Harbor | Internal line | 2026-04-06 | 1791.6 | 205.5 | 36.5
CC-000015 | 1977.3 | Harbor | Internal line | 2026-04-13 | 1832.5 | 207.4 | 3.7
CC-000016 | 1980.4 | Harbor | Internal line | 2026-04-20 | 1830.5 | 128.9 | 17.1
CC-000017 | 1930 | Harbor | Internal line | 2026-04-27 | 1783.4 | 161.8 | 44.4
CC-000018 | 1967 | Harbor | Internal line | 2026-05-04 | 1862.6 | 134.9 | 49.7
CC-000019 | 2011.4 | Harbor | Internal line | 2026-05-11 | 1844.8 | 209.4 | 7
CC-000020 | 2058.1 | Harbor | Internal line | 2026-05-18 | 1909.1 | 904.8 | 2120.4
CC-000021 | 1654.3 | Harbor | Internal line | 2026-05-25 | 1541.8 | 351 | 440.1
CC-000022 | 1947.2 | Harbor | Internal line | 2026-06-01 | 1824.5 | 115.2 | 15.5
CC-000023 | 1984.2 | Harbor | Internal line | 2026-06-08 | 1826.1 | 124.2 | 13.5
CC-000024 | 2029 | Harbor | Internal line | 2026-06-15 | 1953.7 | 190.4 | 50.2
CC-000025 | 2048.4 | Harbor | Internal line | 2026-06-22 | 1859.6 | 137.5 | 20.6
CC-000026 | 2020.5 | Harbor | Internal line | 2026-06-29 | 1821.2 | 124.9 | 9.5
CC-000027 | 1646.6 | Harbor | Internal line | 2026-07-06 | 1496.9 | 162.3 | 38
CC-000028 | 2052.4 | Harbor | Internal line | 2026-07-13 | 1884.6 | 119.6 | 52.2
CC-000029 | 1953.9 | Harbor | Internal line | 2026-07-20 | 1833.4 | 166.8 | 30.1
CC-000030 | 2021.1 | Harbor | Internal line | 2026-07-27 | 1973.8 | 186.6 | 32.2
CC-000031 | 1975.1 | Harbor | Internal line | 2026-08-03 | 1828.1 | 352.5 | 40.9
CC-000032 | 2010.9 | Harbor | Internal line | 2026-08-10 | 1845.4 | 348.9 | 40.5
CC-000033 | 1964.2 | Harbor | Internal line | 2026-08-17 | 1838 | 357.8 | 44.1
CC-000034 | 1998.8 | Harbor | Internal line | 2026-08-24 | 1888.3 | 360.3 | 36.3
CC-000035 | 2018 | Harbor | Internal line | 2026-08-31 | 1969.6 | 280.7 | 17.8
CC-000036 | 345.5 | Harbor | Troubleman | 2026-01-05 | 317.9 | 27.7 | 9
CC-000037 | 358.7 | Harbor | Troubleman | 2026-01-12 | 350.2 | 24.6 | 1.6
CC-000038 | 306.3 | Harbor | Troubleman | 2026-01-19 | 288 | 22.8 | 7.5
CC-000039 | 347.2 | Harbor | Troubleman | 2026-01-26 | 317.3 | 36.9 | 7.1
CC-000040 | 359.5 | Harbor | Troubleman | 2026-02-02 | 343.4 | 37.8 | 0.8
CC-000041 | 361.2 | Harbor | Troubleman | 2026-02-09 | 345.4 | 26.4 | 2.1
CC-000042 | 362.1 | Harbor | Troubleman | 2026-02-16 | 341.5 | 37.8 | 0.4
CC-000043 | 354.3 | Harbor | Troubleman | 2026-02-23 | 332.1 | 27 | 1.4
CC-000044 | 364.1 | Harbor | Troubleman | 2026-03-02 | 355.7 | 29.2 | 6.7
CC-000045 | 360.5 | Harbor | Troubleman | 2026-03-09 | 328.4 | 29.2 | 0.5
CC-000046 | 353.6 | Harbor | Troubleman | 2026-03-16 | 331.1 | 31 | 9.6
CC-000047 | 355.2 | Harbor | Troubleman | 2026-03-23 | 344.6 | 32.2 | 0.6
CC-000048 | 360.6 | Harbor | Troubleman | 2026-03-30 | 337.7 | 30.8 | 4.4
CC-000049 | 350.9 | Harbor | Troubleman | 2026-04-06 | 320.7 | 24.6 | 5.4
CC-000050 | 348.4 | Harbor | Troubleman | 2026-04-13 | 315.7 | 25.1 | 7.5
CC-000051 | 349.4 | Harbor | Troubleman | 2026-04-20 | 337.1 | 30 | 6.6
CC-000052 | 365.1 | Harbor | Troubleman | 2026-04-27 | 356 | 34.5 | 9.4
CC-000053 | 346.5 | Harbor | Troubleman | 2026-05-04 | 330.9 | 23 | 2.4
CC-000054 | 351.1 | Harbor | Troubleman | 2026-05-11 | 316.2 | 35.9 | 1.8
CC-000055 | 361.7 | Harbor | Troubleman | 2026-05-18 | 337.6 | 193.9 | 390
CC-000056 | 292.5 | Harbor | Troubleman | 2026-05-25 | 281.8 | 69.4 | 80
CC-000057 | 354.8 | Harbor | Troubleman | 2026-06-01 | 323.7 | 38 | 4.2
CC-000058 | 361.7 | Harbor | Troubleman | 2026-06-08 | 330.7 | 33.9 | 9.5
CC-000059 | 363.1 | Harbor | Troubleman | 2026-06-15 | 349.3 | 21.8 | 10.2
CC-000060 | 366.7 | Harbor | Troubleman | 2026-06-22 | 343.5 | 36.7 | 2.8
CC-000061 | 357.7 | Harbor | Troubleman | 2026-06-29 | 329.7 | 29.8 | 6.4
CC-000062 | 294.4 | Harbor | Troubleman | 2026-07-06 | 282.2 | 29.8 | 6.4
CC-000063 | 344.4 | Harbor | Troubleman | 2026-07-13 | 311.3 | 22.2 | 9.2
CC-000064 | 350.2 | Harbor | Troubleman | 2026-07-20 | 335.1 | 21.9 | 9.9
CC-000065 | 346.6 | Harbor | Troubleman | 2026-07-27 | 322.8 | 26.1 | 2.4
CC-000066 | 364.4 | Harbor | Troubleman | 2026-08-03 | 355.6 | 62.2 | 6.9
CC-000067 | 347 | Harbor | Troubleman | 2026-08-10 | 313.7 | 58.8 | 5
CC-000068 | 355.2 | Harbor | Troubleman | 2026-08-17 | 338 | 50.1 | 4.5
CC-000069 | 356.2 | Harbor | Troubleman | 2026-08-24 | 325.6 | 50.1 | 0.6
CC-000070 | 346.1 | Harbor | Troubleman | 2026-08-31 | 326.4 | 61.4 | 5.7
CC-000071 | 416.8 | Harbor | Underground | 2026-01-05 | 386.8 | 28.2 | 1.9
CC-000072 | 434.5 | Harbor | Underground | 2026-01-12 | 402.4 | 45.8 | 0.4
CC-000073 | 356.9 | Harbor | Underground | 2026-01-19 | 339.4 | 22.4 | 3.6
CC-000074 | 418.5 | Harbor | Underground | 2026-01-26 | 399.8 | 43.6 | 3.1
CC-000075 | 414.3 | Harbor | Underground | 2026-02-02 | 378.3 | 42.9 | 7.4
CC-000076 | 425.5 | Harbor | Underground | 2026-02-09 | 408.9 | 35.1 | 4.9
CC-000077 | 429.6 | Harbor | Underground | 2026-02-16 | 387.9 | 34.9 | 4.5
CC-000078 | 415.4 | Harbor | Underground | 2026-02-23 | 401.8 | 34.6 | 6.3
CC-000079 | 416.8 | Harbor | Underground | 2026-03-02 | 378.7 | 29.5 | 8.6
CC-000080 | 433.8 | Harbor | Underground | 2026-03-09 | 402.5 | 41.8 | 10.1
CC-000081 | 437.2 | Harbor | Underground | 2026-03-16 | 416.4 | 26.1 | 6.2
CC-000082 | 429.6 | Harbor | Underground | 2026-03-23 | 388.1 | 26 | 4.1
CC-000083 | 417.1 | Harbor | Underground | 2026-03-30 | 378 | 23.6 | 5.6
CC-000084 | 417.1 | Harbor | Underground | 2026-04-06 | 402.1 | 36.4 | 4.1
CC-000085 | 434.3 | Harbor | Underground | 2026-04-13 | 390.9 | 37.4 | 7.2
CC-000086 | 436.2 | Harbor | Underground | 2026-04-20 | 424.3 | 26.2 | 8.4
CC-000087 | 429.9 | Harbor | Underground | 2026-04-27 | 419.9 | 26 | 6.2
CC-000088 | 435.7 | Harbor | Underground | 2026-05-04 | 419 | 37.2 | 7.2
CC-000089 | 429.3 | Harbor | Underground | 2026-05-11 | 388.5 | 38.9 | 2.3
CC-000090 | 431.5 | Harbor | Underground | 2026-05-18 | 396.3 | 196.4 | 474.6
CC-000091 | 367.1 | Harbor | Underground | 2026-05-25 | 353.4 | 81.2 | 127.9
CC-000092 | 430.4 | Harbor | Underground | 2026-06-01 | 408.8 | 29.2 | 6.1
CC-000093 | 433.7 | Harbor | Underground | 2026-06-08 | 401.5 | 31.5 | 6.9
CC-000094 | 420.8 | Harbor | Underground | 2026-06-15 | 402.3 | 26.3 | 6.4
CC-000095 | 424.2 | Harbor | Underground | 2026-06-22 | 398.9 | 26.4 | 4.3
CC-000096 | 423.3 | Harbor | Underground | 2026-06-29 | 414.6 | 49.3 | 4
CC-000097 | 372.4 | Harbor | Underground | 2026-07-06 | 342.7 | 28.9 | 3.4
CC-000098 | 436.6 | Harbor | Underground | 2026-07-13 | 402.1 | 41.4 | 5.5
CC-000099 | 431.1 | Harbor | Underground | 2026-07-20 | 407.6 | 43.9 | 2.7
CC-000100 | 423.3 | Harbor | Underground | 2026-07-27 | 395.3 | 26 | 3.1
CC-000101 | 421.6 | Harbor | Underground | 2026-08-03 | 408.2 | 27.6 | 5.9
CC-000102 | 416.3 | Harbor | Underground | 2026-08-10 | 374.8 | 28.6 | 3.5
CC-000103 | 413.5 | Harbor | Underground | 2026-08-17 | 403.4 | 30 | 4.5
CC-000104 | 437.2 | Harbor | Underground | 2026-08-24 | 415 | 30.4 | 3.4
CC-000105 | 440.2 | Harbor | Underground | 2026-08-31 | 429.8 | 34.9 | 11.8
CC-000106 | 1712.6 | Harbor | Contract line | 2026-01-05 | 1604.2 | 141.6 | 44.4
CC-000107 | 1695.5 | Harbor | Contract line | 2026-01-12 | 1574.2 | 135.3 | 1.3
CC-000108 | 1417.2 | Harbor | Contract line | 2026-01-19 | 1367.4 | 87.1 | 13.4
CC-000109 | 1707.4 | Harbor | Contract line | 2026-01-26 | 1622.3 | 129.3 | 29
CC-000110 | 1756.7 | Harbor | Contract line | 2026-02-02 | 1581.7 | 160.6 | 40.7
CC-000111 | 1751.3 | Harbor | Contract line | 2026-02-09 | 1663.1 | 124.4 | 12.1
CC-000112 | 1702.1 | Harbor | Contract line | 2026-02-16 | 1549.3 | 103.1 | 45.3
CC-000113 | 1706.3 | Harbor | Contract line | 2026-02-23 | 1630.1 | 136.7 | 30.2
CC-000114 | 1735.1 | Harbor | Contract line | 2026-03-02 | 1578 | 133.1 | 39.1
CC-000115 | 1741.1 | Harbor | Contract line | 2026-03-09 | 1574.1 | 163.6 | 5.3
CC-000116 | 1681.1 | Harbor | Contract line | 2026-03-16 | 1523.1 | 165.1 | 14.5
CC-000117 | 1723 | Harbor | Contract line | 2026-03-23 | 1615.1 | 151.6 | 32.4
CC-000118 | 1651.5 | Harbor | Contract line | 2026-03-30 | 1529.3 | 156.5 | 44.7
CC-000119 | 1683.6 | Harbor | Contract line | 2026-04-06 | 1593.4 | 165 | 33.5
CC-000120 | 1733.8 | Harbor | Contract line | 2026-04-13 | 1579.2 | 138.2 | 8.9
CC-000121 | 1745.2 | Harbor | Contract line | 2026-04-20 | 1663.5 | 125.5 | 13.2
CC-000122 | 1738 | Harbor | Contract line | 2026-04-27 | 1606.2 | 130.7 | 19.8
CC-000123 | 1665.4 | Harbor | Contract line | 2026-05-04 | 1573.5 | 144.8 | 46.3
CC-000124 | 1652.7 | Harbor | Contract line | 2026-05-11 | 1499.1 | 165.2 | 4
CC-000125 | 1714.9 | Harbor | Contract line | 2026-05-18 | 1668.7 | 774.1 | 1763.1
CC-000126 | 1450.8 | Harbor | Contract line | 2026-05-25 | 1329.6 | 317.7 | 454.9
CC-000127 | 1654.3 | Harbor | Contract line | 2026-06-01 | 1580.3 | 105.4 | 25.8
CC-000128 | 1699.1 | Harbor | Contract line | 2026-06-08 | 1551 | 99.1 | 37.2
CC-000129 | 1691.1 | Harbor | Contract line | 2026-06-15 | 1586.1 | 174.7 | 23.8
CC-000130 | 1735.8 | Harbor | Contract line | 2026-06-22 | 1664.2 | 171.1 | 25.4
CC-000131 | 1661.5 | Harbor | Contract line | 2026-06-29 | 1613.9 | 128.2 | 20.9
CC-000132 | 1442.5 | Harbor | Contract line | 2026-07-06 | 1379.2 | 119.2 | 17.6
CC-000133 | 1711.7 | Harbor | Contract line | 2026-07-13 | 1561.5 | 108.3 | 19.3
CC-000134 | 1761.2 | Harbor | Contract line | 2026-07-20 | 1632.8 | 146.5 | 5.8
CC-000135 | 1713.9 | Harbor | Contract line | 2026-07-27 | 1544.3 | 173.7 | 45.4
CC-000136 | 1722.7 | Harbor | Contract line | 2026-08-03 | 1672.2 | 113.6 | 6.1
CC-000137 | 1660.7 | Harbor | Contract line | 2026-08-10 | 1623.9 | 151.1 | 41.7
CC-000138 | 1752 | Harbor | Contract line | 2026-08-17 | 1640.3 | 115.3 | 10.8
CC-000139 | 1677.4 | Harbor | Contract line | 2026-08-24 | 1511.4 | 99 | 42.2
CC-000140 | 1691 | Harbor | Contract line | 2026-08-31 | 1653.7 | 197.9 | 23.7
CC-000141 | 1895.6 | Harbor | Vegetation (contract) | 2026-01-05 | 1748.4 | 200.2 | 44.7
CC-000142 | 1944.1 | Harbor | Vegetation (contract) | 2026-01-12 | 1788.1 | 114.9 | 43
CC-000143 | 1658.7 | Harbor | Vegetation (contract) | 2026-01-19 | 1525.6 | 140.6 | 16.8
CC-000144 | 1900.8 | Harbor | Vegetation (contract) | 2026-01-26 | 1731.2 | 168.2 | 47.1
CC-000145 | 1945.3 | Harbor | Vegetation (contract) | 2026-02-02 | 1861 | 162.3 | 46.3
CC-000146 | 1968.8 | Harbor | Vegetation (contract) | 2026-02-09 | 1910.1 | 144.1 | 53.6
CC-000147 | 1948.3 | Harbor | Vegetation (contract) | 2026-02-16 | 1821.3 | 126.3 | 19
CC-000148 | 1966.7 | Harbor | Vegetation (contract) | 2026-02-23 | 1904.9 | 191.8 | 36.5
CC-000149 | 1981.1 | Harbor | Vegetation (contract) | 2026-03-02 | 1863.7 | 172.9 | 40.9
CC-000150 | 1869.3 | Harbor | Vegetation (contract) | 2026-03-09 | 1769.7 | 205.6 | 47.2
CC-000151 | 1968.6 | Harbor | Vegetation (contract) | 2026-03-16 | 1791.6 | 195.4 | 45.8
CC-000152 | 1895.4 | Harbor | Vegetation (contract) | 2026-03-23 | 1740.5 | 133.8 | 15.3
CC-000153 | 1860.7 | Harbor | Vegetation (contract) | 2026-03-30 | 1676.9 | 102 | 24.4
CC-000154 | 1963.7 | Harbor | Vegetation (contract) | 2026-04-06 | 1787.5 | 170.6 | 5.4
CC-000155 | 1938.1 | Harbor | Vegetation (contract) | 2026-04-13 | 1805.4 | 120.7 | 3.7
CC-000156 | 1977.5 | Harbor | Vegetation (contract) | 2026-04-20 | 1861.8 | 175.5 | 16.2
CC-000157 | 1930.1 | Harbor | Vegetation (contract) | 2026-04-27 | 1807.7 | 136.4 | 51.8
CC-000158 | 1935.7 | Harbor | Vegetation (contract) | 2026-05-04 | 1808.2 | 199.5 | 9.2
CC-000159 | 1907.4 | Harbor | Vegetation (contract) | 2026-05-11 | 1857.3 | 160.8 | 42.1
CC-000160 | 1871.1 | Harbor | Vegetation (contract) | 2026-05-18 | 1831.7 | 1062 | 2155.6
CC-000161 | 1636.4 | Harbor | Vegetation (contract) | 2026-05-25 | 1500.9 | 357.2 | 550.1
CC-000162 | 1917 | Harbor | Vegetation (contract) | 2026-06-01 | 1743.9 | 108.7 | 601.6
CC-000163 | 1930.1 | Harbor | Vegetation (contract) | 2026-06-08 | 1874.6 | 145.3 | 470.7
CC-000164 | 1955.6 | Harbor | Vegetation (contract) | 2026-06-15 | 1914.7 | 222.2 | 37.6
CC-000165 | 1891.3 | Harbor | Vegetation (contract) | 2026-06-22 | 1706.3 | 112.7 | 9.1
CC-000166 | 1888.2 | Harbor | Vegetation (contract) | 2026-06-29 | 1730 | 133.1 | 13.2
CC-000167 | 1590.9 | Harbor | Vegetation (contract) | 2026-07-06 | 1519.5 | 158 | 4.5
CC-000168 | 1949.5 | Harbor | Vegetation (contract) | 2026-07-13 | 1875.4 | 166 | 20.7
CC-000169 | 1981.8 | Harbor | Vegetation (contract) | 2026-07-20 | 1853.7 | 124.1 | 14.1
CC-000170 | 1954.7 | Harbor | Vegetation (contract) | 2026-07-27 | 1788.3 | 205.5 | 37.4
CC-000171 | 1877.4 | Harbor | Vegetation (contract) | 2026-08-03 | 1697.4 | 167 | 15
CC-000172 | 1913.7 | Harbor | Vegetation (contract) | 2026-08-10 | 1751.3 | 157.9 | 41.1
CC-000173 | 1907.1 | Harbor | Vegetation (contract) | 2026-08-17 | 1834.9 | 201.1 | 1.8
CC-000174 | 1944.3 | Harbor | Vegetation (contract) | 2026-08-24 | 1800.7 | 155.4 | 47.9
CC-000175 | 1892.9 | Harbor | Vegetation (contract) | 2026-08-31 | 1846.4 | 204.5 | 19.7
CC-000176 | 3193.1 | Crossroads | Internal line | 2026-01-05 | 3093.3 | 262.8 | 12
CC-000177 | 3138.3 | Crossroads | Internal line | 2026-01-12 | 3059.4 | 202.9 | 68.8
CC-000178 | 2671.6 | Crossroads | Internal line | 2026-01-19 | 2598.5 | 224.4 | 4.2
CC-000179 | 3089.4 | Crossroads | Internal line | 2026-01-26 | 2942.4 | 216.7 | 28.6
CC-000180 | 3059.7 | Crossroads | Internal line | 2026-02-02 | 2839.8 | 272.3 | 17.8
CC-000181 | 3107.3 | Crossroads | Internal line | 2026-02-09 | 2904.2 | 344.8 | 60.4
CC-000182 | 3207.4 | Crossroads | Internal line | 2026-02-16 | 3117.3 | 241.6 | 33.2
CC-000183 | 3149 | Crossroads | Internal line | 2026-02-23 | 3060.2 | 327.9 | 0.2
CC-000184 | 3049.1 | Crossroads | Internal line | 2026-03-02 | 2773.8 | 292.2 | 53
CC-000185 | 3064.1 | Crossroads | Internal line | 2026-03-09 | 3000.1 | 227 | 32.7
CC-000186 | 3158.7 | Crossroads | Internal line | 2026-03-16 | 3025.1 | 270.1 | 55
CC-000187 | 3217.8 | Crossroads | Internal line | 2026-03-23 | 3088.2 | 312.3 | 56.3
CC-000188 | 3105 | Crossroads | Internal line | 2026-03-30 | 2841.3 | 313.9 | 20.7
CC-000189 | 3049.5 | Crossroads | Internal line | 2026-04-06 | 2798.9 | 313.5 | 7.7
CC-000190 | 3042.8 | Crossroads | Internal line | 2026-04-13 | 2839.2 | 296.3 | 43.7
CC-000191 | 3111.9 | Crossroads | Internal line | 2026-04-20 | 2878.4 | 326.7 | 42.6
CC-000192 | 3133.3 | Crossroads | Internal line | 2026-04-27 | 3025.2 | 187.5 | 43
CC-000193 | 3090 | Crossroads | Internal line | 2026-05-04 | 2800.8 | 193 | 33.6
CC-000194 | 3181.7 | Crossroads | Internal line | 2026-05-11 | 2928.5 | 290.1 | 45.9
CC-000195 | 3164.7 | Crossroads | Internal line | 2026-05-18 | 2873.7 | 1520.8 | 3512.1
CC-000196 | 2640.3 | Crossroads | Internal line | 2026-05-25 | 2384.4 | 533.3 | 718.6
CC-000197 | 3086.7 | Crossroads | Internal line | 2026-06-01 | 2825.5 | 304.2 | 39.6
CC-000198 | 3236.4 | Crossroads | Internal line | 2026-06-08 | 3162 | 309.2 | 86
CC-000199 | 3155.2 | Crossroads | Internal line | 2026-06-15 | 2852.7 | 207.1 | 51.9
CC-000200 | 3219.1 | Crossroads | Internal line | 2026-06-22 | 3022.5 | 342.1 | 45.5
CC-000201 | 3109 | Crossroads | Internal line | 2026-06-29 | 2902.5 | 244.6 | 49.1
CC-000202 | 2644.2 | Crossroads | Internal line | 2026-07-06 | 2395.8 | 153.7 | 22.2
CC-000203 | 3205.2 | Crossroads | Internal line | 2026-07-13 | 3104 | 363.3 | 41.7
CC-000204 | 3224.3 | Crossroads | Internal line | 2026-07-20 | 3153.9 | 263.9 | 34
CC-000205 | 3181.3 | Crossroads | Internal line | 2026-07-27 | 2941.8 | 226.6 | 72.5
CC-000206 | 3139.9 | Crossroads | Internal line | 2026-08-03 | 2922.4 | 572.6 | 29.1
CC-000207 | 3182.2 | Crossroads | Internal line | 2026-08-10 | 2967.8 | 425.2 | 79.5
CC-000208 | 3114.1 | Crossroads | Internal line | 2026-08-17 | 2973.2 | 492.9 | 14.2
CC-000209 | 3136.9 | Crossroads | Internal line | 2026-08-24 | 3034.8 | 497 | 21.4
CC-000210 | 3054.1 | Crossroads | Internal line | 2026-08-31 | 2842.8 | 435.5 | 21.2
CC-000211 | 483 | Crossroads | Troubleman | 2026-01-05 | 443 | 32.2 | 5.4
CC-000212 | 495.1 | Crossroads | Troubleman | 2026-01-12 | 484.4 | 53.2 | 12.1
CC-000213 | 430.3 | Crossroads | Troubleman | 2026-01-19 | 408 | 26.6 | 11.9
CC-000214 | 494 | Crossroads | Troubleman | 2026-01-26 | 464 | 48.2 | 0.6
CC-000215 | 514.2 | Crossroads | Troubleman | 2026-02-02 | 474.3 | 29.9 | 0.6
CC-000216 | 482.5 | Crossroads | Troubleman | 2026-02-09 | 440.1 | 50 | 5.9
CC-000217 | 504.7 | Crossroads | Troubleman | 2026-02-16 | 466.6 | 38.3 | 9.1
CC-000218 | 503.1 | Crossroads | Troubleman | 2026-02-23 | 474.6 | 32.9 | 6.8
CC-000219 | 497.4 | Crossroads | Troubleman | 2026-03-02 | 465.6 | 55 | 11.9
CC-000220 | 488.7 | Crossroads | Troubleman | 2026-03-09 | 469.1 | 47.5 | 7.4
CC-000221 | 498.4 | Crossroads | Troubleman | 2026-03-16 | 487.8 | 33.1 | 13.2
CC-000222 | 492 | Crossroads | Troubleman | 2026-03-23 | 474.5 | 34.4 | 1.4
CC-000223 | 496.4 | Crossroads | Troubleman | 2026-03-30 | 480.1 | 52.5 | 11.7
CC-000224 | 513 | Crossroads | Troubleman | 2026-04-06 | 467.2 | 37.5 | 10.6
CC-000225 | 485.6 | Crossroads | Troubleman | 2026-04-13 | 453.4 | 37.9 | 6.1
CC-000226 | 512.2 | Crossroads | Troubleman | 2026-04-20 | 491.1 | 38.4 | 8.5
CC-000227 | 509.1 | Crossroads | Troubleman | 2026-04-27 | 488.3 | 41.9 | 4.6
CC-000228 | 491.2 | Crossroads | Troubleman | 2026-05-04 | 447.4 | 28.7 | 10.7
CC-000229 | 492.1 | Crossroads | Troubleman | 2026-05-11 | 443.5 | 31.5 | 9.7
CC-000230 | 488.1 | Crossroads | Troubleman | 2026-05-18 | 446.9 | 213.5 | 487.5
CC-000231 | 420.9 | Crossroads | Troubleman | 2026-05-25 | 393.3 | 70.9 | 127
CC-000232 | 505.6 | Crossroads | Troubleman | 2026-06-01 | 488 | 35.9 | 7
CC-000233 | 501.7 | Crossroads | Troubleman | 2026-06-08 | 472 | 40.5 | 4.9
CC-000234 | 513.2 | Crossroads | Troubleman | 2026-06-15 | 478.8 | 42.6 | 13.7
CC-000235 | 499.9 | Crossroads | Troubleman | 2026-06-22 | 473.2 | 37.7 | 7
CC-000236 | 514.4 | Crossroads | Troubleman | 2026-06-29 | 483.5 | 45.5 | 4.4
CC-000237 | 410.5 | Crossroads | Troubleman | 2026-07-06 | 382.2 | 27.3 | 0.7
CC-000238 | 508.6 | Crossroads | Troubleman | 2026-07-13 | 466 | 33.3 | 9.5
CC-000239 | 486.9 | Crossroads | Troubleman | 2026-07-20 | 441.1 | 48.9 | 1.1
CC-000240 | 513.6 | Crossroads | Troubleman | 2026-07-27 | 465.1 | 40.4 | 5.6
CC-000241 | 489.7 | Crossroads | Troubleman | 2026-08-03 | 464.1 | 91.1 | 3.9
CC-000242 | 506.4 | Crossroads | Troubleman | 2026-08-10 | 486.9 | 92.8 | 12.4
CC-000243 | 489.8 | Crossroads | Troubleman | 2026-08-17 | 462.5 | 88.8 | 10.4
CC-000244 | 492 | Crossroads | Troubleman | 2026-08-24 | 455 | 88.5 | 4.4
CC-000245 | 507.8 | Crossroads | Troubleman | 2026-08-31 | 461.1 | 75.4 | 7.9
CC-000246 | 1297.5 | Crossroads | Underground | 2026-01-05 | 1209.9 | 139.6 | 10.9
CC-000247 | 1263.4 | Crossroads | Underground | 2026-01-12 | 1183.3 | 98 | 20.9
CC-000248 | 1055.9 | Crossroads | Underground | 2026-01-19 | 1001.6 | 78.6 | 2.2
CC-000249 | 1254.3 | Crossroads | Underground | 2026-01-26 | 1217.5 | 119.7 | 30.5
CC-000250 | 1303.3 | Crossroads | Underground | 2026-02-02 | 1193.5 | 119.5 | 3.2
CC-000251 | 1259.4 | Crossroads | Underground | 2026-02-09 | 1163.4 | 91.8 | 19
CC-000252 | 1291 | Crossroads | Underground | 2026-02-16 | 1183.7 | 89 | 24.2
CC-000253 | 1270.5 | Crossroads | Underground | 2026-02-23 | 1146.9 | 128 | 6
CC-000254 | 1297.5 | Crossroads | Underground | 2026-03-02 | 1218.1 | 108.7 | 14.5
CC-000255 | 1297.6 | Crossroads | Underground | 2026-03-09 | 1199.4 | 140.9 | 26.9
CC-000256 | 1270.6 | Crossroads | Underground | 2026-03-16 | 1229.6 | 140.7 | 28.4
CC-000257 | 1310.4 | Crossroads | Underground | 2026-03-23 | 1260.2 | 142.1 | 34.9
CC-000258 | 1250.1 | Crossroads | Underground | 2026-03-30 | 1140.6 | 126.7 | 14.6
CC-000259 | 1288.1 | Crossroads | Underground | 2026-04-06 | 1178.8 | 104.2 | 5.4
CC-000260 | 1315.3 | Crossroads | Underground | 2026-04-13 | 1211.6 | 130.9 | 6.8
CC-000261 | 1316.7 | Crossroads | Underground | 2026-04-20 | 1196.3 | 123.1 | 3.7
CC-000262 | 1248.7 | Crossroads | Underground | 2026-04-27 | 1218.1 | 128.5 | 9.9
CC-000263 | 1305.6 | Crossroads | Underground | 2026-05-04 | 1180.2 | 130.5 | 32
CC-000264 | 1294.4 | Crossroads | Underground | 2026-05-11 | 1266.4 | 139.6 | 16.9
CC-000265 | 1241.9 | Crossroads | Underground | 2026-05-18 | 1172.4 | 675.1 | 1404.6
CC-000266 | 1110.9 | Crossroads | Underground | 2026-05-25 | 1033.1 | 252.9 | 297.5
CC-000267 | 1320.4 | Crossroads | Underground | 2026-06-01 | 1293.5 | 154.9 | 15.4
CC-000268 | 1250.1 | Crossroads | Underground | 2026-06-08 | 1127.3 | 86.7 | 1.4
CC-000269 | 1271.5 | Crossroads | Underground | 2026-06-15 | 1179.9 | 90.1 | 14.1
CC-000270 | 1264.5 | Crossroads | Underground | 2026-06-22 | 1178.4 | 83.1 | 33.6
CC-000271 | 1267.7 | Crossroads | Underground | 2026-06-29 | 1149.9 | 75.6 | 6.8
CC-000272 | 1105 | Crossroads | Underground | 2026-07-06 | 1038.4 | 80.7 | 4.6
CC-000273 | 1291.8 | Crossroads | Underground | 2026-07-13 | 1176.1 | 102.9 | 34.7
CC-000274 | 1312.3 | Crossroads | Underground | 2026-07-20 | 1198.5 | 97.4 | 2.2
CC-000275 | 1306.2 | Crossroads | Underground | 2026-07-27 | 1212.2 | 117.2 | 15.6
CC-000276 | 1288.9 | Crossroads | Underground | 2026-08-03 | 1201.9 | 135.7 | 18.5
CC-000277 | 1253 | Crossroads | Underground | 2026-08-10 | 1218.7 | 101.8 | 27.6
CC-000278 | 1304 | Crossroads | Underground | 2026-08-17 | 1198.8 | 111.6 | 26
CC-000279 | 1244.8 | Crossroads | Underground | 2026-08-24 | 1161.2 | 124.7 | 5.6
CC-000280 | 1292.6 | Crossroads | Underground | 2026-08-31 | 1207.9 | 138.7 | 18.1
CC-000281 | 2555 | Crossroads | Contract line | 2026-01-05 | 2321.5 | 233.3 | 21.3
CC-000282 | 2581.4 | Crossroads | Contract line | 2026-01-12 | 2390.9 | 277.7 | 38
CC-000283 | 2176.4 | Crossroads | Contract line | 2026-01-19 | 2086.8 | 236.2 | 24.1
CC-000284 | 2604.5 | Crossroads | Contract line | 2026-01-26 | 2483 | 260.4 | 9.2
CC-000285 | 2567.2 | Crossroads | Contract line | 2026-02-02 | 2342.3 | 228.2 | 50.7
CC-000286 | 2608 | Crossroads | Contract line | 2026-02-09 | 2438.7 | 155.9 | 70.7
CC-000287 | 2571.3 | Crossroads | Contract line | 2026-02-16 | 2509.1 | 262.5 | 8.7
CC-000288 | 2557.4 | Crossroads | Contract line | 2026-02-23 | 2441.4 | 169.4 | 13.2
CC-000289 | 2617.5 | Crossroads | Contract line | 2026-03-02 | 2464.9 | 279.5 | 72.3
CC-000290 | 2491.4 | Crossroads | Contract line | 2026-03-09 | 2429.6 | 282.5 | 6
CC-000291 | 2541 | Crossroads | Contract line | 2026-03-16 | 2378.2 | 153.2 | 10.7
CC-000292 | 2579.6 | Crossroads | Contract line | 2026-03-23 | 2507.3 | 292 | 2.8
CC-000293 | 2648.2 | Crossroads | Contract line | 2026-03-30 | 2409.5 | 189.5 | 47.2
CC-000294 | 2590.9 | Crossroads | Contract line | 2026-04-06 | 2409.7 | 240.8 | 18.9
CC-000295 | 2490.5 | Crossroads | Contract line | 2026-04-13 | 2263.3 | 161.6 | 54.8
CC-000296 | 2535.3 | Crossroads | Contract line | 2026-04-20 | 2420 | 182.2 | 11.7
CC-000297 | 2503.8 | Crossroads | Contract line | 2026-04-27 | 2273 | 215.8 | 66.8
CC-000298 | 2518.1 | Crossroads | Contract line | 2026-05-04 | 2283 | 234.8 | 43.3
CC-000299 | 2517.2 | Crossroads | Contract line | 2026-05-11 | 2286.8 | 140.3 | 52.2
CC-000300 | 2486 | Crossroads | Contract line | 2026-05-18 | 2371.7 | 1284.1 | 3059.8
CC-000301 | 2199 | Crossroads | Contract line | 2026-05-25 | 2093 | 539.7 | 576.6
CC-000302 | 2560.7 | Crossroads | Contract line | 2026-06-01 | 2343.4 | 277.6 | 17.9
CC-000303 | 2569.3 | Crossroads | Contract line | 2026-06-08 | 2365.3 | 142.8 | 38.1
CC-000304 | 2529.8 | Crossroads | Contract line | 2026-06-15 | 2311.4 | 165.9 | 35.1
CC-000305 | 2600.7 | Crossroads | Contract line | 2026-06-22 | 2534.6 | 299.6 | 3.7
CC-000306 | 2608.4 | Crossroads | Contract line | 2026-06-29 | 2416.5 | 269.4 | 12.2
CC-000307 | 2230.7 | Crossroads | Contract line | 2026-07-06 | 2163.6 | 148.2 | 26.1
CC-000308 | 2601.5 | Crossroads | Contract line | 2026-07-13 | 2543.9 | 166.6 | 8.1
CC-000309 | 2621.8 | Crossroads | Contract line | 2026-07-20 | 2417 | 170.7 | 34
CC-000310 | 2544.5 | Crossroads | Contract line | 2026-07-27 | 2353.5 | 179.8 | 53.3
CC-000311 | 2530.7 | Crossroads | Contract line | 2026-08-03 | 2345.4 | 143.7 | 62.8
CC-000312 | 2546.5 | Crossroads | Contract line | 2026-08-10 | 2383.8 | 180.5 | 39.5
CC-000313 | 2502.3 | Crossroads | Contract line | 2026-08-17 | 2370.8 | 227.2 | 3.5
CC-000314 | 2548.4 | Crossroads | Contract line | 2026-08-24 | 2434.6 | 200.2 | 68.8
CC-000315 | 2532.1 | Crossroads | Contract line | 2026-08-31 | 2357.9 | 205.3 | 6.7
CC-000316 | 1704.5 | Crossroads | Vegetation (contract) | 2026-01-05 | 1605.8 | 143.3 | 26.1
CC-000317 | 1731.5 | Crossroads | Vegetation (contract) | 2026-01-12 | 1608.3 | 173.6 | 22
CC-000318 | 1476.5 | Crossroads | Vegetation (contract) | 2026-01-19 | 1391.9 | 89.6 | 33.4
CC-000319 | 1718.6 | Crossroads | Vegetation (contract) | 2026-01-26 | 1579 | 169 | 1.6
CC-000320 | 1707.6 | Crossroads | Vegetation (contract) | 2026-02-02 | 1575.1 | 166.4 | 35.4
CC-000321 | 1673.7 | Crossroads | Vegetation (contract) | 2026-02-09 | 1508.4 | 177.7 | 29.1
CC-000322 | 1671.8 | Crossroads | Vegetation (contract) | 2026-02-16 | 1561.3 | 155.9 | 30.7
CC-000323 | 1702.8 | Crossroads | Vegetation (contract) | 2026-02-23 | 1632.6 | 136.3 | 0.3
CC-000324 | 1728.4 | Crossroads | Vegetation (contract) | 2026-03-02 | 1670.9 | 153.9 | 9.8
CC-000325 | 1667.3 | Crossroads | Vegetation (contract) | 2026-03-09 | 1572.1 | 139.5 | 36.5
CC-000326 | 1708.9 | Crossroads | Vegetation (contract) | 2026-03-16 | 1600 | 184.7 | 1.3
CC-000327 | 1722.6 | Crossroads | Vegetation (contract) | 2026-03-23 | 1599.7 | 101.9 | 41.5
CC-000328 | 1685.2 | Crossroads | Vegetation (contract) | 2026-03-30 | 1578 | 179.8 | 17.2
CC-000329 | 1661.4 | Crossroads | Vegetation (contract) | 2026-04-06 | 1615.2 | 138 | 38.1
CC-000330 | 1713.1 | Crossroads | Vegetation (contract) | 2026-04-13 | 1660.8 | 145.5 | 47.5
CC-000331 | 1744.9 | Crossroads | Vegetation (contract) | 2026-04-20 | 1643.3 | 144 | 45.8
CC-000332 | 1749.7 | Crossroads | Vegetation (contract) | 2026-04-27 | 1702.3 | 166.4 | 48.2
CC-000333 | 1675 | Crossroads | Vegetation (contract) | 2026-05-04 | 1620.4 | 112.7 | 42.5
CC-000334 | 1657.1 | Crossroads | Vegetation (contract) | 2026-05-11 | 1594.8 | 179.3 | 28.7
CC-000335 | 1656.2 | Crossroads | Vegetation (contract) | 2026-05-18 | 1589.1 | 805.2 | 1788.3
CC-000336 | 1489.9 | Crossroads | Vegetation (contract) | 2026-05-25 | 1427.4 | 346.9 | 616.1
CC-000337 | 1756.8 | Crossroads | Vegetation (contract) | 2026-06-01 | 1709.2 | 168.6 | 492.9
CC-000338 | 1656.4 | Crossroads | Vegetation (contract) | 2026-06-08 | 1583.7 | 183.4 | 546.4
CC-000339 | 1759.3 | Crossroads | Vegetation (contract) | 2026-06-15 | 1643.5 | 155.1 | 29.3
CC-000340 | 1747.5 | Crossroads | Vegetation (contract) | 2026-06-22 | 1648.5 | 192.2 | 24.2
CC-000341 | 1741.7 | Crossroads | Vegetation (contract) | 2026-06-29 | 1601.4 | 176.4 | 1.9
CC-000342 | 1498.3 | Crossroads | Vegetation (contract) | 2026-07-06 | 1358.3 | 139.9 | 9.6
CC-000343 | 1750.2 | Crossroads | Vegetation (contract) | 2026-07-13 | 1591 | 128.3 | 26.8
CC-000344 | 1756.7 | Crossroads | Vegetation (contract) | 2026-07-20 | 1609.3 | 183.9 | 31.7
CC-000345 | 1704.6 | Crossroads | Vegetation (contract) | 2026-07-27 | 1608.2 | 171.9 | 17.4
CC-000346 | 1655.1 | Crossroads | Vegetation (contract) | 2026-08-03 | 1491.6 | 166.2 | 30.7
CC-000347 | 1756.6 | Crossroads | Vegetation (contract) | 2026-08-10 | 1581.4 | 165.9 | 16.4
CC-000348 | 1674.4 | Crossroads | Vegetation (contract) | 2026-08-17 | 1546 | 151.6 | 27.7
CC-000349 | 1703.5 | Crossroads | Vegetation (contract) | 2026-08-24 | 1539.3 | 183.8 | 33.7
CC-000350 | 1697.3 | Crossroads | Vegetation (contract) | 2026-08-31 | 1656.3 | 163.6 | 15.6
CC-000351 | 2837.8 | Bayou | Internal line | 2026-01-05 | 2756.5 | 227.2 | 2.5
CC-000352 | 2754.9 | Bayou | Internal line | 2026-01-12 | 2629.8 | 282.2 | 14.4
CC-000353 | 2378.5 | Bayou | Internal line | 2026-01-19 | 2261.4 | 189.1 | 5.4
CC-000354 | 2929.9 | Bayou | Internal line | 2026-01-26 | 2639.6 | 196.4 | 11.7
CC-000355 | 2893.8 | Bayou | Internal line | 2026-02-02 | 2738.4 | 256.6 | 79.2
CC-000356 | 2868.6 | Bayou | Internal line | 2026-02-09 | 2701.6 | 172.6 | 15.9
CC-000357 | 2830.6 | Bayou | Internal line | 2026-02-16 | 2741 | 224.5 | 21.9
CC-000358 | 2914.8 | Bayou | Internal line | 2026-02-23 | 2747.6 | 272.5 | 10.7
CC-000359 | 2855.6 | Bayou | Internal line | 2026-03-02 | 2707.2 | 230.9 | 16.7
CC-000360 | 2897.7 | Bayou | Internal line | 2026-03-09 | 2623.6 | 187.1 | 61.3
CC-000361 | 2923.4 | Bayou | Internal line | 2026-03-16 | 2678.2 | 271 | 78.2
CC-000362 | 2776.7 | Bayou | Internal line | 2026-03-23 | 2599 | 289.3 | 76.3
CC-000363 | 2798.1 | Bayou | Internal line | 2026-03-30 | 2597.7 | 195.5 | 21.2
CC-000364 | 2882.3 | Bayou | Internal line | 2026-04-06 | 2619 | 296 | 39.4
CC-000365 | 2802.7 | Bayou | Internal line | 2026-04-13 | 2546.9 | 196.8 | 48.8
CC-000366 | 2882.9 | Bayou | Internal line | 2026-04-20 | 2628.8 | 194.3 | 21
CC-000367 | 2783.5 | Bayou | Internal line | 2026-04-27 | 2562.4 | 243.4 | 30.2
CC-000368 | 2777.5 | Bayou | Internal line | 2026-05-04 | 2520.4 | 259.8 | 3.1
CC-000369 | 2902.7 | Bayou | Internal line | 2026-05-11 | 2806.4 | 262.1 | 79.5
CC-000370 | 2802.4 | Bayou | Internal line | 2026-05-18 | 2526.6 | 1191.8 | 2701.6
CC-000371 | 2496 | Bayou | Internal line | 2026-05-25 | 2264.1 | 419.8 | 666.7
CC-000372 | 2932.3 | Bayou | Internal line | 2026-06-01 | 2672.2 | 180.9 | 12.8
CC-000373 | 2859.1 | Bayou | Internal line | 2026-06-08 | 2617.3 | 196.5 | 28.9
CC-000374 | 2758.6 | Bayou | Internal line | 2026-06-15 | 2614.7 | 311.5 | 5.2
CC-000375 | 2936.5 | Bayou | Internal line | 2026-06-22 | 2853.1 | 173.2 | 55.9
CC-000376 | 2840 | Bayou | Internal line | 2026-06-29 | 2581.1 | 242.9 | 17.2
CC-000377 | 2433.7 | Bayou | Internal line | 2026-07-06 | 2220 | 237.7 | 28.2
CC-000378 | 2867.3 | Bayou | Internal line | 2026-07-13 | 2672.4 | 300.9 | 62.2
CC-000379 | 2802.9 | Bayou | Internal line | 2026-07-20 | 2532 | 299.7 | 57.8
CC-000380 | 2830.6 | Bayou | Internal line | 2026-07-27 | 2702.4 | 167.9 | 42.2
CC-000381 | 2873.7 | Bayou | Internal line | 2026-08-03 | 2668.2 | 448.2 | 61.3
CC-000382 | 2889.7 | Bayou | Internal line | 2026-08-10 | 2602.3 | 374.1 | 26.8
CC-000383 | 2862.2 | Bayou | Internal line | 2026-08-17 | 2595.3 | 488.2 | 44.6
CC-000384 | 2886.1 | Bayou | Internal line | 2026-08-24 | 2603.4 | 402.3 | 18.6
CC-000385 | 2816.1 | Bayou | Internal line | 2026-08-31 | 2712.1 | 528.1 | 52.7
CC-000386 | 460.3 | Bayou | Troubleman | 2026-01-05 | 440.8 | 29.1 | 4.2
CC-000387 | 467.2 | Bayou | Troubleman | 2026-01-12 | 451 | 37.5 | 0.5
CC-000388 | 402.3 | Bayou | Troubleman | 2026-01-19 | 363.1 | 43 | 8
CC-000389 | 473.8 | Bayou | Troubleman | 2026-01-26 | 439 | 36.5 | 8.9
CC-000390 | 458.8 | Bayou | Troubleman | 2026-02-02 | 436.6 | 44.2 | 9.6
CC-000391 | 464.8 | Bayou | Troubleman | 2026-02-09 | 447.9 | 43.8 | 1.9
CC-000392 | 468.8 | Bayou | Troubleman | 2026-02-16 | 458.5 | 36.5 | 10.7
CC-000393 | 471 | Bayou | Troubleman | 2026-02-23 | 429.9 | 27.4 | 5.3
CC-000394 | 477.1 | Bayou | Troubleman | 2026-03-02 | 458 | 36.7 | 2.6
CC-000395 | 460 | Bayou | Troubleman | 2026-03-09 | 437.2 | 28 | 2
CC-000396 | 448.8 | Bayou | Troubleman | 2026-03-16 | 438.2 | 38.5 | 9.1
CC-000397 | 469.6 | Bayou | Troubleman | 2026-03-23 | 431.6 | 42.5 | 7
CC-000398 | 454.2 | Bayou | Troubleman | 2026-03-30 | 415.9 | 32.2 | 6.5
CC-000399 | 451.3 | Bayou | Troubleman | 2026-04-06 | 407.4 | 25.4 | 5.9
CC-000400 | 465.2 | Bayou | Troubleman | 2026-04-13 | 436.4 | 32.9 | 12.7
CC-000401 | 468.3 | Bayou | Troubleman | 2026-04-20 | 451.8 | 47.6 | 1.1
CC-000402 | 463.8 | Bayou | Troubleman | 2026-04-27 | 422.8 | 29.5 | 1.2
CC-000403 | 475.2 | Bayou | Troubleman | 2026-05-04 | 444.4 | 51.6 | 5
CC-000404 | 457.5 | Bayou | Troubleman | 2026-05-11 | 444.7 | 31.8 | 5.9
CC-000405 | 469.3 | Bayou | Troubleman | 2026-05-18 | 432.8 | 204.1 | 530.1
CC-000406 | 405.2 | Bayou | Troubleman | 2026-05-25 | 391.5 | 106.9 | 140.1
CC-000407 | 452.9 | Bayou | Troubleman | 2026-06-01 | 414.6 | 48.3 | 9.3
CC-000408 | 460.2 | Bayou | Troubleman | 2026-06-08 | 445.2 | 36.9 | 3.5
CC-000409 | 465 | Bayou | Troubleman | 2026-06-15 | 438.1 | 36 | 11
CC-000410 | 466.4 | Bayou | Troubleman | 2026-06-22 | 433.5 | 46.9 | 1.2
CC-000411 | 465 | Bayou | Troubleman | 2026-06-29 | 442.3 | 37.3 | 5.2
CC-000412 | 396.4 | Bayou | Troubleman | 2026-07-06 | 365.6 | 34.2 | 10.7
CC-000413 | 448 | Bayou | Troubleman | 2026-07-13 | 429.5 | 38.7 | 9.9
CC-000414 | 451.8 | Bayou | Troubleman | 2026-07-20 | 408.4 | 24.5 | 8.9
CC-000415 | 468.5 | Bayou | Troubleman | 2026-07-27 | 428.8 | 33.2 | 10.1
CC-000416 | 467.5 | Bayou | Troubleman | 2026-08-03 | 455.7 | 72.5 | 3.9
CC-000417 | 449.1 | Bayou | Troubleman | 2026-08-10 | 417.8 | 59.9 | 4.6
CC-000418 | 458.6 | Bayou | Troubleman | 2026-08-17 | 415.1 | 65.2 | 1.3
CC-000419 | 455.2 | Bayou | Troubleman | 2026-08-24 | 442.3 | 72.6 | 13.2
CC-000420 | 462.9 | Bayou | Troubleman | 2026-08-31 | 446.9 | 85.7 | 10.5
CC-000421 | 645.5 | Bayou | Underground | 2026-01-05 | 582.7 | 51 | 15.9
CC-000422 | 632.1 | Bayou | Underground | 2026-01-12 | 612.6 | 45.9 | 2.5
CC-000423 | 557.9 | Bayou | Underground | 2026-01-19 | 502.2 | 37.5 | 7.4
CC-000424 | 655.4 | Bayou | Underground | 2026-01-26 | 592 | 42.1 | 8.4
CC-000425 | 637.3 | Bayou | Underground | 2026-02-02 | 594.6 | 41.6 | 6.3
CC-000426 | 620.4 | Bayou | Underground | 2026-02-09 | 560.1 | 42 | 10.5
CC-000427 | 660.8 | Bayou | Underground | 2026-02-16 | 634.8 | 38.5 | 13.6
CC-000428 | 643.9 | Bayou | Underground | 2026-02-23 | 594.4 | 55.9 | 2.7
CC-000429 | 638.1 | Bayou | Underground | 2026-03-02 | 607.6 | 66.8 | 1.4
CC-000430 | 661.9 | Bayou | Underground | 2026-03-09 | 632 | 52.6 | 4.3
CC-000431 | 630.3 | Bayou | Underground | 2026-03-16 | 608.3 | 40 | 15.1
CC-000432 | 634.5 | Bayou | Underground | 2026-03-23 | 590.7 | 62.1 | 5.7
CC-000433 | 641.6 | Bayou | Underground | 2026-03-30 | 602 | 38.8 | 5.2
CC-000434 | 621.7 | Bayou | Underground | 2026-04-06 | 569.5 | 61.2 | 14.8
CC-000435 | 643.3 | Bayou | Underground | 2026-04-13 | 623.8 | 40.1 | 17.8
CC-000436 | 636.5 | Bayou | Underground | 2026-04-20 | 620.4 | 63 | 2.7
CC-000437 | 641.9 | Bayou | Underground | 2026-04-27 | 584.9 | 66.2 | 8.4
CC-000438 | 658.6 | Bayou | Underground | 2026-05-04 | 618.9 | 71.1 | 4.1
CC-000439 | 636 | Bayou | Underground | 2026-05-11 | 584.6 | 67.2 | 2.3
CC-000440 | 625.1 | Bayou | Underground | 2026-05-18 | 595.1 | 335.5 | 670.9
CC-000441 | 553.2 | Bayou | Underground | 2026-05-25 | 529.5 | 103.9 | 149.1
CC-000442 | 661.7 | Bayou | Underground | 2026-06-01 | 599.9 | 54.8 | 17.9
CC-000443 | 623 | Bayou | Underground | 2026-06-08 | 588.8 | 39.4 | 16.3
CC-000444 | 648.1 | Bayou | Underground | 2026-06-15 | 584.8 | 58.2 | 7.5
CC-000445 | 628.6 | Bayou | Underground | 2026-06-22 | 581.8 | 40 | 12.8
CC-000446 | 645 | Bayou | Underground | 2026-06-29 | 629.2 | 50.2 | 16.3
CC-000447 | 537.4 | Bayou | Underground | 2026-07-06 | 519.6 | 38.6 | 3.7
CC-000448 | 639.5 | Bayou | Underground | 2026-07-13 | 589.6 | 64 | 6.6
CC-000449 | 632.6 | Bayou | Underground | 2026-07-20 | 580.9 | 38.4 | 0.7
CC-000450 | 619.6 | Bayou | Underground | 2026-07-27 | 569.5 | 56.3 | 4.4
CC-000451 | 654.5 | Bayou | Underground | 2026-08-03 | 616.1 | 60.5 | 3
CC-000452 | 659.6 | Bayou | Underground | 2026-08-10 | 628.5 | 60.9 | 10.7
CC-000453 | 643.5 | Bayou | Underground | 2026-08-17 | 595.4 | 67.8 | 12.9
CC-000454 | 629.6 | Bayou | Underground | 2026-08-24 | 579.9 | 35.5 | 8.3
CC-000455 | 650.3 | Bayou | Underground | 2026-08-31 | 606 | 67.2 | 12.5
CC-000456 | 2118.4 | Bayou | Contract line | 2026-01-05 | 2035.2 | 167.6 | 59.3
CC-000457 | 2179 | Bayou | Contract line | 2026-01-12 | 2036.4 | 230.6 | 57.2
CC-000458 | 1865.6 | Bayou | Contract line | 2026-01-19 | 1820.2 | 170.1 | 39.8
CC-000459 | 2091.2 | Bayou | Contract line | 2026-01-26 | 2046.1 | 168.9 | 12.8
CC-000460 | 2081.3 | Bayou | Contract line | 2026-02-02 | 1934.8 | 188.9 | 11.7
CC-000461 | 2136.2 | Bayou | Contract line | 2026-02-09 | 2016.5 | 164.3 | 2.6
CC-000462 | 2107.8 | Bayou | Contract line | 2026-02-16 | 1960.5 | 210.9 | 37.7
CC-000463 | 2175.1 | Bayou | Contract line | 2026-02-23 | 2072 | 232.6 | 28.8
CC-000464 | 2110.3 | Bayou | Contract line | 2026-03-02 | 2066.3 | 129.8 | 53.6
CC-000465 | 2166.4 | Bayou | Contract line | 2026-03-09 | 1971.8 | 204.9 | 29.9
CC-000466 | 2200.1 | Bayou | Contract line | 2026-03-16 | 2006.4 | 197.5 | 25.4
CC-000467 | 2191 | Bayou | Contract line | 2026-03-23 | 1980.5 | 144 | 38
CC-000468 | 2107 | Bayou | Contract line | 2026-03-30 | 1906.8 | 185.8 | 32
CC-000469 | 2070.8 | Bayou | Contract line | 2026-04-06 | 1922.1 | 119.6 | 23.8
CC-000470 | 2174.3 | Bayou | Contract line | 2026-04-13 | 2121.7 | 135.7 | 8.8
CC-000471 | 2177.6 | Bayou | Contract line | 2026-04-20 | 1966.3 | 143.6 | 41.4
CC-000472 | 2086.9 | Bayou | Contract line | 2026-04-27 | 1945 | 210.7 | 54.9
CC-000473 | 2188.3 | Bayou | Contract line | 2026-05-04 | 2139 | 195.3 | 23.6
CC-000474 | 2131.3 | Bayou | Contract line | 2026-05-11 | 2008.8 | 169.1 | 53.5
CC-000475 | 2191.6 | Bayou | Contract line | 2026-05-18 | 2127.5 | 1207.4 | 2541.9
CC-000476 | 1769.3 | Bayou | Contract line | 2026-05-25 | 1600.1 | 385.2 | 504.2
CC-000477 | 2073.6 | Bayou | Contract line | 2026-06-01 | 1950.4 | 142.3 | 30.1
CC-000478 | 2080.7 | Bayou | Contract line | 2026-06-08 | 1987.5 | 197.1 | 17.7
CC-000479 | 2157.1 | Bayou | Contract line | 2026-06-15 | 1982.3 | 166.5 | 20
CC-000480 | 2090.9 | Bayou | Contract line | 2026-06-22 | 2014.3 | 174.8 | 31.5
CC-000481 | 2175.4 | Bayou | Contract line | 2026-06-29 | 2053 | 132.9 | 61
CC-000482 | 1811.9 | Bayou | Contract line | 2026-07-06 | 1707 | 113 | 27.9
CC-000483 | 2133.1 | Bayou | Contract line | 2026-07-13 | 2035.1 | 160.2 | 36.4
CC-000484 | 2109.8 | Bayou | Contract line | 2026-07-20 | 1900.7 | 140.6 | 15.5
CC-000485 | 2137.9 | Bayou | Contract line | 2026-07-27 | 2031.4 | 223.2 | 18.2
CC-000486 | 2133.1 | Bayou | Contract line | 2026-08-03 | 1990.3 | 220.9 | 25.1
CC-000487 | 2203.2 | Bayou | Contract line | 2026-08-10 | 2005.6 | 123.8 | 21.4
CC-000488 | 2083.7 | Bayou | Contract line | 2026-08-17 | 1890.5 | 153.3 | 27.3
CC-000489 | 2160.4 | Bayou | Contract line | 2026-08-24 | 2042.3 | 212.1 | 51.1
CC-000490 | 2065.8 | Bayou | Contract line | 2026-08-31 | 1952.3 | 153.6 | 44.6
CC-000491 | 3028.1 | Bayou | Vegetation (contract) | 2026-01-05 | 2944.2 | 304.2 | 46.3
CC-000492 | 2965.3 | Bayou | Vegetation (contract) | 2026-01-12 | 2846.9 | 235.6 | 58.4
CC-000493 | 2501.7 | Bayou | Vegetation (contract) | 2026-01-19 | 2273.2 | 171.5 | 23.8
CC-000494 | 3005.6 | Bayou | Vegetation (contract) | 2026-01-26 | 2909.6 | 250.8 | 58.2
CC-000495 | 2923.8 | Bayou | Vegetation (contract) | 2026-02-02 | 2829.3 | 233.1 | 39.4
CC-000496 | 3088.8 | Bayou | Vegetation (contract) | 2026-02-09 | 2915.2 | 330.1 | 11.9
CC-000497 | 3034.4 | Bayou | Vegetation (contract) | 2026-02-16 | 2876.5 | 331.1 | 84
CC-000498 | 3089.8 | Bayou | Vegetation (contract) | 2026-02-23 | 2986 | 204.6 | 77.1
CC-000499 | 3001.5 | Bayou | Vegetation (contract) | 2026-03-02 | 2933.8 | 252.5 | 79.9
CC-000500 | 2981 | Bayou | Vegetation (contract) | 2026-03-09 | 2832.5 | 331.2 | 12.3
CC-000501 | 3031 | Bayou | Vegetation (contract) | 2026-03-16 | 2816.9 | 244.1 | 51.2
CC-000502 | 2989.6 | Bayou | Vegetation (contract) | 2026-03-23 | 2704.7 | 202.2 | 69.3
CC-000503 | 2943.2 | Bayou | Vegetation (contract) | 2026-03-30 | 2684 | 186.6 | 39.2
CC-000504 | 3010.8 | Bayou | Vegetation (contract) | 2026-04-06 | 2815.3 | 217.7 | 84.1
CC-000505 | 2996.5 | Bayou | Vegetation (contract) | 2026-04-13 | 2700.8 | 304.2 | 8.5
CC-000506 | 2945.7 | Bayou | Vegetation (contract) | 2026-04-20 | 2770.4 | 175.9 | 46
CC-000507 | 2993.6 | Bayou | Vegetation (contract) | 2026-04-27 | 2751.7 | 251.3 | 36.6
CC-000508 | 3088 | Bayou | Vegetation (contract) | 2026-05-04 | 2945.8 | 285.3 | 71.1
CC-000509 | 2921.1 | Bayou | Vegetation (contract) | 2026-05-11 | 2668.7 | 310 | 48.6
CC-000510 | 2916.7 | Bayou | Vegetation (contract) | 2026-05-18 | 2840 | 1647.1 | 3393.7
CC-000511 | 2551.6 | Bayou | Vegetation (contract) | 2026-05-25 | 2483.2 | 670 | 1112.3
CC-000512 | 3006.2 | Bayou | Vegetation (contract) | 2026-06-01 | 2709.7 | 308.8 | 878
CC-000513 | 2926.6 | Bayou | Vegetation (contract) | 2026-06-08 | 2854.1 | 241.8 | 906.3
CC-000514 | 2905.1 | Bayou | Vegetation (contract) | 2026-06-15 | 2615.9 | 192 | 62.7
CC-000515 | 3034.7 | Bayou | Vegetation (contract) | 2026-06-22 | 2899 | 188.2 | 20.8
CC-000516 | 3055.9 | Bayou | Vegetation (contract) | 2026-06-29 | 2807.4 | 325 | 20.5
CC-000517 | 2464.9 | Bayou | Vegetation (contract) | 2026-07-06 | 2358.6 | 187.2 | 69.4
CC-000518 | 2924.1 | Bayou | Vegetation (contract) | 2026-07-13 | 2848.8 | 277.4 | 2.7
CC-000519 | 2890.9 | Bayou | Vegetation (contract) | 2026-07-20 | 2752.4 | 247.2 | 17.7
CC-000520 | 3041 | Bayou | Vegetation (contract) | 2026-07-27 | 2839.3 | 228.6 | 11.1
CC-000521 | 2906.6 | Bayou | Vegetation (contract) | 2026-08-03 | 2748.3 | 273.9 | 3.9
CC-000522 | 2962 | Bayou | Vegetation (contract) | 2026-08-10 | 2809.4 | 316.7 | 62.6
CC-000523 | 3070.2 | Bayou | Vegetation (contract) | 2026-08-17 | 2809.7 | 318.6 | 73.5
CC-000524 | 2965 | Bayou | Vegetation (contract) | 2026-08-24 | 2886 | 341 | 5.9
CC-000525 | 2922.4 | Bayou | Vegetation (contract) | 2026-08-31 | 2774 | 225.7 | 3.3
CC-000526 | 2241 | Prairie | Internal line | 2026-01-05 | 2177 | 230.8 | 40.4
CC-000527 | 2252.3 | Prairie | Internal line | 2026-01-12 | 2141.1 | 218 | 19.3
CC-000528 | 1944.8 | Prairie | Internal line | 2026-01-19 | 1808.5 | 149 | 9.4
CC-000529 | 2349.7 | Prairie | Internal line | 2026-01-26 | 2209.4 | 225.8 | 38.4
CC-000530 | 2338.7 | Prairie | Internal line | 2026-02-02 | 2150.9 | 166.6 | 62.7
CC-000531 | 2311.9 | Prairie | Internal line | 2026-02-09 | 2240.5 | 218.5 | 29.8
CC-000532 | 2283.7 | Prairie | Internal line | 2026-02-16 | 2164.1 | 202 | 55.8
CC-000533 | 2222 | Prairie | Internal line | 2026-02-23 | 2063 | 192.6 | 7.7
CC-000534 | 2346.6 | Prairie | Internal line | 2026-03-02 | 2256.8 | 254 | 16.1
CC-000535 | 2281.5 | Prairie | Internal line | 2026-03-09 | 2181.3 | 205 | 43.7
CC-000536 | 2295.8 | Prairie | Internal line | 2026-03-16 | 2125.3 | 166 | 34
CC-000537 | 2259.8 | Prairie | Internal line | 2026-03-23 | 2212.4 | 160.9 | 25.6
CC-000538 | 2314.1 | Prairie | Internal line | 2026-03-30 | 2143.7 | 250.7 | 30.8
CC-000539 | 2305 | Prairie | Internal line | 2026-04-06 | 2114.2 | 249.4 | 32
CC-000540 | 2314.9 | Prairie | Internal line | 2026-04-13 | 2231.3 | 164.4 | 25.7
CC-000541 | 2303.9 | Prairie | Internal line | 2026-04-20 | 2205.2 | 222.6 | 2.8
CC-000542 | 2347.3 | Prairie | Internal line | 2026-04-27 | 2264.4 | 216.7 | 47.8
CC-000543 | 2223.6 | Prairie | Internal line | 2026-05-04 | 2036.7 | 193.5 | 46.7
CC-000544 | 2338.4 | Prairie | Internal line | 2026-05-11 | 2203.5 | 255.8 | 9.5
CC-000545 | 2318.9 | Prairie | Internal line | 2026-05-18 | 2103.7 | 1165.4 | 2741.4
CC-000546 | 1928.9 | Prairie | Internal line | 2026-05-25 | 1745.1 | 403.4 | 439.3
CC-000547 | 2290.8 | Prairie | Internal line | 2026-06-01 | 2184 | 242.4 | 64.8
CC-000548 | 2311.1 | Prairie | Internal line | 2026-06-08 | 2247.1 | 174.7 | 58
CC-000549 | 2231.6 | Prairie | Internal line | 2026-06-15 | 2151.5 | 161.1 | 38.5
CC-000550 | 2220.5 | Prairie | Internal line | 2026-06-22 | 2034.3 | 240.4 | 47.2
CC-000551 | 2351.1 | Prairie | Internal line | 2026-06-29 | 2252.1 | 209.3 | 3.8
CC-000552 | 1909.2 | Prairie | Internal line | 2026-07-06 | 1800.3 | 146.2 | 3.6
CC-000553 | 2236.8 | Prairie | Internal line | 2026-07-13 | 2116.7 | 204.8 | 41
CC-000554 | 2208.4 | Prairie | Internal line | 2026-07-20 | 2163.6 | 201 | 3.6
CC-000555 | 2237.4 | Prairie | Internal line | 2026-07-27 | 2189.9 | 215.6 | 23.3
CC-000556 | 2297.6 | Prairie | Internal line | 2026-08-03 | 2176 | 433.2 | 35.3
CC-000557 | 2264.6 | Prairie | Internal line | 2026-08-10 | 2092.5 | 409.6 | 58.7
CC-000558 | 2278.9 | Prairie | Internal line | 2026-08-17 | 2109.6 | 357.7 | 50
CC-000559 | 2230.6 | Prairie | Internal line | 2026-08-24 | 2073.2 | 354.7 | 56.8
CC-000560 | 2247.6 | Prairie | Internal line | 2026-08-31 | 2153 | 416.3 | 45
CC-000561 | 388 | Prairie | Troubleman | 2026-01-05 | 372.3 | 41.7 | 10
CC-000562 | 379.5 | Prairie | Troubleman | 2026-01-12 | 359.4 | 42 | 3.9
CC-000563 | 322.5 | Prairie | Troubleman | 2026-01-19 | 297.6 | 29.6 | 3.3
CC-000564 | 389.8 | Prairie | Troubleman | 2026-01-26 | 369.5 | 44.2 | 1.4
CC-000565 | 379.7 | Prairie | Troubleman | 2026-02-02 | 350.4 | 38.6 | 7
CC-000566 | 398.7 | Prairie | Troubleman | 2026-02-09 | 368.5 | 43.6 | 9.1
CC-000567 | 404.5 | Prairie | Troubleman | 2026-02-16 | 375.7 | 32.6 | 10.6
CC-000568 | 397.2 | Prairie | Troubleman | 2026-02-23 | 376 | 28.9 | 3.2
CC-000569 | 392.4 | Prairie | Troubleman | 2026-03-02 | 365.9 | 42.5 | 2
CC-000570 | 394.7 | Prairie | Troubleman | 2026-03-09 | 363.8 | 23.2 | 7.1
CC-000571 | 389.6 | Prairie | Troubleman | 2026-03-16 | 373.3 | 29.3 | 8.2
CC-000572 | 389.9 | Prairie | Troubleman | 2026-03-23 | 351.3 | 31 | 5.2
CC-000573 | 384.6 | Prairie | Troubleman | 2026-03-30 | 351.1 | 27.5 | 2.6
CC-000574 | 398 | Prairie | Troubleman | 2026-04-06 | 372.9 | 24.3 | 0.2
CC-000575 | 383.6 | Prairie | Troubleman | 2026-04-13 | 352.1 | 24.9 | 8.4
CC-000576 | 391.1 | Prairie | Troubleman | 2026-04-20 | 371.3 | 32.9 | 2.1
CC-000577 | 401.3 | Prairie | Troubleman | 2026-04-27 | 374.4 | 44.1 | 0.9
CC-000578 | 379.2 | Prairie | Troubleman | 2026-05-04 | 354.3 | 31.7 | 0.1
CC-000579 | 398.6 | Prairie | Troubleman | 2026-05-11 | 373.3 | 43.4 | 1.1
CC-000580 | 383 | Prairie | Troubleman | 2026-05-18 | 360.9 | 184.5 | 442.3
CC-000581 | 339.4 | Prairie | Troubleman | 2026-05-25 | 318.8 | 63.8 | 85
CC-000582 | 395.6 | Prairie | Troubleman | 2026-06-01 | 368.2 | 29.6 | 1.4
CC-000583 | 385.4 | Prairie | Troubleman | 2026-06-08 | 358.9 | 26.3 | 9.7
CC-000584 | 379.1 | Prairie | Troubleman | 2026-06-15 | 361.4 | 30.9 | 7.9
CC-000585 | 404.2 | Prairie | Troubleman | 2026-06-22 | 375.2 | 39.6 | 7
CC-000586 | 393.8 | Prairie | Troubleman | 2026-06-29 | 376.2 | 29.7 | 9.7
CC-000587 | 322.5 | Prairie | Troubleman | 2026-07-06 | 299.4 | 25.3 | 2
CC-000588 | 399.6 | Prairie | Troubleman | 2026-07-13 | 372.3 | 29.6 | 5.9
CC-000589 | 396.9 | Prairie | Troubleman | 2026-07-20 | 375 | 44.3 | 4.2
CC-000590 | 382.2 | Prairie | Troubleman | 2026-07-27 | 346.3 | 38 | 4.8
CC-000591 | 380.8 | Prairie | Troubleman | 2026-08-03 | 361.4 | 51.4 | 7.5
CC-000592 | 400.5 | Prairie | Troubleman | 2026-08-10 | 377 | 54.5 | 6.4
CC-000593 | 393 | Prairie | Troubleman | 2026-08-17 | 380.7 | 67.2 | 6.4
CC-000594 | 381.2 | Prairie | Troubleman | 2026-08-24 | 348.3 | 68.3 | 8.9
CC-000595 | 390.9 | Prairie | Troubleman | 2026-08-31 | 361.1 | 69.7 | 6.5
CC-000596 | 220.1 | Prairie | Underground | 2026-01-05 | 201.7 | 23 | 5.8
CC-000597 | 220.7 | Prairie | Underground | 2026-01-12 | 207.4 | 18.3 | 3.9
CC-000598 | 181 | Prairie | Underground | 2026-01-19 | 174.2 | 11 | 2.6
CC-000599 | 210.9 | Prairie | Underground | 2026-01-26 | 193.2 | 15.9 | 2.2
CC-000600 | 211.3 | Prairie | Underground | 2026-02-02 | 206.8 | 22.7 | 3
CC-000601 | 210.8 | Prairie | Underground | 2026-02-09 | 197 | 22.6 | 0
CC-000602 | 206.6 | Prairie | Underground | 2026-02-16 | 193.5 | 22.7 | 4.2
CC-000603 | 211.9 | Prairie | Underground | 2026-02-23 | 191.9 | 22.3 | 3.6
CC-000604 | 211.6 | Prairie | Underground | 2026-03-02 | 206.7 | 20 | 5
CC-000605 | 216.4 | Prairie | Underground | 2026-03-09 | 205 | 23.9 | 4.7
CC-000606 | 210.3 | Prairie | Underground | 2026-03-16 | 193.8 | 11.9 | 3.7
CC-000607 | 212.2 | Prairie | Underground | 2026-03-23 | 196.2 | 13.8 | 0.2
CC-000608 | 213.8 | Prairie | Underground | 2026-03-30 | 202.1 | 14.1 | 3.3
CC-000609 | 214.9 | Prairie | Underground | 2026-04-06 | 194.7 | 17.8 | 4.7
CC-000610 | 209.2 | Prairie | Underground | 2026-04-13 | 192.3 | 18.8 | 4.4
CC-000611 | 209.3 | Prairie | Underground | 2026-04-20 | 204.2 | 20.3 | 0.8
CC-000612 | 211.8 | Prairie | Underground | 2026-04-27 | 201.7 | 21.7 | 4
CC-000613 | 218.7 | Prairie | Underground | 2026-05-04 | 203.3 | 16.7 | 0.2
CC-000614 | 219.4 | Prairie | Underground | 2026-05-11 | 212 | 14.2 | 1.4
CC-000615 | 209.2 | Prairie | Underground | 2026-05-18 | 201.9 | 94.9 | 225.4
CC-000616 | 176.7 | Prairie | Underground | 2026-05-25 | 172.9 | 44.6 | 60.5
CC-000617 | 218.6 | Prairie | Underground | 2026-06-01 | 203.2 | 19.7 | 0.8
CC-000618 | 217.8 | Prairie | Underground | 2026-06-08 | 203.6 | 20 | 4.6
CC-000619 | 207.5 | Prairie | Underground | 2026-06-15 | 186.8 | 17.9 | 2.6
CC-000620 | 207.5 | Prairie | Underground | 2026-06-22 | 193.3 | 17.6 | 0.4
CC-000621 | 217.4 | Prairie | Underground | 2026-06-29 | 209.4 | 23.7 | 1.4
CC-000622 | 177.2 | Prairie | Underground | 2026-07-06 | 167.9 | 12.1 | 4.4
CC-000623 | 218.9 | Prairie | Underground | 2026-07-13 | 213.4 | 16.6 | 5.4
CC-000624 | 209.4 | Prairie | Underground | 2026-07-20 | 200.2 | 23.3 | 4.1
CC-000625 | 218.1 | Prairie | Underground | 2026-07-27 | 212.3 | 17.9 | 3.2
CC-000626 | 210.4 | Prairie | Underground | 2026-08-03 | 193.5 | 11.7 | 3.5
CC-000627 | 217.3 | Prairie | Underground | 2026-08-10 | 203.2 | 18.5 | 1.7
CC-000628 | 214.6 | Prairie | Underground | 2026-08-17 | 201.1 | 23.2 | 1.5
CC-000629 | 212.2 | Prairie | Underground | 2026-08-24 | 198.4 | 11.9 | 5.8
CC-000630 | 217.3 | Prairie | Underground | 2026-08-31 | 201.7 | 13.2 | 2.9
CC-000631 | 1464.5 | Prairie | Contract line | 2026-01-05 | 1330.7 | 112.5 | 38.8
CC-000632 | 1398.1 | Prairie | Contract line | 2026-01-12 | 1342.9 | 85.6 | 9.9
CC-000633 | 1224.1 | Prairie | Contract line | 2026-01-19 | 1120.4 | 97.7 | 21.3
CC-000634 | 1404.2 | Prairie | Contract line | 2026-01-26 | 1295.8 | 155.3 | 20.4
CC-000635 | 1441.7 | Prairie | Contract line | 2026-02-02 | 1315.9 | 117.6 | 36.5
CC-000636 | 1414.8 | Prairie | Contract line | 2026-02-09 | 1344.5 | 141.8 | 4.3
CC-000637 | 1395.6 | Prairie | Contract line | 2026-02-16 | 1317.5 | 148.5 | 6.6
CC-000638 | 1401.3 | Prairie | Contract line | 2026-02-23 | 1338.1 | 112.4 | 21.6
CC-000639 | 1453.9 | Prairie | Contract line | 2026-03-02 | 1340.5 | 150.8 | 7.4
CC-000640 | 1379.1 | Prairie | Contract line | 2026-03-09 | 1254.5 | 145.8 | 7.7
CC-000641 | 1403.3 | Prairie | Contract line | 2026-03-16 | 1351.5 | 125.7 | 39.8
CC-000642 | 1413.7 | Prairie | Contract line | 2026-03-23 | 1294.5 | 139.4 | 16.5
CC-000643 | 1381.6 | Prairie | Contract line | 2026-03-30 | 1261.9 | 145.8 | 24.3
CC-000644 | 1384 | Prairie | Contract line | 2026-04-06 | 1269.2 | 121.5 | 37.4
CC-000645 | 1397.1 | Prairie | Contract line | 2026-04-13 | 1344.3 | 102 | 34.7
CC-000646 | 1432.1 | Prairie | Contract line | 2026-04-20 | 1383.3 | 154 | 15.2
CC-000647 | 1445 | Prairie | Contract line | 2026-04-27 | 1365.2 | 148.1 | 30.3
CC-000648 | 1435.1 | Prairie | Contract line | 2026-05-04 | 1365.6 | 161.5 | 20.8
CC-000649 | 1419.8 | Prairie | Contract line | 2026-05-11 | 1342.6 | 88.1 | 13.8
CC-000650 | 1452.9 | Prairie | Contract line | 2026-05-18 | 1372.6 | 720 | 1735.1
CC-000651 | 1189.7 | Prairie | Contract line | 2026-05-25 | 1127.1 | 267 | 323.1
CC-000652 | 1411.9 | Prairie | Contract line | 2026-06-01 | 1272.2 | 113.3 | 35.4
CC-000653 | 1443.9 | Prairie | Contract line | 2026-06-08 | 1405.7 | 108.3 | 35.4
CC-000654 | 1420 | Prairie | Contract line | 2026-06-15 | 1360.2 | 153.8 | 19.9
CC-000655 | 1436.3 | Prairie | Contract line | 2026-06-22 | 1343.8 | 147.9 | 26.8
CC-000656 | 1448.3 | Prairie | Contract line | 2026-06-29 | 1305.9 | 131.4 | 4.7
CC-000657 | 1187.9 | Prairie | Contract line | 2026-07-06 | 1085.6 | 125.5 | 18
CC-000658 | 1415.6 | Prairie | Contract line | 2026-07-13 | 1283.4 | 130.4 | 16.9
CC-000659 | 1383.8 | Prairie | Contract line | 2026-07-20 | 1311.8 | 92.7 | 3.9
CC-000660 | 1423 | Prairie | Contract line | 2026-07-27 | 1350.4 | 122.7 | 37.3
CC-000661 | 1441.6 | Prairie | Contract line | 2026-08-03 | 1331.2 | 141.9 | 7.7
CC-000662 | 1463.4 | Prairie | Contract line | 2026-08-10 | 1340.3 | 147.1 | 17.6
CC-000663 | 1407.5 | Prairie | Contract line | 2026-08-17 | 1280.2 | 85.8 | 13.6
CC-000664 | 1404.5 | Prairie | Contract line | 2026-08-24 | 1366.3 | 155.3 | 28.9
CC-000665 | 1462.9 | Prairie | Contract line | 2026-08-31 | 1357.6 | 97.2 | 14
CC-000666 | 2180.6 | Prairie | Vegetation (contract) | 2026-01-05 | 2073.9 | 229.8 | 42.8
CC-000667 | 2168.1 | Prairie | Vegetation (contract) | 2026-01-12 | 2052.5 | 230.9 | 58.2
CC-000668 | 1812.7 | Prairie | Vegetation (contract) | 2026-01-19 | 1736.7 | 177.9 | 45.2
CC-000669 | 2153.6 | Prairie | Vegetation (contract) | 2026-01-26 | 2037.8 | 164.8 | 11.3
CC-000670 | 2166.5 | Prairie | Vegetation (contract) | 2026-02-02 | 2046.1 | 190.3 | 58.2
CC-000671 | 2132.2 | Prairie | Vegetation (contract) | 2026-02-09 | 1936.5 | 188.9 | 39.5
CC-000672 | 2064.7 | Prairie | Vegetation (contract) | 2026-02-16 | 1914.4 | 134.7 | 49.6
CC-000673 | 2134.9 | Prairie | Vegetation (contract) | 2026-02-23 | 2064.1 | 196.4 | 32.7
CC-000674 | 2143.4 | Prairie | Vegetation (contract) | 2026-03-02 | 2043.6 | 129.5 | 33.9
CC-000675 | 2090.7 | Prairie | Vegetation (contract) | 2026-03-09 | 1913 | 167.3 | 2.7
CC-000676 | 2144.4 | Prairie | Vegetation (contract) | 2026-03-16 | 1965.5 | 136.7 | 6.5
CC-000677 | 2175.9 | Prairie | Vegetation (contract) | 2026-03-23 | 2021 | 224.7 | 14.5
CC-000678 | 2146.3 | Prairie | Vegetation (contract) | 2026-03-30 | 2064 | 181.1 | 34.1
CC-000679 | 2206.7 | Prairie | Vegetation (contract) | 2026-04-06 | 2077.9 | 192.8 | 54.9
CC-000680 | 2073.5 | Prairie | Vegetation (contract) | 2026-04-13 | 2005.9 | 165.5 | 52.8
CC-000681 | 2194.4 | Prairie | Vegetation (contract) | 2026-04-20 | 2019.3 | 229.4 | 48.2
CC-000682 | 2144.4 | Prairie | Vegetation (contract) | 2026-04-27 | 1955.6 | 150.6 | 26.8
CC-000683 | 2138.9 | Prairie | Vegetation (contract) | 2026-05-04 | 2092 | 130.4 | 2.3
CC-000684 | 2071.1 | Prairie | Vegetation (contract) | 2026-05-11 | 2011.5 | 223.7 | 6.5
CC-000685 | 2090.3 | Prairie | Vegetation (contract) | 2026-05-18 | 1923.7 | 872.5 | 2372.1
CC-000686 | 1765.9 | Prairie | Vegetation (contract) | 2026-05-25 | 1679.5 | 323.6 | 608.6
CC-000687 | 2167.7 | Prairie | Vegetation (contract) | 2026-06-01 | 1971.3 | 119.4 | 702.5
CC-000688 | 2140.6 | Prairie | Vegetation (contract) | 2026-06-08 | 2048.7 | 217.7 | 674.9
CC-000689 | 2147.2 | Prairie | Vegetation (contract) | 2026-06-15 | 2095.7 | 226.3 | 42.3
CC-000690 | 2146.6 | Prairie | Vegetation (contract) | 2026-06-22 | 1949.9 | 131.5 | 57.8
CC-000691 | 2087.7 | Prairie | Vegetation (contract) | 2026-06-29 | 1936 | 164 | 35.1
CC-000692 | 1759.5 | Prairie | Vegetation (contract) | 2026-07-06 | 1646.1 | 137.2 | 4.8
CC-000693 | 2064.7 | Prairie | Vegetation (contract) | 2026-07-13 | 2002 | 133 | 41.1
CC-000694 | 2082.6 | Prairie | Vegetation (contract) | 2026-07-20 | 1911.7 | 181.7 | 36.6
CC-000695 | 2084.8 | Prairie | Vegetation (contract) | 2026-07-27 | 2026.4 | 197.3 | 47.6
CC-000696 | 2108.7 | Prairie | Vegetation (contract) | 2026-08-03 | 2011.9 | 150.3 | 19.9
CC-000697 | 2149.5 | Prairie | Vegetation (contract) | 2026-08-10 | 1998.8 | 138 | 42.8
CC-000698 | 2082.9 | Prairie | Vegetation (contract) | 2026-08-17 | 1875.6 | 138.2 | 26.1
CC-000699 | 2092.6 | Prairie | Vegetation (contract) | 2026-08-24 | 1918.2 | 211.2 | 51.3
CC-000700 | 2087.9 | Prairie | Vegetation (contract) | 2026-08-31 | 2042 | 181.8 | 37.7