## Slide 1
Capital Program Overview 2026-2030
Capital program overview, 2026-2030, September 22, 2026. The five-year outlook, 2026 status at the August close and how capital is recovered. Prepared by Capital Portfolio and FP&A for the executive team.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 1

## Slide 2
Five-year outlook: about $6.10 billion
2026: $1.12 billion
2027: $1.18 billion
2028: $1.24 billion
2029: $1.26 billion
2030: $1.30 billion
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 2
Notes: Excludes Harbor North until it is approved.

## Slide 3
Mix
About 83% electric (new service and growth, transmission, reliability and resiliency), about 14% gas (pipe replacement, reinforcement and new business) and the rest shared IT and facilities.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 3

## Slide 4
2026 at the August close
Budget $1,120 million across 152 projects; actual $683.0 million (61%); forecast $1,108 million. Electric $930M budget / $570.4M actual / $920M forecast; Gas $150M / $92.8M / $150M; Shared $40M / $19.8M / $38M.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 4

## Slide 5
Largest 2026 programs
Growth - new service $248M
Transmission $142M
Growth - substation and feeder $131M
Reliability - distribution $118M
Gas - pipe replacement $78M
Resiliency - pole replacement $62M
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 5

## Slide 6
Monthly capital spend
Actual capital by month, January-August 2026: from $68.6 million in January to $109.6 million in August.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 6

## Slide 7
Monthly capital spend · USD
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 7
Chart: 
| 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08
actual_usd | 68622326.23 | 71111198.71 | 78218654.54 | 79691603.85 | 75479954.91 | 92109596.56 | 108148859.07 | 109617806.13

## Slide 8
Resiliency
2026 resiliency budget $196 million; $109.0 million spent; forecast $180 million because undergrounding is forecast at $26 million against $42 million.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 8

## Slide 9
Growth and large loads
11 large-load requests of 20 MW or more total 1,905 MW (10 active, 1,785 MW). Harbor North (estimated $85 million, $6.5 million in 2026 for design and long-lead equipment) is outside the outlook until approved.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 9

## Slide 10
Recovery
Electric: base rates plus DCRF and TCOS updates. Gas: base rates plus annual interim rate adjustments. Resiliency costs follow the plan order. Rate base at December 31, 2025: about $4.62 billion electric and $1.18 billion gas.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 10

## Slide 11
Governance
Five stages from Initiate to Closeout; projects above $50 million need board approval.
Sedgewater Energy Holdings | Capital Portfolio Office with FP&A | 2026-09-22 | 11