## Slide 1
Contractor Partner Forum: 2026-2027 Work Outlook
Contractor Partner Forum, September 23, 2026. Sedgewater's 2026 work so far, the 2027 outlook and our safety priorities. Presented by Contractor Management to contractor leadership.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 1

## Slide 2
2026 so far
34 contractors under master service agreements. Through August we issued 420 releases authorizing $492.7 million; largest programs line construction ($159.9M), gas main replacement ($88.4M) and pole replacement ($61.9M). 26 storm releases ($30.5M) supported the May event response.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 2

## Slide 3
Release values
Authorized and invoiced values across all 2026 releases to August 31.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 3

## Slide 4
Release values · extract summary
Measure: authorized_usd
Unit: USD
Total: 492738841.72
Mean: 1173187.7184
Records: 420
Period: 2026-01-01 to 2026-08-31
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 4

## Slide 5
Release values · extract summary
Measure: invoiced_ytd_usd
Unit: USD
Total: 287812729.46
Mean: 685268.4035
Records: 420
Period: 2026-01-01 to 2026-08-31
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 5

## Slide 6
2027 outlook
Planned 2027 contractor work: $470 million to $560 million. The range is wide because it depends on rate case timing and resiliency pacing. Line construction and vegetation remain the largest scopes.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 6
Notes: We will narrow the range after the board's October decision; do not plan crews to the top of the range yet.

## Slide 7
Where the work is
Resiliency measures continue: pole replacement and bracing, vegetation acceleration, automation, undergrounding, URD cable and transmission hardening. In-scope Bayou and Prairie feeders move to a three-year trimming cycle. 2026 vegetation: 1,740.9 of 2,650 cycle miles and 188.6 of 330 acceleration miles done or in progress.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 7

## Slide 8
Safety: 2027 priorities
Heat illness prevention: rest breaks mandatory at a heat index of 103 degrees.
Minimum approach distance during storm work.
Work-zone traffic control.
Excavation damage prevention.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 8

## Slide 9
Safety: 2026 to date
Contractors reported 34 recordable injuries from January to August 2026. Thank you to the crews who worked the May event safely; we also learned from the incidents that did occur.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 9

## Slide 10
Prequalification and audits
Statuses: Approved, Approved - conditional, Suspended. Tiers A, B and C. Field audits at least monthly for tier A, quarterly for B and C, weekly while conditional. Audits use form SHE-F-112 revision C, which replaced revision B in January 2026.
Sedgewater Energy Holdings | Contractor Management | 2026-09-23 | 10