## Read me
Vegetation Work Units, January 2025 - August 2026
Sedgewater Energy Holdings
Effective date | 2026-09-08
Purpose | Extract all work units by feeder, contractor and program with miles and cost.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Workbook of all vegetation work units issued from January 2025 to August 2026 for cycle trimming, resiliency acceleration, hot spots, customer-request batches and post-storm work. Status at August 31, 2026. Prepared by Vegetation Management.
Sheets | Data 1 - one row per work unit: feeder, district, contractor, program, planned and completed miles, issued, start and completion dates, cost and status.
Sheets | Summary - formula totals of each numeric column.
2025 results | Contractors completed 2,174.3 miles of cycle trimming in 2025 at a recorded cost of $20.5 million, about $9,434 per mile.
2026 progress | The 2026 cycle plan is 2,650 miles, revised on December 30, 2025 after two feeders were re-measured; resiliency acceleration is 330 miles. By August 31, 2026, 1,740.9 of 2,650.0 planned cycle miles and 188.6 of 330.0 acceleration miles had been completed or partly completed. The 2026 Vegetation Management O&M budget is $31.4 million.
2026 progress | Other work: 60 hot-spot units in 2025 and 45 in 2026, and 36 post-storm units after the May 2026 event.
Contractors and cycle | Canopy Line Clearance Company works Harbor and Crossroads; Thornbury Vegetation Services and Oakmoss Utility Forestry work Bayou; Longleaf Right-of-Way Management works Prairie. Circuits are trimmed on a four-year cycle, moving to three years for in-scope Bayou and Prairie feeders under the resiliency plan.
How to read the data | Scheduled units have been issued but not started, so completed miles, start and completion dates are blank and cost is zero. In-progress units show miles completed to date and have no completion date. One in-progress unit has no cost recorded yet.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Vegetation work units, Jan 2025-Aug 2026 | completed_miles | circuit miles | 4970.4 | 7.0502 | 705 | 2025-01-01 | 2026-08-31
Vegetation work units, Jan 2025-Aug 2026 | planned_miles | circuit miles | 6020.9 | 7.498 | 803 | 2025-01-01 | 2026-08-31
Vegetation work units, Jan 2025-Aug 2026 | cost_usd | USD | 54737676.98 | 68251.4676 | 802 | 2025-01-01 | 2026-08-31

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Vegetation work units, Jan 2025-Aug 2026 | work_unit_id | VWU-000001 |  | id
Vegetation work units, Jan 2025-Aug 2026 | completed_miles | Miles completed | circuit miles | number
Vegetation work units, Jan 2025-Aug 2026 | issued_date | Date the work unit was issued to the contractor |  | date
Vegetation work units, Jan 2025-Aug 2026 | feeder_code | Feeder (FK) |  | category
Vegetation work units, Jan 2025-Aug 2026 | district | District (copied) |  | category
Vegetation work units, Jan 2025-Aug 2026 | contractor_code | Vegetation contractor (FK) |  | category
Vegetation work units, Jan 2025-Aug 2026 | program | Work program |  | category
Vegetation work units, Jan 2025-Aug 2026 | planned_miles | Miles planned | circuit miles | number
Vegetation work units, Jan 2025-Aug 2026 | start_date | Crew start |  | date
Vegetation work units, Jan 2025-Aug 2026 | complete_date | Unit closed |  | date
Vegetation work units, Jan 2025-Aug 2026 | cost_usd | Invoiced or accrued cost | USD | number
Vegetation work units, Jan 2025-Aug 2026 | status | Status |  | category

## Data 1
work_unit_id | completed_miles | issued_date | feeder_code | district | contractor_code | program | planned_miles | start_date | complete_date | cost_usd | status
VWU-000001 | 5.2 | 2025-01-02 | BY-S02-01 | Bayou | CT-15 | Cycle | 5.2 | 2025-01-06 | 2025-01-18 | 59111.48 | Complete
VWU-000002 | 1.3 | 2025-01-02 | BY-S25-04 | Bayou | CT-15 | Customer request batch | 1.3 | 2025-01-06 | 2025-01-08 | 20752.22 | Complete
VWU-000003 | 14.9 | 2025-01-02 | PR-S20-04 | Prairie | CT-16 | Cycle | 14.9 | 2025-01-06 | 2025-02-07 | 105749.83 | Complete
VWU-000004 | 8.5 | 2025-01-02 | HB-S11-01 | Harbor | CT-13 | Cycle | 8.5 | 2025-01-10 | 2025-01-23 | 85976.96 | Complete
VWU-000005 | 15.5 | 2025-01-02 | CR-S18-04 | Crossroads | CT-13 | Cycle | 15.5 | 2025-01-13 | 2025-02-11 | 136980.7 | Complete
VWU-000006 | 17.6 | 2025-01-03 | BY-S16-04 | Bayou | CT-15 | Cycle | 17.6 | 2025-01-15 | 2025-02-09 | 186449.91 | Complete
VWU-000007 | 7.9 | 2025-01-03 | CR-S02-01 | Crossroads | CT-13 | Cycle | 7.9 | 2025-01-15 | 2025-02-03 | 69011.39 | Complete
VWU-000008 | 3.1 | 2025-01-02 | PR-S09-02 | Prairie | CT-16 | Cycle | 3.1 | 2025-01-15 | 2025-01-24 | 21088.67 | Complete
VWU-000009 | 9.6 | 2025-01-09 | BY-S17-01 | Bayou | CT-15 | Cycle | 9.6 | 2025-01-16 | 2025-01-30 | 123896.6 | Complete
VWU-000010 | 12.8 | 2025-01-10 | CR-S12-03 | Crossroads | CT-13 | Cycle | 12.8 | 2025-01-18 | 2025-02-10 | 114014.12 | Complete
VWU-000011 | 1.9 | 2025-01-06 | CR-S18-04 | Crossroads | CT-13 | Customer request batch | 1.9 | 2025-01-19 | 2025-01-23 | 30702.13 | Complete
VWU-000012 | 10.5 | 2025-01-02 | BY-S17-01 | Bayou | CT-14 | Cycle | 10.5 | 2025-01-20 | 2025-02-10 | 113568.38 | Complete
VWU-000013 | 1.3 | 2025-01-08 | HB-S20-01 | Harbor | CT-13 | Customer request batch | 1.3 | 2025-01-20 | 2025-01-27 | 16602.7 | Complete
VWU-000014 | 5.2 | 2025-01-02 | PR-S03-02 | Prairie | CT-16 | Cycle | 5.2 | 2025-01-21 | 2025-01-31 | 43265.05 | Complete
VWU-000015 | 14.5 | 2025-01-11 | PR-S13-05 | Prairie | CT-16 | Cycle | 14.5 | 2025-01-22 | 2025-02-21 | 113875.05 | Complete
VWU-000016 | 13 | 2025-01-08 | BY-S04-01 | Bayou | CT-15 | Cycle | 13 | 2025-01-23 | 2025-02-12 | 150847.06 | Complete
VWU-000017 | 0.9 | 2025-01-02 | HB-S20-04 | Harbor | CT-13 | Cycle | 0.9 | 2025-01-23 | 2025-01-27 | 7804.1 | Complete
VWU-000018 | 17.7 | 2025-01-13 | BY-S18-01 | Bayou | CT-14 | Cycle | 17.7 | 2025-01-25 | 2025-02-24 | 180278.9 | Complete
VWU-000019 | 5.6 | 2025-01-20 | CR-S03-02 | Crossroads | CT-13 | Hot spot | 5.6 | 2025-01-27 | 2025-01-30 | 101892.48 | Complete
VWU-000020 | 0.8 | 2025-01-04 | CR-S16-04 | Crossroads | CT-13 | Customer request batch | 0.8 | 2025-01-27 | 2025-02-01 | 10170.44 | Complete
VWU-000021 | 16.9 | 2025-01-22 | CR-S30-07 | Crossroads | CT-13 | Cycle | 16.9 | 2025-01-29 | 2025-02-28 | 173833.05 | Complete
VWU-000022 | 5 | 2025-01-22 | PR-S04-01 | Prairie | CT-16 | Cycle | 5 | 2025-01-29 | 2025-02-11 | 33382.7 | Complete
VWU-000023 | 18.9 | 2025-01-06 | BY-S02-01 | Bayou | CT-15 | Cycle | 18.9 | 2025-01-30 | 2025-02-27 | 188234.41 | Complete
VWU-000024 | 13 | 2025-01-17 | BY-S30-01 | Bayou | CT-14 | Cycle | 13 | 2025-02-01 | 2025-03-02 | 169354.49 | Complete
VWU-000025 | 19.9 | 2025-01-11 | BY-S25-02 | Bayou | CT-14 | Cycle | 19.9 | 2025-02-02 | 2025-03-15 | 209535.68 | Complete
VWU-000026 | 2.2 | 2025-01-08 | HB-S16-04 | Harbor | CT-13 | Customer request batch | 2.2 | 2025-02-03 | 2025-02-07 | 32847.15 | Complete
VWU-000027 | 7.3 | 2025-01-10 | PR-S09-03 | Prairie | CT-16 | Cycle | 7.3 | 2025-02-03 | 2025-02-20 | 62108.13 | Complete
VWU-000028 | 15.7 | 2025-01-17 | HB-S05-04 | Harbor | CT-13 | Cycle | 15.7 | 2025-02-04 | 2025-02-25 | 167324.66 | Complete
VWU-000029 | 3.6 | 2025-01-21 | PR-S02-03 | Prairie | CT-16 | Cycle | 3.6 | 2025-02-04 | 2025-02-12 | 25187.03 | Complete
VWU-000030 | 11.6 | 2025-01-25 | HB-S07-03 | Harbor | CT-13 | Cycle | 11.6 | 2025-02-05 | 2025-03-05 | 106982.73 | Complete
VWU-000031 | 9.2 | 2025-01-11 | PR-S20-04 | Prairie | CT-16 | Cycle | 9.2 | 2025-02-05 | 2025-02-24 | 77100.5 | Complete
VWU-000032 | 8.3 | 2025-01-25 | PR-S03-04 | Prairie | CT-16 | Cycle | 8.3 | 2025-02-06 | 2025-02-24 | 69373.4 | Complete
VWU-000033 | 3.9 | 2025-01-14 | BY-S20-01 | Bayou | CT-14 | Hot spot | 3.9 | 2025-02-07 | 2025-02-09 | 63604.72 | Complete
VWU-000034 | 6.4 | 2025-01-20 | BY-S26-05 | Bayou | CT-15 | Cycle | 6.4 | 2025-02-08 | 2025-02-24 | 83393.52 | Complete
VWU-000035 | 4.7 | 2025-01-25 | BY-S18-01 | Bayou | CT-15 | Cycle | 4.7 | 2025-02-09 | 2025-02-18 | 49480.06 | Complete
VWU-000036 | 7.6 | 2025-01-25 | CR-S08-05 | Crossroads | CT-13 | Cycle | 7.6 | 2025-02-09 | 2025-02-28 | 74399.86 | Complete
VWU-000037 | 7.3 | 2025-01-15 | CR-S10-03 | Crossroads | CT-13 | Cycle | 7.3 | 2025-02-10 | 2025-02-26 | 68138.05 | Complete
VWU-000038 | 1.7 | 2025-02-01 | CR-S14-04 | Crossroads | CT-13 | Customer request batch | 1.7 | 2025-02-10 | 2025-02-17 | 24682.86 | Complete
VWU-000039 | 0.6 | 2025-01-22 | PR-S16-03 | Prairie | CT-16 | Customer request batch | 0.6 | 2025-02-10 | 2025-02-20 | 8089.86 | Complete
VWU-000040 | 7.9 | 2025-01-30 | CR-S19-04 | Crossroads | CT-13 | Cycle | 7.9 | 2025-02-13 | 2025-03-01 | 66665.43 | Complete
VWU-000041 | 2.7 | 2025-01-21 | PR-S07-02 | Prairie | CT-16 | Customer request batch | 2.7 | 2025-02-15 | 2025-02-21 | 41590.72 | Complete
VWU-000042 | 9.7 | 2025-01-20 | BY-S12-02 | Bayou | CT-15 | Cycle | 9.7 | 2025-02-16 | 2025-03-07 | 114304.15 | Complete
VWU-000043 | 3.3 | 2025-02-05 | PR-S06-01 | Prairie | CT-16 | Cycle | 3.3 | 2025-02-16 | 2025-02-25 | 27188.42 | Complete
VWU-000044 | 7.5 | 2025-01-22 | BY-S02-01 | Bayou | CT-14 | Cycle | 7.5 | 2025-02-17 | 2025-03-01 | 85038.9 | Complete
VWU-000045 | 10.6 | 2025-02-04 | PR-S19-05 | Prairie | CT-16 | Cycle | 10.6 | 2025-02-19 | 2025-03-15 | 69877.54 | Complete
VWU-000046 | 9.5 | 2025-02-12 | PR-S19-03 | Prairie | CT-16 | Cycle | 9.5 | 2025-02-20 | 2025-03-09 | 66527.18 | Complete
VWU-000047 | 2.8 | 2025-01-29 | CR-S08-04 | Crossroads | CT-13 | Hot spot | 2.8 | 2025-02-21 | 2025-02-23 | 39357.64 | Complete
VWU-000048 | 1.1 | 2025-01-29 | CR-S16-02 | Crossroads | CT-13 | Customer request batch | 1.1 | 2025-02-21 | 2025-02-23 | 17358.46 | Complete
VWU-000049 | 7.4 | 2025-02-15 | PR-S06-03 | Prairie | CT-16 | Cycle | 7.4 | 2025-02-23 | 2025-03-07 | 53578.07 | Complete
VWU-000050 | 5.1 | 2025-02-01 | BY-S19-02 | Bayou | CT-15 | Cycle | 5.1 | 2025-02-24 | 2025-03-05 | 64340.17 | Complete
VWU-000051 | 4.5 | 2025-02-20 | HB-S08-03 | Harbor | CT-13 | Hot spot | 4.5 | 2025-02-27 | 2025-03-03 | 85087.97 | Complete
VWU-000052 | 6.5 | 2025-02-14 | CR-S13-02 | Crossroads | CT-13 | Cycle | 6.5 | 2025-02-28 | 2025-03-12 | 59286.69 | Complete
VWU-000053 | 9.4 | 2025-02-15 | PR-S03-02 | Prairie | CT-16 | Cycle | 9.4 | 2025-02-28 | 2025-03-15 | 64563.44 | Complete
VWU-000054 | 15.1 | 2025-02-19 | HB-S18-02 | Harbor | CT-13 | Cycle | 15.1 | 2025-03-01 | 2025-03-25 | 135976.97 | Complete
VWU-000055 | 9.4 | 2025-02-18 | PR-S03-04 | Prairie | CT-16 | Cycle | 9.4 | 2025-03-01 | 2025-03-21 | 73946.6 | Complete
VWU-000056 | 14.8 | 2025-02-10 | BY-S19-02 | Bayou | CT-15 | Cycle | 14.8 | 2025-03-04 | 2025-03-31 | 180036.04 | Complete
VWU-000057 | 15.2 | 2025-02-22 | CR-S04-05 | Crossroads | CT-13 | Cycle | 15.2 | 2025-03-04 | 2025-04-05 | 136990.47 | Complete
VWU-000058 | 1.1 | 2025-02-21 | CR-S22-04 | Crossroads | CT-13 | Hot spot | 1.1 | 2025-03-05 | 2025-03-08 | 17089.28 | Complete
VWU-000059 | 4.9 | 2025-02-06 | CR-S21-01 | Crossroads | CT-13 | Cycle | 4.9 | 2025-03-06 | 2025-03-19 | 39880.35 | Complete
VWU-000060 | 11.8 | 2025-02-06 | CR-S24-03 | Crossroads | CT-13 | Cycle | 11.8 | 2025-03-06 | 2025-03-28 | 118877.78 | Complete
VWU-000061 | 3.2 | 2025-02-12 | HB-S20-03 | Harbor | CT-13 | Hot spot | 3.2 | 2025-03-06 | 2025-03-08 | 46097.63 | Complete
VWU-000062 | 6.7 | 2025-02-09 | BY-S02-01 | Bayou | CT-15 | Cycle | 6.7 | 2025-03-09 | 2025-03-25 | 77205.1 | Complete
VWU-000063 | 5.1 | 2025-02-25 | CR-S08-05 | Crossroads | CT-13 | Cycle | 5.1 | 2025-03-10 | 2025-03-23 | 42815.93 | Complete
VWU-000064 | 10 | 2025-02-13 | BY-S28-01 | Bayou | CT-14 | Cycle | 10 | 2025-03-11 | 2025-03-27 | 113593.49 | Complete
VWU-000065 | 2.9 | 2025-03-04 | HB-S02-02 | Harbor | CT-13 | Hot spot | 2.9 | 2025-03-14 | 2025-03-18 | 47031.76 | Complete
VWU-000066 | 2.3 | 2025-02-28 | BY-S16-03 | Bayou | CT-14 | Customer request batch | 2.3 | 2025-03-15 | 2025-03-26 | 34694.41 | Complete
VWU-000067 | 2.2 | 2025-02-21 | CR-S17-02 | Crossroads | CT-13 | Customer request batch | 2.2 | 2025-03-15 | 2025-03-21 | 33720.02 | Complete
VWU-000068 | 4.9 | 2025-03-04 | BY-S08-03 | Bayou | CT-14 | Cycle | 4.9 | 2025-03-18 | 2025-03-31 | 62746.09 | Complete
VWU-000069 | 6 | 2025-03-12 | BY-S05-02 | Bayou | CT-15 | Cycle | 6 | 2025-03-21 | 2025-03-31 | 77243.63 | Complete
VWU-000070 | 2.2 | 2025-03-03 | PR-S19-04 | Prairie | CT-16 | Customer request batch | 2.2 | 2025-03-22 | 2025-04-01 | 28672.69 | Complete
VWU-000071 | 11.7 | 2025-03-01 | PR-S19-05 | Prairie | CT-16 | Cycle | 11.7 | 2025-03-22 | 2025-04-15 | 99419.26 | Complete
VWU-000072 | 2.1 | 2025-03-08 | HB-S20-03 | Harbor | CT-13 | Customer request batch | 2.1 | 2025-03-24 | 2025-04-03 | 33673.06 | Complete
VWU-000073 | 2.8 | 2025-03-06 | BY-S30-01 | Bayou | CT-14 | Cycle | 2.8 | 2025-03-25 | 2025-04-02 | 35631.88 | Complete
VWU-000074 | 2.4 | 2025-03-11 | PR-S20-02 | Prairie | CT-16 | Customer request batch | 2.4 | 2025-03-25 | 2025-04-03 | 38934.78 | Complete
VWU-000075 | 4.8 | 2025-03-14 | CR-S20-04 | Crossroads | CT-13 | Cycle | 4.8 | 2025-03-26 | 2025-04-04 | 38821.72 | Complete
VWU-000076 | 3 | 2025-03-14 | HB-S05-01 | Harbor | CT-13 | Cycle | 3 | 2025-03-26 | 2025-04-04 | 24886.21 | Complete
VWU-000077 | 4.2 | 2025-03-15 | PR-S03-03 | Prairie | CT-16 | Cycle | 4.2 | 2025-03-28 | 2025-04-06 | 29019.38 | Complete
VWU-000078 | 2.7 | 2025-03-09 | BY-S21-04 | Bayou | CT-14 | Customer request batch | 2.7 | 2025-03-29 | 2025-04-01 | 34250.1 | Complete
VWU-000079 | 4.5 | 2025-03-05 | BY-S17-01 | Bayou | CT-15 | Cycle | 4.5 | 2025-03-30 | 2025-04-10 | 56741.63 | Complete
VWU-000080 | 8.8 | 2025-03-23 | BY-S25-02 | Bayou | CT-15 | Cycle | 8.8 | 2025-03-30 | 2025-04-16 | 99538.24 | Complete
VWU-000081 | 5.3 | 2025-03-06 | PR-S03-02 | Prairie | CT-16 | Cycle | 5.3 | 2025-03-31 | 2025-04-10 | 38598.25 | Complete
VWU-000082 | 18 | 2025-03-18 | PR-S08-03 | Prairie | CT-16 | Cycle | 18 | 2025-03-31 | 2025-05-05 | 136581.84 | Complete
VWU-000083 | 11.9 | 2025-03-07 | PR-S08-03 | Prairie | CT-16 | Cycle | 11.9 | 2025-04-02 | 2025-04-21 | 98437.24 | Complete
VWU-000084 | 1 | 2025-03-24 | PR-S04-01 | Prairie | CT-16 | Hot spot | 1 | 2025-04-04 | 2025-04-08 | 18521.95 | Complete
VWU-000085 | 0.6 | 2025-03-17 | PR-S15-01 | Prairie | CT-16 | Cycle | 0.6 | 2025-04-04 | 2025-04-07 | 4328.48 | Complete
VWU-000086 | 15.9 | 2025-03-28 | CR-S04-03 | Crossroads | CT-13 | Cycle | 15.9 | 2025-04-05 | 2025-05-05 | 138747.58 | Complete
VWU-000087 | 2 | 2025-03-12 | CR-S28-03 | Crossroads | CT-13 | Hot spot | 2 | 2025-04-07 | 2025-04-09 | 31683.66 | Complete
VWU-000088 | 1.8 | 2025-03-11 | BY-S08-02 | Bayou | CT-15 | Hot spot | 1.8 | 2025-04-08 | 2025-04-13 | 31086.72 | Complete
VWU-000089 | 4.4 | 2025-03-19 | BY-S18-07 | Bayou | CT-15 | Cycle | 4.4 | 2025-04-08 | 2025-04-19 | 54524.56 | Complete
VWU-000090 | 5.8 | 2025-03-27 | CR-S25-03 | Crossroads | CT-13 | Hot spot | 5.8 | 2025-04-08 | 2025-04-17 | 102006.9 | Complete
VWU-000091 | 2.4 | 2025-03-28 | BY-S08-02 | Bayou | CT-14 | Cycle | 2.4 | 2025-04-09 | 2025-04-16 | 31579.47 | Complete
VWU-000092 | 5.8 | 2025-04-02 | BY-S10-01 | Bayou | CT-14 | Cycle | 5.8 | 2025-04-09 | 2025-04-23 | 59924.7 | Complete
VWU-000093 | 8.1 | 2025-03-17 | HB-S06-01 | Harbor | CT-13 | Cycle | 8.1 | 2025-04-09 | 2025-04-22 | 69435.34 | Complete
VWU-000094 | 4.6 | 2025-03-16 | BY-S26-03 | Bayou | CT-14 | Cycle | 4.6 | 2025-04-10 | 2025-04-19 | 47724.69 | Complete
VWU-000095 | 4.8 | 2025-03-26 | CR-S27-04 | Crossroads | CT-13 | Hot spot | 4.8 | 2025-04-12 | 2025-04-16 | 78498.43 | Complete
VWU-000096 | 7.4 | 2025-03-27 | BY-S04-02 | Bayou | CT-15 | Cycle | 7.4 | 2025-04-13 | 2025-04-27 | 96507.17 | Complete
VWU-000097 | 5.7 | 2025-03-26 | CR-S22-02 | Crossroads | CT-13 | Cycle | 5.7 | 2025-04-13 | 2025-04-25 | 50872.58 | Complete
VWU-000098 | 3.1 | 2025-03-23 | CR-S32-03 | Crossroads | CT-13 | Hot spot | 3.1 | 2025-04-13 | 2025-04-18 | 53299.96 | Complete
VWU-000099 | 10.2 | 2025-03-17 | BY-S05-02 | Bayou | CT-15 | Cycle | 10.2 | 2025-04-14 | 2025-05-06 | 109990.04 | Complete
VWU-000100 | 5 | 2025-03-29 | BY-S16-04 | Bayou | CT-14 | Cycle | 5 | 2025-04-14 | 2025-04-26 | 65124.87 | Complete
VWU-000101 | 3.4 | 2025-03-24 | CR-S13-01 | Crossroads | CT-13 | Hot spot | 3.4 | 2025-04-14 | 2025-04-21 | 47747.15 | Complete
VWU-000102 | 12 | 2025-03-22 | CR-S26-02 | Crossroads | CT-13 | Cycle | 12 | 2025-04-14 | 2025-05-10 | 95773.39 | Complete
VWU-000103 | 11.1 | 2025-03-27 | HB-S09-04 | Harbor | CT-13 | Cycle | 11.1 | 2025-04-15 | 2025-05-11 | 105550.44 | Complete
VWU-000104 | 6.2 | 2025-04-08 | PR-S04-01 | Prairie | CT-16 | Cycle | 6.2 | 2025-04-15 | 2025-04-29 | 43291.37 | Complete
VWU-000105 | 6 | 2025-03-27 | BY-S02-01 | Bayou | CT-14 | Cycle | 6 | 2025-04-16 | 2025-05-01 | 69528.29 | Complete
VWU-000106 | 5.2 | 2025-03-23 | BY-S17-02 | Bayou | CT-14 | Cycle | 5.2 | 2025-04-16 | 2025-04-29 | 59442.13 | Complete
VWU-000107 | 1.7 | 2025-03-29 | PR-S03-01 | Prairie | CT-16 | Hot spot | 1.7 | 2025-04-18 | 2025-04-22 | 28939.46 | Complete
VWU-000108 | 20.5 | 2025-04-04 | PR-S06-01 | Prairie | CT-16 | Cycle | 20.5 | 2025-04-18 | 2025-06-03 | 170480.83 | Complete
VWU-000109 | 8.9 | 2025-04-09 | PR-S06-01 | Prairie | CT-16 | Cycle | 8.9 | 2025-04-19 | 2025-05-10 | 68757.41 | Complete
VWU-000110 | 15.2 | 2025-03-26 | PR-S13-06 | Prairie | CT-16 | Cycle | 15.2 | 2025-04-19 | 2025-05-16 | 123745.22 | Complete
VWU-000111 | 1.6 | 2025-04-11 | BY-S13-05 | Bayou | CT-15 | Customer request batch | 1.6 | 2025-04-20 | 2025-04-27 | 23973.52 | Complete
VWU-000112 | 14.4 | 2025-03-26 | PR-S06-01 | Prairie | CT-16 | Cycle | 14.4 | 2025-04-22 | 2025-05-17 | 94945.6 | Complete
VWU-000113 | 10.1 | 2025-04-09 | HB-S05-06 | Harbor | CT-13 | Cycle | 10.1 | 2025-04-24 | 2025-05-10 | 102948.45 | Complete
VWU-000114 | 4.7 | 2025-04-11 | CR-S13-05 | Crossroads | CT-13 | Hot spot | 4.7 | 2025-04-25 | 2025-04-30 | 75250.06 | Complete
VWU-000115 | 11 | 2025-03-31 | PR-S06-03 | Prairie | CT-16 | Cycle | 11 | 2025-04-25 | 2025-05-13 | 90127.1 | Complete
VWU-000116 | 11.8 | 2025-04-06 | BY-S15-03 | Bayou | CT-14 | Cycle | 11.8 | 2025-04-26 | 2025-05-19 | 146420.15 | Complete
VWU-000117 | 4.7 | 2025-04-06 | HB-S09-03 | Harbor | CT-13 | Cycle | 4.7 | 2025-04-27 | 2025-05-09 | 44824.65 | Complete
VWU-000118 | 7.1 | 2025-04-14 | BY-S02-01 | Bayou | CT-15 | Cycle | 7.1 | 2025-04-28 | 2025-05-12 | 84577.77 | Complete
VWU-000119 | 14.1 | 2025-04-15 | HB-S20-04 | Harbor | CT-13 | Cycle | 14.1 | 2025-04-29 | 2025-05-27 | 143443.12 | Complete
VWU-000120 | 10 | 2025-04-07 | PR-S19-03 | Prairie | CT-16 | Cycle | 10 | 2025-04-29 | 2025-05-16 | 71045.06 | Complete
VWU-000121 | 11.3 | 2025-04-22 | BY-S27-01 | Bayou | CT-14 | Cycle | 11.3 | 2025-04-30 | 2025-05-20 | 122226.61 | Complete
VWU-000122 | 12.3 | 2025-04-22 | BY-S08-02 | Bayou | CT-14 | Cycle | 12.3 | 2025-05-01 | 2025-05-23 | 134012.83 | Complete
VWU-000123 | 5.4 | 2025-04-25 | BY-S08-03 | Bayou | CT-14 | Hot spot | 5.4 | 2025-05-02 | 2025-05-11 | 101700.84 | Complete
VWU-000124 | 10.2 | 2025-04-14 | PR-S03-04 | Prairie | CT-16 | Cycle | 10.2 | 2025-05-02 | 2025-05-19 | 64690.1 | Complete
VWU-000125 | 9.4 | 2025-04-09 | BY-S17-01 | Bayou | CT-14 | Cycle | 9.4 | 2025-05-03 | 2025-05-23 | 115741.42 | Complete
VWU-000126 | 6 | 2025-04-16 | BY-S25-02 | Bayou | CT-14 | Hot spot | 6 | 2025-05-04 | 2025-05-10 | 100379.23 | Complete
VWU-000127 | 10.1 | 2025-04-27 | HB-S10-01 | Harbor | CT-13 | Cycle | 10.1 | 2025-05-04 | 2025-05-22 | 86626.59 | Complete
VWU-000128 | 2.6 | 2025-04-21 | BY-S14-02 | Bayou | CT-14 | Hot spot | 2.6 | 2025-05-05 | 2025-05-07 | 40822.59 | Complete
VWU-000129 | 10 | 2025-04-25 | CR-S21-03 | Crossroads | CT-13 | Cycle | 10 | 2025-05-05 | 2025-05-27 | 102030.29 | Complete
VWU-000130 | 2.1 | 2025-04-16 | CR-S14-04 | Crossroads | CT-13 | Customer request batch | 2.1 | 2025-05-07 | 2025-05-12 | 34251.5 | Complete
VWU-000131 | 9.6 | 2025-04-24 | HB-S07-01 | Harbor | CT-13 | Cycle | 9.6 | 2025-05-07 | 2025-05-23 | 82867.82 | Complete
VWU-000132 | 4.4 | 2025-04-21 | PR-S04-02 | Prairie | CT-16 | Cycle | 4.4 | 2025-05-07 | 2025-05-15 | 29317.16 | Complete
VWU-000133 | 10.4 | 2025-04-15 | CR-S20-02 | Crossroads | CT-13 | Cycle | 10.4 | 2025-05-10 | 2025-05-27 | 103594.31 | Complete
VWU-000134 | 3.9 | 2025-04-27 | HB-S09-04 | Harbor | CT-13 | Cycle | 3.9 | 2025-05-10 | 2025-05-20 | 38477.62 | Complete
VWU-000135 | 11.9 | 2025-04-12 | PR-S20-01 | Prairie | CT-16 | Cycle | 11.9 | 2025-05-10 | 2025-05-28 | 77282.23 | Complete
VWU-000136 | 10.4 | 2025-04-24 | HB-S06-01 | Harbor | CT-13 | Cycle | 10.4 | 2025-05-11 | 2025-05-30 | 84164.69 | Complete
VWU-000137 | 14.7 | 2025-04-29 | HB-S11-01 | Harbor | CT-13 | Cycle | 14.7 | 2025-05-11 | 2025-06-07 | 122657.41 | Complete
VWU-000138 | 6.2 | 2025-04-27 | PR-S19-03 | Prairie | CT-16 | Cycle | 6.2 | 2025-05-12 | 2025-05-26 | 50344.36 | Complete
VWU-000139 | 2.6 | 2025-04-23 | CR-S13-04 | Crossroads | CT-13 | Hot spot | 2.6 | 2025-05-13 | 2025-05-19 | 44079.26 | Complete
VWU-000140 | 3.8 | 2025-05-01 | PR-S19-01 | Prairie | CT-16 | Hot spot | 3.8 | 2025-05-13 | 2025-05-20 | 59521.03 | Complete
VWU-000141 | 3 | 2025-05-01 | BY-S20-02 | Bayou | CT-15 | Customer request batch | 3 | 2025-05-14 | 2025-05-17 | 36991.6 | Complete
VWU-000142 | 5 | 2025-05-01 | PR-S08-03 | Prairie | CT-16 | Cycle | 5 | 2025-05-14 | 2025-05-26 | 37527.55 | Complete
VWU-000143 | 1 | 2025-04-18 | BY-S15-03 | Bayou | CT-14 | Customer request batch | 1 | 2025-05-16 | 2025-05-25 | 16026.29 | Complete
VWU-000144 | 4.6 | 2025-05-10 | BY-S03-03 | Bayou | CT-15 | Cycle | 4.6 | 2025-05-17 | 2025-05-29 | 54960.85 | Complete
VWU-000145 | 7.7 | 2025-04-24 | HB-S02-02 | Harbor | CT-13 | Cycle | 7.7 | 2025-05-18 | 2025-05-30 | 74076.61 | Complete
VWU-000146 | 15.3 | 2025-05-07 | PR-S03-04 | Prairie | CT-16 | Cycle | 15.3 | 2025-05-18 | 2025-06-14 | 99619.96 | Complete
VWU-000147 | 12.7 | 2025-05-06 | PR-S13-06 | Prairie | CT-16 | Cycle | 12.7 | 2025-05-18 | 2025-06-06 | 89181.47 | Complete
VWU-000148 | 0.1 | 2025-04-22 | BY-S16-02 | Bayou | CT-15 | Cycle | 0.1 | 2025-05-19 | 2025-05-22 | 1216.98 | Complete
VWU-000149 | 5.4 | 2025-04-24 | HB-S15-02 | Harbor | CT-13 | Cycle | 5.4 | 2025-05-20 | 2025-06-03 | 52959.66 | Complete
VWU-000150 | 1.1 | 2025-05-16 | CR-S25-03 | Crossroads | CT-13 | Hot spot | 1.1 | 2025-05-24 | 2025-06-01 | 18685.31 | Complete
VWU-000151 | 7 | 2025-05-13 | HB-S02-02 | Harbor | CT-13 | Cycle | 7 | 2025-05-24 | 2025-06-04 | 70719.15 | Complete
VWU-000152 | 4.6 | 2025-05-07 | BY-S09-02 | Bayou | CT-15 | Cycle | 4.6 | 2025-05-26 | 2025-06-06 | 56646.12 | Complete
VWU-000153 | 17.2 | 2025-05-07 | BY-S16-02 | Bayou | CT-15 | Cycle | 17.2 | 2025-05-26 | 2025-06-26 | 173135.56 | Complete
VWU-000154 | 7.4 | 2025-05-04 | HB-S05-01 | Harbor | CT-13 | Cycle | 7.4 | 2025-05-26 | 2025-06-07 | 73376.56 | Complete
VWU-000155 | 15.8 | 2025-05-21 | HB-S09-03 | Harbor | CT-13 | Cycle | 15.8 | 2025-05-28 | 2025-06-26 | 151597.77 | Complete
VWU-000156 | 1.6 | 2025-05-14 | BY-S19-04 | Bayou | CT-14 | Hot spot | 1.6 | 2025-05-29 | 2025-06-07 | 23147.59 | Complete
VWU-000157 | 0.6 | 2025-05-13 | CR-S07-05 | Crossroads | CT-13 | Cycle | 0.6 | 2025-05-29 | 2025-06-01 | 4879.98 | Complete
VWU-000158 | 6.8 | 2025-05-08 | HB-S09-03 | Harbor | CT-13 | Cycle | 6.8 | 2025-05-31 | 2025-06-17 | 71740.27 | Complete
VWU-000159 | 3.2 | 2025-05-12 | HB-S18-02 | Harbor | CT-13 | Cycle | 3.2 | 2025-05-31 | 2025-06-07 | 31612.34 | Complete
VWU-000160 | 5.4 | 2025-05-18 | BY-S15-06 | Bayou | CT-15 | Hot spot | 5.4 | 2025-06-01 | 2025-06-07 | 87869.69 | Complete
VWU-000161 | 1.5 | 2025-05-05 | PR-S11-01 | Prairie | CT-16 | Customer request batch | 1.5 | 2025-06-02 | 2025-06-08 | 23593.86 | Complete
VWU-000162 | 12.9 | 2025-05-22 | BY-S19-02 | Bayou | CT-15 | Cycle | 12.9 | 2025-06-03 | 2025-07-02 | 156164.62 | Complete
VWU-000163 | 5.4 | 2025-05-29 | BY-S26-04 | Bayou | CT-15 | Cycle | 5.4 | 2025-06-05 | 2025-06-14 | 57135.13 | Complete
VWU-000164 | 21.6 | 2025-05-20 | HB-S09-03 | Harbor | CT-13 | Cycle | 21.6 | 2025-06-06 | 2025-07-21 | 228438.92 | Complete
VWU-000165 | 16.9 | 2025-05-31 | BY-S18-02 | Bayou | CT-14 | Cycle | 16.9 | 2025-06-07 | 2025-07-12 | 176524.69 | Complete
VWU-000166 | 8.8 | 2025-05-29 | PR-S13-05 | Prairie | CT-16 | Cycle | 8.8 | 2025-06-07 | 2025-06-21 | 70517.94 | Complete
VWU-000167 | 10.1 | 2025-05-31 | BY-S15-03 | Bayou | CT-14 | Cycle | 10.1 | 2025-06-08 | 2025-06-23 | 123683.99 | Complete
VWU-000168 | 3.2 | 2025-05-14 | BY-S03-03 | Bayou | CT-15 | Cycle | 3.2 | 2025-06-10 | 2025-06-17 | 34655.31 | Complete
VWU-000169 | 1.7 | 2025-06-03 | CR-S02-05 | Crossroads | CT-13 | Customer request batch | 1.7 | 2025-06-10 | 2025-06-17 | 25170.67 | Complete
VWU-000170 | 1.2 | 2025-05-23 | CR-S32-03 | Crossroads | CT-13 | Cycle | 1.2 | 2025-06-10 | 2025-06-15 | 12470.59 | Complete
VWU-000171 | 4.9 | 2025-05-21 | PR-S03-03 | Prairie | CT-16 | Cycle | 4.9 | 2025-06-10 | 2025-06-22 | 38615.15 | Complete
VWU-000172 | 12.3 | 2025-06-04 | BY-S09-05 | Bayou | CT-15 | Cycle | 12.3 | 2025-06-11 | 2025-07-10 | 133269.73 | Complete
VWU-000173 | 6.7 | 2025-05-22 | PR-S03-04 | Prairie | CT-16 | Post-storm | 6.7 | 2025-06-12 | 2025-06-24 | 129761.34 | Complete
VWU-000174 | 7.1 | 2025-05-20 | BY-S08-03 | Bayou | CT-15 | Post-storm | 7.1 | 2025-06-13 | 2025-06-21 | 132267.07 | Complete
VWU-000175 | 3.1 | 2025-05-23 | PR-S18-01 | Prairie | CT-16 | Hot spot | 3.1 | 2025-06-13 | 2025-06-18 | 56610.73 | Complete
VWU-000176 | 8.1 | 2025-05-28 | PR-S02-03 | Prairie | CT-16 | Cycle | 8.1 | 2025-06-14 | 2025-07-03 | 58640.65 | Complete
VWU-000177 | 3.6 | 2025-05-21 | BY-S05-02 | Bayou | CT-14 | Post-storm | 3.6 | 2025-06-15 | 2025-06-27 | 86075.51 | Complete
VWU-000178 | 6 | 2025-06-08 | BY-S19-01 | Bayou | CT-15 | Post-storm | 6 | 2025-06-15 | 2025-06-23 | 140076.65 | Complete
VWU-000179 | 6.1 | 2025-05-24 | BY-S21-01 | Bayou | CT-15 | Post-storm | 6.1 | 2025-06-15 | 2025-06-22 | 121472.76 | Complete
VWU-000180 | 7.1 | 2025-05-24 | BY-S21-01 | Bayou | CT-15 | Post-storm | 7.1 | 2025-06-15 | 2025-06-30 | 174070.92 | Complete
VWU-000181 | 7 | 2025-05-26 | BY-S23-02 | Bayou | CT-15 | Post-storm | 7 | 2025-06-15 | 2025-06-26 | 146630.54 | Complete
VWU-000182 | 5.4 | 2025-06-03 | BY-S04-01 | Bayou | CT-14 | Post-storm | 5.4 | 2025-06-16 | 2025-06-21 | 125367.93 | Complete
VWU-000183 | 2.2 | 2025-05-26 | BY-S06-03 | Bayou | CT-15 | Customer request batch | 2.2 | 2025-06-16 | 2025-06-22 | 31629.46 | Complete
VWU-000184 | 7.6 | 2025-05-27 | PR-S10-03 | Prairie | CT-16 | Post-storm | 7.6 | 2025-06-17 | 2025-06-28 | 164046.83 | Complete
VWU-000185 | 4 | 2025-06-04 | BY-S06-02 | Bayou | CT-15 | Hot spot | 4 | 2025-06-18 | 2025-06-21 | 67095.54 | Complete
VWU-000186 | 4.6 | 2025-06-01 | BY-S18-03 | Bayou | CT-14 | Cycle | 4.6 | 2025-06-18 | 2025-06-27 | 49200.76 | Complete
VWU-000187 | 2.1 | 2025-06-05 | CR-S27-04 | Crossroads | CT-13 | Hot spot | 2.1 | 2025-06-19 | 2025-06-27 | 35032.12 | Complete
VWU-000188 | 1.1 | 2025-06-05 | BY-S13-03 | Bayou | CT-14 | Post-storm | 1.1 | 2025-06-20 | 2025-07-04 | 21752.71 | Complete
VWU-000189 | 6.1 | 2025-05-24 | BY-S18-04 | Bayou | CT-15 | Post-storm | 6.1 | 2025-06-20 | 2025-07-01 | 150156.51 | Complete
VWU-000190 | 8 | 2025-06-13 | CR-S02-03 | Crossroads | CT-13 | Cycle | 8 | 2025-06-20 | 2025-07-04 | 82310.5 | Complete
VWU-000191 | 5.3 | 2025-05-27 | CR-S25-06 | Crossroads | CT-13 | Hot spot | 5.3 | 2025-06-20 | 2025-06-25 | 89296.34 | Complete
VWU-000192 | 8 | 2025-05-25 | PR-S06-03 | Prairie | CT-16 | Post-storm | 8 | 2025-06-20 | 2025-07-04 | 152597.04 | Complete
VWU-000193 | 10.4 | 2025-06-07 | PR-S08-03 | Prairie | CT-16 | Cycle | 10.4 | 2025-06-21 | 2025-07-11 | 80122.64 | Complete
VWU-000194 | 5.9 | 2025-05-25 | BY-S07-02 | Bayou | CT-14 | Post-storm | 5.9 | 2025-06-22 | 2025-07-07 | 142741.63 | Complete
VWU-000195 | 7.4 | 2025-06-03 | CR-S13-06 | Crossroads | CT-13 | Cycle | 7.4 | 2025-06-22 | 2025-07-09 | 61809.15 | Complete
VWU-000196 | 9.1 | 2025-06-11 | CR-S32-03 | Crossroads | CT-13 | Cycle | 9.1 | 2025-06-23 | 2025-07-15 | 88761.13 | Complete
VWU-000197 | 2.4 | 2025-05-29 | PR-S01-03 | Prairie | CT-16 | Customer request batch | 2.4 | 2025-06-23 | 2025-07-02 | 36347.15 | Complete
VWU-000198 | 3.6 | 2025-06-05 | BY-S07-01 | Bayou | CT-15 | Post-storm | 3.6 | 2025-06-24 | 2025-07-01 | 78091.8 | Complete
VWU-000199 | 5.2 | 2025-06-05 | CR-S07-02 | Crossroads | CT-13 | Hot spot | 5.2 | 2025-06-25 | 2025-07-02 | 96936.24 | Complete
VWU-000200 | 1.2 | 2025-06-02 | CR-S08-04 | Crossroads | CT-13 | Customer request batch | 1.2 | 2025-06-26 | 2025-07-04 | 17784.72 | Complete
VWU-000201 | 3.6 | 2025-06-10 | PR-S07-06 | Prairie | CT-16 | Post-storm | 3.6 | 2025-06-26 | 2025-07-07 | 72766.75 | Complete
VWU-000202 | 4.3 | 2025-06-14 | PR-S15-05 | Prairie | CT-16 | Post-storm | 4.3 | 2025-06-26 | 2025-06-30 | 80808.25 | Complete
VWU-000203 | 7.3 | 2025-05-31 | PR-S10-02 | Prairie | CT-16 | Post-storm | 7.3 | 2025-06-27 | 2025-07-01 | 166782.86 | Complete
VWU-000204 | 6.5 | 2025-06-08 | BY-S05-03 | Bayou | CT-15 | Post-storm | 6.5 | 2025-06-28 | 2025-07-06 | 159928.6 | Complete
VWU-000205 | 0.8 | 2025-06-10 | BY-S25-02 | Bayou | CT-15 | Cycle | 0.8 | 2025-06-28 | 2025-07-02 | 10157.19 | Complete
VWU-000206 | 9 | 2025-06-15 | CR-S08-01 | Crossroads | CT-13 | Cycle | 9 | 2025-06-28 | 2025-07-20 | 73984.13 | Complete
VWU-000207 | 5.4 | 2025-06-12 | BY-S23-05 | Bayou | CT-14 | Post-storm | 5.4 | 2025-06-29 | 2025-07-04 | 102003.5 | Complete
VWU-000208 | 0.7 | 2025-06-13 | CR-S14-04 | Crossroads | CT-13 | Customer request batch | 0.7 | 2025-06-29 | 2025-07-03 | 9811.46 | Complete
VWU-000209 | 8.5 | 2025-06-11 | HB-S20-01 | Harbor | CT-13 | Cycle | 8.5 | 2025-06-29 | 2025-07-17 | 86842.2 | Complete
VWU-000210 | 6 | 2025-06-01 | PR-S13-02 | Prairie | CT-16 | Post-storm | 6 | 2025-06-29 | 2025-07-04 | 144359 | Complete
VWU-000211 | 4 | 2025-06-22 | PR-S16-01 | Prairie | CT-16 | Post-storm | 4 | 2025-06-29 | 2025-07-09 | 93709.4 | Complete
VWU-000212 | 7.5 | 2025-06-21 | BY-S21-02 | Bayou | CT-14 | Post-storm | 7.5 | 2025-06-30 | 2025-07-07 | 175683.49 | Complete
VWU-000213 | 15.4 | 2025-06-16 | PR-S04-01 | Prairie | CT-16 | Cycle | 15.4 | 2025-06-30 | 2025-07-22 | 104552.67 | Complete
VWU-000214 | 7 | 2025-06-16 | PR-S08-01 | Prairie | CT-16 | Post-storm | 7 | 2025-06-30 | 2025-07-15 | 171809.77 | Complete
VWU-000215 | 5.7 | 2025-06-16 | HB-S10-02 | Harbor | CT-13 | Cycle | 5.7 | 2025-07-01 | 2025-07-10 | 53229.91 | Complete
VWU-000216 | 3.3 | 2025-06-14 | BY-S12-04 | Bayou | CT-15 | Post-storm | 3.3 | 2025-07-02 | 2025-07-08 | 74810.19 | Complete
VWU-000217 | 2.6 | 2025-06-14 | BY-S27-05 | Bayou | CT-14 | Post-storm | 2.6 | 2025-07-02 | 2025-07-12 | 59743.99 | Complete
VWU-000218 | 10.1 | 2025-06-10 | PR-S15-01 | Prairie | CT-16 | Cycle | 10.1 | 2025-07-03 | 2025-07-24 | 72520.65 | Complete
VWU-000219 | 4.1 | 2025-06-19 | PR-S07-04 | Prairie | CT-16 | Hot spot | 4.1 | 2025-07-05 | 2025-07-08 | 72515.19 | Complete
VWU-000220 | 1.8 | 2025-06-12 | CR-S11-02 | Crossroads | CT-13 | Hot spot | 1.8 | 2025-07-06 | 2025-07-08 | 34098.04 | Complete
VWU-000221 | 2.3 | 2025-06-15 | BY-S18-03 | Bayou | CT-15 | Customer request batch | 2.3 | 2025-07-07 | 2025-07-14 | 35793.73 | Complete
VWU-000222 | 0.9 | 2025-06-28 | CR-S28-03 | Crossroads | CT-13 | Customer request batch | 0.9 | 2025-07-09 | 2025-07-15 | 14685.59 | Complete
VWU-000223 | 4.6 | 2025-06-26 | BY-S22-02 | Bayou | CT-15 | Hot spot | 4.6 | 2025-07-10 | 2025-07-13 | 71750.57 | Complete
VWU-000224 | 16.5 | 2025-06-30 | PR-S19-05 | Prairie | CT-16 | Cycle | 16.5 | 2025-07-14 | 2025-08-14 | 112892.22 | Complete
VWU-000225 | 11.9 | 2025-06-19 | CR-S02-03 | Crossroads | CT-13 | Cycle | 11.9 | 2025-07-15 | 2025-08-02 | 99696.52 | Complete
VWU-000226 | 7.7 | 2025-06-21 | CR-S24-03 | Crossroads | CT-13 | Cycle | 7.7 | 2025-07-15 | 2025-08-02 | 76678.14 | Complete
VWU-000227 | 16 | 2025-06-19 | BY-S30-02 | Bayou | CT-14 | Cycle | 16 | 2025-07-16 | 2025-08-10 | 161167.68 | Complete
VWU-000228 | 5.8 | 2025-07-05 | CR-S15-02 | Crossroads | CT-13 | Hot spot | 5.8 | 2025-07-16 | 2025-07-24 | 88127.32 | Complete
VWU-000229 | 9.7 | 2025-06-28 | BY-S03-03 | Bayou | CT-15 | Cycle | 9.7 | 2025-07-18 | 2025-08-09 | 112146.85 | Complete
VWU-000230 | 11.6 | 2025-06-25 | CR-S07-05 | Crossroads | CT-13 | Cycle | 11.6 | 2025-07-20 | 2025-08-05 | 103481.68 | Complete
VWU-000231 | 1.2 | 2025-07-13 | HB-S02-01 | Harbor | CT-13 | Hot spot | 1.2 | 2025-07-20 | 2025-07-25 | 19126.15 | Complete
VWU-000232 | 7.5 | 2025-07-08 | HB-S04-02 | Harbor | CT-13 | Cycle | 7.5 | 2025-07-20 | 2025-08-01 | 66343.56 | Complete
VWU-000233 | 2.1 | 2025-07-06 | HB-S16-04 | Harbor | CT-13 | Customer request batch | 2.1 | 2025-07-20 | 2025-07-29 | 26174.43 | Complete
VWU-000234 | 18.1 | 2025-07-03 | HB-S12-01 | Harbor | CT-13 | Cycle | 18.1 | 2025-07-21 | 2025-08-15 | 154280.73 | Complete
VWU-000235 | 5.8 | 2025-07-12 | PR-S13-02 | Prairie | CT-16 | Hot spot | 5.8 | 2025-07-21 | 2025-07-24 | 101921.92 | Complete
VWU-000236 | 6 | 2025-06-24 | BY-S05-02 | Bayou | CT-14 | Cycle | 6 | 2025-07-22 | 2025-08-05 | 70813.22 | Complete
VWU-000237 | 11.4 | 2025-07-10 | CR-S28-04 | Crossroads | CT-13 | Cycle | 11.4 | 2025-07-22 | 2025-08-15 | 88331.28 | Complete
VWU-000238 | 13.1 | 2025-07-11 | HB-S11-01 | Harbor | CT-13 | Cycle | 13.1 | 2025-07-22 | 2025-08-10 | 114642.54 | Complete
VWU-000239 | 13 | 2025-07-11 | PR-S09-02 | Prairie | CT-16 | Cycle | 13 | 2025-07-22 | 2025-08-19 | 96927.83 | Complete
VWU-000240 | 12.4 | 2025-07-09 | PR-S06-01 | Prairie | CT-16 | Cycle | 12.4 | 2025-07-23 | 2025-08-21 | 85448.49 | Complete
VWU-000241 | 6 | 2025-07-08 | PR-S13-05 | Prairie | CT-16 | Cycle | 6 | 2025-07-25 | 2025-08-09 | 49887.35 | Complete
VWU-000242 | 17.3 | 2025-07-06 | BY-S30-01 | Bayou | CT-14 | Cycle | 17.3 | 2025-07-26 | 2025-08-28 | 213807.28 | Complete
VWU-000243 | 5.9 | 2025-07-05 | CR-S07-02 | Crossroads | CT-13 | Hot spot | 5.9 | 2025-07-26 | 2025-08-04 | 109892.78 | Complete
VWU-000244 | 7.3 | 2025-07-17 | PR-S19-03 | Prairie | CT-16 | Cycle | 7.3 | 2025-07-29 | 2025-08-12 | 51891.45 | Complete
VWU-000245 | 3.3 | 2025-07-13 | PR-S16-03 | Prairie | CT-16 | Hot spot | 3.3 | 2025-07-30 | 2025-08-04 | 56487.73 | Complete
VWU-000246 | 15.9 | 2025-07-15 | BY-S09-02 | Bayou | CT-14 | Cycle | 15.9 | 2025-08-01 | 2025-09-06 | 194489.33 | Complete
VWU-000247 | 5.3 | 2025-07-16 | BY-S25-05 | Bayou | CT-15 | Hot spot | 5.3 | 2025-08-01 | 2025-08-10 | 74562.24 | Complete
VWU-000248 | 1.8 | 2025-07-19 | PR-S07-04 | Prairie | CT-16 | Customer request batch | 1.8 | 2025-08-05 | 2025-08-14 | 22829.74 | Complete
VWU-000249 | 9.2 | 2025-07-14 | CR-S21-01 | Crossroads | CT-13 | Cycle | 9.2 | 2025-08-09 | 2025-08-25 | 88595.67 | Complete
VWU-000250 | 9.2 | 2025-07-13 | CR-S28-02 | Crossroads | CT-13 | Cycle | 9.2 | 2025-08-09 | 2025-08-23 | 88480.3 | Complete
VWU-000251 | 3.8 | 2025-07-19 | BY-S28-03 | Bayou | CT-14 | Hot spot | 3.8 | 2025-08-13 | 2025-08-16 | 64886.37 | Complete
VWU-000252 | 7 | 2025-08-04 | CR-S19-04 | Crossroads | CT-13 | Cycle | 7 | 2025-08-14 | 2025-08-29 | 64963.6 | Complete
VWU-000253 | 13.1 | 2025-08-02 | PR-S03-03 | Prairie | CT-16 | Cycle | 13.1 | 2025-08-15 | 2025-09-06 | 96806.13 | Complete
VWU-000254 | 7.6 | 2025-07-24 | BY-S08-03 | Bayou | CT-14 | Cycle | 7.6 | 2025-08-16 | 2025-08-30 | 97715.6 | Complete
VWU-000255 | 6.9 | 2025-08-02 | CR-S02-01 | Crossroads | CT-13 | Cycle | 6.9 | 2025-08-16 | 2025-08-28 | 57293.23 | Complete
VWU-000256 | 10.4 | 2025-07-26 | PR-S03-02 | Prairie | CT-16 | Cycle | 10.4 | 2025-08-16 | 2025-09-01 | 82355.23 | Complete
VWU-000257 | 7.8 | 2025-08-03 | BY-S04-01 | Bayou | CT-14 | Cycle | 7.8 | 2025-08-17 | 2025-08-30 | 91638.61 | Complete
VWU-000258 | 20.3 | 2025-08-01 | HB-S10-02 | Harbor | CT-13 | Cycle | 20.3 | 2025-08-17 | 2025-09-16 | 211474.85 | Complete
VWU-000259 | 6.4 | 2025-07-25 | PR-S06-01 | Prairie | CT-16 | Cycle | 6.4 | 2025-08-17 | 2025-08-30 | 41146.09 | Complete
VWU-000260 | 3 | 2025-08-08 | CR-S12-03 | Crossroads | CT-13 | Cycle | 3 | 2025-08-19 | 2025-08-27 | 25087.93 | Complete
VWU-000261 | 3.3 | 2025-08-09 | CR-S18-02 | Crossroads | CT-13 | Cycle | 3.3 | 2025-08-19 | 2025-08-27 | 33847.43 | Complete
VWU-000262 | 3.6 | 2025-07-31 | HB-S06-05 | Harbor | CT-13 | Hot spot | 3.6 | 2025-08-19 | 2025-08-23 | 51679.71 | Complete
VWU-000263 | 2.1 | 2025-08-04 | HB-S20-05 | Harbor | CT-13 | Customer request batch | 2.1 | 2025-08-19 | 2025-08-21 | 34219.97 | Complete
VWU-000264 | 8 | 2025-07-29 | CR-S13-06 | Crossroads | CT-13 | Cycle | 8 | 2025-08-21 | 2025-09-09 | 65856.53 | Complete
VWU-000265 | 6.2 | 2025-07-28 | BY-S22-02 | Bayou | CT-15 | Cycle | 6.2 | 2025-08-22 | 2025-09-03 | 72331.21 | Complete
VWU-000266 | 5.6 | 2025-08-04 | CR-S11-02 | Crossroads | CT-13 | Cycle | 5.6 | 2025-08-22 | 2025-09-06 | 49790.02 | Complete
VWU-000267 | 3.9 | 2025-08-06 | PR-S15-03 | Prairie | CT-16 | Hot spot | 3.9 | 2025-08-23 | 2025-08-30 | 56026.69 | Complete
VWU-000268 | 13.1 | 2025-08-08 | BY-S18-03 | Bayou | CT-15 | Cycle | 13.1 | 2025-08-26 | 2025-09-16 | 131168.39 | Complete
VWU-000269 | 3.7 | 2025-08-06 | BY-S29-02 | Bayou | CT-14 | Hot spot | 3.7 | 2025-08-26 | 2025-09-04 | 58534.78 | Complete
VWU-000270 | 11 | 2025-08-07 | PR-S04-01 | Prairie | CT-16 | Cycle | 11 | 2025-08-27 | 2025-09-12 | 84001.5 | Complete
VWU-000271 | 5.5 | 2025-08-14 | CR-S24-03 | Crossroads | CT-13 | Cycle | 5.5 | 2025-08-29 | 2025-09-11 | 50812.74 | Complete
VWU-000272 | 3.9 | 2025-08-17 | PR-S19-02 | Prairie | CT-16 | Hot spot | 3.9 | 2025-08-30 | 2025-09-04 | 63404.72 | Complete
VWU-000273 | 21.4 | 2025-08-05 | CR-S21-03 | Crossroads | CT-13 | Cycle | 21.4 | 2025-08-31 | 2025-10-16 | 219776.51 | Complete
VWU-000274 | 2.5 | 2025-08-12 | BY-S02-01 | Bayou | CT-14 | Customer request batch | 2.5 | 2025-09-01 | 2025-09-13 | 37984.39 | Complete
VWU-000275 | 10.5 | 2025-08-24 | BY-S17-02 | Bayou | CT-14 | Cycle | 10.5 | 2025-09-01 | 2025-09-18 | 118855.53 | Complete
VWU-000276 | 8.9 | 2025-08-26 | HB-S11-01 | Harbor | CT-13 | Cycle | 8.9 | 2025-09-02 | 2025-09-16 | 74128.66 | Complete
VWU-000277 | 5.4 | 2025-08-20 | CR-S07-06 | Crossroads | CT-13 | Hot spot | 5.4 | 2025-09-03 | 2025-09-07 | 77063.15 | Complete
VWU-000278 | 4.5 | 2025-08-27 | PR-S03-04 | Prairie | CT-16 | Cycle | 4.5 | 2025-09-04 | 2025-09-14 | 38200.67 | Complete
VWU-000279 | 6.5 | 2025-08-12 | BY-S04-01 | Bayou | CT-15 | Cycle | 6.5 | 2025-09-05 | 2025-09-19 | 80175.64 | Complete
VWU-000280 | 3.6 | 2025-08-14 | BY-S15-02 | Bayou | CT-14 | Hot spot | 3.6 | 2025-09-05 | 2025-09-09 | 51308.26 | Complete
VWU-000281 | 5.1 | 2025-08-20 | CR-S04-06 | Crossroads | CT-13 | Hot spot | 5.1 | 2025-09-05 | 2025-09-12 | 91076.79 | Complete
VWU-000282 | 8.9 | 2025-08-21 | BY-S11-02 | Bayou | CT-14 | Cycle | 8.9 | 2025-09-06 | 2025-09-23 | 118583.38 | Complete
VWU-000283 | 5.9 | 2025-08-14 | CR-S13-06 | Crossroads | CT-13 | Hot spot | 5.9 | 2025-09-06 | 2025-09-13 | 93463.41 | Complete
VWU-000284 | 2.8 | 2025-08-23 | HB-S04-02 | Harbor | CT-13 | Cycle | 2.8 | 2025-09-07 | 2025-09-15 | 26146.61 | Complete
VWU-000285 | 8 | 2025-08-24 | CR-S22-02 | Crossroads | CT-13 | Cycle | 8 | 2025-09-08 | 2025-09-27 | 66134.58 | Complete
VWU-000286 | 1.2 | 2025-08-29 | BY-S27-05 | Bayou | CT-15 | Customer request batch | 1.2 | 2025-09-09 | 2025-09-20 | 15634.29 | Complete
VWU-000287 | 9.2 | 2025-08-19 | BY-S18-07 | Bayou | CT-15 | Cycle | 9.2 | 2025-09-10 | 2025-09-24 | 119079.67 | Complete
VWU-000288 | 0.9 | 2025-08-13 | CR-S14-03 | Crossroads | CT-13 | Cycle | 0.9 | 2025-09-10 | 2025-09-14 | 8460.3 | Complete
VWU-000289 | 2.1 | 2025-09-02 | BY-S09-05 | Bayou | CT-15 | Hot spot | 2.1 | 2025-09-12 | 2025-09-15 | 33202.59 | Complete
VWU-000290 | 8.3 | 2025-08-19 | BY-S03-03 | Bayou | CT-15 | Cycle | 8.3 | 2025-09-13 | 2025-09-30 | 90885.97 | Complete
VWU-000291 | 8.2 | 2025-08-24 | BY-S19-02 | Bayou | CT-14 | Cycle | 8.2 | 2025-09-13 | 2025-09-28 | 96670.59 | Complete
VWU-000292 | 2.7 | 2025-09-02 | CR-S22-02 | Crossroads | CT-13 | Cycle | 2.7 | 2025-09-13 | 2025-09-20 | 22602.18 | Complete
VWU-000293 | 15 | 2025-09-03 | HB-S02-02 | Harbor | CT-13 | Cycle | 15 | 2025-09-13 | 2025-10-18 | 128468.32 | Complete
VWU-000294 | 2.1 | 2025-08-20 | BY-S09-05 | Bayou | CT-15 | Cycle | 2.1 | 2025-09-16 | 2025-09-23 | 23823.05 | Complete
VWU-000295 | 9.5 | 2025-08-26 | HB-S16-03 | Harbor | CT-13 | Cycle | 9.5 | 2025-09-16 | 2025-10-07 | 82557.74 | Complete
VWU-000296 | 17.8 | 2025-08-24 | BY-S07-03 | Bayou | CT-14 | Cycle | 17.8 | 2025-09-17 | 2025-10-29 | 225971.59 | Complete
VWU-000297 | 7 | 2025-08-30 | BY-S28-01 | Bayou | CT-15 | Cycle | 7 | 2025-09-17 | 2025-10-01 | 73920.61 | Complete
VWU-000298 | 10.9 | 2025-08-21 | PR-S09-03 | Prairie | CT-16 | Cycle | 10.9 | 2025-09-18 | 2025-10-14 | 79119.76 | Complete
VWU-000299 | 10.7 | 2025-08-24 | BY-S20-01 | Bayou | CT-15 | Cycle | 10.7 | 2025-09-19 | 2025-10-13 | 112023.81 | Complete
VWU-000300 | 17.2 | 2025-08-28 | HB-S15-02 | Harbor | CT-13 | Cycle | 17.2 | 2025-09-19 | 2025-10-18 | 164832.59 | Complete
VWU-000301 | 5 | 2025-08-29 | CR-S16-04 | Crossroads | CT-13 | Hot spot | 5 | 2025-09-22 | 2025-09-28 | 84101.8 | Complete
VWU-000302 | 4.1 | 2025-09-14 | HB-S05-06 | Harbor | CT-13 | Hot spot | 4.1 | 2025-09-24 | 2025-09-29 | 58488.54 | Complete
VWU-000303 | 0.9 | 2025-09-14 | BY-S27-02 | Bayou | CT-15 | Customer request batch | 0.9 | 2025-09-26 | 2025-10-01 | 14667.2 | Complete
VWU-000304 | 0.6 | 2025-09-08 | CR-S13-06 | Crossroads | CT-13 | Customer request batch | 0.6 | 2025-09-28 | 2025-10-02 | 7765.66 | Complete
VWU-000305 | 12.4 | 2025-09-04 | HB-S05-01 | Harbor | CT-13 | Cycle | 12.4 | 2025-09-30 | 2025-10-29 | 103793.04 | Complete
VWU-000306 | 2.3 | 2025-09-20 | HB-S05-05 | Harbor | CT-13 | Customer request batch | 2.3 | 2025-09-30 | 2025-10-11 | 36986.22 | Complete
VWU-000307 | 16.6 | 2025-09-06 | BY-S02-01 | Bayou | CT-15 | Cycle | 16.6 | 2025-10-02 | 2025-10-27 | 201927.64 | Complete
VWU-000308 | 3.6 | 2025-09-16 | PR-S06-02 | Prairie | CT-16 | Hot spot | 3.6 | 2025-10-04 | 2025-10-13 | 53868.33 | Complete
VWU-000309 | 2.7 | 2025-09-15 | BY-S13-01 | Bayou | CT-14 | Customer request batch | 2.7 | 2025-10-05 | 2025-10-14 | 36858.48 | Complete
VWU-000310 | 8.8 | 2025-09-23 | CR-S26-02 | Crossroads | CT-13 | Cycle | 8.8 | 2025-10-05 | 2025-10-19 | 87546.15 | Complete
VWU-000311 | 4.2 | 2025-09-27 | BY-S02-01 | Bayou | CT-14 | Cycle | 4.2 | 2025-10-06 | 2025-10-14 | 48324.53 | Complete
VWU-000312 | 1.9 | 2025-09-27 | BY-S20-01 | Bayou | CT-15 | Cycle | 1.9 | 2025-10-06 | 2025-10-11 | 20778.85 | Complete
VWU-000313 | 10.1 | 2025-09-11 | HB-S03-03 | Harbor | CT-13 | Cycle | 10.1 | 2025-10-08 | 2025-10-25 | 85483.16 | Complete
VWU-000314 | 16 | 2025-09-30 | BY-S10-01 | Bayou | CT-15 | Cycle | 16 | 2025-10-09 | 2025-11-07 | 192947.03 | Complete
VWU-000315 | 4.3 | 2025-09-17 | CR-S05-06 | Crossroads | CT-13 | Cycle | 4.3 | 2025-10-10 | 2025-10-21 | 33355.79 | Complete
VWU-000316 | 5.4 | 2025-09-18 | PR-S06-01 | Prairie | CT-16 | Cycle | 5.4 | 2025-10-10 | 2025-10-21 | 39097.04 | Complete
VWU-000317 | 7.2 | 2025-10-01 | BY-S26-03 | Bayou | CT-14 | Cycle | 7.2 | 2025-10-13 | 2025-10-30 | 79070.78 | Complete
VWU-000318 | 5.7 | 2025-10-01 | CR-S17-03 | Crossroads | CT-13 | Cycle | 5.7 | 2025-10-14 | 2025-10-24 | 45063.01 | Complete
VWU-000319 | 10 | 2025-09-24 | CR-S31-01 | Crossroads | CT-13 | Cycle | 10 | 2025-10-14 | 2025-11-01 | 103865.69 | Complete
VWU-000320 | 3.7 | 2025-10-05 | CR-S16-06 | Crossroads | CT-13 | Hot spot | 3.7 | 2025-10-17 | 2025-10-23 | 58539.05 | Complete
VWU-000321 | 2 | 2025-10-06 | HB-S12-02 | Harbor | CT-13 | Hot spot | 2 | 2025-10-17 | 2025-10-23 | 31903.64 | Complete
VWU-000322 | 4.7 | 2025-10-02 | PR-S04-01 | Prairie | CT-16 | Cycle | 4.7 | 2025-10-17 | 2025-10-30 | 32771.94 | Complete
VWU-000323 | 10.9 | 2025-10-09 | PR-S06-01 | Prairie | CT-16 | Cycle | 10.9 | 2025-10-19 | 2025-11-09 | 87996.37 | Complete
VWU-000324 | 9.4 | 2025-10-01 | PR-S19-05 | Prairie | CT-16 | Cycle | 9.4 | 2025-10-19 | 2025-11-02 | 74960.26 | Complete
VWU-000325 | 4.9 | 2025-10-05 | CR-S15-02 | Crossroads | CT-13 | Cycle | 4.9 | 2025-10-20 | 2025-10-29 | 43704.39 | Complete
VWU-000326 | 7 | 2025-09-22 | PR-S02-03 | Prairie | CT-16 | Cycle | 7 | 2025-10-20 | 2025-11-05 | 56479.4 | Complete
VWU-000327 | 9 | 2025-10-06 | CR-S10-03 | Crossroads | CT-13 | Cycle | 9 | 2025-10-23 | 2025-11-14 | 77272.71 | Complete
VWU-000328 | 20.9 | 2025-10-13 | PR-S04-02 | Prairie | CT-16 | Cycle | 20.9 | 2025-10-23 | 2025-11-22 | 155407.1 | Complete
VWU-000329 | 6 | 2025-10-01 | CR-S13-04 | Crossroads | CT-13 | Cycle | 6 | 2025-10-24 | 2025-11-05 | 50686.51 | Complete
VWU-000330 | 5.4 | 2025-10-04 | BY-S26-03 | Bayou | CT-14 | Cycle | 5.4 | 2025-10-25 | 2025-11-03 | 60040.04 | Complete
VWU-000331 | 2.8 | 2025-09-29 | HB-S18-04 | Harbor | CT-13 | Hot spot | 2.8 | 2025-10-25 | 2025-10-28 | 49403.67 | Complete
VWU-000332 | 9.5 | 2025-10-13 | HB-S20-05 | Harbor | CT-13 | Cycle | 9.5 | 2025-10-25 | 2025-11-11 | 100841.12 | Complete
VWU-000333 | 6.3 | 2025-10-13 | CR-S08-01 | Crossroads | CT-13 | Cycle | 6.3 | 2025-10-26 | 2025-11-08 | 57667.72 | Complete
VWU-000334 | 2 | 2025-10-09 | CR-S23-04 | Crossroads | CT-13 | Hot spot | 2 | 2025-10-27 | 2025-10-30 | 37849.53 | Complete
VWU-000335 | 4.9 | 2025-10-08 | HB-S15-01 | Harbor | CT-13 | Cycle | 4.9 | 2025-10-28 | 2025-11-07 | 42087.99 | Complete
VWU-000336 | 1 | 2025-10-05 | CR-S18-04 | Crossroads | CT-13 | Cycle | 1 | 2025-10-29 | 2025-11-02 | 8621.29 | Complete
VWU-000337 | 4.3 | 2025-10-23 | BY-S15-03 | Bayou | CT-15 | Cycle | 4.3 | 2025-10-30 | 2025-11-09 | 48695.99 | Complete
VWU-000338 | 18 | 2025-10-02 | PR-S15-01 | Prairie | CT-16 | Cycle | 18 | 2025-10-30 | 2025-12-08 | 120167.02 | Complete
VWU-000339 | 13.2 | 2025-10-13 | HB-S11-01 | Harbor | CT-13 | Cycle | 13.2 | 2025-11-01 | 2025-11-23 | 106584.88 | Complete
VWU-000340 | 4.4 | 2025-10-20 | PR-S06-01 | Prairie | CT-16 | Cycle | 4.4 | 2025-11-02 | 2025-11-11 | 28921.32 | Complete
VWU-000341 | 15.7 | 2025-10-16 | HB-S02-02 | Harbor | CT-13 | Cycle | 15.7 | 2025-11-04 | 2025-11-28 | 162159.63 | Complete
VWU-000342 | 5 | 2025-10-17 | PR-S09-03 | Prairie | CT-16 | Cycle | 5 | 2025-11-04 | 2025-11-13 | 36346.4 | Complete
VWU-000343 | 11.4 | 2025-10-11 | PR-S19-03 | Prairie | CT-16 | Cycle | 11.4 | 2025-11-04 | 2025-11-27 | 96961.86 | Complete
VWU-000344 | 3 | 2025-10-29 | CR-S19-01 | Crossroads | CT-13 | Customer request batch | 3 | 2025-11-05 | 2025-11-09 | 47794.84 | Complete
VWU-000345 | 4.6 | 2025-10-29 | CR-S14-03 | Crossroads | CT-13 | Cycle | 4.6 | 2025-11-09 | 2025-11-20 | 47755.95 | Complete
VWU-000346 | 8.6 | 2025-10-26 | CR-S25-05 | Crossroads | CT-13 | Cycle | 8.6 | 2025-11-09 | 2025-11-27 | 69564.15 | Complete
VWU-000347 | 4.5 | 2025-10-28 | BY-S09-02 | Bayou | CT-14 | Cycle | 4.5 | 2025-11-13 | 2025-11-21 | 55544.51 | Complete
VWU-000348 | 1.6 | 2025-10-31 | BY-S18-02 | Bayou | CT-15 | Hot spot | 1.6 | 2025-11-13 | 2025-11-18 | 23885.27 | Complete
VWU-000349 | 13.5 | 2025-10-19 | PR-S19-03 | Prairie | CT-16 | Cycle | 13.5 | 2025-11-13 | 2025-12-07 | 102212.84 | Complete
VWU-000350 | 18.4 | 2025-10-23 | BY-S19-03 | Bayou | CT-15 | Cycle | 18.4 | 2025-11-15 | 2025-12-16 | 185562.09 | Complete
VWU-000351 | 3.4 | 2025-10-28 | PR-S20-02 | Prairie | CT-16 | Hot spot | 3.4 | 2025-11-18 | 2025-11-25 | 53437.68 | Complete
VWU-000352 | 1.9 | 2025-11-09 | PR-S20-01 | Prairie | CT-16 | Cycle | 1.9 | 2025-11-19 | 2025-11-24 | 15169.12 | Complete
VWU-000353 | 2.6 | 2025-10-23 | BY-S24-04 | Bayou | CT-14 | Customer request batch | 2.6 | 2025-11-20 | 2025-11-27 | 34283.48 | Complete
VWU-000354 | 11.8 | 2025-11-09 | PR-S06-01 | Prairie | CT-16 | Cycle | 11.8 | 2025-11-20 | 2025-12-12 | 82686.51 | Complete
VWU-000355 | 4.8 | 2025-11-11 | BY-S15-01 | Bayou | CT-15 | Cycle | 4.8 | 2025-11-21 | 2025-12-03 | 52543.16 | Complete
VWU-000356 | 2.7 | 2025-11-08 | HB-S17-02 | Harbor | CT-13 | Customer request batch | 2.7 | 2025-11-24 | 2025-12-02 | 43887.01 | Complete
VWU-000357 | 3 | 2025-10-31 | PR-S13-01 | Prairie | CT-16 | Customer request batch | 3 | 2025-11-24 | 2025-12-03 | 47204.28 | Complete
VWU-000358 | 12.5 | 2025-11-03 | HB-S08-01 | Harbor | CT-13 | Cycle | 12.5 | 2025-11-28 | 2025-12-16 | 121581.52 | Complete
VWU-000359 | 5.9 | 2025-11-03 | BY-S30-02 | Bayou | CT-15 | Hot spot | 5.9 | 2025-11-30 | 2025-12-05 | 89113.56 | Complete
VWU-000360 | 4.8 | 2025-11-24 | BY-S16-05 | Bayou | CT-15 | Hot spot | 4.8 | 2025-12-01 | 2025-12-07 | 82839.87 | Complete
VWU-000361 | 4.5 | 2025-11-22 | HB-S11-02 | Harbor | CT-13 | Cycle | 4.5 | 2025-12-01 | 2025-12-09 | 41526.45 | Complete
VWU-000362 | 18.7 | 2025-11-16 | BY-S04-03 | Bayou | CT-15 | Cycle | 18.7 | 2025-12-02 | 2026-01-06 | 246678.59 | Complete
VWU-000363 | 6 | 2025-11-09 | BY-S17-01 | Bayou | CT-14 | Cycle | 6 | 2025-12-02 | 2025-12-12 | 78600.62 | Complete
VWU-000364 | 22 | 2025-11-24 | CR-S14-03 | Crossroads | CT-13 | Cycle | 22 | 2025-12-02 | 2026-01-02 | 212000.23 | Complete
VWU-000365 | 13.6 | 2025-11-11 | PR-S09-03 | Prairie | CT-16 | Cycle | 13.6 | 2025-12-02 | 2025-12-27 | 100381.19 | Complete
VWU-000366 | 5.7 | 2025-11-30 | HB-S03-01 | Harbor | CT-13 | Hot spot | 5.7 | 2025-12-13 | 2025-12-15 | 98075.67 | Complete
VWU-000367 | 11.3 | 2025-12-16 | BY-S24-05 | Bayou | CT-14 | Cycle | 11.3 | 2026-01-05 | 2026-01-28 | 148545.44 | Complete
VWU-000368 | 16.9 | 2025-12-21 | BY-S29-01 | Bayou | CT-14 | Cycle | 16.9 | 2026-01-05 | 2026-02-12 | 182998.77 | Complete
VWU-000369 | 5.5 | 2025-12-20 | BY-S26-04 | Bayou | CT-14 | Hot spot | 5.5 | 2026-01-06 | 2026-01-11 | 95408.03 | Complete
VWU-000370 | 1.9 | 2025-12-22 | CR-S27-04 | Crossroads | CT-13 | Hot spot | 1.9 | 2026-01-06 | 2026-01-10 | 30799.35 | Complete
VWU-000371 | 1.9 | 2025-12-30 | BY-S21-01 | Bayou | CT-14 | Hot spot | 1.9 | 2026-01-07 | 2026-01-16 | 31981.47 | Complete
VWU-000372 | 2.4 | 2025-12-28 | HB-S17-01 | Harbor | CT-13 | Customer request batch | 2.4 | 2026-01-09 | 2026-01-20 | 29178.89 | Complete
VWU-000373 | 8.3 | 2025-12-14 | HB-S18-03 | Harbor | CT-13 | Cycle | 8.3 | 2026-01-10 | 2026-01-28 | 85956.91 | Complete
VWU-000374 | 3.1 | 2025-12-18 | PR-S13-05 | Prairie | CT-16 | Hot spot | 3.1 | 2026-01-12 | 2026-01-16 | 44566.01 | Complete
VWU-000375 | 1.1 | 2026-01-06 | BY-S06-03 | Bayou | CT-15 | Cycle | 1.1 | 2026-01-13 | 2026-01-17 | 13114.72 | Complete
VWU-000376 | 5.5 | 2025-12-31 | BY-S20-02 | Bayou | CT-14 | Cycle | 5.5 | 2026-01-14 | 2026-01-26 | 59616.41 | Complete
VWU-000377 | 0.4 | 2026-01-07 | CR-S23-01 | Crossroads | CT-13 | Cycle | 0.4 | 2026-01-14 | 2026-01-17 | 3281.23 | Complete
VWU-000378 | 12.5 | 2025-12-30 | BY-S06-03 | Bayou | CT-15 | Cycle | 12.5 | 2026-01-16 | 2026-02-05 | 144349.71 | Complete
VWU-000379 | 3.1 | 2026-01-06 | HB-S01-02 | Harbor | CT-13 | Hot spot | 3.1 | 2026-01-16 | 2026-01-24 | 46483.07 | Complete
VWU-000380 | 5.5 | 2026-01-01 | HB-S18-03 | Harbor | CT-13 | Cycle | 5.5 | 2026-01-16 | 2026-01-30 | 58513.69 | Complete
VWU-000381 | 14.7 | 2025-12-20 | PR-S01-05 | Prairie | CT-16 | Cycle | 14.7 | 2026-01-16 | 2026-02-06 | 117729.87 | Complete
VWU-000382 | 8.5 | 2025-12-22 | CR-S11-01 | Crossroads | CT-13 | Resiliency acceleration | 8.5 | 2026-01-18 | 2026-02-07 | 79906.71 | Complete
VWU-000383 | 5.5 | 2025-12-28 | CR-S09-04 | Crossroads | CT-13 | Cycle | 5.5 | 2026-01-19 | 2026-01-30 | 51428.69 | Complete
VWU-000384 | 5.7 | 2025-12-25 | HB-S09-04 | Harbor | CT-13 | Hot spot | 5.7 | 2026-01-21 | 2026-01-25 | 99718.58 | Complete
VWU-000385 | 2.7 | 2025-12-29 | PR-S13-04 | Prairie | CT-16 | Resiliency acceleration | 2.7 | 2026-01-21 | 2026-01-29 | 20411.78 | Complete
VWU-000386 | 5.5 | 2026-01-06 | CR-S16-05 | Crossroads | CT-13 | Cycle | 5.5 | 2026-01-22 | 2026-02-05 | 46194.51 | Complete
VWU-000387 | 13.7 | 2025-12-30 | BY-S13-03 | Bayou | CT-15 | Cycle | 13.7 | 2026-01-23 | 2026-02-11 | 158805.16 | Complete
VWU-000388 | 3.8 | 2026-01-01 | PR-S03-02 | Prairie | CT-16 | Hot spot | 3.8 | 2026-01-23 | 2026-01-30 | 66163.37 | Complete
VWU-000389 | 9 | 2026-01-07 | CR-S08-06 | Crossroads | CT-13 | Cycle | 9 | 2026-01-24 | 2026-02-11 | 78160.61 | Complete
VWU-000390 | 1.8 | 2026-01-07 | CR-S05-06 | Crossroads | CT-13 | Customer request batch | 1.8 | 2026-01-25 | 2026-02-03 | 23551.29 | Complete
VWU-000391 | 0.9 | 2026-01-06 | HB-S18-04 | Harbor | CT-13 | Customer request batch | 0.9 | 2026-01-26 | 2026-01-28 | 13726.8 | Complete
VWU-000392 | 5.1 | 2026-01-17 | BY-S09-01 | Bayou | CT-14 | Hot spot | 5.1 | 2026-01-28 | 2026-01-31 | 95483.89 | Complete
VWU-000393 | 3 | 2026-01-03 | CR-S07-01 | Crossroads | CT-13 | Cycle | 3 | 2026-01-28 | 2026-02-06 | 26676.92 | Complete
VWU-000394 | 12.8 | 2026-01-14 | CR-S09-01 | Crossroads | CT-13 | Resiliency acceleration | 12.8 | 2026-01-28 | 2026-02-24 | 136447.27 | Complete
VWU-000395 | 4.9 | 2026-01-15 | CR-S28-03 | Crossroads | CT-13 | Cycle | 4.9 | 2026-01-29 | 2026-02-10 | 40998.5 | Complete
VWU-000396 | 13.9 | 2026-01-13 | BY-S14-01 | Bayou | CT-14 | Cycle | 13.9 | 2026-01-30 | 2026-02-24 | 144296.08 | Complete
VWU-000397 | 13.5 | 2026-01-03 | BY-S26-02 | Bayou | CT-15 | Cycle | 13.5 | 2026-01-30 | 2026-02-22 | 176943.4 | Complete
VWU-000398 | 9.4 | 2026-01-09 | CR-S14-02 | Crossroads | CT-13 | Cycle | 9.4 | 2026-02-01 | 2026-02-16 | 77570.76 | Complete
VWU-000399 | 7.9 | 2026-01-24 | PR-S13-03 | Prairie | CT-16 | Cycle | 7.9 | 2026-02-01 | 2026-02-19 | 65111.55 | Complete
VWU-000400 | 5.3 | 2026-01-10 | BY-S12-03 | Bayou | CT-15 | Cycle | 5.3 | 2026-02-02 | 2026-02-16 | 55022.37 | Complete
VWU-000401 | 10.4 | 2026-01-27 | PR-S05-02 | Prairie | CT-16 | Cycle | 10.4 | 2026-02-03 | 2026-02-23 | 88110.26 | Complete
VWU-000402 | 4.4 | 2026-01-10 | HB-S07-02 | Harbor | CT-13 | Resiliency acceleration | 4.4 | 2026-02-04 | 2026-02-12 | 41306.47 | Complete
VWU-000403 | 18.6 | 2026-01-11 | PR-S18-01 | Prairie | CT-16 | Cycle | 18.6 | 2026-02-04 | 2026-03-05 | 151398.6 | Complete
VWU-000404 | 5.7 | 2026-01-13 | PR-S19-02 | Prairie | CT-16 | Cycle | 5.7 | 2026-02-05 | 2026-02-19 | 40710.12 | Complete
VWU-000405 | 4.8 | 2026-01-26 | CR-S10-02 | Crossroads | CT-13 | Cycle | 4.8 | 2026-02-06 | 2026-02-16 | 39928.03 | Complete
VWU-000406 | 10.6 | 2026-01-16 | BY-S12-04 | Bayou | CT-15 | Cycle | 10.6 | 2026-02-07 | 2026-02-26 | 119331.72 | Complete
VWU-000407 | 4.9 | 2026-01-17 | BY-S29-01 | Bayou | CT-14 | Cycle | 4.9 | 2026-02-07 | 2026-02-18 | 54821.52 | Complete
VWU-000408 | 2.3 | 2026-01-26 | BY-S12-04 | Bayou | CT-15 | Cycle | 2.3 | 2026-02-10 | 2026-02-17 | 23942.12 | Complete
VWU-000409 | 19.1 | 2026-01-29 | HB-S13-02 | Harbor | CT-13 | Cycle | 19.1 | 2026-02-10 | 2026-03-12 | 199047.85 | Complete
VWU-000410 | 3.2 | 2026-01-30 | BY-S10-05 | Bayou | CT-14 | Cycle | 3.2 | 2026-02-11 | 2026-02-18 | 37728.47 | Complete
VWU-000411 | 14.2 | 2026-01-31 | BY-S23-04 | Bayou | CT-15 | Cycle | 14.2 | 2026-02-11 | 2026-03-11 | 180775.78 | Complete
VWU-000412 | 11.7 | 2026-01-17 | CR-S03-02 | Crossroads | CT-13 | Cycle | 11.7 | 2026-02-12 | 2026-03-08 | 94429.49 | Complete
VWU-000413 | 1.3 | 2026-01-22 | PR-S01-04 | Prairie | CT-16 | Cycle | 1.3 | 2026-02-13 | 2026-02-18 | 10869.53 | Complete
VWU-000414 | 2.1 | 2026-02-04 | BY-S13-03 | Bayou | CT-15 | Cycle | 2.1 | 2026-02-14 | 2026-02-20 | 25100.25 | Complete
VWU-000415 | 0.8 | 2026-01-30 | CR-S20-01 | Crossroads | CT-13 | Cycle | 0.8 | 2026-02-16 | 2026-02-20 | 6608.92 | Complete
VWU-000416 | 12.5 | 2026-02-08 | CR-S19-01 | Crossroads | CT-13 | Cycle | 12.5 | 2026-02-17 | 2026-03-12 | 109376.16 | Complete
VWU-000417 | 19.6 | 2026-02-04 | BY-S26-06 | Bayou | CT-14 | Cycle | 19.6 | 2026-02-18 | 2026-03-20 | 202401.89 | Complete
VWU-000418 | 6.6 | 2026-02-13 | PR-S15-05 | Prairie | CT-16 | Cycle | 6.6 | 2026-02-20 | 2026-03-04 | 43989.69 | Complete
VWU-000419 | 14.4 | 2026-02-13 | PR-S17-01 | Prairie | CT-16 | Cycle | 14.4 | 2026-02-22 | 2026-03-23 | 96891.04 | Complete
VWU-000420 | 10 | 2026-02-06 | PR-S19-01 | Prairie | CT-16 | Cycle | 10 | 2026-02-23 | 2026-03-15 | 82469.05 | Complete
VWU-000421 | 4.9 | 2026-01-29 | BY-S18-02 | Bayou | CT-15 | Hot spot | 4.9 | 2026-02-24 | 2026-03-02 | 83641.84 | Complete
VWU-000422 | 12.8 | 2026-02-05 | BY-S21-05 | Bayou | CT-14 | Cycle | 12.8 | 2026-02-25 | 2026-03-27 | 154265.07 | Complete
VWU-000423 | 4.4 | 2026-01-29 | BY-S29-01 | Bayou | CT-15 | Cycle | 4.4 | 2026-02-25 | 2026-03-06 | 44442.29 | Complete
VWU-000424 | 12.8 | 2026-02-09 | BY-S06-02 | Bayou | CT-15 | Cycle | 12.8 | 2026-02-27 | 2026-03-17 | 153664.62 | Complete
VWU-000425 | 7 | 2026-02-04 | CR-S01-04 | Crossroads | CT-13 | Cycle | 7 | 2026-02-27 | 2026-03-11 | 69682.54 | Complete
VWU-000426 | 4.5 | 2026-02-15 | CR-S08-01 | Crossroads | CT-13 | Hot spot | 4.5 | 2026-02-27 | 2026-03-05 | 73060.55 | Complete
VWU-000427 | 4 | 2026-02-16 | PR-S02-03 | Prairie | CT-16 | Hot spot | 4 | 2026-02-27 | 2026-03-01 | 65526.06 | Complete
VWU-000428 | 5.4 | 2026-02-02 | CR-S23-01 | Crossroads | CT-13 | Cycle | 5.4 | 2026-02-28 | 2026-03-09 | 50004.06 | Complete
VWU-000429 | 7.5 | 2026-02-17 | PR-S07-05 | Prairie | CT-16 | Cycle | 7.5 | 2026-03-01 | 2026-03-19 | 50727.8 | Complete
VWU-000430 | 6.8 | 2026-02-18 | BY-S12-03 | Bayou | CT-15 | Cycle | 6.8 | 2026-03-03 | 2026-03-18 | 70027.61 | Complete
VWU-000431 | 2.5 | 2026-02-09 | BY-S17-03 | Bayou | CT-14 | Resiliency acceleration | 2.5 | 2026-03-03 | 2026-03-09 | 30636.51 | Complete
VWU-000432 | 20.8 | 2026-02-09 | BY-S26-01 | Bayou | CT-15 | Cycle | 20.8 | 2026-03-03 | 2026-04-03 | 264111.95 | Complete
VWU-000433 | 3.6 | 2026-02-06 | CR-S22-02 | Crossroads | CT-13 | Hot spot | 3.6 | 2026-03-04 | 2026-03-08 | 66859.18 | Complete
VWU-000434 | 2.7 | 2026-02-08 | PR-S20-01 | Prairie | CT-16 | Customer request batch | 2.7 | 2026-03-05 | 2026-03-09 | 39313.22 | Complete
VWU-000435 | 7.3 | 2026-02-21 | BY-S13-06 | Bayou | CT-14 | Cycle | 7.3 | 2026-03-06 | 2026-03-20 | 87550.35 | Complete
VWU-000436 | 13.6 | 2026-02-27 | BY-S15-06 | Bayou | CT-14 | Resiliency acceleration | 13.6 | 2026-03-07 | 2026-04-04 | 168535.96 | Complete
VWU-000437 | 8 | 2026-02-14 | PR-S14-04 | Prairie | CT-16 | Cycle | 8 | 2026-03-07 | 2026-03-19 | 65332.62 | Complete
VWU-000438 | 1 | 2026-02-27 | BY-S22-02 | Bayou | CT-15 | Hot spot | 1 | 2026-03-08 | 2026-03-17 | 18105.37 | Complete
VWU-000439 | 4.2 | 2026-02-12 | CR-S30-05 | Crossroads | CT-13 | Cycle | 4.2 | 2026-03-08 | 2026-03-18 | 39638.24 | Complete
VWU-000440 | 4.2 | 2026-02-22 | BY-S19-02 | Bayou | CT-14 | Hot spot | 4.2 | 2026-03-09 | 2026-03-17 | 75819.69 | Complete
VWU-000441 | 9.8 | 2026-02-25 | CR-S26-03 | Crossroads | CT-13 | Cycle | 9.8 | 2026-03-10 | 2026-03-27 | 81167.32 | Complete
VWU-000442 | 10.7 | 2026-02-21 | PR-S13-03 | Prairie | CT-16 | Cycle | 10.7 | 2026-03-10 | 2026-03-29 | 69334.66 | Complete
VWU-000443 | 12.4 | 2026-03-04 | BY-S24-03 | Bayou | CT-14 | Cycle | 12.4 | 2026-03-11 | 2026-04-08 | 135802.63 | Complete
VWU-000444 | 2.4 | 2026-03-02 | PR-S01-02 | Prairie | CT-16 | Cycle | 2.4 | 2026-03-11 | 2026-03-17 | 16058.9 | Complete
VWU-000445 | 4.6 | 2026-03-04 | BY-S16-05 | Bayou | CT-15 | Resiliency acceleration | 4.6 | 2026-03-12 | 2026-03-22 | 54905.24 | Complete
VWU-000446 | 2 | 2026-02-27 | BY-S19-04 | Bayou | CT-15 | Customer request batch | 2 | 2026-03-12 | 2026-03-18 | 24520.29 | Complete
VWU-000447 | 7.7 | 2026-02-13 | PR-S01-05 | Prairie | CT-16 | Cycle | 7.7 | 2026-03-13 | 2026-03-31 | 50404.74 | Complete
VWU-000448 | 12.1 | 2026-02-22 | CR-S14-04 | Crossroads | CT-13 | Cycle | 12.1 | 2026-03-14 | 2026-04-06 | 117181.01 | Complete
VWU-000449 | 2.2 | 2026-02-27 | BY-S13-02 | Bayou | CT-14 | Hot spot | 2.2 | 2026-03-15 | 2026-03-20 | 32291.91 | Complete
VWU-000450 | 1 | 2026-03-07 | CR-S13-05 | Crossroads | CT-13 | Customer request batch | 1 | 2026-03-15 | 2026-03-24 | 12279.9 | Complete
VWU-000451 | 9.3 | 2026-03-01 | CR-S20-03 | Crossroads | CT-13 | Cycle | 9.3 | 2026-03-15 | 2026-03-31 | 94700.79 | Complete
VWU-000452 | 9.3 | 2026-02-24 | CR-S31-02 | Crossroads | CT-13 | Resiliency acceleration | 9.3 | 2026-03-15 | 2026-03-30 | 98654.54 | Complete
VWU-000453 | 16.1 | 2026-02-27 | PR-S07-02 | Prairie | CT-16 | Cycle | 16.1 | 2026-03-16 | 2026-04-09 | 134109.14 | Complete
VWU-000454 | 1.9 | 2026-02-18 | BY-S19-04 | Bayou | CT-14 | Customer request batch | 1.9 | 2026-03-17 | 2026-03-29 | 30166.68 | Complete
VWU-000455 | 1.2 | 2026-03-05 | BY-S30-02 | Bayou | CT-14 | Hot spot | 1.2 | 2026-03-17 | 2026-03-23 | 18506.86 | Complete
VWU-000456 | 7.3 | 2026-02-28 | HB-S16-01 | Harbor | CT-13 | Cycle | 7.3 | 2026-03-17 | 2026-03-31 | 67828.97 | Complete
VWU-000457 | 10.8 | 2026-02-23 | BY-S25-01 | Bayou | CT-14 | Cycle | 10.8 | 2026-03-19 | 2026-04-11 | 134433.51 | Complete
VWU-000458 | 8.3 | 2026-02-24 | HB-S12-03 | Harbor | CT-13 | Cycle | 8.3 | 2026-03-19 | 2026-04-08 | 84207.98 | Complete
VWU-000459 | 1.7 | 2026-02-25 | BY-S14-01 | Bayou | CT-14 | Customer request batch | 1.7 | 2026-03-23 | 2026-04-02 | 22466.06 | Complete
VWU-000460 | 3.1 | 2026-03-01 | BY-S16-02 | Bayou | CT-15 | Hot spot | 3.1 | 2026-03-23 | 2026-03-27 | 52920.61 | Complete
VWU-000461 | 15.7 | 2026-03-10 | PR-S13-01 | Prairie | CT-16 | Cycle | 15.7 | 2026-03-24 | 2026-04-29 | 133000.92 | Complete
VWU-000462 | 1.8 | 2026-03-10 | PR-S13-04 | Prairie | CT-16 | Hot spot | 1.8 | 2026-03-24 | 2026-03-29 | 29237.42 | Complete
VWU-000463 | 13.3 | 2026-03-04 | BY-S27-05 | Bayou | CT-15 | Cycle | 13.3 | 2026-03-25 | 2026-04-14 | 148725.49 | Complete
VWU-000464 | 8.1 | 2026-03-07 | BY-S14-03 | Bayou | CT-14 | Cycle | 8.1 | 2026-03-26 | 2026-04-14 | 89055.96 | Complete
VWU-000465 | 1.7 | 2026-03-11 | PR-S15-01 | Prairie | CT-16 | Customer request batch | 1.7 | 2026-03-26 | 2026-04-02 | 27042.82 | Complete
VWU-000466 | 1.7 | 2026-03-10 | CR-S11-02 | Crossroads | CT-13 | Customer request batch | 1.7 | 2026-03-27 | 2026-03-29 | 24405.52 | Complete
VWU-000467 | 1.9 | 2026-03-17 | HB-S19-01 | Harbor | CT-13 | Hot spot | 1.9 | 2026-03-27 | 2026-04-05 | 32831.51 | Complete
VWU-000468 | 15.9 | 2026-03-02 | PR-S12-03 | Prairie | CT-16 | Cycle | 15.9 | 2026-03-28 | 2026-04-29 | 128195.3 | Complete
VWU-000469 | 8.3 | 2026-03-19 | BY-S25-03 | Bayou | CT-14 | Cycle | 8.3 | 2026-03-29 | 2026-04-18 | 100607.97 | Complete
VWU-000470 | 10.6 | 2026-03-01 | BY-S26-02 | Bayou | CT-15 | Cycle | 10.6 | 2026-03-29 | 2026-04-21 | 105072.11 | Complete
VWU-000471 | 12.7 | 2026-03-07 | BY-S29-01 | Bayou | CT-15 | Cycle | 12.7 | 2026-03-29 | 2026-04-27 | 129058.55 | Complete
VWU-000472 | 5 | 2026-03-11 | CR-S09-04 | Crossroads | CT-13 | Hot spot | 5 | 2026-03-29 | 2026-04-02 | 75155.94 | Complete
VWU-000473 | 7.6 | 2026-03-22 | BY-S10-04 | Bayou | CT-14 | Cycle | 7.6 | 2026-03-30 | 2026-04-17 | 85533.41 | Complete
VWU-000474 | 0.5 | 2026-03-20 | CR-S09-05 | Crossroads | CT-13 | Cycle | 0.5 | 2026-03-30 | 2026-04-02 | 4663.63 | Complete
VWU-000475 | 2.2 | 2026-03-02 | HB-S04-01 | Harbor | CT-13 | Cycle | 2.2 | 2026-03-30 | 2026-04-06 | 19409.91 | Complete
VWU-000476 | 6.2 | 2026-03-09 | BY-S03-01 | Bayou | CT-15 | Cycle | 6.2 | 2026-03-31 | 2026-04-15 | 68564.32 | Complete
VWU-000477 | 6.5 | 2026-03-18 | BY-S10-04 | Bayou | CT-14 | Cycle | 6.5 | 2026-03-31 | 2026-04-16 | 79172.59 | Complete
VWU-000478 | 9.7 | 2026-03-11 | BY-S28-03 | Bayou | CT-15 | Cycle | 9.7 | 2026-03-31 | 2026-04-17 | 122706.06 | Complete
VWU-000479 | 2.6 | 2026-03-07 | CR-S08-01 | Crossroads | CT-13 | Hot spot | 2.6 | 2026-04-01 | 2026-04-09 | 41690.06 | Complete
VWU-000480 | 5.5 | 2026-03-12 | BY-S19-04 | Bayou | CT-15 | Resiliency acceleration | 5.5 | 2026-04-02 | 2026-04-14 | 60460.51 | Complete
VWU-000481 | 9.5 | 2026-03-13 | HB-S01-01 | Harbor | CT-13 | Resiliency acceleration | 9.5 | 2026-04-03 | 2026-04-21 | 87630.29 | Complete
VWU-000482 | 2.1 | 2026-03-19 | BY-S06-02 | Bayou | CT-14 | Cycle | 2.1 | 2026-04-06 | 2026-04-13 | 26927.17 | Complete
VWU-000483 | 1.9 | 2026-03-23 | HB-S18-04 | Harbor | CT-13 | Customer request batch | 1.9 | 2026-04-06 | 2026-04-18 | 25936.96 | Complete
VWU-000484 | 2.3 | 2026-03-26 | PR-S03-03 | Prairie | CT-16 | Customer request batch | 2.3 | 2026-04-06 | 2026-04-08 | 35234.16 | Complete
VWU-000485 | 6.2 | 2026-03-25 | PR-S20-02 | Prairie | CT-16 | Cycle | 6.2 | 2026-04-06 | 2026-04-22 | 42019.72 | Complete
VWU-000486 | 7.2 | 2026-03-16 | CR-S25-04 | Crossroads | CT-13 | Cycle | 7.2 | 2026-04-07 | 2026-04-23 | 69264.3 | Complete
VWU-000487 | 10 | 2026-03-28 | HB-S17-02 | Harbor | CT-13 | Cycle | 10 | 2026-04-07 | 2026-04-22 | 95338.4 | Complete
VWU-000488 | 14.5 | 2026-03-13 | BY-S01-02 | Bayou | CT-15 | Cycle | 14.5 | 2026-04-08 | 2026-05-11 | 188321.36 | Complete
VWU-000489 | 1.6 | 2026-03-17 | PR-S01-03 | Prairie | CT-16 | Hot spot | 1.6 | 2026-04-08 | 2026-04-13 | 22571.81 | Complete
VWU-000490 | 9.1 | 2026-03-23 | CR-S16-05 | Crossroads | CT-13 | Cycle | 9.1 | 2026-04-10 | 2026-04-26 | 78746.19 | Complete
VWU-000491 | 10.6 | 2026-03-16 | BY-S10-04 | Bayou | CT-14 | Cycle | 10.6 | 2026-04-11 | 2026-05-01 | 105038.88 | Complete
VWU-000492 | 14 | 2026-03-31 | CR-S08-06 | Crossroads | CT-13 | Cycle | 14 | 2026-04-11 | 2026-05-02 | 117843.04 | Complete
VWU-000493 | 2.9 | 2026-03-27 | CR-S16-04 | Crossroads | CT-13 | Cycle | 2.9 | 2026-04-11 | 2026-04-20 | 23433.94 | Complete
VWU-000494 | 15.2 | 2026-03-22 | HB-S19-04 | Harbor | CT-13 | Cycle | 15.2 | 2026-04-11 | 2026-05-13 | 126261.41 | Complete
VWU-000495 | 6 | 2026-03-30 | PR-S18-02 | Prairie | CT-16 | Cycle | 6 | 2026-04-12 | 2026-04-24 | 43729.29 | Complete
VWU-000496 | 5.8 | 2026-03-26 | CR-S18-05 | Crossroads | CT-13 | Hot spot | 5.8 | 2026-04-13 | 2026-04-17 | 98078.52 | Complete
VWU-000497 | 4.7 | 2026-03-27 | HB-S02-01 | Harbor | CT-13 | Hot spot | 4.7 | 2026-04-15 | 2026-04-24 | 70403.93 | Complete
VWU-000498 | 14.2 | 2026-04-06 | BY-S12-03 | Bayou | CT-15 | Cycle | 14.2 | 2026-04-16 | 2026-05-12 | 150850.75 | Complete
VWU-000499 | 12.8 | 2026-04-05 | CR-S25-02 | Crossroads | CT-13 | Cycle | 12.8 | 2026-04-17 | 2026-05-17 | 100068.91 | Complete
VWU-000500 | 6.6 | 2026-03-30 | HB-S17-03 | Harbor | CT-13 | Cycle | 6.6 | 2026-04-18 | 2026-05-05 | 60638.06 | Complete
VWU-000501 | 2.3 | 2026-03-28 | PR-S17-01 | Prairie | CT-16 | Cycle | 2.3 | 2026-04-18 | 2026-04-25 | 16993.69 | Complete
VWU-000502 | 5.5 | 2026-04-04 | PR-S05-02 | Prairie | CT-16 | Cycle | 5.5 | 2026-04-19 | 2026-04-29 | 35402.34 | Complete
VWU-000503 | 9 | 2026-03-29 | PR-S19-01 | Prairie | CT-16 | Cycle | 9 | 2026-04-19 | 2026-05-11 | 69519.81 | Complete
VWU-000504 | 8.3 | 2026-03-25 | BY-S14-02 | Bayou | CT-14 | Cycle | 8.3 | 2026-04-22 | 2026-05-12 | 96100.97 | Complete
VWU-000505 | 8.1 | 2026-04-03 | HB-S20-03 | Harbor | CT-13 | Cycle | 8.1 | 2026-04-22 | 2026-05-10 | 70267.59 | Complete
VWU-000506 | 8.9 | 2026-03-29 | PR-S01-05 | Prairie | CT-16 | Cycle | 8.9 | 2026-04-22 | 2026-05-08 | 67125.82 | Complete
VWU-000507 | 4.2 | 2026-04-02 | PR-S18-06 | Prairie | CT-16 | Cycle | 4.2 | 2026-04-24 | 2026-05-03 | 30989.12 | Complete
VWU-000508 | 1.3 | 2026-04-10 | BY-S14-01 | Bayou | CT-15 | Cycle | 1.3 | 2026-04-27 | 2026-05-02 | 15909.52 | Complete
VWU-000509 | 17.5 | 2026-04-08 | PR-S01-04 | Prairie | CT-16 | Cycle | 17.5 | 2026-04-27 | 2026-05-26 | 144068.62 | Complete
VWU-000510 | 11 | 2026-04-19 | BY-S29-01 | Bayou | CT-14 | Cycle | 11 | 2026-04-28 | 2026-05-15 | 115144.52 | Complete
VWU-000511 | 3.6 | 2026-04-16 | CR-S13-03 | Crossroads | CT-13 | Resiliency acceleration | 3.6 | 2026-04-28 | 2026-05-07 | 37469.86 | Complete
VWU-000512 | 5.1 | 2026-04-02 | CR-S30-05 | Crossroads | CT-13 | Cycle | 5.1 | 2026-04-29 | 2026-05-10 | 51946.34 | Complete
VWU-000513 | 3.8 | 2026-04-08 | PR-S04-02 | Prairie | CT-16 | Hot spot | 3.8 | 2026-04-29 | 2026-05-05 | 60325.98 | Complete
VWU-000514 | 8.3 | 2026-04-05 | PR-S17-02 | Prairie | CT-16 | Cycle | 8.3 | 2026-04-29 | 2026-05-13 | 66507.1 | Complete
VWU-000515 | 5.7 | 2026-04-03 | CR-S05-02 | Crossroads | CT-13 | Hot spot | 5.7 | 2026-04-30 | 2026-05-09 | 106044.18 | Complete
VWU-000516 | 8.2 | 2026-04-17 | CR-S23-04 | Crossroads | CT-13 | Cycle | 8.2 | 2026-04-30 | 2026-05-14 | 65939.24 | Complete
VWU-000517 | 12 | 2026-04-06 | BY-S29-04 | Bayou | CT-14 | Cycle | 12 | 2026-05-01 | 2026-05-28 | 119070.06 | Complete
VWU-000518 | 2.8 | 2026-04-21 | CR-S02-03 | Crossroads | CT-13 | Customer request batch | 2.8 | 2026-05-04 | 2026-05-16 | 39617.88 | Complete
VWU-000519 | 6.7 | 2026-04-21 | PR-S15-05 | Prairie | CT-16 | Cycle | 6.7 | 2026-05-04 | 2026-05-20 | 47791.65 | Complete
VWU-000520 | 7.4 | 2026-04-25 | PR-S19-01 | Prairie | CT-16 | Cycle | 7.4 | 2026-05-04 | 2026-05-16 | 58961.52 | Complete
VWU-000521 | 19.1 | 2026-04-10 | PR-S11-03 | Prairie | CT-16 | Cycle | 19.1 | 2026-05-05 | 2026-06-15 | 152949.43 | Complete
VWU-000522 | 3.6 | 2026-04-20 | BY-S23-03 | Bayou | CT-15 | Cycle | 3.6 | 2026-05-06 | 2026-05-16 | 46458 | Complete
VWU-000523 | 9.2 | 2026-04-17 | PR-S01-05 | Prairie | CT-16 | Cycle | 9.2 | 2026-05-06 | 2026-05-26 | 69947.65 | Complete
VWU-000524 | 8.9 | 2026-04-11 | CR-S31-02 | Crossroads | CT-13 | Resiliency acceleration | 8.9 | 2026-05-07 | 2026-05-27 | 93154.54 | Complete
VWU-000525 | 2.8 | 2026-04-13 | PR-S07-05 | Prairie | CT-16 | Cycle | 2.8 | 2026-05-07 | 2026-05-13 | 17862.42 | Complete
VWU-000526 | 14.3 | 2026-04-11 | BY-S29-01 | Bayou | CT-15 | Cycle | 14.3 | 2026-05-08 | 2026-06-07 | 180688.06 | Complete
VWU-000527 | 18.8 | 2026-05-01 | CR-S07-03 | Crossroads | CT-13 | Cycle | 18.8 | 2026-05-08 | 2026-06-11 | 186068.47 | Complete
VWU-000528 | 9.3 | 2026-04-10 | HB-S05-05 | Harbor | CT-13 | Cycle | 9.3 | 2026-05-08 | 2026-05-23 | 93149.88 | Complete
VWU-000529 | 1.2 | 2026-04-23 | HB-S15-03 | Harbor | CT-13 | Hot spot | 1.2 | 2026-05-10 | 2026-05-16 | 17725.44 | Complete
VWU-000530 | 3.7 | 2026-04-18 | CR-S24-01 | Crossroads | CT-13 | Cycle | 3.7 | 2026-05-11 | 2026-05-20 | 35783.12 | Complete
VWU-000531 | 7 | 2026-04-21 | CR-S30-01 | Crossroads | CT-13 | Resiliency acceleration | 7 | 2026-05-11 | 2026-05-25 | 68919.26 | Complete
VWU-000532 | 6.9 | 2026-04-20 | HB-S18-03 | Harbor | CT-13 | Cycle | 6.9 | 2026-05-11 | 2026-05-26 | 71429.36 | Complete
VWU-000533 | 11 | 2026-04-18 | BY-S20-03 | Bayou | CT-15 | Cycle | 11 | 2026-05-12 | 2026-05-30 | 139636.07 | Complete
VWU-000534 | 9.5 | 2026-05-03 | HB-S17-03 | Harbor | CT-13 | Cycle | 9.5 | 2026-05-13 | 2026-05-27 | 91692.42 | Complete
VWU-000535 | 1.9 | 2026-05-03 | BY-S26-04 | Bayou | CT-14 | Hot spot | 1.9 | 2026-05-15 | 2026-05-19 | 30600.95 | Complete
VWU-000536 | 20.2 | 2026-04-19 | PR-S17-02 | Prairie | CT-16 | Cycle | 20.2 | 2026-05-16 | 2026-06-13 | 169452.59 | Complete
VWU-000537 | 1.7 | 2026-05-06 | CR-S15-01 | Crossroads | CT-13 | Hot spot | 1.7 | 2026-05-17 | 2026-05-25 | 31629.48 | Complete
VWU-000538 | 1.9 | 2026-04-29 | CR-S22-04 | Crossroads | CT-13 | Customer request batch | 1.9 | 2026-05-17 | 2026-05-26 | 28110.76 | Complete
VWU-000539 | 4.4 | 2026-05-10 | PR-S11-03 | Prairie | CT-16 | Cycle | 4.4 | 2026-05-17 | 2026-05-26 | 34756.88 | Complete
VWU-000540 | 4.5 | 2026-05-01 | BY-S20-02 | Bayou | CT-14 | Post-storm | 4.5 | 2026-05-20 | 2026-06-04 | 85157.91 | Complete
VWU-000541 | 10.2 | 2026-05-04 | CR-S14-02 | Crossroads | CT-13 | Cycle | 10.2 | 2026-05-21 | 2026-06-11 | 93465.22 | Complete
VWU-000542 | 7.9 | 2026-05-12 | CR-S20-04 | Crossroads | CT-13 | Post-storm | 7.9 | 2026-05-21 | 2026-06-02 | 168379.34 | Complete
VWU-000543 | 16.9 | 2026-05-03 | PR-S07-02 | Prairie | CT-16 | Cycle | 16.9 | 2026-05-22 | 2026-06-27 | 132866.35 | Complete
VWU-000544 | 3.9 | 2026-04-30 | CR-S23-03 | Crossroads | CT-13 | Post-storm | 3.9 | 2026-05-23 | 2026-05-29 | 76521.05 | Complete
VWU-000545 | 2.4 | 2026-04-26 | CR-S15-03 | Crossroads | CT-13 | Customer request batch | 2.4 | 2026-05-24 | 2026-05-29 | 37353.6 | Complete
VWU-000546 | 5.3 | 2026-05-04 | BY-S11-03 | Bayou | CT-14 | Post-storm | 5.3 | 2026-05-25 | 2026-06-06 | 100093.95 | Complete
VWU-000547 | 7.5 | 2026-05-14 | PR-S20-02 | Prairie | CT-16 | Cycle | 7.5 | 2026-05-25 | 2026-06-12 | 54036.58 | Complete
VWU-000548 | 7.1 | 2026-05-07 | HB-S19-01 | Harbor | CT-13 | Cycle | 7.1 | 2026-05-26 | 2026-06-09 | 58872.87 | Complete
VWU-000549 | 3.8 | 2026-05-08 | BY-S27-04 | Bayou | CT-14 | Cycle | 3.8 | 2026-05-27 | 2026-06-07 | 42573.89 | Complete
VWU-000550 | 4.7 | 2026-05-13 | BY-S29-01 | Bayou | CT-15 | Cycle | 4.7 | 2026-05-27 | 2026-06-06 | 62214.35 | Complete
VWU-000551 | 4.6 | 2026-04-29 | CR-S25-03 | Crossroads | CT-13 | Post-storm | 4.6 | 2026-05-27 | 2026-06-11 | 104168.45 | Complete
VWU-000552 | 5.3 | 2026-05-02 | PR-S16-04 | Prairie | CT-16 | Hot spot | 5.3 | 2026-05-28 | 2026-06-03 | 80350.1 | Complete
VWU-000553 | 6.4 | 2026-05-19 | PR-S20-01 | Prairie | CT-16 | Post-storm | 6.4 | 2026-05-28 | 2026-06-03 | 132777 | Complete
VWU-000554 | 6 | 2026-05-08 | BY-S30-03 | Bayou | CT-15 | Cycle | 6 | 2026-05-29 | 2026-06-12 | 72087.81 | Complete
VWU-000555 | 6.2 | 2026-05-02 | CR-S08-06 | Crossroads | CT-13 | Post-storm | 6.2 | 2026-05-29 | 2026-06-11 | 141887.51 | Complete
VWU-000556 | 1.8 | 2026-05-20 | PR-S11-01 | Prairie | CT-16 | Post-storm | 1.8 | 2026-05-29 | 2026-06-06 | 43311.8 | Complete
VWU-000557 | 2.3 | 2026-05-17 | CR-S03-03 | Crossroads | CT-13 | Customer request batch | 2.3 | 2026-05-30 | 2026-06-07 | 32436.74 | Complete
VWU-000558 | 6.7 | 2026-05-18 | CR-S12-02 | Crossroads | CT-13 | Post-storm | 6.7 | 2026-05-30 | 2026-06-04 | 134839.9 | Complete
VWU-000559 | 5.6 | 2026-05-16 | PR-S16-05 | Prairie | CT-16 | Post-storm | 5.6 | 2026-05-30 | 2026-06-10 | 137899.43 | Complete
VWU-000560 | 6.8 | 2026-05-17 | CR-S22-03 | Crossroads | CT-13 | Post-storm | 6.8 | 2026-05-31 | 2026-06-09 | 136512.79 | Complete
VWU-000561 | 13.6 | 2026-05-07 | BY-S13-06 | Bayou | CT-15 | Cycle | 13.6 | 2026-06-01 | 2026-06-21 | 159230.73 | Complete
VWU-000562 | 18.3 | 2026-05-16 | BY-S25-04 | Bayou | CT-15 | Cycle | 18.3 | 2026-06-01 | 2026-07-12 | 221997.91 | Complete
VWU-000563 | 3.5 | 2026-05-17 | CR-S12-01 | Crossroads | CT-13 | Post-storm | 3.5 | 2026-06-01 | 2026-06-15 | 73793.88 | Complete
VWU-000564 | 3.4 | 2026-05-15 | CR-S25-06 | Crossroads | CT-13 | Post-storm | 3.4 | 2026-06-01 | 2026-06-16 | 73602.3 | Complete
VWU-000565 | 7.1 | 2026-05-20 | PR-S02-02 | Prairie | CT-16 | Post-storm | 7.1 | 2026-06-01 | 2026-06-09 | 137483.84 | Complete
VWU-000566 | 4.6 | 2026-05-17 | PR-S20-04 | Prairie | CT-16 | Post-storm | 4.6 | 2026-06-01 | 2026-06-12 | 110617.35 | Complete
VWU-000567 | 6.7 | 2026-05-12 | HB-S16-01 | Harbor | CT-13 | Cycle | 6.7 | 2026-06-02 | 2026-06-15 | 55037.33 | Complete
VWU-000568 | 1.9 | 2026-05-05 | PR-S20-02 | Prairie | CT-16 | Post-storm | 1.9 | 2026-06-02 | 2026-06-17 | 43421.01 | Complete
VWU-000569 | 4.3 | 2026-05-22 | BY-S26-06 | Bayou | CT-15 | Post-storm | 4.3 | 2026-06-03 | 2026-06-06 | 104190.68 | Complete
VWU-000570 | 2.2 | 2026-05-26 | CR-S04-04 | Crossroads | CT-13 | Post-storm | 2.2 | 2026-06-03 | 2026-06-12 | 40656.42 | Complete
VWU-000571 | 7 | 2026-05-18 | CR-S12-03 | Crossroads | CT-13 | Post-storm | 7 | 2026-06-03 | 2026-06-10 | 140962.62 | Complete
VWU-000572 | 4.4 | 2026-05-15 | PR-S10-03 | Prairie | CT-16 | Post-storm | 4.4 | 2026-06-03 | 2026-06-18 | 89553.18 | Complete
VWU-000573 | 5.6 | 2026-05-11 | PR-S15-04 | Prairie | CT-16 | Post-storm | 5.6 | 2026-06-03 | 2026-06-07 | 113566.63 | Complete
VWU-000574 | 12.5 | 2026-05-22 | BY-S13-06 | Bayou | CT-14 | Cycle | 12.5 | 2026-06-04 | 2026-06-22 | 160264.44 | Complete
VWU-000575 | 1.5 | 2026-05-13 | BY-S16-02 | Bayou | CT-15 | Post-storm | 1.5 | 2026-06-04 | 2026-06-07 | 28827.25 | Complete
VWU-000576 | 3.2 | 2026-05-16 | CR-S30-03 | Crossroads | CT-13 | Post-storm | 3.2 | 2026-06-04 | 2026-06-13 | 62662.38 | Complete
VWU-000577 | 12 | 2026-05-18 | HB-S13-02 | Harbor | CT-13 | Cycle | 12 | 2026-06-04 | 2026-06-24 | 98179.61 | Complete
VWU-000578 | 2.7 | 2026-05-10 | BY-S16-05 | Bayou | CT-15 | Post-storm | 2.7 | 2026-06-05 | 2026-06-14 | 53488.17 | Complete
VWU-000579 | 2.2 | 2026-05-20 | CR-S02-04 | Crossroads | CT-13 | Post-storm | 2.2 | 2026-06-05 | 2026-06-19 | 40759.06 | Complete
VWU-000580 | 16.3 | 2026-05-28 | HB-S19-03 | Harbor | CT-13 | Cycle | 16.3 | 2026-06-05 | 2026-07-03 | 170730.43 | Complete
VWU-000581 | 3.8 | 2026-05-26 | BY-S09-05 | Bayou | CT-14 | Post-storm | 3.8 | 2026-06-06 | 2026-06-17 | 92628.06 | Complete
VWU-000582 | 2.4 | 2026-05-09 | CR-S16-02 | Crossroads | CT-13 | Post-storm | 2.4 | 2026-06-06 | 2026-06-15 | 51570.21 | Complete
VWU-000583 | 5.6 | 2026-05-25 | HB-S17-02 | Harbor | CT-13 | Cycle | 5.6 | 2026-06-06 | 2026-06-16 | 48107.43 | Complete
VWU-000584 | 4.7 | 2026-05-14 | PR-S19-02 | Prairie | CT-16 | Post-storm | 4.7 | 2026-06-08 | 2026-06-11 | 102861.98 | Complete
VWU-000585 | 6.9 | 2026-05-13 | PR-S19-04 | Prairie | CT-16 | Post-storm | 6.9 | 2026-06-08 | 2026-06-13 | 142707.07 | Complete
VWU-000586 | 1.3 | 2026-05-14 | BY-S13-01 | Bayou | CT-15 | Post-storm | 1.3 | 2026-06-09 | 2026-06-18 | 26459.29 | Complete
VWU-000587 | 5.6 | 2026-05-30 | BY-S16-01 | Bayou | CT-15 | Post-storm | 5.6 | 2026-06-09 | 2026-06-20 | 124932.62 | Complete
VWU-000588 | 3.9 | 2026-05-24 | CR-S08-06 | Crossroads | CT-13 | Post-storm | 3.9 | 2026-06-09 | 2026-06-12 | 82444.55 | Complete
VWU-000589 | 7.2 | 2026-05-12 | CR-S22-02 | Crossroads | CT-13 | Post-storm | 7.2 | 2026-06-09 | 2026-06-17 | 151760.65 | Complete
VWU-000590 | 4.4 | 2026-05-31 | BY-S22-04 | Bayou | CT-15 | Post-storm | 4.4 | 2026-06-10 | 2026-06-16 | 105215.11 | Complete
VWU-000591 | 14.8 | 2026-05-23 | BY-S21-01 | Bayou | CT-14 | Cycle | 14.8 | 2026-06-11 | 2026-07-04 | 195760.45 | Complete
VWU-000592 | 12.7 | 2026-05-26 | CR-S06-01 | Crossroads | CT-13 | Cycle | 12.7 | 2026-06-11 | 2026-07-05 | 100700.63 | Complete
VWU-000593 | 7.5 | 2026-06-02 | CR-S08-05 | Crossroads | CT-13 | Post-storm | 7.5 | 2026-06-11 | 2026-06-15 | 166352.82 | Complete
VWU-000594 | 12.9 | 2026-06-01 | PR-S20-02 | Prairie | CT-16 | Cycle | 12.9 | 2026-06-11 | 2026-07-04 | 91105.98 | Complete
VWU-000595 | 4.3 | 2026-05-20 | CR-S15-03 | Crossroads | CT-13 | Post-storm | 4.3 | 2026-06-12 | 2026-06-26 | 80319.2 | Complete
VWU-000596 | 13.7 | 2026-05-31 | PR-S18-02 | Prairie | CT-16 | Cycle | 13.7 | 2026-06-12 | 2026-07-09 | 95649.26 | Complete
VWU-000597 | 4.5 | 2026-05-30 | BY-S14-03 | Bayou | CT-14 | Cycle | 4.5 | 2026-06-13 | 2026-06-25 | 45326.5 | Complete
VWU-000598 | 6.4 | 2026-05-24 | BY-S18-06 | Bayou | CT-14 | Post-storm | 6.4 | 2026-06-13 | 2026-06-17 | 124975.16 | Complete
VWU-000599 | 9.3 | 2026-05-25 | CR-S22-01 | Crossroads | CT-13 | Cycle | 9.3 | 2026-06-13 | 2026-07-02 | 85597.57 | Complete
VWU-000600 | 6.1 | 2026-05-22 | PR-S06-02 | Prairie | CT-16 | Post-storm | 6.1 | 2026-06-13 | 2026-06-17 | 118615.18 | Complete
VWU-000601 | 5.2 | 2026-06-07 | BY-S27-04 | Bayou | CT-14 | Cycle | 5.2 | 2026-06-14 | 2026-06-25 | 62108.12 | Complete
VWU-000602 | 11.8 | 2026-05-29 | PR-S13-03 | Prairie | CT-16 | Cycle | 11.8 | 2026-06-14 | 2026-07-05 | 77066.61 | Complete
VWU-000603 | 12.5 | 2026-05-27 | CR-S11-01 | Crossroads | CT-13 | Resiliency acceleration | 12.5 | 2026-06-16 | 2026-07-06 | 139031.52 | Complete
VWU-000604 | 7.7 | 2026-05-27 | CR-S19-02 | Crossroads | CT-13 | Cycle | 7.7 | 2026-06-16 | 2026-07-01 | 68870.32 | Complete
VWU-000605 | 2.2 | 2026-05-23 | BY-S24-03 | Bayou | CT-14 | Customer request batch | 2.2 | 2026-06-17 | 2026-06-21 | 31194.94 | Complete
VWU-000606 | 7.6 | 2026-06-03 | PR-S15-02 | Prairie | CT-16 | Cycle | 7.6 | 2026-06-18 | 2026-07-02 | 54189.25 | Complete
VWU-000607 | 9.1 | 2026-05-24 | CR-S01-02 | Crossroads | CT-13 | Cycle | 9.1 | 2026-06-19 | 2026-07-06 | 84014.91 | Complete
VWU-000608 | 5.7 | 2026-06-12 | CR-S17-01 | Crossroads | CT-13 | Cycle | 5.7 | 2026-06-19 | 2026-07-01 | 55735.4 | Complete
VWU-000609 | 8.2 | 2026-06-03 | CR-S27-04 | Crossroads | CT-13 | Cycle | 8.2 | 2026-06-19 | 2026-07-06 | 79611.99 | Complete
VWU-000610 | 2.3 | 2026-06-07 | BY-S07-01 | Bayou | CT-15 | Customer request batch | 2.3 | 2026-06-20 | 2026-06-27 | 29894.47 | Complete
VWU-000611 | 5.7 | 2026-06-05 | BY-S23-03 | Bayou | CT-15 | Hot spot | 5.7 | 2026-06-20 | 2026-06-23 | 87182.26 | Complete
VWU-000612 | 6.2 | 2026-06-10 | HB-S07-04 | Harbor | CT-13 | Cycle | 6.2 | 2026-06-21 | 2026-07-03 | 60628.88 | Complete
VWU-000613 | 5.5 | 2026-05-26 | BY-S21-05 | Bayou | CT-14 | Hot spot | 5.5 | 2026-06-22 | 2026-06-27 | 88490.22 | Complete
VWU-000614 | 5.5 | 2026-05-31 | HB-S06-03 | Harbor | CT-13 | Cycle | 5.5 | 2026-06-22 | 2026-07-04 | 57880.69 | Complete
VWU-000615 | 1.3 | 2026-06-06 | PR-S01-04 | Prairie | CT-16 | Customer request batch | 1.3 | 2026-06-22 | 2026-06-30 | 20269.15 | Complete
VWU-000616 | 3.3 | 2026-05-27 | CR-S30-05 | Crossroads | CT-13 | Cycle | 3.3 | 2026-06-23 | 2026-06-30 | 29658.7 | Complete
VWU-000617 | 7.6 | 2026-05-29 | CR-S13-01 | Crossroads | CT-13 | Cycle | 7.6 | 2026-06-24 | 2026-07-08 | 68548.57 | Complete
VWU-000618 | 7 | 2026-06-17 | CR-S15-03 | Crossroads | CT-13 | Cycle | 7 | 2026-06-26 | 2026-07-13 | 56134.45 | Complete
VWU-000619 | 1.3 | 2026-06-16 | BY-S06-02 | Bayou | CT-14 | Customer request batch | 1.3 | 2026-06-27 | 2026-07-05 | 18576.56 | Complete
VWU-000620 | 4.6 | 2026-06-06 | BY-S29-01 | Bayou | CT-15 | Cycle | 4.6 | 2026-06-27 | 2026-07-07 | 55162.25 | Complete
VWU-000621 | 1.8 | 2026-06-11 | HB-S06-01 | Harbor | CT-13 | Hot spot | 1.8 | 2026-06-27 | 2026-07-01 | 31419.7 | Complete
VWU-000622 | 15 | 2026-06-13 | HB-S03-01 | Harbor | CT-13 | Resiliency acceleration | 15 | 2026-06-28 | 2026-07-26 | 172810.63 | Complete
VWU-000623 | 3.2 | 2026-06-21 | BY-S15-06 | Bayou | CT-15 | Hot spot | 3.2 | 2026-06-30 | 2026-07-04 | 56920.73 | Complete
VWU-000624 | 1.4 | 2026-06-22 | BY-S17-01 | Bayou | CT-15 | Hot spot | 1.4 | 2026-06-30 | 2026-07-03 | 20527.68 | Complete
VWU-000625 | 1.9 | 2026-06-12 | BY-S20-03 | Bayou | CT-14 | Customer request batch | 1.9 | 2026-07-01 | 2026-07-09 | 26368.9 | Complete
VWU-000626 | 5.2 | 2026-06-04 | BY-S28-03 | Bayou | CT-15 | Cycle | 5.2 | 2026-07-01 | 2026-07-13 | 64911.03 | Complete
VWU-000627 | 1.8 | 2026-06-05 | BY-S13-06 | Bayou | CT-15 | Cycle | 1.8 | 2026-07-02 | 2026-07-08 | 21861.83 | Complete
VWU-000628 | 5.1 | 2026-06-19 | BY-S18-01 | Bayou | CT-15 | Hot spot | 5.1 | 2026-07-02 | 2026-07-04 | 93941.37 | Complete
VWU-000629 | 11.2 | 2026-06-22 | CR-S05-02 | Crossroads | CT-13 | Cycle | 11.2 | 2026-07-02 | 2026-07-21 | 88209.36 | Complete
VWU-000630 | 11.1 | 2026-06-23 | CR-S20-03 | Crossroads | CT-13 | Cycle | 11.1 | 2026-07-02 | 2026-07-27 | 105098.02 | Complete
VWU-000631 | 18.8 | 2026-06-25 | BY-S03-02 | Bayou | CT-15 | Resiliency acceleration | 18.8 | 2026-07-03 | 2026-08-08 | 206192.56 | Complete
VWU-000632 | 10.6 | 2026-06-20 | HB-S04-01 | Harbor | CT-13 | Cycle | 10.6 | 2026-07-03 | 2026-07-21 | 87859.53 | Complete
VWU-000633 | 4.3 | 2026-06-10 | PR-S07-05 | Prairie | CT-16 | Cycle | 4.3 | 2026-07-03 | 2026-07-13 | 36184.64 | Complete
VWU-000634 | 16.6 | 2026-06-10 | PR-S18-02 | Prairie | CT-16 | Cycle | 16.6 | 2026-07-04 | 2026-07-28 | 130190.54 | Complete
VWU-000635 | 2.9 | 2026-06-27 | HB-S03-03 | Harbor | CT-13 | Hot spot | 2.9 | 2026-07-05 | 2026-07-13 | 45889.1 | Complete
VWU-000636 | 0.6 | 2026-06-10 | HB-S20-04 | Harbor | CT-13 | Customer request batch | 0.6 | 2026-07-05 | 2026-07-13 | 9786.85 | Complete
VWU-000637 | 1.5 | 2026-06-09 | PR-S07-05 | Prairie | CT-16 | Customer request batch | 1.5 | 2026-07-05 | 2026-07-15 | 21269.81 | Complete
VWU-000638 | 6 | 2026-06-09 | BY-S08-02 | Bayou | CT-14 | Hot spot | 6 | 2026-07-06 | 2026-07-15 | 100928.12 | Complete
VWU-000639 | 11.2 | 2026-06-29 | PR-S09-01 | Prairie | CT-16 | Cycle | 11.2 | 2026-07-08 | 2026-08-02 | 79897.83 | Complete
VWU-000640 | 6.7 | 2026-06-15 | BY-S25-04 | Bayou | CT-15 | Cycle | 6.7 | 2026-07-09 | 2026-07-25 | 83819.44 | Complete
VWU-000641 | 20.1 | 2026-06-29 | PR-S14-04 | Prairie | CT-16 | Cycle | 20.1 | 2026-07-09 | 2026-08-12 | 148679.08 | Complete
VWU-000642 | 7.2 | 2026-06-23 | CR-S29-02 | Crossroads | CT-13 | Resiliency acceleration | 7.2 | 2026-07-10 | 2026-07-28 | 77206.14 | Complete
VWU-000643 | 8.3 | 2026-06-22 | PR-S18-01 | Prairie | CT-16 | Cycle | 8.3 | 2026-07-10 | 2026-07-27 | 60001.94 | Complete
VWU-000644 | 15 | 2026-07-02 | BY-S10-04 | Bayou | CT-15 | Cycle | 15 | 2026-07-12 | 2026-08-06 | 160734.41 | Complete
VWU-000645 | 3.4 | 2026-07-02 | BY-S13-05 | Bayou | CT-14 | Resiliency acceleration | 3.4 | 2026-07-12 | 2026-07-19 | 47339.46 | Complete
VWU-000646 | 11.2 | 2026-07-05 | BY-S18-05 | Bayou | CT-15 | Cycle | 11.2 | 2026-07-12 | 2026-07-31 | 122251.95 | Complete
VWU-000647 | 3.7 | 2026-07-03 | BY-S21-01 | Bayou | CT-14 | Cycle | 3.7 | 2026-07-14 | 2026-07-21 | 41053.01 | Complete
VWU-000648 | 4 | 2026-07-08 | BY-S15-06 | Bayou | CT-14 | Resiliency acceleration | 4 | 2026-07-15 | 2026-07-24 | 44697.85 | Complete
VWU-000649 | 9.1 | 2026-07-02 | HB-S07-02 | Harbor | CT-13 | Resiliency acceleration | 9.1 | 2026-07-15 | 2026-08-02 | 105234.09 | Complete
VWU-000650 | 4.6 | 2026-07-09 | CR-S08-02 | Crossroads | CT-13 | Cycle | 4.6 | 2026-07-16 | 2026-07-27 | 42410.78 | Complete
VWU-000651 | 11.3 | 2026-06-29 | CR-S20-01 | Crossroads | CT-13 | Cycle | 11.3 | 2026-07-16 | 2026-08-02 | 103480.9 | Complete
VWU-000652 | 12.6 | 2026-07-11 | HB-S13-01 | Harbor | CT-13 | Cycle | 12.6 | 2026-07-22 | 2026-08-17 | 133097.05 | Complete
VWU-000653 | 1.5 | 2026-06-28 | PR-S02-03 | Prairie | CT-16 | Customer request batch | 1.5 | 2026-07-23 | 2026-07-31 | 23673.1 | Complete
VWU-000654 | 1.1 | 2026-07-08 | BY-S29-01 | Bayou | CT-15 | Cycle | 1.1 | 2026-07-24 | 2026-07-29 | 14348.82 | Complete
VWU-000655 | 0.9 | 2026-07-05 | HB-S01-04 | Harbor | CT-13 | Customer request batch | 0.9 | 2026-07-24 | 2026-07-27 | 12541.23 | Complete
VWU-000656 | 10.5 | 2026-07-07 | CR-S13-05 | Crossroads | CT-13 | Cycle | 10.5 | 2026-07-25 | 2026-08-18 | 91675.39 | Complete
VWU-000657 | 5.8 | 2026-07-18 | CR-S18-01 | Crossroads | CT-13 | Cycle | 5.8 | 2026-07-25 | 2026-08-04 | 59027.33 | Complete
VWU-000658 | 12.9 | 2026-07-02 | PR-S01-04 | Prairie | CT-16 | Cycle | 12.9 | 2026-07-25 | 2026-08-25 | 83062.18 | Complete
VWU-000659 | 1.2 | 2026-06-30 | PR-S11-02 | Prairie | CT-16 | Customer request batch | 1.2 | 2026-07-25 | 2026-07-28 | 15214.96 | Complete
VWU-000660 | 3.3 | 2026-07-20 | BY-S18-04 | Bayou | CT-14 | Hot spot | 3.3 | 2026-07-28 | 2026-08-02 | 47770.53 | Complete
VWU-000661 | 2.6 | 2026-07-06 | CR-S29-02 | Crossroads | CT-13 | Hot spot | 2.6 | 2026-07-28 | 2026-08-05 | 40203.33 | Complete
VWU-000662 | 1.2 | 2026-07-21 | PR-S20-03 | Prairie | CT-16 | Customer request batch | 1.2 | 2026-07-28 | 2026-08-07 | 17881.25 | Complete
VWU-000663 | 16.3 | 2026-07-02 | BY-S18-05 | Bayou | CT-14 | Cycle | 16.3 | 2026-07-29 | 2026-08-28 | 174145.39 | Complete
VWU-000664 | 6.1 | 2026-07-12 | CR-S06-03 | Crossroads | CT-13 | Cycle | 6.1 | 2026-07-29 | 2026-08-11 | 62707.66 | Complete
VWU-000665 | 3.3 | 2026-07-17 | PR-S16-02 | Prairie | CT-16 | Hot spot | 3.3 | 2026-07-29 | 2026-08-02 | 58902.42 | Complete
VWU-000666 | 14.1 | 2026-07-12 | BY-S07-01 | Bayou | CT-15 | Resiliency acceleration | 18.1 | 2026-07-30 |  | 159837.46 | In progress
VWU-000667 | 12 | 2026-07-06 | BY-S17-04 | Bayou | CT-14 | Cycle | 12 | 2026-07-30 | 2026-08-28 | 126792.25 | Complete
VWU-000668 | 3.2 | 2026-07-08 | HB-S14-03 | Harbor | CT-13 | Hot spot | 3.2 | 2026-07-30 | 2026-08-04 | 53063.45 | Complete
VWU-000669 | 8 | 2026-07-13 | PR-S07-02 | Prairie | CT-16 | Cycle | 8 | 2026-07-30 | 2026-08-15 | 62341.46 | Complete
VWU-000670 | 2.1 | 2026-07-07 | PR-S13-05 | Prairie | CT-16 | Customer request batch | 2.1 | 2026-07-30 | 2026-08-07 | 32039.71 | Complete
VWU-000671 | 14.6 | 2026-07-14 | BY-S21-05 | Bayou | CT-15 | Cycle | 16.2 | 2026-07-31 |  | 171507.45 | In progress
VWU-000672 | 1.3 | 2026-07-05 | PR-S08-02 | Prairie | CT-16 | Customer request batch | 1.3 | 2026-07-31 | 2026-08-11 | 17540.85 | Complete
VWU-000673 | 9.4 | 2026-07-19 | HB-S08-05 | Harbor | CT-13 | Cycle | 9.4 | 2026-08-01 | 2026-08-23 | 97280.06 | Complete
VWU-000674 | 11.1 | 2026-07-17 | BY-S17-04 | Bayou | CT-15 | Cycle | 11.1 | 2026-08-02 | 2026-08-23 | 114560.25 | Complete
VWU-000675 | 3.9 | 2026-07-19 | BY-S09-01 | Bayou | CT-14 | Cycle | 3.9 | 2026-08-03 | 2026-08-13 | 39668.91 | Complete
VWU-000676 | 9.6 | 2026-07-22 | HB-S06-03 | Harbor | CT-13 | Cycle | 9.6 | 2026-08-03 | 2026-08-19 | 81715.18 | Complete
VWU-000677 | 7.9 | 2026-07-11 | HB-S19-01 | Harbor | CT-13 | Cycle | 7.9 | 2026-08-03 | 2026-08-23 | 78095.63 | Complete
VWU-000678 | 4 | 2026-07-06 | PR-S10-02 | Prairie | CT-16 | Hot spot | 4 | 2026-08-03 | 2026-08-05 | 69259.9 | Complete
VWU-000679 | 7.1 | 2026-07-20 | CR-S25-04 | Crossroads | CT-13 | Cycle | 7.1 | 2026-08-04 | 2026-08-18 | 70407.91 | Complete
VWU-000680 | 1.4 | 2026-07-25 | BY-S25-04 | Bayou | CT-15 | Customer request batch | 1.4 | 2026-08-05 | 2026-08-12 | 19143.29 | Complete
VWU-000681 | 4.2 | 2026-07-21 | HB-S01-01 | Harbor | CT-13 | Resiliency acceleration | 4.2 | 2026-08-07 | 2026-08-15 | 40404.29 | Complete
VWU-000682 | 6.8 | 2026-07-14 | PR-S17-02 | Prairie | CT-16 | Cycle | 6.8 | 2026-08-08 | 2026-08-20 | 56426.28 | Complete
VWU-000683 | 9.7 | 2026-07-29 | PR-S20-02 | Prairie | CT-16 | Cycle | 10.8 | 2026-08-10 |  | 79998.45 | In progress
VWU-000684 | 8.7 | 2026-08-04 | BY-S09-01 | Bayou | CT-15 | Cycle | 13 | 2026-08-11 |  | 99710 | In progress
VWU-000685 | 5 | 2026-08-07 | BY-S06-03 | Bayou | CT-14 | Cycle | 5 | 2026-08-14 | 2026-08-24 | 52896.35 | Complete
VWU-000686 | 6.7 | 2026-08-06 | HB-S07-04 | Harbor | CT-13 | Cycle | 7.4 | 2026-08-16 |  | 65435 | In progress
VWU-000687 | 6.2 | 2026-07-22 | PR-S03-06 | Prairie | CT-16 | Cycle | 6.2 | 2026-08-16 | 2026-08-31 | 51755.81 | Complete
VWU-000688 | 4.5 | 2026-08-07 | PR-S20-01 | Prairie | CT-16 | Hot spot | 4.5 | 2026-08-16 | 2026-08-25 | 78164.18 | Complete
VWU-000689 | 6.3 | 2026-07-30 | BY-S17-03 | Bayou | CT-15 | Resiliency acceleration | 6.3 | 2026-08-17 | 2026-08-30 | 82577.72 | Complete
VWU-000690 | 8.3 | 2026-07-23 | PR-S07-05 | Prairie | CT-16 | Cycle | 14.6 | 2026-08-18 |  | 66697.52 | In progress
VWU-000691 | 7.2 | 2026-07-29 | BY-S08-01 | Bayou | CT-14 | Cycle | 18.7 | 2026-08-19 |  | 87528.69 | In progress
VWU-000692 | 4.7 | 2026-08-07 | BY-S26-01 | Bayou | CT-14 | Cycle | 4.7 | 2026-08-19 | 2026-08-28 | 47011.89 | Complete
VWU-000693 | 6.3 | 2026-08-03 | BY-S14-02 | Bayou | CT-14 | Cycle | 11.5 | 2026-08-20 |  | 64349.01 | In progress
VWU-000694 | 1.8 | 2026-08-08 | BY-S24-03 | Bayou | CT-14 | Cycle | 1.8 | 2026-08-20 | 2026-08-25 | 21216.35 | Complete
VWU-000695 | 3.4 | 2026-08-08 | CR-S03-03 | Crossroads | CT-13 | Hot spot | 3.4 | 2026-08-20 | 2026-08-26 | 56593.67 | Complete
VWU-000696 | 3.9 | 2026-08-09 | BY-S05-01 | Bayou | CT-14 | Cycle | 13.4 | 2026-08-22 |  | 39808.43 | In progress
VWU-000697 | 4.7 | 2026-08-03 | PR-S18-06 | Prairie | CT-16 | Cycle | 20.4 | 2026-08-22 |  | 33713.82 | In progress
VWU-000698 | 3 | 2026-08-09 | BY-S18-05 | Bayou | CT-14 | Cycle | 15.1 | 2026-08-24 |  | 38784.02 | In progress
VWU-000699 | 2 | 2026-08-14 | PR-S09-01 | Prairie | CT-16 | Cycle | 3 | 2026-08-25 |  | 16398.52 | In progress
VWU-000700 | 1.3 | 2026-08-12 | PR-S03-06 | Prairie | CT-16 | Cycle | 2.2 | 2026-08-27 |  | 8593.45 | In progress
VWU-000701 | 1.8 | 2026-08-01 | PR-S03-06 | Prairie | CT-16 | Cycle | 15.8 | 2026-08-28 |  | 11390.68 | In progress
VWU-000702 | 1.6 | 2026-08-11 | PR-S12-03 | Prairie | CT-16 | Cycle | 8.5 | 2026-08-28 |  | 10085.71 | In progress
VWU-000703 | 1.1 | 2026-08-04 | BY-S03-02 | Bayou | CT-14 | Resiliency acceleration | 10 | 2026-08-29 |  | 13467.93 | In progress
VWU-000704 | 1 | 2026-08-19 | CR-S22-01 | Crossroads | CT-13 | Cycle | 4.8 | 2026-08-29 |  |  | In progress
VWU-000705 | 0 | 2026-08-12 | HB-S15-03 | Harbor | CT-13 | Cycle | 16.4 | 2026-08-31 |  | 0 | In progress
VWU-000706 |  | 2026-08-18 | HB-S16-01 | Harbor | CT-13 | Cycle | 4.7 |  |  | 0 | Scheduled
VWU-000707 |  | 2026-07-14 | BY-S12-04 | Bayou | CT-14 | Cycle | 5.4 |  |  | 0 | Scheduled
VWU-000708 |  | 2026-08-21 | PR-S20-02 | Prairie | CT-16 | Cycle | 10.3 |  |  | 0 | Scheduled
VWU-000709 |  | 2026-07-28 | BY-S26-01 | Bayou | CT-15 | Cycle | 2.1 |  |  | 0 | Scheduled
VWU-000710 |  | 2026-08-06 | BY-S29-01 | Bayou | CT-15 | Cycle | 10.6 |  |  | 0 | Scheduled
VWU-000711 |  | 2026-08-09 | CR-S23-01 | Crossroads | CT-13 | Cycle | 5.8 |  |  | 0 | Scheduled
VWU-000712 |  | 2026-07-05 | PR-S15-02 | Prairie | CT-16 | Cycle | 10.8 |  |  | 0 | Scheduled
VWU-000713 |  | 2026-08-25 | BY-S10-04 | Bayou | CT-15 | Cycle | 5 |  |  | 0 | Scheduled
VWU-000714 |  | 2026-07-18 | BY-S13-01 | Bayou | CT-15 | Cycle | 5 |  |  | 0 | Scheduled
VWU-000715 |  | 2026-07-24 | CR-S17-01 | Crossroads | CT-13 | Cycle | 4 |  |  | 0 | Scheduled
VWU-000716 |  | 2026-08-05 | PR-S18-02 | Prairie | CT-16 | Cycle | 7.6 |  |  | 0 | Scheduled
VWU-000717 |  | 2026-08-26 | BY-S24-05 | Bayou | CT-14 | Cycle | 6.7 |  |  | 0 | Scheduled
VWU-000718 |  | 2026-08-26 | CR-S07-04 | Crossroads | CT-13 | Cycle | 8.3 |  |  | 0 | Scheduled
VWU-000719 |  | 2026-08-10 | PR-S11-03 | Prairie | CT-16 | Cycle | 7.6 |  |  | 0 | Scheduled
VWU-000720 |  | 2026-08-12 | CR-S08-02 | Crossroads | CT-13 | Cycle | 6.3 |  |  | 0 | Scheduled
VWU-000721 |  | 2026-08-21 | CR-S22-01 | Crossroads | CT-13 | Cycle | 9.3 |  |  | 0 | Scheduled
VWU-000722 |  | 2026-08-15 | PR-S13-01 | Prairie | CT-16 | Cycle | 7 |  |  | 0 | Scheduled
VWU-000723 |  | 2026-07-10 | PR-S15-05 | Prairie | CT-16 | Cycle | 19.4 |  |  | 0 | Scheduled
VWU-000724 |  | 2026-07-24 | CR-S09-02 | Crossroads | CT-13 | Cycle | 11.5 |  |  | 0 | Scheduled
VWU-000725 |  | 2026-07-31 | BY-S16-05 | Bayou | CT-14 | Resiliency acceleration | 0.6 |  |  | 0 | Scheduled
VWU-000726 |  | 2026-07-29 | BY-S17-04 | Bayou | CT-15 | Cycle | 1.5 |  |  | 0 | Scheduled
VWU-000727 |  | 2026-07-04 | CR-S22-01 | Crossroads | CT-13 | Cycle | 18.5 |  |  | 0 | Scheduled
VWU-000728 |  | 2026-07-20 | BY-S21-05 | Bayou | CT-15 | Cycle | 9.6 |  |  | 0 | Scheduled
VWU-000729 |  | 2026-07-24 | HB-S13-01 | Harbor | CT-13 | Cycle | 4.6 |  |  | 0 | Scheduled
VWU-000730 |  | 2026-07-16 | BY-S16-05 | Bayou | CT-15 | Resiliency acceleration | 10.8 |  |  | 0 | Scheduled
VWU-000731 |  | 2026-08-14 | BY-S03-02 | Bayou | CT-15 | Resiliency acceleration | 14.1 |  |  | 0 | Scheduled
VWU-000732 |  | 2026-07-16 | BY-S17-03 | Bayou | CT-15 | Resiliency acceleration | 5.2 |  |  | 0 | Scheduled
VWU-000733 |  | 2026-08-10 | PR-S19-02 | Prairie | CT-16 | Cycle | 0.9 |  |  | 0 | Scheduled
VWU-000734 |  | 2026-08-15 | PR-S14-02 | Prairie | CT-16 | Cycle | 9.4 |  |  | 0 | Scheduled
VWU-000735 |  | 2026-07-25 | BY-S13-01 | Bayou | CT-14 | Cycle | 4.4 |  |  | 0 | Scheduled
VWU-000736 |  | 2026-08-21 | PR-S01-02 | Prairie | CT-16 | Cycle | 9.6 |  |  | 0 | Scheduled
VWU-000737 |  | 2026-08-27 | HB-S02-03 | Harbor | CT-13 | Resiliency acceleration | 11 |  |  | 0 | Scheduled
VWU-000738 |  | 2026-07-18 | HB-S18-04 | Harbor | CT-13 | Cycle | 12.4 |  |  | 0 | Scheduled
VWU-000739 |  | 2026-07-15 | PR-S13-01 | Prairie | CT-16 | Cycle | 6.1 |  |  | 0 | Scheduled
VWU-000740 |  | 2026-07-14 | CR-S09-01 | Crossroads | CT-13 | Resiliency acceleration | 0.9 |  |  | 0 | Scheduled
VWU-000741 |  | 2026-07-25 | CR-S20-03 | Crossroads | CT-13 | Cycle | 6.8 |  |  | 0 | Scheduled
VWU-000742 |  | 2026-07-18 | PR-S18-01 | Prairie | CT-16 | Cycle | 8.8 |  |  | 0 | Scheduled
VWU-000743 |  | 2026-07-29 | BY-S10-05 | Bayou | CT-14 | Cycle | 14.4 |  |  | 0 | Scheduled
VWU-000744 |  | 2026-07-15 | BY-S21-05 | Bayou | CT-14 | Cycle | 4.3 |  |  | 0 | Scheduled
VWU-000745 |  | 2026-08-14 | BY-S09-03 | Bayou | CT-15 | Cycle | 20.7 |  |  | 0 | Scheduled
VWU-000746 |  | 2026-07-18 | BY-S30-03 | Bayou | CT-15 | Cycle | 15.7 |  |  | 0 | Scheduled
VWU-000747 |  | 2026-08-16 | HB-S08-02 | Harbor | CT-13 | Cycle | 7.6 |  |  | 0 | Scheduled
VWU-000748 |  | 2026-08-15 | CR-S16-04 | Crossroads | CT-13 | Cycle | 11.5 |  |  | 0 | Scheduled
VWU-000749 |  | 2026-07-16 | CR-S13-01 | Crossroads | CT-13 | Cycle | 13.4 |  |  | 0 | Scheduled
VWU-000750 |  | 2026-08-04 | PR-S01-05 | Prairie | CT-16 | Cycle | 1.3 |  |  | 0 | Scheduled
VWU-000751 |  | 2026-07-13 | PR-S19-02 | Prairie | CT-16 | Cycle | 11.2 |  |  | 0 | Scheduled
VWU-000752 |  | 2026-08-13 | CR-S09-04 | Crossroads | CT-13 | Cycle | 6.6 |  |  | 0 | Scheduled
VWU-000753 |  | 2026-07-23 | CR-S25-03 | Crossroads | CT-13 | Cycle | 5.1 |  |  | 0 | Scheduled
VWU-000754 |  | 2026-08-07 | CR-S25-01 | Crossroads | CT-13 | Cycle | 4.1 |  |  | 0 | Scheduled
VWU-000755 |  | 2026-07-06 | BY-S19-04 | Bayou | CT-15 | Resiliency acceleration | 10.4 |  |  | 0 | Scheduled
VWU-000756 |  | 2026-07-08 | CR-S22-04 | Crossroads | CT-13 | Cycle | 0.9 |  |  | 0 | Scheduled
VWU-000757 |  | 2026-07-27 | BY-S05-01 | Bayou | CT-15 | Cycle | 19.9 |  |  | 0 | Scheduled
VWU-000758 |  | 2026-08-31 | HB-S20-03 | Harbor | CT-13 | Cycle | 5.5 |  |  | 0 | Scheduled
VWU-000759 |  | 2026-07-30 | CR-S11-01 | Crossroads | CT-13 | Resiliency acceleration | 6.7 |  |  | 0 | Scheduled
VWU-000760 |  | 2026-08-01 | PR-S17-01 | Prairie | CT-16 | Cycle | 21.1 |  |  | 0 | Scheduled
VWU-000761 |  | 2026-07-06 | CR-S17-01 | Crossroads | CT-13 | Cycle | 7 |  |  | 0 | Scheduled
VWU-000762 |  | 2026-08-07 | BY-S23-03 | Bayou | CT-15 | Cycle | 14.2 |  |  | 0 | Scheduled
VWU-000763 |  | 2026-08-05 | CR-S09-05 | Crossroads | CT-13 | Cycle | 5.5 |  |  | 0 | Scheduled
VWU-000764 |  | 2026-07-04 | HB-S13-01 | Harbor | CT-13 | Cycle | 4.7 |  |  | 0 | Scheduled
VWU-000765 |  | 2026-08-29 | HB-S17-02 | Harbor | CT-13 | Cycle | 20.7 |  |  | 0 | Scheduled
VWU-000766 |  | 2026-07-08 | BY-S05-01 | Bayou | CT-15 | Cycle | 12.5 |  |  | 0 | Scheduled
VWU-000767 |  | 2026-08-25 | PR-S01-05 | Prairie | CT-16 | Cycle | 20.2 |  |  | 0 | Scheduled
VWU-000768 |  | 2026-08-13 | PR-S05-02 | Prairie | CT-16 | Cycle | 13.4 |  |  | 0 | Scheduled
VWU-000769 |  | 2026-07-02 | BY-S10-04 | Bayou | CT-14 | Cycle | 8.7 |  |  | 0 | Scheduled
VWU-000770 |  | 2026-08-31 | BY-S23-04 | Bayou | CT-15 | Cycle | 6.3 |  |  | 0 | Scheduled
VWU-000771 |  | 2026-07-05 | CR-S16-02 | Crossroads | CT-13 | Cycle | 11 |  |  | 0 | Scheduled
VWU-000772 |  | 2026-08-20 | BY-S15-06 | Bayou | CT-15 | Resiliency acceleration | 14.3 |  |  | 0 | Scheduled
VWU-000773 |  | 2026-07-16 | HB-S03-02 | Harbor | CT-13 | Cycle | 13.3 |  |  | 0 | Scheduled
VWU-000774 |  | 2026-07-06 | CR-S04-01 | Crossroads | CT-13 | Cycle | 12.5 |  |  | 0 | Scheduled
VWU-000775 |  | 2026-08-23 | BY-S10-04 | Bayou | CT-15 | Cycle | 8.2 |  |  | 0 | Scheduled
VWU-000776 |  | 2026-07-29 | BY-S05-01 | Bayou | CT-15 | Cycle | 1.2 |  |  | 0 | Scheduled
VWU-000777 |  | 2026-08-25 | CR-S22-04 | Crossroads | CT-13 | Cycle | 14.2 |  |  | 0 | Scheduled
VWU-000778 |  | 2026-07-02 | HB-S07-05 | Harbor | CT-13 | Cycle | 17.7 |  |  | 0 | Scheduled
VWU-000779 |  | 2026-07-16 | PR-S18-02 | Prairie | CT-16 | Cycle | 4.2 |  |  | 0 | Scheduled
VWU-000780 |  | 2026-07-05 | PR-S01-05 | Prairie | CT-16 | Cycle | 12.4 |  |  | 0 | Scheduled
VWU-000781 |  | 2026-08-27 | PR-S19-02 | Prairie | CT-16 | Cycle | 5.7 |  |  | 0 | Scheduled
VWU-000782 |  | 2026-08-13 | BY-S12-03 | Bayou | CT-15 | Cycle | 8.6 |  |  | 0 | Scheduled
VWU-000783 |  | 2026-07-06 | HB-S14-01 | Harbor | CT-13 | Cycle | 11.9 |  |  | 0 | Scheduled
VWU-000784 |  | 2026-07-27 | BY-S18-05 | Bayou | CT-14 | Cycle | 10.2 |  |  | 0 | Scheduled
VWU-000785 |  | 2026-08-10 | CR-S30-06 | Crossroads | CT-13 | Cycle | 3.9 |  |  | 0 | Scheduled
VWU-000786 |  | 2026-07-05 | HB-S07-02 | Harbor | CT-13 | Resiliency acceleration | 12 |  |  | 0 | Scheduled
VWU-000787 |  | 2026-08-17 | PR-S17-01 | Prairie | CT-16 | Cycle | 10.5 |  |  | 0 | Scheduled
VWU-000788 |  | 2026-08-14 | HB-S19-03 | Harbor | CT-13 | Cycle | 4 |  |  | 0 | Scheduled
VWU-000789 |  | 2026-07-01 | BY-S14-03 | Bayou | CT-15 | Cycle | 9.7 |  |  | 0 | Scheduled
VWU-000790 |  | 2026-07-13 | BY-S06-02 | Bayou | CT-14 | Cycle | 19.1 |  |  | 0 | Scheduled
VWU-000791 |  | 2026-08-13 | BY-S03-01 | Bayou | CT-15 | Cycle | 10.3 |  |  | 0 | Scheduled
VWU-000792 |  | 2026-08-03 | HB-S19-01 | Harbor | CT-13 | Cycle | 12.3 |  |  | 0 | Scheduled
VWU-000793 |  | 2026-08-06 | HB-S11-03 | Harbor | CT-13 | Cycle | 11.8 |  |  | 0 | Scheduled
VWU-000794 |  | 2026-08-09 | CR-S07-01 | Crossroads | CT-13 | Cycle | 11.7 |  |  | 0 | Scheduled
VWU-000795 |  | 2026-07-24 | CR-S25-01 | Crossroads | CT-13 | Cycle | 13.5 |  |  | 0 | Scheduled
VWU-000796 |  | 2026-08-02 | BY-S07-04 | Bayou | CT-15 | Cycle | 10.6 |  |  | 0 | Scheduled
VWU-000797 |  | 2026-08-16 | PR-S01-02 | Prairie | CT-16 | Cycle | 5.2 |  |  | 0 | Scheduled
VWU-000798 |  | 2026-07-30 | HB-S11-03 | Harbor | CT-13 | Cycle | 13.5 |  |  | 0 | Scheduled
VWU-000799 |  | 2026-08-25 | BY-S29-01 | Bayou | CT-14 | Cycle | 14.4 |  |  | 0 | Scheduled
VWU-000800 |  | 2026-07-19 | BY-S07-01 | Bayou | CT-15 | Resiliency acceleration | 8 |  |  | 0 | Scheduled
VWU-000801 |  | 2026-07-20 | PR-S13-04 | Prairie | CT-16 | Resiliency acceleration | 17.9 |  |  | 0 | Scheduled
VWU-000802 |  | 2026-07-24 | HB-S01-01 | Harbor | CT-13 | Resiliency acceleration | 12.9 |  |  | 0 | Scheduled
VWU-000803 |  | 2026-08-07 | HB-S03-01 | Harbor | CT-13 | Resiliency acceleration | 3.7 |  |  | 0 | Scheduled