## Slide 1
Resiliency Plan Year 1 Checkpoint: August 2026
Resiliency Plan year 1 checkpoint, September 17, 2026. Progress, spend and issues for the nine approved measures at August 31, 2026. Presented by the Resiliency Program Manager.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 1

## Slide 2
The plan
Approved by the PUCT on October 23, 2025: nine measures, about $612 million of capital and $41 million of O&M over 2026-2028. We filed on April 28, 2025 proposing about $890 million; the approved plan removed two measures and reduced undergrounding.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 2

## Slide 3
Progress: poles, trimming, automation, undergrounding
Units completed against 2026 targets at August 31 (units differ by measure):
Pole replacement and bracing: 3,020 of 4,200 poles
Vegetation cycle acceleration: 188.6 of 330 circuit miles
Feeder automation (IGSD): 115 of 180 devices
Strategic undergrounding: 8 of 21 circuit miles
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 3

## Slide 4
Progress: substations, cable, transmission, monitoring
Substation flood mitigation: 0 of 2 substations (both in construction)
URD cable replacement: 26 of 38 cable miles
Transmission structure hardening: 84 of 160 structures
Weather stations and damage model: 14 of 14 stations
Substation physical security: 1 of 4 sites
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 4

## Slide 5
Spend
January-August: $109.0 million of capital and $3.37 million of O&M. 2026 capital budget $196 million; forecast $180 million, mainly because undergrounding is forecast at $26 million against $42 million.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 5

## Slide 6
Monthly resiliency capital
Capital recorded against the nine measures by month, January-August 2026.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 6

## Slide 7
Monthly resiliency capital · USD
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 7
Chart: 
| 2026-01 | 2026-02 | 2026-03 | 2026-04 | 2026-05 | 2026-06 | 2026-07 | 2026-08
capital_usd | 11463297.32 | 12380970.94 | 12534801.7 | 13064998.38 | 12636961.33 | 14355252.35 | 15897110.91 | 16666607.07

## Slide 8
Issue: undergrounding behind plan
Permitting and design took longer than assumed, and two projects were re-scoped to shorter crossings in July. Those two now show forecast in-service dates earlier than baseline because of the smaller scope.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 8
Notes: Asking the steering group to accept the lower 2026 undergrounding forecast and re-phase miles into 2027.

## Slide 9
Vegetation acceleration
In-scope Bayou and Prairie feeders move to a three-year cycle. 188.6 of 330 acceleration miles and 1,740.9 of 2,650 cycle miles done or in progress.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 9

## Slide 10
Reporting and next plan
First-half progress report filed June 26, 2026; second-half report due December 31. The PUCT must decide a complete plan within 180 days, and an updated plan cannot take effect earlier than three years after the prior approval.
Sedgewater Energy Holdings | Resiliency Program Office | 2026-09-17 | 10