## Read me
Gas System Inventory and 2026 Leak Survey Plan
Sedgewater Energy Holdings
Effective date | 2026-09-10
Purpose | Provide main and service inventory by material and decade and the 2026 leak survey plan status.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | Workbook of the gas main and service inventory at December 31, 2025 and the leak survey areas with 2026 status at August 31, 2026. Prepared by Gas Engineering for the steel replacement review and survey planning.
Sheets | Data 1 - main miles, services and 2025 leak repairs by district, material and installation decade (year-end 2025).
Sheets | Data 2 - leak survey areas: survey type, main miles, last survey, next due date, 2026 plan flag and 2026 completion date.
Sheets | Summary - formula totals of each numeric column.
Different dates | The inventory is at December 31, 2025; the survey status is at August 31, 2026. Mileage replaced in 2026 is not yet reflected in the inventory.
Inventory | 4,980 miles of main: polyethylene 3,720, coated and protected steel 1,172, unprotected steel 84 and other plastic 4, with 251,000 services. 914 leaks on mains and services were repaired in 2025. The unprotected steel program aims to remove it by the end of 2029; the 2026 target is 22 miles and 2,400 steel services.
2026 leak surveys | 160 of 519 survey areas are scheduled for 2026. At August 31, 138 were complete (1,027.5 of 1,261.8 main miles), including all 70 business-district areas, and no area was past its due date.
2026 leak surveys | Business districts are surveyed every year, unprotected steel areas every three years and other areas every five years. Federal rules require business-district surveys at intervals not exceeding 15 months and at least once each calendar year, and other areas at least once every five calendar years at intervals not exceeding 63 months.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Gas mains and services by district, material and decade (2025-12-31) | main_miles | miles | 4980 | 41.5 | 120 | 2025-12-31 | 2025-12-31
Gas mains and services by district, material and decade (2025-12-31) | services | services | 251000 | 2091.6667 | 120 | 2025-12-31 | 2025-12-31
Gas mains and services by district, material and decade (2025-12-31) | leaks_repaired_2025 | leaks | 914 | 7.6167 | 120 | 2025-12-31 | 2025-12-31
Leak survey areas and 2026 plan | main_miles | miles | 4980 | 9.5954 | 519 | 2026-01-01 | 2026-08-31

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Gas mains and services by district, material and decade (2025-12-31) | record_id | GI-0001 |  | id
Gas mains and services by district, material and decade (2025-12-31) | main_miles | Main miles | miles | number
Gas mains and services by district, material and decade (2025-12-31) | services | Service lines | services | integer
Gas mains and services by district, material and decade (2025-12-31) | leaks_repaired_2025 | Leaks repaired 2025 | leaks | integer
Gas mains and services by district, material and decade (2025-12-31) | district | Gas district |  | category
Gas mains and services by district, material and decade (2025-12-31) | material | Material |  | category
Gas mains and services by district, material and decade (2025-12-31) | install_decade | Install decade |  | category
Leak survey areas and 2026 plan | area_code | LS-0001 |  | id
Leak survey areas and 2026 plan | main_miles | Main miles in area | miles | number
Leak survey areas and 2026 plan | district | Gas district |  | category
Leak survey areas and 2026 plan | survey_type | Interval basis |  | category
Leak survey areas and 2026 plan | last_survey_date | Previous survey |  | date
Leak survey areas and 2026 plan | due_date | Required by (ISO date string; may be future) |  | category
Leak survey areas and 2026 plan | planned_2026 | In 2026 plan |  | category
Leak survey areas and 2026 plan | completed_date | 2026 completion |  | date

## Data 1
record_id | main_miles | services | leaks_repaired_2025 | district | material | install_decade
GI-0001 | 0 | 0 | 0 | Crossroads | Polyethylene | pre-1960
GI-0002 | 0 | 0 | 0 | Crossroads | Polyethylene | 1960s
GI-0003 | 14.3 | 810 | 3 | Crossroads | Polyethylene | 1970s
GI-0004 | 85.6 | 4846 | 15 | Crossroads | Polyethylene | 1980s
GI-0005 | 199.8 | 11311 | 24 | Crossroads | Polyethylene | 1990s
GI-0006 | 428.1 | 24236 | 37 | Crossroads | Polyethylene | 2000s
GI-0007 | 456.6 | 25850 | 28 | Crossroads | Polyethylene | 2010s
GI-0008 | 242.6 | 13735 | 9 | Crossroads | Polyethylene | 2020s
GI-0009 | 10.4 | 471 | 9 | Crossroads | Coated steel - protected | pre-1960
GI-0010 | 46.8 | 2120 | 36 | Crossroads | Coated steel - protected | 1960s
GI-0011 | 78 | 3533 | 46 | Crossroads | Coated steel - protected | 1970s
GI-0012 | 72.8 | 3297 | 30 | Crossroads | Coated steel - protected | 1980s
GI-0013 | 36.4 | 1649 | 10 | Crossroads | Coated steel - protected | 1990s
GI-0014 | 10.4 | 471 | 2 | Crossroads | Coated steel - protected | 2000s
GI-0015 | 5.2 | 235 | 1 | Crossroads | Coated steel - protected | 2010s
GI-0016 | 0 | 0 | 0 | Crossroads | Coated steel - protected | 2020s
GI-0017 | 1.8 | 82 | 4 | Crossroads | Unprotected steel | pre-1960
GI-0018 | 1.2 | 54 | 2 | Crossroads | Unprotected steel | 1960s
GI-0019 | 0 | 0 | 0 | Crossroads | Unprotected steel | 1970s
GI-0020 | 0 | 0 | 0 | Crossroads | Unprotected steel | 1980s
GI-0021 | 0 | 0 | 0 | Crossroads | Unprotected steel | 1990s
GI-0022 | 0 | 0 | 0 | Crossroads | Unprotected steel | 2000s
GI-0023 | 0 | 0 | 0 | Crossroads | Unprotected steel | 2010s
GI-0024 | 0 | 0 | 0 | Crossroads | Unprotected steel | 2020s
GI-0025 | 0 | 0 | 0 | Crossroads | Other plastic | pre-1960
GI-0026 | 0 | 0 | 0 | Crossroads | Other plastic | 1960s
GI-0027 | 0 | 0 | 0 | Crossroads | Other plastic | 1970s
GI-0028 | 0 | 0 | 0 | Crossroads | Other plastic | 1980s
GI-0029 | 0 | 0 | 0 | Crossroads | Other plastic | 1990s
GI-0030 | 0 | 0 | 0 | Crossroads | Other plastic | 2000s
GI-0031 | 0 | 0 | 0 | Crossroads | Other plastic | 2010s
GI-0032 | 0 | 0 | 0 | Crossroads | Other plastic | 2020s
GI-0033 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | pre-1960
GI-0034 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 1960s
GI-0035 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 1970s
GI-0036 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 1980s
GI-0037 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 1990s
GI-0038 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 2000s
GI-0039 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 2010s
GI-0040 | 0 | 0 | 0 | Crossroads | Cast or wrought iron | 2020s
GI-0041 | 0 | 0 | 0 | Bayou | Polyethylene | pre-1960
GI-0042 | 0 | 0 | 0 | Bayou | Polyethylene | 1960s
GI-0043 | 60.6 | 3360 | 14 | Bayou | Polyethylene | 1970s
GI-0044 | 333.1 | 18471 | 54 | Bayou | Polyethylene | 1980s
GI-0045 | 393.6 | 21826 | 46 | Bayou | Polyethylene | 1990s
GI-0046 | 363.4 | 20151 | 30 | Bayou | Polyethylene | 2000s
GI-0047 | 242.2 | 13431 | 14 | Bayou | Polyethylene | 2010s
GI-0048 | 121.1 | 6715 | 4 | Bayou | Polyethylene | 2020s
GI-0049 | 61.2 | 2715 | 29 | Bayou | Coated steel - protected | pre-1960
GI-0050 | 171.4 | 7604 | 70 | Bayou | Coated steel - protected | 1960s
GI-0051 | 183.6 | 8145 | 58 | Bayou | Coated steel - protected | 1970s
GI-0052 | 122.4 | 5430 | 27 | Bayou | Coated steel - protected | 1980s
GI-0053 | 55.1 | 2444 | 9 | Bayou | Coated steel - protected | 1990s
GI-0054 | 12.2 | 541 | 1 | Bayou | Coated steel - protected | 2000s
GI-0055 | 6.1 | 271 | 1 | Bayou | Coated steel - protected | 2010s
GI-0056 | 0 | 0 | 0 | Bayou | Coated steel - protected | 2020s
GI-0057 | 28.1 | 1247 | 35 | Bayou | Unprotected steel | pre-1960
GI-0058 | 22.9 | 1016 | 25 | Bayou | Unprotected steel | 1960s
GI-0059 | 0 | 0 | 0 | Bayou | Unprotected steel | 1970s
GI-0060 | 0 | 0 | 0 | Bayou | Unprotected steel | 1980s
GI-0061 | 0 | 0 | 0 | Bayou | Unprotected steel | 1990s
GI-0062 | 0 | 0 | 0 | Bayou | Unprotected steel | 2000s
GI-0063 | 0 | 0 | 0 | Bayou | Unprotected steel | 2010s
GI-0064 | 0 | 0 | 0 | Bayou | Unprotected steel | 2020s
GI-0065 | 0 | 0 | 0 | Bayou | Other plastic | pre-1960
GI-0066 | 0 | 0 | 0 | Bayou | Other plastic | 1960s
GI-0067 | 3 | 133 | 4 | Bayou | Other plastic | 1970s
GI-0068 | 0 | 0 | 0 | Bayou | Other plastic | 1980s
GI-0069 | 0 | 0 | 0 | Bayou | Other plastic | 1990s
GI-0070 | 0 | 0 | 0 | Bayou | Other plastic | 2000s
GI-0071 | 0 | 0 | 0 | Bayou | Other plastic | 2010s
GI-0072 | 0 | 0 | 0 | Bayou | Other plastic | 2020s
GI-0073 | 0 | 0 | 0 | Bayou | Cast or wrought iron | pre-1960
GI-0074 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 1960s
GI-0075 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 1970s
GI-0076 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 1980s
GI-0077 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 1990s
GI-0078 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 2000s
GI-0079 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 2010s
GI-0080 | 0 | 0 | 0 | Bayou | Cast or wrought iron | 2020s
GI-0081 | 0 | 0 | 0 | Prairie | Polyethylene | pre-1960
GI-0082 | 0 | 0 | 0 | Prairie | Polyethylene | 1960s
GI-0083 | 23.4 | 1004 | 6 | Prairie | Polyethylene | 1970s
GI-0084 | 155.8 | 6687 | 27 | Prairie | Polyethylene | 1980s
GI-0085 | 202.6 | 8696 | 25 | Prairie | Polyethylene | 1990s
GI-0086 | 202.5 | 8691 | 17 | Prairie | Polyethylene | 2000s
GI-0087 | 140.2 | 6018 | 9 | Prairie | Polyethylene | 2010s
GI-0088 | 54.5 | 2339 | 2 | Prairie | Polyethylene | 2020s
GI-0089 | 24 | 824 | 13 | Prairie | Coated steel - protected | pre-1960
GI-0090 | 72 | 2472 | 34 | Prairie | Coated steel - protected | 1960s
GI-0091 | 96 | 3296 | 35 | Prairie | Coated steel - protected | 1970s
GI-0092 | 66 | 2266 | 17 | Prairie | Coated steel - protected | 1980s
GI-0093 | 30 | 1030 | 6 | Prairie | Coated steel - protected | 1990s
GI-0094 | 9 | 309 | 1 | Prairie | Coated steel - protected | 2000s
GI-0095 | 3 | 103 | 0 | Prairie | Coated steel - protected | 2010s
GI-0096 | 0 | 0 | 0 | Prairie | Coated steel - protected | 2020s
GI-0097 | 15 | 515 | 24 | Prairie | Unprotected steel | pre-1960
GI-0098 | 15 | 515 | 20 | Prairie | Unprotected steel | 1960s
GI-0099 | 0 | 0 | 0 | Prairie | Unprotected steel | 1970s
GI-0100 | 0 | 0 | 0 | Prairie | Unprotected steel | 1980s
GI-0101 | 0 | 0 | 0 | Prairie | Unprotected steel | 1990s
GI-0102 | 0 | 0 | 0 | Prairie | Unprotected steel | 2000s
GI-0103 | 0 | 0 | 0 | Prairie | Unprotected steel | 2010s
GI-0104 | 0 | 0 | 0 | Prairie | Unprotected steel | 2020s
GI-0105 | 0 | 0 | 0 | Prairie | Other plastic | pre-1960
GI-0106 | 0 | 0 | 0 | Prairie | Other plastic | 1960s
GI-0107 | 1 | 35 | 1 | Prairie | Other plastic | 1970s
GI-0108 | 0 | 0 | 0 | Prairie | Other plastic | 1980s
GI-0109 | 0 | 0 | 0 | Prairie | Other plastic | 1990s
GI-0110 | 0 | 0 | 0 | Prairie | Other plastic | 2000s
GI-0111 | 0 | 0 | 0 | Prairie | Other plastic | 2010s
GI-0112 | 0 | 0 | 0 | Prairie | Other plastic | 2020s
GI-0113 | 0 | 0 | 0 | Prairie | Cast or wrought iron | pre-1960
GI-0114 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 1960s
GI-0115 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 1970s
GI-0116 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 1980s
GI-0117 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 1990s
GI-0118 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 2000s
GI-0119 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 2010s
GI-0120 | 0 | 0 | 0 | Prairie | Cast or wrought iron | 2020s

## Data 2
area_code | main_miles | district | survey_type | last_survey_date | due_date | planned_2026 | completed_date
LS-0001 | 6.5 | Crossroads | Business district - annual | 2025-04-10 | 2026-07-10 | Yes | 2026-05-28
LS-0002 | 5.8 | Crossroads | Business district - annual | 2025-10-06 | 2026-12-31 | Yes | 2026-03-30
LS-0003 | 5.6 | Crossroads | Business district - annual | 2025-07-16 | 2026-10-16 | Yes | 2026-06-10
LS-0004 | 4.5 | Crossroads | Business district - annual | 2025-10-25 | 2026-12-31 | Yes | 2026-01-26
LS-0005 | 4 | Crossroads | Business district - annual | 2025-07-11 | 2026-10-11 | Yes | 2026-01-13
LS-0006 | 6 | Crossroads | Business district - annual | 2025-11-30 | 2026-12-31 | Yes | 2026-01-20
LS-0007 | 6.4 | Crossroads | Business district - annual | 2025-09-16 | 2026-12-16 | Yes | 2026-03-02
LS-0008 | 6.9 | Crossroads | Business district - annual | 2025-08-21 | 2026-11-21 | Yes | 2026-02-02
LS-0009 | 5.9 | Crossroads | Business district - annual | 2025-09-21 | 2026-12-21 | Yes | 2026-02-25
LS-0010 | 5 | Crossroads | Business district - annual | 2025-09-03 | 2026-12-03 | Yes | 2026-05-26
LS-0011 | 2.3 | Crossroads | Business district - annual | 2025-08-04 | 2026-11-04 | Yes | 2026-06-16
LS-0012 | 3.3 | Crossroads | Business district - annual | 2025-11-13 | 2026-12-31 | Yes | 2026-02-27
LS-0013 | 7 | Crossroads | Business district - annual | 2025-08-22 | 2026-11-22 | Yes | 2026-01-20
LS-0014 | 7.5 | Crossroads | Business district - annual | 2025-06-01 | 2026-09-01 | Yes | 2026-03-07
LS-0015 | 4.2 | Crossroads | Business district - annual | 2025-11-12 | 2026-12-31 | Yes | 2026-07-09
LS-0016 | 5.8 | Crossroads | Business district - annual | 2025-06-02 | 2026-09-02 | Yes | 2026-02-17
LS-0017 | 6.7 | Crossroads | Business district - annual | 2025-05-17 | 2026-08-17 | Yes | 2026-01-31
LS-0018 | 5.3 | Crossroads | Business district - annual | 2025-07-24 | 2026-10-24 | Yes | 2026-04-08
LS-0019 | 4.8 | Crossroads | Business district - annual | 2025-06-20 | 2026-09-20 | Yes | 2026-01-20
LS-0020 | 2.2 | Crossroads | Business district - annual | 2025-06-18 | 2026-09-18 | Yes | 2026-07-28
LS-0021 | 5.6 | Crossroads | Business district - annual | 2025-03-24 | 2026-06-24 | Yes | 2026-05-21
LS-0022 | 4.9 | Crossroads | Business district - annual | 2025-09-02 | 2026-12-02 | Yes | 2026-03-28
LS-0023 | 1.2 | Crossroads | Unprotected steel - 3-year | 2025-04-03 | 2028-07-03 | No
LS-0024 | 1.1 | Crossroads | Unprotected steel - 3-year | 2023-03-26 | 2026-06-26 | Yes | 2026-04-15
LS-0025 | 0.6 | Crossroads | Unprotected steel - 3-year | 2024-08-24 | 2027-11-24 | No
LS-0026 | 0.8 | Crossroads | Unprotected steel - 3-year | 2025-09-24 | 2028-12-24 | No
LS-0027 | 1.1 | Crossroads | Unprotected steel - 3-year | 2023-12-06 | 2026-12-31 | Yes | 2026-06-20
LS-0028 | 7.5 | Crossroads | Outside business district - 5-year | 2024-10-07 | 2029-12-31 | No
LS-0029 | 10.8 | Crossroads | Outside business district - 5-year | 2025-10-29 | 2030-12-31 | No
LS-0030 | 12.9 | Crossroads | Outside business district - 5-year | 2021-08-24 | 2026-11-24 | Yes
LS-0031 | 9.6 | Crossroads | Outside business district - 5-year | 2022-01-10 | 2027-04-10 | No
LS-0032 | 7.6 | Crossroads | Outside business district - 5-year | 2023-10-13 | 2028-12-31 | No
LS-0033 | 9.4 | Crossroads | Outside business district - 5-year | 2024-10-12 | 2029-12-31 | No
LS-0034 | 10.6 | Crossroads | Outside business district - 5-year | 2025-03-20 | 2030-06-20 | No
LS-0035 | 8.4 | Crossroads | Outside business district - 5-year | 2021-04-24 | 2026-07-24 | Yes | 2026-07-15
LS-0036 | 9.3 | Crossroads | Outside business district - 5-year | 2022-05-30 | 2027-08-30 | No
LS-0037 | 13.5 | Crossroads | Outside business district - 5-year | 2023-06-28 | 2028-09-28 | No
LS-0038 | 9.7 | Crossroads | Outside business district - 5-year | 2024-05-06 | 2029-08-06 | No
LS-0039 | 13.2 | Crossroads | Outside business district - 5-year | 2025-05-02 | 2030-08-02 | No
LS-0040 | 12.8 | Crossroads | Outside business district - 5-year | 2021-10-01 | 2026-12-31 | Yes
LS-0041 | 10.2 | Crossroads | Outside business district - 5-year | 2022-03-27 | 2027-06-27 | No
LS-0042 | 9.5 | Crossroads | Outside business district - 5-year | 2023-02-06 | 2028-05-06 | No
LS-0043 | 8.7 | Crossroads | Outside business district - 5-year | 2024-08-06 | 2029-11-06 | No
LS-0044 | 10.6 | Crossroads | Outside business district - 5-year | 2025-11-30 | 2030-12-31 | No
LS-0045 | 12.5 | Crossroads | Outside business district - 5-year | 2021-04-08 | 2026-07-08 | Yes | 2026-06-27
LS-0046 | 7.7 | Crossroads | Outside business district - 5-year | 2022-11-19 | 2027-12-31 | No
LS-0047 | 10.5 | Crossroads | Outside business district - 5-year | 2023-08-20 | 2028-11-20 | No
LS-0048 | 12 | Crossroads | Outside business district - 5-year | 2024-11-15 | 2029-12-31 | No
LS-0049 | 10.7 | Crossroads | Outside business district - 5-year | 2025-05-16 | 2030-08-16 | No
LS-0050 | 13.1 | Crossroads | Outside business district - 5-year | 2021-01-21 | 2026-04-21 | Yes | 2026-02-24
LS-0051 | 13.1 | Crossroads | Outside business district - 5-year | 2022-05-13 | 2027-08-13 | No
LS-0052 | 12.7 | Crossroads | Outside business district - 5-year | 2023-01-13 | 2028-04-13 | No
LS-0053 | 7.5 | Crossroads | Outside business district - 5-year | 2024-03-09 | 2029-06-09 | No
LS-0054 | 12.8 | Crossroads | Outside business district - 5-year | 2025-05-18 | 2030-08-18 | No
LS-0055 | 8.2 | Crossroads | Outside business district - 5-year | 2021-09-27 | 2026-12-27 | Yes
LS-0056 | 11.5 | Crossroads | Outside business district - 5-year | 2022-08-24 | 2027-11-24 | No
LS-0057 | 12.4 | Crossroads | Outside business district - 5-year | 2023-01-25 | 2028-04-25 | No
LS-0058 | 11.2 | Crossroads | Outside business district - 5-year | 2024-01-30 | 2029-04-30 | No
LS-0059 | 10.2 | Crossroads | Outside business district - 5-year | 2025-10-01 | 2030-12-31 | No
LS-0060 | 12.7 | Crossroads | Outside business district - 5-year | 2021-10-20 | 2026-12-31 | Yes | 2026-07-17
LS-0061 | 11.3 | Crossroads | Outside business district - 5-year | 2022-08-05 | 2027-11-05 | No
LS-0062 | 10.9 | Crossroads | Outside business district - 5-year | 2023-01-25 | 2028-04-25 | No
LS-0063 | 13.4 | Crossroads | Outside business district - 5-year | 2024-10-02 | 2029-12-31 | No
LS-0064 | 10.5 | Crossroads | Outside business district - 5-year | 2025-05-23 | 2030-08-23 | No
LS-0065 | 10.5 | Crossroads | Outside business district - 5-year | 2021-07-11 | 2026-10-11 | Yes
LS-0066 | 9.6 | Crossroads | Outside business district - 5-year | 2022-04-05 | 2027-07-05 | No
LS-0067 | 9.2 | Crossroads | Outside business district - 5-year | 2023-03-16 | 2028-06-16 | No
LS-0068 | 13.2 | Crossroads | Outside business district - 5-year | 2024-06-11 | 2029-09-11 | No
LS-0069 | 7.7 | Crossroads | Outside business district - 5-year | 2025-01-17 | 2030-04-17 | No
LS-0070 | 9.9 | Crossroads | Outside business district - 5-year | 2021-11-02 | 2026-12-31 | Yes | 2026-07-04
LS-0071 | 8.9 | Crossroads | Outside business district - 5-year | 2022-03-27 | 2027-06-27 | No
LS-0072 | 8.6 | Crossroads | Outside business district - 5-year | 2023-06-05 | 2028-09-05 | No
LS-0073 | 10.3 | Crossroads | Outside business district - 5-year | 2024-11-15 | 2029-12-31 | No
LS-0074 | 10.4 | Crossroads | Outside business district - 5-year | 2025-07-23 | 2030-10-23 | No
LS-0075 | 8.2 | Crossroads | Outside business district - 5-year | 2021-01-11 | 2026-04-11 | Yes | 2026-02-22
LS-0076 | 9.7 | Crossroads | Outside business district - 5-year | 2022-03-02 | 2027-06-02 | No
LS-0077 | 8 | Crossroads | Outside business district - 5-year | 2023-09-18 | 2028-12-18 | No
LS-0078 | 13.2 | Crossroads | Outside business district - 5-year | 2024-03-30 | 2029-06-30 | No
LS-0079 | 9.2 | Crossroads | Outside business district - 5-year | 2025-09-10 | 2030-12-10 | No
LS-0080 | 9.6 | Crossroads | Outside business district - 5-year | 2021-05-21 | 2026-08-21 | Yes | 2026-06-28
LS-0081 | 9.6 | Crossroads | Outside business district - 5-year | 2022-11-18 | 2027-12-31 | No
LS-0082 | 12.9 | Crossroads | Outside business district - 5-year | 2023-10-09 | 2028-12-31 | No
LS-0083 | 10.8 | Crossroads | Outside business district - 5-year | 2024-06-07 | 2029-09-07 | No
LS-0084 | 8 | Crossroads | Outside business district - 5-year | 2025-01-12 | 2030-04-12 | No
LS-0085 | 9 | Crossroads | Outside business district - 5-year | 2021-03-03 | 2026-06-03 | Yes | 2026-04-08
LS-0086 | 12.1 | Crossroads | Outside business district - 5-year | 2022-02-07 | 2027-05-07 | No
LS-0087 | 9.7 | Crossroads | Outside business district - 5-year | 2023-03-18 | 2028-06-18 | No
LS-0088 | 8.9 | Crossroads | Outside business district - 5-year | 2024-08-01 | 2029-11-01 | No
LS-0089 | 8.7 | Crossroads | Outside business district - 5-year | 2025-09-10 | 2030-12-10 | No
LS-0090 | 7.5 | Crossroads | Outside business district - 5-year | 2021-10-01 | 2026-12-31 | Yes | 2026-05-23
LS-0091 | 10 | Crossroads | Outside business district - 5-year | 2022-05-04 | 2027-08-04 | No
LS-0092 | 11.4 | Crossroads | Outside business district - 5-year | 2023-05-28 | 2028-08-28 | No
LS-0093 | 13.5 | Crossroads | Outside business district - 5-year | 2024-09-19 | 2029-12-19 | No
LS-0094 | 11.7 | Crossroads | Outside business district - 5-year | 2025-09-24 | 2030-12-24 | No
LS-0095 | 11.6 | Crossroads | Outside business district - 5-year | 2021-01-27 | 2026-04-27 | Yes | 2026-04-11
LS-0096 | 12.1 | Crossroads | Outside business district - 5-year | 2022-04-19 | 2027-07-19 | No
LS-0097 | 10.8 | Crossroads | Outside business district - 5-year | 2023-11-23 | 2028-12-31 | No
LS-0098 | 7.6 | Crossroads | Outside business district - 5-year | 2024-12-04 | 2029-12-31 | No
LS-0099 | 8 | Crossroads | Outside business district - 5-year | 2025-11-05 | 2030-12-31 | No
LS-0100 | 8.4 | Crossroads | Outside business district - 5-year | 2021-03-27 | 2026-06-27 | Yes | 2026-05-06
LS-0101 | 13.1 | Crossroads | Outside business district - 5-year | 2022-04-12 | 2027-07-12 | No
LS-0102 | 13.2 | Crossroads | Outside business district - 5-year | 2023-08-29 | 2028-11-29 | No
LS-0103 | 11.1 | Crossroads | Outside business district - 5-year | 2024-10-17 | 2029-12-31 | No
LS-0104 | 12.8 | Crossroads | Outside business district - 5-year | 2025-05-07 | 2030-08-07 | No
LS-0105 | 11.6 | Crossroads | Outside business district - 5-year | 2021-04-24 | 2026-07-24 | Yes | 2026-06-27
LS-0106 | 11.9 | Crossroads | Outside business district - 5-year | 2022-06-20 | 2027-09-20 | No
LS-0107 | 8.9 | Crossroads | Outside business district - 5-year | 2023-01-23 | 2028-04-23 | No
LS-0108 | 7.9 | Crossroads | Outside business district - 5-year | 2024-03-18 | 2029-06-18 | No
LS-0109 | 8.1 | Crossroads | Outside business district - 5-year | 2025-04-14 | 2030-07-14 | No
LS-0110 | 10.9 | Crossroads | Outside business district - 5-year | 2021-07-09 | 2026-10-09 | Yes | 2026-01-20
LS-0111 | 12.2 | Crossroads | Outside business district - 5-year | 2022-10-26 | 2027-12-31 | No
LS-0112 | 7.9 | Crossroads | Outside business district - 5-year | 2023-05-07 | 2028-08-07 | No
LS-0113 | 12.8 | Crossroads | Outside business district - 5-year | 2024-06-12 | 2029-09-12 | No
LS-0114 | 12 | Crossroads | Outside business district - 5-year | 2025-02-15 | 2030-05-15 | No
LS-0115 | 8.2 | Crossroads | Outside business district - 5-year | 2021-10-30 | 2026-12-31 | Yes | 2026-07-16
LS-0116 | 10.9 | Crossroads | Outside business district - 5-year | 2022-06-01 | 2027-09-01 | No
LS-0117 | 11.7 | Crossroads | Outside business district - 5-year | 2023-03-26 | 2028-06-26 | No
LS-0118 | 9.4 | Crossroads | Outside business district - 5-year | 2024-08-10 | 2029-11-10 | No
LS-0119 | 7.5 | Crossroads | Outside business district - 5-year | 2025-10-06 | 2030-12-31 | No
LS-0120 | 8.5 | Crossroads | Outside business district - 5-year | 2021-06-10 | 2026-09-10 | Yes | 2026-08-01
LS-0121 | 11.8 | Crossroads | Outside business district - 5-year | 2022-02-17 | 2027-05-17 | No
LS-0122 | 8.2 | Crossroads | Outside business district - 5-year | 2023-11-19 | 2028-12-31 | No
LS-0123 | 13.1 | Crossroads | Outside business district - 5-year | 2024-11-30 | 2029-12-31 | No
LS-0124 | 12 | Crossroads | Outside business district - 5-year | 2025-04-23 | 2030-07-23 | No
LS-0125 | 9.1 | Crossroads | Outside business district - 5-year | 2021-12-05 | 2026-12-31 | Yes
LS-0126 | 9.2 | Crossroads | Outside business district - 5-year | 2022-04-19 | 2027-07-19 | No
LS-0127 | 12.3 | Crossroads | Outside business district - 5-year | 2023-01-19 | 2028-04-19 | No
LS-0128 | 9.9 | Crossroads | Outside business district - 5-year | 2024-03-02 | 2029-06-02 | No
LS-0129 | 9.4 | Crossroads | Outside business district - 5-year | 2025-03-10 | 2030-06-10 | No
LS-0130 | 9.4 | Crossroads | Outside business district - 5-year | 2021-03-27 | 2026-06-27 | Yes | 2026-05-18
LS-0131 | 10.7 | Crossroads | Outside business district - 5-year | 2022-04-20 | 2027-07-20 | No
LS-0132 | 8.3 | Crossroads | Outside business district - 5-year | 2023-11-13 | 2028-12-31 | No
LS-0133 | 12.9 | Crossroads | Outside business district - 5-year | 2024-04-21 | 2029-07-21 | No
LS-0134 | 11.1 | Crossroads | Outside business district - 5-year | 2025-01-23 | 2030-04-23 | No
LS-0135 | 10.7 | Crossroads | Outside business district - 5-year | 2021-09-29 | 2026-12-29 | Yes | 2026-03-07
LS-0136 | 12 | Crossroads | Outside business district - 5-year | 2022-06-12 | 2027-09-12 | No
LS-0137 | 7.9 | Crossroads | Outside business district - 5-year | 2023-03-26 | 2028-06-26 | No
LS-0138 | 9.9 | Crossroads | Outside business district - 5-year | 2024-12-01 | 2029-12-31 | No
LS-0139 | 11.3 | Crossroads | Outside business district - 5-year | 2025-07-04 | 2030-10-04 | No
LS-0140 | 8.9 | Crossroads | Outside business district - 5-year | 2021-06-13 | 2026-09-13 | Yes | 2026-08-28
LS-0141 | 12 | Crossroads | Outside business district - 5-year | 2022-03-27 | 2027-06-27 | No
LS-0142 | 11.6 | Crossroads | Outside business district - 5-year | 2023-08-22 | 2028-11-22 | No
LS-0143 | 7.6 | Crossroads | Outside business district - 5-year | 2024-10-24 | 2029-12-31 | No
LS-0144 | 10.9 | Crossroads | Outside business district - 5-year | 2025-05-17 | 2030-08-17 | No
LS-0145 | 10.5 | Crossroads | Outside business district - 5-year | 2021-02-14 | 2026-05-14 | Yes | 2026-04-11
LS-0146 | 10.7 | Crossroads | Outside business district - 5-year | 2022-09-02 | 2027-12-02 | No
LS-0147 | 12.8 | Crossroads | Outside business district - 5-year | 2023-01-16 | 2028-04-16 | No
LS-0148 | 13.1 | Crossroads | Outside business district - 5-year | 2024-06-03 | 2029-09-03 | No
LS-0149 | 7.6 | Crossroads | Outside business district - 5-year | 2025-04-20 | 2030-07-20 | No
LS-0150 | 11.7 | Crossroads | Outside business district - 5-year | 2021-11-08 | 2026-12-31 | Yes | 2026-06-27
LS-0151 | 12.2 | Crossroads | Outside business district - 5-year | 2022-02-17 | 2027-05-17 | No
LS-0152 | 11.6 | Crossroads | Outside business district - 5-year | 2023-03-19 | 2028-06-19 | No
LS-0153 | 13 | Crossroads | Outside business district - 5-year | 2024-11-20 | 2029-12-31 | No
LS-0154 | 8.2 | Crossroads | Outside business district - 5-year | 2025-11-09 | 2030-12-31 | No
LS-0155 | 8.5 | Crossroads | Outside business district - 5-year | 2021-02-03 | 2026-05-03 | Yes | 2026-04-09
LS-0156 | 12 | Crossroads | Outside business district - 5-year | 2022-08-26 | 2027-11-26 | No
LS-0157 | 7.9 | Crossroads | Outside business district - 5-year | 2023-03-09 | 2028-06-09 | No
LS-0158 | 8.4 | Crossroads | Outside business district - 5-year | 2024-05-29 | 2029-08-29 | No
LS-0159 | 9.2 | Crossroads | Outside business district - 5-year | 2025-07-04 | 2030-10-04 | No
LS-0160 | 11.7 | Crossroads | Outside business district - 5-year | 2021-02-03 | 2026-05-03 | Yes | 2026-04-21
LS-0161 | 11.1 | Crossroads | Outside business district - 5-year | 2022-07-25 | 2027-10-25 | No
LS-0162 | 11.2 | Crossroads | Outside business district - 5-year | 2023-05-13 | 2028-08-13 | No
LS-0163 | 11.4 | Crossroads | Outside business district - 5-year | 2024-06-22 | 2029-09-22 | No
LS-0164 | 7.4 | Crossroads | Outside business district - 5-year | 2025-07-14 | 2030-10-14 | No
LS-0165 | 10.5 | Crossroads | Outside business district - 5-year | 2021-06-29 | 2026-09-29 | Yes | 2026-07-25
LS-0166 | 11.1 | Crossroads | Outside business district - 5-year | 2022-06-05 | 2027-09-05 | No
LS-0167 | 7.7 | Crossroads | Outside business district - 5-year | 2023-01-31 | 2028-04-30 | No
LS-0168 | 11.2 | Crossroads | Outside business district - 5-year | 2024-02-16 | 2029-05-16 | No
LS-0169 | 12 | Crossroads | Outside business district - 5-year | 2025-09-27 | 2030-12-27 | No
LS-0170 | 9.4 | Crossroads | Outside business district - 5-year | 2021-07-14 | 2026-10-14 | Yes
LS-0171 | 11.9 | Crossroads | Outside business district - 5-year | 2022-01-17 | 2027-04-17 | No
LS-0172 | 12.3 | Crossroads | Outside business district - 5-year | 2023-11-07 | 2028-12-31 | No
LS-0173 | 8.5 | Crossroads | Outside business district - 5-year | 2024-03-03 | 2029-06-03 | No
LS-0174 | 13.2 | Crossroads | Outside business district - 5-year | 2025-05-21 | 2030-08-21 | No
LS-0175 | 12.4 | Crossroads | Outside business district - 5-year | 2021-07-05 | 2026-10-05 | Yes
LS-0176 | 9.1 | Crossroads | Outside business district - 5-year | 2022-10-12 | 2027-12-31 | No
LS-0177 | 11 | Crossroads | Outside business district - 5-year | 2023-10-01 | 2028-12-31 | No
LS-0178 | 4.1 | Bayou | Business district - annual | 2025-05-26 | 2026-08-26 | Yes | 2026-05-23
LS-0179 | 4.5 | Bayou | Business district - annual | 2025-06-28 | 2026-09-28 | Yes | 2026-05-26
LS-0180 | 3 | Bayou | Business district - annual | 2025-05-27 | 2026-08-27 | Yes | 2026-02-01
LS-0181 | 4.8 | Bayou | Business district - annual | 2025-02-19 | 2026-05-19 | Yes | 2026-04-05
LS-0182 | 4.2 | Bayou | Business district - annual | 2025-05-29 | 2026-08-29 | Yes | 2026-06-05
LS-0183 | 7.2 | Bayou | Business district - annual | 2025-04-07 | 2026-07-07 | Yes | 2026-06-11
LS-0184 | 7.1 | Bayou | Business district - annual | 2025-08-18 | 2026-11-18 | Yes | 2026-05-26
LS-0185 | 3.6 | Bayou | Business district - annual | 2025-12-02 | 2026-12-31 | Yes | 2026-01-23
LS-0186 | 2.8 | Bayou | Business district - annual | 2025-11-09 | 2026-12-31 | Yes | 2026-06-03
LS-0187 | 7.9 | Bayou | Business district - annual | 2025-04-06 | 2026-07-06 | Yes | 2026-02-12
LS-0188 | 5.5 | Bayou | Business district - annual | 2025-11-07 | 2026-12-31 | Yes | 2026-03-06
LS-0189 | 5.3 | Bayou | Business district - annual | 2025-06-16 | 2026-09-16 | Yes | 2026-01-28
LS-0190 | 4.4 | Bayou | Business district - annual | 2025-10-07 | 2026-12-31 | Yes | 2026-05-10
LS-0191 | 3.5 | Bayou | Business district - annual | 2025-10-17 | 2026-12-31 | Yes | 2026-04-01
LS-0192 | 3.7 | Bayou | Business district - annual | 2025-08-19 | 2026-11-19 | Yes | 2026-05-04
LS-0193 | 5.9 | Bayou | Business district - annual | 2025-04-09 | 2026-07-09 | Yes | 2026-07-04
LS-0194 | 5.2 | Bayou | Business district - annual | 2025-08-23 | 2026-11-23 | Yes | 2026-02-09
LS-0195 | 3.8 | Bayou | Business district - annual | 2025-04-28 | 2026-07-28 | Yes | 2026-04-05
LS-0196 | 3.2 | Bayou | Business district - annual | 2025-08-08 | 2026-11-08 | Yes | 2026-06-22
LS-0197 | 7.9 | Bayou | Business district - annual | 2025-02-23 | 2026-05-23 | Yes | 2026-02-27
LS-0198 | 6.5 | Bayou | Business district - annual | 2025-07-20 | 2026-10-20 | Yes | 2026-06-05
LS-0199 | 6.6 | Bayou | Business district - annual | 2025-09-09 | 2026-12-09 | Yes | 2026-02-16
LS-0200 | 4.2 | Bayou | Business district - annual | 2025-05-11 | 2026-08-11 | Yes | 2026-03-27
LS-0201 | 3.2 | Bayou | Business district - annual | 2025-10-19 | 2026-12-31 | Yes | 2026-06-19
LS-0202 | 3.6 | Bayou | Business district - annual | 2025-03-25 | 2026-06-25 | Yes | 2026-04-07
LS-0203 | 7.2 | Bayou | Business district - annual | 2025-12-01 | 2026-12-31 | Yes | 2026-01-17
LS-0204 | 1.9 | Bayou | Business district - annual | 2025-07-14 | 2026-10-14 | Yes | 2026-06-17
LS-0205 | 4.6 | Bayou | Business district - annual | 2025-07-26 | 2026-10-26 | Yes | 2026-06-28
LS-0206 | 6.6 | Bayou | Business district - annual | 2025-08-26 | 2026-11-26 | Yes | 2026-06-25
LS-0207 | 6.8 | Bayou | Business district - annual | 2025-05-08 | 2026-08-08 | Yes | 2026-03-20
LS-0208 | 13.2 | Bayou | Unprotected steel - 3-year | 2024-04-16 | 2027-07-16 | No
LS-0209 | 7.9 | Bayou | Unprotected steel - 3-year | 2025-03-09 | 2028-06-09 | No
LS-0210 | 13.8 | Bayou | Unprotected steel - 3-year | 2023-12-05 | 2026-12-31 | Yes | 2026-07-13
LS-0211 | 8.8 | Bayou | Unprotected steel - 3-year | 2024-10-12 | 2027-12-31 | No
LS-0212 | 7.9 | Bayou | Unprotected steel - 3-year | 2025-07-06 | 2028-10-06 | No
LS-0213 | 8.9 | Bayou | Unprotected steel - 3-year | 2023-07-06 | 2026-10-06 | Yes | 2026-07-24
LS-0214 | 10.7 | Bayou | Unprotected steel - 3-year | 2024-08-11 | 2027-11-11 | No
LS-0215 | 10.4 | Bayou | Unprotected steel - 3-year | 2025-04-05 | 2028-07-05 | No
LS-0216 | 7.6 | Bayou | Outside business district - 5-year | 2022-11-20 | 2027-12-31 | No
LS-0217 | 12.6 | Bayou | Outside business district - 5-year | 2023-02-16 | 2028-05-16 | No
LS-0218 | 8.9 | Bayou | Outside business district - 5-year | 2024-07-04 | 2029-10-04 | No
LS-0219 | 12 | Bayou | Outside business district - 5-year | 2025-12-05 | 2030-12-31 | No
LS-0220 | 11.1 | Bayou | Outside business district - 5-year | 2021-08-12 | 2026-11-12 | Yes | 2026-04-14
LS-0221 | 11 | Bayou | Outside business district - 5-year | 2022-11-03 | 2027-12-31 | No
LS-0222 | 10.4 | Bayou | Outside business district - 5-year | 2023-10-22 | 2028-12-31 | No
LS-0223 | 11.7 | Bayou | Outside business district - 5-year | 2024-04-16 | 2029-07-16 | No
LS-0224 | 12.7 | Bayou | Outside business district - 5-year | 2025-05-07 | 2030-08-07 | No
LS-0225 | 10.4 | Bayou | Outside business district - 5-year | 2021-10-14 | 2026-12-31 | Yes | 2026-04-22
LS-0226 | 13.6 | Bayou | Outside business district - 5-year | 2022-07-27 | 2027-10-27 | No
LS-0227 | 8.2 | Bayou | Outside business district - 5-year | 2023-03-31 | 2028-06-30 | No
LS-0228 | 7.7 | Bayou | Outside business district - 5-year | 2024-05-13 | 2029-08-13 | No
LS-0229 | 12.9 | Bayou | Outside business district - 5-year | 2025-10-27 | 2030-12-31 | No
LS-0230 | 7.8 | Bayou | Outside business district - 5-year | 2021-09-10 | 2026-12-10 | Yes | 2026-02-15
LS-0231 | 10.2 | Bayou | Outside business district - 5-year | 2022-01-15 | 2027-04-15 | No
LS-0232 | 8.6 | Bayou | Outside business district - 5-year | 2023-10-20 | 2028-12-31 | No
LS-0233 | 7.8 | Bayou | Outside business district - 5-year | 2024-07-05 | 2029-10-05 | No
LS-0234 | 8.3 | Bayou | Outside business district - 5-year | 2025-03-08 | 2030-06-08 | No
LS-0235 | 9 | Bayou | Outside business district - 5-year | 2021-01-24 | 2026-04-24 | Yes | 2026-03-09
LS-0236 | 11.3 | Bayou | Outside business district - 5-year | 2022-03-25 | 2027-06-25 | No
LS-0237 | 11.3 | Bayou | Outside business district - 5-year | 2023-06-06 | 2028-09-06 | No
LS-0238 | 7.9 | Bayou | Outside business district - 5-year | 2024-07-14 | 2029-10-14 | No
LS-0239 | 13.5 | Bayou | Outside business district - 5-year | 2025-08-05 | 2030-11-05 | No
LS-0240 | 12.3 | Bayou | Outside business district - 5-year | 2021-03-21 | 2026-06-21 | Yes | 2026-05-12
LS-0241 | 11.8 | Bayou | Outside business district - 5-year | 2022-11-27 | 2027-12-31 | No
LS-0242 | 11.1 | Bayou | Outside business district - 5-year | 2023-08-31 | 2028-11-30 | No
LS-0243 | 8.6 | Bayou | Outside business district - 5-year | 2024-07-28 | 2029-10-28 | No
LS-0244 | 13.2 | Bayou | Outside business district - 5-year | 2025-04-14 | 2030-07-14 | No
LS-0245 | 10.4 | Bayou | Outside business district - 5-year | 2021-11-12 | 2026-12-31 | Yes
LS-0246 | 11.3 | Bayou | Outside business district - 5-year | 2022-02-26 | 2027-05-26 | No
LS-0247 | 7.5 | Bayou | Outside business district - 5-year | 2023-06-16 | 2028-09-16 | No
LS-0248 | 12 | Bayou | Outside business district - 5-year | 2024-02-26 | 2029-05-26 | No
LS-0249 | 11.3 | Bayou | Outside business district - 5-year | 2025-09-30 | 2030-12-30 | No
LS-0250 | 9.4 | Bayou | Outside business district - 5-year | 2021-02-12 | 2026-05-12 | Yes | 2026-05-04
LS-0251 | 13.6 | Bayou | Outside business district - 5-year | 2022-02-15 | 2027-05-15 | No
LS-0252 | 7.8 | Bayou | Outside business district - 5-year | 2023-09-04 | 2028-12-04 | No
LS-0253 | 13.5 | Bayou | Outside business district - 5-year | 2024-10-02 | 2029-12-31 | No
LS-0254 | 13.6 | Bayou | Outside business district - 5-year | 2025-09-23 | 2030-12-23 | No
LS-0255 | 12.1 | Bayou | Outside business district - 5-year | 2021-10-29 | 2026-12-31 | Yes
LS-0256 | 10.2 | Bayou | Outside business district - 5-year | 2022-05-12 | 2027-08-12 | No
LS-0257 | 9.5 | Bayou | Outside business district - 5-year | 2023-05-24 | 2028-08-24 | No
LS-0258 | 11.9 | Bayou | Outside business district - 5-year | 2024-03-31 | 2029-06-30 | No
LS-0259 | 12.5 | Bayou | Outside business district - 5-year | 2025-07-09 | 2030-10-09 | No
LS-0260 | 12.6 | Bayou | Outside business district - 5-year | 2021-04-19 | 2026-07-19 | Yes | 2026-06-26
LS-0261 | 11.5 | Bayou | Outside business district - 5-year | 2022-02-05 | 2027-05-05 | No
LS-0262 | 8.8 | Bayou | Outside business district - 5-year | 2023-06-25 | 2028-09-25 | No
LS-0263 | 9.8 | Bayou | Outside business district - 5-year | 2024-03-23 | 2029-06-23 | No
LS-0264 | 13 | Bayou | Outside business district - 5-year | 2025-05-05 | 2030-08-05 | No
LS-0265 | 10.7 | Bayou | Outside business district - 5-year | 2021-05-05 | 2026-08-05 | Yes | 2026-06-24
LS-0266 | 8.5 | Bayou | Outside business district - 5-year | 2022-05-11 | 2027-08-11 | No
LS-0267 | 13.5 | Bayou | Outside business district - 5-year | 2023-10-11 | 2028-12-31 | No
LS-0268 | 10.2 | Bayou | Outside business district - 5-year | 2024-08-31 | 2029-11-30 | No
LS-0269 | 13.6 | Bayou | Outside business district - 5-year | 2025-06-16 | 2030-09-16 | No
LS-0270 | 8.9 | Bayou | Outside business district - 5-year | 2021-11-10 | 2026-12-31 | Yes | 2026-02-02
LS-0271 | 8.5 | Bayou | Outside business district - 5-year | 2022-01-23 | 2027-04-23 | No
LS-0272 | 7.4 | Bayou | Outside business district - 5-year | 2023-06-25 | 2028-09-25 | No
LS-0273 | 7.6 | Bayou | Outside business district - 5-year | 2024-09-13 | 2029-12-13 | No
LS-0274 | 9.8 | Bayou | Outside business district - 5-year | 2025-04-21 | 2030-07-21 | No
LS-0275 | 9.7 | Bayou | Outside business district - 5-year | 2021-09-05 | 2026-12-05 | Yes | 2026-08-20
LS-0276 | 8.6 | Bayou | Outside business district - 5-year | 2022-05-08 | 2027-08-08 | No
LS-0277 | 8.9 | Bayou | Outside business district - 5-year | 2023-06-07 | 2028-09-07 | No
LS-0278 | 11.1 | Bayou | Outside business district - 5-year | 2024-09-01 | 2029-12-01 | No
LS-0279 | 9.6 | Bayou | Outside business district - 5-year | 2025-10-22 | 2030-12-31 | No
LS-0280 | 9.3 | Bayou | Outside business district - 5-year | 2021-03-03 | 2026-06-03 | Yes | 2026-04-09
LS-0281 | 10.6 | Bayou | Outside business district - 5-year | 2022-08-16 | 2027-11-16 | No
LS-0282 | 10.5 | Bayou | Outside business district - 5-year | 2023-10-05 | 2028-12-31 | No
LS-0283 | 8.1 | Bayou | Outside business district - 5-year | 2024-08-10 | 2029-11-10 | No
LS-0284 | 11.2 | Bayou | Outside business district - 5-year | 2025-07-11 | 2030-10-11 | No
LS-0285 | 8.1 | Bayou | Outside business district - 5-year | 2021-07-14 | 2026-10-14 | Yes
LS-0286 | 11.4 | Bayou | Outside business district - 5-year | 2022-11-02 | 2027-12-31 | No
LS-0287 | 9.8 | Bayou | Outside business district - 5-year | 2023-11-10 | 2028-12-31 | No
LS-0288 | 10.2 | Bayou | Outside business district - 5-year | 2024-02-29 | 2029-05-29 | No
LS-0289 | 7.7 | Bayou | Outside business district - 5-year | 2025-07-04 | 2030-10-04 | No
LS-0290 | 10 | Bayou | Outside business district - 5-year | 2021-03-23 | 2026-06-23 | Yes | 2026-05-04
LS-0291 | 7.8 | Bayou | Outside business district - 5-year | 2022-07-03 | 2027-10-03 | No
LS-0292 | 10.5 | Bayou | Outside business district - 5-year | 2023-04-15 | 2028-07-15 | No
LS-0293 | 7.8 | Bayou | Outside business district - 5-year | 2024-04-24 | 2029-07-24 | No
LS-0294 | 13.1 | Bayou | Outside business district - 5-year | 2025-06-25 | 2030-09-25 | No
LS-0295 | 12.5 | Bayou | Outside business district - 5-year | 2021-05-15 | 2026-08-15 | Yes | 2026-07-06
LS-0296 | 13.2 | Bayou | Outside business district - 5-year | 2022-10-16 | 2027-12-31 | No
LS-0297 | 8 | Bayou | Outside business district - 5-year | 2023-02-26 | 2028-05-26 | No
LS-0298 | 11.3 | Bayou | Outside business district - 5-year | 2024-06-06 | 2029-09-06 | No
LS-0299 | 11.4 | Bayou | Outside business district - 5-year | 2025-08-30 | 2030-11-30 | No
LS-0300 | 13 | Bayou | Outside business district - 5-year | 2021-03-20 | 2026-06-20 | Yes | 2026-05-09
LS-0301 | 9.4 | Bayou | Outside business district - 5-year | 2022-03-20 | 2027-06-20 | No
LS-0302 | 12.4 | Bayou | Outside business district - 5-year | 2023-11-20 | 2028-12-31 | No
LS-0303 | 8.7 | Bayou | Outside business district - 5-year | 2024-05-09 | 2029-08-09 | No
LS-0304 | 11.6 | Bayou | Outside business district - 5-year | 2025-06-19 | 2030-09-19 | No
LS-0305 | 12.1 | Bayou | Outside business district - 5-year | 2021-06-06 | 2026-09-06 | Yes | 2026-07-17
LS-0306 | 9.2 | Bayou | Outside business district - 5-year | 2022-06-20 | 2027-09-20 | No
LS-0307 | 12.2 | Bayou | Outside business district - 5-year | 2023-06-11 | 2028-09-11 | No
LS-0308 | 11.2 | Bayou | Outside business district - 5-year | 2024-01-16 | 2029-04-16 | No
LS-0309 | 12 | Bayou | Outside business district - 5-year | 2025-01-20 | 2030-04-20 | No
LS-0310 | 13.5 | Bayou | Outside business district - 5-year | 2021-05-12 | 2026-08-12 | Yes | 2026-06-20
LS-0311 | 11.7 | Bayou | Outside business district - 5-year | 2022-04-28 | 2027-07-28 | No
LS-0312 | 12.2 | Bayou | Outside business district - 5-year | 2023-01-12 | 2028-04-12 | No
LS-0313 | 8.9 | Bayou | Outside business district - 5-year | 2024-05-24 | 2029-08-24 | No
LS-0314 | 7.7 | Bayou | Outside business district - 5-year | 2025-02-22 | 2030-05-22 | No
LS-0315 | 9.9 | Bayou | Outside business district - 5-year | 2021-11-17 | 2026-12-31 | Yes | 2026-06-06
LS-0316 | 12.2 | Bayou | Outside business district - 5-year | 2022-02-12 | 2027-05-12 | No
LS-0317 | 8.2 | Bayou | Outside business district - 5-year | 2023-04-22 | 2028-07-22 | No
LS-0318 | 9.9 | Bayou | Outside business district - 5-year | 2024-06-06 | 2029-09-06 | No
LS-0319 | 7.6 | Bayou | Outside business district - 5-year | 2025-04-20 | 2030-07-20 | No
LS-0320 | 9 | Bayou | Outside business district - 5-year | 2021-08-16 | 2026-11-16 | Yes | 2026-02-02
LS-0321 | 7.5 | Bayou | Outside business district - 5-year | 2022-09-08 | 2027-12-08 | No
LS-0322 | 8.9 | Bayou | Outside business district - 5-year | 2023-10-16 | 2028-12-31 | No
LS-0323 | 8 | Bayou | Outside business district - 5-year | 2024-07-08 | 2029-10-08 | No
LS-0324 | 9 | Bayou | Outside business district - 5-year | 2025-09-29 | 2030-12-29 | No
LS-0325 | 9.9 | Bayou | Outside business district - 5-year | 2021-04-12 | 2026-07-12 | Yes | 2026-06-12
LS-0326 | 11.8 | Bayou | Outside business district - 5-year | 2022-07-20 | 2027-10-20 | No
LS-0327 | 12.7 | Bayou | Outside business district - 5-year | 2023-08-02 | 2028-11-02 | No
LS-0328 | 7.4 | Bayou | Outside business district - 5-year | 2024-09-14 | 2029-12-14 | No
LS-0329 | 11.7 | Bayou | Outside business district - 5-year | 2025-03-17 | 2030-06-17 | No
LS-0330 | 12.2 | Bayou | Outside business district - 5-year | 2021-05-05 | 2026-08-05 | Yes | 2026-06-26
LS-0331 | 10.8 | Bayou | Outside business district - 5-year | 2022-09-28 | 2027-12-28 | No
LS-0332 | 11.5 | Bayou | Outside business district - 5-year | 2023-08-24 | 2028-11-24 | No
LS-0333 | 9.2 | Bayou | Outside business district - 5-year | 2024-08-30 | 2029-11-30 | No
LS-0334 | 9.7 | Bayou | Outside business district - 5-year | 2025-10-11 | 2030-12-31 | No
LS-0335 | 11.5 | Bayou | Outside business district - 5-year | 2021-07-26 | 2026-10-26 | Yes
LS-0336 | 13.1 | Bayou | Outside business district - 5-year | 2022-03-29 | 2027-06-29 | No
LS-0337 | 12 | Bayou | Outside business district - 5-year | 2023-01-20 | 2028-04-20 | No
LS-0338 | 10.9 | Bayou | Outside business district - 5-year | 2024-09-27 | 2029-12-27 | No
LS-0339 | 7.6 | Bayou | Outside business district - 5-year | 2025-05-25 | 2030-08-25 | No
LS-0340 | 8.6 | Bayou | Outside business district - 5-year | 2021-01-29 | 2026-04-29 | Yes | 2026-04-07
LS-0341 | 11.7 | Bayou | Outside business district - 5-year | 2022-05-18 | 2027-08-18 | No
LS-0342 | 11.1 | Bayou | Outside business district - 5-year | 2023-08-23 | 2028-11-23 | No
LS-0343 | 9.9 | Bayou | Outside business district - 5-year | 2024-02-10 | 2029-05-10 | No
LS-0344 | 11.9 | Bayou | Outside business district - 5-year | 2025-01-16 | 2030-04-16 | No
LS-0345 | 11.7 | Bayou | Outside business district - 5-year | 2021-06-21 | 2026-09-21 | Yes | 2026-07-22
LS-0346 | 9 | Bayou | Outside business district - 5-year | 2022-05-23 | 2027-08-23 | No
LS-0347 | 10.2 | Bayou | Outside business district - 5-year | 2023-05-09 | 2028-08-09 | No
LS-0348 | 8.8 | Bayou | Outside business district - 5-year | 2024-09-28 | 2029-12-28 | No
LS-0349 | 10.9 | Bayou | Outside business district - 5-year | 2025-10-07 | 2030-12-31 | No
LS-0350 | 9.3 | Bayou | Outside business district - 5-year | 2021-02-18 | 2026-05-18 | Yes | 2026-05-05
LS-0351 | 9.8 | Bayou | Outside business district - 5-year | 2022-05-21 | 2027-08-21 | No
LS-0352 | 8.3 | Bayou | Outside business district - 5-year | 2023-08-04 | 2028-11-04 | No
LS-0353 | 13.1 | Bayou | Outside business district - 5-year | 2024-03-26 | 2029-06-26 | No
LS-0354 | 7.7 | Bayou | Outside business district - 5-year | 2025-08-02 | 2030-11-02 | No
LS-0355 | 8.1 | Bayou | Outside business district - 5-year | 2021-02-20 | 2026-05-20 | Yes | 2026-04-17
LS-0356 | 8.5 | Bayou | Outside business district - 5-year | 2022-03-27 | 2027-06-27 | No
LS-0357 | 7.8 | Bayou | Outside business district - 5-year | 2023-08-27 | 2028-11-27 | No
LS-0358 | 10.4 | Bayou | Outside business district - 5-year | 2024-02-07 | 2029-05-07 | No
LS-0359 | 11.8 | Bayou | Outside business district - 5-year | 2025-09-19 | 2030-12-19 | No
LS-0360 | 12.3 | Bayou | Outside business district - 5-year | 2021-09-02 | 2026-12-02 | Yes
LS-0361 | 7.4 | Bayou | Outside business district - 5-year | 2022-01-25 | 2027-04-25 | No
LS-0362 | 11.8 | Bayou | Outside business district - 5-year | 2023-09-05 | 2028-12-05 | No
LS-0363 | 7.5 | Bayou | Outside business district - 5-year | 2024-07-20 | 2029-10-20 | No
LS-0364 | 8.5 | Bayou | Outside business district - 5-year | 2025-06-16 | 2030-09-16 | No
LS-0365 | 13 | Bayou | Outside business district - 5-year | 2021-03-23 | 2026-06-23 | Yes | 2026-05-27
LS-0366 | 9.9 | Bayou | Outside business district - 5-year | 2022-06-18 | 2027-09-18 | No
LS-0367 | 9.1 | Bayou | Outside business district - 5-year | 2023-07-25 | 2028-10-25 | No
LS-0368 | 12.8 | Bayou | Outside business district - 5-year | 2024-10-07 | 2029-12-31 | No
LS-0369 | 10.9 | Bayou | Outside business district - 5-year | 2025-02-03 | 2030-05-03 | No
LS-0370 | 10.2 | Bayou | Outside business district - 5-year | 2021-04-08 | 2026-07-08 | Yes | 2026-06-04
LS-0371 | 13.1 | Bayou | Outside business district - 5-year | 2022-09-17 | 2027-12-17 | No
LS-0372 | 9.6 | Bayou | Outside business district - 5-year | 2023-10-05 | 2028-12-31 | No
LS-0373 | 11.1 | Bayou | Outside business district - 5-year | 2024-09-17 | 2029-12-17 | No
LS-0374 | 12.5 | Bayou | Outside business district - 5-year | 2025-09-18 | 2030-12-18 | No
LS-0375 | 7.8 | Bayou | Outside business district - 5-year | 2021-06-25 | 2026-09-25 | Yes | 2026-01-27
LS-0376 | 7.9 | Bayou | Outside business district - 5-year | 2022-07-02 | 2027-10-02 | No
LS-0377 | 9.4 | Bayou | Outside business district - 5-year | 2023-10-04 | 2028-12-31 | No
LS-0378 | 7.9 | Bayou | Outside business district - 5-year | 2024-07-13 | 2029-10-13 | No
LS-0379 | 12.9 | Bayou | Outside business district - 5-year | 2025-11-01 | 2030-12-31 | No
LS-0380 | 11.2 | Bayou | Outside business district - 5-year | 2021-01-19 | 2026-04-19 | Yes | 2026-03-20
LS-0381 | 13.4 | Bayou | Outside business district - 5-year | 2022-11-18 | 2027-12-31 | No
LS-0382 | 12.3 | Bayou | Outside business district - 5-year | 2023-01-28 | 2028-04-28 | No
LS-0383 | 8.9 | Bayou | Outside business district - 5-year | 2024-04-08 | 2029-07-08 | No
LS-0384 | 11.3 | Bayou | Outside business district - 5-year | 2025-01-11 | 2030-04-11 | No
LS-0385 | 8.9 | Bayou | Outside business district - 5-year | 2021-02-05 | 2026-05-05 | Yes | 2026-04-02
LS-0386 | 10.1 | Bayou | Outside business district - 5-year | 2022-06-11 | 2027-09-11 | No
LS-0387 | 13.2 | Bayou | Outside business district - 5-year | 2023-03-20 | 2028-06-20 | No
LS-0388 | 8.9 | Bayou | Outside business district - 5-year | 2024-09-21 | 2029-12-21 | No
LS-0389 | 11.7 | Bayou | Outside business district - 5-year | 2025-05-12 | 2030-08-12 | No
LS-0390 | 9.5 | Bayou | Outside business district - 5-year | 2021-01-23 | 2026-04-23 | Yes | 2026-03-24
LS-0391 | 13.4 | Bayou | Outside business district - 5-year | 2022-07-16 | 2027-10-16 | No
LS-0392 | 8.5 | Bayou | Outside business district - 5-year | 2023-02-20 | 2028-05-20 | No
LS-0393 | 10.7 | Bayou | Outside business district - 5-year | 2024-08-22 | 2029-11-22 | No
LS-0394 | 7.6 | Bayou | Outside business district - 5-year | 2025-07-21 | 2030-10-21 | No
LS-0395 | 9.9 | Bayou | Outside business district - 5-year | 2021-11-10 | 2026-12-31 | Yes
LS-0396 | 12.6 | Bayou | Outside business district - 5-year | 2022-02-13 | 2027-05-13 | No
LS-0397 | 9.7 | Bayou | Outside business district - 5-year | 2023-03-03 | 2028-06-03 | No
LS-0398 | 13.1 | Bayou | Outside business district - 5-year | 2024-10-17 | 2029-12-31 | No
LS-0399 | 7.4 | Bayou | Outside business district - 5-year | 2025-08-11 | 2030-11-11 | No
LS-0400 | 13.4 | Bayou | Outside business district - 5-year | 2021-11-08 | 2026-12-31 | Yes
LS-0401 | 13.2 | Bayou | Outside business district - 5-year | 2022-01-14 | 2027-04-14 | No
LS-0402 | 13.6 | Bayou | Outside business district - 5-year | 2023-10-19 | 2028-12-31 | No
LS-0403 | 2 | Prairie | Business district - annual | 2025-04-21 | 2026-07-21 | Yes | 2026-05-13
LS-0404 | 4.6 | Prairie | Business district - annual | 2025-10-19 | 2026-12-31 | Yes | 2026-04-01
LS-0405 | 4.9 | Prairie | Business district - annual | 2025-05-31 | 2026-08-31 | Yes | 2026-04-30
LS-0406 | 5.2 | Prairie | Business district - annual | 2025-10-27 | 2026-12-31 | Yes | 2026-02-20
LS-0407 | 3.9 | Prairie | Business district - annual | 2025-08-04 | 2026-11-04 | Yes | 2026-07-16
LS-0408 | 2.4 | Prairie | Business district - annual | 2025-10-08 | 2026-12-31 | Yes | 2026-07-25
LS-0409 | 7.8 | Prairie | Business district - annual | 2025-08-17 | 2026-11-17 | Yes | 2026-06-17
LS-0410 | 3.7 | Prairie | Business district - annual | 2025-06-14 | 2026-09-14 | Yes | 2026-02-24
LS-0411 | 5.6 | Prairie | Business district - annual | 2025-10-26 | 2026-12-31 | Yes | 2026-01-24
LS-0412 | 2.9 | Prairie | Business district - annual | 2025-06-09 | 2026-09-09 | Yes | 2026-07-05
LS-0413 | 7.4 | Prairie | Business district - annual | 2025-10-13 | 2026-12-31 | Yes | 2026-01-18
LS-0414 | 1.5 | Prairie | Business district - annual | 2025-05-11 | 2026-08-11 | Yes | 2026-03-02
LS-0415 | 6.4 | Prairie | Business district - annual | 2025-05-05 | 2026-08-05 | Yes | 2026-01-29
LS-0416 | 2.3 | Prairie | Business district - annual | 2025-07-01 | 2026-10-01 | Yes | 2026-02-05
LS-0417 | 4.6 | Prairie | Business district - annual | 2025-12-02 | 2026-12-31 | Yes | 2026-02-13
LS-0418 | 2.1 | Prairie | Business district - annual | 2025-09-21 | 2026-12-21 | Yes | 2026-05-07
LS-0419 | 4.2 | Prairie | Business district - annual | 2025-10-31 | 2026-12-31 | Yes | 2026-06-01
LS-0420 | 6.8 | Prairie | Business district - annual | 2025-04-20 | 2026-07-20 | Yes | 2026-06-08
LS-0421 | 9.7 | Prairie | Unprotected steel - 3-year | 2024-06-01 | 2027-09-01 | No
LS-0422 | 8.8 | Prairie | Unprotected steel - 3-year | 2025-09-15 | 2028-12-15 | No
LS-0423 | 7.8 | Prairie | Unprotected steel - 3-year | 2023-02-06 | 2026-05-06 | Yes | 2026-03-10
LS-0424 | 13.9 | Prairie | Unprotected steel - 3-year | 2024-03-06 | 2027-06-06 | No
LS-0425 | 7.8 | Prairie | Unprotected steel - 3-year | 2025-06-22 | 2028-09-22 | No
LS-0426 | 10.7 | Prairie | Outside business district - 5-year | 2022-09-01 | 2027-12-01 | No
LS-0427 | 7.7 | Prairie | Outside business district - 5-year | 2023-09-06 | 2028-12-06 | No
LS-0428 | 10.2 | Prairie | Outside business district - 5-year | 2024-04-22 | 2029-07-22 | No
LS-0429 | 10.3 | Prairie | Outside business district - 5-year | 2025-04-21 | 2030-07-21 | No
LS-0430 | 8.6 | Prairie | Outside business district - 5-year | 2021-07-27 | 2026-10-27 | Yes | 2026-03-09
LS-0431 | 9.5 | Prairie | Outside business district - 5-year | 2022-02-17 | 2027-05-17 | No
LS-0432 | 7.4 | Prairie | Outside business district - 5-year | 2023-09-09 | 2028-12-09 | No
LS-0433 | 12.5 | Prairie | Outside business district - 5-year | 2024-09-04 | 2029-12-04 | No
LS-0434 | 9 | Prairie | Outside business district - 5-year | 2025-01-21 | 2030-04-21 | No
LS-0435 | 12.8 | Prairie | Outside business district - 5-year | 2021-10-11 | 2026-12-31 | Yes
LS-0436 | 7.7 | Prairie | Outside business district - 5-year | 2022-11-08 | 2027-12-31 | No
LS-0437 | 10.8 | Prairie | Outside business district - 5-year | 2023-08-18 | 2028-11-18 | No
LS-0438 | 12.7 | Prairie | Outside business district - 5-year | 2024-08-18 | 2029-11-18 | No
LS-0439 | 9.5 | Prairie | Outside business district - 5-year | 2025-04-03 | 2030-07-03 | No
LS-0440 | 7.4 | Prairie | Outside business district - 5-year | 2021-10-27 | 2026-12-31 | Yes
LS-0441 | 11.1 | Prairie | Outside business district - 5-year | 2022-02-12 | 2027-05-12 | No
LS-0442 | 12.6 | Prairie | Outside business district - 5-year | 2023-03-25 | 2028-06-25 | No
LS-0443 | 9 | Prairie | Outside business district - 5-year | 2024-02-18 | 2029-05-18 | No
LS-0444 | 10.8 | Prairie | Outside business district - 5-year | 2025-11-19 | 2030-12-31 | No
LS-0445 | 7.6 | Prairie | Outside business district - 5-year | 2021-04-27 | 2026-07-27 | Yes | 2026-07-15
LS-0446 | 7.4 | Prairie | Outside business district - 5-year | 2022-11-05 | 2027-12-31 | No
LS-0447 | 11.5 | Prairie | Outside business district - 5-year | 2023-09-13 | 2028-12-13 | No
LS-0448 | 10.5 | Prairie | Outside business district - 5-year | 2024-10-28 | 2029-12-31 | No
LS-0449 | 9.6 | Prairie | Outside business district - 5-year | 2025-07-05 | 2030-10-05 | No
LS-0450 | 9.1 | Prairie | Outside business district - 5-year | 2021-06-06 | 2026-09-06 | Yes | 2026-08-24
LS-0451 | 12.9 | Prairie | Outside business district - 5-year | 2022-03-19 | 2027-06-19 | No
LS-0452 | 11 | Prairie | Outside business district - 5-year | 2023-08-06 | 2028-11-06 | No
LS-0453 | 10.9 | Prairie | Outside business district - 5-year | 2024-08-16 | 2029-11-16 | No
LS-0454 | 11.3 | Prairie | Outside business district - 5-year | 2025-05-16 | 2030-08-16 | No
LS-0455 | 13.4 | Prairie | Outside business district - 5-year | 2021-10-31 | 2026-12-31 | Yes
LS-0456 | 8.8 | Prairie | Outside business district - 5-year | 2022-02-20 | 2027-05-20 | No
LS-0457 | 8.2 | Prairie | Outside business district - 5-year | 2023-03-20 | 2028-06-20 | No
LS-0458 | 13 | Prairie | Outside business district - 5-year | 2024-02-18 | 2029-05-18 | No
LS-0459 | 10.2 | Prairie | Outside business district - 5-year | 2025-10-27 | 2030-12-31 | No
LS-0460 | 11.5 | Prairie | Outside business district - 5-year | 2021-10-13 | 2026-12-31 | Yes | 2026-05-18
LS-0461 | 10.3 | Prairie | Outside business district - 5-year | 2022-04-21 | 2027-07-21 | No
LS-0462 | 13.6 | Prairie | Outside business district - 5-year | 2023-03-18 | 2028-06-18 | No
LS-0463 | 12.7 | Prairie | Outside business district - 5-year | 2024-02-21 | 2029-05-21 | No
LS-0464 | 12.5 | Prairie | Outside business district - 5-year | 2025-09-20 | 2030-12-20 | No
LS-0465 | 9.5 | Prairie | Outside business district - 5-year | 2021-08-27 | 2026-11-27 | Yes
LS-0466 | 9 | Prairie | Outside business district - 5-year | 2022-05-09 | 2027-08-09 | No
LS-0467 | 11.7 | Prairie | Outside business district - 5-year | 2023-06-09 | 2028-09-09 | No
LS-0468 | 11.3 | Prairie | Outside business district - 5-year | 2024-10-18 | 2029-12-31 | No
LS-0469 | 12.3 | Prairie | Outside business district - 5-year | 2025-08-06 | 2030-11-06 | No
LS-0470 | 10.8 | Prairie | Outside business district - 5-year | 2021-04-03 | 2026-07-03 | Yes | 2026-06-20
LS-0471 | 9.6 | Prairie | Outside business district - 5-year | 2022-01-28 | 2027-04-28 | No
LS-0472 | 12.4 | Prairie | Outside business district - 5-year | 2023-09-22 | 2028-12-22 | No
LS-0473 | 13.2 | Prairie | Outside business district - 5-year | 2024-06-12 | 2029-09-12 | No
LS-0474 | 8.6 | Prairie | Outside business district - 5-year | 2025-02-27 | 2030-05-27 | No
LS-0475 | 12.8 | Prairie | Outside business district - 5-year | 2021-11-11 | 2026-12-31 | Yes | 2026-01-23
LS-0476 | 13.4 | Prairie | Outside business district - 5-year | 2022-10-28 | 2027-12-31 | No
LS-0477 | 8.3 | Prairie | Outside business district - 5-year | 2023-01-22 | 2028-04-22 | No
LS-0478 | 8.3 | Prairie | Outside business district - 5-year | 2024-05-16 | 2029-08-16 | No
LS-0479 | 11.7 | Prairie | Outside business district - 5-year | 2025-07-22 | 2030-10-22 | No
LS-0480 | 13 | Prairie | Outside business district - 5-year | 2021-11-18 | 2026-12-31 | Yes | 2026-08-03
LS-0481 | 13.6 | Prairie | Outside business district - 5-year | 2022-08-29 | 2027-11-29 | No
LS-0482 | 9.5 | Prairie | Outside business district - 5-year | 2023-04-10 | 2028-07-10 | No
LS-0483 | 10.6 | Prairie | Outside business district - 5-year | 2024-04-01 | 2029-07-01 | No
LS-0484 | 13.1 | Prairie | Outside business district - 5-year | 2025-07-27 | 2030-10-27 | No
LS-0485 | 12.5 | Prairie | Outside business district - 5-year | 2021-05-08 | 2026-08-08 | Yes | 2026-06-23
LS-0486 | 7.9 | Prairie | Outside business district - 5-year | 2022-06-06 | 2027-09-06 | No
LS-0487 | 9.4 | Prairie | Outside business district - 5-year | 2023-05-04 | 2028-08-04 | No
LS-0488 | 9.6 | Prairie | Outside business district - 5-year | 2024-08-10 | 2029-11-10 | No
LS-0489 | 7.5 | Prairie | Outside business district - 5-year | 2025-04-26 | 2030-07-26 | No
LS-0490 | 10.8 | Prairie | Outside business district - 5-year | 2021-06-05 | 2026-09-05 | Yes | 2026-07-23
LS-0491 | 9.7 | Prairie | Outside business district - 5-year | 2022-05-16 | 2027-08-16 | No
LS-0492 | 8.5 | Prairie | Outside business district - 5-year | 2023-03-16 | 2028-06-16 | No
LS-0493 | 8.6 | Prairie | Outside business district - 5-year | 2024-03-17 | 2029-06-17 | No
LS-0494 | 12.5 | Prairie | Outside business district - 5-year | 2025-09-29 | 2030-12-29 | No
LS-0495 | 8.2 | Prairie | Outside business district - 5-year | 2021-11-20 | 2026-12-31 | Yes
LS-0496 | 9.4 | Prairie | Outside business district - 5-year | 2022-06-18 | 2027-09-18 | No
LS-0497 | 12.7 | Prairie | Outside business district - 5-year | 2023-03-10 | 2028-06-10 | No
LS-0498 | 10 | Prairie | Outside business district - 5-year | 2024-06-23 | 2029-09-23 | No
LS-0499 | 9.4 | Prairie | Outside business district - 5-year | 2025-11-01 | 2030-12-31 | No
LS-0500 | 7.6 | Prairie | Outside business district - 5-year | 2021-07-18 | 2026-10-18 | Yes
LS-0501 | 12.1 | Prairie | Outside business district - 5-year | 2022-08-08 | 2027-11-08 | No
LS-0502 | 13.1 | Prairie | Outside business district - 5-year | 2023-06-21 | 2028-09-21 | No
LS-0503 | 12.8 | Prairie | Outside business district - 5-year | 2024-06-21 | 2029-09-21 | No
LS-0504 | 7.5 | Prairie | Outside business district - 5-year | 2025-05-19 | 2030-08-19 | No
LS-0505 | 10.9 | Prairie | Outside business district - 5-year | 2021-07-26 | 2026-10-26 | Yes
LS-0506 | 12.1 | Prairie | Outside business district - 5-year | 2022-08-31 | 2027-11-30 | No
LS-0507 | 11.7 | Prairie | Outside business district - 5-year | 2023-06-20 | 2028-09-20 | No
LS-0508 | 11.2 | Prairie | Outside business district - 5-year | 2024-11-08 | 2029-12-31 | No
LS-0509 | 13.1 | Prairie | Outside business district - 5-year | 2025-06-19 | 2030-09-19 | No
LS-0510 | 11.2 | Prairie | Outside business district - 5-year | 2021-05-13 | 2026-08-13 | Yes | 2026-07-23
LS-0511 | 7.6 | Prairie | Outside business district - 5-year | 2022-10-31 | 2027-12-31 | No
LS-0512 | 8.9 | Prairie | Outside business district - 5-year | 2023-07-24 | 2028-10-24 | No
LS-0513 | 9.2 | Prairie | Outside business district - 5-year | 2024-09-10 | 2029-12-10 | No
LS-0514 | 8.7 | Prairie | Outside business district - 5-year | 2025-10-14 | 2030-12-31 | No
LS-0515 | 11.5 | Prairie | Outside business district - 5-year | 2021-11-17 | 2026-12-31 | Yes
LS-0516 | 13.6 | Prairie | Outside business district - 5-year | 2022-07-31 | 2027-10-31 | No
LS-0517 | 7.5 | Prairie | Outside business district - 5-year | 2023-06-11 | 2028-09-11 | No
LS-0518 | 9.1 | Prairie | Outside business district - 5-year | 2024-02-22 | 2029-05-22 | No
LS-0519 | 8.6 | Prairie | Outside business district - 5-year | 2025-08-17 | 2030-11-17 | No