## Read me
Project milestone snapshot
Mesa Lantern Energy LLC
Effective date | 2026-09-26
Purpose | A dated milestone view for the three modeled projects.
Coverage | See each dataset dictionary and summary. Missing numeric values are excluded, not zero.
Summary interpretation | Descriptive statistics of selected records only. Totals of percentages and adjustment values are not operating KPIs.
Introduction | A dated milestone view for the three modeled projects. This draft is prepared for capital reviewers as part of Mesa Lantern Energy's initial information handoff. It describes the modeled operation at the stated date and should be read with the period and coverage of its supporting records.
Purpose and immediate use | Project stage distinguishes proposal, approval, in-progress work, and completion. Compare planned and actual dates without filling a blank actual date from a target. Requested or approved budgets should not be mistaken for paid costs.
Project authorization | Projects and Development separates proposals from authorized work. The meter verification campaign is approved and in progress; the Sage Creek pad access improvement remains a proposal; the compressor overhaul is approved but has not started. Budget, schedule, owner, and approval date belong on milestones. A proposal may be evaluated, but its requested budget or target date is not evidence of expenditure or completion.
Record question for review | Place the Sage Creek proposed milestone beside the approved compressor overhaul milestone. A target date appears in both, but only one has approval. The actual date remains empty until the supported event occurs.
Review action and handoff | Use this snapshot with the issued status memorandum; if stages change, request a new dated version rather than altering the old one.

## Summary
Dataset | Measure | Unit | Total | Mean | Records | Period start | Period end
Project Milestones | budget_usd | USD | 107876511.86 | 2397255.8191 | 45 | 2026-08-31 | 2026-08-31
Project Milestones | percent_complete | percent | 2540.74 | 56.4609 | 45 | 2026-08-31 | 2026-08-31

## Dictionary
Dataset | Field | Definition | Unit | Type | Reference
Project Milestones | milestone_id | Unique milestone |  | id
Project Milestones | project_id | Project |  | entity_ref | project
Project Milestones | planned_date | Plan date |  | date
Project Milestones | actual_date | Actual date if complete |  | date
Project Milestones | stage | Authorization stage |  | category
Project Milestones | budget_usd | Approved or requested budget | USD | number
Project Milestones | percent_complete | Verified progress estimate | percent | number

## Data 1
milestone_id | project_id | planned_date | actual_date | stage | budget_usd | percent_complete
project_milestones-000001 | Meter verification campaign | 2026-03-25 |  | in_progress | 1750653.53 | 51.23
project_milestones-000002 | Compressor overhaul | 2026-04-22 |  | in_progress | 1383234.99 | 57.21
project_milestones-000003 | Meter verification campaign | 2026-05-29 |  | in_progress | 3617160.98 | 19.78
project_milestones-000004 | Sage Creek pad access improvement | 2026-02-26 | 2026-05-03 | complete | 3429041.71 | 100
project_milestones-000005 | Sage Creek pad access improvement | 2026-08-17 |  | in_progress | 4322407.49 | 93.97
project_milestones-000006 | Compressor overhaul | 2026-08-26 | 2026-03-20 | complete | 607919.42 | 100
project_milestones-000007 | Compressor overhaul | 2026-06-01 |  | approved | 2065216.88 | 0.83
project_milestones-000008 | Meter verification campaign | 2026-08-31 |  | approved | 3078424.58 | 27.05
project_milestones-000009 | Meter verification campaign | 2026-02-08 |  | approved | 2338028.81 | 77.23
project_milestones-000010 | Compressor overhaul | 2026-08-22 |  | in_progress | 1122486.08 | 81.5
project_milestones-000011 | Compressor overhaul | 2026-05-27 |  | approved | 214132.12 | 20.1
project_milestones-000012 | Meter verification campaign | 2026-08-18 | 2026-07-11 | complete | 4695777.41 | 100
project_milestones-000013 | Compressor overhaul | 2026-01-02 |  | approved | 666660.97 | 35.03
project_milestones-000014 | Compressor overhaul | 2026-04-17 | 2026-01-07 | complete | 1922792.48 | 100
project_milestones-000015 | Meter verification campaign | 2026-01-12 |  | proposed | 3893162.87 | 0
project_milestones-000016 | Sage Creek pad access improvement | 2026-01-11 |  | proposed | 1172995.03 | 0
project_milestones-000017 | Meter verification campaign | 2026-05-01 |  | proposed | 3696774.99 | 0
project_milestones-000018 | Meter verification campaign | 2026-07-07 |  | in_progress | 3790114.06 | 85.3
project_milestones-000019 | Sage Creek pad access improvement | 2026-07-16 |  | in_progress | 3065527.01 | 63.22
project_milestones-000020 | Compressor overhaul | 2026-05-10 |  | in_progress | 2332607.9 | 81.3
project_milestones-000021 | Sage Creek pad access improvement | 2026-01-09 |  | approved | 2478107.02 | 32.62
project_milestones-000022 | Compressor overhaul | 2026-04-19 |  | approved | 3300677.58 | 78.41
project_milestones-000023 | Sage Creek pad access improvement | 2026-05-16 | 2026-07-22 | complete | 1798451.9 | 100
project_milestones-000024 | Compressor overhaul | 2026-04-11 |  | approved | 3715120.58 | 51.04
project_milestones-000025 | Compressor overhaul | 2026-05-03 |  | approved | 4643081.89 | 55.73
project_milestones-000026 | Sage Creek pad access improvement | 2026-07-27 |  | approved | 4106264.19 | 68.19
project_milestones-000027 | Compressor overhaul | 2026-07-24 |  | proposed | 3567927.77 | 0
project_milestones-000028 | Sage Creek pad access improvement | 2026-06-28 |  | proposed | 1380854.64 | 0
project_milestones-000029 | Meter verification campaign | 2026-07-30 |  | approved | 1181372.78 | 97.3
project_milestones-000030 | Meter verification campaign | 2026-01-26 |  | proposed | 2198506.82 | 0
project_milestones-000031 | Sage Creek pad access improvement | 2026-04-26 |  | approved | 1609868.29 | 27.36
project_milestones-000032 | Meter verification campaign | 2026-05-07 |  | proposed | 3556727.03 | 0
project_milestones-000033 | Sage Creek pad access improvement | 2026-03-03 |  | approved | 420733.5 | 51.16
project_milestones-000034 | Sage Creek pad access improvement | 2026-01-22 |  | in_progress | 1290260.69 | 94.15
project_milestones-000035 | Sage Creek pad access improvement | 2026-05-23 |  | approved | 1828230.46 | 89.67
project_milestones-000036 | Sage Creek pad access improvement | 2026-07-12 | 2026-06-26 | complete | 3841162.52 | 100
project_milestones-000037 | Sage Creek pad access improvement | 2026-01-04 | 2026-03-27 | complete | 1519571.42 | 100
project_milestones-000038 | Sage Creek pad access improvement | 2026-06-27 | 2026-05-16 | complete | 1758420.19 | 100
project_milestones-000039 | Meter verification campaign | 2026-07-07 | 2026-01-09 | complete | 2336008.34 | 100
project_milestones-000040 | Meter verification campaign | 2026-04-15 | 2026-03-17 | complete | 1717649.95 | 100
project_milestones-000041 | Meter verification campaign | 2026-02-25 |  | in_progress | 1410689.37 | 1.36
project_milestones-000042 | Sage Creek pad access improvement | 2026-02-03 |  | proposed | 1627302.61 | 0
project_milestones-000043 | Compressor overhaul | 2026-04-02 |  | proposed | 1213889.01 | 0
project_milestones-000044 | Sage Creek pad access improvement | 2026-03-17 | 2026-06-28 | complete | 2277732.78 | 100
project_milestones-000045 | Meter verification campaign | 2026-03-03 | 2026-08-31 | complete | 3932781.22 | 100